## Sheet1
Project Name | IR no. | Description | Discipline | Ttade | BUILDING NAME OR Area Name | FLOOR No. | Submitted Date | Received Date | Status
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0001 | First course of blockwork between axes (7-12) & (F-L) at Ground floor ( 300.10 ) for area (Z3) s Per Attached Sketch. | ARCH | Blockwork First course | Z3 | GF | 43097 | 43111 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0002 | First course of blockwork between axes (3-7) & (K-L) at Ground floor ( 300.10 ) for area (Z4) s Per Attached Sketch. | ARCH | Blockwork First course | Z4 | GF | 43103 | 43111 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0003 | First course of blockwork between axes (12-18) & (K-L) at Ground floor ( 300.10 ) for area (Z2) s Per Attached Sketch. | ARCH | Blockwork First course | Z2 | GF | 43103 | 43111 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0004 | First course of blockwork between axes (1-7) & (A-F) at Ground floor ( 300.10 ) for area (Z5) s Per Attached Sketch. | ARCH | Blockwork First course | Z5 | GF | 43103 | 43111 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0005 | First course of blockwork between axes (1-7) & (K-L) at FIRST floor ( 304.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 1st | 43116 | 43134 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0006 | First course of blockwork between axes (5-7) & (A-F) at FIRST floor ( 304.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 1st | 43116 | 43134 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0007 | First course of blockwork between axes (14-18) & (H-L) at FIRST floor ( 304.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 1st | 43132 | 43145 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0008 | First course of blockwork between axes (A-E)/18 at FIRST floor ( 304.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 1st | 43132 | 43145 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0009 | First course of blockwork between axes(1-6)&(G-L) at FIRST floor ( 304.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 1st | 43132 | 43145 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0010 | First course of blockwork between axes(1-6)&(A-E) at FIRST floor ( 304.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 1st | 43132 | 43145 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0011 | First course of blockwork between axes(B-E)/18 at Ground floor ( 300.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | GF | 43132 | 43145 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0012 | First course of blockwork between axes(G-L)/18 at Ground floor ( 300.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | GF | 43132 | 43145 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0013 | First course of blockwork between axes(1-3)&(k-l) at Ground floor ( 300.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | GF | 43132 | 43145 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0014 | First course of blockwork between axes(1-6)&(A-E) at second floor ( 308.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 2nd | 43139 | 43169 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0015 | First course of blockwork between axes(1-6)&(E-l) at SECOND floor ( 308.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 2nd | 43139 | 43169 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0016 | First course of blockwork between axes(10-13)&(E-L) at first floor ( 304.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 1st | 43139 | 43169 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0017 | First course of blockwork between axes(10-13)&(E-L) at Second floor ( 304.20 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 2nd | 43145 | 43173 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0018 | First course of blockwork between axes(10-13)&(E-L) at first floor ( 304.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 1st | 43145 | 43173 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0019 | First course of blockwork between axes(7-9)&(E-L) at first floor ( 304.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 1st | 43145 | 43169 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0020 | First course of blockwork between axes(14-17)&(A-B) at ground floor ( 300.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | GF | 43145 | 43169 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0021 | First course of blockwork between axes(1-5)&(F-L) at Third floor ( 312.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 3rd | 43149 | 43172 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0022 | First course of blockwork between axes(14-16)&(A-B) at ground floor ( 300.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | GF | 43149 | 43169 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0023 | First course of blockwork between axes(12-14)&(L-K) at first floor ( 304.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 1st | 43149 | 43173 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0024 | First course of blockwork between axes(17-18)&(F-H) at first floor ( 304.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 1st | 43149 | 43173 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0025 | First course of blockwork between axes(12-18)&(L-K) at SECOND floor ( 308.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 2nd | 43150 | 43169 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0026 | First course of blockwork between axes(13-18)&(A-B) at SECOND floor ( 308.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 2nd | 43150 | 43169 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0027 | First course of blockwork between axes(13-18)&(L-F) at THIRD floor ( 312.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 3rd | 43152 | 43172 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0028 | First course of blockwork between axes(9-7)&(L-E) at THIRD floor ( 312.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 3rd | 43152 | 43172 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0029 | First course of blockwork between axes(1-2)&(A-F) at THIRD floor ( 312.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 3rd | 43152 | 43169 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0030 | First course of blockwork between axes(5-6)&(A-F) at THIRD floor ( 312.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 3rd | 43152 | 43169 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0031 | First course of blockwork between axes(1-2)&(A-E) at THIRD floor ( 312.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 3rd | 43158 | 43169 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0032 | First course of blockwork between axes(5-6)&(A-E) at THIRD floor ( 312.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 3rd | 43158 | 43172 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0033 | First course of blockwork between axes(1-6)&(A-B) at THIRD floor ( 312.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 3rd | 43158 | 43169 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0034 | First course of blockwork between axes(1-6)&(L-K) at FOURTH floor ( 316.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 4th | 43158 | 43169 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0035 | First course of blockwork between axes(1-2)&(L-E) at FOURTH floor ( 316.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 4th | 43158 | 43169 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0036 | First course of blockwork between axes(1-6)&(L-K) at FIFTH floor ( 320.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 5th | 43158 | 43169 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0037 | First course of blockwork between axes(1-2)&(L-E) at FIFTH floor ( 320.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 5th | 43158 | 43169 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0038 | First course of blockwork between axes(10-12)&(L-E) at SECOND floor ( 308.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 2nd | 43158 | 43169 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0039 | First course of blockwork between axes(12-18)&(L-E) at THIRD floor ( 312.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 3rd | 43158 | 43172 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0040 | First course of blockwork between axes(12-18)&(A-E) at THIRD floor ( 312.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 3rd | 43158 | 43169 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0041 | First course of blockwork between axes(12-6)&(L-E) at THIRD floor ( 312.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 3rd | 43162 | 43178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0042 | First course of blockwork between axes(6-12)&(L-E) at FOURTH floor ( 316.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 4th | 43162 | 43178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0043 | First course of blockwork between axes(12-18)&(L-K) at FOURTH floor ( 316.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 4th | 43162 | 43178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0044 | First course of blockwork between axes(18-17)&(A-E) at THIRD floor ( 312.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 3rd | 43162 | 43186 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0045 | First course of blockwork between axes(1-7)&(A-F) at FOURTH floor ( 316.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 5th | 43162 | 43178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0046 | First course of blockwork between axes(18-17)&(L-F) at FOURTH floor ( 316.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 4th | 43169 | 43178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0047 | First course of blockwork between axes(18-13)&(A-F) at FOURTH floor ( 316.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 4th | 43169 | 43186 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0048 | First course of blockwork between axes(12-7)&(E-L) at FIFTH floor ( 320.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 5th | 43169 | 43178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0049 | First course of blockwork between axes(10-12)&(E-L) at SIXTH floor ( 324.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 6th | 43169 | 43186 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0050 | First course of blockwork between axes(13-9)&(J-L) at FIFTH floor ( 320.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 5th | 43172 | 43178 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0051 | First course of blockwork between axes (J-L)/(10) at SIXTH floor ( 324.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 6th | 43172 | 43183 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0052 | First course of blockwork between axes(1-6)&(A-F) at FIFTH floor ( 320.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 5th | 43172 | 43186 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0053 | First course of blockwork between axes(12-18)&(K-L) at FIFTH floor ( 320.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 5th | 43172 | 43178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0054 | First course of blockwork between axes(7-12)&(E-L) at SIXTH floor ( 324.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 6th | 43176 | 43183 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0055 | First course of blockwork between axes(7-9)&(E-L) at SEVENTH floor ( 328.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 7th | 43176 | 43183 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0056 | First course of blockwork between axes(17-18)&(F-L) at FIFTH floor ( 320.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 5th | 43176 | 43183 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0057 | Surface Prepration and Release For Painting For First Basement (B1) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting Surface Prepration | Z2 | B1 | 43176 | 43183 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0058 | First course of blockwork between axes(13-18)&(A-B) at FIFTH floor ( 320.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 5th | 43180 | 43186 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0059 | First course of blockwork between axes(10-12)&(K-L) at SEVENTH floor ( 328.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 7th | 43180 | 43192 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0060 | First course of blockwork between axes (J-H)/(9) at THIRD floor ( 312.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 3rd | 43180 | 43183 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0061 | First course of blockwork between axes (J-H)/(9) at FOURTH floor ( 316.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 4th | 43180 | 43183 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0062 | First course of blockwork between axes (J-H)/(9) at FIFTH floor ( 320.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 5th | 43180 | 43183 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0063 | First course of blockwork between axes (J-H)/(9) at SIXTH floor ( 324.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 6th | 43180 | 43183 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0064 | First course of blockwork between axes(12-15)&(A-E) at First floor ( 304.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 1st | 43183 | 43192 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0065 | First course of blockwork between axes(17-18)&(F-L) at SIXTH floor ( 324.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 6th | 43184 | 43191 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0066 | First course of blockwork between axes (H-J)/10 at THIRD floor ( 312.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 3rd | 43184 | 43192 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0067 | First course of blockwork between axes (H-J)/10 at FOURTH floor ( 316.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 4th | 43184 | 43192 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0068 | First course of blockwork between axes (H-J)/10 at FIFTH floor ( 320.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 5th | 43184 | 43192 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0069 | First course of blockwork between axes (H-J)/10 at SIXTH floor ( 324.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 6th | 43184 | 43191 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0070 | Full Height façade only of blockwork between axes (1-5)&(L-E) for area (Z4) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | ML | 43185 | 43205 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0071 | Full Height façade only of blockwork between axes (1-2)&(5-6)&(A-B) for area (Z5) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | ML | 43185 | 43205 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0072 | First course of blockwork between axes (8-1)&(F-L) at Seventh floor ( 328.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 7th | 43186 | 43192 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0073 | First course of blockwork between axes (15-16)&(K-L) at Second floor ( 308.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 2nd | 43187 | 43192 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0074 | First course of blockwork between axes (13-14)&(A-D) at Fifth floor ( 320.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 5th | 43187 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0075 | First course of blockwork between axes (10-12)&(E-H) at Seventh floor ( 328.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 7th | 43187 | 43192 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0076 | First course of blockwork between axes (G-H)/(10) at THIRD floor ( 312.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 3rd | 43187 | 43192 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0077 | First course of blockwork between axes (G-H)/(10) at FOURTH floor ( 316.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 4th | 43187 | 43192 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0078 | First course of blockwork between axes (G-H)/(10) at FIFTH floor ( 320.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 5th | 43187 | 43192 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0079 | First course of blockwork between axes (G-H)/(10) at SIXTH floor ( 324.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 6th | 43187 | 43192 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0080 | First course of blockwork between axes (5-7)&(E-G) at GROUND floor ( 300.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | GF | 43187 | 43192 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0081 | First course of blockwork between axes (5-7)&(E-G) at FIRST floor ( 304.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 1st | 43187 | 43192 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0082 | First course of blockwork between axes (13-17)&(K-L) at Seventh floor ( 328.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 7th | 43190 | 43192 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0083 | First course of blockwork between axes (10-12)&(E-L) at Seventh floor ( 328.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 7th | 43191 | 43202 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0084 | First course of blockwork between axes (14-15)&(A-B) at Ground floor ( 300.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | GF | 43193 | 43209 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0085 | First course of blockwork between axes (1-2)&(E-G) at Ground floor ( 300.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | GF | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0086 | First course of blockwork between axes (1-2)&(B-D) at Ground floor ( 300.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | GF | 43193 | 43209 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0087 | First course of blockwork between axes (12-18)&(A-F) at First floor ( 304.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 1st | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0088 | First course of blockwork between axes (1-2)&(E-G) at First floor ( 304.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 1st | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0089 | First course of blockwork between axes (1-2)&(C-D) at First floor ( 304.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 1st | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0090 | First course of blockwork between axes (1-2)&(E-G) at First floor ( 304.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 1st | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0091 | First course of blockwork between axes (13-14)&(A-D) at Second floor ( 308.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 2nd | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0092 | First course of blockwork between axes (17-18)&(A-F) at Second floor ( 308.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 2nd | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0093 | First course of blockwork between axes (17-18)&(G-K) at Second floor ( 308.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 2nd | 43193 | 43209 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0094 | First course of blockwork between axes (1-2)&(F-H) at Second floor ( 308.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 2nd | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0095 | First course of blockwork between axes (17-18)&(D-F) at Third floor ( 312.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 3rd | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0096 | First course of blockwork between axes (5-6)&(K-L) at Third floor ( 312.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 3rd | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0097 | First course of blockwork between axes (1-2)&(E-G) at Third floor ( 312.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 3rd | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0098 | First course of blockwork between axes (1-2)&(E-F) at Third floor ( 312.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 3rd | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0099 | First course of blockwork between axes (13-14)&(C-F) at Fourth floor ( 316.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 4th | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0100 | First course of blockwork between axes (5-6)&(K-L) at Fourth floor ( 316.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 4th | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0101 | First course of blockwork between axes (17-18)&(A-F) at Fifth floor ( 320.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 5th | 43193 | 43209 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0102 | First course of blockwork between axes (13-14)&(A-F) at Fifth floor ( 320.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 5th | 43193 | 43209 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0103 | First course of blockwork between axes (9-6)&(E-L) at Fifth floor ( 320.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 5th | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0104 | First course of blockwork between axes (1-2)&(L-F) at Fifth floor ( 320.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 5th | 43193 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0105 | First course of blockwork between axes (14-18)&(L-F) at Sixth floor ( 324.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 6th | 43193 | 43202 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0106 | First course of blockwork between axes (6-13)&(E-L) at Sixth floor ( 324.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 6th | 43193 | 43202 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0107 | First course of blockwork between axes (1-6)&(L-F) at Sixth floor ( 324.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 6th | 43193 | 43209 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0108 | First course of blockwork between axes (12-18)&(K-L) at SEVENTH floor (328.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 7th | 43193 | 43202 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0109 | First course of blockwork between axes (6-13)&(E-L) at SEVENTH floor (328.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 7th | 43193 | 43202 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0110 | First course of blockwork between axes (17-18)&(G-L) at SEVENTH floor(328.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 7th | 43193 | 43202 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0111 | First course of blockwork between axes (10-12)&(E-L) at eighth floor(333.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 8th | 43193 | 43202 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0112 | First course of blockwork between axes (11-12)&(E-G) at Second floor(308.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 2nd | 43194 | 43209 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0113 | First course of blockwork between axes (11-12)&(E-G) at Third floor(312.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 3rd | 43194 | 43209 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0114 | First course of blockwork between axes (13-14)&(D-F) at Second floor(308.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 2nd | 43194 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0115 | First course of blockwork between axes (13-14)&(D-G) at Third floor(312.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 3rd | 43194 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0116 | First course of blockwork between axes (12-14)&(E -G) at First floor(304.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 1st | 43195 | 43202 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0117 | First course of blockwork between axes (1-3)&(A-F) at First Basement floor(295.60 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | B1 | 43198 | 43205 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0118 | First course of blockwork between axes (1-3)&(E-L) at First Basement floor(295.60 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | B1 | 43198 | 43205 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0119 | Surface Prepration and Release For Painting For Ceiling at First Basement (295.60) at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting Surface Prepration | Z1 | B1 | 43198 | 43209 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0120 | Surface Prepration and Release For Painting For Ceiling at First Basement (295.60) at Zone(3) axes (F-L) &(13-6) as Per Attached Sketch. | ARCH | Painting Surface Prepration | Z3 | B1 | 43198 | 43209 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0121 | First course of blockwork between axes (17-18)&(E-G) at Second floor(308.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 2nd | 43201 | 43209 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0122 | First course of blockwork between axes (17-18)&(E-G) at Third floor(312.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 3rd | 43201 | 43209 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0123 | First course of blockwork between axes (12-18)&(F-G) at Seventh floor(328.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 7th | 43204 | 43262 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0124 | First course of blockwork between axes (H-J)/10 at Fourth floor(316.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 4th | 43204 | 43206 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0125 | First course of blockwork between axes (H-J)/10 at FIFTH floor(320.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 5th | 43204 | 43206 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0126 | First course of blockwork between axes (H-J)/10 at THIRD floor(312.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 3rd | 43204 | 43206 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0127 | First course of blockwork between axes (7-8)&(E-H) at NINTH floor(338.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 9th | 43204 | 43262 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0128 | First course of blockwork between axes (11-12)&(E-G) at SECOND floor(308.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 2nd | 43204 | 43206 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0129 | First course of blockwork between axes (11-12)&(E-G) at THIRD floor(312.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 3rd | 43204 | 43206 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0130 | First course of blockwork between axes (11-12)&(E-G) at FOURTH floor(316.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 4th | 43204 | 43206 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0131 | First course of blockwork between axes (11-12)&(E-G) at FIFTH floor(320.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 5th | 43204 | 43206 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0132 | First course of blockwork between axes (11-12)&(E-G) at SIXTH floor(324.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 6th | 43204 | 43262 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0133 | First course of blockwork between axes (2-5)&(K-L) at SEVENTH floor(328.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 7th | 43206 | 43219 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0134 | First course of blockwork between axes (7-8)&(E-G) at SIXTH floor(324.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 6th | 43206 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0135 | First course of blockwork between axes (11-12)&(E-G) at FIFTH floor(320.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 5th | 43206 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0136 | First course of blockwork between axes (11-12)&(E-G) at FOURTH floor(316.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 4th | 43206 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0137 | First course of blockwork between axes (13-14)&(C-E) at FOURTH floor(316.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 4th | 43208 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0138 | First course of blockwork between axes (12-14)&(A-C) at GROUND floor(300.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | GF | 43208 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0139 | First course of blockwork between axes (11-12)&(K-L) at SECOND floor(308.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 2nd | 43208 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0140 | First course of blockwork between axes (11-12)&(K-L) at THIRD floor(312.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 3rd | 43208 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0141 | First course of blockwork between axes (11-12)&(K-L) at FOURTH floor(316.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 4th | 43208 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0142 | First course of blockwork between axes (14-18)&(K-L) at ground floor(300.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | GF | 43209 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0143 | First course of blockwork between axes (17-18)&(A-B) at ground floor(300.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | GF | 43209 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0144 | First course of blockwork between axes (6-9)&(E-L) at eighth floor(333.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 8th | 43211 | 43219 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0145 | First course of blockwork between axes (1-2)&(E-G) at GROUND floor(300.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | GF | 43211 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0146 | First course of blockwork between axes (1-2)&(E-G) at FIRST floor(304.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 1st | 43211 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0147 | First course of blockwork between axes (1-2)&(E-G) at SECOND floor(308.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 2nd | 43211 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0148 | First course of blockwork between axes (1-2)&(E-G) at THIRD floor(312.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 3rd | 43211 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0149 | First course of blockwork between axes (1-2)&(E-G) at FOURTH floor(316.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 4th | 43211 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0150 | First course of blockwork between axes (1-2)&(F-G) at FIFTH floor(320.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 5th | 43211 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0151 | First course of blockwork between axes (1-2)&(F-G) at SIXTH floor(324.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 6th | 43211 | 43219 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0152 | First course of blockwork between axes (2-4)&(F-H) at First basement floor(296.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 1st | 43212 | 43223 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0153 | First course of blockwork between axes (1-2)&(F-H) at Ground floor(300.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | GF | 43212 | 43225 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0154 | First course of blockwork between axes (17-18)&(E-G) at Fifth floor(320.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 5th | 43213 | 43225 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0155 | First course of blockwork between axes (7-10)&(k-l) at ninth floor(338.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 9th | 43213 | 43225 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0156 | First course of blockwork between axes (12-14)&(E-K) at First Basement floor(295.60 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | B1 | 43215 | 43230 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0157 | First course of blockwork between axes (13-16)&(A-F) at First Basement floor(295.60 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | B1 | 43215 | 43230 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0158 | First course of blockwork between axes (7-9)&(E-L) at ninth floor(338.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 9th | 43215 | 43228 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0159 | First course of blockwork between axes (7-8)&(k-L) at nineth floor(338.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 9th | 43219 | 43225 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0160 | First course of blockwork between axes (7-8)&(k-L) at EIGHTH floor(333.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 8th | 43219 | 43223 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0161 | First course of blockwork between axes (7-8)&(k-L) at SEVENTH floor(328.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 7th | 43219 | 43223 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0162 | First course of blockwork between axes (7-8)&(k-L) at FIFTH floor(320.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 5th | 43219 | 43225 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0163 | First course of blockwork between axes (1-2)&(G-L) at SEVENTH floor(328.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 7th | 43222 | 43225 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0164 | First course of blockwork between axes (7-8)&(E-H) at EIGHTH floor(333.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 8th | 43222 | 43225 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0165 | First course of blockwork between axes (7-12)&(E-H) at NINETH floor(338.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 9th | 43222 | 43228 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0166 | Full Height façade only of blockwork between axes (1-2)&(F-L) for area (Z4) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | ML | 43223 | 43235 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0167 | First course of blockwork between axes (17-18)&(E-F) at GROUND floor(300.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | GF | 43227 | 43232 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0168 | First course of blockwork between axes (15-16)&(K-L) at First floor(304.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 1st | 43227 | 43232 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0169 | First course of blockwork between axes (1-6)&(A-F) at SECOND BASEMENT floor(291.80 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | B2 | 43227 | 43228 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0170 | First course of blockwork between axes (2-7)&(H-L) at First floor(304.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 1st | 43229 | 43235 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0171 | Full Height of blockwork between axes (1-7)&(E-L) AT FIRST BASEMENT Floor (295.60) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | B1 | 43229 | 43235 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0172 | Full Height of blockwork between axes (1-6)&(A-F) AT FIRST BASEMENT Floor (295.60) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | B1 | 43229 | 43235 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0173 | First course of blockwork between axes (15-16)&(G-H) at First floor(304.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 1st | 43229 | 43235 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0174 | First course of blockwork between axes (3-5)&(B-D) at First floor(304.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 1st | 43229 | 43235 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0175 | First course of blockwork between axes (12-14)&(H-J) at First floor(304.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 1st | 43230 | 43235 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0176 | First course of blockwork between axes (14-17)&(J-L) at First floor(304.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 1st | 43234 | 43241 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0177 | First course of blockwork between axes (15-16)&(C-D) at First floor(304.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 1st | 43234 | 43241 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0178 | First course of blockwork between axes (2-5)&(F-G) at SEVENTH floor(328.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 7th | 43236 | 43240 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0179 | First course of blockwork between axes (3-7)&(G-J) at Second floor(308.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 2nd | 43236 | 43241 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0180 | First course of blockwork between axes (3-5)&(G-J) at Third floor(312.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 3rd | 43236 | 43241 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0181 | First course of blockwork between axes (3-4)&(B-D) at Third floor(312.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 3rd | 43236 | 43241 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0182 | First course of blockwork between axes (12-14)&(F-J) at SECOND BASEMENT floor(291.80 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | B2 | 43236 | 43241 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0183 | First course of blockwork between axes (3-4)&(D-E) AT FIRST BASEMENT Floor (295.60) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | B1 | 43236 | 43241 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0184 | First course of blockwork between axes (15-17)&(F-H) AT FIRST Floor (304.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 1st | 43236 | 43241 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0185 | Full Height of blockwork between axes (11-18)&(A-E) AT FIRST BASEMENT Floor (295.60) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | B1 | 43237 | 43241 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0186 | Full Height of blockwork between axes (12-18)&(F-L) AT FIRST BASEMENT Floor (295.60) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | B1 | 43237 | 43241 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0187 | First course of blockwork between axes (12-13)&(k-L) at FIFTH floor(320.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 5th | 43240 | 43256 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0188 | First course of blockwork between axes (12-13)&(k-L) at SIXTH floor(324.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 6th | 43240 | 43256 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0189 | First course of blockwork between axes (12-13)&(k-L) at Seventh floor(328.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 3rd | 43240 | 43253 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0190 | First course of blockwork between axes (12-13)&(k-L) at EIGHTH floor(333.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 8th | 43240 | 43253 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0191 | First course of blockwork between axes (12-14)&(G-J) at Second floor(308.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 2nd | 43240 | 43253 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0192 | First course of blockwork between axes (15-18)&(B-F) at FIRST floor(304.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 1st | 43240 | 43256 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0193 | First course of blockwork between axes (14-16)&(F-J) at second floor(308.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 2nd | 43241 | 43253 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0194 | First course of blockwork between axes (3-4)&(B-D) at FOURTH floor (316.10) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 4th | 43241 | 43253 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0195 | First course of blockwork between axes (15-18)&(B-E) at SECOND BASEMENT floor (291.80) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | B2 | 43241 | 43253 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0196 | First course of blockwork between axes (15-18)&(G-L) at SECOND BASEMENT floor (291.80) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | B2 | 43241 | 43253 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0197 | First course of blockwork between axes (4-7)&(H-J) at FOURTH floor (316.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 4th | 43241 | 43253 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0198 | First course of blockwork between axes (14-16)&(A-D) at Second floor (308.10) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 2nd | 43246 | 43253 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0199 | First course of blockwork between axes (12-14)&(G-J) at Second floor (308.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 2nd | 43246 | 43253 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0200 | First course of blockwork between axes (8-9)&(G-J) at Second floor (308.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 2nd | 43246 | 43255 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0201 | First course of blockwork between axes (14-16)&(B-D) at Third floor (312.10) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 3rd | 43246 | 43251 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0202 | First course of blockwork between axes (8-9)&(G-J) at First floor (304.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 1st | 43246 | 43255 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0203 | First course of blockwork between axes (14-17)&(F-H) at Fourth floor (316.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 4th | 43246 | 43256 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0204 | First course of blockwork between axes (2-5)&(F-H) at Fourth floor (316.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 4th | 43246 | 43251 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0205 | First course of blockwork between axes (5-7)&(G-J) at FIFTH floor (320.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 5th | 43246 | 43251 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0206 | First course of blockwork between axes (4-6)&(A-F) AT FIRST BASEMENT Floor (295.60) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | B1 | 43247 | 43255 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0207 | First course of blockwork between axes (12-17)&(F-J) at Third floor(312.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 3rd | 43248 | 43251 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0208 | First course of blockwork between axes (8-9)&(G-J) at Third floor(312.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 3rd | 43248 | 43251 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0209 | First course of blockwork between axes (14-16)&(C-D) AT FIRST BASEMENT Floor (295.60) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | B1 | 43250 | 43255 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0210 | First course of blockwork between axes (14-17)&(B-D) at Fourth floor (316.10) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 4th | 43250 | 43260 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0211 | First course of blockwork between axes (8-9)&(G-J) at FIFTH floor (320.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 5th | 43250 | 43260 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0212 | First course of blockwork between axes (8-11)&(G-J) at Fourth floor (316.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 4th | 43250 | 43260 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0213 | First course of blockwork between axes (2-8)&(B-D) at FIFTH floor (320.10) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 5th | 43250 | 43260 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0214 | First course of blockwork between axes (3-5)&(F-J) at FIFTH floor (320.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 5th | 43250 | 43260 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0215 | Second Coat of approved Putty For Painting For First Basement (295.60) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z2 | B1 | 43250 | 43261 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0216 | check Final coat of approved painting material For First Basement (295.60) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting Final Coat | Z2 | B1 | 43250 | 43261 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0217 | First course of blockwork between axes (3-7)&(F-J) at SIXTH floor (324.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 6th | 43260 | 43262 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0218 | First course of blockwork between axes (8-9)&(G-J) at SIXTH floor (324.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 6th | 43260 | 43262 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0219 | First course of blockwork between axes (10-11)&(G-J) at THIRD floor (312.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 3rd | 43260 | 43262 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0220 | First course of blockwork between axes (10-11)&(G-J) at SECOND floor (308.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 2nd | 43260 | 43262 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0221 | First course of blockwork between axes (10-11)&(G-J) at FIRST floor (304.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 1st | 43260 | 43262 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0222 | Second Coat of approved Putty For Painting For First Basement (295.60) at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z1 | B1 | 43279 | 43286 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0223 | check Final coat of approved painting material For First Basement (295.60) at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting Final Coat | Z1 | B1 | 43279 | 43288 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0224 | Second Coat of approved Putty For Painting For First Basement (295.60) at Zone(3) axes (F-L) &(13-6) as Per Attached Sketch. | ARCH | Painting second Putty | Z3 | B1 | 43279 | 43286 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0225 | First course of blockwork between axes (8-9)&(G-J) at Seventh floor(328.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 7th | 43279 | 43286 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0226 | First course of blockwork between axes (2-5)&(B-D) at SIxth floor(324.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 6th | 43285 | 43290 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0227 | First course of blockwork between axes (14-17)&(B-D) at Fifth floor(320.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 5th | 43285 | 43290 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0228 | First course of blockwork between axes (14-17)&(F-H) at Fifth floor(320.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 5th | 43285 | 43290 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0229 | First course of blockwork between axes (14-17)&(F-H) at THIRD floor(312.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 3rd | 43285 | 43290 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0230 | First course of blockwork between axes (3-2)&(E-D) at FIRST floor(304.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 1st | 43285 | 43290 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0231 | First course of blockwork between axes (2-5)&(F-H) at FIRST floor(304.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 1st | 43285 | 43290 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0232 | Surface Prepration and Release For Painting For Ceiling at First Basement (295.60) at Zone(4) axes (E-L) &(1-6) as Per Attached Sketch. | ARCH | Painting Surface Prepration | Z4 | B1 | 43285 | 43290 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0233 | Full Height of blockwork between axes (1-6)&(A-E) FROM SECOND FlooR TO FIFTH FLOOR for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | ML | 43289 | 43293 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0234 | Full Height of blockwork between axes (13-18)&(A-B) FROM SECOND FlooR TO FIFTH FLOOR for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | ML | 43289 | 43293 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0235 | Surface Prepration and Release For Painting For Ceiling at First Basement (295.60) at Zone(5) axes (A-F) &(1-7) as Per Attached Sketch. | ARCH | Painting Surface Prepration | Z5 | B1 | 43290 | 43292 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0236 | First course of blockwork between axes (12-17)&(G-K) at Fifth floor(320.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 5th | 43291 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0237 | First course of blockwork between axes (10-11)&(G-J) at Fifth floor(320.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 5th | 43291 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0238 | First course of blockwork between axes (17-14)&(E-B) at SIxth floor(324.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 6th | 43291 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0239 | First course of blockwork between axes (2-7)&(F-J) at SIxth floor(324.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 6th | 43291 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0240 | Full Height of blockwork between axes (14-18)&(B-F) AT FIRST Floor (304.10) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | 1st | 43291 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0241 | Full Height of blockwork between axes (12-17)&(F-L) AT FIRST Floor (304.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 1st | 43291 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0242 | Full Height of blockwork between axes (8-11)&(H-J) AT FIRST Floor (304.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 1st | 43291 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0243 | Full Height of blockwork between axes (2-7)&(F-L) AT FIRST Floor (304.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 1st | 43291 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0244 | Full Height of blockwork between axes (1-5)&(A-E) AT FIRST Floor (304.10) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | 1st | 43291 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0245 | Full Height of blockwork between axes (14-16)&(A-E) AT SECOND Floor (308.10) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | 2nd | 43292 | 43296 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0246 | Full Height of blockwork between axes (12-17)&(F-J) AT SECOND Floor (308.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 2nd | 43292 | 43296 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0247 | Full Height of blockwork between axes (8-11)&(G-J) AT SECOND Floor (308.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 2nd | 43292 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0248 | Full Height of blockwork between axes (2-7)&(F-K) AT SECOND Floor (308.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 2nd | 43292 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0249 | Full Height of blockwork between axes (2-5)&(A-D) AT SECOND Floor (308.10) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | 2nd | 43292 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0250 | First course of blockwork between axes (2-5)&(F-J) at Seventh floor(328.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 7th | 43292 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0251 | check Final coat of approved painting material For First Basement (295.60) at Zone(1) axes (0-A) &(13-18) as Per Attached Sketch. | ARCH | Painting Final Coat | Z1 | B1 | 43292 | 43298 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0252 | Second Coat of approved Putty For Painting For First Basement (295.60) at Zone(4) axes (E-L) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z4 | B1 | 43292 | 43298 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0253 | Second Coat of approved Putty For Painting For First Basement (295.60) at Zone(5) axes (0-F) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z5 | B1 | 43292 | 43298 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0254 | check Final coat of approved painting material For First Basement (295.60) at Zone(3) axes (F-L) &(13-6) as Per Attached Sketch. | ARCH | Painting Final Coat | Z3 | B1 | 43292 | 43298 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0255 | First course of blockwork between axes (12-16)&(F-K) at SIXTH floor(324.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 6th | 43297 | 43300 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0256 | First course of blockwork between axes (13-15)&(G-K) at FOURTH floor(316.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 4th | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0257 | First course of blockwork between axes (3-4)&(H-G) at FOURTH floor(316.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 4th | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0258 | First course of blockwork between axes (3-4)&(H-G) at FIFTH floor(320.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 5th | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0259 | Full Height of blockwork between axes (5-2)&(B-E) AT THERD Floor (312.10) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | 3rd | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0260 | Full Height of blockwork between axes (2-5)&(F-K) AT THIRD Floor (312.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 3rd | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0261 | Full Height of blockwork between axes (8-9)&(G-J) AT THIRD Floor (312.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 3rd | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0262 | Full Height of blockwork between axes (5-2)&(B-E) AT FOURTH Floor (316.10) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | 4th | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0263 | Full Height of blockwork between axes (2-5)&(F-K) AT FOURTH Floor (316.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 4th | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0264 | Full Height of blockwork between axes (8-9)&(G-J) AT FOURTH Floor (316.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 4th | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0265 | First course of blockwork between axes (14-17)&(F-K) at SEVENTH floor(328.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 7th | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0266 | First course of blockwork between axes (10-11)&(G-J) at SEVENTH floor(328.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 7th | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0267 | First course of blockwork between axes (2-5)&(F-K) at SEVENTH floor(328.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 7th | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0268 | First course of blockwork between axes (10-11)&(H-J) at SIXTH floor(324.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 6th | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0269 | First course of blockwork between axes (7-9)&(H-K) at EIGHTH floor(333.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 8th | 43303 | 43309 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0270 | check Final coat of approved painting material For First Basement (295.60) at Zone(4) axes (L-E) &(1-7) as Per Attached Sketch. | ARCH | Painting Final Coat | Z4 | B1 | 43306 | 43311 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0271 | check Final coat of approved painting material For First Basement (295.60) at Zone(5) axes (A-E) &(1-7) as Per Attached Sketch. | ARCH | Painting Final Coat | Z5 | B1 | 43306 | 43311 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0272 | Full Height of blockwork between axes (10-11)&(G-J) AT SECOND Floor (308.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 2nd | 43306 | 43311 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0273 | Full Height of blockwork between axes (12-18)&(A-E) FROM SECOND FlooR TO FIFTH FLOOR for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | ML | 43306 | 43311 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0274 | Full Height of blockwork between axes (6-11)&(F-L) AT FIRST BASEMENT Floor (295.60) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | B1 | 43306 | 43311 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0275 | Full Height of blockwork between axes (14-16)&(A-E) AT FIFTH Floor (320.10) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | 5th | 43306 | 43311 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0276 | Full Height of blockwork between axes (12-17)&(F-J) AT FIFTH Floor (320.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 5th | 43306 | 43311 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0277 | Full Height of blockwork between axes (8-11)&(G-J) AT FIFTH Floor (320.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 5th | 43306 | 43311 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0278 | Full Height of blockwork between axes (2-7)&(F-K) AT FIFTH Floor (320.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 5th | 43306 | 43311 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0279 | Full Height of blockwork between axes (2-5)&(A-D) AT FIFTH Floor (320.10) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | 5th | 43306 | 43311 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0280 | First course of blockwork between axes (13-18)&(0-D) at Second basement floor(291.80) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | B2 | 43311 | 43316 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0281 | First course of blockwork between axes (8-11)&(H-J) at Second basement floor(291.80) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | B2 | 43311 | 43316 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0282 | First primer coat for façade between axes (1-6)&(L-E) for area (Z4) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z4 | ML | 43313 | 43318 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0283 | SECOND primer coat for façade between axes (1-6)&(L-E) for area (Z4) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z4 | ML | 43313 | 43318 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0284 | Check Surface Prepration and dots and accessories for plaster works between axes (1-6)&(A-E) at First basement floor(295.60) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | B1 | 43313 | 43318 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0285 | Check Surface Prepration and dots and accessories for plaster works between axes (1-6)&(L-E) at First basement floor(295.60) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | B1 | 43313 | 43318 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0286 | Check Surface Prepration and dots and accessories for plaster works between axes (6-9)&(L-G) at First basement floor(295.60) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | B1 | 43313 | 43318 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0287 | Check for Final Plaser between axes (1-6)&(A-E) at First basement floor(295.60) for area (Z5) as Per Attached | ARCH | Final Plaster | Z5 | B1 | 43313 | 43318 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0288 | Check for Final plaster between axes (1-6)&(L-E) at First basement floor(295.60) for area (Z4) as Per Attached | ARCH | Final Plaster | Z4 | B1 | 43313 | 43318 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0289 | Check for Final plaster between axes (6-9)&(L-G) at First basement floor(295.60) for area (Z3) as Per Attached Sketch. | ARCH | Final Plaster | Z3 | B1 | 43313 | 43318 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0290 | Surface Prepration and Release For Painting For Ceiling at SECOND Basement (291.80) at Zone(5) axes (A-F) &(1-7) as Per Attached Sketch. | ARCH | Painting Surface Prepration | Z5 | B2 | 43313 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0291 | First course of blockwork between axes (10-12)&(G-K) at EIGHTH floor(333.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 8th | 43317 | 43320 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0292 | First course of blockwork between axes (2-5)&(G-K) at EIGHTH floor(333.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 8th | 43317 | 43320 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0293 | First course of blockwork between axes (14-17)&(G-K) at EIGHTH floor(333.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 8th | 43317 | 43320 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0294 | Full Height of blockwork between axes (10-11)&(G-J) AT FOURTH Floor (316.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 4th | 43317 | 43320 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0295 | Full Height of blockwork between axes (12-17)&(F-K) AT FOURTH Floor (316.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 4th | 43317 | 43320 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0296 | Full Height of blockwork between axes (14-17)&(B-D) AT FOURTH Floor (316.10) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | 4th | 43317 | 43320 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0297 | Surface Prepration and Release For Painting For Ceiling at SECOND Basement (291.80) at Zone(3) axes (E-L) &(6-13) as Per Attached Sketch. | ARCH | Painting Surface Prepration | Z3 | B2 | 43324 | 43330 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0298 | Surface Prepration and Release For Painting For Ceiling at SECOND Basement (291.80) at Zone(4) axes (E-L) &(1-7) as Per Attached Sketch. | ARCH | Painting Surface Prepration | Z4 | B2 | 43324 | 43330 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0299 | First primer coat for façade between axes (12-18)&(A-B) for area (Z1) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43324 | 43328 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0300 | SECOND primer coat for façade between axes (12-18)&(A-B) for area (Z1) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43324 | 43328 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0301 | Full Height of blockwork between axes (10-11)&(G-J) AT FIFTH Floor (320.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 5th | 43326 | 43330 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0302 | Full Height of blockwork between axes (8-9)&(G-J) at SIXTH floor (324.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 6th | 43327 | 43330 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0303 | Full Height of blockwork between axes (3-7)&(G-K) at SIxth floor(324.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 6th | 43327 | 43330 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0304 | Full Height of blockwork between axes (1-6)&(A-F) at SECOND BASEMENT floor(291.80 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | B2 | 43327 | 43330 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0305 | First primer coat for façade between axes (17-18)&(A-F) for area (Z1) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43327 | 43330 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0306 | SECOND primer coat for façade between axes (17-18)&(A-F) for area (Z1) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43327 | 43330 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0307 | Second Coat of approved Putty For Painting For SECOND Basement (291.80) at Zone(5) axes (A-F) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z5 | B2 | 43327 | 43330 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0308 | Surface Prepration and Release For Painting For Ceiling at First Basement (295.60) at Zone(3) axes (J-L) &(9-11) as Per Attached Sketch. | ARCH | Painting Surface Prepration | Z3 | B1 | 43339 | 43344 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0309 | Second Coat of approved Putty For Painting For First Basement (295.60) at Zone(3) axes (J-L) &(9-11) as Per Attached Sketch. | ARCH | Painting second Putty | Z3 | B1 | 43339 | 43347 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0310 | check Final coat of approved painting material For First Basement (295.60) at Zone(3) axes (J-L) &(9-11) as Per Attached Sketch. | ARCH | Painting Final Coat | Z3 | B1 | 43339 | 43347 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0311 | Check Surface Prepration and dots and accessories for plaster works between axes (8-9)&(G-J) at SECOND floor(308.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 2nd | 43341 | 43347 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0312 | Check Surface Prepration and dots and accessories for plaster works between axes (4-7)&(G-J) at SECOND floor(308.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 2nd | 43341 | 43347 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0313 | Check Surface Prepration and dots and accessories for plaster works between axes (3-4)&(B-D) at SECOND floor(308.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | 2nd | 43341 | 43347 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0314 | Check Surface Prepration and dots and accessories for plaster works between axes (8-9)&(G-J) at THIRD floor(312.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 3rd | 43341 | 43347 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0315 | Check Surface Prepration and dots and accessories for plaster works between axes (4-7)&(G-J) at THIRD floor(312.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 3rd | 43341 | 43347 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0316 | Check Surface Prepration and dots and accessories for plaster works between axes (3-4)&(B-D) at THIRD floor(312.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | 3rd | 43341 | 43347 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0317 | Check Surface Prepration and dots and accessories for plaster works between axes (4-7)&(G-J) at Fourth floor(316.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 4th | 43344 | 43352 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0318 | Check Surface Prepration and dots and accessories for plaster works between axes (8-9)&(G-J) at Fourth floor(316.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 4th | 43344 | 43352 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0319 | Check Surface Prepration and dots and accessories for plaster works between axes (2-5)&(B-D) at Fourth floor(316.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | 4th | 43344 | 43352 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0320 | Check final Coat of approved Putty For Painting For SECOND Basement (291.80) at Zone(5) axes (A-F) &(1-7) as Per Attached Sketch. | ARCH | Painting Final Coat | Z5 | B2 | 43344 | 43352 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0321 | Check fixation of chassis under marbel clading for façade between axis (4-6)&(1-2)&(L-K) from second floor to sixth floor zone(4)as per attached sketch. | ARCH | Marble Chassis | Z4 | ML | 43344 | 43358 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0322 | Check for Final plaster between axes (5-2)&(B-D) at SECOND floor(308.10) for area (Z5) as Per Attached Sketch. | ARCH | Final Plaster | Z5 | 2nd | 43345 | 43352 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0323 | Check for Final plaster between axes (7-4)&(G-K) at SECOND floor(308.10) for area (Z4) as Per Attached Sketch. | ARCH | Final Plaster | Z4 | 2nd | 43345 | 43352 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0324 | Check for Final plaster between axes (10-11)&(G-J) at SECOND floor(308.10) for area (Z3) as Per Attached Sketch. | ARCH | Final Plaster | Z3 | 2nd | 43345 | 43352 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0325 | Check fixation of rockwool under marbel clading for façade between axis (4-6)&(1-2)&(L-K) from level(308.10 To 320.10) zone(4)as per attached sketch. | ARCH | Marble Rockwool | Z4 | ML | 43349 | 43358 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0326 | Check fixation and finishing for marbel clading for façade between axis (4-6)&(1-2)&(L-K) from level(308.10 To 320.10) zone(4)as per attached sketch. | ARCH | Marble Façade | Z4 | ML | 43349 | 43358 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0327 | Check Surface Prepration and dots and accessories for plaster works between axes (12-18)&(0-F) at First basement floor(295.60) for area (Z1) as Per Attached Sketch. | ARCH | Plaster Dots | Z1 | B1 | 43355 | 43361 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0328 | Check for Final Plaster between axes (12-18)&(0-F) at First basement floor(295.60) for area (Z1) as Per Attached Sketch. | ARCH | Final Plaster | Z1 | B1 | 43355 | 43361 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0329 | Check Surface Prepration and dots and accessories for plaster works between axes (12-18)&(E-L) at First basement floor(295.60) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | B1 | 43355 | 43361 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0330 | Check for Final Plaster between axes (12-18)&(E-L) at First basement floor(295.60) for area (Z2) as Per Attached Sketch. | ARCH | Final Plaster | Z2 | B1 | 43355 | 43361 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0331 | Check Surface Prepration and dots and accessories for plaster works between axes (6-13)&(F-L) at First basement floor(295.60) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | B1 | 43355 | 43361 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0332 | Check for Final Plaster between axes (6-13)&(F-L) at First basement floor(295.60) for area (Z3) as Per Attached Sketch. | ARCH | Final Plaster | Z3 | B1 | 43355 | 43361 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0333 | Full Height of blockwork between axes (14-17)&(B-D) AT THERD Floor (312.10) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | 3rd | 43355 | 43360 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0334 | Full Height of blockwork between axes (13-17)&(F-K) AT THIRD Floor (312.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 3rd | 43355 | 43360 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0335 | Full Height of blockwork between axes (10-11)&(G-J) AT THIRD Floor (312.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 3rd | 43355 | 43360 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0336 | Surface Prepration and Release For Painting For Ceiling at SECOND Basement (291.80) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting Surface Prepration | Z2 | B2 | 43355 | 43360 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0337 | Second Coat of approved Putty For Painting For SECOND Basement (291.80) at Zone(4) axes (E-L) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z4 | B2 | 43355 | 43360 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0338 | Check Surface Prepration and dots and accessories for plaster works between axes (14-17)&(C-D) at Fourth floor(316.10) for area (Z1) as Per Attached Sketch. | ARCH | Plaster Dots | Z1 | 4th | 43361 | 43365 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0339 | Check Surface Prepration and dots and accessories for plaster works between axes (12-15)&(G-K) at Fourth floor(316.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 4th | 43361 | 43365 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0340 | Check Surface Prepration and dots and accessories for plaster works between axes (8-9)&(G-J) at SIXTH floor(324.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 6th | 43361 | 43365 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0341 | Full Height façade only of blockwork between axes (1-7)&(0-B) for area (Z5) From ground to first Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | ML | 43361 | 43365 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0342 | Full Height façade only of blockwork between axes (12-18)&(0-B) for area (Z1) From ground to first Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | ML | 43361 | 43365 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0343 | Full Height of blockwork between axes (12-18)&(F-L) AT Second basement Floor (291.80) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | B2 | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0344 | Full Height of blockwork between axes (2-5)&(B-E) AT SIXTH Floor (324.10) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | 6th | 43369 | 43389 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0345 | Check Surface Prepration and dots and accessories for plaster works between axes (1-6)&(A-F) at Second basement floor(291.80) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | B2 | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0346 | Check Surface Prepration and dots and accessories for plaster works between axes (2-5)&(B-D) at First floor(304.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | 1st | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0347 | Check Surface Prepration and dots and accessories for plaster works between axes (4-7)&(G-J) at First floor(304.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 1st | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0348 | Check Surface Prepration and dots and accessories for plaster works between axes (8-9)&(G-J) at First floor(304.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 1st | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0349 | Check Surface Prepration and dots and accessories for plaster works between axes (15-16)&(C-D) at Second floor(308.10) for area (Z1) as Per Attached Sketch. | ARCH | Plaster Dots | Z1 | 2nd | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0350 | Check Surface Prepration and dots and accessories for plaster works between axes (12-14)(G-J) at Second floor(308.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 2nd | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0351 | Check Surface Prepration and dots and accessories for plaster works between axes (10-11)(H-G) at Second floor(308.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 2nd | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0352 | Check Surface Prepration and dots and accessories for plaster works between axes (10-11)(H-G) at Third floor(312.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 3rd | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0353 | Check Surface Prepration and dots and accessories for plaster works between axes (12-15)(G-K) at Third floor(312.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 3rd | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0354 | Check Surface Prepration and dots and accessories for plaster works between axes (14-17)(C-D) at Third floor(312.10) for area (Z1) as Per Attached Sketch. | ARCH | Plaster Dots | Z1 | 3rd | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0355 | Check Surface Prepration and dots and accessories for plaster works between axes (10-11)(G-J) at Fourth floor(316.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 4th | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0356 | Check Surface Prepration and dots and accessories for plaster works between axes (12-15)(G-J) at Fifth floor(320.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 5th | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0357 | Check Surface Prepration and dots and accessories for plaster works between axes (4-7)(G-K) at Fifth floor(320.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 5th | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0358 | Check Surface Prepration and dots and accessories for plaster works between axes (8-11)(G-J) at Fifth floor(320.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 5th | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0359 | Check Surface Prepration and dots and accessories for plaster works between axes (2-5)(B-D) at Fifth floor(320.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | 5th | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0360 | Check Surface Prepration and dots and accessories for plaster works between axes (14-17)(C-D) at Fifth floor(320.10) for area (Z1) as Per Attached Sketch. | ARCH | Plaster Dots | Z1 | 5th | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0361 | Check Surface Prepration and dots and accessories for plaster works between axes (4-5)(G-J) at Sixth floor(320.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 6th | 43369 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0362 | First primer coat for façade between axes(12-18)&(0-B) for area (Z1) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43372 | 43377 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0363 | SECOND primer coat for façade between axes(12-18)&(0-B) for area (Z1) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43372 | 43377 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0364 | First primer coat for façade between axes (1-7)&(0-B) for area (Z5) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z5 | ML | 43372 | 43377 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0365 | SECOND primer coat for façade between axes(1-7)&(0-B) for area (Z5) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z5 | ML | 43372 | 43377 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0366 | Second Coat of approved Putty For Painting For Second Basement (291.80) at Zone(3) axes (E-L) &(6-13) as Per Attached Sketch. | ARCH | Painting second Putty | Z3 | B2 | 43372 | 43377 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0367 | check Final coat of approved painting material For Second Basement (291.80) at Zone(4) axes (E-L) &(1-7) as Per Attached Sketch. | ARCH | Painting Final Coat | Z4 | B2 | 43372 | 43377 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0368 | check Final coat of approved painting material For Second Basement (291.80) at Zone(5) axes (0-F) &(1-7) as Per Attached Sketch. | ARCH | Painting Final Coat | Z5 | B2 | 43372 | 43377 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0369 | First course of blockwork between axes (2-5)&(G-K) at EIGHTH floor(333.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 8th | 43383 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0370 | Full Height of blockwork between axes (7-12)&(G-J) AT EIGHTH floor(333.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 8th | 43383 | 43387 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0371 | Full Height of blockwork between axes (7-12)&(G-J) AT SEVENTH floor(328.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 7th | 43383 | 43387 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0372 | Check Surface Prepration and dots and accessories for plaster works between axes (12-18)&(E-L) at Second basement floor(291.80) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | B2 | 43383 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0373 | Full Height of blockwork between axes (13-18)&(0-F) AT second basement floor(291.80) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | B2 | 43383 | 43390 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0374 | First course of blockwork between axes (1-7)&(E-L) at Second basement floor(291.80) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | B2 | 43383 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0375 | Full Height of blockwork between axes (1-6)&(0-A) AT Second basement floor(291.80) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | B2 | 43383 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0376 | Full Height of blockwork between axes (8-13)&(F-L) AT Second basement floor(291.80) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | B2 | 43383 | 43387 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0377 | Check fixation of chassis under marble clading for façade between axis (13-18)/(A-B) from second floor to FIFTH floor zone(1)as per attached sketch. | ARCH | Marble Chassis | Z1 | ML | 43384 | 43395 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0378 | Check fixation of chassis under marble clading for façade between axis (1-5)/(G-L) from second floor to SIXTH floor zone(4)as per attached sketch. | ARCH | Marble Chassis | Z4 | ML | 43384 | 43395 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0379 | First course of blockwork between axes (7-12)&(G-K) at NINETH floor(338.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 9th | 43391 | 43396 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0380 | FULL HEIGHT of blockwork between axes (7-12)&(G-K) at NINETH floor(338.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 9th | 43391 | 43396 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0381 | check Final coat of approved painting material For Second Basement (291.80) at Zone(3) axes (E-L) &(6-13) as Per Attached Sketch. | ARCH | Painting Final Coat | Z3 | B2 | 43394 | 43400 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0382 | Second Coat of approved Putty For Painting For SECOND Basement (291.80) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z2 | B2 | 43394 | 43400 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0383 | Check for Final Plaster between axes (12-18)&(F-L) at second basement floor(291.80) for area (Z2) as Per Attached Sketch. | ARCH | Final Plaster | Z2 | B2 | 43394 | 43400 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0384 | Full Height of blockwork between axes (12-17)&(F-K) AT SIXTH floor(324.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 6th | 43400 | 43405 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0385 | Full Height of blockwork between axes (10-11)&(H-J) AT SIXTH floor(324.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 6th | 43400 | 43405 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0386 | Check Surface Prepration and dots and accessories for plaster works between axes (10-11)(G-J) at SEVENTH floor(328.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 7th | 43400 | 43405 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0387 | Check Surface Prepration and dots and accessories for plaster works between axes (10-11)(G-J) at EIGHTH floor(333.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 8th | 43400 | 43405 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0388 | First course of blockwork between axes (1-7)&(E-K) at Second basement floor(291.80) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | B2 | 43400 | 43405 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0389 | Full Height of blockwork between axes (1-7)&(E-L) at Second basement floor(291.80) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | B2 | 43400 | 43405 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0390 | First course of blockwork between axes (12-14)&(F-C) at Second basement floor(291.80) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | B2 | 43400 | 43405 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0391 | Check Surface Prepration and dots and accessories for plaster works between axes (13-18)&(0-F) at Second basement floor(291.80) for area (Z1) as Per Attached Sketch. | ARCH | Plaster Dots | Z1 | B2 | 43400 | 43405 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0392 | First course of blockwork between axes (11-13)&(K-L) at Second basement floor(291.80) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | B2 | 43400 | 43405 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0393 | Check Surface Prepration and dots and accessories for plaster works between axes (14-15)&(H-K) at Seventh floor(328.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 7th | 43403 | 43408 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0394 | Check Surface Prepration and dots and accessories for plaster works between axes (8-9)&(G-J) at Seventh floor(328.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 7th | 43403 | 43408 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0395 | Check Surface Prepration and dots and accessories for plaster works between axes (4-5)&(G-K) at Seventh floor(328.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 7th | 43403 | 43408 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0396 | Check Surface Prepration and dots and accessories for plaster works between axes (8-9)&(G-J) at EIGHTH floor(333.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 8th | 43403 | 43408 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0397 | Full Height of blockwork between axes (3-4)&(F-H) AT First Floor (304.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 1st | 43404 | 43412 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0398 | First course of blockwork between axes (3-4)&(F-H) at second floor(308.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 2nd | 43404 | 43409 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0399 | Full Height of blockwork between axes (3-4)&(F-H) AT SECOND Floor (308.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 2nd | 43404 | 43412 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0400 | Full Height façade only of blockwork between axes (17-18)&(F-L) for area (Z2) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | ML | 43407 | 43412 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0401 | First primer coat for façade between axes (17-18)&(F-L) for area (Z2) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43407 | 43412 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0402 | SECOND primer coat for façade between axes(17-18)&(F-L) for area (Z2) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43407 | 43412 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0403 | First primer coat for façade between axes (13-14)&(A-F) for area (Z1) From Second to FIFTH Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43407 | 43412 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0404 | SECOND primer coat for façade between axes (13-14)&(A-F) for area (Z1) From Second to FIFTH Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43407 | 43412 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0405 | Full Height façade only of blockwork between axes (17-18)&(F-L) for area (Z2) From ground to first Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | ML | 43407 | 43412 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0406 | First primer coat for façade between axes (17-18)&(F-L) for area (Z2) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43407 | 43412 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0407 | SECOND primer coat for façade between axes(17-18)&(F-L) for area (Z2) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43407 | 43412 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0408 | FULL HEIGHT of blockwork between axes (10-12)&(G-J) at NINETH floor(338.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 9th | 43407 | 43412 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0409 | Check fixation of chassis under marble clading for façade between axis (1-5)/(F-L) from second floor to SIXTH floor zone(4)as per attached sketch. | ARCH | Marble Chassis | Z4 | ML | 43409 | 43415 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0410 | Check fixation of rockwool under marbel clading for façade between axis (13-18)&(A-B) from Second floor to fifth floor zone(1)as per attached sketch. | ARCH | Marble Rockwool | Z1 | ML | 43409 | 43415 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0411 | Check fixation of rockwool under marbel clading for façade between axis (1-5)&(F-L) from Second floor to Sixth floor zone(4)as per attached sketch. | ARCH | Marble Rockwool | Z4 | ML | 43409 | 43415 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0412 | Check Surface Prepration and dots and accessories for plaster works between axes (12-15)(G-K) at Sixth floor(324.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 6th | 43409 | 43415 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0413 | Check Surface Prepration and dots and accessories for plaster works between axes (1-7)(E-L) at Second Basement (291.80) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | B2 | 43409 | 43415 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0414 | Check Surface Prepration and dots and accessories for plaster works between axes (6-13)(G-K) at Second Basement (291.80) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | B2 | 43409 | 43415 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0415 | Full Height of blockwork between axes (11-13)&(J-L) AT Second Basement (291.80) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | B2 | 43409 | 43415 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0416 | Full Height of blockwork between axes (14-16)&(G-J) AT Second Basement (291.80) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | B2 | 43409 | 43415 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0417 | check Final coat of approved painting material For Second Basement (291.80) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting Final Coat | Z2 | B2 | 43412 | 43422 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0418 | check Final coat of approved painting material For Second Basement (291.80) at Zone(5) axes (A-F) &(1-7) as Per Attached Sketch. | ARCH | Painting Final Coat | Z5 | B2 | 43412 | 43422 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0419 | Surface Prepration and Release For Painting For Ceiling at SECOND Basement (291.80) at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting Surface Prepration | Z1 | B2 | 43412 | 43422 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0420 | Second Coat of approved Putty For Painting For SECOND Basement (291.80) at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z1 | B2 | 43412 | 43422 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0421 | Check Surface Prepration and dots for ceramic tiles between axes (2-5)(F-H) at Second floor(308.10) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Dots | Z4 | 2nd | 43417 | 43422 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0422 | check Final coat of approved painting material For Second Basement (291.80) at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting Final Coat | Z1 | B2 | 43418 | 43422 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0423 | Full Height façade only of blockwork between axes (13-18)&(k-L) for area (Z2) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | ML | 43422 | 43429 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0424 | First primer coat for façade between axes (13-18)&(k-L) for area (Z2) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43422 | 43429 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0425 | SECOND primer coat for façade between axes(13-18)&(k-L) for area (Z2) From Second to Sixth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43422 | 43429 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0426 | Check fixation of chassis under marble clading for façade between axis (13-18)/(F-L) from second floor to SIXTH floor zone(2)as per attached sketch. | ARCH | Marble Chassis | Z2 | ML | 43422 | 43431 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0427 | First primer coat for façade between axes (1-7)&(A-F) for area (Z5) From SECOND to SIXTH Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z5 | ML | 43422 | 43429 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0428 | SECOND primer coat for façade between axes(1-7)&(A-F) for area (Z5) From SECOND to SIXTH Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z5 | ML | 43422 | 43429 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0429 | Check fixation of chassis under marble clading for façade between axis(1-7)&(A-F) for area (Z5) From SECOND to SIXTH Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z5 | ML | 43422 | 43431 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0430 | Check Surface Prepration and dots and accessories for plaster works between axes (2-7)(E-L) at Second Basement (291.80) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | B2 | 43422 | 43429 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0431 | Check Surface Prepration and dots and accessories for plaster works between axes (12-16)&(E-K) at Second basement floor(291.80) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | B2 | 43422 | 43429 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0432 | Full Height of blockwork between axes (12-14)&(F-C) at Second basement floor(291.80) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | B2 | 43422 | 43429 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0433 | Check Surface Prepration and dots and accessories for plaster works between axes (1-7)&(0-F) at Second basement floor(291.80) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | B2 | 43422 | 43429 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0434 | Check Surface Prepration and dots and accessories for plaster works between axes (6-12)&(G-L) at Second basement floor(291.80) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | B2 | 43422 | 43429 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0435 | Check fixation of chassis under marble clading for façade between axis (17-18)/(A-F) from second floor to FIFTH floor zone(1)as per attached sketch. | ARCH | Marble Chassis | Z1 | ML | 43429 | 43437 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0436 | Check fixation of rockwool under marbel clading for façade between axis (17-18)&(A-F) from Second floor to fifth floor zone(1)as per attached sketch. | ARCH | Marble Rockwool | Z1 | ML | 43429 | 43437 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0437 | First course of blockwork between axes (1-6)&(A-E) at SECOND floor(308.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 2nd | 43429 | 43437 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0438 | First course of blockwork between axes (16-18)&(D-G) at SECOND BASEMENT floor(291.80 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | B2 | 43429 | 43437 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0439 | Check Surface Prepration and dots and accessories for plaster works between axes (12-14)&(C-F) at Second basement floor(291.80) for area (Z1) as Per Attached Sketch. | ARCH | Plaster Dots | Z1 | B2 | 43429 | 43437 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0440 | Check fixation of chassis under marble clading for façade between axis (13-14)/(A-F) from second floor to FIFTH floor zone(1)as per attached sketch. | ARCH | Marble Chassis | Z1 | ML | 43435 | 43449 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0441 | First primer coat for façade between axes (5-6)&(A-F) for area (Z5) From SECOND to SIXTH Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z5 | ML | 43435 | 43449 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0442 | SECOND primer coat for façade between axes(5-6)&(A-F) for area (Z5) From SECOND to SIXTH Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z5 | ML | 43435 | 43449 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0443 | Check fixation of chassis under marble clading for façade between axis (5-6)/(A-F) from second floor to FIFTH floor zone(5)as per attached sketch. | ARCH | Marble Chassis | Z5 | ML | 43435 | 43449 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0444 | First course of blockwork between axes (1-7)&(E-L) at SECOND floor(308.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 2nd | 43435 | 43452 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0445 | First course of blockwork between axes (6-9)&(E-L) at SECOND floor(308.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 2nd | 43435 | 43452 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0446 | Check Surface Prepration and dots for ceramic tiles between axes (2-5)&(F-H) at first floor(304.10) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Dots | Z4 | 1st | 43444 | 43452 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0447 | Check for Final Plaster between axes (1-7)&(A-F) at Second basement floor(291.80) for area (Z5) as Per Attached Sketch. | ARCH | Final Plaster | Z5 | B2 | 43444 | 43452 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0448 | Check for Final Plaster between axes (1-7)&(E-L) at Second basement floor(291.80) for area (Z4) as Per Attached Sketch. | ARCH | Final Plaster | Z4 | B2 | 43444 | 43452 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0449 | Check for Final Plaster between axes (12-18)&(A-F) at Second basement floor(291.80) for area (Z1) as Per Attached Sketch. | ARCH | Final Plaster | Z1 | B2 | 43444 | 43452 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0450 | Check for Final Plaster between axes (12-18)&(E-L) at Second basement floor(291.80) for area (Z2) as Per Attached Sketch. | ARCH | Final Plaster | Z2 | B2 | 43444 | 43452 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0451 | First course of blockwork between axes (12-18)&(A-F) at first floor(304.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 1st | 43444 | 43452 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0452 | First course of blockwork between axes (12-18)&(A-F) at second floor(308.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 2nd | 43444 | 43452 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0453 | First course of blockwork between axes (12-18)&(E-L) at first floor(304.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 1st | 43444 | 43452 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0454 | First course of blockwork between axes (6-12)&(L-F) at first floor(304.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 1st | 43445 | 43458 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0455 | First course of blockwork between axes (1-7)&(A-F) at first floor(304.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 1st | 43445 | 43458 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0456 | First course of blockwork between axes (1-7)&(F-L) at first floor(304.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 1st | 43445 | 43458 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0457 | Check fixation of chassis under marble clading for façade between axis(1-7)&(A-F) for area (Z5) From SECOND to SIXTH Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z5 | ML | 43446 | 43452 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0458 | First course of blockwork between axes (12-18)&(E-L) at second floor(308.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 2nd | 43446 | 43458 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0459 | First course of blockwork between axes (10-13)&(F-L) at second floor(308.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 2nd | 43446 | 43458 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0460 | First course of blockwork between axes (13-18)&(A-F) at Third floor(312.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 3rd | 43450 | 43457 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0461 | First course of blockwork between axes (13-18)&(E-L) at Third floor(312.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 3rd | 43450 | 43457 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0462 | First course of blockwork between axes (7-13)&(E-L) at Third floor(312.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 3rd | 43450 | 43457 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0463 | First course of blockwork between axes (1-7)&(E-L) at Third floor(312.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 3rd | 43450 | 43457 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0464 | First course of blockwork between axes (1-6)&(A-F) at Third floor(312.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 3rd | 43450 | 43457 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0465 | First course of blockwork between axes (13-18)&(A-F) at Fourth floor(316.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 4th | 43450 | 43457 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0466 | First course of blockwork between axes (12-18)&(E-L) at Fourth floor(316.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 4th | 43450 | 43457 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0467 | First course of blockwork between axes (6-13)&(F-L) at Fourth floor(316.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 4th | 43450 | 43457 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0468 | First course of blockwork between axes (1-7)&(E-L) at Fourth floor(316.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 4th | 43450 | 43457 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0469 | First course of blockwork between axes (1-6)&(A-F) at Fourth floor(316.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 4th | 43450 | 43457 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0470 | Check Surface Prepration and dots for ceramic tiles between axes (2-5)&(F-H) at third floor(312.10) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Dots | Z4 | 3rd | 43452 | 43457 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0471 | Check Surface Prepration and dots for ceramic tiles between axes (2-5)&(F-H) at fourth floor(316.10) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Dots | Z4 | 4th | 43452 | 43463 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0472 | Check Surface Prepration and dots for plaster works between axes (14-17)&(F-H) at first floor(304.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 1st | 43452 | 43463 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0473 | Check Surface Prepration and dots for plaster works between axes (14-17)&(F-H) at third floor(312.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 3rd | 43452 | 43463 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0474 | Full Height façade only of blockwork between axes (12-14)&(A-F) for area (Z1) From ground to first Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | ML | 43456 | 43459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0475 | First primer coat for façade between axes(12-14)&(A-F) for area (Z1) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43456 | 43459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0476 | SECOND primer coat for façade between axes(12-14)&(A-F) for area (Z1) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43456 | 43459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0477 | Full Height façade only of blockwork between axes (5-7)&(A-F) for area (Z5) From ground to first Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | ML | 43456 | 43459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0478 | First primer coat for façade between axes(5-7)&(A-F) for area (Z5) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z5 | ML | 43456 | 43459 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0479 | SECOND primer coat for façade between axes(5-7)&(A-F) for area (Z5) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z5 | ML | 43456 | 43459 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0480 | First course of blockwork between axes (13-18)&(A-F) at FIFTH floor(320.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | 5th | 43456 | 43459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0481 | First course of blockwork between axes (13-18)&(E-L) at FIFTH floor(320.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 5th | 43456 | 43459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0482 | First course of blockwork between axes (7-13)&(E-L) at FIFTH floor(320.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 5th | 43456 | 43459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0483 | First course of blockwork between axes (1-7)&(E-L) at FIFTH floor(320.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 5th | 43456 | 43459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0484 | First course of blockwork between axes (1-6)&(A-F) at FIFTH floor(320.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | 5th | 43456 | 43459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0485 | Full Height of blockwork between axes (2-5)&(F-H) at FIRST floor(304.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 1st | 43456 | 43459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0486 | Full Height of blockwork between axes (2-5)&(F-H) at SECOND floor(308.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 2nd | 43456 | 43459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0487 | First course of blockwork between axes (12-18)&(F-L) at sixth floor(324.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 6th | 43464 | 43477 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0488 | First course of blockwork between axes (6-13)&(F-L) at sixth floor(324.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 6th | 43464 | 43477 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0489 | First course of blockwork between axes (1-7)&(F-L) at sixth floor(324.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 6th | 43464 | 43477 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0490 | First course of blockwork between axes (1-7)&(F-L) at Seventh floor(328.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | 7th | 43464 | 43477 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0491 | Check Surface Prepration and dots for ceramic tiles between axes (14-17)&(F-H) at second floor(308.10) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Dots | Z2 | 2nd | 43465 | 43477 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0492 | Check Surface Prepration and dots for ceramic tiles between axes (14-17)&(F-H) at Fourth floor(316.10) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Dots | Z2 | 4th | 43465 | 43477 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0493 | Check Surface Prepration and dots for ceramic tiles between axes (2-5)&(F-H) at SIXTH floor(324.10) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Dots | Z4 | 6th | 43465 | 43477 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0494 | Check Surface Prepration and dots for ceramic tiles between axes (14-17)&(F-H) at Fifth floor(320.10) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Dots | Z2 | 5th | 43466 | 43477 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0495 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(1-5)&(G-L) for area (Z4) From SECOND to SEVENTH Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z4 | ML | 43475 | 43500 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0496 | Full Height façade only of blockwork between axes (17-18)&(A-F) for area (Z1) From GROUND to FIRST Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | ML | 43475 | 43484 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0497 | Check fixation of rockwool under marbel clading for façade between axis (12-18)&(A-F) from level(308.10 To 320.10) zone(1)as per attached sketch. | ARCH | Marble Rockwool | Z1 | ML | 43477 | 43486 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0498 | Check fixation and finishing for marbel clading for façade between axis(12-18)&(A-F) from level(308.10 To 320.10) zone(1)as per attached sketch. | ARCH | Marble Façade | Z1 | ML | 43477 | 43486 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0499 | Check fixation of rockwool under marbel clading for façade between axis (12-18)&(F-L) from level(308.10 To 324.10) zone(2)as per attached sketch. | ARCH | Marble Rockwool | Z2 | ML | 43477 | 43486 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0500 | Check fixation and finishing for marbel clading for façade between axis(12-18)&(F-L) from level(308.10 To 324.10) zone(2)as per attached sketch. | ARCH | Marble Façade | Z2 | ML | 43477 | 43486 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0501 | Check fixation of rockwool under marbel clading for façade between axis (1-7)&(A-F) from level(308.10 To 320.10) zone(5)as per attached sketch. | ARCH | Marble Rockwool | Z5 | ML | 43477 | 43493 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0502 | Check fixation and finishing for marbel clading for façade between axis(1-7)&(A-F) from level(308.10 To 320.10) zone(5)as per attached sketch. | ARCH | Marble Façade | Z5 | ML | 43477 | 43486 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0503 | Check Surface Prepration and dots for ceramic tiles between axes (14-17)&(F-H) at fifth floor(320.10) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Dots | Z4 | 5th | 43486 | 43493 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0504 | First course of blockwork between axes (6-13)&(A-F) at first basement floor(295.60 ) for area (Z6) as Per Attached Sketch. | ARCH | Blockwork First course | Z6 | B1 | 43492 | 43499 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0505 | Full Height of blockwork between axes (6-13)&(A-F) at first basement floor(295.60 ) for area (Z6) as Per Attached Sketch. | ARCH | Blockwork Full height | Z6 | B1 | 43492 | 43499 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0506 | Check Surface Prepration and dots and accessories for plaster works between axes (6-13)&(A-F) at first basement floor(295.60 ) for area (Z6) as Per Attached Sketch. | ARCH | Plaster Dots | Z6 | B1 | 43492 | 43499 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0507 | First course of blockwork between axes (6-13)&(F-L) at seventh floor(328.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 7th | 43492 | 43499 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0508 | First course of blockwork between axes (12-18)&(F-L) at seventh floor(328.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | 7th | 43492 | 43499 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0509 | Full Height of blockwork between axes (12-18)&(A-F) at first floor(304.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | 1st | 43492 | 43499 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0510 | Full Height of blockwork between axes (12-18)&(E-L) at first floor(304.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 1st | 43492 | 43499 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0511 | Full Height of blockwork between axes (6-13)&(F-L) at first floor(304.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 1st | 43492 | 43499 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0512 | Full Height of blockwork between axes (1-7)&(F-L) at first floor(304.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 1st | 43492 | 43499 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0513 | Full Height of blockwork between axes (1-7)&(A-F) at first floor(304.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | 1st | 43492 | 43499 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0514 | Full Height of blockwork between axes (12-18)&(A-F) at Second floor(308.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | 2nd | 43492 | 43499 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0515 | Full Height of blockwork between axes (12-18)&(E-L) at Second floor(308.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 2nd | 43492 | 43499 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0516 | Full Height of blockwork between axes (6-13)&(F-L) at Second floor(308.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 2nd | 43492 | 43499 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0517 | Full Height of blockwork between axes (1-7)&(F-L) atSecond floor(308.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 2nd | 43492 | 43499 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0518 | Full Height of blockwork between axes (1-6)&(A-F) at Second floor(308.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | 2nd | 43492 | 43499 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0519 | Full Height façade only of blockwork between axes (6-9)&(K-L) for area (Z3) From ground to nineth Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | ML | 43492 | 43500 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0520 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(1-6)&(A-E) for area (Z5) From SECOND to fifth Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z5 | ML | 43494 | 43500 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0521 | First course of blockwork between axes (8-11)&(G-K) at fourth floor(316.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 4th | 43495 | 43500 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0522 | First primer coat for façade between axes(17-18)&(A-F) for area (Z1) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43513 | 43517 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0523 | SECOND primer coat for façade between axes(17-18)&(A-F) for area (Z1) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43513 | 43517 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0524 | Full Height façade only of blockwork between axes (12-18)&(K-L) for area (Z2) From ground to first Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | ML | 43513 | 43520 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0525 | First primer coat for façade between axes (12-18)&(K-L) for area (Z2) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43513 | 43517 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0526 | SECOND primer coat for façade between axes (12-18)&(K-L) for area (Z2) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43513 | 43517 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0527 | Full Height façade only of blockwork between axes (0-7)&(F-L) for area (Z4) From ground to first Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | ML | 43513 | 43520 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0528 | First primer coat for façade between axes (0-7)&(F-L) for area (Z4) From ground to first Floor as Per Attached Sketch.. | ARCH | Water Proofing Façade | Z4 | ML | 43513 | 43520 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0529 | SECOND primer coat for façade between axes (0-7)&(F-L) for area (Z4) From ground to first Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z4 | ML | 43513 | 43520 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0530 | Full Height façade only of blockwork between axes (0-2)&(A-F) for area (Z5) From ground to first Floor as Per Attached Sketch.. | ARCH | Blockwork Full height | Z5 | ML | 43513 | 43520 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0531 | First primer coat for façade between axes (0-2)&(A-F) for area (Z5) From ground to first Floor as Per Attached Sketch.. | ARCH | Water Proofing Façade | Z5 | ML | 43513 | 43520 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0532 | SECOND primer coat for façade between axes (0-2)&(A-F) for area (Z5) From ground to first Floor as Per Attached Sketch.. | ARCH | Water Proofing Façade | Z5 | ML | 43513 | 43520 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0533 | Check Surface Prepration and dots and accessories for plaster works between axes (A-F)&(13-18) at SECOND floor(308.10) for area (Z1) as Per Attached Sketch. | ARCH | Plaster Dots | Z1 | 2nd | 43520 | 43522 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0534 | Full Height of blockwork between axes (6-9)&(F-L) at third floor(312.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 3rd | 43521 | 43528 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0535 | Full Height of blockwork between axes (1-7)&(E-L) at third floor(312.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 3rd | 43521 | 43528 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0536 | Full Height of blockwork between axes (1-6)&(A-F) at third floor(312.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | 3rd | 43521 | 43528 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0537 | Full Height façade only of blockwork between axes (6-13)&(E-L) for area (Z3) From ground to nineth Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | ML | 43521 | 43528 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0538 | First course of blockwork between axes (6-13)&(F-L) at 8TH floor(333.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 8th | 43523 | 43528 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0539 | First course of blockwork between axes (6-13)&(F-L) at 9TH floor(338.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 9th | 43523 | 43526 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0540 | Check Surface Prepration and dots for ceramic tiles between axes (17-18)&(D-E) at first basement(295.60) for area (Z1) as Per Attached Sketch. | ARCH | Ceramic Dots | Z1 | B1 | 43528 | 43535 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0541 | Check Surface Prepration and dots for ceramic tiles between axes (1-2)&(D-E) at first basement(295.60) for area (Z5) as Per Attached Sketch. | ARCH | Ceramic Dots | Z5 | B1 | 43528 | 43535 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0542 | Check fixation of chassis under marble clading for façade between axis(12-18)&(A-F) for area (Z1) From Ground to first Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z1 | ML | 43528 | 43535 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0543 | Check fixation of chassis under marble clading for façade between axis(12-18)&(F-L) for area (Z2) From Ground to first Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z2 | ML | 43528 | 43535 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0544 | Check fixation of chassis under marble clading for façade between axis(1-7)&(F-L) for area (Z4) From Ground to first Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z4 | ML | 43528 | 43535 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0545 | Check fixation of chassis under marble clading for façade between axis(1-7)&(A-F) for area (Z5) From Ground to first Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z5 | ML | 43528 | 43535 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0546 | Check Surface Prepration and dots and accessories for plaster works for stair NO.(1) between axes (3-4)&(B-C) from level (291.80-324.20) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | ML | 43530 | 43540 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0547 | Check Surface Prepration and dots and accessories for plaster works between axes (A-F)&(12-18) at first floor(304.10) for area (Z1) as Per Attached Sketch. | ARCH | Plaster Dots | Z1 | 1st | 43534 | 43543 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0548 | Check Surface Prepration and dots and accessories for plaster works between axes (G-K)&(6-9) at first floor(304.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 1st | 43536 | 43544 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0549 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(2-7) at first floor(304.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 1st | 43536 | 43544 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0550 | Check Surface Prepration and dots and accessories for plaster works between axes (E-K)&(2-7) at second floor(308.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 2nd | 43536 | 43544 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0551 | Check Surface Prepration and dots and accessories for plaster works between axes (A-F)&(2-5) at second floor(308.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | 2nd | 43536 | 43544 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0552 | Check Surface Prepration and dots and accessories for plaster works between axes (E-K)&(2-7) at third floor(312.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 3rd | 43536 | 43544 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0553 | Full Height of blockwork between axes (6-9)&(F-L) at fourth floor(316.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 4th | 43542 | 43549 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0554 | Full Height of blockwork between axes (6-9)&(F-L) at fifth floor(320.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 5th | 43542 | 43549 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0555 | Full Height of blockwork between axes (6-9)&(F-L) at sixth floor(324.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 6th | 43542 | 43549 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0556 | Check Surface Prepration and dots and accessories for plaster works between axes (G-K)&(6-9) at third floor(312.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 3rd | 43542 | 43551 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0557 | Full Height of blockwork between axes (2-5)&(F-H) at third floor(312.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 3rd | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0558 | Full Height of blockwork between axes (2-5)&(F-H) at fourth floor(316.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 4th | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0559 | Full Height of blockwork between axes (2-5)&(F-H) at fifth floor(320.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 5th | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0560 | Full Height of blockwork between axes (2-5)&(F-H) at sixth floor(324.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 6th | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0561 | Full Height of blockwork between axes (14-17)&(F-H) at first floor(304.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 1st | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0562 | Full Height of blockwork between axes (14-17)&(F-H) at second floor(308.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 2nd | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0563 | Full Height of blockwork between axes (14-17)&(F-H) at third floor(312.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 3rd | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0564 | Full Height of blockwork between axes (14-17)&(F-H) at fourth floor(316.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 4th | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0565 | Full Height of blockwork between axes (14-17)&(F-H) at fifth floor(320.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 5th | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0566 | Full Height of blockwork between axes (14-17)&(F-H) at sixth floor(324.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 6th | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0567 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(12-18) at second floor(308.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 2nd | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0568 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(12-18) at first floor(304.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 1st | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0569 | Check Surface Prepration and dots for ceramic tiles between axes (2-5)&(F-H) at seventh floor(328.10) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Dots | Z4 | 7th | 43557 | 43562 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0570 | Full Height of blockwork between axes (13-18)&(A-F) at Third floor(312.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | 3rd | 43557 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0571 | Full Height of blockwork between axes (13-18)&(E-L) at Third floor(312.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 3rd | 43557 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0572 | Full Height of blockwork between axes (13-18)&(A-F) at fourth floor(316.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | 4th | 43557 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0573 | Full Height of blockwork between axes (13-18)&(E-L) at fourth floor(316.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 4th | 43557 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0574 | Full Height of blockwork between axes (13-18)&(A-F) at fifth floor(320.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | 5th | 43557 | 43564 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0575 | Full Height of blockwork between axes (12-18)&(E-L) at fifth floor(320.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 5th | 43557 | 43564 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0576 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(14-17)&(K-L) for area (Z2) From SECOND to SEVENTH Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z2 | ML | 43562 | 43564 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0577 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(17-18)&(B-E) for area (Z1) From SECOND to fifth Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z1 | ML | 43562 | 43564 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0578 | Check fixation of chassis under marble clading for façade between axis(5-6)&(B-E) for area (Z5) From SECOND to FIFTH Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z5 | ML | 43562 | 43568 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0579 | Check fixation of chassis under marble clading for façade between axis(14-17)&(K-L) for area (Z2) From second to seventh Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z2 | ML | 43562 | 43566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0580 | Full Height of blockwork between axes (1-7)&(F-L) at seventh floor(328.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 7th | 43562 | 43568 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0581 | Check fixation of chassis under marble clading for façade between axis(17-18)&(G-K) for area (Z2) From second to seventh Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z2 | ML | 43563 | 43568 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0582 | Full Height façade only of blockwork between axes (6-9)&(E-L) for area (Z3) From ground to nineth Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | ML | 43563 | 43568 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0583 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(7-9)&(K-L) for area (Z3) From second to nineth Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z3 | ML | 43563 | 43568 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0584 | Full Height of blockwork between axes (2-5)&(G-K) at ROOF floor(333.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | RF | 43565 | 43576 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0585 | Check Surface Prepration and dots and accessories for plaster works between axes (2-5)&(G-K) at ROOF floor(333.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | RF | 43565 | 43576 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0586 | Check for Final Plaster between axes (E-L)&(12-18) at first floor(304.10) for area (Z2) as Per Attached Sketch. | ARCH | Final Plaster | Z2 | 1st | 43565 | 43570 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0587 | Check for Final Plaster between axes (A-F)&(12-18) at first floor(304.10) for area (Z1) as Per Attached Sketch. | ARCH | Final Plaster | Z1 | 1st | 43565 | 43570 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0588 | Check fixation of chassis under marble clading for façade between axis(1-6)&(K-L) for area (Z4) From Ground to first Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z4 | ML | 43565 | 43573 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0589 | First primer coat for façade between axes(6-9)&(E-L) for area (Z3) From ground to nineth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z3 | ML | 43565 | 43573 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0590 | SECOND primer coat for façade between axes (6-9)&(E-L) for area (Z3) From ground to nineth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z3 | ML | 43565 | 43573 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0591 | Check fixation of chassis under marble clading for façade between axis(6-9)&(E-L) for area (Z3) From ground to nineth Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z3 | ML | 43565 | 43573 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0592 | Check Surface Prepration and dots and accessories for plaster works between axes (13-18)&(A-F) at third floor(312.10) for area (Z1) as Per Attached Sketch. | ARCH | Plaster Dots | Z1 | 3rd | 43569 | 43573 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0593 | Check Surface Prepration and dots and accessories for plaster works between axes (13-18)&(E-L)) at third floor(312.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 3rd | 43569 | 43573 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0594 | Check for Final Plaster between axes (A-F)&(13-18) at second floor(308.10) for area (Z1) as Per Attached Sketch. | ARCH | Final Plaster | Z1 | 2nd | 43569 | 43573 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0595 | Full Height of blockwork between axes (14-17)&(G-K) at ROOF floor(333.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | RF | 43569 | 43573 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0596 | Check Surface Prepration and dots and accessories for plaster works between axes (14-17)&(G-K) at ROOF floor(333.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | RF | 43569 | 43573 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0597 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(14-18)&(F-L) for area (Z2) From ground to first Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z2 | ML | 43569 | 43573 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0598 | Full Height of blockwork between axes (12-18)&(F-L) at sixth floor(324.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 6th | 43572 | 43582 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0599 | Check Surface Prepration and dots for ceramic tiles between axes (13-18)&(E-F) at third floor(312.10) for area (Z1) as Per Attached Sketch. | ARCH | Ceramic Dots | Z1 | 3rd | 43572 | 43576 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0600 | Check Surface Prepration and dots for ceramic tiles between axes (13-14)&(E-F) at fourth floor(316.10) for area (Z1) as Per Attached Sketch. | ARCH | Ceramic Dots | Z1 | 4th | 43572 | 43576 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0601 | Check Surface Prepration and dots for ceramic tiles between axes (12-14)&(J-K) at fourth floor(316.10) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Dots | Z2 | 4th | 43572 | 43576 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0602 | Check Surface Prepration and dots for ceramic tiles between axes (14-15)&(D-E) at fifth floor(320.10) for area (Z1) as Per Attached Sketch. | ARCH | Ceramic Dots | Z1 | 5th | 43572 | 43576 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0603 | Check first cours of blockwork between axes (12-18)&(E-L)) at ground floor(300.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | GF | 43572 | 43582 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0604 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(1-7) at second floor(308.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 2nd | 43576 | 43585 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0605 | Check Surface Prepration and dots and accessories for plaster works between axes (A-F)&(1-7) at second floor(308.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | 2nd | 43576 | 43585 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0606 | Check Surface Prepration and dots for ceramic tiles between axes (5-6)&(D-F) at third floor(312.10) for area (Z5) as Per Attached Sketch. | ARCH | Ceramic Dots | Z5 | 3rd | 43576 | 43582 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0607 | Check Surface Prepration and dots for ceramic tiles between axes (4-6)&(E-F) at fourth floor(316.10) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Dots | Z4 | 4th | 43576 | 43582 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0608 | Check Surface Prepration and dots for ceramic tiles between axes (2-3)&(C-D) at fifth floor(320.10) for area (Z5) as Per Attached Sketch. | ARCH | Ceramic Dots | Z5 | 5th | 43576 | 43582 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0609 | Check Surface Prepration and dots for ceramic tiles between axes (2-3)&(H-G) at sixth floor(324.10) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Dots | Z4 | 6th | 43576 | 43582 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0610 | Check Surface Prepration and dots and accessories for plaster works between axes (A-F)&(13-18) at fourth floor(316.10) for area (Z1) as Per Attached Sketch. | ARCH | Plaster Dots | Z1 | 4th | 43579 | 43582 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0611 | Check Surface Prepration and dots and accessories for plaster works between axes (L-E)&(13-18) at fourth floor(316.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 4th | 43579 | 43582 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0612 | Full Height of blockwork between axes (6-13)&(E-L) AT THIRD Floor (312.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 3rd | 43579 | 43585 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0613 | Check Surface Prepration and dots for ceramic tiles between axes (8-9)&(G-K) at first floor(304.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 1st | 43579 | 43585 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0614 | Check Surface Prepration and dots for ceramic tiles between axes (7-9)&(F-L) at third floor(312.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 3rd | 43579 | 43585 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0615 | Check Surface Prepration and dots for ceramic tiles between axes (7-9)&(G-L) at fourth floor(316.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 4th | 43579 | 43585 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0616 | Check Surface Prepration and dots for ceramic tiles between axes (7-9)&(G-L) at fifth floor(320.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 5th | 43579 | 43585 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0617 | Check Surface Prepration and dots for ceramic tiles between axes (7-9)&(G-L) at sixth floor(324.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 6th | 43579 | 43585 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0618 | Check for Final Plaster between axes (E-L)&(12-18) at second floor(308.10) for area (Z2) as Per Attached Sketch. | ARCH | Final Plaster | Z2 | 2nd | 43579 | 43582 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0619 | Check Surface Prepration and dots for ceramic tiles between axes (14-17)&(F-H) at seventh floor(328.10) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Dots | Z2 | 7th | 43582 | 43594 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0620 | Check Surface Prepration and dots for ceramic tiles between axes (14-17)&(F-H) at sixth floor(324.10) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Dots | Z2 | 6th | 43583 | 43594 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0621 | Full Height of blockwork between axes (10-13)&(E-L) at fifth Floor (320.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 5th | 43593 | 43604 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0622 | Full Height of blockwork between axes (10-13)&(E-L) at sixth Floor (324.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 6th | 43593 | 43604 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0623 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(12-18) at sixth floor(324.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 6th | 43593 | 43604 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0624 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(6-12) at second floor(308.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 2nd | 43593 | 43604 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0625 | Check for Final Plaster between axes (A-F)&(13-18) at fourth floor(316.10) for area (Z1) as Per Attached Sketch. | ARCH | Final Plaster | Z1 | 4th | 43593 | 43604 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0626 | Check for Final Plaster between axes (E-L)&(12-18) at fourth floor(316.10) for area (Z2) as Per Attached Sketch. | ARCH | Final Plaster | Z2 | 4th | 43593 | 43604 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0627 | Check for Final Plaster between axes (E-L)&(12-18) at third floor(312.10) for area (Z2) as Per Attached Sketch. | ARCH | Final Plaster | Z2 | 3rd | 43593 | 43604 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0628 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(17-18)&(F-L) for area (Z2) From second to seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z2 | ML | 43593 | 43604 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0629 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(10-12)&(K-L) for area (Z3) From ground to nineth Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z3 | ML | 43593 | 43604 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0630 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(12-18)&(A-F) for area (Z1) From ground to first Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z1 | ML | 43593 | 43604 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0631 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(1-6)&(G-L) for area (Z4) From ground to first Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z4 | ML | 43593 | 43600 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0632 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(1-7)&(A-E) for area (Z5) From ground to first Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z5 | ML | 43593 | 43600 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0633 | Check first cours of blockwork between axes (12-18)&(A-F) at ground floor(300.10) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork First course | Z1 | GF | 43601 | 43607 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0634 | Full Height of blockwork between axes (12-18)&(A-F) at ground floor(300.10) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | GF | 43601 | 43607 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0635 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(10-13) at fourth floor(316.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 4th | 43601 | 43607 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0636 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(10-13) at third floor(312.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 3rd | 43601 | 43607 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0637 | Check Surface Prepration and dots and accessories for plaster works between axes (G-K)&(2-5) at roof floor(333.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | RF | 43601 | 43607 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0638 | Check Surface Prepration and dots for ceramic tiles between axes (K-L)&(8-9) at eighth floor(333.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 8th | 43601 | 43606 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0639 | Surface Prepration For Painting For Ceiling at roof floor (333.10) at Zone(4) axes (F-L) &(1-5) as Per Attached Sketch. | ARCH | Painting Surface Prepration | Z4 | RF | 43601 | 43607 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0640 | Check fixation of chassis under marble clading for façade between axis(0-1)&(G-L) for area (Z4) From ground to first Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z4 | ML | 43601 | 43607 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0641 | Check fixation of chassis under marble clading for façade between axis(1-7)&(0-A) for area (Z5) From ground to first Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z5 | ML | 43601 | 43607 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0642 | Check fixation of chassis under marble clading for façade between axis(1-7)&(0-A) for area (Z5) From Ground to first Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z5 | ML | 43612 | 43617 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0643 | Check fixation of chassis under marble clading for façade between axis(12-18)&(A-F) for area (Z1) From Ground to first Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z1 | ML | 43612 | 43617 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0644 | Check fixation of chassis under marble clading for façade between axis(0-1)&(F-L) for area (Z4) From Ground to first Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z4 | ML | 43612 | 43617 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0645 | Check first cours of blockwork between axes (6-13)&(F-L) at roof floor (344.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | RF | 43629 | 43635 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0646 | Full Height of blockwork between axes (6-9)&(E-L) at seventh floor(328.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 7th | 43629 | 43635 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0647 | Check Surface Prepration and dots and accessories for plaster works between axes (6-9)&(E-L) at seventh floor(328.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 7th | 43629 | 43635 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0648 | Check for Final Plaster between axes (A-F)&(13-18) at third floor(312.10) for area (Z1) as Per Attached Sketch. | ARCH | Final Plaster | Z1 | 3rd | 43629 | 43635 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0649 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(7-12)&(F-L) for area (Z3) From second to nineth Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z3 | ML | 43629 | 43635 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0650 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(12-18)&(A-E) for area (Z1) From second toFIFTH Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z1 | ML | 43629 | 43635 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0651 | Check fixation of chassis under marble clading for façade between axis(6-9)&(K-L) for area (Z3) From ground to nineth Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z3 | ML | 43629 | 43635 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0652 | Check fixation of chassis under marble clading for façade between axis(18-12)&(F-L) for area (Z2) From ground to FIRST Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z2 | ML | 43629 | 43635 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0653 | Check Surface Prepration and dots and accessories for plaster works between axes (1-7)&(E-L) at first floor(304.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 1st | 43631 | 43635 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0654 | Check Surface Prepration and dots and accessories for plaster works between axes (1-7)&(A-F) at first floor(304.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | 1st | 43631 | 43635 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0655 | Check Surface Prepration and dots and accessories for plaster works between axes (1-7)&(E-L) at second floor(308.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 2nd | 43631 | 43635 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0656 | Check Surface Prepration and dots and accessories for plaster works between axes (1-7)&(A-F) at second floor(308.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | 2nd | 43631 | 43635 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0657 | Check Surface Prepration and dots and accessories for plaster works between axes (10-13)&(F-L) at sixth floor(324.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 6th | 43633 | 43638 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0658 | Check Surface Prepration and dots for ceramic tiles between axes (10-11)&(G-K) at first floor(304.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 1st | 43633 | 43638 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0659 | Check Surface Prepration and dots for ceramic tiles between axes (10-11)&(G-K) at second floor(308.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 2nd | 43633 | 43638 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0660 | Check Surface Prepration and dots for ceramic tiles between axes (10-11)&(G-K) at third floor(312.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 3rd | 43633 | 43638 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0661 | Check for Final Plaster between axes (F-L)&(12-18) at sixth floor(324.10) for area (Z2) as Per Attached Sketch. | ARCH | Final Plaster | Z2 | 6th | 43633 | 43638 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0662 | Check fixation of chassis under marble clading for façade between axis(7-12)&(E-L) for area (Z3) From ground to nineth Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z3 | ML | 43633 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0663 | First course of blockwork between axes(7-9)&(E-L) at eighth floor ( 333.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | 8th | 43640 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0664 | Full Height of blockwork between axes (7-9)&(E-L) at eighth floor(333.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 8th | 43640 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0665 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(7-9) at eighth floor(333.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 8th | 43640 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0666 | Full Height of blockwork between axes (7-9)&(E-L) at nineth floor(338.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 9th | 43640 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0667 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(7-9) at nineth floor(338.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 9th | 43640 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0668 | Check Surface Prepration and dots for ceramic tiles between axes (7-9)&(J-K) at third floor(338.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 9th | 43640 | 43645 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0669 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(1-7) at third floor(312.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 3rd | 43641 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0670 | Check Surface Prepration and dots and accessories for plaster works between axes (A-F)&(1-6) at third floor(312.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | 3rd | 43641 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0671 | check cement based waterproof coating for toilets between axes (F-H)&(5-2) at first floor (304.10)for area (z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 1st | 43645 | 43666 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0672 | check cement based waterproof coating for toilets between axes (F-H)&(5-2) at second floor (308.10)for area (z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 2nd | 43645 | 43666 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0673 | check cement based waterproof coating for toilets between axes (F-H)&(14-17) at first floor (304.10)for area (z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 1st | 43645 | 43648 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0674 | check cement based waterproof coating for toilets between axes (F-H)&(14-17) at second floor (308.10)for area (z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 2nd | 43646 | 43648 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0675 | Check fixation of chassis under marble clading for façade between axis(13-14)&(B-F) for area (Z1) From second to fifth Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z1 | ML | 43646 | 43653 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0676 | Check fixation of rockwool under marbel clading for façade between axis (12-18)&(F-L) from ground to second Floor zone(z2)as per attached sketch. | ARCH | Marble Rockwool | Z2 | ML | 43646 | 43661 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0677 | Check fixation of rockwool under marbel clading for façade between axis (14-17)&(K-L) from second to seventh Floor zone(z2)as per attached sketch | ARCH | Marble Rockwool | Z2 | ML | 43646 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0678 | Check fixation of rockwool under marbel clading for façade between axis (5-6)&(B-E) from second to fifth Floor zone(z5)as per attached sketch | ARCH | Marble Rockwool | Z5 | ML | 43646 | 43659 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0679 | Check fixation of rockwool under marbel clading for façade between axis (2-5)&(A-B) from second to fifth Floor zone(z5)as per attached sketch | ARCH | Marble Rockwool | Z5 | ML | 43646 | 43659 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0680 | Check fixation of rockwool under marbel clading for façade between axis (1-2)&(B-E) from second to fifth Floor zone(z5)as per attached sketch | ARCH | Marble Rockwool | Z5 | ML | 43646 | 43659 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0681 | Check fixation of rockwool under marbel clading for façade between axis (1-7)&(R-L) from first to seventh Floor zone(4)as per attached sketch | ARCH | Marble Rockwool | Z4 | ML | 43646 | 43659 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0682 | Check fixation of rockwool under marbel clading for façade between axis (1-2)&(E-L) from ground to second Floor zone(z4)as per attached sketch | ARCH | Marble Rockwool | Z4 | ML | 43646 | 43659 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0683 | Check fixation of rockwool under marbel clading for façade between axis (6-7)&(A-E) from ground to second Floor zone(z5)as per attached sketch | ARCH | Marble Rockwool | Z5 | ML | 43646 | 43659 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0684 | Check fixation of rockwool under marbel clading for façade between axis (1-7)&(A-E) from ground to second Floor zone(z5)as per attached sketch | ARCH | Marble Rockwool | Z5 | ML | 43646 | 43659 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0685 | Check fixation of rockwool under marbel clading for façade between axis (12-13)&(A-E) from ground to second Floor zone(z1)as per attached sketch. | ARCH | Marble Rockwool | Z1 | ML | 43646 | 43647 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0686 | Check fixation of rockwool under marbel clading for façade between axis (12-13)&(A-E) from ground to second Floor zone(z1)as per attached sketch. | ARCH | Marble Rockwool | Z1 | ML | 43646 | 43647 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0687 | Check fixation of rockwool under marbel clading for façade between axis (12-13)&(A-E) from ground to second Floor zone(z1)as per attached sketch. | ARCH | Marble Rockwool | Z1 | ML | 43646 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0688 | Check Surface Prepration and dots for ceramic tiles between axes (10-11)&(G-R) at sixth floor(324.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 6th | 43646 | 43653 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0689 | Check Surface Prepration and dots for ceramic tiles between axes (10-11)&(G-R) at fifth floor(320.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 5th | 43646 | 43648 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0690 | Check Surface Prepration and dots for ceramic tiles between axes (10-11)&(G-R) at fourth floor(324.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 4th | 43646 | 43653 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0691 | check fixation for chassis of aqua panel between (1-6) & (E-L) &(z4) at roof floor level (333.10) . | ARCH | Aqua Panel (Chassis) | Z4 | RF | 43647 | 43653 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0692 | water test for the toilet AT FIRST FLOOR level (304.10) between axis (F-H)&(17-14) for area (Z2) As Per Attached Sketch. | ARCH | Water Test | Z2 | 1st | 43648 | 43653 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0693 | water test for the BATH ROOM AT SECOND FLOOR level (308.10) between axis (F-H)&(17-14) for area (Z2) As Per Attached Sketch. | ARCH | Water Test | Z2 | 2nd | 43648 | 43653 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0694 | water test for the toilet AT FIRST FLOOR level (304.10) between axis (F-H)&(2-5) for area (Z4) As Per Attached Sketch. | ARCH | Water Test | Z4 | 1st | 43648 | 43666 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0695 | water test for the BATH ROOM AT SECOND FLOOR level (308.10) between axis (F-H)&(2-5) for area (Z4) As Per Attached Sketch. | ARCH | Water Test | Z4 | 2nd | 43648 | 43666 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0696 | THIRD primer coat for façade between axes (1-7)&(A-F) for area (Z5) From ground to SECOND Floor as Per Attached Sketch.. | ARCH | Water Proofing Façade | Z5 | ML | 43648 | 43666 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0697 | THIRD primer coat for façade between axes (12-18)&(A-F) for area (Z1) From ground to SECOND Floor as Per Attached Sketch.. | ARCH | Water Proofing Façade | Z1 | ML | 43648 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0698 | THIRD primer coat for façade between axes (12-18)&(L-F) for area (Z2) From ground to SECOND Floor as Per Attached Sketch.. | ARCH | Water Proofing Façade | Z2 | ML | 43648 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0699 | THIRD primer coat for façade between axes (1-7)&(L-F) for area (Z4) From ground to SECOND Floor as Per Attached Sketch.. | ARCH | Water Proofing Façade | Z4 | ML | 43648 | 43666 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0700 | THIRD primer coat for façade between axes (1-7)&(L-F) for area (Z4) From SECOND to SEVENTH Floor as Per Attached Sketch.. | ARCH | Water Proofing Façade | Z4 | ML | 43648 | 43666 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0701 | THERD primer coat for façade between axes (12-18)&(L-F) for area (Z2) From SECOND to SEVENTH Floor as Per Attached Sketch.. | ARCH | Water Proofing Façade | Z2 | ML | 43648 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0702 | THIRD primer coat for façade between axes (12-18)&(A-F) for area (Z1) From SECOND to FIFTH Floor as Per Attached Sketch.. | ARCH | Water Proofing Façade | Z1 | ML | 43648 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0703 | THIRD primer coat for façade between axes (1-7)&(A-F) for area (Z5) From SECOND to FIFTH Floor as Per Attached Sketch.. | ARCH | Water Proofing Façade | Z5 | ML | 43648 | 43666 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0704 | Check fixation and installation for marbel between axis(1-6)&(K-L) for area (Z4) From ground to first Floor as Per Attached Sketch. | ARCH | Marble Façade | Z4 | ML | 43653 | 43673 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0705 | Check fixation and installation for marbel between axis(1-6)&(K-L) for area (Z4) From second to seventh Floor as Per Attached Sketch. | ARCH | Marble Façade | Z4 | ML | 43653 | 43682 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0706 | Check fixation and installation for marbel between axis(1-2)&(L-F) for area (Z4) From ground to first Floor as Per Attached Sketch. | ARCH | Marble Façade | Z4 | ML | 43653 | 43673 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0707 | Check fixation and installation for marbel between axis(1-2)&(L-F) for area (Z4) From second to seventh Floor as Per Attached Sketch. | ARCH | Marble Façade | Z4 | ML | 43653 | 43699 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0708 | Check fixation and installation for marbel between axis(1-6)&(A-B) for area (Z5) From ground to first Floor as Per Attached Sketch. | ARCH | Marble Façade | Z5 | ML | 43653 | 43673 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0709 | Check fixation and installation for marbel between axis(1-6)&(A-B) for area (Z5) From second to fifth Floor as Per Attached Sketch. | ARCH | Marble Façade | Z5 | ML | 43653 | 43699 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0710 | Check fixation and installation for marbel between axis(0-1)&(A-F) for area (Z5) From ground to first Floor as Per Attached Sketch. | ARCH | Marble Façade | Z5 | ML | 43653 | 43673 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0711 | Check fixation and installation for marbel between axis(0-1)&(A-F) for area (Z5) From second to fifth Floor as Per Attached Sketch. | ARCH | Marble Façade | Z5 | ML | 43653 | 43699 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0712 | Check fixation and installation for marbel between axis(5-7)&(A-F) for area (Z5) From ground to Second Floor as Per Attached Sketch. | ARCH | Marble Façade | Z5 | ML | 43653 | 43673 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0713 | Check fixation and installation for marbel between axis(5-7)&(A-F) for area (Z5) From second to fifth Floor as Per Attached Sketch. | ARCH | Marble Façade | Z5 | ML | 43653 | 43699 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0714 | Check fixation and installation for marbel between axis(12-18)&(A-B) for area (Z1) From ground to first Floor as Per Attached Sketch. | ARCH | Marble Façade | Z1 | ML | 43653 | 43673 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0715 | Check fixation and installation for marbel between axis(12-18)&(A-B) for area (Z1) From second to fifth Floor as Per Attached Sketch. | ARCH | Marble Façade | Z1 | ML | 43653 | 43699 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0716 | Check fixation and installation for marbel between axis(17-18)&(A-F) for area (Z1) From ground to first Floor as Per Attached Sketch. | ARCH | Marble Façade | Z1 | ML | 43653 | 43673 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0717 | Check fixation and installation for marbel between axis(17-18)&(A-F) for area (Z1) From second to fifth Floor as Per Attached Sketch. | ARCH | Marble Façade | Z1 | ML | 43653 | 43699 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0718 | Check fixation and installation for marbel between axis(12-14)&(A-F) for area (Z1) From ground to Second Floor as Per Attached Sketch. | ARCH | Marble Façade | Z1 | ML | 43653 | 43673 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0719 | Check fixation and installation for marbel between axis(12-14)&(A-F) for area (Z1) From second to fifth Floor as Per Attached Sketch. | ARCH | Marble Façade | Z1 | ML | 43653 | 43699 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0720 | Check fixation and installation for marbel between axis(12-18)&(K-L) for area (Z2) From ground to first (Second) Floor as Per Attached Sketch. | ARCH | Marble Façade | Z2 | ML | 43653 | 43673 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0721 | Check fixation and installation for marbel between axis(12-18)&(K-L) for area (Z2) From second to seventh Floor as Per Attached Sketch. | ARCH | Marble Façade | Z2 | ML | 43653 | 43699 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0722 | Check fixation and installation for marbel between axis(17-18)&(L-F) for area (Z2) From ground to first Floor as Per Attached Sketch. | ARCH | Marble Façade | Z2 | ML | 43653 | 43673 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0723 | Check fixation and installation for marbel between axis(17-18)&(L-F) for area (Z2) From second to seventh Floor as Per Attached Sketch. | ARCH | Marble Façade | Z2 | ML | 43653 | 43699 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0724 | Second Coat of approved Putty For Painting For FIRST FLOOR (304.10) at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z1 | 1st | 43654 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0725 | Second Coat of approved Putty For Painting For FIRST FLOOR (304.10) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z2 | 1st | 43654 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0726 | Second Coat of approved Putty For Painting For FIRST FLOOR (304.10) at Zone(3A) axes (E-L) &(10-13) as Per Attached Sketch. | ARCH | Painting second Putty | Z3 | 1st | 43654 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0727 | Second Coat of approved Putty For Painting For FIRST FLOOR (304.10) at Zone(3B) axes (E-L) &(6-9) as Per Attached Sketch. | ARCH | Painting second Putty | Z3B | 1st | 43654 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0728 | Second Coat of approved Putty For Painting For FIRST FLOOR (304.10) at Zone(4) axes (E-L) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z4 | 1st | 43654 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0729 | Second Coat of approved Putty For Painting For FIRST FLOOR (304.10) at Zone(5) axes (A-F) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z5 | 1st | 43654 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0730 | Second Coat of approved Putty For Painting For SECOND FLOOR (308.10) at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z1 | 2nd | 43654 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0731 | Second Coat of approved Putty For Painting For SECOND FLOOR (308.10) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z2 | 2nd | 43654 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0732 | Second Coat of approved Putty For Painting For SECOND FLOOR (308.10) at Zone(3A) axes (E-L) &(10-13) as Per Attached Sketch. | ARCH | Painting second Putty | Z3A | 2nd | 43654 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0733 | Second Coat of approved Putty For Painting For SECOND FLOOR (308.10) at Zone(3B) axes (E-L) &(6-9) as Per Attached Sketch. | ARCH | Painting second Putty | Z3B | 2nd | 43654 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0734 | Second Coat of approved Putty For Painting For SECOND FLOOR (308.10) at Zone(4) axes (E-L) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z4 | 2nd | 43654 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0735 | Second Coat of approved Putty For Painting For SECOND FLOOR (308.10) at Zone(5) axes (A-F) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z5 | 2nd | 43654 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0736 | Second Coat of approved Putty For Painting For THIRD FLOOR (312.10) at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z1 | 3rd | 43655 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0737 | Second Coat of approved Putty For Painting For THIRD FLOOR (312.10) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z2 | 3rd | 43655 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0738 | Second Coat of approved Putty For Painting For THIRD FLOOR (312.10) at Zone(3A) axes (E-L) &(10-13) as Per Attached Sketch. | ARCH | Painting second Putty | Z3A | 3rd | 43655 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0739 | Second Coat of approved Putty For Painting For THIRD FLOOR (312.10) at Zone(3B) axes (E-L) &(6-9) as Per Attached Sketch. | ARCH | Painting second Putty | Z3B | 3rd | 43655 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0740 | Second Coat of approved Putty For Painting For THIRD FLOOR (312.10) at Zone(4) axes (E-L) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z4 | 3rd | 43655 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0741 | Second Coat of approved Putty For Painting For THIRD FLOOR (312.10) at Zone(5) axes (A-F) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z5 | 3rd | 43655 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0742 | Second Coat of approved Putty For Painting For FOURTH FLOOR (316.10) at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z1 | 4th | 43655 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0743 | Second Coat of approved Putty For Painting For FOURTH FLOOR (316.10) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z2 | 4th | 43655 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0744 | Second Coat of approved Putty For Painting For FOURTH FLOOR (316.10) at Zone(3A) axes (E-L) &(10-13) as Per Attached Sketch. | ARCH | Painting second Putty | Z3A | 4th | 43655 | 43659 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0745 | Second Coat of approved Putty For Painting For FOURTH FLOOR (316.10) at Zone(3B) axes (E-L) &(6-9) as Per Attached Sketch. | ARCH | Painting second Putty | Z3B | 4th | 43655 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0746 | Second Coat of approved Putty For Painting For FOURTH FLOOR (316.10) at Zone(4) axes (E-L) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z4 | 4th | 43655 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0747 | Second Coat of approved Putty For Painting For FOURTH FLOOR (316.10) at Zone(5) axes (A-F) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z5 | 4th | 43655 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0748 | Check fixation and installation for Terrazo Tiles between axis(5-6)&(B-E) for area (Z5) at upper roof Floor as Per Attached Sketch. | ARCH | Terrazo Upper roof | Z5 | 6th | 43655 | 43666 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0749 | Check fixation and installation for Terrazo Tiles between axis(2-5)&(G-K) for area (Z4) at upper roof Floor as Per Attached Sketch. | ARCH | Terrazo Upper roof | Z4 | 8th | 43655 | 43666 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0750 | Check fixation and installation for Terrazo Tiles between axis(14-17)&(G-K) for area (Z2) at upper roof Floor as Per Attached Sketch. | ARCH | Terrazo Upper roof | Z2 | 8th | 43655 | 43666 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0751 | Check fixation and installation for Terrazo Tiles between axis(15-16)&(B-E) for area (Z1) at upper roof Floor as Per Attached Sketch. | ARCH | Terrazo Upper roof | Z1 | 6th | 43655 | 43666 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0752 | water test for the BATH ROOM AT Third FLOOR level (312.10) between axis (F-H)&(17-14) for area (Z2) As Per Attached Sketch. | ARCH | Water Test | Z2 | 3rd | 43656 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0753 | check cement based waterproof coating for toilets between axes (F-H)&(14-17) at Third floor (312.10)for area (z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 3rd | 43656 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0754 | Check for Final Plaster between axes (10-13)&(E-L) at First floor(304.10) for area (Z3) as Per Attached Sketch. | ARCH | Final Plaster | Z3 | 1st | 43656 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0755 | Check for Final Plaster between axes (10-13)&(E-L) at Second floor(308.10) for area (Z3) as Per Attached Sketch. | ARCH | Final Plaster | Z3 | 2nd | 43656 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0756 | Check for Final Plaster between axes (10-13)&(E-L) at Third floor(312.10) for area (Z3) as Per Attached Sketch. | ARCH | Final Plaster | Z3 | 3rd | 43656 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0757 | Check for Final Plaster between axes (14-17)&(A-E) at Sixth floor(324.10) for area (Z1) as Per Attached Sketch. | ARCH | Final Plaster | Z1 | 6th | 43656 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0758 | Check for Final Plaster between axes (12-18)&(E-L) at Fifth floor(320.10) for area (Z2) as Per Attached Sketch. | ARCH | Final Plaster | Z2 | 5th | 43656 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0759 | Check for Final Plaster between axes (13-18)&(E-L) at Fifth floor(320.10) for area (Z1) as Per Attached Sketch. | ARCH | Final Plaster | Z1 | 5th | 43656 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0760 | Check Surface Prepration and dots and accessories for plaster works between axes (12-18)&(A-F) at GROUND floor(300.10) for area (Z1) as Per Attached Sketch. | ARCH | Plaster Dots | Z1 | GF | 43656 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0761 | Check Surface Prepration and dots and accessories for plaster works between axes (12-18)&(E-L) at GROUND floor(300.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | GF | 43656 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0762 | Full Height of blockwork between axes (12-18)&(E-L) at ground floor(300.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | GF | 43656 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0763 | Full Height of blockwork between axes (1-7)&(F-G) from sixth to seventh floor for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | ML | 43656 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0764 | Full Height of blockwork between axes (12-18)&(F-L) from sixth to seventh floor for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | ML | 43656 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0765 | Check fixation of chassis under marble clading for façade between axis(12-18)&(B-F) for area (Z1) From second to fifth Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z1 | ML | 43656 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0766 | Check Surface Prepration and dots and accessories for plaster works between axes (1-6)&(A-F) at FOURTH floor(316.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | 4th | 43656 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0767 | Check Surface Prepration and dots and accessories for plaster works between axes (1-6)&(L-F) at FOURTH floor(316.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 4th | 43656 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0768 | Check first cours of blockwork between axes (1-7)&(E-L) at ground floor(300.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork First course | Z4 | GF | 43657 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0769 | Check first cours of blockwork between axes (1-7)&(A-F) at ground floor(300.10) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork First course | Z5 | GF | 43657 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0770 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(1-7) at Ground floor(300.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | GF | 43657 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0771 | Check Surface Prepration and dots and accessories for plaster works between axes (A-F)&(1-7) at Ground floor(300.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | GF | 43657 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0772 | Full Height of blockwork between axes (1-7)&(E-L) at ground floor(300.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | GF | 43657 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0773 | Full Height of blockwork between axes (1-7)&(A-F) at ground floor(300.10) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | GF | 43657 | 43666 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0774 | Check Surface Prepration and dots for plaster works between axes (10-13)&(H-L) at EIGHTH floor(333.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 8th | 43666 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0775 | Full Height of blockwork between axes (10-13)&(E-L) at Seventh floor(328.10) for area (Z3A) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3A | 7th | 43667 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0776 | Full Height of blockwork between axes (12-18)&(F-L) at Seventh floor(328.10) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | 7th | 43667 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0777 | Full Height of blockwork between axes (8-13)&(E-L) at Eighth floor(333.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 8th | 43667 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0778 | Full Height of blockwork between axes (8-13)&(E-L) at Nineth floor(338.10) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 9th | 43667 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0779 | Check Surface Prepration and dots for plaster works between axes (12-18)&(F-L) at Seventh floor(328.10) for area (Z2) as Per Attached Sketch. | ARCH | Plaster Dots | Z2 | 7th | 43667 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0780 | Check Surface Prepration and dots for plaster works between axes (7-13)&(E-L) at Seventh floor(328.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 7th | 43667 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0781 | Check Surface Prepration and dots for plaster works between axes (1-7)&(F-L) at Seventh floor(328.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 7th | 43667 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0782 | Check Surface Prepration and dots for plaster works between axes (7-13)&(E-L) at Eighth floor(333.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 8th | 43667 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0783 | Check Surface Prepration and dots for plaster works between axes (7-13)&(E-L) at Nineth floor(338.10) for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | 9th | 43667 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0784 | Second Coat of approved Putty For Painting For Walls & columns of First Basement (295.60) at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z1 | B1 | 43667 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0785 | Surface Prepration and Release Painting For Walls & columns of First Basement (295.60) at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Plaster Dots | Z1 | B1 | 43667 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0786 | Full Height façade only of blockwork between axes (12-18)&(E-F) for area (Z1) From Ground to Nineth Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | ML | 43668 | 43702 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0787 | Full Height façade only of blockwork between axes (12-18)&(E-L) for area (Z2) From Ground to Nineth Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z2 | ML | 43668 | 43695 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0788 | Full Height façade only of blockwork between axes (1-7)&(E-L) for area (Z4) From Ground to Nineth Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | ML | 43668 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0789 | Full Height façade only of blockwork between axes (1-7)&(A-F) for area (Z5) From Ground to Nineth Floor as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | ML | 43668 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0790 | Check for Final Plaster between axes (E-L)&(6-9) at first floor(304.10) for area (Z3B) as Per Attached Sketch. | ARCH | Final Plaster | Z3B | 1st | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0791 | Check for Final Plaster between axes (E-L)&(1-7) at first floor(304.10) for area (Z4) as Per Attached Sketch. | ARCH | Final Plaster | Z4 | 1st | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0792 | Check for Final Plaster between axes (A-F)&(1-7) at first floor(304.10) for area (Z5) as Per Attached Sketch. | ARCH | Final Plaster | Z5 | 1st | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0793 | Check for Final Plaster between axes (E-L)&(6-9) at second floor(308.10) for area (Z3B) as Per Attached Sketch. | ARCH | Final Plaster | Z3B | 2nd | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0794 | Check for Final Plaster between axes (E-L)&(1-7) at second floor(308.10) for area (Z4) as Per Attached Sketch. | ARCH | Final Plaster | Z4 | 2nd | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0795 | Check for Final Plaster between axes (A-F)&(1-6) at second floor(308.10) for area (Z5) as Per Attached Sketch. | ARCH | Final Plaster | Z5 | 2nd | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0796 | Check for Final Plaster between axes (E-L)&(6-9) at Third floor(312.10) for area (Z3B) as Per Attached Sketch. | ARCH | Final Plaster | Z3B | 3rd | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0797 | Check for Final Plaster between axes (E-L)&(10-13) at Fourth floor(316.10) for area (Z3A) as Per Attached Sketch. | ARCH | Final Plaster | Z3A | 4th | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0798 | Check for Final Plaster between axes (E-L)&(6-9) at Fourth floor(316.10) for area (Z3B) as Per Attached Sketch. | ARCH | Final Plaster | Z3B | 4th | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0799 | Check for Final Plaster between axes (E-L)&(1-7) at Fourth floor(316.10) for area (Z4) as Per Attached Sketch. | ARCH | Final Plaster | Z4 | 4th | 43670 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0800 | Check for Final Plaster between axes (A-F)&(1-6) at Fourth floor(316.10) for area (Z5) as Per Attached Sketch. | ARCH | Final Plaster | Z5 | 4th | 43670 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0801 | Check for Final Plaster between axes (E-L)&(1-7) at Third floor(312.10) for area (Z4) as Per Attached Sketch. | ARCH | Final Plaster | Z4 | 3rd | 43670 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0802 | Check for Final Plaster between axes (A-F)&(1-6) at Third floor(312.10) for area (Z5) as Per Attached Sketch. | ARCH | Final Plaster | Z5 | 3rd | 43670 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0803 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(6-9) at Fifth floor(320.10) for area (Z3B) as Per Attached Sketch. | ARCH | Plaster Dots | Z3B | 5th | 43670 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0804 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(1-7) at Fifth floor(320.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 5th | 43670 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0805 | Check Surface Prepration and dots and accessories for plaster works between axes (A-F)&(1-6) at Fifth floor(320.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | 5th | 43670 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0806 | Check for Final Plaster between axes (A-F)&(1-6) at fifth floor(320.10) for area (Z5) as Per Attached Sketch. | ARCH | Final Plaster | Z5 | 5th | 43673 | 43680 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0807 | Check for Final Plaster between axes (F-L)&(1-7) at fifth floor(320.10) for area (Z4) as Per Attached Sketch. | ARCH | Final Plaster | Z4 | 5th | 43673 | 43680 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0808 | Check for Final Plaster between axes (F-L)&(6-13) at fifth floor(320.10) for area (Z3) as Per Attached Sketch. | ARCH | Final Plaster | Z3 | 5th | 43673 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0809 | Check Surface Prepration and dots and accessories for plaster works between axes (F-L)&(1-7) at sixth floor(324.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | 6th | 43673 | 43681 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0810 | Check Surface Prepration and dots and accessories for plaster works between axes (A-E)&(2-5) at sixth floor(324.10) for area (Z5) as Per Attached Sketch. | ARCH | Plaster Dots | Z5 | 6th | 43673 | 43680 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0811 | Check for Final Plaster between axes (G-K)&(14-17) at EIGHTH floor(333.10) for area (Z2) as Per Attached Sketch. | ARCH | Final Plaster | Z2 | 8th | 43673 | 43702 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0812 | Check for Final Plaster between axes (G-K)&(2-5) at EIGHTH floor(333.10) for area (Z4) as Per Attached Sketch. | ARCH | Final Plaster | Z4 | 8th | 43673 | 43680 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0813 | Check for Final Plaster between axes (12-18)&(F-L) at Seventh floor(328.10) for area (Z2) as Per Attached Sketch. | ARCH | Final Plaster | Z2 | 7th | 43675 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0814 | Check for Final Plaster between axes (7-13)&(E-L) at Seventh floor(328.10) for area (Z3) as Per Attached Sketch. | ARCH | Final Plaster | Z3 | 7th | 43675 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0815 | Check for Final Plaster between axes (1-7)&(F-L) at Seventh floor(328.10) for area (Z4) as Per Attached Sketch. | ARCH | Final Plaster | Z4 | 7th | 43675 | 43681 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0816 | Check Surface Prepration and dots for ceramic tiles between axes (6-9)&(F-L) at SECOND floor(308.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 2nd | 43675 | 43681 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0817 | Check Surface Prepration and dots for ceramic tiles between axes (10-12)&(F-L) at SECOND floor(308.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 2nd | 43675 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0818 | Check Surface Prepration and dots for ceramic tiles between axes (10-12)&(J-L) at THIRD floor(312.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 3rd | 43675 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0819 | Check Surface Prepration and dots for ceramic tiles between axes (10-12)&(J-L) at FOURTH floor(316.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 4th | 43675 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0820 | Check Surface Prepration and dots for ceramic tiles between axes (10-12)&(J-L) at FIFTH floor(320.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 5th | 43675 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0821 | Check Surface Prepration and dots for ceramic tiles between axes (10-12)&(F-L) at SIXTH floor(324.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 6th | 43675 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0822 | Check Surface Prepration and dots for ceramic tiles between axes (10-12)&(F-L) at SEVENTH floor(328.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 7th | 43675 | 43695 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0823 | Check Surface Prepration and dots for ceramic tiles between axes (10-12)&(J-L) at EIGHTH floor(333.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 8th | 43675 | 43695 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0824 | Check Surface Prepration and dots for ceramic tiles between axes (7-9)&(J-K) at EIGHTH floor(333.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 8th | 43675 | 43681 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0825 | Check Surface Prepration and dots for ceramic tiles between axes (8-12)&(J-L) at NINETH floor(338.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 9th | 43675 | 43695 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0826 | First primer coat for façade between axes(12-9)&(E-L) for area (Z3) From ground to nineth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z3 | ML | 43676 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0827 | SECOND primer coat for façade between axes (12-9)&(E-L) for area (Z3) From ground to nineth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z3 | ML | 43676 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0828 | THIRD primer coat for façade between axes (12-6)&(E-L) for area (Z3) From ground to nineth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z3 | ML | 43676 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0829 | Check fixation of chassis under marble clading for façade between axis(6-13)&(E-L) for area (Z3) From ground to nineth Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z3 | ML | 43678 | 43695 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0830 | First primer coat for façade between axes(12-18)&(A-F) for area (Z1) From ground to fifth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43678 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0831 | SECOND primer coat for façade between axes (12-18)&(A-F) for area (Z1) From ground to fifth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43678 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0832 | THIRD primer coat for façade between axes(12-18)&(A-F) for area (Z1) From ground to fifth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z1 | ML | 43678 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0833 | Check fixation of chassis under marble clading for façade between axis(12-18)&(A-F) for area (Z1) From ground to fifth Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z1 | ML | 43678 | 43695 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0834 | First primer coat for façade between axes(12-18)&(F-L) for area (Z2) From ground to seventh Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43678 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0835 | SECOND primer coat for façade between axes(12-18)&(F-L) for area (Z2) From ground to seventh Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43678 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0836 | THIRD primer coat for façade between axes(12-18)&(F-L) for area (Z2) From ground to seventh Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43678 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0837 | Check fixation of chassis under marble clading for façade between axis(12-18)&(F-L) for area (Z2) From ground to seventh Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z2 | ML | 43678 | 43695 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0838 | First primer coat for façade between axes (1-7)&(F-L) for area (Z4) From ground to seventh Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z4 | ML | 43678 | 43698 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0839 | SECOND primer coat for façade between axes (1-7)&(F-L) for area (Z4) From ground to seventh Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z4 | ML | 43678 | 43698 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0840 | THIRD primer coat for façade between axes (1-7)&(F-L) for area (Z4) From ground to seventh Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z4 | ML | 43678 | 43698 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0841 | Check fixation of chassis under marble clading for façade between axis (1-7)&(F-L) for area (Z4) From ground to seventh Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z4 | ML | 43678 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0842 | First primer coat for façade between axes(1-7)&(A-F) for area (Z5) From ground to fifth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z5 | ML | 43678 | 43698 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0843 | SECOND primer coat for façade between axes(1-7)&(A-F) for area (Z5) From ground to fifth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z5 | ML | 43678 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0844 | THIRD primer coat for façade between axes(1-7)&(A-F) for area (Z5) From ground to fifth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z5 | ML | 43678 | 43698 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0845 | Check fixation of chassis under marble clading for façade between axes(1-7)&(A-F) for area (Z5) From ground to fifth Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z5 | ML | 43678 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0846 | check fixation for chassis of aqua panel between (13-18) & (A-F) (Z1) at roof floor level (324.10) . | ARCH | Aqua Panel (Chassis) | Z1 | RF | 43684 | 43702 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0847 | check fixation for chassis of aqua panel between (1-7) & (A-F) (Z5) at roof floor level (324.10) . | ARCH | Aqua Panel (Chassis) | Z5 | RF | 43684 | 43702 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0848 | check fixation for chassis of aqua panel between (13-18) & (F-L) (Z2) at roof floor level (333.10) . | ARCH | Aqua Panel (Chassis) | Z2 | RF | 43684 | 43702 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0849 | Check for Final Plaster between axes (A-F)&(1-6) at sixth floor(324.10) for area (Z5) as Per Attached Sketch. | ARCH | Final Plaster | Z5 | 6th | 43698 | 43709 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0850 | Check for Final Plaster between axes (F-L)&(1-7) at sixth floor(324.10) for area (Z4) as Per Attached Sketch. | ARCH | Final Plaster | Z4 | 6th | 43698 | 43709 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0851 | Check for Final Plaster between axes (F-L)&(6-13) at sixth floor(324.10) for area (Z3) as Per Attached Sketch. | ARCH | Final Plaster | Z3 | 6th | 43698 | 43711 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0852 | Check for Final Plaster between axes (F-L)&(6-13) at eighth floor(333.10) for area (Z3) as Per Attached Sketch. | ARCH | Final Plaster | Z3 | 8th | 43698 | 43711 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0853 | Check for Final Plaster between axes (F-L)&(6-13) at ninth floor(338.10) for area (Z3) as Per Attached Sketch. | ARCH | Final Plaster | Z3 | 9th | 43698 | 43711 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0854 | Check fixation and installation of geotextile sheet for exterior underground sanitary for subsurface drainage as Per Attached Sketch. | ARCH | Subsurface Drainage |  | EX | 43699 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0855 | Check Surface Prepration and dots for ceramic tiles between axes (9-10)&(G-K) at NINETH floor(338.10) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Dots | Z3 | 9th | 43709 | 43713 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0856 | Check Surface Prepration and dots for ceramic tiles between axes (14-17)&(F-H) at GROUND floor(300.10) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Dots | Z2 | GF | 43710 | 43719 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0857 | Check Surface Prepration and dots for ceramic tiles between axes (2-5)&(F-H) at ground floor(300.10) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Dots | Z4 | GF | 43710 | 43725 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0858 | Check fixation for curtin wall glass between axis(12-18)&(A-E) for area (Z1) From ground to first Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z1 | ML | 43716 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0859 | Check fixation for curtin wall glass between axis(12-18)&(A-E) for area (Z1) From second to Fifth Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z1 | ML | 43716 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0860 | Check fixation for curtin wall glass between axis(13-18)&(G-L) for area (Z2) From ground to first Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z2 | ML | 43716 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0861 | Check fixation for curtin wall glass between axis(14-18)&(G-L) for area (Z2) From second to seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z2 | ML | 43716 | 43736 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0862 | Check fixation for curtin wall glass between axis(1-6)&(G-L) for area (Z4) From ground to first Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z4 | ML | 43716 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0863 | Check fixation for curtin wall glass between axis(1-6)&(G-L) for area (Z4) From second to seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z4 | ML | 43716 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0864 | Check fixation for curtin wall glass between axis(1-7)&(A-E) for area (Z5) at ground and first Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z5 | ML | 43716 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0865 | Check fixation for curtin wall glass between axis(1-6)&(A-E) for area (Z5) From second to fifth Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z5 | ML | 43716 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0866 | Check fixation for ceramic tiles for flooring and skerting at first floor between axis(12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Porcelain | Z1 | 1st | 43716 | 43719 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0867 | Check fixation for ceramic tiles for flooring and skerting at first floor between axis(12-18)&(E-L) for area (Z2) as Per Attached Sketch. | ARCH | Porcelain | Z2 | 1st | 43716 | 43719 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0868 | Check fixation for ceramic tiles for flooring and skerting at first floor between axis(10-13)&(E-L) for area (Z3-A) as Per Attached Sketch. | ARCH | Porcelain | Z3A | 1st | 43716 | 43719 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0869 | Check fixation for ceramic tiles for flooring and skerting at first floor between axis(6-9)&(E-L) for area (Z3-B) as Per Attached Sketch. | ARCH | Porcelain | Z3B | 1st | 43716 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0870 | Check fixation for ceramic tiles for flooring and skerting at first floor between axis(1-7)&(E-L) for area (Z4) as Per Attached Sketch. | ARCH | Porcelain | Z4 | 1st | 43716 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0871 | Check fixation for ceramic tiles(Porcelain) for flooring and skerting at first floor between axis(1-7)&(A-F) for area (Z5) as Per Attached Sketch. | ARCH | Porcelain | Z5 | 1st | 43716 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0872 | Check fixation for ceramic tiles for flooring and skerting at second floor between axis(12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Porcelain | Z1 | 2nd | 43716 | 43727 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0873 | Check fixation for ceramic tiles for flooring and skerting at second floor between axis(12-18)&(E-L) for area (Z2) as Per Attached Sketch. | ARCH | Porcelain | Z2 | 2nd | 43716 | 43727 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0874 | Check fixation for ceramic tiles for flooring and skerting at second floor between axis(10-13)&(E-L) for area (Z3-A) as Per Attached Sketch. | ARCH | Porcelain | Z3A | 2nd | 43716 | 43727 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0875 | Check fixation for ceramic tiles for flooring and skerting at second floor between axis(6-9)&(E-L) for area (Z3-B) as Per Attached Sketch. | ARCH | Porcelain | Z3B | 2nd | 43716 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0876 | Check fixation for ceramic tiles for flooring and skerting at second floor between axis(1-7)&(E-L) for area (Z4) as Per Attached Sketch. | ARCH | Porcelain | Z4 | 2nd | 43716 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0877 | Check fixation for ceramic tiles(Porcelain) for flooring and skerting at second floor between axis(1-7)&(A-F) for area (Z5) as Per Attached Sketch. | ARCH | Porcelain | Z5 | 2nd | 43716 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0878 | Check Surface Prepration and dots for ceramic tiles between axes (1-6)(D-F) at Second floor(308.10) for area (Z5) as Per Attached Sketch. | ARCH | Ceramic Dots | Z5 | 2nd | 43717 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0879 | Check Surface Prepration and dots for ceramic tiles between axes (13-18)(D-F) at third floor(312.10) for area (Z1) as Per Attached Sketch. | ARCH | Ceramic Dots | Z1 | 3rd | 43717 | 43719 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0880 | Check Surface Prepration and dots for ceramic tiles between axes (14-15)(D-E) at fifth floor(320.10) for area (Z1) as Per Attached Sketch. | ARCH | Ceramic Dots | Z1 | 5th | 43717 | 43719 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0881 | Check Surface Prepration and dots for ceramic tiles between axes (12-14)(J-K) at fourth floor(316.10) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Dots | Z2 | 4th | 43717 | 43719 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0882 | Second Coat of approved Putty For Painting For Walls & columns of First Basement (295.60) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z2 | B1 | 43717 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0883 | Second Coat of approved Putty For Painting For Walls & columns of First Basement (295.60) at Zone(3) axes (E-L) &(6-13) as Per Attached Sketch. | ARCH | Painting second Putty | Z3 | B1 | 43717 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0884 | Second Coat of approved Putty For Painting For Walls & columns of First Basement (295.60) at Zone(4) axes (E-L) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z4 | B1 | 43717 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0885 | Second Coat of approved Putty For Painting For Walls & columns of First Basement (295.60) at Zone(5) axes (A-F) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z5 | B1 | 43717 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0886 | Second Coat of approved Putty For Painting For Walls & columns of second Basement (291.80) at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z1 | B2 | 43717 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0887 | Second Coat of approved Putty For Painting For Walls & columns of second Basement (291.80) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z2 | B2 | 43717 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0888 | Second Coat of approved Putty For Painting For Walls & columns of second Basement (291.80) at Zone(3) axes (E-L) &(6-13) as Per Attached Sketch. | ARCH | Painting second Putty | Z3 | B2 | 43717 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0889 | Second Coat of approved Putty For Painting For Walls & columns of second Basement (291.80) at Zone(4) axes (E-L) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z4 | B2 | 43717 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0890 | Second Coat of approved Putty For Painting For Walls & columns of second Basement (291.80) at Zone(5) axes (A-F) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z5 | B2 | 43717 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0891 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at third floor between axis(12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Porcelain | Z1 | 3rd | 43718 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0892 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at third floor between axis(12-18)&(E-L) for area (Z2) as Per Attached Sketch. | ARCH | Porcelain | Z2 | 3rd | 43718 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0893 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at third floor between axis(10-13)&(E-L) for area (Z3A) as Per Attached Sketch. | ARCH | Porcelain | Z3A | 3rd | 43718 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0894 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at third floor between axis(6-9)&(E-L) for area (Z3B) as Per Attached Sketch. | ARCH | Porcelain | Z3B | 3rd | 43718 | 43731 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0895 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at third floor between axis(1-7)&(E-L) for area (Z4) as Per Attached Sketch. | ARCH | Porcelain | Z4 | 3rd | 43718 | 43731 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0896 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at third floor between axis(1-7)&(A-F) for area (Z5) as Per Attached Sketch. | ARCH | Porcelain | Z5 | 3rd | 43718 | 43731 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0897 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at fourth floor between axis(12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Porcelain | Z1 | 4th | 43718 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0898 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at fourth floor between axis(12-18)&(E-L) for area (Z2) as Per Attached Sketch. | ARCH | Porcelain | Z2 | 4th | 43718 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0899 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at fourth floor between axis(10-13)&(E-L) for area (Z3-A) as Per Attached Sketch. | ARCH | Porcelain | Z3A | 4th | 43718 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0900 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at fourth floor between axis(6-9)&(E-L) for area (Z3-B) as Per Attached Sketch. | ARCH | Porcelain | Z3B | 4th | 43718 | 43731 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0901 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at fourth floor between axis(1-7)&(E-L) for area (Z4) as Per Attached Sketch. | ARCH | Porcelain | Z4 | 4th | 43718 | 43731 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0902 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at fourth floor between axis(1-7)&(A-F) for area (Z5) as Per Attached Sketch. | ARCH | Porcelain | Z5 | 4th | 43718 | 43731 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0903 | Check Surface Prepration and dots for ceramic tiles between axes (16-18)(C-D) at third floor(312.10) for area (Z1) as Per Attached Sketch. | ARCH | Ceramic Dots | Z1 | 3rd | 43719 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0904 | check fixation for aqua panel and cement board between (1-6) & (E-L) at (z4) at roof floor level (333.10) . | ARCH | Aqua Panel | Z4 | RF | 43720 | 43731 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0905 | check fixation for aqua panel and cement board between (13-18) & (A-F) at (Z1) at roof floor level (324.10) . | ARCH | Aqua Panel | Z1 | RF | 43720 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0906 | check fixation for aqua panel and cement board between (1-7) & (A-F) at (Z5) at roof floor level (324.10) . | ARCH | Aqua Panel | Z5 | RF | 43720 | 43731 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0907 | check fixation for aqua panel and cement board between (13-18) & (F-L) at (Z2) at roof floor level (333.10) . | ARCH | Aqua Panel | Z2 | RF | 43720 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0908 | Check fixation for ceramic tiles for walls at first floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls | Z2 | 1st | 43720 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0909 | Check fixation for ceramic tiles for walls and flooring at second floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 2nd | 43720 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0910 | Check fixation for ceramic tiles for walls at third floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls | Z2 | 3rd | 43720 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0911 | Check fixation for ceramic tiles for walls and flooring at first floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | 1st | 43720 | 43731 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0912 | Check fixation for ceramic tiles for walls and flooring at second floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | 2nd | 43720 | 43731 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0913 | Check fixation for ceramic tiles for walls and flooring at third floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | 3rd | 43720 | 43731 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0914 | Check fixation for marble threshold for flooring at first floor between axis(12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Marble Thresholed | Z1 | 1st | 43725 | 43727 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0915 | Check fixation for marble threshold for flooring at first floor between axis(12-18)&(E-L) for area (Z2) as Per Attached Sketch. | ARCH | Marble Thresholed | Z2 | 1st | 43725 | 43727 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0916 | Check fixation for marble threshold for flooring at first floor between axis(10-13)&(E-L) for area (Z3-A) as Per Attached Sketch. | ARCH | Marble Thresholed | Z3A | 1st | 43725 | 43727 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0917 | Check fixation for marble threshold for flooring at second floor between axis(12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Marble Thresholed | Z1 | 2nd | 43725 | 43727 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0918 | Check fixation for marble threshold for flooring at second floor between axis(12-18)&(E-L) for area (Z2) as Per Attached Sketch. | ARCH | Marble Thresholed | Z2 | 2nd | 43725 | 43727 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0919 | Check fixation for marble threshold for flooring at second floor between axis(10-13)&(E-L) for area (Z3-A) as Per Attached Sketch. | ARCH | Marble Thresholed | Z3A | 2nd | 43725 | 43727 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0920 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at seventh floor between axis(12-18)&(E-L) for area (Z2) as Per Attached Sketch. | ARCH | Porcelain | Z2 | 7th | 43725 | 43727 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0921 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(12-14)&(K-L) for area (Z2) From SECOND to SEVENTH Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z2 | ML | 43726 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0922 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(5-7)&(K-L) for area (Z4) From SECOND to SEVENTH Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z4 | ML | 43726 | 43736 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0923 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at seventh floor between axis(12-18)&(E-L) for area (Z2) as Per Attached Sketch. | ARCH | Porcelain | Z2 | 7th | 43726 | 43736 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0924 | check cement based waterproof coating for toilets between axes (E-D)&(17-18) at first basement floor (297.10)for area (z1) as per attached sketch. | ARCH | Water Proofing Cement base | Z1 | B1 | 43729 | 43736 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0925 | check cement based waterproof coating for toilets between axes (E-D)&(1-2) at first basement floor (297.10)for area (z5) as per attached sketch. | ARCH | Water Proofing Cement base | Z5 | B1 | 43729 | 43736 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0926 | water test for the BATH ROOM AT first basement FLOOR level (297.10) between axis (E-D)&(1-5) for area (Z5) As Per Attached Sketch. | ARCH | Water Test | Z5 | B1 | 43729 | 43736 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0927 | water test for the BATH ROOM AT first basement FLOOR level (297.10) between axis (E-D)&(17-18) for area (Z1) As Per Attached Sketch. | ARCH | Water Test | Z1 | B1 | 43729 | 43736 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0928 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at first basement between axis(15-17)&(D-E) for area (Z1) as Per Attached Sketch. | ARCH | Porcelain | Z1 | B1 | 43730 | 43736 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0929 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at first basement between axis(13-16)&(F-J) for area (Z2) as Per Attached Sketch. | ARCH | Porcelain | Z2 | B1 | 43730 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0930 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at first basement between axis(3-6)&(F-J) for area (Z4) as Per Attached Sketch. | ARCH | Porcelain | Z4 | B1 | 43730 | 43736 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0931 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at first basement between axis(2-4)&(D-E) for area (Z5) as Per Attached Sketch. | ARCH | Porcelain | Z5 | B1 | 43730 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0932 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at second basement between axis(15-17)&(D-E) for area (Z1) as Per Attached Sketch. | ARCH | Porcelain | Z1 | B2 | 43730 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0933 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at second basement between axis(13-16)&(F-J) for area (Z2) as Per Attached Sketch. | ARCH | Porcelain | Z2 | B2 | 43730 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0934 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at second basement between axis(3-6)&(F-J) for area (Z4) as Per Attached Sketch. | ARCH | Porcelain | Z4 | B2 | 43730 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0935 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at second basement between axis(2-4)&(D-E) for area (Z5) as Per Attached Sketch. | ARCH | Porcelain | Z5 | B2 | 43730 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0936 | check cement based waterproof coating for toilets between axes (F-L)&(7-9) at second floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 2nd | 43733 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0937 | water test for the toilet AT second floor level (308.10) between axis (F-L)&(7-9) for area (Z3) As Per Attached Sketch. | ARCH | Water Test | Z3 | 2nd | 43733 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0938 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(2-3)&(E-G) for area (Z4) From SECOND to SEVENTH Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z4 | ML | 43733 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0939 | Check fixation of chassis under marble clading for façade between axis(2-5)&(F-G) for area (Z4) From Sixth to Eighth Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z4 | ML | 43733 | 43745 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0940 | check cement based waterproof coating for toilets between axes (F-H)&(2-5) at third floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 3rd | 43733 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0941 | water test for the toilet at third floor level (312.10) between axis (F-H)&(2-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 3rd | 43733 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0942 | check cement based waterproof coating for toilets between axes (F-H)&(2-5) at fourth floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 4th | 43733 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0943 | water test for the toilet at fourth floor level (316.10) between axis (F-H)&(2-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 4th | 43733 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0944 | check cement based waterproof coating for toilets between axes (F-H)&(14-17) at fourth floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 4th | 43733 | 43748 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0945 | water test for the toilet at fourth floor level (316.10) between axis (F-H)&(14-17) for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 4th | 43733 | 43748 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0946 | First primer coat for façade between axes(1-6)&(F-G) for area (Z4) From Sixth to seventh Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z4 | ML | 43736 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0947 | SECOND primer coat for façade between axes (1-6)&(F-G) for area (Z4) From Sixth to seventh Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z4 | ML | 43736 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0948 | THIRD primer coat for façade between axes (1-6)&(F-G) for area (Z4) From Sixth to seventh Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z4 | ML | 43736 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0949 | Check fixation of rockwool under marbel clading for façade between axis (1-6)&(F-G) for area (Z4) From Sixth to seventh Floor as Per Attached Sketch. | ARCH | Marble Rockwool | Z4 | ML | 43736 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0950 | First primer coat for façade between axes(13-18)&(F-G) for area (Z2) From Sixth to seventh Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43736 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0951 | SECOND primer coat for façade between axes (13-18)&(F-G) for area (Z2) From Sixth to seventh Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43736 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0952 | THIRD primer coat for façade between axes (13-18)&(F-G) for area (Z2) From Sixth to seventh Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43736 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0953 | Check fixation of chassis under marble clading for façade between axis(13-18)&(F-G) for area (Z2) From Sixth to seventh Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z2 | ML | 43736 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0954 | Check fixation of rockwool under marbel clading for façade between axis (13-18)&(F-G) for area (Z2) From Sixth to seventh Floor as Per Attached Sketch. | ARCH | Marble Rockwool | Z2 | ML | 43736 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0955 | check cement based waterproof coating for toilets between axes (G-K)&(8-9) at first floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 1st | 43737 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0956 | water test for the toilet at first floor level (304.10) between axis (G-K)&(8-9) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 1st | 43737 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0957 | check cement based waterproof coating for toilets between axes (F-H)&(2-5) at fifth floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 5th | 43737 | 43745 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0958 | water test for the toilet at fifth floor level (320.10) between axis (F-H)&(2-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 5th | 43737 | 43737 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0959 | check fixation of steel door frame at first basement for area (Z1,2,3,4,5)between axes (A_L) (1_18) as per attached sketch. | ARCH | Steel doors Frame | Z1,2,3,4,5 | B1 | 43737 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0960 | check fixation of steel door frame at second basement for area (Z1,2,3,4,5)between axes (A_L) (1_18) as per attached sketch. | ARCH | Steel doors Frame | Z1,2,3,4,5 | B2 | 43737 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0961 | check cement based waterproof coating for toilets between axes (F-L)&(9-12) at Sixth floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 6th | 43738 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0962 | water test for the toilet at Sixth floor level (324.10) between axis (F-L)&(9-12) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 6th | 43738 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0963 | check cement based waterproof coating for toilets between axes (F-L)&(7-9) at third floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 3rd | 43744 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0964 | water test for the toilet at third floor level (312.10) between axis (F-L)&(7-9) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 3rd | 43744 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0965 | check cement based waterproof coating for toilets between axes (D-F)&(5-6) at second floor for area (Z5) as per attached sketch. | ARCH | Water Proofing Cement base | Z5 | 2nd | 43744 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0966 | water test for the toilet at second floor level (308.10) between axis (D-F)&(5-6) for area (Z5) as per attached sketch. | ARCH | Water Test | Z5 | 2nd | 43744 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0967 | check cement based waterproof coating for toilets between axes (F-H)&(14-17) at fifth floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 5th | 43745 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0968 | water test for the toilet at fifth floor level (320.10) between axis (F-H)&(14-17) for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 5th | 43745 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0969 | check cement based waterproof coating for toilets between axes (G-L)&(10-12) at fourth floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 4th | 43747 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0970 | water test for the toilet at fourth floor level (316.10) between axis (G-L)&(10-12) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 4th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0971 | Second Coat of approved Putty For Painting For fifth floor (320.10) at Zone(1) axes (A-F) &(13-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z1 | 5th | 43747 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0972 | Second Coat of approved Putty For Painting For fifth floor (320.10) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z2 | 5th | 43747 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0973 | Second Coat of approved Putty For Painting For fifth floor (320.10) at Zone(3A) axes (E-L) &(10-12) as Per Attached Sketch. | ARCH | Painting second Putty | Z3A | 5th | 43747 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0974 | Second Coat of approved Putty For Painting For fifth floor (320.10) at Zone(3B) axes (E-L) &(6-9) as Per Attached Sketch. | ARCH | Painting second Putty | Z3B | 5th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0975 | Second Coat of approved Putty For Painting For fifth floor (320.10) at Zone(4) axes (E-L) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z4 | 5th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0976 | Second Coat of approved Putty For Painting For fifth floor (320.10) at Zone(5) axes (A-F) &(1-6) as Per Attached Sketch. | ARCH | Painting second Putty | Z5 | 5th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0977 | Second Coat of approved Putty For Painting For sixth floor (324.10) at Zone(1) axes (A-F) &(13-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z1 | 6th | 43747 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0978 | Second Coat of approved Putty For Painting For sixth floor (324.10) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z2 | 6th | 43747 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0979 | Second Coat of approved Putty For Painting For sixth floor (324.10) at Zone(3A) axes (E-L) &(10-13) as Per Attached Sketch. | ARCH | Painting second Putty | Z3A | 6th | 43747 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0980 | Second Coat of approved Putty For Painting For sixth floor (324.10) at Zone(3B) axes (E-L) &(6-9) as Per Attached Sketch. | ARCH | Painting second Putty | Z3B | 6th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0981 | Second Coat of approved Putty For Painting For sixth floor (324.10) at Zone(4) axes (E-L) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z4 | 6th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0982 | Second Coat of approved Putty For Painting For sixth floor (324.10) at Zone(5) axes (A-F) &(1-6) as Per Attached Sketch. | ARCH | Painting second Putty | Z5 | 6th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0983 | Second Coat of approved Putty For Painting For seventh floor (328.10) at Zone(2) axes (F-L) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z2 | 7th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0984 | Second Coat of approved Putty For Painting For seventh floor (328.10) at Zone(3A) axes (E-L) &(10-13) as Per Attached Sketch. | ARCH | Painting second Putty | Z3A | 7th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0985 | Second Coat of approved Putty For Painting For seventh floor (328.10) at Zone(3B) axes (E-L) &(6-9) as Per Attached Sketch. | ARCH | Painting second Putty | Z3B | 7th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0986 | Second Coat of approved Putty For Painting For seventh floor (328.10) at Zone(4) axes (F-L) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z4 | 7th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0987 | Second Coat of approved Putty For Painting For eighth floor (333.10) at Zone(2) axes (F-L) &(13-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z2 | 8th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0988 | Second Coat of approved Putty For Painting For eighth floor (333.10) at Zone(3) axes (E-L) &(6-13) as Per Attached Sketch. | ARCH | Painting second Putty | Z3 | 8th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0989 | Second Coat of approved Putty For Painting For eighth floor (333.10) at Zone(4) axes (F-L) &(1-6) as Per Attached Sketch. | ARCH | Painting second Putty | Z4 | 8th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0990 | Second Coat of approved Putty For Painting For ninth floor (338.10) at Zone(3) axes (E-L) &(6-13) as Per Attached Sketch. | ARCH | Painting second Putty | Z3 | 9th | 43747 | 43753 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0991 | water test for the toilet at Sixth floor level (324.10) between axis (F-L)&(9-11) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 6th | 43750 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0992 | check cement based waterproof coating for toilets between axes (G-L)&(7-9) at FOURTH floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 4th | 43751 | 43757 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0993 | water test for the toilet at FOURTH floor level (316.10) between axis (G-L)&(7-9) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 4th | 43751 | 43757 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0994 | check cement based waterproof coating for toilets between axes (E-F)&(4-5) at FOURTH floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 4th | 43751 | 43757 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0995 | water test for the toilet at FOURTH floor level (316.10) between axis (E-F)&(4-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 4th | 43751 | 43757 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0996 | check cement based waterproof coating for toilets between axes (E-F)&(1-2) at SECOND floor for area (Z5) as per attached sketch. | ARCH | Water Proofing Cement base | Z5 | 2nd | 43751 | 43757 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0997 | water test for the toilet at SECOND floor level (308.10) between axis (E-F)&(1-2) for area (Z5) as per attached sketch. | ARCH | Water Test | Z5 | 2nd | 43751 | 43757 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0998 | check cement based waterproof coating for toilets between axes (F-H)&(2-5) at SIXTH floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 6th | 43751 | 43757 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-0999 | water test for the toilet at SIXTH floor level (324.10) between axis (F-H)&(2-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 6th | 43751 | 43757 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1000 | check cement based waterproof coating for toilets between axes (G-K)&(10-11) at first floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 1st | 43753 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1001 | water test for the toilet at first floor level (304.10) between axis (G-K)&(10-11) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 1st | 43753 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1002 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at sixth floor between axis(12-18)&(F-L) for area (Z2) as Per Attached Sketch. | ARCH | Porcelain | Z2 | 6th | 43753 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1003 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at sixth floor between axis(10-13)&(E-L) for area (Z3) as Per Attached Sketch. | ARCH | Porcelain | Z3 | 6th | 43753 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1004 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(5-7)/(L) for area (Z4) From second to seventh floor as Per Attached Sketch. | ARCH | Curtain Wall | Z4 | ML | 43755 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1005 | check cement based waterproof coating for toilets between axes (G-L)&(7-10) at fourth floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 4th | 43755 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1006 | water test for the toilet at fourth floor level (316.10) between axis (G-L)&(7-10) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 4th | 43755 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1007 | check cement based waterproof coating for toilets between axes (E-F)&(4-5) at fourth floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 4th | 43755 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1008 | water test for the toilet at fourth floor level (316.10) between axis (E-F)&(4-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 4th | 43755 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1009 | check cement based waterproof coating for toilets between axes (D-F)&(5-6) at third floor for area (Z5) as per attached sketch. | ARCH | Water Proofing Cement base | Z5 | 3rd | 43755 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1010 | water test for the toilet at third floor level (312.10) between axis (D-F)&(5-6) for area (Z5) as per attached sketch. | ARCH | Water Test | Z5 | 3rd | 43755 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1011 | check cement based waterproof coating for toilets between axes (F-H)&(14-17) at fourth floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 4th | 43757 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1012 | water test for the toilet at fourth floor level (316.10) between axis (F-H)&(14-17) for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 4th | 43757 | 43766 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1013 | check cement based waterproof coating for toilets between axes (F-H)&(14-17) at sixth floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 6th | 43757 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1014 | water test for the toilet at sixth floor level (324.10) between axis (F-H)&(14-17) for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 6th | 43757 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1015 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at fifth floor between axis(13-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Porcelain | Z1 | 5th | 43757 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1016 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at fifth floor between axis(12-18)&(E-L) for area (Z2) as Per Attached Sketch. | ARCH | Porcelain | Z2 | 5th | 43757 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1017 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at fifth floor between axis(10-13)&(E-L) for area (Z3-A) as Per Attached Sketch. | ARCH | Porcelain | Z3A | 5th | 43757 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1018 | First primer coat for façade between axes (14-17)&(F-G) for area (Z2) From ground to sixth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43757 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1019 | SECOND primer coat for façade between axes (14-17)&(F-G) for area (Z2) From ground to sixth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43757 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1020 | THIRD primer coat for façade between axes (14-17)&(F-G) for area (Z2) From ground to sixth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43757 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1021 | Check fixation of chassis under marble clading for façade between axis (14-17)&(F-G) for area (Z2) From ground to sixth Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z2 | ML | 43757 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1022 | Check fixation of rockwool under marbel clading for façade between axis (14-17)&(F-G) for area (Z2) From ground to sixth Floor as Per Attached Sketch. | ARCH | Marble Rockwool | Z2 | ML | 43757 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1023 | Check fixation of chassis under marble clading for façade between axis (12-15)&(D-F) for area (Z1) from ground to seventh floor as Per Attached Sketch. | ARCH | Marble Chassis | Z1 | ML | 43758 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1024 | Check fixation for marble threshold for flooring at third floor between axis(10-13)&(E-L) for area (Z3-A) as Per Attached Sketch. | ARCH | Marble Thresholed | Z3A | 3rd | 43759 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1025 | Check fixation for marble threshold for flooring at fourth floor between axis(12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Marble Thresholed | Z1 | 4th | 43759 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1026 | Check fixation for marble threshold for flooring at fourth floor between axis(12-18)&(E-L) for area (Z2) as Per Attached Sketch. | ARCH | Marble Thresholed | Z2 | 4th | 43759 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1027 | Check fixation for marble threshold for flooring at fourth floor between axis(10-13)&(E-L) for area (Z3-A) as Per Attached Sketch. | ARCH | Marble Thresholed | Z3A | 4th | 43759 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1028 | Check fixation for marble threshold for flooring at fifth floor between axis(12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Marble Thresholed | Z1 | 5th | 43759 | 43766 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1029 | Check fixation for marble threshold for flooring at fifth floor between axis(12-18)&(E-L) for area (Z2) as Per Attached Sketch. | ARCH | Marble Thresholed | Z2 | 5th | 43759 | 43766 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1030 | Check fixation for marble threshold for flooring at fifth floor between axis(10-13)&(E-L) for area (Z3-A) as Per Attached Sketch. | ARCH | Marble Thresholed | Z3A | 5th | 43759 | 43766 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1031 | Check fixation for marble threshold for flooring at sixth floor between axis(12-18)&(E-L) for area (Z2) as Per Attached Sketch. | ARCH | Marble Thresholed | Z2 | 6th | 43759 | 43766 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1032 | Check fixation for marble threshold for flooring at sixth floor between axis(10-13)&(E-L) for area (Z3-A) as Per Attached Sketch. | ARCH | Marble Thresholed | Z3A | 6th | 43759 | 43766 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1033 | Check fixation for marble threshold for flooring at third floor between axis(12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Marble Thresholed | Z1 | 3rd | 43759 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1034 | Check fixation for marble threshold for flooring at third floor between axis(12-18)&(E-L) for area (Z2) as Per Attached Sketch. | ARCH | Marble Thresholed | Z2 | 3rd | 43759 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1035 | check cement based waterproof coating for toilets between axes (C-F)&(13-18) at third floor for area (Z1) as per attached sketch. | ARCH | Water Proofing Cement base | Z1 | 3rd | 43760 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1036 | water test for the toilet at third floor level (312.10) between axis (C-F)&(13-18) for area (Z1) as per attached sketch. | ARCH | Water Test | Z1 | 3rd | 43760 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1037 | check cement based waterproof coating for toilets between axes (E-F)&(5-6) at fourth floor for area (Z5) as per attached sketch. | ARCH | Water Proofing Cement base | Z5 | 4th | 43760 | 43769 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1038 | water test for the toilet at fourth floor level (316.10) between axis (E-F)&(5-6) for area (Z5) as per attached sketch. | ARCH | Water Test | Z5 | 4th | 43760 | 43769 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1039 | check cement based waterproof coating for toilets between axes (G-H)&(3-5) at first floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 1st | 43760 | 43769 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1040 | water test for the toilet at first floor level (304.10) between axis (G-H)&(3-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 1st | 43760 | 43769 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1041 | Check fixation and installation for transom and mullion for curtin wall on bridge between axis(9-10)&(F-L) for area (Z3) From seventh to tenth floor as Per Attached Sketch. | ARCH | Curtain Wall | Z3 | ML | 43760 | 43779 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1042 | Check fixation for ceramic tiles for walls and flooring at fourth floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 4th | 43765 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1043 | Check fixation for ceramic tiles for walls and flooring at fifth floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 5th | 43765 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1044 | Check fixation for ceramic tiles for walls and flooring at sixth floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 6th | 43765 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1045 | Check fixation for ceramic tiles for walls and flooring at fourth floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | 4th | 43765 | 43773 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1046 | Check fixation for ceramic tiles for walls and flooring at fifth floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | 5th | 43765 | 43773 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1047 | Check fixation for ceramic tiles for walls and flooring at sixth floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | 6th | 43765 | 43773 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1048 | Check fixation for ceramic tiles for walls and flooring at first floor between axis(10-11)&(G-K) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | 1st | 43765 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1049 | Check fixation for ceramic tiles for walls and flooring at first floor between axis(8-9)&(G-K) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | 1st | 43765 | 43773 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1050 | check cement based waterproof coating for toilets between axes (F-L)&(10-12) at second floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 2nd | 43765 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1051 | water test for the toilet at second floor level (308.10) between axis (F-L)&(10-12) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 2nd | 43765 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1052 | Check fixation for ceramic tiles for walls and flooring at second floor between axis(10-12)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | 2nd | 43765 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1053 | Check fixation for ceramic tiles for walls and flooring at second floor between axis(7-9)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | 2nd | 43765 | 43773 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1054 | Check fixation for ceramic tiles for walls and flooring at second floor between axis(1-6)&(D-F) for area (Z5) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z5 | 2nd | 43765 | 43773 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1055 | Check fixation for ceramic tiles for walls and flooring at third floor between axis(13-18)&(C-F) for area (Z1) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z1 | 3rd | 43765 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1056 | check cement based waterproof coating for toilets between axes (G-L)&(10-12) at third floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 3rd | 43765 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1057 | water test for the toilet at thirf floor level (312.10) between axis (G-L)&(10-12) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 3rd | 43765 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1058 | Check fixation for ceramic tiles for walls and flooring at third floor between axis(10-12)&(G-L) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | 3rd | 43765 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1059 | Check fixation for ceramic tiles for walls and flooring at third floor between axis(7-9)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | 3rd | 43765 | 43773 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1060 | Check fixation for ceramic tiles for walls and flooring at third floor between axis(5-6)&(E-F) for area (Z5) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z5 | 3rd | 43765 | 43773 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1061 | check cement based waterproof coating for toilets between axes (E-F)&(13-14) at fourth floor for area (Z1) as per attached sketch. | ARCH | Water Proofing Cement base | Z1 | 4th | 43765 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1062 | water test for the toilet at fourth floor level (316.10) between axis (E-F)&(13-14) for area (Z1) as per attached sketch. | ARCH | Water Test | Z1 | 4th | 43765 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1063 | Check fixation for ceramic tiles for walls and flooring at fourth floor between axis(13-14)&(E-F) for area (Z1) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z1 | 4th | 43765 | 43773 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1064 | Check fixation for ceramic tiles for walls and flooring at fourth floor between axis(10-12)&(G-L) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | 4th | 43765 | 43773 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1065 | Check fixation of rockwool under marbel clading for façade between axis (12-18)&(A-F) from second to sixth floor zone(1)as per attached sketch. | ARCH | Marble Rockwool | Z1 | ML | 43766 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1066 | Check fixation of rockwool under marbel clading for façade between axis (12-18)&(0-F) from ground to second floor zone(1)as per attached sketch. | ARCH | Marble Rockwool | Z1 | ML | 43766 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1067 | Check fixation of rockwool under marbel clading for façade between axis (1-6)&(K-L) from ground to second Floor zone(z4)as per attached sketch | ARCH | Marble Rockwool | Z4 | ML | 43766 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1068 | Check fixation of rockwool under marbel clading for façade between axis (12-18)&(F-L) from ground to second Floor zone(Z2)as per attached sketch | ARCH | Marble Rockwool | Z2 | ML | 43766 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1069 | Full Height of blockwork between axes (6-13)&(E-L) at fourth floor(316.10 ) for area (Z3) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | 4th | 43767 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1070 | Full Height of blockwork between axes (1-7)&(E-L) at fourth floor(316.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 4th | 43767 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1071 | Full Height of blockwork between axes (1-6)&(A-F) at fourth floor(316.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | 4th | 43767 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1072 | Full Height of blockwork between axes (1-7)&(E-L) at fifth floor(320.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 5th | 43767 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1073 | Full Height of blockwork between axes (1-6)&(A-F) at fifth floor(320.10 ) for area (Z5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z5 | 5th | 43767 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1074 | Full Height of blockwork between axes (14-17)&(A-F) at sixth floor(324.10 ) for area (Z1) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | 6th | 43767 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1075 | Full Height of blockwork between axes (1-7)&(E-L) at sixth floor(324.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 6th | 43767 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1076 | Full Height of blockwork between axes (2-7)&(F-L) at seventh floor(328.10 ) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | 7th | 43767 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1077 | Check fixation of rockwool under marbel clading for façade between axis (9-10)&(G-K) from ground to sixth floor zone(3)as per attached sketch. | ARCH | Marble Rockwool | Z3 | ML | 43767 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1078 | Check fixation of rockwool under marbel clading for façade between axis (10-12)&(E-L) from ground to tenth floor zone(3)as per attached sketch. | ARCH | Marble Rockwool | Z3 | ML | 43767 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1079 | Check fixation of rockwool under marbel clading for façade between axis (7-9)&(E-L) from ground to tenth floor zone(3)as per attached sketch. | ARCH | Marble Rockwool | Z3 | ML | 43767 | 43771 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1080 | check cement based waterproof coating for toilets between axes (E-L)&(10-12) at fifth floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 5th | 43769 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1081 | water test for the toilet at fifth floor level (320.10) between axis (E-L)&(10-12) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 5th | 43769 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1082 | check cement based waterproof coating for pantry between axes (G-H)&(14-16) at second floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 2nd | 43769 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1083 | water test for the pantry at fifth floor level (320.10) between axis (G-H)&(14-16) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 2nd | 43769 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1084 | Check fixation for ceramic tiles for walls and flooring at first basement between axis(17-18)&(D-E) for area (Z1) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z1 | B1 | 43771 | 43779 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1085 | Check fixation for ceramic tiles for walls and flooring at first basement between axis(1-2)&(D-E) for area (Z5) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z5 | B1 | 43771 | 43779 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1086 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at first basement between axis(17-18)&(C-E) for area (Z1) as Per Attached Sketch. | ARCH | Porcelain | Z1 | B1 | 43771 | 43773 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1087 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at first basement between axis(1-2)&(C-E) for area (Z5) as Per Attached Sketch. | ARCH | Porcelain | Z5 | B1 | 43771 | 43779 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1088 | Check fixation for ceramic tiles for walls at first basement between axis(17-18)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls | Z2 | B1 | 43771 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1089 | Check fixation for ceramic tiles for walls at first basement between axis(1-2)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls | Z4 | B1 | 43771 | 43779 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1090 | check cement based waterproof coating for pantry and janitor room between axes (G-H)&(3-5) at third floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 3rd | 43774 | 43779 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1091 | water test for the pantry and janitor room at third floor level (312.10) between axis (G-H)&(3-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 3rd | 43774 | 43779 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1092 | check cement based waterproof coating for pantry and janitor room between axes (G-H)&(3-5) at second floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 2nd | 43774 | 43779 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1093 | water test for the pantry and janitor room at second floor level (308.10) between axis (G-H)&(3-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 2nd | 43774 | 43779 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1094 | check cement based waterproof coating for pantry and janitor room between axes (G-H)&(3-5) at fourth floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 4th | 43774 | 43779 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1095 | water test for the pantry and janitor room at fourth floor level (316.10) between axis (G-H)&(3-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 4th | 43774 | 43779 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1096 | check cement based waterproof coating for toilets between axes (G-L)&(7-9) at sixth floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 6th | 43774 | 43779 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1097 | water test for the toilet at sixth floor level (324.10) between axis (G-L)&(7-9) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 6th | 43774 | 43779 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1098 | check cement based waterproof coating for pantry between axes (G-H)&(14-16) at first floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 1st | 43775 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1099 | water test for the pantry at first floor level (304.10) between axis (G-H)&(14-16) for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 1st | 43775 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1100 | check cement based waterproof coating for pantry between axes (G-H)&(14-16) at third floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 3rd | 43775 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1101 | water test for the pantry at third floor level (312.10) between axis (G-H)&(14-16) for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 3rd | 43775 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1102 | check cement based waterproof coating for pantry between axes (G-H)&(14-16) at fourth floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 4th | 43775 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1103 | water test for the pantry at fourth floor level (316.10) between axis (G-H)&(14-16) for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 4th | 43775 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1104 | check cement based waterproof coating for pantry between axes (G-H)&(14-16) at fifth floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 5th | 43775 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1105 | water test for the pantry at fifth floor level (320.10) between axis (G-H)&(14-16) for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 5th | 43775 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1106 | check cement based waterproof coating for toilet between axes (D-E)&(14-15) at fifth floor for area (Z1) as per attached sketch. | ARCH | Water Proofing Cement base | Z1 | 5th | 43775 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1107 | water test for the toilet at fifth floor level (320.10) between axis (D-E)&(14-15) for area (Z1) as per attached sketch. | ARCH | Water Test | Z1 | 5th | 43775 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1108 | Check fixation of steel chassis under toilet marble between axis (14-17)&(F-H) for area (Z2) at ground floor as Per Attached Sketch. | ARCH | Marble Toilet Chassis | Z2 | GF | 43775 | 43783 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1109 | Check first course of blockwork between axes (9-10)&(G-K) from ground to second floor for area (Z3) as Per Attached Sketch. | ARCH | Blockwork First course | Z3 | ML | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1110 | check cement based waterproof coating for pantry between axes (G-H)&(3-5) at second floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 2nd | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1111 | water test for the pantry at second floor level (308.10) between axis (G-H)&(3-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 2nd | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1112 | check cement based waterproof coating for pantry between axes (G-H)&(3-5) at third floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 3rd | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1113 | water test for the pantry at third floor level (312.10) between axis (G-H)&(3-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 3rd | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1114 | check cement based waterproof coating for pantry between axes (G-H)&(3-5) at fourth floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 4th | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1115 | water test for the pantry at fourth floor level (316.10) between axis (G-H)&(3-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 4th | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1116 | check cement based waterproof coating for pantry between axes (G-H)&(3-5) at fifth floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 5th | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1117 | water test for the pantry at fifth floor level (320.10) between axis (G-H)&(3-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 5th | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1118 | check cement based waterproof coating for toilet between axes (G-L)&(7-9) at fifth floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 5th | 43775 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1119 | water test for the toilet at fifth floor level (320.10) between axis (G-L)&(7-9) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 5th | 43775 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1120 | check cement based waterproof coating for pantry between axes (G-H)&(3-5) at sixth floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 6th | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1121 | water test for the pantry at sixth floor level (324.10) between axis (G-H)&(3-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 6th | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1122 | Check fixation for ceramic tiles for walls and flooring at second floor between axis(10-12)&(J-L) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | 2nd | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1123 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at ninth floor between axis(7-12)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | Porcelain | Z3 | 9th | 43782 | 43785 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1124 | check cement based waterproof coating for toilet between axes (G-H)&(2-3) at sixth floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 6th | 43783 | 43802 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1125 | water test for the toilet at sixth floor level (324.10) between axis (G-H)&(2-3) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 6th | 43783 | 43802 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1126 | check cement based waterproof coating for pantry and janitor room between axes (G-H)&(3-5) at ground floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | GF | 43783 | 43802 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1127 | water test for the pantry and janitor room at ground floor level (300.10) between axis (G-H)&(3-5) for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | GF | 43783 | 43788 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1128 | check cement based waterproof coating for pantry room between axes (G-H)&(14-16) at ground floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | GF | 43787 | 43796 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1129 | water test for the pantry room at ground floor level (300.10) between axis (G-H)&(14-16) for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | GF | 43787 | 43796 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1130 | Check Surface Prepration and dots and accessories for plaster works between axes (G-k)&(9-10) from ground to second floor for area (Z3) as Per Attached Sketch. | ARCH | Plaster Dots | Z3 | ML | 43787 | 43800 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1131 | Check for Final Plaster between axes (G-k)&(9-10) from ground to second floor for area (Z3) as Per Attached Sketch. | ARCH | Final Plaster | Z3 | ML | 43787 | 43800 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1132 | check fixation of garbage chute from ground to seventh floor for area (Z4) as Per Attached Sketch. | ARCH | Garbage Chute | Z4 | ML | 43789 | 43809 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1133 | Check fixation for ceramic tiles for flooring and walls for pantry at second floor between axis(14-16)&(G-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 2nd | 43789 | 43796 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1134 | check cement based waterproof coating for toilet between axes (F-H)&(14-17) at ground floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | GF | 43790 | 43796 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1135 | water test for the toilet at ground floor for area (Z2) level (300.10) between axes (F-H)&(14-17) as per attached sketch. | ARCH | Water Test | Z2 | GF | 43790 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1136 | Check first fix for wooden doors at second floor between axis (13-18)&(A-F) for area(Z1) as Per Attached Sketch. | ARCH | Wooden door Frame | Z1 | 2nd | 43794 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1137 | Check first fix for wooden doors at second floor between axis (13-18)&(E-L) for area(Z2) as Per Attached Sketch. | ARCH | Wooden door Frame | Z2 | 2nd | 43794 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1138 | Check first fix for wooden doors at second floor between axis (10-13)&(E-L) for area(Z3A) as Per Attached Sketch. | ARCH | Wooden door Frame | Z3A | 2nd | 43794 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1139 | Check first fix for wooden doors at second floor between axis (6-9)&(E-L) for area(Z3B) as Per Attached Sketch. | ARCH | Wooden door Frame | Z3B | 2nd | 43794 | 43809 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1140 | Check first fix for wooden doors at second floor between axis (1-7)&(E-L) for area(Z4) as Per Attached Sketch. | ARCH | Wooden door Frame | Z4 | 2nd | 43794 | 43809 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1141 | Check first fix for wooden doors at second floor between axis (1-7)&(A-F) for area(Z5) as Per Attached Sketch. | ARCH | Wooden door Frame | Z5 | 2nd | 43794 | 43809 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1142 | check cement based waterproof coating for toilet between axes (F-H)&(2-5) at seventh floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 7th | 43801 | 43809 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1143 | water test for the toilet at seventh floor for area (Z4) level (328.10) between axes (F-H)&(2-5) as per attached sketch. | ARCH | Water Test | Z4 | 7th | 43801 | 43809 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1144 | check cement based waterproof coating for toilet between axes (J-L)&(7-9) at Eighth floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 8th | 43801 | 43809 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1145 | water test for the toilet at Eighth floor for area (Z3) level (333.10) between axes (J-L)&(7-9) as per attached sketch. | ARCH | Water Test | Z3 | 8th | 43801 | 43809 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1146 | check cement based waterproof coating for toilet between axes (F-H)&(14-17) at seventh floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 7th | 43803 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1147 | water test for the toilet at seventh floor for area (Z2) level (328.10) between axes (F-H)&(14-17) as per attached sketch. | ARCH | Water Test | Z2 | 7th | 43803 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1148 | Check fixation of steel chassis under toilet marble between axis (14-17)&(F-H) for area (Z2) at seventh floor as Per Attached Sketch. | ARCH | Marble Toilet Chassis | Z2 | 7th | 43803 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1149 | Check fixation of steel chassis under toilet marble between axis (2-5)&(F-H) for area (Z4) at seventh floor as Per Attached Sketch. | ARCH | Marble Toilet Chassis | Z4 | 7th | 43803 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1150 | Check fixation for marble sill for interior curtin wall upstand between axis (13-18)&(A-F) for area (Z1) at second floor as Per Attached Sketch. | ARCH | Marble sill | Z1 | 2nd | 43809 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1151 | Check fixation for marble sill for interior curtin wall upstand between axis (14-18)&(G-L) for area (Z2) at second floor as Per Attached Sketch. | ARCH | Marble sill | Z2 | 2nd | 43809 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1152 | Check fixation for marble sill for interior curtin wall upstand between axis (6-12)&(E-L) for area (Z3) at second floor as Per Attached Sketch. | ARCH | Marble sill | Z3 | 2nd | 43809 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1153 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (13-18)&(A-F) for area (Z1) at second floor as Per Attached Sketch. | ARCH | Marble sill | Z1 | 2nd | 43809 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1154 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (13-18)&(A-F) for area (Z1) at second floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z1 | 2nd | 43809 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1155 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (12-17)&(E-K) for area (Z2) at second floor as Per Attached Sketch. | ARCH | Marble sill | Z2 | 2nd | 43809 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1156 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (12-17)&(E-K) for area (Z2) at second floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z2 | 2nd | 43809 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1157 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (11-13)&(G-K) for area (Z3) at second floor as Per Attached Sketch. | ARCH | Marble sill | Z3 | 2nd | 43809 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1158 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (11-13)&(G-K) for area (Z3) at second floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z3 | 2nd | 43809 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1159 | check cement based waterproof coating for toilet between axes (E-L)&(10-11) at seventh floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 7th | 43813 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1160 | water test for the toilet at seventh floor for area (Z3) level (328.10) between axes (E-L)&(10-11) as per attached sketch. | ARCH | Water Test | Z3 | 7th | 43813 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1161 | check cement based waterproof coating for toilet between axes (G-K)&(1-7) at seventh floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 7th | 43813 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1162 | water test for the toilet at seventh floor for area (Z4) level (328.10) between axes (G-K)&(1-7) as per attached sketch. | ARCH | Water Test | Z4 | 7th | 43813 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1163 | check cement based waterproof coating for toilet between axes (J-L)&(10-12) at EIGHTH floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 8th | 43813 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1164 | water test for the toilet at EIGHTH floor for area (Z3) level (333.10) between axes (J-L)&(10-12) as per attached sketch. | ARCH | Water Test | Z3 | 8th | 43813 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1165 | check cement based waterproof coating for toilet between axes (G-L)&(9-12) at ninth floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 9th | 43813 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1166 | water test for the toilet at ninth floor for area (Z3) level (338.10) between axes (G-L)&(9-12) as per attached sketch. | ARCH | Water Test | Z3 | 9th | 43813 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1167 | Check fixation of steel chassis under toilet marble between axis (8-11)&(J-K) for area (Z3) at EIGHTH floor as Per Attached Sketch. | ARCH | Marble Toilet Chassis | Z3 | 8th | 43813 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1168 | check fixation of steel door frames at first basement for area (Z1,2,3,4,5)between axes (A_L) (1_18) as per attached sketch. | ARCH | Steel doors Frame | Z1,2,3,4,5 | B1 | 43813 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1169 | check fixation of steel door frames at second basement for area (Z1,2,3,4,5)between axes (A_L) (1_18) as per attached sketch. | ARCH | Steel doors Frame | Z1,2,3,4,5 | B2 | 43813 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1170 | Check first fix for closets and shelves at second floor between axis (13-18)&(A-F) for area(Z1) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z1 | 2nd | 43816 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1171 | Check first fix for closets and shelves at second floor between axis (14-18)&(G-L) for area(Z2) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z2 | 2nd | 43816 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1172 | Check first fix for closets and shelves at second floor between axis (10-12)&(E-L) for area(Z3A) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z3A | 2nd | 43816 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1173 | Check first fix for closets and shelves at second floor between axis (7-9)&(E-L) for area(Z3B) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z3B | 2nd | 43816 | 43834 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1174 | Check first fix for closets and shelves at second floor between axis (1-5)&(G-L) for area(Z4) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z4 | 2nd | 43816 | 43834 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1175 | Check first fix for closets and shelves at second floor between axis (1-6)&(A-E) for area(Z5) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z5 | 2nd | 43816 | 43834 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1176 | Check first fix for closets and shelves at third floor between axis (13-18)&(A-F) for area(Z1) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z1 | 3rd | 43816 | 43837 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1177 | Check first fix for closets and shelves at third floor between axis (14-18)&(G-L) for area(Z2) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z2 | 3rd | 43816 | 43837 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1178 | Check first fix for closets and shelves at third floor between axis (10-12)&(E-L) for area(Z3A) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z3A | 3rd | 43816 | 43837 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1179 | Check first fix for closets and shelves at third floor between axis (7-9)&(E-L) for area(Z3B) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z3B | 3rd | 43816 | 43834 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1180 | Check first fix for closets and shelves at third floor between axis (1-5)&(G-L) for area(Z4) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z4 | 3rd | 43816 | 43834 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1181 | Check first fix for closets and shelves at third floor between axis (1-6)&(A-E) for area(Z5) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z5 | 3rd | 43816 | 43834 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1182 | Check first fix for wooden doors at third floor between axis (13-18)&(A-F) for area(Z1) as Per Attached Sketch. | ARCH | Wooden door Frame | Z1 | 3rd | 43816 | 43823 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1183 | Check first fix for wooden doors at third floor between axis (13-18)&(E-L) for area(Z2) as Per Attached Sketch. | ARCH | Wooden door Frame | Z2 | 3rd | 43816 | 43823 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1184 | Check first fix for wooden doors at third floor between axis (10-13)&(E-L) for area(Z3A) as Per Attached Sketch. | ARCH | Wooden door Frame | Z3A | 3rd | 43816 | 43823 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1185 | Check first fix for wooden doors at third floor between axis (6-9)&(E-L) for area(Z3B) as Per Attached Sketch. | ARCH | Wooden door Frame | Z3B | 3rd | 43816 | 43825 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1186 | Check first fix for wooden doors at third floor between axis (1-7)&(E-L) for area(Z4) as Per Attached Sketch. | ARCH | Wooden door Frame | Z4 | 3rd | 43816 | 43825 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1187 | Check first fix for wooden doors at third floor between axis (1-7)&(A-F) for area(Z5) as Per Attached Sketch. | ARCH | Wooden door Frame | Z5 | 3rd | 43816 | 43825 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1188 | Check fixation and insulation for wood substructure for mirror in staff and public toilets for zone (2,3,4) at first floor as Per Attached Sketch. | ARCH | Mirrors Toilet Wood sub. Strc. | Z2,3,4 | 1st | 43817 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1189 | Check fixation and insulation for wood substructure for mirror in staff and public toilets for zone (2,3,4,5) at second floor as Per Attached Sketch. | ARCH | Mirrors Toilet Wood sub. Strc. | Z2,3,4,5 | 2nd | 43817 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1190 | Check fixation and insulation for wood substructure for mirror in staff and public toilets for zone (1,2,3,4,5) at third floor as Per Attached Sketch. | ARCH | Mirrors Toilet Wood sub. Strc. | Z1,2,3,4,5 | 3rd | 43817 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1191 | Check fixation and insulation for wood substructure for mirror in staff and public toilets for zone (1,2,3,4,5) at fourth floor as Per Attached Sketch. | ARCH | Mirrors Toilet Wood sub. Strc. | Z1,2,3,4,5 | 4th | 43817 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1192 | Check fixation and insulation for wood substructure for mirror in staff and public toilets for zone (1,2,3,4,5) at fifth floor as Per Attached Sketch. | ARCH | Mirrors Toilet Wood sub. Strc. | Z1,2,3,4,5 | 5th | 43817 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1193 | Check fixation and insulation for wood substructure for mirror in staff and public toilets for zone (2,3,4) at sixth floor as Per Attached Sketch. | ARCH | Mirrors Toilet Wood sub. Strc. | Z2,3,4 | 6th | 43817 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1194 | Check fixation and insulation for wood substructure for mirror in staff and public toilets for zone (2,4) at ground floor as Per Attached Sketch. | ARCH | Mirrors Toilet Wood sub. Strc. | Z2,4 | GF | 43817 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1195 | Check fixation of marble for flooring of corridor infront of elevetors at zone(1,2) between axis (D-J)/(15-16) at first floor as Per Attached Sketch. | ARCH | Marble Flooring | Z1,2 | 1st | 43817 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1196 | Check fixation of marble for flooring of corridor infront of elevetors at zone(1,2) between axis (D-J)/(15-16) at second floor as Per Attached Sketch. | ARCH | Marble Flooring | Z1,2 | 2nd | 43817 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1197 | First primer coat for column between axes(14-17)&(E-F) for area (Z2) From ground to fifth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43817 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1198 | SECOND primer coat for column between axes(14-17)&(E-F) for area (Z2) From ground to fifth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43817 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1199 | THIRD primer coat for column between axes(14-17)&(E-F) for area (Z2) From ground to fifth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z2 | ML | 43817 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1200 | Check fixation of chassis under marble clading for column between axis(14-17)&(E-F) for area (Z2) From ground to fifth Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z2 | ML | 43817 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1201 | Check fixation of rockwool under marbel clading for column between axis (14-17)&(E-F) for area (Z2) From ground to fifth Floor as Per Attached Sketch. | ARCH | Marble Rockwool | Z2 | ML | 43817 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1202 | First primer coat for column between axes(2-5)&(E-F) for area (Z4) From ground to fifth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z4 | ML | 43817 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1203 | SECOND primer coat for column between axes(2-5)&(E-F) for area (Z4) From ground to fifth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z4 | ML | 43817 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1204 | THIRD primer coat for column between axes(2-5)&(E-F) for area (Z4) From ground to fifth Floor as Per Attached Sketch. | ARCH | Water Proofing Façade | Z4 | ML | 43817 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1205 | Check fixation of chassis under marble clading for column between axis(2-5)&(E-F) for area (Z4) From ground to fifth Floor as Per Attached Sketch. | ARCH | Marble Chassis | Z4 | ML | 43817 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1206 | Check fixation of rockwool under marbel clading for column between axis(2-5)&(E-F) for area (Z4) From ground to fifth Floor as Per Attached Sketch. | ARCH | Marble Rockwool | Z4 | ML | 43817 | 43821 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1207 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (13-17)&(G-K) for area (Z2) at seventh floor as Per Attached Sketch. | ARCH | Marble sill | Z2 | 7th | 43820 | 43825 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1208 | Check fixation for marble threshold for flooring at seventh floor between axis(12-18)&(F-L) for area (Z2) as Per Attached Sketch. | ARCH | Marble Thresholed | Z2 | 7th | 43820 | 43825 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1209 | Check fixation for ceramic tiles for walls and flooring at ground floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | GF | 43820 | 43825 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1210 | check fixation of steel door frames at second floor for area (Z3B,4,5)between axes (A_L) (1_9) as per attached sketch. | ARCH | Steel doors Frame | Z3B,4,5 | 2nd | 43821 | 43825 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1211 | check fixation of steel door frames at third floor for area (Z3B,4,5)between axes (A_L) (1_9) as per attached sketch. | ARCH | Steel doors Frame | Z3B,4,5 | 3rd | 43821 | 43825 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1212 | check fixation of steel door frames at second floor for area (Z1,2,3A)between axes (A_L) (10-18) as per attached sketch. | ARCH | Steel doors Frame | Z1,2,3A | 2nd | 43822 | 43825 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1213 | check fixation of steel door frames at third floor for area (Z1,2,3A)between axes (A_L) (10-18) as per attached sketch. | ARCH | Steel doors Frame | Z1,2,3A | 3rd | 43822 | 43825 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1214 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (7-12)&(F-L) for area (Z3) at Eighth floor as Per Attached Sketch. | ARCH | Marble sill | Z3 | 8th | 43822 | 43825 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1215 | Check fixation of corner guard at first basement for zone(1,2,3,4,5,6) between axis (A-L)/1-18) as Per Attached Sketch. | ARCH | Corner Guard | Z1,2,3,4,5,6 | B1 | 43823 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1216 | Check fixation of corner guard at second basement for zone(1,2,3,4,5,6) between axis (A-L)/1-18) as Per Attached Sketch. | ARCH | Corner Guard | Z1,2,3,4,5,6 | B2 | 43823 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1217 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (1-7)&(A-L) for area (Z3B,4,5) at second floor as Per Attached Sketch. | ARCH | Marble sill | Z3B,4,5 | 2nd | 43823 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1218 | Check full closure for walls of second floorat zone 5 between axis(A-F)/(1-6) as Per Attached Sketch. | ARCH | Full Closure | Z5 | 2nd | 43823 | 43834 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1219 | check fixation of steel door frames at first floor for area (Z1,2,3A)between axes (A_L) (10_17) as per attached sketch. | ARCH | Steel doors Frame | Z1,2,3A | 1st | 43824 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1220 | Check full closure for walls of second floorat zone 1 between axis(A-F)/(13-18) as Per Attached Sketch. | ARCH | Full Closure | Z1 | 2nd | 43824 | 43837 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1221 | check cement based waterproof coating for pantry and janitor room between axes (G-H)&(14-16) at Seventh floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 7th | 43824 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1222 | water test for the pantry and janitor room at Seventh floor level (328.10) between axis (G-H)&(14-16) for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 7th | 43824 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1223 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at seventh floor between axis(1-7)&(F-L) for area (Z4) as Per Attached Sketch. | ARCH | Porcelain | Z4 | 7th | 43824 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1224 | First course of blockwork between axes (12-15)&(E-H) at GROUND floor(300.10 ) for area (Z2) as Per Attached Sketch. | ARCH | Blockwork First course | Z2 | GF | 43825 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1225 | Check fixation for ceramic tiles for walls and flooring at fourth floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | 4th | 43829 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1226 | Check fixation for ceramic tiles for walls and flooring at sixth floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | 6th | 43829 | 43834 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1227 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at ninth floor between axis(7-12)&(F-K) for area (Z3) as Per Attached Sketch. | ARCH | Porcelain | Z3 | 9th | 43829 | 43849 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1228 | check fixation of steel door frames at ground floor for area (Z1,2,3A)between axes (A_L) (10-18) as per attached sketch. | ARCH | Steel doors Frame | Z1,2,3A | GF | 43829 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1229 | Check first fix for wooden doors at Fifth floor between axis (2-9)&(B-L) for area(Z4,5,3B) as Per Attached Sketch. | ARCH | Wooden door Frame | Z4,5,3B | 5th | 43829 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1230 | First course of blockwork between axes (4-9) & (J_E) at GROUND floor(300.10 ) for area (Z4,5,3B) as Per Attached Sketch. | ARCH | Blockwork First course | Z3B,4,5 | GF | 43831 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1231 | check fixation of steel door frames at ground floor for area (Z4,5,3B)between axes (A_L) (1-8) as per attached sketch. | ARCH | Steel doors Frame | Z4,5,3B | GF | 43831 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1232 | check fixation of steel door frames at First floor for area (Z4,5,3B)between axes (A_K) (1-9) as per attached sketch. | ARCH | Steel doors Frame | Z4,5,3B | 1st | 43831 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1233 | Check fixation of marble for flooring of corridor infront of elevetors at zone(1,2) between axis (D-J)/(15-16) at Third floor as Per Attached Sketch. | ARCH | Marble Flooring | Z1,2 | 3rd | 43831 | 43837 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1234 | Check fixation of marble for flooring of corridor infront of elevetors at zone(1,2) between axis (D-J)/(15-16) at Fourth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z1,2 | 4th | 43831 | 43837 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1235 | Check fixation of marble for flooring of corridor infront of elevetors at zone(2) between axis (J-G)/(15-16) at Fifth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z2 | 5th | 43831 | 43837 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1236 | Check fixation of marble for walls of corridor infront of elevetors at zone(1) between axis (D-E)/(15-16) at Ground floor as Per Attached Sketch. | ARCH | Marble Walls | Z1 | GF | 43831 | 43837 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1237 | Check fixation of marble for walls of corridor infront of elevetors at zone(1) between axis (D-E)/(15-16) at Second floor as Per Attached Sketch. | ARCH | Marble Walls | Z1 | 2nd | 43831 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1238 | Check fixation of marble for walls for Enterance at zone (2) between axis (F-G)/(16-17) at Ground floor as Per Attached Sketch. | ARCH | Marble Walls | Z2 | GF | 43831 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1239 | check fixation of sub structure under wooden clading at Z1 between axis (D_E)(15-16) at Ground floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z1 | GF | 43831 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1240 | check fixation of sub structure under wooden clading at Z1 between axis (D_E)(15-16) at First floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z1 | 1st | 43831 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1241 | Check fixation of marble for flooring of corridor infront of elevetors at zone(4,5) between axis (D-K)/(2-5) at first floor as Per Attached Sketch. | ARCH | Marble Flooring | Z4,5 | 1st | 43831 | 43837 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1242 | Check fixation of marble for flooring of corridor infront of elevetors at zone(4,5) between axis (D-K)/(2-5) at second floor as Per Attached Sketch. | ARCH | Marble Flooring | Z4,5 | 2nd | 43831 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1243 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (2-9)&(A-L) for area (Z3B,4,5) at first floor as Per Attached Sketch. | ARCH | Marble sill | Z3B,4,5 | 1st | 43831 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1244 | Check fixation for marble sill for interior curtin wall upstand between axis (2-9)&(A-L) for area (Z3B,4,5) at first floor as Per Attached Sketch. | ARCH | Marble sill curtain wall | Z3B,4,5 | 1st | 43831 | 43837 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1245 | Check fixation for marble sill for interior curtin wall upstand between axis (2-9)&(A-L) for area (Z3B,4,5) at second floor as Per Attached Sketch. | ARCH | Marble sill | Z3B,4,5 | 2nd | 43831 | 43837 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1246 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Eighth floor between axis(7-12)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | Porcelain | Z3 | 8th | 43832 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1247 | Check fixation for double black marble for stair from second floor to third floor (308.10 to 312.10) between axis(15-16)&(D-F) for area (Z1) as Per Attached Sketch. | ARCH | Marble Stairs | Z1 | ML | 43834 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1248 | check fixation for interlock for walkway of landscape as Per Attached Sketch. | ARCH | Interlock |  | EX | 43834 | 43845 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1249 | Check full closure for walls of third floor at zone 1 between axis(A-F)/(13-18) as Per Attached Sketch. | ARCH | Full Closure | Z1 | 3rd | 43834 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1250 | Check fixation for marble sill for interior curtin wall upstand between axis (13-18)&(A-F) for area (Z1) at third floor as Per Attached Sketch. | ARCH | Marble sill | Z1 | 3rd | 43834 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1251 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (12-17)&(A-F) for area (Z1) at third floor as Per Attached Sketch. | ARCH | Marble sill | Z1 | 3rd | 43834 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1252 | Check fixation for marble sill for interior curtin wall upstand between axis (14-18)&(G-L) for area (Z2) at third floor as Per Attached Sketch. | ARCH | Marble sill | Z2 | 3rd | 43834 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1253 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (12-17)&(E-L) for area (Z2) at third floor as Per Attached Sketch. | ARCH | Marble sill | Z2 | 3rd | 43834 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1254 | Check fixation for marble sill for interior curtin wall upstand between axis (10-13)&(F-L) for area (Z3A) at third floor as Per Attached Sketch. | ARCH | Marble sill | Z3A | 3rd | 43834 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1255 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (11-13)&(F-L) for area (Z3A) at third floor as Per Attached Sketch. | ARCH | Marble sill | Z3A | 3rd | 43834 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1256 | Check firs fix for false celing for VIP entrance between axis (9-10)&(G-K) for area (Z3) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3 | GF | 43834 | 43845 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1257 | check fixation for interlock for walkway of landscape as Per Attached Sketch. | ARCH | Interlock |  | EX | 43834 | 43845 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1258 | Check fixation for ceramic tiles for walls and flooring at ground floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | GF | 43836 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1259 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (14-17)&(J-K) for area (Z2) at seventh floor as Per Attached Sketch. | ARCH | Marble sill | Z2 | 7th | 43836 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1260 | Check fixation for marble threshold for flooring at seventh floor between axis(14-17)&(G-K) for area (Z2) as Per Attached Sketch. | ARCH | Marble Thresholed | Z2 | 7th | 43836 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1261 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (7-12)&(G-H) for area (Z3) at Eighth floor as Per Attached Sketch. | ARCH | Marble sill | Z3 | 8th | 43836 | 43846 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1262 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (2-8)&(A-K) for area (Z3B,4,5) at Third floor as Per Attached Sketch. | ARCH | Marble sill | Z3B,4,5 | 3rd | 43836 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1263 | Check fixation for marble sill for interior curtin wall upstand between axis (1-9)&(A-L) for area (Z3B,4,5) at Third floor as Per Attached Sketch. | ARCH | Marble sill | Z3B,4,5 | 3rd | 43836 | 43846 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1264 | check fixation of steel door leaf and accessories at second floor for area (Z1,2,3A)between axes (A_K) (10-17) as per attached sketch. | ARCH | Steel doors Leaf | Z1,2,3A | 2nd | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1265 | Check first fix for wooden doors frames at First floor between axis (10-18)&(A-K) for area(Z1,2,3A) as Per Attached Sketch. | ARCH | Wooden door Frame | Z1,2,3A | 1st | 43836 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1266 | Check fixation and installation for Terrazo Tiles under carpet between axis(9-10)&(F-L) for area (Z3) at Seventh Floor as Per Attached Sketch. | ARCH | Terrazo Roof | Z3 | 7th | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1267 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at seventh floor between axis(7-12)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | Porcelain | Z3 | 7th | 43836 | 43849 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1268 | Check first fix for wooden doors frames at First floor between axis (2-9)&(A-L) for area(Z4,5,3B) as Per Attached Sketch. | ARCH | Wooden door Frame | Z4,5,3B | 1st | 43836 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1269 | check fixation of steel door leaf and accessories at second floor for area (Z4,5,3B)between axes (A_K) (2-9) as per attached sketch. | ARCH | Steel doors Leaf | Z4,5,3B | 2nd | 43836 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1270 | check fixation of steel door frames at First floor for area (Z4,5,3B)between axes (B-K) (2-9) as per attached sketch. | ARCH | Steel doors Frame | Z4,5,3B | 1st | 43836 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1271 | check fixation of steel door frames at second floor for area (Z4,5,3B)between axes (A_K) (1-9) as per attached sketch. | ARCH | Steel doors Frame | Z4,5,3B | 2nd | 43836 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1272 | check fixation of steel door frames at third floor for area (Z3B,4,5)between axes (B-K) (2_9) as per attached sketch. | ARCH | Steel doors Frame | Z3B,4,5 | 3rd | 43836 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1273 | check fixation of steel door frames at fourth floor for area (Z3B,4,5)between axes (A-K) (2_9) as per attached sketch. | ARCH | Steel doors Frame | Z3B,4,5 | 4th | 43836 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1274 | check fixation of steel door frames at fifth floor for area (Z3B,4,5)between axes (A-K) (2_9) as per attached sketch. | ARCH | Steel doors Frame | Z3B,4,5 | 5th | 43836 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1275 | check fixation of steel door frames at sixth floor for area (Z3B,4)between axes (F-K) (1_9) as per attached sketch. | ARCH | Steel doors Frame | Z3B,4,5 | 6th | 43836 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1276 | Check fixation of marble for flooring of corridor infront of elevetors at zone(4) between axis (G-K)/(3-4) at second floor as Per Attached Sketch. | ARCH | Marble Flooring | Z4 | 2nd | 43838 | 43845 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1277 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Eighth floor between axis(8-12)&(F-K) for area (Z3) as Per Attached Sketch. | ARCH | Porcelain | Z3 | 8th | 43838 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1278 | check fixation of steel door leaf without accessories at third floor for area (3B,Z4)between axes (F_L) (1-9) as per attached sketch. | ARCH | Steel doors Leaf | Z3B,4 | 3rd | 43841 | 43845 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1279 | Check fixation for marble threshold for flooring at seventh floor between axis(1-7)&(F-L) for area (Z4) as Per Attached Sketch. | ARCH | Marble Thresholed | Z4 | 7th | 43841 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1280 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (1-7)&(G-K) for area (Z4) at seventh floor as Per Attached Sketch. | ARCH | Marble sill | Z4 | 7th | 43841 | 43846 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1281 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (7-12)&(G-H) for area (Z3) at Ninth floor as Per Attached Sketch. | ARCH | Marble sill | Z3 | 9th | 43842 | 43849 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1282 | Check for Final Plaster between axes (13-18)&(E-L) at Ground floor(300.10) for area (Z1) as Per Attached Sketch. | ARCH | Final Plaster | Z1 | GF | 43843 | 43846 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1283 | Check for Final Plaster between axes (13-18)&(E-L) at Ground floor(300.10) for area (Z2) as Per Attached Sketch. | ARCH | Final Plaster | Z2 | GF | 43843 | 43846 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1284 | check fixation of steel door leaf without accessories at third floor for area (1,2,3A)between axes (A-L) (10-17) as per attached sketch. | ARCH | Steel doors Leaf | Z1,2,3A | 3rd | 43844 | 43849 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1285 | Full Height of blockwork between axes (4-9) & (J_E) at ground floor(300.10 ) for area (3B,Z4,5) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3B,4,5 | GF | 43844 | 43849 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1286 | Check Surface Prepration and dots and accessories for plaster works between axes (4-9)&(J_E) at ground floor for area (3B,Z4,5) as Per Attached Sketch. | ARCH | Plaster Dots | Z3B,4,5 | GF | 43844 | 43849 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1287 | Check full closure for walls of fifth floor at zone 5 between axis(A-F)/(1-7) as Per Attached Sketch. | ARCH | Full Closure | Z5 | 5th | 43844 | 43849 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1288 | check fixation of steel door frames at Fourth floor for area Z(1,2,3A)between axes (A_K) (10-17) as per attached sketch. | ARCH | Steel doors Frame | Z1,2,3A | 4th | 43848 | 43856 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1289 | check crystalline waterproofing for water tank(flooring-walls-ceiling) between axes (G_L)/(1-2) at zone(4) as per attached sketch. | ARCH | Crystaline | Z4 | ML | 43848 | 43857 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1290 | check fixation of interior expansion joint at ground floor between axes (E-F)/(2-3) at zone(5) as per attached sketch. | ARCH | Expansion Joint | Z5 | GF | 43850 | 43856 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1291 | check fixation of interior expansion joint at second floor between axes (E-F)/(2-6) at zone(5) as per attached sketch. | ARCH | Expansion Joint | Z5 | 2nd | 43850 | 43856 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1292 | check fixation of interior expansion joint at third floor between axes (E-F)/(2-5) at zone(5) as per attached sketch. | ARCH | Expansion Joint | Z5 | 3rd | 43850 | 43856 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1293 | check fixation of steel door leaf without accessories at first basement for area (1,2,3,4,5,6)between axes (A-L) (1-18) as per attached sketch. | ARCH | Steel doors Leaf | Z1,2,3,4,5,6 | B1 | 43851 | 43857 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1294 | First course of blockwork between axes (3-16) & (0-G) at second basement for area (1,4,5) as Per Attached Sketch. | ARCH | Blockwork First course | Z1,4,5 | B2 | 43851 | 43857 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1295 | First course of blockwork between axes (2-17) & (A-B) at first basement for area (1,5) as Per Attached Sketch. | ARCH | Blockwork First course | Z1,5 | B2 | 43851 | 43857 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1296 | check fixation for wheel stopper at second basement between axes (A-L)/(1-18) at zone(1,2,3,4,5,6) as per attached sketch. | ARCH | Wheel Stopper | Z1,2,3,4,5,6 | B2 | 43851 | 43857 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1297 | check cement based waterproof coating for Toilet between axes (J_L)(7-9) at Ninth floor for area (Z3B) as per attached sketch. | ARCH | Water Proofing Cement base | Z3B | 9th | 43851 | 43862 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1298 | water test for toilet at ninth floor level (338.10) between axis (J_L)/(7-9) for area (Z3B) as per attached sketch. | ARCH | Water Test | Z3B | 9th | 43851 | 43862 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1299 | check fixation of interior expansion joint at ground floor between axes (E-F)/(14-17) at zone(1) as per attached sketch. | ARCH | Expansion Joint | Z1 | GF | 43850 | 43857 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1300 | check fixation of interior expansion joint at second floor between axes (E-F)/(14-17) at zone(1) as per attached sketch.(walls and flooring only) | ARCH | Expansion Joint | Z1 | 2nd | 43850 | 43857 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1301 | check fixation of interior expansion joint at third floor between axes (E-F)/(14-17) at zone(1) as per attached sketch. | ARCH | Expansion Joint | Z1 | 3rd | 43850 | 43857 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1302 | Full Height of blockwork between axes (4-7)&(E-L) at ground floor(300.10) for area (Z4) as Per Attached Sketch. | ARCH | Blockwork Full height | Z4 | GF | 43851 | 43857 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1303 | Check Surface Prepration and dots and accessories for plaster works between axes (E-L)&(4-7) at Ground floor(300.10) for area (Z4) as Per Attached Sketch. | ARCH | Plaster Dots | Z4 | GF | 43851 | 43857 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1304 | Check for Final Plaster between axes (1-7)&(E-L) at Ground floor(300.10) for area (Z4) as Per Attached Sketch. | ARCH | Final Plaster | Z4 | GF | 43851 | 43857 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1305 | Check for Final Plaster between axes (1-7)&(A-F) at ground floor for area (5) as Per Attached Sketch. | ARCH | Final Plaster | Z5 | GF | 43852 | 43856 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1306 | Check for Final Plaster between axes (7-9)&(G-J) at ground floor for area (3B) as Per Attached Sketch. | ARCH | Final Plaster | Z3B | GF | 43852 | 43856 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1307 | Check full closure for walls of first floor floor at zone (1) between axis(A-G)/(13-18) as Per Attached Sketch. | ARCH | Full Closure | Z1 | 1st | 43852 | 43856 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1308 | Check full closure for walls of first floor at zone (5) between axis(A-F)/(1-7) as Per Attached Sketch. | ARCH | Full Closure | Z5 | 1st | 43856 | 43862 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1309 | Check first fix for false celing at first floor between axis (12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1 | 1st | 43857 | 43866 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1310 | Check full closure for walls of Second floor at zone (3B) between axis(E-L)/(6-9) as Per Attached Sketch. | ARCH | Full Closure | Z3B | 2nd | 43857 | 43862 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1311 | Check full closure for walls of Second floor at zone (4) between axis(E-L)/(1-7) as Per Attached Sketch. | ARCH | Full Closure | Z4 | 2nd | 43857 | 43862 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1312 | Check first fix for G.B sheet(Bulk head) at second floor between axis (6-9)&(E-L) for area (3B) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3B | 2nd | 43857 | 43862 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1313 | Check first fix for G.B sheet(Bulk head) at second floor between axis (1-7)&(E-L) for area (4) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z4 | 2nd | 43857 | 43862 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1314 | Check first fix for false celing(Bulk head) at second floor between axis (1-6)&(A-F) for area (5) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z5 | 2nd | 43857 | 43862 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1315 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (2-7)&(E-L) for area (Z4) at first floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z4 | 1st | 43857 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1316 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (2-5)&(A-E) for area (Z5) at first floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z5 | 1st | 43857 | 43862 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1317 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (2-7)&(E-K) for area (Z4) at second floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z4 | 2nd | 43857 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1318 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (2-5)&(A-E) for area (Z5) at second floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z5 | 2nd | 43857 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1319 | Check fixation of marble for flooring of corridor infront of elevetors at zone(4,5) between axis (D-G)/(2-5) at Ground floor as Per Attached Sketch. | ARCH | Marble Flooring | Z4,5 | GF | 43858 | 43866 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1320 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Ground between axis(1-7)&(E-L) for area (Z4) as Per Attached Sketch. | ARCH | Porcelain | Z4 | GF | 43858 | 43866 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1321 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Ground between axis(1-6)&(A-F) for area (Z5) as Per Attached Sketch. | ARCH | Porcelain | Z5 | GF | 43858 | 43866 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1322 | Check fixation and installation for Terrazo Tiles between axis(12-18)&(A-F) for area (Z1) at Second Floor as Per Attached Sketch. | ARCH | Terrazo Roof | Z1 | 2nd | 43859 | 43866 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1323 | Check full closure for walls of Third floor at zone (3B,4,5) between axis(E-L)/(2-9) as Per Attached Sketch. | ARCH | Full Closure | Z3B,4,5 | 3rd | 43859 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1324 | Check fixation and installation for Terrazo Tiles between axis(12-18)&(F-L) for area (Z2) at Second Floor as Per Attached Sketch. | ARCH | Terrazo Roof | Z2 | 2nd | 43859 | 43866 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1325 | Check fixation for kalimera mrable form ground floor to sixth floor between axis(E-L)/(2-9) as Per Attached Sketch. | ARCH | Kalimera Marble |  | ML | 43859 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1326 | Check full closure for Toilet At Second floor for area zone (3B,4,5) between axis(E-L)/(1-9) as Per Attached Sketch. | ARCH | Full Closure | Z3B,4,5 | 2nd | 43859 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1327 | Check fixation for double black marble for stair from Ground floor to First floor (300.10 to 304.10) between axis(15-16)&(D-F) for area (Z1) as Per Attached Sketch. | ARCH | Marble Stairs | Z1 | GF | 43859 | 43866 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1328 | Check fixation for double black marble for stair from First floor to Second floor (304.10 to 308.10) between axis(15-16)&(D-F) for area (Z1) as Per Attached Sketch. | ARCH | Marble Stairs | Z1 | 1st | 43859 | 43866 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1329 | check fixation of steel door leaf at first floor for area (3B,4,5)between axes (A-K) (3-9) as per attached sketch. | ARCH | Steel doors Leaf | Z3B,4,5 | 1st | 43860 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1330 | check fixation of steel door leaf at first floor for area (1,2,3A)between axes (A-K) (10-17) as per attached sketch. | ARCH | Steel doors Leaf | Z1,2,3A | 1st | 43860 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1331 | Check full closure for walls of first floor at zone (2) between axis(E-L)/(12-18) as Per Attached Sketch. | ARCH | Full Closure | Z2 | 1st | 43864 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1332 | Check first fix for false celing at first floor between axis (12-18)&(E-L) for area (2) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z2 | 1st | 43864 | 43865 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1333 | Check full closure for walls of third floor at zone (1) between axis(A-F)/(13-18) as Per Attached Sketch. | ARCH | Full Closure | Z1 | 3rd | 43864 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1334 | Check first fix for false celing at third floor between axis (13-18)&(A-F) for area (1) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1 | 3rd | 43864 | 43866 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1335 | Check first fix for wooden doors frames at fourth floor between axis (10-18)&(A-L) for area(1,2,3A) as Per Attached Sketch. | ARCH | Wooden door Frame | Z1,2,3A | 4th | 43864 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1336 | Check full closure for walls of third floor at zone (3B,4) between axis(F-L)/(2-10) as Per Attached Sketch. | ARCH | Full Closure | Z3B,4 | 3rd | 43864 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1337 | Check first fix for G.B sheet(Bulk head) at first floor between axis (12-18)&(E-L) for area (2) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z2 | 1st | 43865 | 43874 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1338 | Check first fix for G.B sheet(Bulk head) at third floor between axis (13-18)&(A-F) for area (1) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1 | 3rd | 43865 | 43874 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1339 | Check first fix for G.B sheet(Bulk head) at first floor between axis (12-18)&(A-F) for area (1) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1 | 1st | 43866 | 43874 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1340 | check fixation of steel door frames at fifth floor for area (1,2,3A)between axes (A_L) (10-17) as per attached sketch. | ARCH | Steel doors Frame | Z1,2,3A | 5th | 43867 | 43874 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1341 | check fixation of steel door frames at sixth floor for area (2,3A)between axes (G-K) (10-17) as per attached sketch. | ARCH | Steel doors Frame | Z2,3A | 6th | 43867 | 43874 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1342 | check cement based waterproof coating for Kitchen between axes (H_L)(9-10) at Ninth floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 9th | 43870 | 43874 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1343 | water test for Kitchen at ninth floor level (338.10) between axis (H_L)/(9-10) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 9th | 43870 | 43874 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1344 | check installation of wooden door leaf at second floor for area (3B,4,5)between axes (A-L) (1-9) as per attached sketch. | ARCH | Wooden door Leaf | Z3B,4,5 | 2nd | 43871 | 43885 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1345 | check installation of wooden door leaf at third floor for area (3B,4,5)between axes (A-L) (1-9) as per attached sketch. | ARCH | Wooden door Leaf | Z3B,4,5 | 3rd | 43871 | 43885 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1346 | check installation of wooden door leaf at First floor for area (1,2,3A)between axes (A-L) (10-18) as per attached sketch. | ARCH | Wooden door Leaf | Z1,2,3A | 1st | 43871 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1347 | check installation of wooden door leaf at Second floor for area (1,2,3A)between axes (A-L) (10-18) as per attached sketch. | ARCH | Wooden door Leaf | Z1,2,3A | 2nd | 43871 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1348 | Check fixation and installation for Terrazo Tiles between axis(1-7)&(F-L) for area (Z4) at Second Floor as Per Attached Sketch. | ARCH | Terrazo Roof | Z4 | 2nd | 43877 | 43885 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1349 | Check full closure for walls of fifth floor at zone 4 between axis(E-L)/(1-7) as Per Attached Sketch. | ARCH | Full Closure | Z4 | 5th | 43877 | 43885 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1350 | check fixation of steel door leaf without accessories at second basement for area (1,2,3,4,5,6)between axes (A-L) (1-18) as per attached sketch. | ARCH | Steel doors Leaf | Z1,2,3,4,5,6 | B2 | 43879 | 43893 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1351 | check fixation of steel door frames at seventh floor for area (2)between axes (G-K) (12-17) as per attached sketch. | ARCH | Steel doors Frame | Z2 | 7th | 43880 | 43893 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1352 | check fixation of steel door frames at seventh floor for area (3)between axes (G-K) (7-12) as per attached sketch. | ARCH | Steel doors Frame | Z3 | 7th | 43880 | 43893 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1353 | check fixation of steel door frames at seventh floor for area (4)between axes (G-K) (2-7) as per attached sketch. | ARCH | Steel doors Frame | Z4 | 7th | 43880 | 43893 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1354 | check fixation of steel door frames at eighth floor for area (3)between axes (H-K) (8-11) as per attached sketch. | ARCH | Steel doors Frame | Z3 | 8th | 43880 | 43893 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1355 | check fixation of steel door frames at ninth floor for area (3) between axes (H-K) (8-11) as per attached sketch. | ARCH | Steel doors Frame | Z3 | 9th | 43880 | 43893 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1356 | Check full closure for walls of ninth floor at zone (3) between axis(H-K)/(9-10) as Per Attached Sketch. | ARCH | Full Closure | Z3 | 9th | 43884 | 43893 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1357 | Check full closure for walls of first floor at zone (3A) between axis(E-L)/(10-13) as Per Attached Sketch. | ARCH | Full Closure | Z3A | 1st | 43885 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1358 | Check first fix for G.B sheet(Bulk head) at first floor between axis (10-13)&(E-L) for area (3A) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3A | 1st | 43885 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1359 | Check full closure for walls of third floor at zone (2) between axis(E-L)/(12-18) as Per Attached Sketch. | ARCH | Full Closure | Z2 | 3rd | 43885 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1360 | Check first fix for G.B sheet(Bulk head) at third floor between axis (12-18)&(E-L) for area (2) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z2 | 3rd | 43885 | 43911 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1361 | Check full closure for walls of third floor at zone (3A) between axis(E-L)/(10-13) as Per Attached Sketch. | ARCH | Full Closure | Z3A | 3rd | 43885 | 43911 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1362 | Check first fix for G.B sheet(Bulk head) at third floor between axis (10-13)&(E-L) for area (3A) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3A | 3rd | 43885 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1363 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (7-12)&(G-H) for area (Z3) at ninth floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z3 | 9th | 43888 | 43893 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1364 | Check fixation of steel chassis under toilet marble between axis (8-11)&(J-K) for area (Z3) at seventh floor as Per Attached Sketch. | ARCH | Marble Toilet Chassis | Z3 | 9th | 43888 | 43893 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1365 | Check fixation of sky light between axis (15-16)&(E-G) for area (2) as Per Attached Sketch. | ARCH | Sky Light | Z2 | 6th | 43892 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1366 | Check fixation of sky light between axis (3-4)&(E-G) for area (4) as Per Attached Sketch. | ARCH | Sky Light | Z4 | 6th | 43892 | 43911 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1367 | Check full closure for walls of Seventh floor at zone (4) between axis (F-L)/(1-7) as Per Attached Sketch. | ARCH | Full Closure | Z4 | 7th | 43892 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1368 | Check full closure for walls of Eighth floor at zone (3) between axis (E- L)/(6-15) as Per Attached Sketch. | ARCH | Full Closure | Z3 | 8th | 43892 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1369 | Check fixation of stainless steel eagle at façade between axis (9-10)&(F-G) at eighth for area (3) as Per Attached Sketch. | ARCH | Eagle | Z3 | 8th | 43892 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1370 | Check fixation of stainless steel eagle at façade between axis (9-10)&(K-L) at eighth for area (3) as Per Attached Sketch. | ARCH | Eagle | Z3 | 8th | 43892 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1371 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (10-18)&(A-L) for area (Z1,2,3A) at first floor as Per Attached Sketch. | ARCH | Marble sill | Z1,2,3A | 1st | 43894 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1372 | Check fixation for marble sill for interior curtin wall upstand between axis (10-18)&(A-L) for area (Z1,2,3A) at first floor as Per Attached Sketch. | ARCH | Marble sill | Z1,2,3A | 1st | 43894 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1373 | Check full closure for walls of Seventh floor at zone (2) between axis (F-L)/(12-18) as Per Attached Sketch. | ARCH | Full Closure | Z2 | 7th | 43894 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1374 | Check fixation for Marble tiles for Toilet for walls and flooring at Ninth floor between axis(9-11)&(H-K) for area (Z3) as Per Attached Sketch. | ARCH | Marble Toilet | Z3 | 9th | 43895 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1375 | Check fixation for Marble tiles for Kitchen for flooring at Ninth floor between axis(9-10)&(H-J) for area (Z3) as Per Attached Sketch. | ARCH | Marble Flooring | Z3 | 9th | 43897 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1376 | Check fixation for Ceramic tiles for Kitchen for walls at Ninth floor between axis(9-10)&(H-J) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls | Z3 | 9th | 43897 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1377 | check cement based waterproof coating for garbage room between axes (G-H)&(3-4) at seventh floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 7th | 43900 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1378 | water test for garbage room between axes (G-H)&(3-4) at seventh floor for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 7th | 43900 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1379 | check cement based waterproof coating for garbage room between axes (G-H)&(14-16) at seventh floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 7th | 43900 | 43911 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1380 | water test for garbage room between axes (G-H)&(14-16) at seventh floor for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 7th | 43900 | 43911 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1381 | check cement based waterproof coating for garbage room between axes (G-H)&(15-16) at second floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 2nd | 43909 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1382 | water test for garbage room between axes (G-H)&(15-16) at second floor for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 2nd | 43909 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1383 | check cement based waterproof coating for garbage room between axes (G-H)&(15-16) at third floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 3rd | 43909 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1384 | water test for garbage room between axes (G-H)&(15-16) at third floor for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 3rd | 43909 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1385 | check cement based waterproof coating for garbage room between axes (G-H)&(15-16) at fourth floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 4th | 43909 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1386 | water test for garbage room between axes (G-H)&(15-16) at fourth floor for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 4th | 43909 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1387 | check cement based waterproof coating for garbage room between axes (G-H)&(15-16) at fifth floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 5th | 43909 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1388 | water test for garbage room between axes (G-H)&(15-16) at fifth floor for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 5th | 43909 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1389 | Check first fix for G.B sheet(Bulk head) at Seventh floor between axis (1-7)&(F-L) for area (4) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z4 | 7th | 43911 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1390 | check cement based waterproof coating for garbage room between axes (G-H)&(3-4) at First floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 1st | 43911 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1391 | water test for garbage room between axes (G-H)&(3-4) at First floor for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 1st | 43911 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1392 | check cement based waterproof coating for garbage room between axes (G-H)&(3-4) at Second floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 2nd | 43911 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1393 | water test for garbage room between axes (G-H)&(3-4) at Second floor for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 2nd | 43911 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1394 | check cement based waterproof coating for garbage room between axes (G-H)&(3-4) at Third floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 3rd | 43911 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1395 | water test for garbage room between axes (G-H)&(3-4) at Third floor for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 3rd | 43911 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1396 | check cement based waterproof coating for garbage room between axes (G-H)&(3-4) at Fourth floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 4th | 43911 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1397 | water test for garbage room between axes (G-H)&(3-4) at Fourth floor for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 4th | 43911 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1398 | check cement based waterproof coating for garbage room between axes (G-H)&(3-4) at Fifth floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 5th | 43911 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1399 | water test for garbage room between axes (G-H)&(3-4) at Fifth floor for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 5th | 43911 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1400 | Check first fix for G.B sheet(Bulk head) at Ninth floor between axis (7-12)&(F-L) for area (3) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3 | 9th | 43913 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1401 | Check full closure for walls of Seventh floor at zone (3) between axis (E-L)/(7-13) as Per Attached Sketch. | ARCH | Full Closure | Z3 | 7th | 43914 | 43928 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1402 | Check fixation for Marble tiles for Toilet for walls and flooring at Ninth floor between axis(9-11)&(H-K) for area (Z3) as Per Attached Sketch. | ARCH | Marble Toilet | Z3 | 9th | 43927 | 43934 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1403 | Check first fix for G.B sheet(Bulk head) at Seventh floor between axis (12-18)&(F-L) for area (2) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z2 | 7th | 43934 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1404 | Check fixation for toilet accessories at first floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Toilet Accessories | Z2 | 1st | 43935 | 43946 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1405 | Check fixation for toilet accessories at first floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Toilet Accessories | Z4 | 1st | 43935 | 43946 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1406 | Check fixation for toilet accessories at Second floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Toilet Accessories | Z4 | 2nd | 43935 | 43946 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1407 | Check fixation for toilet accessories at Second floor between axis(7-9)&(F-L) for area (Z3B) as Per Attached Sketch. | ARCH | Toilet Accessories | Z3B | 2nd | 43935 | 43950 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1408 | Check fixation for toilet accessories at Second floor between axis(1-6)&(D-F) for area (Z5) as Per Attached Sketch. | ARCH | Toilet Accessories | Z5 | 2nd | 43935 | 43950 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1409 | Check fixation for toilet accessories at Second floor between axis(10-12)&(F-L) for area (Z3A) as Per Attached Sketch. | ARCH | Toilet Accessories | Z3A | 2nd | 43935 | 43950 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1410 | Check fixation for toilet accessories at Third floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Toilet Accessories | Z2 | 3rd | 43935 | 43946 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1411 | Check fixation for toilet accessories at third floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Toilet Accessories | Z4 | 3rd | 43935 | 43946 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1412 | Check fixation for toilet accessories at fourth floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Toilet Accessories | Z4 | 4th | 43935 | 43946 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1413 | Check first fix for G.B sheet(Bulk head) at Eightth floor between axis (6-13)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3 | 8th | 43936 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1414 | Check first fix for closets and shelves at first floor between axis (10-12)&(E-L) for area (3A) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z3A | 1st | 43937 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1415 | Check full closure for walls of second floorat zone 2 between axis(F-L)/(12-18) as Per Attached Sketch. | ARCH | Full Closure | Z2 | 2nd | 43937 | 43950 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1416 | Check full closure for walls of second floorat zone 3A between axis(E-L)/(10-13) as Per Attached Sketch. | ARCH | Full Closure | Z3A | 2nd | 43937 | 43950 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1417 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (10-13)&(A-L) for area (Z1,23A) at third floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z1,2,3A | 3rd | 43937 | 43950 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1418 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (10-13)&(A-L) for area (Z1,23A) at fourth floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z1,2,3A | 4th | 43937 | 43950 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1419 | Check full closure for walls of Eighth floorat zone 3 between axis(F-L)/(9-10) as Per Attached Sketch. | ARCH | Full Closure | Z3 | 8th | 43940 | 43957 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1420 | Check full closure for walls of ninth floorat zone 3 between axis(F-L)/(9-10) as Per Attached Sketch. | ARCH | Full Closure | Z3 | 9th | 43940 | 43957 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1421 | Check first fix for G.B sheet(Bulk head) at Eighth floor between axis (9-10)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3 | 8th | 43940 | 43957 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1422 | Check first fix for G.B sheet(Bulk head) at ninth floor between axis (9-10)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3 | 9th | 43940 | 43957 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1423 | check fixation and installation for wood sub structure under wooden clading at Z3 between axis (G-L)(8-11) at ninth floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z3 | 9th | 43947 | 43950 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1424 | check fixation of steel door leaf without accessories at third floor for area (5)between axes (A-H) (3-5) as per attached sketch. | ARCH | Steel doors Leaf | Z5 | 3rd | 43948 | 43950 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1425 | check fixation of steel door leaf without accessories at fourth floor for area (3B,4,5)between axes (A-k) (3-9) as per attached sketch. | ARCH | Steel doors Leaf | Z3B,4,5 | 4th | 43948 | 43950 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1426 | check fixation of steel door leaf without accessories at fifth floor for area (3B,4,5)between axes (A-k) (3-9) as per attached sketch. | ARCH | Steel doors Leaf | Z3B,4,5 | 5th | 43948 | 43950 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1427 | check fixation of steel door leaf without accessories at sixth floor for area (3B,4)between axes (F-k) (1-9) as per attached sketch. | ARCH | Steel doors Leaf | Z3B,4 | 6th | 43948 | 43950 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1428 | check fixation of steel door leaf without accessories at Fourth floor for area (1,2,3A)between axes (A-k) (10-16) as per attached sketch. | ARCH | Steel doors Leaf | Z1,2,3A | 4th | 43948 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1429 | check fixation of steel door leaf without accessories at Fifth floor for area (1,2,3A)between axes (A-k) (10-16) as per attached sketch. | ARCH | Steel doors Leaf | Z1,2,3A | 5th | 43948 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1430 | check fixation of steel door leaf without accessories at Sixth floor for area (1,2,3A)between axes (A-k) (10-17) as per attached sketch. | ARCH | Steel doors Leaf | Z1,2,3A | 6th | 43948 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1431 | Check first fix for closets and shelves at Seventh floor between axis (2-17)&(F-k) for area (2,3,4) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z2,3,4 | 7th | 43948 | 43949 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1432 | Check first fix for closets and shelves at Eighth floor between axis (7-12)&(G-K) for area (3) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z3 | 8th | 43948 | 43949 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1433 | Check first fix for closets and shelves at Ninth floor between axis (8-11)&(H-k) for area (3) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z3 | 9th | 43948 | 43949 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1434 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (10-18)&(A-L) for area (Z1,2,3A) at fourth floor as Per Attached Sketch. | ARCH | Marble sill | Z1,2,3A | 4th | 43949 | 43957 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1435 | Check full closure for walls of third floor at zone (4,5) between axis(A-F)/(1-6) as Per Attached Sketch. | ARCH | Full Closure | Z4,5 | 3rd | 43949 | 43956 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1436 | check fixation of steel door leaf without accessories at Seventh floor for area (1,2,3A)between axes (F-k) (2-17) as per attached sketch. | ARCH | Steel doors Leaf | Z1,2,3A | 7th | 43949 | 43956 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1437 | check fixation of steel door leaf without accessories at Eighth floor for area (3)between axes (G-k) (7-12) as per attached sketch. | ARCH | Steel doors Leaf | Z3 | 8th | 43949 | 43956 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1438 | check fixation of steel door leaf without accessories at ninth floor for area (3)between axes (H-k) (8-11) as per attached sketch. | ARCH | Steel doors Leaf | Z3 | 9th | 43949 | 43956 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1439 | check cement based waterproof coating for janitor room between axes (G-H)&(3-4) at Fifth floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 5th | 43950 | 43956 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1440 | water test for janitor room between axes (G-H)&(3-4) at Fifth floor for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 5th | 43950 | 43956 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1441 | check cement based waterproof coating for janitor room between axes (G-H)&(3-4) at sixth floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | 6th | 43950 | 43956 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1442 | water test for janitor room between axes (G-H)&(3-4) at sixth floor for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | 6th | 43950 | 43956 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1443 | check cement based waterproof coating for toilet and garbage room between axes (F-H)&(2-5) at ground floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | GF | 43950 | 43956 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1444 | water test for toilet and garbage room between axes (F-H)&(2-5) at ground floor for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | GF | 43950 | 43956 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1445 | check cement based waterproof coating for Ablution between axes (B-C)&(4-5) at ground floor for area (Z5) as per attached sketch. | ARCH | Water Proofing Cement base | Z5 | GF | 43950 | 43956 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1446 | water test for Ablution between axes (B-C)&(4-5) at ground floor for area (Z5) as per attached sketch. | ARCH | Water Test | Z5 | GF | 43950 | 43956 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1447 | check fixation of garbage chute from ground to seventh floor for area (Z2) as Per Attached Sketch. | ARCH | Garbage Chute | Z2 | ML | 43950 | 43956 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1448 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (2-8)&(A-K) for area (Z4,5) at fourth floor as Per Attached Sketch. | ARCH | Marble sill | Z4,5 | 4th | 43950 | 43956 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1449 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at fourth floor between axis(1-6)&(A-F) for area (Z5) as Per Attached Sketch. | ARCH | Porcelain | Z5 | 4th | 43950 | 43956 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1450 | Check fixation of marble for walls of corridor infront of elevetors at zone(5) between axis (D-E)/(2-5) at Third floor as Per Attached Sketch. | ARCH | Marble Walls | Z5 | 3rd | 43953 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1451 | Check fixation of marble for walls of corridor infront of elevetors at zone(5) between axis (D-E)/(2-5) at Fourth floor as Per Attached Sketch. | ARCH | Marble Walls | Z5 | 4th | 43953 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1452 | Check fixation of marble for walls of corridor infront of elevetors at zone(5) between axis (D-E)/(2-5) at fifth floor as Per Attached Sketch. | ARCH | Marble Walls | Z5 | 5th | 43953 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1453 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (10-17)&(A-K) for area (Z1,2,3A) at first floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z1,2,3A | 1st | 43956 | 43965 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1454 | Check full closure for walls of Fourth floor at zone (4,5,3B) between axis(A-L)/(1-9) as Per Attached Sketch. | ARCH | Full Closure | Z4,5,3B | 4th | 43956 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1455 | check cement based waterproof coating for garbage room between axes (G-H)&(14-16) at First floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 1st | 43956 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1456 | water test for garbage room between axes (G-H)&(14-16) at First floor for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 1st | 43956 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1457 | check cement based waterproof coating for garbage room between axes (G-H)&(14-16) at Sixth floor for area (Z2) as per attached sketch. | ARCH | Water Proofing Cement base | Z2 | 6th | 43956 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1458 | water test for garbage room between axes (G-H)&(14-16) at Sixth floor for area (Z2) as per attached sketch. | ARCH | Water Test | Z2 | 6th | 43956 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1459 | Check full closure for walls of fifth floor at zone 1 between axis(A-F)/(12-18) as Per Attached Sketch. | ARCH | Full Closure | Z1 | 5th | 43956 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1460 | Check full closure for walls of fifth floor at zone 2 between axis(E-L)/(12-18) as Per Attached Sketch. | ARCH | Full Closure | Z2 | 5th | 43956 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1461 | Check full closure for walls of fifth floor at zone 3 between axis(E-L)/(6-13) as Per Attached Sketch. | ARCH | Full Closure | Z3 | 5th | 43956 | 43965 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1462 | check installation of wooden door leaf at First floor for area (4,5,3B)between axes (A-L) (2-9) as per attached sketch. | ARCH | Wooden door Leaf | Z4,5,3B | 1st | 43957 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1463 | Check fixation of marble for flooring of corridor infront of elevetors at zone(4,5,3B) between axis (D-F)/(2-5) at Fourth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z4,5,3B | 4th | 43957 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1464 | check installation of wooden door leaf at Eighth floor for area (3)between axes (F-L) (7-12) as per attached sketch. | ARCH | Wooden door Leaf | Z3 | 8th | 43957 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1465 | Check fixation and insulation for wood substructure for mirror in staff and public toilets for zone (3) between axes (J-K) (8-11) at ninth floor as Per Attached Sketch. | ARCH | Mirrors Toilet Wood sub. Strc. | Z3 | 9th | 43957 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1466 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (10-18)&(A-L) for area (Z1,2,3A) at Fifth floor as Per Attached Sketch. | ARCH | Marble sill | Z1,2,3A | 5th | 43960 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1467 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (10-18)&(A-L) for area (Z1,2,3A) at Sixth floor as Per Attached Sketch. | ARCH | Marble sill | Z1,2,3A | 6th | 43960 | 43965 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1468 | Check fixation of marble for flooring of corridor infront of elevetors at zone(3A) between axis (D-L)/(10-12) at Ground floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | GF | 43960 | 43965 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1469 | Check fixation of marble for walls for Enterance at zone (3A) between axis (D-L)/(10-12) at Ground floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | GF | 43960 | 43965 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1470 | Check full closure for walls of Fourth floor at zone (1,2,3A) between axis(A-L)/(10-18) as Per Attached Sketch. | ARCH | Full Closure | Z1,2,3A | 4th | 43960 | 43965 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1471 | Check full closure for walls of Sixth floor at zone (1,2,3A) between axis(A-L)/(10-18) as Per Attached Sketch. | ARCH | Full Closure | Z1,2,3A | 6th | 43960 | 43965 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1472 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (10-17)&(A-K) for area (Z1,2,3A) at Fifth floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z1,2,3A | 5th | 43960 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1473 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (10-17)&(A-K) for area (Z1,2,3A) at Sixth floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z1,2,3A | 6th | 43960 | 43969 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1474 | check installation of wooden door leaf at Ninth floor for area (3)between axes (E-L) (7-12) as per attached sketch. | ARCH | Wooden door Leaf | Z3 | 9th | 43961 | 43981 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1475 | water test for the pantry room at Ninth floor at level(338.10) between axes (J-K)&(8-9) for area (Z3) as per attached sketch. | ARCH | Water Test | Z3 | 9th | 43961 | 43969 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1476 | check cement based waterproof coating for pantry room between axes (J-K)&(8-9) at Ninth floor for area (Z3) as per attached sketch. | ARCH | Water Proofing Cement base | Z3 | 9th | 43961 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1477 | Check first fix for wooden doors frames at Ninth floor between axis (7-12)&(F-K) for area(3) as Per Attached Sketch. | ARCH | Wooden door Frame | Z3 | 9th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1478 | Check first fix for wooden doors frames at Eighth floor between axis (7-12)&(F-k) for area(3) as Per Attached Sketch. | ARCH | Wooden door Frame | Z3 | 8th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1479 | Check first fix for wooden doors frames at Seventh floor between axis (7-12)&(F-k) for area(3) as Per Attached Sketch. | ARCH | Wooden door Frame | Z3 | 7th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1480 | check installation of wooden door leaf at Seventh floor for area (3)between axes (F-k) (7-12) as per attached sketch. | ARCH | Wooden door Leaf | Z3 | 7th | 43964 | 43981 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1481 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (13-17)&(G-L) for area (Z2) at Seventh floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z2 | 7th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1482 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (2-6)&(G-L) for area (Z4) at Seventh floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z4 | 7th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1483 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (7-13)&(G-H) for area (Z3) at Eighth floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z3 | 8th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1484 | Check first fix for wooden doors frames at Fifth floor between axis (10-18)&(A-L) for area(1,2,3A) as Per Attached Sketch. | ARCH | Wooden door Frame | Z1,2,3A | 5th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1485 | Check first fix for wooden doors frames at sixth floor between axis (10-18)&(F-L) for area(2,3A) as Per Attached Sketch. | ARCH | Wooden door Frame | Z2,3A | 6th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1486 | Check fixation of marble for flooring of corridor infront of elevetors at zone(1) between axis (D-E)/(15-17) at fifth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z1 | 5th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1487 | check fixation for wheel stopper at first basement between axes (A-L)/(1-18) at zone(1,2,3,4,5,6) as per attached sketch. | ARCH | Wheel Stopper | Z1,2,3,4,5,6 | B1 | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1488 | second putty for acrylic points at first basement between axes (A-L)/(9-18) at zone(1,2,3A) as per attached sketch. | ARCH | Painting second Putty | Z1,2,3A | B1 | 43964 | 43967 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1489 | Check fixation of marble for walls of corridor infront of elevetors at zone(1) between axis (D-E)/(15-16) at third floor as Per Attached Sketch. | ARCH | Marble Walls | Z1 | 3rd | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1490 | Check fixation of marble for walls of corridor infront of elevetors at zone(1) between axis (D-E)/(15-16) at fourth floor as Per Attached Sketch. | ARCH | Marble Walls | Z1 | 4th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1491 | Check fixation of marble for walls of corridor infront of elevetors at zone(1) between axis (D-E)/(15-16) at fifth floor as Per Attached Sketch. | ARCH | Marble Walls | Z1 | 5th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1492 | second putty for acrylic points at second basement between axes (A-L)/(9-18) at zone(1,2,3A) as per attached sketch. | ARCH | Painting second Putty | Z1,2,3A | B2 | 43965 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1493 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at fourth floor between axis(7-9)&(F-L) for area (3B) as Per Attached Sketch. | ARCH | Porcelain | Z3B | 4th | 43965 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1494 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at fourth floor between axis(1-7)&(F-L) for area (4) as Per Attached Sketch. | ARCH | Porcelain | Z4 | 4th | 43965 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1495 | Check fixation of marble for flooring of corridor infront of elevetors at zone(5) between axis (D-E)/(2-5) at Fifth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z5 | 5th | 43965 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1496 | Check fixation for ceramic tiles for walls and flooring at fifth floor between axis(2-3)&(C-D) for area (Z5) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z5 | 5th | 43965 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1497 | Check fixation for ceramic tiles for walls and flooring at fifth floor between axis(7-9)&(G-L) for area (Z3B) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3B | 5th | 43965 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1498 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (1-7)&(A-L) for area (Z4,5) at fourth floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z4,5 | 4th | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1499 | Check full closure for walls of second floor at zone 3B between axis(F-L)/(7-9) as Per Attached Sketch. | ARCH | Full Closure | Z3B | 2nd | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1500 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Ground floor between axis(1-7)&(A-L) for area (Z4,5) as Per Attached Sketch. | ARCH | Porcelain | Z4,5 | GF | 43992 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1501 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at sixth floor between axis(1-9)&(F-L) for area (Z3B,4) as Per Attached Sketch. | ARCH | Porcelain | Z3B,4 | 6th | 43992 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1502 | Check fixation of marble for flooring of corridor infront of elevetors at zone(3b,4) between axis (G-K)/(3-8) at Fifth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B,4 | 5th | 43992 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1503 | Check fixation of marble for flooring of corridor infront of elevetors at zone(3b,4) between axis (G-K)/(3-8) at sixth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B,4 | 6th | 43992 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1504 | Check fixation of marble for flooring of corridor infront of elevetors at zone(3b) between axis (F-L)/(7-9) at Ground floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | GF | 43992 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1505 | Check fixation of marble for flooring of corridor infront of elevetors at zone(1,2) between axis (D-J)/(15-16) at Fifth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z1,2 | 5th | 43992 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1506 | Check fixation and insulation for wood substructure for mirror in staff and public toilets for zone (3) between axes (E-L) (7-12) at Eighth floor as Per Attached Sketch. | ARCH | Mirrors Toilet Wood sub. Strc. | Z3 | 8th | 43992 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1507 | Check fixation and insulation for wood substructure for mirror in staff and public toilets for zone (3) between axes (G-L) (8-11) at Ninth floor as Per Attached Sketch. | ARCH | Mirrors Toilet Wood sub. Strc. | Z3 | 9th | 43993 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1508 | check fixation of interior expansion joint at Seventh floor between axes (F-L)/(9-10) at zone(3) as per attached sketch. | ARCH | Expansion Joint | Z3 | 7th | 43996 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1509 | check fixation of interior expansion joint at Eighth floor between axes (F-L)/(9-10) at zone(3) as per attached sketch. | ARCH | Expansion Joint | Z3 | 8th | 43996 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1510 | check fixation of interior expansion joint at Ninth floor between axes (F-L)/(9-10) at zone(3) as per attached sketch. | ARCH | Expansion Joint | Z3 | 9th | 43996 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1511 | check cement based waterproof coating for Toilet between axes (K-L)&(5-6) at ground floor for area (Z4) as per attached sketch. | ARCH | Water Proofing Cement base | Z4 | GF | 44002 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1512 | water test for Toilet between axes (K-L)&(5-6) at ground floor for area (Z4) as per attached sketch. | ARCH | Water Test | Z4 | GF | 44002 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1513 | Check full closure for walls of First floor at zone (3B,4) between axis(F-L)/(1-9) as Per Attached Sketch. | ARCH | Full Closure | Z3B,4 | 1st | 44004 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1514 | Check full closure for walls of Ground floor at zone (1,2) between axis(A-L)/(12-18) as Per Attached Sketch. | ARCH | Full Closure | Z1,2 | GF | 44004 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1515 | Check Surface Prepration for flooring between axes (10-18)&(E-L) at Second basement floor(291.80) for area (Z2,3A) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z2,3A | B2 | 44004 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1516 | Check fixation for ceramic tiles for walls and flooring at fourth floor between axis(4-9)&(E-L) for area (Z3B,4,5) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3B,4,5 | 4th | 44005 | 44012 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1517 | Check first fix for wooden doors frames at Seventh floor between axis (2-6)&(G-K) for area(Z2) as Per Attached Sketch. | ARCH | Wooden door Frame | Z2 | 7th | 44006 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1518 | Check first fix for wooden doors frames at Seventh floor between axis (12-17)&(G-K) for area(Z4) as Per Attached Sketch. | ARCH | Wooden door Frame | Z4 | 7th | 44006 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1519 | Check full closure for walls of Ground floor at zone (3B,4,5) between axis(A-L)/(1-7) as Per Attached Sketch. | ARCH | Full Closure | Z3B,4,5 | GF | 44013 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1520 | Check first fix for G.B sheet(Bulk head) at First basement between axis (2-17)&(D-K) for area (Z1,2,4,5) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,2,4,5 | B1 | 44013 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1521 | Check first fix for G.B sheet(Bulk head) at Second basement between axis (2-17)&(D-K) for area (Z1,2,4,5) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,2,4,5 | B2 | 44016 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1522 | Check Surface Prepration for flooring between axes (13-18)&(A-F) at Second basement floor(291.80) for area (Z1) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z1 | B2 | 44016 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1523 | check primer layer for flooring of Second basement floor at zone (2,3A) between axes (9-16)(E-L) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z2,3A | B2 | 44018 | 44032 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1524 | Check first fix for G.B sheet(Bulk head) at Second basement between axis (6-14)&(G-J) for area (Z3A,3B) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3A,3B | B2 | 44018 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1525 | Check first fix for G.B sheet(Bulk head) at Third floor between axis (1-9)&(A-L) for area (Z3B,4,5) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3B,4,5 | 3rd | 44018 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1526 | Check first fix for G.B sheet(Bulk head) at Ground Floor axis (1-7)&(A-L) for area (Z4,5) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z4,5 | GF | 44018 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1527 | Check Surface Prepration for flooring between axes (5-9)&(G-L) at Second basement floor(291.80) for area (Z3B) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z3B | B2 | 44019 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1528 | Check first fix for G.B sheet(Bulk head) at First floor between axis (1-9)&(A-L) for area (Z3B,4,5) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3B,4,5 | 1st | 44019 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1529 | water test for Ablution between axes (A-C)&(14-15) at ground floor for area (Z1) as per attached sketch. | ARCH | Water Test | Z1 | GF | 44019 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1530 | Cement based for Ablution between axes (A-C)&(14-15) at ground floor for area (Z1) as per attached sketch. | ARCH | Water Proofing Cement base | Z1 | GF | 44019 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1531 | Check first fix for acceccories (G.B Tiles) at First floor for area (Z1,2,3A) between axes(A-L) &(10-18) as per attached sketch. | ARCH | False ceiling (Tiles) 1st | Z1,2,3A | 1st | 44019 | 44021 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1532 | Check first fix for acceccories (G.B Tiles) at Sixth floor for area (Z2,3A) between axes(A-L) &(10-18) Exclude (corridors) as per attached sketch. | ARCH | False ceiling (Tiles) 1st | Z2,3A | 6th | 44019 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1533 | Check first fix for G.B sheet(Bulk head) at Sixth floor between axis (10-18)&(A-L) for area (Z2,3A) Exclude (corridors) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z2,3A | 6th | 44019 | 44021 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1534 | check sika floor (324) layer of Second basement floor for zone(2,3A) between axes (E-L) & (9-16) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z2,3A | B2 | 44020 | 44025 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1535 | Check fixation of marble for walls of corridor infront of elevetors at zone(3A) between axis (G-K)/(11-12) at Third floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 3rd | 44021 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1536 | Check fixation of marble for flooring of corridor infront of elevetors at zone(3A) between axis (G-K)/(11-12) at Third floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 3rd | 44021 | 44032 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1537 | Check Surface Prepration for flooring between axes (1-6)&(A-L) at Second basement floor(291.80) for area (Z4,5) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z4,5 | B2 | 44024 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1538 | check installation of wooden door leaf at Seventh floor for area (Z2)between axes (F-k) (12-17) as per attached sketch. | ARCH | Wooden door Leaf | Z2 | 7th | 44026 | 44032 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1539 | check installation of wooden door leaf at Seventh floor for area (Z4)between axes (G-k) (2-6) as per attached sketch. | ARCH | Wooden door Leaf | Z4 | 7th | 44026 | 44039 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1540 | Check fixation for ceramic tiles for walls and flooring at sixth floor between axis(10-12)&(F-L) for area (Z3A) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3A | 6th | 44033 | 44051 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1541 | check fixation of interior expansion joint at First floor between axes (E-F)/(13-17) at zone(1) as per attached sketch.(walls and flooring only) | ARCH | Expansion Joint | Z1 | 1st | 44033 | 44039 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1542 | check fixation of interior expansion joint at First floor between axes (E-F)/(2-6) at zone(5) as per attached sketch.(walls and flooring only) | ARCH | Expansion Joint | Z5 | 1st | 44033 | 44051 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1543 | check fixation of interior expansion joint at Fourth floor between axes (E-F)/(2-6) at zone(5) as per attached sketch.(walls and flooring only) | ARCH | Expansion Joint | Z5 | 4th | 44033 | 44051 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1544 | Check first fix for wooden doors frames at Ground floor between axis (11-18)&(A-L) for area(1,2,3A) as Per Attached Sketch. | ARCH | Wooden door Frame | Z1,2,3A | GF | 44034 | 44039 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1545 | Check first fix for wooden doors frames at Ground floor between axis (1-7)&(A-L) for area(4,5,3B) as Per Attached Sketch. | ARCH | Wooden door Frame | Z4,5,3B | GF | 44034 | 44039 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1546 | Check Second Putty For Acrylic Painting For walls at Ground Floor at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z1 | GF | 44037 | 44039 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1547 | Check Second Putty For Acrylic Painting For walls at Ground Floor at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting second Putty | Z2 | GF | 44037 | 44039 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1548 | Check Second Putty For Acrylic Painting For walls at Ground Floor at Zone(3) axes (E-L) &(7-12) as Per Attached Sketch. | ARCH | Painting second Putty | Z3 | GF | 44037 | 44051 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1549 | Check Second Putty For Acrylic Painting For walls at Ground Floor at Zone(4) axes (E-L) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z4 | GF | 44037 | 44051 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1550 | Check Second Putty For Acrylic Painting For walls at Ground Floor at Zone(5) axes (A-E) &(1-7) as Per Attached Sketch. | ARCH | Painting second Putty | Z5 | GF | 44037 | 44051 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1551 | Check for Final Plaster between axes (10-12)&(E-L) at ground floor for area (3A) as Per Attached Sketch. | ARCH | Final Plaster | Z3A | GF | 44037 | 44039 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1552 | Check first fix for G.B sheet(Bulk head) at fourth floor between axis (1-9)&(A-L) for area (4,5,3B) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z4,5,3B | 4th | 44038 | 44051 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1553 | Check first fix for G.B sheet(Bulk head) at fifth floor between axis (1-9)&(A-L) for area (4,5,3B) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z4,5,3B | 5th | 44038 | 44051 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1554 | Check first fix for G.B sheet(Bulk head) at Sixth floor between axis (1-9)&(F-L) for area (3B,4) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3B,4 | 6th | 44038 | 44051 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1555 | Check first fix for G.B sheet(Bulk head) at Seventh floor between axis (7-13)&(F-L) for area (3) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3 | 7th | 44038 | 44051 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1556 | Check first fix for G.B sheet(Bulk head) at Ground floor between axis (12-18)&(A-L) for area (1,2) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,2 | GF | 44038 | 44051 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1557 | Check first fix for G.B sheet(Bulk head) at Second floor between axis (10-18)&(A-L) for area (1,2,3A) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,2,3A | 2nd | 44038 | 44051 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1558 | Check first fix for G.B sheet(Bulk head) at Fourth floor between axis (10-18)&(A-L) for area (1,2,3A) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,2,3A | 4th | 44038 | 44051 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1559 | Check first fix for G.B sheet(Bulk head) at Fifth floor between axis (10-18)&(A-L) for area (1,2,3A) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,2,3A | 5th | 44038 | 44051 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1560 | Check fixation for ceramic tiles for walls at fifth floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls | Z2 | 5th | 44040 | 44051 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1561 | Check fixation for marble walls and flooring at Ground Floor for Area Z(3A) between Axis(10-11)&(H-J) as Per Attached Sketch. | ARCH | Marble walls and flooring | Z3A | GF | 44053 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1562 | Check fixation of ceramic flooring for Public toilet at Sixth floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic flooring | Z2 | 6th | 44054 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1563 | Check fixation of marble for walls of corridor infront of elevetors at zone(3) between axis (G-K)/(7-12) at Seventh floor as Per Attached Sketch. | ARCH | Marble Walls | Z3 | 7th | 44054 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1564 | Check fixation of marble for walls of corridor infront of elevetors at zone(3) between axis (G-K)/(7-12) at Eighth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3 | 8th | 44054 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1565 | Check fixation of marble for walls of corridor infront of elevetors at zone(3) between axis (G-K)/(7-12) at Ninth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3 | 9th | 44054 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1566 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3) between axis (G-K)/(7-12) at Seventh floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3 | 7th | 44054 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1567 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3) between axis (G-K)/(7-12) at Eighth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3 | 8th | 44054 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1568 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3) between axis (G-K)/(7-12) at Ninth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3 | 9th | 44054 | 44070 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1569 | Check fixation for interior aluminium doors between axis (1-18)& (A-L) at First floor as Per Attached Sketch. | ARCH | Aluminium Doors | Z1,2,3,4,5 | 1st | 44058 | 44070 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1570 | Check fixation for interior aluminium doors between axis (1-18)& (A-L) at Ground floor as Per Attached Sketch. | ARCH | Aluminium Doors | Z1,2,3,4,5 | GF | 44058 | 44070 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1571 | Check fixation for marble walls at First Floor for Area Z(3A) between Axis(10-11)&(H-J) as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 1st | 44059 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1572 | Check fixation for marble Flooring at First Floor for Area Z(3A) between Axis(10-11)&(H-J) as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 1st | 44059 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1573 | Check fixation for marble walls at Second Floor for Area Z(3A) between Axis(10-11)&(H-J) as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 2nd | 44059 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1574 | Check fixation for marble Flooring at Second Floor for Area Z(3A) between Axis(10-11)&(H-J) as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 2nd | 44059 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1575 | Check fixation for marble walls at First Floor for Area Z(3B) between Axis(7-8)&(H-J) as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 1st | 44060 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1576 | Check fixation for marble Flooring at First Floor for Area Z(3B) between Axis(7-8)&(H-J) as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 1st | 44060 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1577 | Check fixation for marble walls at Second Floor for Area Z(3B) between Axis(7-8)&(H-J) as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 2nd | 44060 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1578 | Check fixation for marble Flooring at Second Floor for Area Z(3B) between Axis(7-8)&(H-J) as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 2nd | 44060 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1579 | Check fixation for marble walls at Third Floor for Area Z(3B) between Axis(7-8)&(H-J) as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 3rd | 44060 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1580 | Check fixation for marble Flooring at Third Floor for Area Z(3B) between Axis(7-8)&(H-J) as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 3rd | 44060 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1581 | Check Surface Prepration for flooring between axes (12-18)&(A-F) at First basement floor for area (Z1) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z1 | B1 | 44062 | 44069 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1582 | Check first fix for closets and shelves at Ninth floor between axis (7-12)&(G-L) for area (3) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z3 | 9th | 44062 | 44069 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1583 | check primer layer for flooring of First basement floor at zone (1) between axes (12-18)(A-F) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z1 | B1 | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1584 | Check first fix for closets and shelves at Eighth floor between axis (7-12)&(G-L) for area (3) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z3 | 8th | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1585 | Check first fix for closets and shelves at Seventh floor between axis (7-12)&(G-L) for area (3) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z3 | 7th | 44069 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1586 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3A) between axis (G-K)/(11-12) at Ninth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 9th | 44070 |  | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1587 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3B) between axis (G-K)/(7-8) at Ninth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 9th | 44070 |  | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1588 | check sika floor (324) layer of First basement floor for zone(1) between axes (A-F) & (13-18) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z1 | B1 | 44072 |  | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1589 | check second putty for acrylic paints for Emergency Stairs(walls+ceiling) for area Z(5) from level (291.900) to (331.200) as per attached sketch. | ARCH | Painting second Putty | Z5 | ML | 44073 |  | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1590 | Check Surface Prepration for flooring between axes (12-18)&(E-L) at First basement floor for area (Z2) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z2 | B1 | 44075 |  | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1591 | Check fixation for Ceramic tiles for Toilet for walls and flooring at third floor between axis(9-12)&(G-L) for area (Z3A) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3A | 3rd | 44077 |  | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1592 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Ground floor between axis(12-18)&(A-L) for area (Z1,2) as Per Attached Sketch. | ARCH | Porcelain | Z1,2 | GF | 44077 |  | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1593 | check primer layer for flooring of First basement floor at zone (2) between axes (12-18)(E-L) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z2 | B1 | 44079 | 44091 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1594 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Ground floor for area Zone(2) axes (H-J) &(13-15) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2 | GF | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1595 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Ground floor for area Zone(4) axes (H-J) &(4-5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4 | GF | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1596 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at First floor for area Zone(2) axes (H-J) &(13-15) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2 | 1st | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1597 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at First floor for area Zone(4) axes (H-J) &(4-5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4 | 1st | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1598 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Second floor for area Zone(2) axes (H-J) &(13-15) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2 | 2nd | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1599 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Second floor for area Zone(4) axes (H-J) &(4-5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4 | 2nd | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1600 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Third floor for area Zone(2) axes (H-J) &(13-15) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2 | 3rd | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1601 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Third floor for area Zone(4) axes (H-J) &(4-5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4 | 3rd | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1602 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Fourth floor for area Zone(2) axes (H-J) &(13-15) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2 | 4th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1603 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Fourth floor for area Zone(4) axes (H-J) &(4-5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4 | 4th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1604 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Fifth floor for area Zone(2) axes (H-J) &(13-15) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2 | 5th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1605 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Fifth floor for area Zone(4) axes (H-J) &(4-5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4 | 5th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1606 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Sixth floor for area Zone(2) axes (H-J) &(13-15) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2 | 6th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1607 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Sixth floor for area Zone(4) axes (H-J) &(4-5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4 | 6th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1608 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Seventh floor for area Zone(3) axes (H-J) &(6-9) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z3 | 7th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1609 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Seventh floor for area Zone(4) axes (H-J) &(4-5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4 | 7th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1610 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Eighth floor for area Zone(3) axes (H-J) &(6-9) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z3 | 8th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1611 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Ninth floor for area Zone(3) axes (H-J) &(6-9) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z3 | 9th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1612 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at First Basement for area Zone(2,4) axes (H-J) &(4-16) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2,4 | B1 | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1613 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Second Basement for area Zone(2,4) axes (H-J) &(4-16) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2,4 | B2 | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1614 | check sika floor (324) layer of First basement floor for zone(2) between axes (12-18)&(E-L) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z2 | B1 | 44084 | 44096 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1615 | Check Surface Prepration for flooring between axes (9-11)&(G-K) at First basement floor for area (Z3) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z3 | B1 | 44084 | 44096 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1616 | Check full closure for walls of Sixth floor at zone (4,3B) between axis(F-L)/(1-9) as Per Attached Sketch. | ARCH | Full Closure | Z4,3B | 6th | 44086 | 44091 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1617 | check fixation of interior expansion joint for walls and flooring only at Fourth floor between axes (E-F)/(14-17) at zone(1) as per attached sketch. | ARCH | Expansion Joint | Z1 | 4th | 44088 | 44101 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1618 | check fixation of interior expansion joint for walls and flooring only at Fifth floor between axes (E-F)/(14-17) at zone(1) as per attached sketch. | ARCH | Expansion Joint | Z1 | 5th | 44088 | 44101 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1619 | check fixation of interior expansion joint for walls and flooring only at Fifth floor between axes (E-F)/(2-5) at zone(5) as per attached sketch. | ARCH | Expansion Joint | Z5 | 5th | 44088 | 44091 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1620 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (7-9)&(G-K) for area (Z3B) at second floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z3B | 2nd | 44088 | 44091 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1621 | check installation of wooden door leaf at Ground floor for area (Z1,2,3A)between axes (A-L) (11-18) as per attached sketch. | ARCH | Wooden door Leaf | Z1,2,3A | GF | 44088 | 44101 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1622 | Check fixation of marble for walls of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Seventh floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 7th | 44089 | 44101 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1623 | Check fixation of marble for walls of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Eighth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 8th | 44089 | 44101 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1624 | Check fixation of marble for walls of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Ninth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 9th | 44089 | 44101 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1625 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Seventh floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 7th | 44089 | 44101 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1626 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Eighth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 8th | 44089 | 44101 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1627 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Ninth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 9th | 44089 | 44101 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1628 | check primer layer for flooring of First basement floor at zone (3) between axes (9-11)(G-K) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z3 | B1 | 44094 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1629 | Check fixation and installation for marbel between axis(1-4)&(K-L) for area (Z4) at Ground Floor as Per Attached Sketch. | ARCH | Marble Façade | Z4 | GF | 44094 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1630 | check Final coat (Epoxy) for flooring and skerting for fire Alarm closet at Third floor for area Zone(4,5) axes (C-J) &(1-7) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4,5 | 3rd | 44094 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1631 | Check fixation for ceramic tiles for Flooring at first floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic flooring | Z2 | 1st | 44095 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1632 | Check fixation for ceramic tiles for walls and Flooring for Pantry room at first floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 1st | 44095 | 44136 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1633 | Check fixation for ceramic tiles for walls and Flooring for Janitor room at first floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 1st | 44095 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1634 | Check Surface Prepration for flooring between axes (1-9)&(E-L) at First basement floor for area (Z4) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z4 | B1 | 44098 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1635 | check primer layer for flooring of First basement floor at zone (4) between axes (1-9)(E-L) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z4 | B1 | 44102 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1636 | check fixation of vinyl flooring at First floor for Area Z(2) between axes (15-16)(G-H) as Per Attached Sketch. | ARCH | Vinyl | Z2 | 1st | 44102 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1637 | check fixation of vinyl flooring at Second floor for Area Z(2) between axes (15-16)(G-H) as Per Attached Sketch. | ARCH | Vinyl | Z2 | 2nd | 44102 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1638 | check fixation of vinyl flooring at Third floor for Area Z(2) between axes (15-16)(G-H) as Per Attached Sketch. | ARCH | Vinyl | Z2 | 3rd | 44102 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1639 | Check first fix for G.B sheet(Bulk head) at third floor between axis (10-13)&(H-K) for area (3A) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3A | 3rd | 44104 | 44117 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1640 | Check fixation of marble for walls of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Third floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 3rd | 44105 | 44117 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1641 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Fourth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 4th | 44105 | 44117 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1642 | Check fixation of marble for walls of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Fifth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 5th | 44105 | 44117 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1643 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Third floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 3rd | 44105 | 44117 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1644 | Check fixation of marble for walls of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Fourth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 4th | 44105 | 44117 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1645 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Fifth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 5th | 44105 | 44117 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1646 | Check fixation of marble for walls of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Sixth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 6th | 44105 | 44117 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1647 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3A) between axis (H-J)/(10-12) at Sixth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 6th | 44105 | 44117 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1648 | Check fixation for ceramic tiles for flooring at sixth floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic flooring | Z2 | 6th | 44105 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1649 | check sika floor (324) layer of First basement floor for zone(4) between axes (1-9)&(E-L) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z4 | B1 | 44107 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1650 | Check Surface Prepration for flooring between axes (1-9)&(A-F) at First basement floor for area (Z5) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z5 | B1 | 44107 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1651 | Check fixation for ceramic tiles for flooring and walls for Janitor and Carbage room at second floor between axis(14-16)&(G-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 2nd | 44108 | 44136 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1652 | Check Finishing for marble sill under 12mm tempered glass partition for corridors between axis (10-18)&(A-L) for area (Z1,2,3A) at Second floor as Per Attached Sketch. | ARCH | Marble sill finishing | Z1,2,3A | 2nd | 44108 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1653 | second putty for Epoxy for Flooring and Skerting for HVAC and Electric Rooms at second Floor between axes (G-K)/(12-14) at zone(2) as per attached sketch. | ARCH | Painting (Epoxy) | Z2,3A | 2nd | 44108 | 44117 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1654 | second putty for Epoxy for Flooring and Skerting for HVAC and Electric Rooms at second Floor between axes (C-D)/(14-17) at zone(1) as per attached sketch. | ARCH | Painting (Epoxy) | Z1 | 2nd | 44108 | 44117 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1655 | second putty for Epoxy for Flooring and Skerting for HVAC Rooms at First Floor between axes (C-D)/(14-17) at zone(1) as per attached sketch. | ARCH | Painting (Epoxy) | Z1 | 1st | 44108 | 44117 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1656 | second putty for Epoxy for Flooring and Skerting for HVAC Rooms at First Floor between axes (G-K)/(12-14) at zone(2) as per attached sketch. | ARCH | Painting (Epoxy) | Z2 | 1st | 44108 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1657 | check Final coat (359) layer of First basement floor for zone(4) between axes (1-9)&(E-L) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z4 | B1 | 44110 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1658 | check primer layer for flooring of First basement floor at zone (5) between axes (1-9)(A-F) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z5 | B1 | 44110 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1659 | check installation of wooden door leaf at Fifth floor for area (Z1)between axes (A-F) (13-17) as per attached sketch. | ARCH | Wooden door Leaf | Z1 | 5th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1660 | check sika floor (324) layer of First basement floor for zone(5) between axes (1-6)&(A-F) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z5 | B1 | 44115 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1661 | check fixation of interior expansion joint for walls and flooring only at Third floor between axes (E-F)/(14-17) at zone(2) as per attached sketch. | ARCH | Expansion Joint | Z2 | 3rd | 44121 | 44136 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1662 | second putty for Epoxy for Flooring and Skerting for HVAC and Electric Rooms at Third Floor between axes (C-J)/(10-17) at zone(1,2,3A) as per attached sketch. | ARCH | Painting (Epoxy) | Z1,2,3A | 3rd | 44123 | 44136 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1663 | check Final coat (Epoxy) for Flooring and Skerting for HVAC and Electric Rooms at Third Floor between axes (C-J)/(10-17) at zone(1,2,3A) as per attached sketch. | ARCH | Painting (Epoxy) | Z1,2,3A | 3rd | 44123 | 44136 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1664 | Check fixation of ceramic flooring for Public toilet at Third floor between axis(14-17)&(F-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic flooring | Z2 | 3rd | 44123 | 44136 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1665 | Check fixation for ceramic tiles for flooring and walls for Janitor room at Third floor between axis(15-16)&(G-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 3rd | 44123 | 44136 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1666 | Check fixation for ceramic tiles for flooring and walls for Pantry room at Third floor between axis(14-16)&(G-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 3rd | 44123 | 44136 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1667 | Check fixation for ceramic tiles for flooring and walls for Carbage room at Third floor between axis(14-16)&(G-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 3rd | 44123 | 44136 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1668 | check Fixation of wooden door leaf at Fifth floor for area (Z2)between axes (F-L) (12-18) as per attached sketch. | ARCH | Wooden door Leaf | Z2 | 5th | 44123 | 44136 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1669 | Check fixation for ceramic tiles for flooring and walls for Toilet at Fourth floor between axis(6-8)&(J-K) for area (Z3B) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3B | 4th | 44125 | 44147 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1670 | Check Finishing for marble sill under 12mm tempered glass partition for corridors between axis (10-18)&(A-L) for area (Z1,2,3A) at First floor as Per Attached Sketch. | ARCH | Marble sill finishing | Z1,2,3A | 1st | 44125 | 44136 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1671 | Check Surface Prepration for flooring from(297.10) to (291.80) for Two basements between axes (8-11)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z3 | B1&B2 | 44136 | 44153 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1672 | check primer layer for flooring from (297.10) to (291.80) for Two basements between axes (8-11)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z3 | B1&B2 | 44137 | 44153 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1673 | second putty for Epoxy for Flooring and Skerting for HVAC and Electric Rooms at First Floor between axes (C-J)/(2-7) at zone(4,5) as per attached sketch. | ARCH | Painting (Epoxy) | Z4,5 | 1st | 44137 | 44153 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1674 | check sika floor (324) layer for Two basements between axes (8-12)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z3 | B1&B2 | 44138 | 44164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1675 | check Final coat (359) layer for Two basements between axes (8-12)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z3 | B1&B2 | 44142 | 44164 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1676 | Check fixation for 16mm tempered glass partition between axis (3-4)&(D-E) for area (Z5) at Ground floor as Per Attached Sketch. | ARCH | tempered glass | Z5 | GF | 44144 | 44153 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1677 | Check fixation for 16mm tempered glass partition between axis (3-4)&(D-E) for area (Z5) at First floor as Per Attached Sketch. | ARCH | tempered glass | Z5 | 1st | 44144 | 44153 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1678 | Check fixation for 16mm tempered glass partition between axis (3-4)&(D-E) for area (Z5) at Second floor as Per Attached Sketch. | ARCH | tempered glass | Z5 | 2nd | 44144 | 44153 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1679 | Check fixation for 16mm tempered glass partition between axis (3-4)&(D-E) for area (Z5) at Third floor as Per Attached Sketch. | ARCH | tempered glass | Z5 | 3rd | 44144 | 44153 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1680 | Check fixation for 16mm tempered glass partition between axis (3-4)&(D-E) for area (Z5) at Fourth floor as Per Attached Sketch. | ARCH | tempered glass | Z5 | 4th | 44144 | 44153 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1681 | Check fixation for 16mm tempered glass partition between axis (3-4)&(D-E) for area (Z5) at Fifth floor as Per Attached Sketch. | ARCH | tempered glass | Z5 | 5th | 44144 | 44153 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1682 | check Final coat (Epoxy) for Flooring and Skerting for HVAC and Electric Rooms at second Floor between axes (C-D)/(14-17) at zone(1) as per attached sketch. | ARCH | Painting (Epoxy) | Z1 | 2nd | 44145 | 44164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1683 | check Final coat (Epoxy) for Flooring and Skerting for HVAC and Electric Rooms at second Floor between axes (G-K)/(10-14) at zone(2) as per attached sketch. | ARCH | Painting (Epoxy) | Z2 | 2nd | 44145 | 44164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1684 | Check fixation for ceramic tiles for flooring and walls for Toilet at Seventh floor between axis(2-17)&(F-H) for area (Z2,4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2,4 | 7th | 44151 | 44164 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1685 | check installation of wooden door leaf at Ground floor for area (3B,4,5)between axes (A-L) (1-8) as per attached sketch. | ARCH | Wooden door Leaf | Z4,5,3B | GF | 44153 | 44167 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1686 | Check fixation for ceramic tiles for flooring and walls for Pantry at Fourth floor between axis(14-16)&(G-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 4th | 44153 | 44164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1687 | Check fixation for ceramic tiles for flooring and walls for Janitor at Fourth floor between axis(15-16)&(G-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 4th | 44153 | 44164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1688 | Check fixation for ceramic tiles for flooring and walls for Garbage at Fourth floor between axis(15-16)&(G-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 4th | 44153 | 44164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1689 | Check Finishing for marble sill under 12mm tempered glass partition for corridors between axis (14-17)&(A-D) for area (Z1) at Third floor as Per Attached Sketch. | ARCH | Marble sill finishing | Z1 | 3rd | 44153 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1690 | Check Finishing for marble sill under 12mm tempered glass partition for corridors between axis (12-17)&(E-K) for area (Z2) at Third floor as Per Attached Sketch. | ARCH | Marble sill finishing | Z2 | 3rd | 44153 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1691 | Check Finishing for marble sill under 12mm tempered glass partition for corridors between axis (6-8)&(G-K) for area (Z3B) at Third floor as Per Attached Sketch. | ARCH | Marble sill finishing | Z3 | 3rd | 44153 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1692 | Check fixation for 16mm tempered glass partition between axis (12-18)&(A-F) for area (Z1) at Ground floor as Per Attached Sketch. | ARCH | tempered glass | Z1 | GF | 44158 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1693 | Check fixation for ceramic tiles for walls and flooring at second floor between axis(9-11)&(G-K) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | 2nd | 44160 | 44188 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1694 | check Second putty (Epoxy) for flooring and skerting for HVAC and Electric rooms at Third floor for area Zone(4,5) axes (C-J) &(1-7) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4,5 | 3rd | 44165 | 44167 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1695 | Check fixation for marble sill for interior curtin wall upstand between axis (1-9)&(A-L) for area (Z3B,4,5) at Fourth floor as Per Attached Sketch. | ARCH | Marble sill | Z3B,4,5 | 4th | 44165 | 44167 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1696 | Check fixation for 16mm tempered glass partition between axis (12-18)&(F-L) for area (Z2) at Ground floor as Per Attached Sketch. | ARCH | tempered glass | Z2 | GF | 44165 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1697 | Check fixation for ceramic tiles for walls and flooring for Kitchen at Ground floor between axis(13-15)&(E-G) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | GF | 44166 | 44178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1698 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (14-15)&(C-E) for area (Z1) at Ground floor as Per Attached Sketch. | ARCH | Marble sill | Z1 | GF | 44166 | 44178 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1699 | Check fixation for ceramic tiles for walls and flooring for Janitor &Pantry and Garbage room at Third floor between axis(3-4)&(G-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | 3rd | 44167 | 44177 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1700 | Check fixation for ceramic tiles for walls and flooring for Janitor &Pantry and Garbage room at Fifth floor between axis(3-4)&(G-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | 5th | 44167 | 44177 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1701 | check fixation of vinyl flooring at First floor for Area Z(4) between axes (3-4)(G-H) as Per Attached Sketch. | ARCH | Vinyl | Z4 | 1st | 44167 | 44177 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1702 | check fixation of vinyl flooring at Second floor for Area Z(4) between axes (3-4)(G-H) as Per Attached Sketch. | ARCH | Vinyl | Z4 | 2nd | 44167 | 44177 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1703 | check fixation of vinyl flooring at Fourth floor for Area Z(4) between axes (3-4)(G-H) as Per Attached Sketch. | ARCH | Vinyl | Z4 | 4th | 44167 | 44177 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1704 | check Second putty (Epoxy) for flooring and skerting for HVAC and Electric rooms at Fourth floor for area Zone(1,2,3A) between axes (C-K) &(10-17) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,3A | 4th | 44167 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1705 | check Final coat (Epoxy) for flooring and skerting for HVAC and Electric rooms at Fourth floor for area Zone(1,2,3A) between axes (C-K) &(10-17) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,3A | 4th | 44167 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1706 | check First fix for Exterior expansion joint of curtin wall from Seventh to Roof floor between axes (9-10)&(K-L) as Per Attached Sketch. | ARCH | Expansion Joint |  | ML | 44167 | 44178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1707 | check Second fix for Exterior expansion joint of curtin wall from Seventh to Roof floor between axes (9-10)&(K-L) as Per Attached Sketch. | ARCH | Expansion Joint |  | ML | 44167 | 44178 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1708 | check installation of royestonea regia palms and C ycas Revoluta at landscape as per attached sketch . | ARCH | Agriculture |  | EX | 44170 | 44178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1709 | check installation of Archontophoenix palms and at landscape as per attached sketch . | ARCH | Agriculture |  | EX | 44170 | 44178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1710 | second putty for Epoxy for Flooring and Skerting for HVAC and Electric Rooms at Second Floor between axes (C-K)/(2-7) at zone(4,5) as per attached sketch. | ARCH | Painting (Epoxy) | Z4,5 | 2nd | 44178 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1711 | second putty for Epoxy for Flooring and Skerting for HVAC and Electric Rooms at Sixth Floor between axes (G-K)/(4-7) at zone(4) as per attached sketch. | ARCH | Painting (Epoxy) | Z4 | 6th | 44179 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1712 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(9-10)&(J-K) for area (Z3) From Ground to First Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z3 | ML | 44180 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1713 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(12-15)&(J-K) for area (Z2) From Ground to First Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z2 | ML | 44180 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1714 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(17-18)&(A-E) for area (Z1) From Ground to Second Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z1 | ML | 44180 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1715 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(9-10)&(E-G) for area (Z3) From Ground to First Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z3 | ML | 44180 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1716 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(5-8)&(K-L) for area (Z4) From Ground to Fifth Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z4 | ML | 44180 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1717 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis(5-8)&(E-G) for area (Z4,5) From Ground to Fifth Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z4,5 | ML | 44180 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1718 | Check Finishing for marble sill under 12mm tempered glass partition for corridors between axis (7-12)&(G-H) for area (Z3) at Eighth floor as Per Attached Sketch. | ARCH | Marble sill finishing | Z3 | 8th | 44184 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1719 | Check Finishing for marble sill under 12mm tempered glass partition for corridors between axis (7-12)&(G-H) for area (Z3) at Ninth floor as Per Attached Sketch. | ARCH | Marble sill finishing | Z3 | 9th | 44184 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1720 | check Final coat (Epoxy) for flooring and skerting for Electric room at Seventh floor for area Zone(3A) between axes (G-J) &(10-11) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z3A | 7th | 44184 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1721 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Ninth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 9th | 44184 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1722 | Check fixation of marble for walls of corridor infront of elevetorsat zone(3B) between axis (H-J)/(8-9) at Ninth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 9th | 44184 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1723 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Eighth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 8th | 44184 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1724 | Check fixation of marble for walls of corridor infront of elevetorsat zone(3B) between axis (H-J)/(8-9) at Eighth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 8th | 44184 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1725 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(2) between axis (G-J)/(14-16) at Seventh floor as Per Attached Sketch. | ARCH | Marble Flooring | Z2 | 7th | 44184 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1726 | Check fixation of marble for walls of corridor infront of elevetors at zone(2) between axis (G-J)/(14-16) at Seventh floor as Per Attached Sketch. | ARCH | Marble Walls | Z2 | 7th | 44184 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1727 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at Seventh floor as Per Attached Sketch. | ARCH | Marble Flooring | Z4 | 7th | 44184 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1728 | Check fixation of marble for walls of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at Seventh floor as Per Attached Sketch. | ARCH | Marble Walls | Z4 | 7th | 44184 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1729 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Seventh floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 7th | 44184 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1730 | Check fixation of marble for walls of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Seventh floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 7th | 44184 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1731 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(2) between axis (G-J)/(14-16) at Sixth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z2 | 6th | 44185 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1732 | Check fixation of marble for walls of corridor infront of elevetors at zone(2) between axis (G-J)/(14-16) at Sixth floor as Per Attached Sketch. | ARCH | Marble Walls | Z2 | 6th | 44185 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1733 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3A) between axis (G-K)/(11-12) at Sixth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 6th | 44185 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1734 | Check fixation of marble for walls of corridor infront of elevetors at zone(3A) between axis (G-K)/(11-12) at Sixth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 6th | 44185 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1735 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Sixth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 6th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1736 | Check fixation of marble for walls of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Sixth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 6th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1737 | Check fixation of marble for walls of corridor infront of elevetors at zone(3B) between axis (G-J)/(7-8) at Sixth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 6th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1738 | Check fixation of marble for walls of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at Sixth floor as Per Attached Sketch. | ARCH | Marble Walls | Z4 | 6th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1739 | Check fixation of marble for Walls of corridor infront of elevetors at zone(2) between axis (J-G)/(15-16) at Fifth floor as Per Attached Sketch. | ARCH | Marble Walls | Z2 | 5th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1740 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Fifth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 5th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1741 | Check fixation of marble for walls of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Fifth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 5th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1742 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3A) between axis (G-K)/(11-12) at Fifth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 5th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1743 | Check fixation of marble for walls of corridor infront of elevetors at zone(3A) between axis (G-K)/(11-12) at Fifth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 5th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1744 | Check fixation of marble for walls of corridor infront of elevetors at zone(3B) between axis (H-J)/(7-8) at Fifth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 5th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1745 | Check fixation of marble for walls of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at Fifth floor as Per Attached Sketch. | ARCH | Marble Walls | Z4 | 5th | 44185 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1746 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(2) between axis (G-J)/(14-16) at Fourth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z2 | 4th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1747 | Check fixation of marble for walls of corridor infront of elevetors at zone(2) between axis (G-J)/(14-16) at Fourth floor as Per Attached Sketch. | ARCH | Marble Walls | Z2 | 4th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1748 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3A) between axis (G-K)/(11-12) at Fourth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 4th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1749 | Check fixation of marble for walls of corridor infront of elevetors at zone(3A) between axis (G-K)/(11-12) at Fourth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 4th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1750 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3B) between axis (H-J)/(7-8) at Fourth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 4th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1751 | Check fixation of marble for walls of corridor infront of elevetors at zone(3B) between axis (H-J)/(7-8) at Fourth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 4th | 44185 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1752 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Fourth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 4th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1753 | Check fixation of marble for walls of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Fourth floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 4th | 44185 | 44201 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1754 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at Fourth floor as Per Attached Sketch. | ARCH | Marble Flooring | Z4 | 4th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1755 | Check fixation of marble for walls of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at Fourth floor as Per Attached Sketch. | ARCH | Marble Walls | Z4 | 4th | 44185 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1756 | second putty for Epoxy for Flooring and Skerting for HVAC and Electric Rooms at Sixth Floor between axes (G-L)/(10-14) at zone(2) as per attached sketch. | ARCH | Painting (Epoxy) | Z2,3A | 6th | 44185 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1757 | Check fixation of marble for walls of corridor infront of elevetors at zone(2) between axis (G-J)/(15-16) at Third floor as Per Attached Sketch. | ARCH | Marble Walls | Z2 | 3rd | 44186 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1758 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at Third floor as Per Attached Sketch. | ARCH | Marble Flooring | Z4 | 3rd | 44186 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1759 | Check fixation of marble for walls of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at Third floor as Per Attached Sketch. | ARCH | Marble Walls | Z4 | 3rd | 44186 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1760 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(5) between axis (D-F)/(2-5) at Third floor as Per Attached Sketch. | ARCH | Marble Flooring | Z5 | 3rd | 44186 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1761 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Third floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 3rd | 44186 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1762 | Check fixation of marble for walls of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Third floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 3rd | 44186 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1763 | check Final coat (359) layer for flooring Of First Basement at Zone(1) axes (A-F) &(12-18) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z1 | B1 | 44186 | 44223 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1764 | check Final coat (359) layer for flooring Of First Basement (B1) at Zone(2) axes (E-L) &(12-18) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z2 | B1 | 44186 | 44223 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1765 | check Final coat (359) layer for flooring of First basement floor at zone (5) between axes (1-9)(A-F) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z5 | B1 | 44186 | 44223 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1766 | check sika floor (324) layer for First basement between axes (6-13)&(E-L) for area (Z3) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z3 | B1 | 44186 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1767 | check primer layer for flooring of Second basement floor at zone (1) between axes (12-18)(A-F) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z1 | B2 | 44186 | 44188 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1768 | check primer layer for flooring between axes (5-9)&(G-L) at Second basement floor for area (Z3B) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z3B | B2 | 44186 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1769 | check primer layer for flooring between axes (1-6)&(A-L) at Second basement floor for area (Z4,5) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z4,5 | B2 | 44186 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1770 | Check Surface Prepration for flooring between axes (6-13)&(A-F) at Second basement floor for area (Z6) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z6 | B2 | 44186 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1771 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis (G-L) for area (Z2,3A) From Fifth to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z2,3A | ML | 44186 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1772 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis (G-L) for area (Z3B,4) From Fifth to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z3B,4 | ML | 44186 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1773 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis (1-18) for area (Z2,4) From Fifth to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z2,4 | ML | 44186 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1774 | Check fixation and installation for glass for curtin wall between axis (1-18) for area (Z2,4) From Fifth to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z2,4 | ML | 44186 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1775 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at Second floor as Per Attached Sketch. | ARCH | Marble Flooring | Z4 | 2nd | 44186 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1776 | Check fixation of marble for walls of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at Second floor as Per Attached Sketch. | ARCH | Marble Walls | Z4 | 2nd | 44186 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1777 | Check fixation of marble for Walls of corridor infront of elevetors at zone(5) between axis (D-F)/(2-5) at Second floor as Per Attached Sketch. | ARCH | Marble Walls | Z5 | 2nd | 44186 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1778 | Check fixation of marble for walls of corridor infront of elevetors at zone(2) between axis (G-J)/(15-16) at Second floor as Per Attached Sketch. | ARCH | Marble Walls | Z2 | 2nd | 44186 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1779 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3A) between axis (G-K)/(11-12) at Second floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 2nd | 44186 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1780 | Check fixation of marble for walls of corridor infront of elevetors at zone(3A) between axis (G-K)/(11-12) at Second floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 2nd | 44186 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1781 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Second floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 2nd | 44186 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1782 | Check fixation of marble for walls of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Second floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 2nd | 44186 | 44201 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1783 | Check fixation for ceramic tiles for walls and flooring for Toilet Allocation at Fifth floor for area (Z1) between axis(14-15)&(D-E) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z1 | 5th | 44186 | 44188 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1784 | Check fixation of marble for walls of corridor infront of elevetors at zone(1) between axis (D-E)/(15-16) at First floor as Per Attached Sketch. | ARCH | Marble Walls | Z1 | 1st | 44187 | 44215 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1785 | Check fixation of marble for walls of corridor infront of elevetors at zone(2) between axis (G-J)/(15-16) at First floor as Per Attached Sketch. | ARCH | Marble Walls | Z2 | 1st | 44187 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1786 | Check fixation of marble for walls of corridor infront of elevetors at zone(3A) between axis (G-K)/(11-12) at First floor as Per Attached Sketch. | ARCH | Marble Walls | Z3A | 1st | 44187 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1787 | Check fixation of marble for walls of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at First floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | 1st | 44187 | 44201 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1788 | Check fixation of marble for walls of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at First floor as Per Attached Sketch. | ARCH | Marble Walls | Z4 | 1st | 44187 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1789 | Check fixation of marble for Walls of corridor infront of elevetors at zone(5) between axis (D-F)/(2-5) at First floor as Per Attached Sketch. | ARCH | Marble Walls | Z5 | 1st | 44187 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1790 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3A) between axis (G-K)/(11-12) at First floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3A | 1st | 44187 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1791 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at First floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | 1st | 44187 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1792 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at First floor as Per Attached Sketch. | ARCH | Marble Flooring | Z4 | 1st | 44187 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1793 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(1) between axis (D-E)/(15-16) at Ground floor as Per Attached Sketch. | ARCH | Marble Flooring | Z1 | GF | 44187 | 44215 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1794 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(2) between axis (G-J)/(14-16) at Ground floor as Per Attached Sketch. | ARCH | Marble Flooring | Z2 | GF | 44187 | 44215 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1795 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Grond floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3B | GF | 44187 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1796 | Check fixation of marble for Flooring of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at Ground floor as Per Attached Sketch. | ARCH | Marble Flooring | Z4 | GF | 44187 | 44215 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1797 | Check fixation of marble for walls of corridor infront of elevetors at zone(1) between axis (D-E)/(15-16) at Ground floor as Per Attached Sketch. | ARCH | Marble Walls | Z1 | GF | 44187 | 44215 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1798 | Check fixation of marble for walls of corridor infront of elevetors at zone(3B) between axis (H-J)/(8-9) at Ground floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | GF | 44187 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1799 | Check fixation of marble for walls of corridor infront of elevetors at zone(3B) between axis (H-J)/(7-8) at Ground floor as Per Attached Sketch. | ARCH | Marble Walls | Z3B | GF | 44187 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1800 | Check fixation of marble for walls of corridor infront of elevetors at zone(4) between axis (G-J)/(3-4) at Ground floor as Per Attached Sketch. | ARCH | Marble Walls | Z4 | GF | 44187 | 44215 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1801 | Check fixation of marble for Walls of corridor infront of elevetors at zone(5) between axis (D-F)/(2-5) at Ground floor as Per Attached Sketch. | ARCH | Marble Walls | Z5 | GF | 44187 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1802 | check primer layer for flooring between axes (6-13)&(A-F) at Second basement floor for area (Z6) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z6 | B2 | 44187 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1803 | check sika floor (324) layer for flooring between axes (1-6)&(A-L) at Second basement floor for area (Z4,5) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z4,5 | B2 | 44187 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1804 | check sika floor (324) layer for flooring between axes (5-9)&(G-L) at Second basement floor for area (Z3B) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z3B | B2 | 44187 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1805 | check sika floor (324) layer for flooring of Second basement floor at zone (1) between axes (12-18)(A-F) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z1 | B2 | 44187 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1806 | check Final coat (359) layer for flooring of First basement floor at zone (3) between axes (6-13)(F-L) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z3 | B1 | 44187 | 44223 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1807 | second putty for Epoxy for Flooring and Skerting for Transformer Rooms at First basement between axes (A-C)/(5-14) at zones (1,5) as per attached sketch. | ARCH | Painting (Epoxy) | Z1,5 | B1 | 44187 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1808 | Check fixation for 16mm tempered glass partition between axis (3-4)&(E-F) for area (Z5) at Ground floor as Per Attached Sketch. | ARCH | tempered glass | Z5 | GF | 44187 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1809 | Check fixation for 16mm tempered glass partition between axis (3-4)&(E-F) for area (Z5) at First floor as Per Attached Sketch. | ARCH | tempered glass | Z5 | 1st | 44187 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1810 | Check fixation for 16mm tempered glass partition between axis (3-4)&(E-F) for area (Z5) at Second floor as Per Attached Sketch. | ARCH | tempered glass | Z5 | 2nd | 44187 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1811 | Check fixation for 16mm tempered glass partition between axis (3-4)&(E-F) for area (Z5) at Third floor as Per Attached Sketch. | ARCH | tempered glass | Z5 | 3rd | 44187 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1812 | Check fixation for 16mm tempered glass partition between axis (3-4)&(E-F) for area (Z5) at Fourth floor as Per Attached Sketch. | ARCH | tempered glass | Z5 | 4th | 44187 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1813 | Check fixation for 16mm tempered glass partition between axis (3-4)&(E-F) for area (Z5) at Fifth floor as Per Attached Sketch. | ARCH | tempered glass | Z5 | 5th | 44187 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1814 | Check fixation for ceramic tiles for walls and flooring for perparation Area at Ground floor between axis(14-15)&(E-F) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | GF | 44187 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1815 | Check fixation for ceramic tiles for walls and flooring at fourth floor between axis(13-14)&(E-F) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 4th | 44187 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1816 | Check fixation for ceramic tiles for flooring and walls for Toilet at Seventh floor between axis(2-5)&(F-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | 7th | 44188 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1817 | check sika floor (324) layer for flooring between axes (6-13)&(A-F) at Second basement floor for area (Z6) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z6 | B2 | 44188 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1818 | check Final coat (359) layer for flooring between axes (1-6)&(A-L) at Second basement floor for area (Z4,5) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z4,5 | B2 | 44188 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1819 | check Final coat (359) layer for flooring between axes (G-K) &(6-9) at Second basement for area Z (3B) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z3B | B2 | 44188 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1820 | check Final coat (359) layer for flooring of Second basement floor at zone (2,3A) between axes (9-18)(E-L) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z2,3A | B2 | 44188 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1821 | check Final coat (359) layer for flooring of Second basement floor at zone (1) between axes (12-18)(A-F) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z1 | B2 | 44188 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1822 | check Second Putty (Epoxy) for flooring and skerting for Electric room at Seventh floor for area Zone(4) between axes (G-J) &(4-5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4 | 7th | 44188 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1823 | Check fixation for ceramic tiles for walls and flooring for Garbage room at first floor between axis(15-16)&(G-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 1st | 44188 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1824 | check fixation of steel door leaF at ground floor for area (Z1,2,3A)between axes (A_L) (10-18) as per attached sketch. | ARCH | Steel doors Leaf | Z1,2,3A | GF | 44188 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1825 | check fixation of steel door Leaf at ground floor for area (Z4,5,3B)between axes (A_L) (1-8) as per attached sketch. | ARCH | Steel doors Leaf | Z4,5,3B | GF | 44188 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1826 | Check fixation for ceramic tiles for walls and flooring at Ninth floor between axis (10-12)&(J-K) for area (Z3A) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3A | 9th | 44188 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1827 | Check fixation for ceramic tiles for walls and flooring at Ninth floor between axis (7-9)&(J-K) for area (Z3B) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3B | 9th | 44188 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1828 | check installation of Duranta Gold&Carissa Macrocarpa&Paspalum Sod&Canna Glucac and Canna Indica at landscape as per attached sketch . | ARCH | Agriculture |  | EX | 44188 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1829 | check Final coat (Epoxy) for flooring and skerting for Electric room at Seventh floor for area Zone(4) between axes (G-J) &(4-5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4 | 7th | 44188 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1830 | Check Fixation of GRC Decorative columns at landscape as per attached sketch . | ARCH | Decorative Columns |  | EX | 44188 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1831 | check Final coat (Epoxy) for Flooring and Skerting for Transformer Rooms at First basement between axes (A-C)/(5-14) at zones (1,5) as per attached sketch. | ARCH | Painting (Epoxy) | Z1,5 | B1 | 44189 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1832 | check Final coat (Epoxy) for Flooring and Skerting for HVAC and Electric Rooms at second Floor between axes (G-K)/(12-14) at zone(2) as per attached sketch. | ARCH | Painting (Epoxy) | Z2 | 2nd | 44189 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1833 | check Final coat (Epoxy) for Flooring and Skerting for HVAC and Electric Rooms at second Floor between axes (C-D)/(14-17) at zone(1) as per attached sketch. | ARCH | Painting (Epoxy) | Z1 | 2nd | 44189 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1834 | check Final coat (Epoxy) for Flooring and Skerting for HVAC and Electric Room at First Floor between axes (C-D)/(14-17) at zone(1) as per attached sketch. | ARCH | Painting (Epoxy) | Z1 | 1st | 44189 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1835 | check Final coat (Epoxy) for Flooring and Skerting for HVAC Rooms at First Floor between axes (G-K)/(12-14) at zone(2) as per attached sketch. | ARCH | Painting (Epoxy) | Z2 | 1st | 44189 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1836 | check Final coat (Epoxy) for Flooring and Skerting for HVAC and Electric Rooms at Sixth Floor between axes (G-L)/(10-14) at zone(2,3A) as per attached sketch. | ARCH | Painting (Epoxy) | Z2,3A | 6th | 44189 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1837 | check fixation for HPL Partition for Public toilet at First floor fore area Z(4) between axes (F-H)&(2-5) as per attached sketch. | ARCH | HPL partition | Z4 | 1st | 44192 | 44201 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1838 | check Second Putty (Epoxy) for flooring and skerting for Electric and HVAC room at Fifth floor for area Zone(1,2) between axes (C-J) & (12-16) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2 | 5th | 44196 | 44215 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1839 | Check fixation for ceramic tiles for walls and flooring for Garbage&Pantry and Janitor at Fifth floor between axis (15-16)&(G-H) for area (Z2) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z2 | 5th | 44196 | 44215 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1840 | check fixation of vinyl flooring for Das room at Fifth floor for Area Z(2) between axes (15-16)(G-H) as Per Attached Sketch. | ARCH | Vinyl | Z2 | 5th | 44196 | 44215 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1841 | Check fixation for ceramic tiles for walls and flooring for Toilet at Fifth floor between axis (9-12)&(F-L) for area (Z3A) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3A | 5th | 44196 | 44215 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1842 | check Second Putty (Epoxy) for flooring and skerting at First basement for area Zone(1,2,4,5) between axes (A-H) & (5-14) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,4,5 | B1 | 44198 | 44215 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1843 | check Final coat (Epoxy) for flooring and skerting at First basement for area Zone(1,2,4,5) between axes (A-H) & (5-14) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,4,5 | B1 | 44199 | 44215 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1844 | Check fixation for ceramic tiles for walls and flooring at second floor between axis(10-12)&(F-G) for area (Z3A) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3A | 2nd | 44200 | 44215 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1845 | Check fixation for ceramic tiles for walls and flooring at second floor between axis(8-10)&(G-K) for area (Z3B) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3B | 2nd | 44201 | 44215 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1846 | Check fixation for ceramic tiles for walls and flooring at Ninth floor between axis(8-9)&(J-L) for area (Z3B) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3B | 9th | 44203 | 44223 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1847 | Check fixation for ceramic tiles for walls and flooring at Ninth floor between axis(10-11)&(J-L) for area (Z3A) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3A | 9th | 44203 | 44223 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1848 | check Final coat (Epoxy) for flooring and skerting for Electric room at Eighth floor for area Zone(3A) between axes (G-J) &(10-11) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z3A | 8th | 44203 | 44223 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1849 | check Final coat (Epoxy) for flooring and skerting for Electric room at Ninth floor for area Zone(3A) between axes (G-J) &(10-11) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z3A | 9th | 44203 | 44223 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1850 | check installation of Azdirachta indica&Ficus religosa&cassia purpurea&bauhinia pur purea&delonnix regia&pas palum&carissa grandi flora&strelizia reginae and Duranta gold at landscape as per attached sketch . | ARCH | Agriculture |  | EX | 44206 | 44223 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1851 | check Final coat (Epoxy) for flooring and skerting for HVAC and Electric Rooms at First Floor between axes (C-J)/(2-7) at zone(4,5) as per attached sketch. | ARCH | Painting (Epoxy) | Z4,5 | 1st | 44207 | 44223 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1852 | check Final coat (Epoxy) for flooring and skerting for for HVAC and Electric Rooms at Second Floor between axes (C-K)/(2-7) at zone(4,5) as per attached sketch. | ARCH | Painting (Epoxy) | Z4,5 | 2nd | 44207 | 44223 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1853 | check Final coat (Epoxy) for flooring and skerting for for HVAC and Electric Rooms at Sixth Floor between axes (G-K)/(4-7) at zone(4) as per attached sketch. | ARCH | Painting (Epoxy) | Z4 | 6th | 44207 | 44223 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1854 | check First fix for Exterior expansion joint of curtin wall from Seventh to Roof floor between axes (9-10)&(F-G) as Per Attached Sketch. | ARCH | Expansion Joint |  | ML | 44208 | 44223 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1855 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Fifth floor between axis(1-6)&(A-F) for area (Z5) as Per Attached Sketch. | ARCH | Porcelain | Z5 | 5th | 44209 | 44223 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1856 | check Second Putty of Acrylic paintings for walls between axes (14-17)&(A-E) at Sixth floor for area (Z1) as Per Attached Sketch. | ARCH | Painting second Putty | Z1 | 6th | 44209 | 44223 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1857 | check First fix for Wooden Locker and cladding for 1st under Secretary At Second floor for Area Z(3B,4,5) between axes (2-8)&(D-L) as Per Attached Sketch. | ARCH | Wooden Locker&Cladding | Z3B,4,5 | 2nd | 44210 | 44223 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1858 | check First fix for Wooden Locker and cladding for 1st under Secretary At Second floor for Area Z(3A,2,1) between axes (11-12)&(F-L) as Per Attached Sketch. | ARCH | Wooden Locker&Cladding | Z1,2,3A | 2nd | 44210 | 44223 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1859 | Check fixation for ceramic tiles for walls and flooring for Pantry&Garbage and Janitor at Second floor between axis(3-5)&(H-G) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | 2nd | 44213 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1860 | Check fixation for 16mm tempered glass partition between axis (15-17)&(D-F) for area (Z1) at Ground floor as Per Attached Sketch. | ARCH | tempered glass | Z1 | GF | 44214 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1861 | Check fixation for 16mm tempered glass partition between axis (15-17)&(D-F) for area (Z1) at First floor as Per Attached Sketch. | ARCH | tempered glass | Z1 | 1st | 44214 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1862 | Check fixation for 16mm tempered glass partition between axis (15-17)&(D-F) for area (Z1) at Second floor as Per Attached Sketch. | ARCH | tempered glass | Z1 | 2nd | 44214 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1863 | Check fixation for 16mm tempered glass partition between axis (15-17)&(D-F) for area (Z1) at Third floor as Per Attached Sketch. | ARCH | tempered glass | Z1 | 3rd | 44214 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1864 | Check fixation for 16mm tempered glass partition between axis (15-17)&(D-F) for area (Z1) at Fourth floor as Per Attached Sketch. | ARCH | tempered glass | Z1 | 4th | 44214 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1865 | Check fixation for 16mm tempered glass partition between axis (15-17)&(D-F) for area (Z1) at Fifth floor as Per Attached Sketch. | ARCH | tempered glass | Z1 | 5th | 44214 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1866 | Check fixation of marble for Flooring of VIP Entrance at zone(3)between axis (G-K)/(9-10) at Ground floor as Per Attached Sketch. | ARCH | Marble Flooring | Z3 | GF | 44214 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1867 | Check fixation of marble for Walls of VIP Entrance at zone(3) between axis (G-K)/(9-10) at Ground floor as Per Attached Sketch. | ARCH | Marble Walls | Z3 | GF | 44214 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1868 | check Second Putty (Epoxy) for flooring and skerting at Second basement for area Zone(1) between axes (A-E) &(13-18) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1 | B2 | 44215 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1869 | check fixation for External Ramp Handrail for Area Zone (4) as Per Attached Sketch. | ARCH | External Ramp Handrail | Z4 | EX | 44220 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1870 | check fixation for External Ramp Handrail for Area Zone (2) as Per Attached Sketch. | ARCH | External Ramp Handrail | Z2 | EX | 44220 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1871 | check fixation for stainless steel frame mirror for toilet At Second floor for area zone (2) between Axes (F-H)&(14-17) as Per Attached Sketch. | ARCH | Stainless Steel frame mirror | Z2 | 2nd | 44220 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1872 | Check fixation and insulation for wood substructure for mirror in toilets for zone (2,3A,4) between axes (F-L) (2-17) at Seventh floor as Per Attached Sketch. | ARCH | Mirrors Toilet Wood sub. Strc. | Z2,3A,4 | 7th | 44220 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1873 | check Final coat (Epoxy) for flooring and skerting at Second basement for area Zone(1) between axes (A-E) &(13-18) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1 | B2 | 44222 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1874 | Check first fix for wooden doors frames at sixth floor between axis (1-9)&(F-L) for area(3B,4) as Per Attached Sketch. | ARCH | Wooden door Frame | Z3B,4 | 6th | 44223 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1875 | check fixation for HPL Partition for Public toilet at Ground floor fore area Z(4) between axes (F-H)&(2-5) as per attached sketch. | ARCH | HPL partition | Z4 | GF | 44226 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1876 | Check fixation for ceramic tiles for walls and flooring for Pantry&Garbage and Janitor at Ground floor between axis(3-5)&(H-G) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z4 | GF | 44226 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1877 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (1-9)&(A-L) for area (Z3B,4,5) at third floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z3B,4,5 | 3rd | 44227 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1878 | Check fixation for ceramic tiles for walls and flooring for Toilet at Sixth floor between axis(2-9)&(L-G) for area (Z3B,4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3B,4 | 6th | 44227 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1879 | check Final coat (Epoxy) for flooring and skerting for Electric and HVAC room at Fifth floor for area Zone(1,2) between axes (C-J) & (12-16) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2 | 5th | 44227 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1880 | check Second Putty (Epoxy) for flooring and skerting for Electric room at Fifth floor for area Zone(3A) between axes (G-J) &(10-11) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z3A | 5th | 44227 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1881 | check Final coat (Epoxy) for flooring and skerting for Electric and HVAC room at Fifth floor for area Zone(4) between axes (H-J) &(4-7) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4 | 5th | 44228 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1882 | check Final coat (Epoxy) for flooring and skerting for Electric and HVAC room at Fifth floor for area Zone(5) between axes (C-D) &(3-5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z5 | 5th | 44228 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1883 | Check fixation and installation for marbel Fecade between axis(1-2)&(A-F) for area (Z5) From Ground to Second Floor as Per Attached Sketch. | ARCH | Marble Façade | Z5 | ML | 44228 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1884 | Check fixation for ceramic tiles for walls and flooring for Toilet at Ninth floor between axis(9-10)&(G-H) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | 9th | 44228 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1885 | Check first fix for G.B sheet(Bulk head) at First basement between axis (1-18)&(C-E) for area (Z1,5) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,5 | B1 | 44228 | 44252 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1886 | check fixation of wooden clading at Z1 between axis (D_E)(15-16) at Ground floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z1 | GF | 44230 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1887 | check fixation of wooden clading at Z1 between axis (D_E)(15-16) at First floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z1 | 1st | 44230 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1888 | check fixation of Sub Structure under wooden clading at Z(2,3A) between axis (G_L)(10-18) at First floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z2,3A | 1st | 44230 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1889 | check Second Putty (Epoxy) for flooring and skerting at Second basement for area Zone(2) between axes (E-L) &(13-18) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2 | B2 | 44230 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1890 | check Final coat (Epoxy) for flooring and skerting at Second basement for area Zone(2) between axes (E-L) &(13-18) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2 | B2 | 44230 | 44252 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1891 | Check first fix for closets and shelves at Second floor between axis (1-6)&(A-E) for area (5) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z5 | 2nd | 44231 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1892 | Check fixation for ceramic tiles for walls and flooring for Toilet at Eighth floor between axis(8-11)&(K-L) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | 8th | 44231 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1893 | check fixation for Enternal Glass Handrail from Ground to Fifth floor between Axis (A-F)&(15-16) for Area Zone (1) as Per Attached Sketch. | ARCH | Enternal Glass Handrail | Z1 | ML | 44235 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1894 | check Second Putty (Epoxy) for flooring and skerting at Second basement for area Zone(3A) between axes (F-L) &(10-13) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z3A | B2 | 44237 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1895 | check Final coat (Epoxy) for flooring and skerting at Second basement for area Zone(3A) between axes (F-L) &(10-13) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z3A | B2 | 44237 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1896 | Check first fix for wooden doors leaf at Fifth floor between axis (1-5)&(B-F) for area(Z5) as Per Attached Sketch. | ARCH | Wooden door Leaf | Z5 | 5th | 44237 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1897 | check fixation for HPL Partition for Public toilet at Fourth floor for area Z(4) between axes (F-H)&(3-4) as per attached sketch. | ARCH | HPL partition | Z4 | 4th | 44237 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1898 | Check first fix for closets and shelves at first floor between axis (7-9)&(E-L) for area (3B) as Per Attached Sketch. | ARCH | Wooden Closest & Shelves | Z3B | 1st | 44237 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1899 | check First fix for Wooden Locker and cladding under Secretary At Third floor for Area Z(3B,4,5) between axes (2-8)&(D-L) as Per Attached Sketch. | ARCH | Wooden Locker&Cladding | Z3B,4,5 | 3rd | 44238 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1900 | Check fixation for marble sill under 12mm tempered glass partition for corridors between axis (2-8)&(A-K) for area (Z4,5) at Fifth floor as Per Attached Sketch. | ARCH | Marble sill | Z4,5 | 5th | 44244 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1901 | check Second Putty (Epoxy) for flooring and skerting at Second basement for area Zone(3B,4) between axes (F-K) &(3-9) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z3B,4 | B2 | 44244 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1902 | check Final coat (Epoxy) for flooring and skerting at Second basement for area Zone(3B,4) between axes (F-K) &(3-9) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z3B,4 | B2 | 44244 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1903 | check First fix for Wooden Locker and cladding for 1st under Secretary At Third floor for Area Z(1,2,3A) between axes (11-16)&(B-H) as Per Attached Sketch. | ARCH | Wooden Locker&Cladding | Z1,2,3A | 3rd | 44244 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1904 | Check fixation for 16mm tempered glass partition between axis (7-9)&(G-K) for area (Z3B) at First floor as Per Attached Sketch. | ARCH | tempered glass | Z3B | 1st | 44248 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1905 | check installation of Duranta Gold & Carissa Macrocarpa & Paspalum & Hedera Helx & Tecomaria & Euphorbia-Red & Strelitzia Reginee & Carissa Grand Flora & Canna Gluce and Canna Indica at landscape as per attached sketch . | ARCH | Agriculture |  | EX | 44250 | 44270 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1906 | check fixation for HPL Partition for Public toilet at Second floor for area Z(2) between axes (F-H)&(14-17) as per attached sketch. | ARCH | HPL partition | Z2 | 2nd | 44250 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1907 | check fixation for HPL Partition for Public toilet at Third floor for area Z(2) between axes (F-H)&(14-17) as per attached sketch. | ARCH | HPL partition | Z2 | 3rd | 44250 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1908 | Check fixation and installation for marbel Fecade ((From (300.50) to (308.10)) between axis(17-19)&(A-F) for area (Z1) From Ground to Second Floor as Per Attached Sketch. | ARCH | Marble Façade | Z1 | ML | 44251 | 44271 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1909 | check fixation for HPL Partition for Public toilet at Third floor for area Z(4) between axes (F-H)&(2-5) as per attached sketch. | ARCH | HPL partition | Z4 | 3rd | 44251 | 44271 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1910 | Check fixation of Wooden Cladding of corridor infront of elevetors at zone(1,2,3A) between axis (A-L)/(10-18) at First floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z1,2,3A | 1st | 44251 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1911 | Check fixation of Stainless Steel of corridor infront of elevetors at zone(1) between axis (D-E)/(15-16) at Ground floor as Per Attached Sketch. | ARCH | Stainless steel (Elevators) | Z1 | GF | 44251 | 44306 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1912 | Check fixation of Stainless Steel of corridor infront of elevetors at zone(1,2,3A) between axis (A-L)/(10-18) at First floor as Per Attached Sketch. | ARCH | Stainless steel (Elevators) | Z1,2,3A | 1st | 44251 | 44306 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1913 | Check fixation and installation for marbel Fecade between axis(12-19)&(A-B) for area (Z1) At Ground Floor as Per Attached Sketch. | ARCH | Marble Façade | Z1 | GF | 44259 | 44271 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1914 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Fifth floor between axis(6-10)&(F-L) for area (Z3B) as Per Attached Sketch. | ARCH | Porcelain | Z3B | 5th | 44259 | 44271 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1915 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Fifth floor between axis(1-8)&(F-L) for area (Z4) as Per Attached Sketch. | ARCH | Porcelain | Z4 | 5th | 44259 | 44271 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1916 | check Second Putty (Epoxy) for flooring and skerting for HVAC and ELECTRIC rooms at Fourth floor for area Zone(4) between axes (G-J) &(4-7) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4 | 4th | 44259 | 44271 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1917 | check Final (Epoxy) for flooring and skerting for HVAC and ELECTRIC rooms at Fourth floor for area Zone(5) between axes (C-D) &(2-5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z5 | 4th | 44259 | 44271 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1918 | check Second Putty (Epoxy) for flooring and skerting for HVAC and ELECTRIC rooms at Fourth floor for area Zone(5) between axes (C-D) &(2-5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z5 | 4th | 44259 | 44271 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1919 | check Final (Epoxy) for flooring and skerting for HVAC and ELECTRIC rooms at Fourth floor for area Zone(4) between axes (G-J) &(4-7) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z4 | 4th | 44259 | 44271 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1920 | check Second Putty (Epoxy) for flooring at Second Basement for area Zone(5) between axes (A-F) &(1-7) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z5 | B2 | 44263 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1921 | check Final coat (Epoxy) for flooring at Second Basement for area Zone(5) between axes (A-F) &(1-7) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z5 | B2 | 44263 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1922 | Check fixation and installation for transom and mullion and EPDM for curtin wall between axis (11-14)&(F-G) for area (Z2) From Ground to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z2 | ML | 44264 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1923 | Check fixation and installation for glass for curtin wall between axis (11-14)&(F-G) for area (Z2) From Ground to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z2 | ML | 44264 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1924 | Check first fix for G.B sheet(Bulk head) at Fifth floor between axis (5-10)&(F-L) for area (Z3B) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3B | 5th | 44264 | 44271 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1925 | Check fixation for ceramic tiles for walls and flooring for Toilet at Seventh floor between axis(5-13)&(H-K) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | 7th | 44264 | 44271 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1926 | Check fixation for ceramic tiles for walls for Garbage rooms at first Basement between axis(1-18)&(F-H) for area (Z2,4) as Per Attached Sketch. | ARCH | Ceramic Walls | Z2,4 | B1 | 44265 | 44271 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1927 | check Second Putty (Epoxy) for flooring and Skerting for Garbage rooms at first Basement between axis(1-18)&(F-H) for area (Z2,4) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2,4 | B1 | 44265 | 44271 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1928 | check Final coat (Epoxy) for flooring and Skerting for Garbage rooms at first Basement between axis(1-18)&(F-H) for area (Z2,4) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2,4 | B1 | 44265 | 44271 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1929 | Check fixation and installation for marbel Fecade between axis(1-6)&(A-B) for area (Z5) From Second to Fifth Floor as Per Attached Sketch. | ARCH | Marble Façade | Z5 | ML | 44277 | 44311 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1930 | check installation of wooden door leaf at Fifth floor for area (3B)between axes (F-L) (7-9) as per attached sketch. | ARCH | Wooden door Leaf | Z3B | 5th | 44277 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1931 | check installation of wooden door leaf at Fifth floor for area (4)between axes (F-L) (2-7) as per attached sketch. | ARCH | Wooden door Leaf | Z4 | 5th | 44277 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1932 | check First fix for Wooden Locker and cladding for 1st under Secretary At Fourth floor for Area Z(1,2,3A) between axes (11-15)&(D-L) as Per Attached Sketch. | ARCH | Wooden Locker&Cladding | Z1,2,3A | 4th | 44278 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1933 | check First fix for Wooden Locker and cladding for 1st under Secretary At Fifth floor for Area Z(1,2,3A) between axes (11-15)&(C-L) as Per Attached Sketch. | ARCH | Wooden Locker&Cladding | Z1,2,3A | 5th | 44278 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1934 | check installation of wooden door leaf at Fifth floor for area (1,2,3A) between axes (B-L) (10-17) as per attached sketch. | ARCH | Wooden door Leaf | Z1,2,3A | 5th | 44278 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1935 | Check first fix for closets and shelves at Fifth floor for area (2,3A) between axes (F-L) (10-18) as per attached sketch. | ARCH | Wooden Closest & Shelves | Z2,3A | 5th | 44278 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1936 | Check fixation for ceramic tiles for walls and flooring for Toilet at Eighth floor between axis(8-11)&(K-L) for area (Z3) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring | Z3 | 8th | 44280 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1937 | check fixation of Sub Structure under wooden cladding at Z(1,2,3A) between axis (A_L)(10-18) at Second floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z1,2,3A | 2nd | 44282 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1938 | check fixation of Sub Structure under wooden cladding at Z(1,2,3A) between axis (A_L)(10-18) at Third floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z1,2,3A | 3rd | 44282 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1939 | check fixation of wooden cladding at Z(1,2,3A) between axis (A_L)(10-18) at Second floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z1,2,3A | 2nd | 44282 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1940 | check fixation of wooden cladding at Z(1,2,3A) between axis (A_L)(10-18) at Third floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z1,2,3A | 3rd | 44282 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1941 | Check fixation of Stainless Steel of corridor infront of elevetors at zone(1,2,3A) between axis (A-L)/(10-18) at Second floor as Per Attached Sketch. | ARCH | Stainless steel (Elevators) | Z1,2,3A | 2nd | 44282 | 44306 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1942 | Check fixation of Stainless Steel of corridor infront of elevetors at zone(1,2,3A) between axis (A-L)/(10-18) at Third floor as Per Attached Sketch. | ARCH | Stainless steel (Elevators) | Z1,2,3A | 3rd | 44282 | 44306 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1943 | check Second Putty (Epoxy) for flooring and Skerting of pavement and wheel stopper at Second Basement between axis(12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z1 | B2 | 44284 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1944 | check Final coat (Epoxy) for flooring and Skerting of pavement and wheel stopper at Second Basement between axis(12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z1 | B2 | 44284 | 44306 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1945 | check fixation of Sub Structure under wooden cladding at Z(2) between axis (J_L)(15-17) at Ground floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z2 | GF | 44290 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1946 | Check fixation and installation for glass for curtin wall between axis (1-7)&(A-F) for area (Z5) From Second to Fifth Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z5 | ML | 44290 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1947 | check First fix for Wooden Locker and cladding for 1st under Secretary At Fifth floor for Area Z(3B,5) between axes (1-8)&(C-L) as Per Attached Sketch. | ARCH | Wooden Locker&Cladding | Z3B,5 | 5th | 44298 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1948 | Check fixiation for Flooring marble for walk way at landscape as Per Attached Sketch. | ARCH | Marble (Landscape) |  | EX | 44306 | 44333 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1949 | Check Installation and Fixation of Internal Golden Stainless Steel Eagle at Ground floor for Area Z (1,2,3,4,5) between Axis (1-18)&(A-L) as Per Attached Sketch. | ARCH | Internal Golden S.S Eagle | Z1,2,3,4,5 | GF | 44311 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1950 | check First fix for Wooden Locker and cladding for 1st under Secretary At Fourth floor for Area Z(3B,5) between axes (1-9)&(A-L) as Per Attached Sketch. | ARCH | Wooden Locker&Cladding | Z3B,5 | 4th | 44312 | 44333 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1951 | check Second Putty (Epoxy) for flooring and Skerting of pavement and wheel stopper at Second Basement between axis(12-18)&(F-L) for area (Z2) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z2 | B2 | 44314 | 44333 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1952 | Check fixation and installation for Terrazo Tiles at Roof between axis(1-6)&(F-L) for area (Z4) at Eighth Floor as Per Attached Sketch. | ARCH | Terrazo Roof | Z4 | 8th | 44320 | 44333 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1953 | Check fixation and installation for Terrazo Tiles at Roof between axis(13-18)&(F-L) for area (Z2) at Eighth Floor as Per Attached Sketch. | ARCH | Terrazo Roof | Z2 | 8th | 44320 | 44374 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1954 | Check fixation and installation for Terrazo Tiles at Roof between axis(13-18)&(A-F) for area (Z1) at Sixth Floor as Per Attached Sketch. | ARCH | Terrazo Roof | Z1 | 6th | 44320 | 44374 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1955 | Check fixation and installation for Terrazo Tiles at Roof between axis(1-6)&(F-L) for area (Z5) at Sixth Floor as Per Attached Sketch. | ARCH | Terrazo Roof | Z5 | 6th | 44320 | 44381 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1956 | Check fixation and installation for Terrazo Tiles at Roof between axis(7-12)&(E-L) for area (Z3) at Roof as Per Attached Sketch. | ARCH | Terrazo Roof | Z3 | RF | 44320 | 44374 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1957 | Check fixation and installation for Terrazo Tiles at Roof between axis(1-6)&(F-L) for area (Z5) at Second Floor as Per Attached Sketch. | ARCH | Terrazo Roof | Z5 | 2nd | 44320 | 44381 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1958 | check fixation of Sub Structure under wooden cladding at Z(4) between axis (J_L)(3-5) at Ground floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z4 | GF | 44322 | 44405 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1959 | check first fix for wooden cladding at Z(2) between axis (J_L)(15-17) at Ground floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z2 | GF | 44322 | 44408 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1960 | check first fix for wooden cladding at Z(4) between axis (J_L)(3-5) at Ground floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z4 | GF | 44322 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1961 | Check Fixation for chasis&Rock wool for HVAC ROOMS for Walls At First Floor for Area Z(1,2,4,5) between axis (C-K)&(2-17) as Per Attached Sketch. | ARCH | Chasis&Rock wool | Z1,2,4,5 | 1st | 44322 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1962 | Check Fixation for chasis&Rock wool for HVAC ROOMS for Walls At Second Floor for Area Z(1,2,4,5) between axis (C-K)&(2-17) as Per Attached Sketch. | ARCH | Chasis&Rock wool | Z1,2,4,5 | 2nd | 44322 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1963 | Check Fixation for chasis&Rock wool for HVAC ROOMS for Walls At Third Floor for Area Z(1,2,4,5) between axis (C-K)&(2-17) as Per Attached Sketch. | ARCH | Chasis&Rock wool | Z1,2,4,5 | 3rd | 44322 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1964 | check installation of wooden door leaf at Third floor for area (1,2,3A) between axes (B-L) (10-17) as per attached sketch. | ARCH | Wooden door Leaf | Z1,2,3A | 3rd | 44336 | 44368 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1965 | Check fixation and installation for marbel Fecade between axis(12-13)&(A-E) for area (Z1) From Ground to Second Floor as Per Attached Sketch. | ARCH | Marble Façade | Z1 | ML | 44339 | 44438 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1966 | Check Final coat (Epoxy) for flooring and Skerting of pavement and wheel stopper at Second Basement between axis(12-18)&(F-L) for area (Z2) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z2 | B2 | 44343 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1967 | check installation of wooden door leaf at Sixth floor for area (2,3A) between axes (F-L) (10-17) as per attached sketch. | ARCH | Wooden door Leaf | Z2,3A | 6th | 44346 | 44368 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1968 | check installation of wooden door leaf at Sixth floor for area (3B,4) between axes (F-L) (1-9) as per attached sketch. | ARCH | Wooden door Leaf | Z3B,4 | 6th | 44346 | 44368 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1969 | check fixation of vinyl flooring for Main Building Entrance room at First basement for Area Z(1,5) between axes (1-18)(A) as Per Attached Sketch. | ARCH | Vinyl | Z1,5 | B1 | 44350 | 44405 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1970 | Check fixation for Marble Counter for Area Z(2) At Ground Floor between Axis (15-16)&(J-L) as Per Attached Sketch. | ARCH | Marble Counter | Z2 | GF | 44350 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1971 | Check fixation for (Wooden Planks) for flooring and skerting at Ninth floor between axis(9-11)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | Engineering wood | Z3 | 9th | 44350 | 44368 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1972 | Check fixation and installation for glass for curtin wall between axis (12-18)&(A-G) for area (Z1,2) From Second to Fifth Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z1,2 | ML | 44353 | 44369 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1973 | Check fixation for Shutter doors at First Basement for Area Z(2,4) between Axis (1-18)&(A) as Per Attached Sketch. | ARCH | Shutter Doors | Z2,4 | B1 | 44356 | 44368 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1974 | Check First fix for (G.B) Walls and ceiling at Ground Floor for Area Z (1,5) Between Axis (1-18)&(A-C) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,5 | GF | 44356 | 44369 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1975 | Check Fixation for Rock Wool for walls and Ceiling at Transformer rooms At Ground Floor for Area Z (1,5) Between Axis (1-18)&(A-C) as Per Attached Sketch. | ARCH | Rock wool | Z1,5 | GF | 44356 | 44369 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1976 | Check Fixation for External Ramp handrail for Area Z(3) At Ground Floor Between Axis (10-12)&(K-L) as Per Attached Sketch. | ARCH | External Ramp Handrail | Z3 | GF | 44356 | 44368 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1977 | Check first fix for G.B sheet(Bulk head) at Ground Floor between axis (1-18)&(A-L) for area (Z1,2,3,4,5) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,2,3,4,5 | GF | 44360 | 44430 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1978 | Check fixation for Marble Counter for Area Z(3) At Ground Floor between Axis (9-10)&(J-K) as Per Attached Sketch. | ARCH | Marble Counter | Z3 | GF | 44364 | 44380 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1979 | Check Fixation for Signage Metal walls for (CORE) At Ground Floor for area Z(1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Metal Signage | Z1,2,3,4,5 | GF | 44364 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1980 | Check Fixation for Signage Metal walls for (CORE) At First basement for area Z(1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Metal Signage | Z1,2,3,4,5 | B1 | 44364 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1981 | Check Fixation for Signage Metal walls for (CORE) At Second basement for area Z(1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Metal Signage | Z1,2,3,4,5 | B2 | 44364 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1982 | Check Crystaline water proofing for Pump room And Irrigation tank at Landscape as Per Attached Sketch. | ARCH | Crystaline |  | EX | 44368 | 44375 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1983 | check fixation for interlock for walkway of landscape as Per Attached Sketch. | ARCH | Interlock |  | EX | 44369 | 44374 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1984 | Check Fixation for Signage Metal walls for (CORE) At First Floor for area Z(1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Metal Signage | Z1,2,3,4,5 | 1st | 44369 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1985 | Check Fixation for Signage Metal walls for (CORE) At Second Floor for area Z(1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Metal Signage | Z1,2,3,4,5 | 2nd | 44369 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1986 | Check Fixation for Signage Metal walls for (CORE) At Third Floor for area Z(1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Metal Signage | Z1,2,3,4,5 | 3rd | 44369 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1987 | Check Fixation for Signage Metal walls for (CORE) At Fourth Floor for area Z(1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Metal Signage | Z1,2,3,4,5 | 4th | 44369 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1988 | Check Fixation for Signage Metal walls for (CORE) At Fifth Floor for area Z(1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Metal Signage | Z1,2,3,4,5 | 5th | 44369 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1989 | Check Fixation for Signage Metal walls for (CORE) At Sixth Floor for area Z(1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Metal Signage | Z1,2,3,4,5 | 6th | 44369 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1990 | Check first fix for G.B sheet(Bulk head) at First Floor between axis (2-17)&(C-K) for area (Z1,2,3,4,5) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,2,3,4,5 | 1st | 44370 | 44381 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1991 | Check fixation and installation for mirrors in toilets for zone (2,4) between axes (F-H) (2-17) at Ground floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | GF | 44370 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1992 | Check fixation and installation for mirrors in toilets for zone (2,4) between axes (F-H) (2-17) at First floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | 1st | 44370 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1993 | Check fixation and installation for mirrors in toilets for zone (2,4) between axes (F-H) (2-17) at Second floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | 2nd | 44370 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1994 | Check fixation and installation for mirrors in toilets for zone (2,4) between axes (F-H) (2-17) at Third floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | 3rd | 44370 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1995 | Check fixation and installation for mirrors in toilets for zone (2,4) between axes (F-H) (2-17) at Fourth floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | 4th | 44370 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1996 | Check fixation and installation for mirrors in toilets for zone (2,4) between axes (F-H) (2-17) at Fifth floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | 5th | 44370 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1997 | Check fixation and installation for mirrors in toilets for zone (2,4) between axes (F-H) (2-17) at Sixth floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | 6th | 44370 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1998 | check fixation for Enternal Glass and Stainles Steel for Handrail from Ground to Fifth floor between Axis (D-F)&(2-5) for Area Zone (5) as Per Attached Sketch. | ARCH | Enternal Glass Handrail | Z5 | ML | 44370 | 44430 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-1999 | Check fixation and installation for glass for curtin wall (VIP) between axis (7-12)&(E-L) for area (Z3) From Ground to First Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z3 | ML | 44374 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2000 | Check fixation and installation for glass for curtin wall between axis (7-12)&(E-L) for area (Z3) From Seventh to Ninth Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z3 | ML | 44374 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2001 | Check fixation and installation for glass for curtin wall between axis (7-12)&(E-L) for area (Z3) From Seventh to Ninth Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z3 | ML | 44374 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2002 | Check fixation and installation for curtin wall between axis (12-18)&(E-L) for area (Z2) From Ground to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z2 | ML | 44374 | 44381 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2003 | check Second Putty (Epoxy) for flooring and Skerting for UPS&BATTERY rooms at First Basement between axis(16-18)&(C-E) for area (Z1,5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,5 | B1 | 44375 | 44381 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2004 | check final coat (Epoxy) for flooring and Skerting for UPS&BATTERY rooms at First Basement between axis(16-18)&(C-E) for area (Z1,5) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,5 | B1 | 44375 | 44381 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2005 | Check fixiation for Flooring marble for walk way at landscape as Per Attached Sketch. | ARCH | Marble (Landscape) |  | EX | 44376 | 44405 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2006 | check fixation of Sub Structure under wooden cladding at Z(4) between axis (J_L)(2-4) at Ground floor as Per Attached Sketch. | ARCH | Wooden Cladding (sub structure) | Z4 | GF | 44376 | 44430 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2007 | check first fix for wooden cladding at Z(4) between axis (J_L)(2-4) at Ground floor as Per Attached Sketch. | ARCH | Wooden Cladding | Z4 | GF | 44376 | 44430 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2008 | Check fixation for 6mm tempered glass partition for (Public Toilet) between axis (2-17)&(F-H) for area (Z2,4) at Ground floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | GF | 44377 | 44430 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2009 | Check fixation for 6mm tempered glass partition for (Public Toilet) between axis (2-17)&(F-H) for area (Z2,4) at First floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | 1st | 44377 | 44430 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2010 | Check fixation for 6mm tempered glass partition for (Public Toilet) between axis (2-17)&(F-H) for area (Z2,4) at Second floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | 2nd | 44377 | 44430 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2011 | Check fixation for 6mm tempered glass partition for (Public Toilet) between axis (2-17)&(F-H) for area (Z2,4) at Third floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | 3rd | 44377 | 44430 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2012 | Check fixation for 6mm tempered glass partition for (Public Toilet) between axis (2-17)&(F-H) for area (Z2,4) at Fourth floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | 4th | 44377 | 44430 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2013 | Check fixation for 6mm tempered glass partition for (Public Toilet) between axis (2-17)&(F-H) for area (Z2,4) at Fifth floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | 5th | 44377 | 44430 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2014 | Check fixation for 6mm tempered glass partition for (Public Toilet) between axis (2-17)&(F-H) for area (Z2,4) at Sixth floor as Per Attached Sketch. | ARCH | Mirrors Toilet | Z2,4 | 6th | 44377 | 44430 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2015 | Check fixation Sun Breakers (Façade) for Curtin wall Glass at First floor between axis(1-18)&(A-L) for area (Z1,2,4,5) as Per Attached Sketch. | ARCH | Sun Breakers Façade | Z1,2,4,5 | 1st | 44382 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2016 | Check fixation Sun Breakers (Façade) for Curtin wall Glass at Fifth floor between axis(1-18)&(A-L) for area (Z1,5) as Per Attached Sketch. | ARCH | Sun Breakers Façade | Z1,5 | 5th | 44382 | 44422 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2017 | Check fixation Sun Breakers (Façade) for Curtin wall Glass at Seventh floor between axis(1-18)&(F-L) for area (Z2,4) as Per Attached Sketch. | ARCH | Sun Breakers Façade | Z2,4 | 7th | 44382 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2018 | Check fixation and installation for marbel of Stair between axis(15-16)&(D-F) for area (Z1) from Second to fifth as Per Attached Sketch. | ARCH | Marble Stairs | Z1 | ML | 44383 | 44438 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2019 | Check fixation and installation for marbel of Stair between axis(3-5)&(D-F) for area (Z5) from Ground to fifth as Per Attached Sketch. | ARCH | Marble Stairs | Z5 | ML | 44383 | 44438 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2020 | Check Fixation for External Ramp handrail At Landscape as Per Attached Sketch. | ARCH | External Ramp Handrail |  | EX | 44383 | 44408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2021 | Check Fixation and installation for Louver steel at Sixth floor for area Z(1,5) between axis (1-18)&(A_F) as Per Attached Sketch. | ARCH | Louver Steel | Z1,5 | 6th | 44384 | 44422 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2022 | Check Fixation for G.B for Walls at HVAC ROOMS (2 Layers) At First Floor for Area Z(1,2,4,5) between axis (C-K)&(2-17) as Per Attached Sketch. | ARCH | Acoustic insulation | Z1,2,4,5 | 1st | 44410 | 44422 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2023 | Check Fixation for G.B for Walls at HVAC ROOMS (2 Layers) At Second Floor for Area Z(1,2,4,5) between axis (C-K)&(2-17) as Per Attached Sketch. | ARCH | Acoustic insulation | Z1,2,4,5 | 2nd | 44410 | 44422 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2024 | Check Fixation for G.B for Walls at HVAC ROOMS (2 Layers) At Third Floor for Area Z(1,2,4,5) between axis (C-K)&(2-17) as Per Attached Sketch. | ARCH | Acoustic insulation | Z1,2,4,5 | 3rd | 44410 | 44422 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2025 | Check Fixation for (G.B) Walls and ceiling (Generator Room) ( 3 Layers) at Ground Floor for Area Z (1,5) Between Axis (1-18)&(A-C) as Per Attached Sketch. | ARCH | Acoustic insulation | Z1,5 | GF | 44410 | 44438 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2026 | Check Fixation for Metal Panel for Walls (Generator Room) at Ground Floor for Area Z (1,5) Between Axis (1-18)&(A-C) as Per Attached Sketch. | ARCH | Acoustic insulation | Z1,5 | GF | 44410 | 44438 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2027 | Check fixation Sun Breakers (Façade) for Curtin wall Glass at Seventh floor between axis(12-18)&(F-L) for area (Z2) as Per Attached Sketch. | ARCH | Sun Breakers Façade | Z2 | 7th | 44410 | 44422 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2028 | check fixation for HPL Partition at First Basement for area Z(1,5) between axes (D-E)&(1-18) as per attached sketch. | ARCH | HPL partition | Z1,5 | B1 | 44410 | 44422 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2029 | Check Fixation for doors for Louver at Sixth floor for area Z(1) between axis (14-17)&(B_E) as Per Attached Sketch. | ARCH | Louver Doors | Z1 | 6th | 44422 | 44430 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2030 | Check Fixation for doors for Louver at Sixth floor for area Z(5) between axis (2-5)&(B_E) as Per Attached Sketch. | ARCH | Louver Doors | Z5 | 6th | 44422 | 44430 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2031 | check Second Putty (Epoxy) for flooring and Skerting at First Basement between axis(1-8)&(A-G) for area (Z5) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z5 | B1 | 44422 | 44430 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2032 | check final coat (Epoxy) for flooring and Skerting at First Basement between axis(1-8)&(A-G) for area (Z5) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z5 | B1 | 44422 | 44430 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2033 | check Second Putty (Epoxy) for flooring and Skerting at Second Basement between axis(1-8)&(A-G) for area (Z5) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z5 | B2 | 44422 | 44430 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2034 | check final coat (Epoxy) for flooring and Skerting at Second Basement between axis(1-8)&(A-G) for area (Z5) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z5 | B2 | 44422 | 44430 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2035 | Check Fixation for Marble for Walk Way at Landscape accordding to the attached sketch. | ARCH | Marble (Landscape) |  | EX | 44434 | 44438 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2036 | Check Water Test and Finishing for glass for curtin wall between axis (9-10)&(K-L) for area (Z3) From Ground to Second Floor as Per Attached Sketch. | ARCH | Curtain Wall Water test | Z3 | ML | 44437 | 44451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2037 | Check first fix for acceccories (G.B Tiles) at First floor for area (Z3B,4,5) between axes(A-L) &(1-10) as per attached sketch. | ARCH | False ceiling (Tiles) 1st | 4,5,3B | 1st | 44437 | 44447 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2038 | Check first fix for acceccories (G.B Tiles) at Ground floor for area (Z1,2,3A) between axes(A-L) &(10-18) as per attached sketch. | ARCH | False ceiling (Tiles) 1st | Z1,2,3A | GF | 44437 | 44447 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2039 | Check first fix for acceccories (G.B Tiles) at Ground floor for area (Z3B,4,5) between axes(A-L) &(1-10) as per attached sketch. | ARCH | False ceiling (Tiles) 1st | 4,5,3B | GF | 44437 | 44447 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2040 | Check Fixation for Marble for Walk Way at Landscape accordding to the attached sketch. | ARCH | Marble (Landscape) |  | EX | 44437 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2041 | Check Fixation for External Ramp handrail At Landscape as Per Attached Sketch. | ARCH | External Ramp Handrail |  | EX | 44439 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2042 | Check fixation and installation for glass for curtin wall between axis (1-10)&(A-F) for area (Z4-5) From Ground to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) |  | ML | 44439 | 44451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2043 | Check Water Test and Finishing for glass for curtin wall between axis (1-10)&(A-F) for area (Z4-5) From Ground to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall Water test |  | ML | 44439 | 44451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2044 | Check fixation for wooden doors leaf at Fourth floor between axis (10-18)&(A-L) for area(1,2,3A) as Per Attached Sketch. | ARCH | Wooden door Leaf | Z1,2,3A | 4th | 44439 | 44447 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2045 | Check first fix for wooden doors Frame at Fourth floor between axis (1-9)&(A-L) for area(3B,4,5) as Per Attached Sketch. | ARCH | Wooden door Frame | 3B,4,5 | 4th | 44439 | 44447 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2046 | Check fixation for wooden doors leaf at Fourth floor between axis (1-9)&(A-L) for area(3B,4,5) as Per Attached Sketch. | ARCH | Wooden door Leaf | 3B,4,5 | 4th | 44439 | 44447 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2047 | Check Fixation for Marble for Walk Way at Landscape accordding to the attached sketch. | ARCH | Marble (Landscape) |  | EX | 44439 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2048 | Check Fixation for Marble for Walk Way at Landscape accordding to the attached sketch. | ARCH | Marble (Landscape) |  | EX | 44439 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2049 | Check fixation for ceramic tiles for walls and flooring for (Pantry-Janitor-Garbage ) room at Sixth floor between axis(3-5)&(G-H) for area (Z4) as Per Attached Sketch. | ARCH | Ceramic Walls&flooring |  | 6th | 44439 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2050 | check Second Putty (Epoxy) for flooring and Skerting (Bavement) at First Basement between axis(1-10)&(E-L) for area (Z4) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z4 | B1 | 44439 | 44447 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2051 | Final coat (Epoxy) for flooring and Skerting (Bavement) at First Basement between axis(1-10)&(E-L) for area (Z4) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z4 | B1 | 44439 | 44447 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2052 | Check for Final Plaster between axes (6-13)&(E-L) at Roof floor for area (Z3) as Per Attached Sketch. | ARCH | Final Plaster | Z3 | RF | 44440 | 44451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2053 | Check for Final Plaster between axes (2-17)&(G-K) at Ninth floor for area (2,4) as Per Attached Sketch. | ARCH | Final Plaster | Z2,4 | 9th | 44440 | 44451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2054 | Check for Final Plaster between axes (1-18)&(F-L) at Eighth floor for area (2,4) as Per Attached Sketch. | ARCH | Final Plaster | Z2,4 | 8th | 44440 | 44451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2055 | Check for Final Plaster between axes (2-17)&(A-F) at Seventh floor for area (1,5) as Per Attached Sketch. | ARCH | Final Plaster | 1,5 | 7th | 44440 | 44451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2056 | Check for Final Plaster between axes (1-18)&(A-F) at Sixth floor for area (1,5) as Per Attached Sketch. | ARCH | Final Plaster | 1,5 | 6th | 44440 | 44451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2057 | Check Fixation for Skerting Terrazo At Ninth Floor between axes (2-17)&(G-K) for Area Z(2,4) as Per Attached Sketch. | ARCH | Skerting Terrazo | 2,4 | 9th | 44440 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2058 | Check Fixation for Skerting Terrazo At Eighth Floor between axes (2-17)&(F-L) for Area Z(2,4) as Per Attached Sketch. | ARCH | Skerting Terrazo | 2,4 | 8th | 44440 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2059 | Check Fixation for Skerting Terrazo At Seventh Floor between axes (2-17)&(A-F) for Area Z(1,5) as Per Attached Sketch. | ARCH | Skerting Terrazo | 1,5 | 7th | 44440 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2060 | Check Fixation for Skerting Terrazo At Sixth Floor between axes (1-18)&(A-G) for Area Z(1,5) as Per Attached Sketch. | ARCH | Skerting Terrazo | 1,5 | 6th | 44440 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2061 | Check Fixation for Skerting Terrazo At Second Floor between axes (1-18)&(A-L) for Area Z(1,2,4,5) as Per Attached Sketch. | ARCH | Skerting Terrazo | 1,2,4,5 | 2nd | 44440 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2062 | Check Fixation for threeshold under louver at Sixth Floor for Area Z(1,5) between Axes (2-17)&(B-D) as Per Attached Sketch. | ARCH | ThreeShold Under louver | 1,5 | 6th | 44443 | 44447 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2063 | Check Fixation for Metal flash At Sixth Floor (Roof) for Area Z(1,5) between Axes (1-18)&(A-G) as Per Attached Sketch. | ARCH | Metal Flash | 1,5 | 6th | 44443 | 44447 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2064 | Check Fixation for Metal flash At Seventh Floor (Roof) for Area Z(1,5) between Axes (1-18)&(A-F) as Per Attached Sketch. | ARCH | Metal Flash | 1,5 | 7th | 44443 | 44447 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2065 | Check Fixation for Metal flash At Eighth Floor (Upper Roof) for Area Z(2,4) between Axes (1-18)&(F-L) as Per Attached Sketch. | ARCH | Metal Flash | 2,4 | 8th | 44443 | 44447 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2066 | Check Fixation for Metal flash At Ninth Floor (Upper Roof) for Area Z(2,4) between Axes (1-18)&(G-K) as Per Attached Sketch. | ARCH | Metal Flash | 2,4 | 9th | 44443 | 44447 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2067 | Check fixation for block work for walls for Landscape Signage as Per Attached Sketch. | ARCH | Blockwork Full height |  | EX | 44445 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2068 | Check fixation for Interlock for walkway at Landscape as Per Attached Sketch. | ARCH | Interlock |  | EX | 44445 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2069 | Check fixation for Interlock for walkway at Landscape as Per Attached Sketch. | ARCH | Interlock |  | EX | 44445 | 44468 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2070 | Check fixation for Interlock for walkway at Landscape as Per Attached Sketch. | ARCH | Interlock |  | EX | 44445 | 44468 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2071 | Check Fixation for Marble for Walk Way at Landscape accordding to the attached sketch. | ARCH | Marble (Landscape) |  | EX | 44445 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2072 | Check Fixation for Marble for Walk Way at Landscape accordding to the attached sketch. | ARCH | Marble (Landscape) |  | EX | 44445 | 44468 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2073 | Check fixation for trash bin at Landscpae as Per Attached Sketch. | ARCH | trash bin (Landscape) |  | EX | 44446 | 44447 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2074 | Check fixation for trash bin at Landscpae as Per Attached Sketch. | ARCH | trash bin (Landscape) |  | EX | 44446 | 44447 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2075 | Check fixation for Marble Cladding at Landscpae as Per Attached Sketch. | ARCH | Marble cladding (Landscape) |  | EX | 44446 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2076 | Check Fixation for Marble Signage (EXTERNAL) at Landscape accordding to the attached sketch. | ARCH | Marble Signage (Landscape) |  | EX | 44446 | 44535 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2077 | Check fixation and installation for marbel Fecade between axis(1-18)&(F-G) for area (Z2,4) From Fifth to Seventh Floor as Per Attached Sketch. | ARCH | Marble Façade | Z2,4 | ML | 44448 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2078 | Check Fixation for Metal Strip for Walk Way at Landscape accordding to the attached sketch. | ARCH | Metal Strip |  | EX | 44451 | 44464 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2079 | check Final coat of approved painting material At First floor for area Zone(3B,4,5) axes (A-L) &(1-10) as Per Attached Sketch. | ARCH | Painting Final Coat | Z3B,4,5 | 1st | 44451 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2080 | check Final coat of approved painting material At First floor for area Zone(1,2,3A) axes (A-L) &(10-18) as Per Attached Sketch. | ARCH | Painting Final Coat | Z1,2,3A | 1st | 44451 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2081 | check installation of Euphorbia-Red at landscape as per attached sketch . | ARCH | Agriculture |  | EX | 44454 | 44475 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2082 | check installation of Lantana montevidensts and Carissa Macrocapa at landscape as per attached sketch . | ARCH | Agriculture |  | EX | 44454 | 44475 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2083 | check Second Putty (Epoxy) for flooring and Skerting (Bavement) at First Basement between axis(12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z1 | B1 | 44455 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2084 | Final coat (Epoxy) for flooring and Skerting (Bavement) at First Basement between axis(12-18)&(A-F) for area (Z1) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z1 | B1 | 44455 | 44468 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2085 | check Second Putty (Epoxy) for flooring and Skerting (Bavement) at First Basement between axis(12-18)&(F-L) for area (Z2) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z2 | B1 | 44455 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2086 | Final coat (Epoxy) for flooring and Skerting (Bavement) at First Basement between axis(12-18)&(F-L) for area (Z2) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z2 | B1 | 44455 | 44468 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2087 | check Second Putty (Epoxy) for flooring and Skerting (Bavement) at First Basement between axis(6-12)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z3 | B1 | 44455 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2088 | Final coat (Epoxy) for flooring and Skerting (Bavement) at First Basement between axis(6-12)&(F-L) for area (Z3) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z3 | B1 | 44455 | 44468 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2089 | check Second Putty (Epoxy) for flooring and Skerting for Electric Rooms at First Basement for area Z(1,3,4,5) between axis(1-18)&(A-L) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,3,4,5 | B1 | 44457 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2090 | Final coat (Epoxy) for flooring and Skerting for Electric Rooms at First Basement for area Z(1,3,4,5) between axis(1-18)&(A-L) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,3,4,5 | B1 | 44457 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2091 | Check Surface Prepration for flooring between axes (6-15)&(A-G) at First basement for area (Z6) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z6 | B1 | 44460 | 44464 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2092 | check primer layer for flooring between axes (6-15)&(A-G) at First basement for area (Z6) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z6 | B1 | 44460 | 44464 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2093 | Check Fixation for Marble Set for Walk Way at Landscape accordding to the attached sketch. | ARCH | Marble Set (Landscape) |  | EX | 44460 | 44464 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2094 | Check Fixation for marble walls and ceiling at Second Floor (ROOF) for Area Z(1,2,4,5) between axes (1-18)&(A-L) accordding to the attached sketch. | ARCH | Marble Ceiling & walls | Z1,2,4,5 | 2nd | 44460 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2095 | Check fixation and installation for marbel Fecade between axis(9-10)&(F-L) for area (Z3) From Ground to Seventh Floor as Per Attached Sketch. | ARCH | Marble Façade | Z3 | ML | 44461 | 44468 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2096 | Check Fixation for Signage Metal walls for (CORE) At Second Floor for area Z(1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Metal Signage | Z1,2,3,4,5 | 2nd | 44461 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2097 | check Final coat of approved painting material At Second floor for area Zone(3B,4,5) axes (A-L) &(1-10) as Per Attached Sketch. | ARCH | Painting Final Coat | Z3B,4,5 | 2nd | 44461 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2098 | check Final coat of approved painting material At Second floor for area Zone(1,2,3A) axes (A-L) &(10-18) as Per Attached Sketch. | ARCH | Painting Final Coat | Z1,2,3A | 2nd | 44461 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2099 | Check first fix for acceccories and G.B Tiles at Second floor for area (Z1,2,3A) between axes(A-L) &(10-18) as per attached sketch. | ARCH | False ceiling (Tiles) 1st | Z1,2,3A | 2nd | 44461 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2100 | Check first fix for acceccories and G.B Tiles at Second floor for area (Z3B,4,5) between axes(A-L) &(1-10) as per attached sketch. | ARCH | False ceiling (Tiles) 1st | 4,5,3B | 2nd | 44461 | 44468 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2101 | Check final coat for ceiling "anti carbonation" painting at second basment between axis (1-18)&(A-L) At Z(6) as per attached sketch. | ARCH | Painting Final Coat "anti carbonation" | Z6 | B2 | 44462 | 44468 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2102 | Check final coat for walls and colmouns "anti carbonation" painting at second basment between axis (1-18)&(A-L) as per attached sketch. | ARCH | Painting Final Coat "anti carbonation" |  | B2 | 44462 | 44468 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2103 | Check fixation and installation for curtin wall between axis (G-L) for area (Z3B,4) From Seventh to Ninth Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z2 | ML | 44462 | 44468 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2104 | Check fixation and installation for curtin wall Glass between axis(G-L) for area (Z3B,4) From Seventh to Ninth Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z2 | ML | 44462 | 44468 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2105 | Final coat (Epoxy) for flooring and Skerting at Second Basement for area Z(1,2,4,5,6) between axis(1-18)&(A-L) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,4,5,6 | B2 | 44462 | 44468 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2106 | Final coat Painting (Acrylic) for Walls and Ceiling at Second Basement for area Z(1,2,3,4,5,6) between axis(1-18)&(A-L) as Per Attached Sketch. | ARCH | Painting Final Coat | Z1,2,3,4,5,6 | B2 | 44462 | 44468 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2107 | Check Fixation for chasis&Rock wool for HVAC ROOMS for Walls At Ground Floor for Area Z(1,2,4,5) between axis (C-K)&(2-17) as Per Attached Sketch. | ARCH | Chasis&Rock wool | Z1,2,4,5 | GF | 44465 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2108 | Check Fixation for chasis&Rock wool for HVAC ROOMS for Walls At Fourth Floor for Area Z(1,2,4,5) between axis (C-K)&(2-17) as Per Attached Sketch. | ARCH | Chasis&Rock wool | Z1,2,4,5 | 4th | 44465 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2109 | Check Fixation for chasis&Rock wool for HVAC ROOMS for Walls At Fifth Floor for Area Z(1,2,4,5) between axis (C-K)&(5-14) as Per Attached Sketch. | ARCH | Chasis&Rock wool | Z2,4,5 | 5th | 44465 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2110 | Check Fixation for chasis&Rock wool for HVAC ROOMS for Walls At Sixth Floor for Area Z(1,2,4,5) between axis (G -K)&(5-14) as Per Attached Sketch. | ARCH | Chasis&Rock wool | Z2,4 | 6th | 44465 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2111 | check fixation of interior expansion joint From Ceiling To Ceiling at First floor between axes (A-L)/(1-18) at zone(1,2,3,4,5) as per attached sketch. | ARCH | Expansion Joint Ceiling to Ceiling | 1,2,3,4,5 | 1st | 44469 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2112 | check fixation of interior expansion joint From Ceiling To Ceiling at Second floor between axes (A-L)/(1-18) at zone(1,2,3,4,5) as per attached sketch. | ARCH | Expansion Joint Ceiling to Ceiling | 1,2,3,4,5 | 2nd | 44469 | 44488 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2113 | check fixation of interior expansion joint From Ceiling To Ceiling at Third floor between axes (A-L)/(1-18) at zone(1,2,3,4,5) as per attached sketch. | ARCH | Expansion Joint Ceiling to Ceiling | 1,2,3,4,5 | 3rd | 44469 | 44488 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2114 | check fixation of interior expansion joint From Ceiling To Ceiling at Fourth floor between axes (A-L)/(1-18) at zone(1,2,3,4,5) as per attached sketch. | ARCH | Expansion Joint Ceiling to Ceiling | 1,2,3,4,5 | 4th | 44469 | 44488 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2115 | check fixation of interior expansion joint From Ceiling To Ceiling at Fifth floor between axes (A-L)/(1-18) at zone(1,2,3,4,5) as per attached sketch. | ARCH | Expansion Joint Ceiling to Ceiling | 1,2,3,4,5 | 5th | 44469 | 44488 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2116 | check fixation of interior expansion joint From Ceiling To Ceiling at Ground floor between axes (A-L)/(1-18) at zone(1,2,3,4,5) as per attached sketch. | ARCH | Expansion Joint Ceiling to Ceiling | 1,2,3,4,5 | GF | 44469 | 44488 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2117 | check Final coat of approved painting material At Sixth floor for area Zone(1,5) axes (A-G) &(1-18) as Per Attached Sketch. | ARCH | Painting Final Coat | 1,5 | 6th | 44471 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2118 | check Final coat of approved painting material At Second floor for area Zone(1,2,4,5) axes (A-L) &(1-18) as Per Attached Sketch. | ARCH | Painting Final Coat | 1,2,4,5 | 2nd | 44471 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2119 | Check fixation of marble for Flooring of (Ramp) at Landscape as Per Attached Sketch. | ARCH | Marble Flooring (Ramp) |  | EX | 44471 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2120 | Check fixation of marble for Flooring and Stairs at Landscape as Per Attached Sketch. | ARCH | Marble Flooring&Stairs |  | EX | 44471 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2121 | Check Fixation and installation for Louver steel at Roof for area Z(2,4) between axis (2-17)&(G-K) as Per Attached Sketch. | ARCH | Louver Steel | 2,4 | RF | 44471 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2122 | Check Fixation for threeshold under louver at Roof for area Z(2,4) between axis (2-17)&(G-K) as Per Attached Sketch. | ARCH | ThreeShold Under louver | 2,4 | RF | 44471 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2123 | Check Fixation for doors for Louver at Eighth floor for area Z(2,4) between axis (2-17)&(G-K) as Per Attached Sketch. | ARCH | Louver Doors | 2,4 | 8th | 44471 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2124 | Check Fixation for Metal flash cobing At Seventh Floor (Upper Roof) for Area Z(1,5) between Axes (2-17)&(A-F) as Per Attached Sketch. | ARCH | Metal Flash | 1,5 | 7th | 44471 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2125 | Check Fixation for Metal flash cobing At Ninth Floor (Upper Roof) for Area Z(2,4) between Axes (2-17)&(G-K) as Per Attached Sketch. | ARCH | Metal Flash | 2,4 | 9th | 44471 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2126 | check fixation of interior expansion joint at Sixth floor between axes (E-F)/(1-18) at zone(1,5) as per attached sketch. | ARCH | Expansion Joint | 1,5 | 6th | 44471 | 44489 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2127 | check fixation of interior expansion joint at Roof between axes (F-L)/(8-11) at zone(3) as per attached sketch. | ARCH | Expansion Joint | Z3 | RF | 44471 | 44488 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2128 | Check fixation and installation for marbel Fecade between axis(6-10)&(E-L) for area (Z3) From Ground to Roof as Per Attached Sketch. | ARCH | Marble Façade | Z3 | ML | 44471 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2129 | Check Fixation and Installation for Sandwich Panel for Upper Roof between axis (6-13)&(E-L) as Per Attached Sketch. | ARCH | Sandwich Panel | Z3 | UR | 44471 | 44489 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2130 | Check fixation and installation for curtin wall Glass between axis for area (Z4,5) From Ground to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | 4,5 | ML | 44472 | 44488 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2131 | Check fixation of Stainless Steel Signage At Facade between axis (F-G)&(9-10) at Eighth floor for area Z(3) as Per Attached Sketch. | ARCH | Stainless Steel (Signage) | Z3 | 8th | 44472 | 44500 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2132 | Check fixation of Stainless Steel Signage At Facade between axis (K-L)&(9-10) at Eighth floor for area Z(3) as Per Attached Sketch. | ARCH | Stainless Steel (Signage) | Z3 | 8th | 44472 | 44500 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2133 | check Final coat of approved painting material At Seventh floor ( Upper Roof) for area Zone(1,5) axes (A-G) &(1-18) as Per Attached Sketch. | ARCH | Painting Final Coat | 1,5 | 7th | 44472 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2134 | check Final coat of approved painting material At Eighth floor (Roof) for area Zone(2,4) axes (E-L) &(1-18) as Per Attached Sketch. | ARCH | Painting Final Coat | 2,4 | 8th | 44472 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2135 | check Final coat of approved painting material At Ninth floor (Upper Roof) for area Zone(2,4) axes (E-L) &(1-18) as Per Attached Sketch. | ARCH | Painting Final Coat | 2,4 | 9th | 44472 | 44476 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2136 | Check Water Test and Finishing for glass for curtin wall between axis (1-8)&(F-L) for area (Z4) From Second to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall Water test | 4 | ML | 44473 | 44488 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2137 | Check Water Test and Finishing for glass for curtin wall between axis (1-18)&(A-L) for area (Z1,2,4,5) From Ground to First Floor as Per Attached Sketch. | ARCH | Curtain Wall Water test | 1,2,4,5 | ML | 44473 | 44489 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2138 | Check Water Test and Finishing for glass for curtin wall between axis (7-9)&(E-L) for area (Z3B) From Ground to Ninth Floor as Per Attached Sketch. | ARCH | Curtain Wall Water test | 3B | ML | 44474 | 44489 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2139 | Check Fixation and installation for Louver steel at Ground floor for area Z(1,5) between axis (1-18)&(A_F) as Per Attached Sketch. | ARCH | Louver Steel | Z1,5 | GF | 44480 | 44489 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2140 | Check First Fix for Cladding of Canopy at Roof Floor for Area Z (3) between axis (6-13)&(E-L) as Per Attached Sketch. | ARCH | Cladding Canopy | Z3 | RF | 44480 | 44535 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2141 | Check fixation and installation for marbel Fecade between axis(6-13)&(G-K) for area (Z3) From Eighth to Roof as Per Attached Sketch. | ARCH | Marble Façade | Z3 | ML | 44482 | 44488 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2142 | Check fixation and installation for curtain wall between axis (7-12)& (E-L) for area (Z3A,3B) From Ground to Ninth Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z3A&3B | ML | 44486 | 44489 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2143 | Check fixation and installation for curtain wall Glass between axis (7-12)&(E-L) for area (Z3A,3B) From Ground to Ninth Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z3A&3B | ML | 44486 | 44489 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2144 | Check Water Test and Finishing for glass for curtain wall between axis (7-12)&(E-L) for area (Z3A,3B) From Ground to Ninth Floor as Per Attached Sketch. | ARCH | Curtain Wall Water test | Z3A&3B | ML | 44486 | 44489 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2145 | Check fixation for block work for Area Z(3A) between axis (10-12)&(K-L) from Groud to Ninth floor as Per Attached Sketch. | ARCH | Blockwork Full height | 3A | ML | 44486 | 44502 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2146 | Check Fixation for Metal flash At Second Floor (Roof) for Area Z(1,2,4,5) between Axes (1-18)&(A-L) as Per Attached Sketch. | ARCH | Metal Flash | 1,2,4,5 | 2nd | 44486 | 44489 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2147 | Check fixation for block work At Roof for Area Z(3) between axis (7-12)&(F-L) as Per Attached Sketch. | ARCH | Blockwork Full height | Z3 | RF | 44486 | 44489 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2148 | check fixation of expansion joint for walls and flooring only at Ground Floor between axes (E-K)/(9-17) at zone(1,2,3B) as per attached sketch. | ARCH | Expansion Joint | 2,3B | GF | 44487 | 44489 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2149 | Check fixation and installation for curtain wall between axis (1-7)&(A-L) for area (Z4,5) From Ground to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall | 4,5 | ML | 44488 | 44535 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2150 | Check fixation and installation for curtain wall Glass between axis (1-7)&(A-L) for area (Z4,5) From Ground to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | 4,5 | ML | 44488 | 44535 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2151 | Check Water Test and Finishing for glass for curtain wall between axis (1-7)&(A-L) for area (Z4,5) From Ground to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall Water test | 4,5 | ML | 44488 | 44535 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2152 | Check fixation and installation for curtain wall between axis (5-8)& (K-L) for area (Z4) From Ground to Sixth Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z4 | ML | 44493 | 44500 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2153 | Check fixation and installation for curtain wall Glass between axis (5-8)&(K-L) for area (Z4) From Ground to Sixth Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z4 | ML | 44493 | 44500 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2154 | Check Water Test and Finishing for glass for curtain wall between axis(5-8)&(K-L) for area (Z4) From Ground to Sixth Floor as Per Attached Sketch. | ARCH | Curtain Wall Water test | Z4 | ML | 44493 | 44500 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2155 | Check Water Test and Finishing for glass for curtain wall between axis(11-18)&(A-E) for area (Z1) From Second to Fifth Floor as Per Attached Sketch. | ARCH | Curtain Wall Water test | Z1 | ML | 44497 | 44500 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2156 | Check Water Test and Finishing for glass for curtain wall between axis (1-7)&(A-E) for area (Z5) From Second to Fifth Floor as Per Attached Sketch. | ARCH | Curtain Wall Water test | Z5 | ML | 44497 | 44500 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2157 | Check Water Test and Finishing for glass for curtain wall between axis (12-18)&(E-L) for area (Z2) From Second to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall Water test | Z2 | ML | 44497 | 44500 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2158 | Check Water Test and Finishing for glass for curtain wall between axis (10-18)&(A-L) for area (Z1,2) From Ground to Seventh Floor as Per Attached Sketch. | ARCH | Curtain Wall Water test | Z1,2 | ML | 44497 | 44500 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2159 | Check Fixation for Steel Ladder at Roof for area Z(3) between axis (8-9)&(H-K) as Per Attached Sketch. | ARCH | Steel Ladder | Z3 | RF | 44501 | 44531 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2160 | Check Fixation for Steel Ladder at Sixth floor for area Z(1,5) between axis (2-17)&(B-D) as Per Attached Sketch. | ARCH | Steel Ladder | Z1,5 | 6th | 44501 | 44531 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2161 | Check Fixation for Steel Ladder at Eighth floor for area Z(2,4) between axis (2-17)&(H-K) as Per Attached Sketch. | ARCH | Steel Ladder | Z2,4 | 8th | 44501 | 44531 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2162 | Check fixation of Stainless Steel of corridor infront of elevetors at zone(1,2,3A) between axis (A-L)/(10-18) at Fourth floor as Per Attached Sketch. | ARCH | Stainless steel (Elevators) | Z1,2,3A | 4th | 44502 | 44535 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2163 | Check fixation of Stainless Steel of corridor infront of elevetors at zone(1,2,3A) between axis (A-L)/(10-18) at Fifth floor as Per Attached Sketch. | ARCH | Stainless steel (Elevators) | Z1,2,3A | 5th | 44502 | 44535 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2164 | Check fixation of Stainless Steel of corridor infront of elevetors at zone(1,2,3A) between axis (A-L)/(10-18) at Sixth floor as Per Attached Sketch. | ARCH | Stainless steel (Elevators) | Z1,2,3A | 6th | 44503 | 44535 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2165 | Check first fix for Gypsum board ( 2 Layers ) fire Rated for walls at HVAC ROOMS At Ground Floor for Area Z(1,2,4,5) between axis (C-K)&(2-17) as Per Attached Sketch. | ARCH | Acoustic insulation | Z1,2,4,5 | GF | 44503 | 44511 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2166 | Check first fix for Gypsum board ( 2 Layers ) fire Rated for walls at HVAC ROOMS At First Floor for Area Z(1,2,4,5) between axis (C-K)&(2-17) as Per Attached Sketch. | ARCH | Acoustic insulation | Z1,2,4,5 | 1st | 44503 | 44511 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2167 | Check first fix for Gypsum board ( 2 Layers ) fire Rated for walls at HVAC ROOMS At Second Floor for Area Z(1,2,4,5) between axis (C-K)&(2-17) as Per Attached Sketch. | ARCH | Acoustic insulation | Z1,2,4,5 | 2nd | 44503 | 44511 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2168 | Check first fix for Gypsum board ( 2 Layers ) fire Rated for walls at HVAC ROOMS At Third Floor for Area Z(1,2,4,5) between axis (C-K)&(2-17) as Per Attached Sketch. | ARCH | Acoustic insulation | Z1,2,4,5 | 3rd | 44503 | 44511 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2169 | Check first fix for Gypsum board ( 2 Layers ) fire Rated for walls at HVAC ROOMS At Fourth Floor for Area Z(1,2,4,5) between axis (C-K)&(2-17) as Per Attached Sketch. | ARCH | Acoustic insulation | Z1,2,4,5 | 4th | 44503 | 44511 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2170 | Check first fix for Gypsum board ( 2 Layers ) fire Rated for walls at HVAC ROOMS At Fifth Floor for Area Z(2,4,5) between axis (C-K)&(5-14) as Per Attached Sketch. | ARCH | Acoustic insulation | Z2,4,5 | 5th | 44503 | 44511 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2171 | Check first fix for Gypsum board ( 2 Layers ) fire Rated for walls at HVAC ROOMS At Sixth Floor for Area Z(2,4) between axis (C-K)&(5-14) as Per Attached Sketch. | ARCH | Acoustic insulation | Z2,4 | 6th | 44503 | 44511 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2172 | Check Fixation and installation for Bergola at Landscape as Per Attached Sketch. | ARCH | Bergola |  | EX | 44509 | 44553 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2173 | Check cello bor monoglass acoustic spray (gray color) for walls and ceilling for generator (Z1).(Z5) between axis (A-C)&(1-18) at ground floor as per attached sketch. | ARCH | Acoustic insulation | Z1,5 | GF | 44510 | 44553 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2174 | Check Fixation for stainless steel for Elevators At Seventh floor for area zone (2,4) between Axes (G-K)&(2-17) as Per Attached Sketch. | ARCH | Stainless steel (Elevators) | Z2,4 | 7th | 44510 | 44553 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2175 | Demolation of Terrazo at Roof for Second Floor for area Z(1,2,4,5) between axis (1-18)&(E-L) as Per Attached Sketch. | ARCH | Demolation (Terrazo) | Z1,2,4,5 | 2nd | 44514 | 44535 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2176 | Demolation for Block work for Garb room at first basement for area Z (2,4) between axis (3-16) & (G-H) as Per Attached Sketch. | ARCH | Demolation (Block work) | 2,4 | B1 | 44515 | 44531 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2177 | Demolation for Ceramic walls for Garb room at first basement for area Z (2,4) between axis (3-16) & (G-H) as Per Attached Sketch. | ARCH | Demolation (Ceramic walls) | 2,4 | B1 | 44515 | 44531 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2178 | Demolation for Steel Door for Garb room at first basement for area Z (2,4) between axis (3-16) & (G-H) as Per Attached Sketch. | ARCH | Demolation (Steel door) | 2,4 | B1 | 44515 | 44531 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2179 | Check fixation and installation for marbel Fecade between axis(9-12)&(L-J) for area (Z3) From Ground to Roof as Per Attached Sketch. | ARCH | Marble Façade | Z3 | ML | 44515 | 44531 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2180 | check Second Putty (Epoxy) for flooring and Skerting (Bavement) at First Basement between axis(5-14)&(A-L) for area (Z6) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z6 | B1 | 44522 | 44553 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2181 | Final coat (Epoxy) for flooring and Skerting (Bavement) at First Basement between axis(5-14)&(A-L) for area (Z6) as Per Attached Sketch. | ARCH | Painting Epoxy Pavement | Z6 | B1 | 44522 | 44553 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2182 | check sika floor (324) layer for flooring between axes (7-13)&(A-F) at first basement floor for area (Z6) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z6 | B1 | 44528 | 44535 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2183 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (1-9)&(A-L) for area (Z3B,4,5) at fifth floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z3B,4,5 | 5th | 44537 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2184 | Check fixation for interior aluminium framed glazing panels and 12mm tempered glass at corridors between axis (1-9)&(F-L) for area (Z3B,4) at sixth floor as Per Attached Sketch. | ARCH | 12mm Tempered glass | Z3B,4 | 6th | 44537 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2185 | check Final coat of approved painting material At Sixth floor (ROOF) for Aqua panel at Zone (1,5) axes (A-G) &(1-18) as Per Attached Sketch. | ARCH | Aqua Panel (Painting) | Zone (1,5) | 6th | 44538 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2186 | check Final coat of approved painting material At eighth floor (ROOF) for Aqua panel at Zone (2,4) axes (A-G) &(1-18) as Per Attached Sketch. | ARCH | Aqua Panel (Painting) | Zone (2,4) | 8th | 44538 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2187 | ceck fixation for geotextil and gravel for landscape as per attached sketch. | ARCH | gravel & geotextil |  | EX | 44539 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2188 | Check fixation and installation for Marbel Flooring and Skerting between axis(1-18)&(E-L) for area (Z2,4) at Fifth Floor as Per Attached Sketch. | ARCH | Marble Flooring&Skerting | Z2,4 | 5th | 44543 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2189 | Check fixation and installation for Marbel Flooring and Skerting between axis(1-18)&(E-L) for area (Z2,4) at Seventh Floor as Per Attached Sketch. | ARCH | Marble Flooring&Skerting | Z2,4 | 7th | 44543 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2190 | Check fixation of Stainless Steel ( Gold ) at Ground floor for area zone(3) between axis (E-L)/(7-12) as Per Attached Sketch. | ARCH | Stainless Steel (Gold) | Z3 | GF | 44551 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2191 | Check fixation of Stainless Steel ( Gold ) at First floor for area zone(3) between axis (E-L)/(7-12) as Per Attached Sketch. | ARCH | Stainless Steel (Gold) | Z3 | 1st | 44551 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2192 | Check fixation of Stainless Steel ( Gold ) at Second floor for area zone(3) between axis (E-L)/(7-12) as Per Attached Sketch. | ARCH | Stainless Steel (Gold) | Z3 | 2nd | 44551 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2193 | Check fixation of Stainless Steel ( Gold ) at Third floor for area zone(3) between axis (E-L)/(7-12) as Per Attached Sketch. | ARCH | Stainless Steel (Gold) | Z3 | 3rd | 44551 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2194 | Check fixation of Stainless Steel ( Gold ) at Fourth floor for area zone(3) between axis (E-L)/(7-12) as Per Attached Sketch. | ARCH | Stainless Steel (Gold) | Z3 | 4th | 44551 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2195 | Check fixation of Stainless Steel ( Gold ) at Fifth floor for area zone(3) between axis (E-L)/(7-12) as Per Attached Sketch. | ARCH | Stainless Steel (Gold) | Z3 | 5th | 44551 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2196 | Check fixation of Stainless Steel ( Gold ) at Sixth floor for area zone(3) between axis (E-L)/(7-12) as Per Attached Sketch. | ARCH | Stainless Steel (Gold) | Z3 | 6th | 44551 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2197 | Check fixation of Stainless Steel ( Gold ) at Seventh floor for area zone(3) between axis (E-L)/(7-12) as Per Attached Sketch. | ARCH | Stainless Steel (Gold) | Z3 | 7th | 44551 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2198 | Check fixation of Stainless Steel ( Gold ) at Eighth floor for area zone(3) between axis (E-L)/(7-12) as Per Attached Sketch. | ARCH | Stainless Steel (Gold) | Z3 | 8th | 44551 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2199 | Check fixation and installation for curtin wall for area (Z4) From Seventh to Ninth Floor as Per Attached Sketch. | ARCH | Curtain Wall | Z4 | ML | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2200 | Check fixation and installation for curtin wall (Glass) for area (Z4) From Seventh to 10th Floor as Per Attached Sketch. | ARCH | Curtain Wall (Glass) | Z4 | ML | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2201 | Check fixation for Raised Floor At Ground Floor for Area Z(1,5) between Axis (1-18)&(A-F) as Per Attached Sketch. | ARCH | Raised Floor | Z1,5 | GF | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2202 | Check First Fix for Bulk Head And G.B tiles At First Basement for Area Z(1,2,4,5,6) Between Axis (1-18)&(A-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 1st | Z1,2,4,5,6 | B1 | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2203 | Check First Fix for Bulk Head And G.B tiles At Second Basement for Area Z(1,2,4,5,6) Between Axis (1-18)&(A-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 1st | Z1,2,4,5,6 | B2 | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2204 | Check First Fix for Bulk Head And G.B tiles At Ground Floor for Area Z(1,2,3,4,5) Between Axis (1-18)&(A-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 1st | Z1,2,3,4,5 | GF | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2205 | Check First Fix for Bulk Head And G.B tiles At First Floor for Area Z(1,2,3,4,5) Between Axis (1-18)&(A-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 1st | Z1,2,3,4,5 | 1st | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2206 | Check First Fix for Bulk Head And G.B tiles At Second Floor for Area Z(2,3,4) Between Axis (3-17)&(F-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 1st | Z2,3,4 | 2nd | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2207 | Check First Fix for Bulk Head And G.B tiles At Third Floor for Area Z(2,3,4) Between Axis (3-17)&(F-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 1st | Z2,3,4 | 3rd | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2208 | Check First Fix for Bulk Head And G.B tiles At Fourth Floor for Area Z(2,3,4) Between Axis (3-17)&(F-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 1st | Z2,3,4 | 4th | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2209 | Check First Fix for Bulk Head And G.B tiles At Fifth Floor for Area Z(2,3,4) Between Axis (3-17)&(F-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 1st | Z2,3,4 | 5th | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2210 | Check First Fix for Bulk Head And G.B tiles At Sixth Floor for Area Z(2,3,4) Between Axis (3-17)&(F-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 1st | Z2,3,4 | 6th | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2211 | Check First Fix for Bulk Head And G.B tiles At Seventh Floor for Area Z(2,3,4) Between Axis (3-17)&(F-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 1st | Z2,3,4 | 7th | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2212 | Check First Fix for Bulk Head And G.B tiles At Eighth Floor for Area Z(3) Between Axis (8-12)&(H-J) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 1st | Z3 | 8th | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2213 | Check First Fix for Bulk Head And G.B tiles At Ninth Floor for Area Z(3) Between Axis (8-12)&(H-J) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 1st | Z3 | 9th | 44552 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2214 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Ground floor between axis(1-18)&(A-L) for area (Z1,2,4,5) as Per Attached Sketch. | ARCH | Porcelain | Z1,2,4,5 | GF | 44552 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2215 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at First floor between axis(2-17)&(G-H) for area (Z2,4) as Per Attached Sketch. | ARCH | Porcelain | Z2,4 | 1st | 44552 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2216 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Second floor between axis(2-17)&(G-H) for area (Z2,4) as Per Attached Sketch. | ARCH | Porcelain | Z2,4 | 2nd | 44552 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2217 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Third floor between axis(2-17)&(G-H) for area (Z2,4) as Per Attached Sketch. | ARCH | Porcelain | Z2,4 | 3rd | 44552 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2218 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Fourth floor between axis(2-17)&(G-H) for area (Z2,4) as Per Attached Sketch. | ARCH | Porcelain | Z2,4 | 4th | 44552 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2219 | Check fixation for ceramic tiles (Porcelain) for flooring and skerting at Fifth floor between axis(2-17)&(G-H) for area (Z2,4) as Per Attached Sketch. | ARCH | Porcelain | Z2,4 | 5th | 44552 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2220 | Check Second Fix for Bulk Head And G.B tiles At Third Floor for Area Z(1,2,3A) Between Axis (10-18)&(A-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 2nd | Z1,2,3A | 3rd | 44556 | 44569 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2221 | Check Second Fix for Bulk Head And G.B tiles At Fourth Floor for Area Z(1,2,3A) Between Axis (10-18)&(A-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 2nd | Z1,2,3A | 4th | 44556 | 44569 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2222 | Check Second Fix for Bulk Head And G.B tiles At Fifth Floor for Area Z(1,2,3A) Between Axis (10-18)&(A-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 2nd | Z1,2,3A | 5th | 44556 | 44569 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2223 | Check Final Epoxy for Flooring At Second basement For Area Z (1,2,3,4,5,6) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,3,4,5,6 | B2 | 44556 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2224 | Check Final Epoxy for Flooring At First basement For Area Z (1,2,3,4,5,6) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,3,4,5,6 | B1 | 44556 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2225 | Check Final Epoxy for Flooring At Ground Floor For Area Z (1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,3,4,5 | GF | 44556 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2226 | Check Final Epoxy for Flooring At First Floor For Area Z (1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,3,4,5 | 1st | 44556 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2227 | Check Final Epoxy for Flooring At Second Floor For Area Z (1,2,3,4) between Axis (B-K)&(2-17) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,3,4 | 2nd | 44556 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2228 | Check Final Epoxy for Flooring At Third Floor For Area Z (1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,3,4,5 | 3rd | 44556 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2229 | Check Final Epoxy for Flooring At Fourth Floor For Area Z (1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,3,4,5 | 4th | 44556 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2230 | Check Final Epoxy for Flooring At Fifth Floor For Area Z (1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,3,4,5 | 5th | 44556 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2231 | Check Final Epoxy for Flooring At Sixth Floor For Area Z (1,2,3,4,5) between Axis (A-L)&(1-18) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z1,2,3,4,5 | 6th | 44556 | 44566 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2232 | Check Final Epoxy for Flooring At Seventh Floor For Area Z (2,3,4) between Axis (G-K)&(2-17) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2,3,4 | 7th | 44556 | 44566 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2233 | Check Final Epoxy for Flooring At Eighth Floor For Area Z (2,3,4) between Axis (G-K)&(2-17) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z2,3,4 | 8th | 44556 | 44566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2234 | Check Final Epoxy for Flooring At Ninth Floor For Area Z (3) between Axis (G-K)&(6-13) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z3 | 9th | 44556 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2235 | Check Final Epoxy for Flooring At Roof For Area Z (3) between Axis (G-K)&(6-13) as Per Attached Sketch. | ARCH | Painting (Epoxy) | Z3 | RF | 44556 | 44564 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2236 | Check fixation for block work (Full height) At Ground Floor for Area Z(2,3,4) between axis (2-17)&(F-L) as Per Attached Sketch. | ARCH | Blockwork Full height | Z2,3,4 | GF | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2237 | Check fixation for block work (Full height) At First Basement for Area Z(1) between axis (12-18)&(A-D) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1 | B1 | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2238 | Check fixation for block work (Full height) At Second Basement for Area Z(1,4,5,6) between axis (1-18)&(A-L) as Per Attached Sketch. | ARCH | Blockwork Full height | Z1,4,5,6 | B2 | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2239 | check fixation of steel door Leaf at Sixth floor for area (Z2)between axes (G_K) (15-17) as per attached sketch. | ARCH | Steel doors Leaf | Z2 | 6th | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2240 | Check first fix for (Bulk head) at Second Floor between axis (2-17)&(D-K) for area (Z1,2,3,4,5) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,2,3,4,5 | 2nd | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2241 | Check first fix for (Bulk head) at Third Floor between axis (2-17)&(D-K) for area (Z1,2,3,4,5) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,2,3,4,5 | 3rd | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2242 | Check first fix for (Bulk head) at Fourth Floor between axis (2-17)&(D-K) for area (Z1,2,3,4,5) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,2,3,4,5 | 4th | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2243 | Check first fix for (Bulk head) at Fifth Floor between axis (2-17)&(D-K) for area (Z1,2,3,4,5) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z1,2,3,4,5 | 5th | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2244 | Check first fix for (Bulk head) at Sixth Floor between axis (2-16)&(G-K) for area (Z2,3,4) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z2,3,4 | 6th | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2245 | Check first fix for (Bulk head) at Seventh Floor between axis (2-16)&(G-K) for area (Z2,3,4) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z2,3,4 | 7th | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2246 | Check first fix for (Bulk head) at Eighth Floor between axis (6-12)&(G-K) for area (Z3) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3 | 8th | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2247 | Check first fix for (Bulk head) at Ninth Floor between axis (7-12)&(G-K) for area (Z3) as Per Attached Sketch. | ARCH | False ceiling (Bulk head) 1st | Z3 | 9th | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2248 | check fixation of steel door Leaf at Fifth floor for area (Z1,2)between axes (B_J) (14-16) as per attached sketch. | ARCH | Steel doors Leaf | Z1,2 | 5th | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2249 | check fixation of steel door Leaf at Fourth floor for area (Z1,2)between axes (B_J) (12-16) as per attached sketch. | ARCH | Steel doors Leaf | Z1,2 | 4th | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2250 | check fixation of steel door Leaf at Third floor for area (Z2,3B)between axes (G_K) (8-16) as per attached sketch. | ARCH | Steel doors Leaf | Z2,3B | 3rd | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2251 | check Final Coat (359) for flooring between axes (5-14)&(A-F) at first basement floor for area (Z6) as Per Attached Sketch. | ARCH | Painting Polyurethane | Z6 | B1 | 44557 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2252 | Check Fixation for Metal Strip for Walk Way at Landscape accordding to the attached sketch. | ARCH | Metal Strip |  | EX | 44570 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2253 | Check fixation and Finishing for closets and shelves at Sixth floor for area (2,3,4) between axes (A-L) (10-18) as per attached sketch. | ARCH | Wooden Closest & Shelves | Z2,3,4 | 6th | 44572 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2254 | Check Second Fix for Bulk Head And G.B tiles At First Floor for Area Z(1,2,3A) Between Axis (10-18)&(A-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 2nd | Z1,2,3A | 1st | 44573 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2255 | Check Second Fix for Bulk Head And G.B tiles At Third Floor for Area Z(3B,4,5) Between Axis (1-10)&(A-L) as Per Attached Sketch. | ARCH | False ceiling (Bulk head+Tiles) 2nd | Z3B,4,5 | 3rd | 44573 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | SIA-RFI-AR-GF-2256 | Check fixation for concrete curb at landscape as per attached sketch. | ARCH | curb landscape |  | EX | 44576 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0001 | Level Of Control Points In Site | STR | Levels | Levels | FOUNDATION | 42885 | 42886 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0002 | Cordinates Of Control Points In Site | STR | Setting out | Setting out | FOUNDATION | 42885 | 42886 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0003 | Level of Excavation at Site | STR | Levels | Levels | FOUNDATION | 42886 | 42887 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0004 | Dry Load Bearing Test (2 Points) And Pits (3 Points) Before Submerge At Excavation Level (289.10) As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42886 | 42889 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0005 | submerge and compaction for excavation level (289.10) according to Geotechnical recommendation report as per attached sketch. | STR | Formation | Formation | FOUNDATION | 42890 | 42894 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0006 | level of excavation | STR | Levels | Levels | FOUNDATION | 42890 | 42894 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0007 | level of excavation befor replacement | STR | Levels | Levels | FOUNDATION | 42890 | 42891 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0008 | Load Bearing Test And Sand Cone Test (8Points) After Submerge And Compaction At Excavation Level (289.10) As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42894 | 42897 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0009 | Submerged And Compacted First Layer Of Red Soil Replacement (250mm) Thickness According To Geotechnical Recommendation Report As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42892 | 42894 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0010 | First Layer Of Replacement (289.35) As Per Sketch. | STR | Levels | Levels | FOUNDATION | 42892 | 42894 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0011 | Second Layer Of Replacement (289.60) As Per Sketch. | STR | Levels | Levels | FOUNDATION | 42892 | 42894 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0012 | Level And Location Of blainding. As Per Sketch. | STR | Levels | Levels | FOUNDATION | 42892 | 42894 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0013 | Submerged And Compacted Second Layer Of Red Soil Replacement (250mm) Thickness At Level (289.60) According To Geotechnical Recommendation Report As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42892 | 42894 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0014 | Formwork For Plain concrete For Zone (1) With T.O.C = 289.70 As Per Attached Sketch. | STR | Formwork | Formwork | FOUNDATION | 42892 | 42894 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0015 | Pouring Request For Plain concrete For Zone (1) With T.O.C = 289.70 As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42893 | 42894 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0016 | Level Of excavation befor replacement area (2 & 3) | STR | Levels | Levels | FOUNDATION | 42896 | 42898 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0017 | Dry Load Bearing Test Beside Zone (3) Before Submrge At Excavation Level (289.10) As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42896 | 42897 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0018 | Dry Load Bearing Test For Zone (4) Before Submrge At Excavation Level (289.10) As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42896 | 42897 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0019 | Load Bearing Test And Sand Cone Test (16 Points) After Submerge And Compaction For Zone(2&3) At Excavation Level (289.10) As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42898 | 42898 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0020 | Submerged And Compacted First Layer Of Red Soil Replacement (250mm) Thickness For Zone (2&3) At Level (289.35) According To Geotechnical Recommendation Report As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42898 | 42898 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0021 | Calibration For SIAC Batch Plant | STR |  |  |  | 42898 | 42901 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0022 | First Layer For Replacement For Area (2 & 3) At Level (289.35) As Per Sketch Attached. | STR | Levels | Levels | FOUNDATION | 42898 | 42898 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0023 | Second Layer For Replacement For Area (2 & 3) At Level (289.60) As Per Sketch Attached. | STR | Levels | Levels | FOUNDATION | 42898 | 42898 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0024 | Dry Load Bearing Test Beside Zone (5) Before Submerge At Excavation Level (289.10) As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42898 | 42901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0025 | Load Bearing Test For Zone (2 & 3) For 2 Points After Red Soil Replacement And Compaction At Level (289.60) As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42898 | 42901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0026 | Level And Location Of Plain concrete At Area (2 & 3) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42898 | 42901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0027 | Formwork for plain Concrete With T.O.C=289.70 For Zone (2 & 3) As Per Attached Sketch. | STR | Formwork | Formwork | FOUNDATION | 42899 | 42901 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0028 | Pouring Request for plain Concrete With T.O.C=289.70 For Zone (2 & 3) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42899 | 42901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0029 | Formwork for plain Concrete With T.O.C=289.70 For Zone (3) As Per Attached Sketch. | STR | Formwork | Formwork | FOUNDATION | 42899 | 42901 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0030 | Pouring Request for plain Concrete With T.O.C=289.70 For Zone (3) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42899 | 42901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0031 | Level And Location For Blain Concrete For Area (3) At Level (289.70) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42899 | 42901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0032 | Level Of Excavation For Area (4 & 5) At level (298.10) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42899 | 42901 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0033 | Submerged And Compacted First Layer Of Red Soil Replacement (250mm) Thickness At Level (289.35) For Zone (4 & 5) According To Geotechnical Recommendation Report As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42900 | 42904 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0034 | Submerged And Compacted Second Layer Of Red Soil Replacement (250mm) Thickness At Level (289.60) For Zone (4 & 5) According To Geotechnical Recommendation Report As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42900 | 42904 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0035 | First Layer Of Replacement (289.35) For Zone (4 & 5) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42900 | 42903 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0036 | Second Layer Of Replacement (289.60) For Zone (4 & 5) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42900 | 42904 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0037 | Formwork for plain Concrete With T.O.C=289.70 For Zone (4 & 5) As Per Attached Sketch. | STR | Formwork | Formwork | FOUNDATION | 42901 | 42904 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0038 | Pouring Request for plain Concrete With T.O.C=289.70 For Zone (4 & 5) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42901 | 42904 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0039 | Level and location for plain concrete (289.70) for area (4 & 5) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42901 | 42904 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0040 | Excavation level of area (6) at level (289.10) | STR | Levels | Levels | FOUNDATION | 42904 | 42907 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0041 | First layer of replacement of area (6) at level (289.35) | STR | Levels | Levels | FOUNDATION | 42904 | 42907 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0042 | Dry Load Bearing Test Beside Zone (6) Before Submrge At Excavation Level (289.10) As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42904 | 42907 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0043 | Submerged And Compacted First Layer Of Red Soil Replacement (250mm) Thickness For Zone (6) At Level (289.35) and sand cone test (8 points) According To Geotechnical Recommendation Report As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42904 | 42907 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0044 | Formwork for plain Concrete With T.O.C=289.70 For Zone (6) As Per Attached Sketch. | STR | Formwork | Formwork | FOUNDATION | 42904 | 42907 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0045 | Pouring Request for plain Concrete With T.O.C=289.70 For Zone (6) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42904 | 42907 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0046 | Load bearing test for Red Soil Replacement For Zone (6) At Level (289.60) and sand cone test (8 points) According To Geotechnical Recommendation Report As Per Attached Sketch. | STR | Formation | Formation | FOUNDATION | 42905 | 42907 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0047 | Formwork for plain Concrete With T.O.C=289.70 For Zone (6) As Per Attached Sketch. | STR | Formwork | Formwork | FOUNDATION | 42905 | 42907 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0048 | Pouring Request for plain Concrete With T.O.C=289.70 For Zone (6) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42905 | 42907 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0049 | Level of excavation for area (7) at level (289.10) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42905 | 42907 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0050 | Plan concrete for area (6) at level (289.70) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42905 | 42907 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0051 | Second layer of replacement for area (6) at level (289.60) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42905 | 42907 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0052 | Surface preparation for plain concrete for zone (4 & 5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42907 | 42907 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0053 | Primer coat for plain concrete for zone (4 & 5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42907 | 42907 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0054 | Excavation level of area (7) at level (289.10) | STR | Levels | Levels | FOUNDATION | 42919 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0055 | Excavation level of area (8) at level (289.10) | STR | Levels | Levels | FOUNDATION | 42919 | 42925 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0056 | First layer of replacement of area (7) at level (289.35) | STR | Levels | Levels | FOUNDATION | 42919 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0057 | First layer of replacement of area (8) at level (289.35) | STR | Levels | Levels | FOUNDATION | 42919 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0058 | Excavation level of Sump pit from axes (1&2 / A&B) (287.15) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42919 | 42925 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0059 | Excavation level of Sump pit from axes (9&10 / H&J) (287.15) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42919 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0060 | Excavation level of Elevator pit t from axes (3 & 4 / D & E) (287.15) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42919 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0061 | First layer of replacement Sump pit from axes (7&8 / H&J) (287.40) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42919 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0062 | Second layer of replacement Sump pit from axes (7&8 / H&J) (287.65) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42919 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0063 | Membrane coat for plain concrete for zone (4 & 5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42919 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0064 | Protection board for Membrane coat for plain concrete for zone (4 & 5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42919 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0065 | Pouring request for plain concrete (5cm thickness) with T.O.C (289.75) for zone (4 & 5) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42919 | 42925 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0066 | Surface preparation for plain concrete for zone (6) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42919 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0067 | Primer coat for plain concrete for zone (6) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42919 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0068 | Membrane coat for plain concrete for zone (6) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42919 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0069 | Protection board for Membrane coat for plain concrete for zone (6) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42919 | 43262 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0070 | Pouring request for plain concrete (5cm thickness) with T.O.C (289.75) for zone (6) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42919 | 43262 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0071 | Level and locaction for plain concrete for Sump pit from axes (1&2 / A&B) (288.05) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42920 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0072 | First layer of replacement Sump pit from axes (1&2 / A&B) (287.70) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42920 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0073 | Second layer of replacement Sump pit from axes (1&2 / A&B) (287.95) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42920 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0074 | First layer replacement of Elevator pit t from axes (3 & 4 / D & E) (287.40) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42920 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0075 | Second layer replacement of Elevator pit t from axes (3 & 4 / D & E) (287.65) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42920 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0076 | Level and location for plain concrete of Elevator pit t from axes (3 & 4 / D & E) (287.75) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42920 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0077 | Second layer of replacement of area (7) at level (289.60) as per sketch. | STR | Levels | Levels | FOUNDATION | 42920 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0078 | Top level for pain concrete (289.75) for area as per sketch. | STR | Levels | Levels | FOUNDATION | 42920 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0079 | Top level for pain concrete (289.75) for area as per sketch. | STR | Levels | Levels | FOUNDATION | 42920 | 42925 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0080 | Second layer of replacement of area (8) at level (289.60) as per sketch. | STR | Levels | Levels | FOUNDATION | 42924 | 42926 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0081 | Excavation level of Sump pit from axes (2&3 / L&K) (287.20) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42924 | 42926 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0082 | First layer for replacement of Sump pit from axes (2&3 / L&K) (287.45) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42924 | 42926 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0083 | Second layer for replacement of Sump pit from axes (2&3 / L&K) (287.45) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42924 | 42926 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0084 | Level and locaction for plain concrete for Sump pit from axes (2&3 / L&K) (287.80) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42924 | 42926 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0085 | Top level for plain concrete (289.75) for area as per sketch. | STR | Levels | Levels | FOUNDATION | 42924 | 42926 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0086 | Primer coat for plain concrete for zone (1) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42924 | 42926 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0087 | Membrane coat for plain concrete for zone (2) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42924 | 42926 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0088 | Protection board for Membrane coat for plain concrete for zone (2) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42924 | 42926 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0089 | First layer for membrane 4mm for Arya As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42925 | 42926 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0090 | Second layer for Bituminous Protection board 3mm for Area As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42925 | 42926 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0091 | Pouring request for plain concrete for sump pit with T.O.C (288.10) for arya (1) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42925 | 42926 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0092 | Pouring request for plain concrete for sump pit with T.O.C (287.85) for arya (3) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42925 | 42926 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0093 | Pouring request for plain concrete for elevatotr pit with T.O.C (287.80) for arya (2) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42925 | 42926 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0094 | Pouring request for plain concrete (5 cm thickness) for with T.O.C (289.75) for Area (2) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42928 | 42929 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0095 | Protection board for Membrane coat for plain concrete for zone (2) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42928 | 42929 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0096 | Pouring request for plain concrete (5 cm thickness) for with T.O.C (289.75) for Area (2) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42928 | 42929 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0097 | Protection board for Membrane coat for plain concrete for zone (1) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42928 | 42929 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0098 | Pouring request for plain concrete (5 cm thickness) for with T.O.C (289.75) for Area (1) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42928 | 42929 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0099 | Pouring request for plain concrete for with T.O.C (289.70) for Area (7 & 8) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42928 | 42929 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0100 | Formwork for plain Concrete With T.O.C = 289.70 For Zone (7 & 8) As Per Attached Sketch. | STR | Formwork | Formwork | FOUNDATION | 42928 | 42929 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0101 | Pouring request for plain concrete for elevatotr pit (TOC = 287.40) and Sump pit ( TOC = 287.8 ) for Area (4 & 5) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42928 | 42929 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0102 | Excavation level of Sump pit from axes (15&16 / L&K) (287.20) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0103 | First layer for replacement of Sump pit from axes (15&16 / L&K) (287.45) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0104 | Second layer for replacement of Sump pit from axes (15&16 / L&K) (287.70) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0105 | Second layer for replacement of Sump pit from axes (15&16 / L&K) (287.70) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0106 | Excavation level of Elevator pit t from axes (11&12 / H&J) (286.75) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0107 | First layer of replacement of Elevator pit t from axes (11&12 / H&J) (287.00) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0108 | Second layer of replacement of Elevator pit t from axes (11&12 / H&J) (287.25) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0109 | Level and locaction for plain concrete for Elevator pit t from axes (11&12 / H&J) (287.35) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0110 | Excavation level for Elevator pits t from axes (03 & 04 / H&J) (286.90) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0111 | First layer of replacement for Elevator pits t from axes (03 & 04 / H&J) (287.15) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0112 | Second layer of replacement for Elevator pits t from axes (03 & 04 / H&J) (287.40) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0113 | Level and location for plain concrete for Elevator pits t from axes (03 & 04 / H&J) (287.50) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0114 | Level and location for plain concrete (289.70) for area (7 & 8) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0115 | Level and location for plain concrete (289.70) for area (3 & 4) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0116 | Top level for plain concrete (289.75) for area (1) as per sketch. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0117 | Top level for plain concrete (289.75) for area (1) as per sketch. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0118 | Top level for plain concrete (289.75) for area (2 & 3) as per sketch. | STR | Levels | Levels | FOUNDATION | 42929 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0119 | Surface preparation for plain concrete for area (P4 & P5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42932 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0120 | Primer coat for plain concrete for area (P4 & P5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42932 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0121 | Membrane coat for plain concrete for area (P4 & P5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42932 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0122 | Protection board for Membrane coat for plain concrete for area (P4 & P5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42932 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0123 | Protection board for Membrane coat for plain concrete of sump pit for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42932 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0124 | Surface preparation and primer coat for plain concrete of elevator pit for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42932 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0125 | Membrane coat for plain concrete of elevator pit for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42932 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0126 | Protection board for Membrane coat for plain concrete of elevator pit for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42932 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0127 | Pouring request for plain concrete for sump pit with T.O.C (287.85) for area (P2) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42932 | 42935 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0128 | Surface preparation for plain concrete for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42934 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0129 | Primer coat for plain concrete for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42934 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0130 | MemPrane coat for plain concrete for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42934 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0131 | Protection board for Membrane coat for plain concrete for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42934 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0132 | Pouring request for plain concrete (5 cm thickness) for with T.O.C (289.75) for Area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42934 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0133 | Pouring request for plain concrete for elevatotr pit (TOC = 287.80 & T.O.C = 287.55 ) for Area (P1 & P2) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42934 | 42939 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0134 | Pouring request for plain concrete for elevatotr pit (T.O.C = 287.40 ) for Area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42934 | 42939 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0135 | Pouring request for plain concrete (5 cm thickness) for with T.O.C (289.75) for Area (P4 & P5) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42934 | 42939 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0136 | Pouring request for plain concrete with T.O.C (289.70) for Area (P1) & sump pit (T.O.C = 288.10) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42934 | 42939 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0137 | Membrane coat for plain concrete of elevator pit ( T.O.C = 287.80) and sump pit (TOC = 287.85) for area (P4 & P5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42934 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0138 | Protection board for Membrane coat for plain concrete of elevator pit ( T.O.C = 287.80) and sump pit (TOC = 287.85) for area (P4 & P5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42934 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0139 | Primer coat for plain concrete of elevator pit ( T.O.C = 287.55) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42934 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0140 | Excavation level of Elevator pit t from axes (15 &16 / H&J) (286.90) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42934 | 42936 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0141 | First layer of replacement for Elevator pit t from axes (15 &16 / H&J) (287.15) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42934 | 42936 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0142 | Second layer of replacement for Elevator pit t from axes (15 &16 / H&J) (287.40) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42934 | 42936 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0143 | Level and location for plain concrete for Elevator pits t from axes (15 & 16 / H&J) (287.50) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42934 | 42936 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0144 | Excavation level for Elevator pits from axes (08 & 09 / H&J) (286.75) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42934 | 42936 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0145 | First layer replacement for Elevator pits from axes (08 & 09 / H&J) (287.00) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42934 | 42936 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0146 | Second layer replacement for Elevator pits from axes (08 & 09 / H&J) (287.25) as per sketch attached. | STR | Levels | Levels | FOUNDATION | 42934 | 42936 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0147 | Level and location for plain concrete for elevator pit (287.35) for area (8 & 9 / H & J) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42934 | 42936 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0148 | Excavation level for elevator pit (287.15) for area (15 & 16 / D & E) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42934 | 42936 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0149 | First layer replacement for elevator pit (287.40) for area (15 & 16 / D & E) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42934 | 42936 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0150 | Second layer replacement for elevator pit (287.65) for area (15 & 16 / D & E) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42934 | 42936 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0151 | Level and location for plain concrete for elevator pit (287.75) for area (15 & 16 / D & E) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42934 | 42936 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0152 | Excavation level for Sump pit (287.45) for area (17 & 18 / A & B) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42934 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0153 | First layer for replacement for Sump pit (287.70) for area (17 & 18 / A & B) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42934 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0154 | Second layer for replacement for Sump pit (287.95) for area (17 & 18 / A & B) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42934 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0155 | Level And location of plain concrete for Sump pit (288.05) for area (17 & 18 / A & B) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42934 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0156 | Top level for plain concrete (289.75) for area as per sketch. | STR | Levels | Levels | FOUNDATION | 42934 | 42936 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0157 | Level And Location Of plain concrete for level(289.70). As Per Sketch. | STR | Levels | Levels | FOUNDATION | 42934 | 42935 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0158 | Membrane coat for plain concrete of elevator pit (T.O.C = 287.55) for area (P4) As Per Attached Sketch | STR | water proofing | water proofing | FOUNDATION | 42935 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0159 | Protection board for Membrane coat for plain concrete of elevator pit ( T.O.C = 287.55) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42935 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0160 | Pouring request for plain concrete (T.O.C = 289.70 ) for Area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42935 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0161 | Check top and bottom reinforcement for R.C foundation between axes (9-11) & (J-L) with (TOC = 291.15) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42935 | 42937 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0162 | Pouring request for R.C foundation at area (P3) between axes (9-11) & (J-L) with (TOC = 291.15) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42935 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0163 | Surface preparation and primer coat for plain concrete of elevator pit (TOC = 287.40) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42935 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0164 | Membrane coat for plain concrete of elevator pit (TOC = 287.40) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42935 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0165 | Protection board for Membrane coat for plain concrete of elevator pit (TOC = 287.40) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42935 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0166 | Surface preparation and primer coat for plain concrete of elevator pit (TOC = 287.80 & 287.55) for area (P1& P2) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42935 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0167 | Membrane coat for plain concrete of elevator pit (TOC = 287.80 & 287.55) for area (P1& P2) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42935 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0168 | Check formwork and level for R.C foundation between axes (9-11) & (J-L) with (TOC = 291.15) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42935 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0169 | Protection board for Membrane coat for plain concrete of elevator pit (TOC = 290.65, 290.50) for area (P3 & P4) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42936 | 42939 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0170 | Pouring request for plain concrete (5cm thickness) of elevator pit (TOC = 290.65, 290.50) for area (P3 & P4) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42936 | 42939 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0171 | Surface preparation and primer coat for plain concrete of elevator pit and sump pit (TOC = 290.90, 290.65 & 290.95) for area (P1& P2) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42936 | 42939 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0172 | Membrane coat for plain concrete of elevator pit and sump pit (TOC = 290.65 & 290.95) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42936 | 42941 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0173 | Protection board for Membrane coat for plain concrete of elevator pit (TOC = 287.40) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42936 | 42939 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0174 | Offset 50cm for columns As Per Attached Sketch. | STR | Levels | Levels | B2 | 42938 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0175 | Surface preparation and primer coat for plain concrete of Sump pit (TOC = 288.10) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42938 | 42939 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0176 | Membrane coat for plain concrete of Sump pit (TOC = 288.10) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42939 | 42940 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0177 | Protection board for Membrane coat for plain concrete of Sump pit and Elevator pit (TOC = 288.10, TOC = 287.40) for area (P3 & P5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42939 | 42940 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0178 | Pouring request for plain concrete (5cm thikness) of Sump pit and Elevator pit (TOC = 288.10, TOC = 287.40) for area (P3 & P5) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42939 | 42940 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0179 | Check bottom reinforcement for R.C RAFT foundation between axes (2-6) & (A-C) with (TOC = 290.75) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42940 | 42954 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0180 | Check top reinforcement for R.C RAFT foundation between axes (2-6) & (A-C) with (TOC = 290.75) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42940 | 42954 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0181 | Pouring request for R.C RAFT foundation at area (P5) between axes (2-6) & (A-C) with (TOC = 290.75) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42940 | 42954 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0182 | Surface preparation and primer coat for plain concrete (TOC = 289.70) for area (P1 & P2) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42940 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0183 | Membrane coat for plain concrete (TOC = 289.70) for area (P1 & P2) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42940 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0184 | Protection board for Membrane coat for plain concrete (TOC = 289.70) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42940 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0185 | Surface preparation and primer coat for plain concrete (TOC = 289.70) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42940 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0186 | Membrane coat for plain concrete (TOC = 289.70) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42940 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0187 | Protection board for Membrane coat for plain concrete (TOC = 289.70) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42940 | 42943 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0188 | Pouring request for plain concrete (5cm thikness) (TOC = 289.75) for area (P1 & P3) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42940 | 42954 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0189 | Check location columns of RC Raft foundation and level of Raft (TOC = 290.75) between axes (3-6 / A-B) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42942 | 42947 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0190 | Check Offset 50cm for columns between axes (3-6 / A-B) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42942 | 42947 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0191 | Protection board for Membrane coat for plain concrete (TOC = 289.70) for area (P1&P2) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 42945 | 42949 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0192 | Pouring request for plain concrete (5cm thikness) (TOC = 289.75) for area (P1&P2) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42945 | 42954 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0193 | Check bottom reinforcement for R.C RAFT foundation between axes (4-6) & (B-F) with (TOC = 290.75) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42945 | 42961 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0194 | Offset 50cm for columns and kikers at axies (C, D & E / 5 - 6) for area (P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42946 | 42961 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0195 | Check formwork and level for R.C foundation between axes(C, D & E / 5 - 6) for area (P5) (TOC = 290.75) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42946 | 42955 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0196 | Check Top reinforcement for R.C RAFT foundation between axes (4-6) & (B-F) with (TOC = 290.75) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42948 | 42961 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0197 | Pouring Request for R.C RAFT foundation between axes (4-6) & (B-F) with (TOC = 290.75) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42948 | 42961 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0198 | Check bottom reinforcement for R.C RAFT foundation between axes (6-10) & (J-L) with (TOC = 291.15) for area (P3) As Per Attached Sketch.tch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42948 | 42961 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0199 | Check Top reinforcement for R.C RAFT foundation between axes (6-10) & (J-L) with (TOC = 291.15) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42948 | 42961 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0200 | Check RFT for columns from level (290.75 to 295.20) between axis (3-5) & (A) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42948 | 42954 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0201 | Check formwork for columns from level (290.75 to 295.20) between axis (3-5) & (A) for area (P5) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42948 | 42954 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0202 | Pouring request for columns from level (290.75 to 295.20) between axis (3-5) & (A) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42948 | 42954 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0203 | Pouring request for R.C RAFT foundation between axes (6-10) & (J-L) with (TOC = 291.15) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42949 | 42961 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0204 | Check bottom reinforcement for R.C RAFT foundation between axes (10-13) &(J-L) with (TOC = 291.15) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42949 | 42954 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0205 | Check top reinforcement for R.C RAFT foundation between axes (10-13) &(J-L) with (TOC = 291.15) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42949 | 42954 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0206 | Pouring request for R.C RAFT foundation between axes (10-13) &(J-L) with (TOC = 291.15) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42949 | 42961 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0207 | Check formwork and level for R.C foundation between axes (9-11) & (J-L) with (TOC = 291.15) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42950 | 42955 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0208 | Check Offset 50cm for columns between axes (7-9/ L-K) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42950 | 42954 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0209 | Offset 30cm for columns As Per Attached Sketch. | STR | Setting out | Setting out |  | 42950 | 42954 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0210 | Check formwork and level for R.C foundation between axes (11,12 & 13) & (L-K) with (TOC = 291.15) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42953 | 42955 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0211 | Check Offset 50cm for columns between axes (11,12 & 13) & (L-K) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42953 | 42955 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0212 | Check RFT for columns from level (290.75 to 295.20) between axis (3-5) & (A-E) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42955 | 42961 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0213 | Check formwork for columns from level (290.75 to 295.20) between axis (3-5) & (A-E) for area (P5) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42955 | 42961 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0214 | Pouring request for columns from level (290.75 to 295.20) between axis (3-5) & (A-E) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42955 | 42961 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0215 | Check formwork and level for R.C foundation between axes (7-12) & (F-J) with (TOC = 291.15) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42957 | 42963 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0216 | Walls of sump pit between axis (H-J / 9-10) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42957 | 42963 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0217 | Check RFT for column from level (290.75 to 295.20) between axis (5-6) & (E-F) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42957 | 42963 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0218 | Check formwork for column from level (290.75 to 295.20) between axis (5-6) & (E-F) for area (P5) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42957 | 42963 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0219 | Pouring request for column from level (290.75 to 295.20) between axis (5-6) & (E-F) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42957 | 42963 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0220 | Check bottom reinforcement for R.C RAFT foundation between axes (6-13) &(F-H) with (TOC = 291.15) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42957 | 42963 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0221 | Check Top reinforcement for R.C RAFT foundation between axes (6-13) &(F-H) with (TOC = 291.15) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42957 | 42963 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0222 | Pouring request for R.C RAFT foundation between axes (6-13) &(F-H) with (TOC = 291.15) for area (P3) As Per Attached Sketch | STR | Concreting | Concreting | FOUNDATION | 42957 | 42963 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0223 | Check RFT for retaining wall from level (290.75 to 295.20) between axis (2-6) & (A) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42957 | 42987 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0224 | Check bottom reinforcement for R.C RAFT foundation between axes (2-6) &(J-L) with (TOC = 291.00) for area (P4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42957 | 42996 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0225 | Check Offset 50cm for columns between axes (7-12) & (F-G) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42959 | 42963 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0226 | Check Offset 50cm of kickers for columns between axes (7-12) & (F-G) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42959 | 42963 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0227 | Check formwork and level for R.C foundation between axes (17-18) & (F-L) with (TOC = 291.00) As Per Attached Sketch. | STR | Setting out | Setting out | FOUNDATION | 42962 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0228 | Check formwork and level for R.C foundation between axes (3-7) & (K-L) with (TOC = 291.00) As Per Attached Sketch. | STR | Setting out | Setting out | FOUNDATION | 42962 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0229 | Check bottom reinforcement for R.C RAFT foundation between axes (16-18) &(F-L) with (TOC = 291.00) for area (P2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42963 | 42968 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0230 | Check TOP reinforcement for R.C RAFT foundation between axes (16-18) &(F-L) with (TOC = 291.00) for area (P2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42963 | 42968 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0231 | Pouring request for R.C RAFT foundation between axes (16-18) &(F-L) with (TOC = 291.00) for area (P2) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42963 | 42968 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0232 | Check bottom reinforcement for R.C RAFT foundation between axes (13-17) &(J-L) with (TOC = 291.00) for area (P2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42963 | 42968 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0233 | Check TOP reinforcement for R.C RAFT foundation between axes (13-17) &(J-L) with (TOC = 291.00) for area (P2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42963 | 42968 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0234 | Pouring request for R.C RAFT foundation between axes (13-17) &(J-L) with (TOC = 291.00) for area (P2) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42963 | 42968 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0235 | Check formwork and level for R.C foundation between axes (13-16) & (K-L) with (TOC = 291.00) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42963 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0236 | Offset 50cm for columns and kikers at axies (F - L / 17 - 18) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42963 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0237 | Offset 50cm for columns and kikers at axies (F - L / 17 - 18) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42963 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0238 | Check TOP reinforcement for R.C RAFT foundation between axes (3-6) &(J-L) with (TOC = 291.00) for area (P4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42966 | 42987 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0239 | Pouring Request for R.C RAFT foundation between axes (3-6) &(J-L) with (TOC = 291.00) for area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42966 | 42987 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0240 | Check Bottom reinforcement for R.C RAFT foundation between axes (3-6) &(J-L) with (TOC = 291.00) for area (P4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42966 | 42971 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0241 | Check Top reinforcement for R.C RAFT foundation between axes (13-17) &(F-K) with (TOC = 291.00) for area (P2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42966 | 42971 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0242 | Pouring request for R.C RAFT foundation between axes (13-17) &(F-K) with (TOC = 291.00) for area (P2) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42966 | 42971 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0243 | Check formwork for retaining wall from level (290.75 to 295.20) between axis (2-6) & (A) for area (P5) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42966 | 42971 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0244 | Pouring request for retaining wall from level (290.75 to 295.20) between axis (2-6) & (A) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42966 | 42971 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0245 | Check bottom reinforcement for R.C RAFT foundation between axes (13-18) & (A-F) with (TOC = 290.75) for area (P1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42966 | 42987 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0246 | Check bottom reinforcement for R.C RAFT foundation between axes (6-13) & (G-K) with (TOC = 291.15) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42966 | 42987 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0247 | Check RFT for columns from level (291.15 to 295.20) between axis (9-11) & (K-L) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42966 | 42971 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0248 | Check formwork and level for R.C foundation between axes (13-16) & (F-J) with (TOC = 291.00) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42967 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0249 | Check formwork and level for R.C foundation between axes (17-18) & (C, D & F) with (TOC = 290.75) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42967 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0250 | Check formwork for slab and bottom level of slab between axis (3, 4 & 5 / A & B) As Per Attached Sketch. | STR | Levels | Levels | B2 | 42967 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0251 | Top level of slab between axis (3, 4 & 5 / A & B) As Per Attached Sketch. | STR | Levels | Levels | B2 | 42967 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0252 | Check bottom and top reinforcement for R.C sump pit between axes (9-10) & (H-J) with (TOC = 289.20) for area (P3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | FOUNDATION | 42968 | 42987 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0253 | Pouring request for R.C sump pit between axes (9-10) & (H-J) with (TOC = 289.20) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42968 | 42987 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0254 | Check formwork for columns from level (291.15 to 295.20) between axis (9-11) & (K-L) for area (P3) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42968 | 42971 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0255 | Pouring request for columns from level (291.15 to 295.20) between axis (9-11) & (K-L) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42968 | 42971 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0256 | Check RFT for retaining wall from level (291.15 to 295.20) between axis (9-11) & (L) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42968 | 42971 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0257 | Check bottom and top reinforcement for R.C slab between axes (2-6) & (A-C) with (TOC = 295.60) for area (P5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 42968 | 42971 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0258 | Pouring request for R.C slab between axes (2-6) & (A-C) with (TOC = 295.60) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42968 | 42971 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0259 | Offset 50cm for columns and kikers at axies (K - L / 13 - 16) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42968 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0260 | Offset 50cm for columns and kikers at axies (F - J / 13 - 16) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42968 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0261 | Offset 50cm for columns and kikers at axies (K - L / 4 - 6) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42968 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0262 | Check formwork and level for R.C foundation between axes (13-17) & (A-C) with (TOC = 290.75) As Per Attached Sketch. | STR | Setting out | Setting out | FOUNDATION | 42970 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0263 | Check Offset 50cm for columns at slab B1 level (+295.60) between axes (3-5) & (A-B) As Per Attached Sketch. | STR | Setting out | Setting out | B1 | 42970 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0264 | Check Top reinforcement for R.C RAFT foundation between axes (13-18) & (A-F) with (TOC = 290.75) for area (P1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0265 | Pouring request for R.C RAFT foundation between axes (13-18) & (A-F) with (TOC = 290.75) for area (P1) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0266 | Check top reinforcement for R.C elevator pit between axes (7-9) & (H-J) with (TOC = 288.80) for area (P3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | FOUNDATION | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0267 | Pouring request for R.C elevator pit between axes (7-9) & (H-J) with (TOC = 288.80) for area (P3) As Per Attached Sketch | STR | Concreting | Concreting | FOUNDATION | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0268 | Check RFT for retaining wall from level (290.75 to 295.20) between axis (A-E)/(6) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0269 | Check formwork for retaining wall from level (290.75 to 295.20) between axis (A-E)/(6) for area (P5) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42973 | 42977 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0270 | Pouring request for retaining wall from level (290.75 to 295.20) between axis (A-E)/(6) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0271 | Check bottom reinforcement for R.C RAFT foundation between axes (1-6) & (A-F) with (TOC = 290.75) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0272 | Check top reinforcement for R.C RAFT foundation between axes (1-6) & (A-F) with (TOC = 290.75) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0273 | Pouring request for R.C RAFT foundation between axes (1-6) & (A-F) with (TOC = 290.75) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0274 | Check top reinforcement for R.C RAFT between axes (6-10) & (G-K) with (TOC = 291.15) for area (P3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | FOUNDATION | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0275 | Pouring request for R.C RAFT between axes (6-10) & (G-K) with (TOC = 291.15) for area (P3) As Per Attached Sketch | STR | Concreting | Concreting | FOUNDATION | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0276 | Check formwork and level for R.C foundation between axes (1-5) & (A-C) with (TOC = 290.75) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0277 | Offset 50cm for columns and kikers at axies (A -C / 13 -17) for area (P4) As Per Attached Sketch. | STR | Levels | Levels |  | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0278 | Check formwork and level for R.C foundation between axes (10-13) & (H-J) with (TOC = 291.15) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0279 | Check formwork and level for R.C foundation between axes (6-9) & (H-J) with (TOC = 291.15) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42973 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0280 | Check formwork and level for R.C foundation between axes (13-16) & (D-E) with (TOC = 290.75) - PART (Z1) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42975 | 43003 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0281 | Offset 50cm for columns and kikers at axies (A - F / 1 - 5) for area (P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42975 | 43003 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0282 | Check formwork for retaining wall from level (291.15 to 295.20) between axis (9-11) & (L) for area (P3) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42976 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0283 | Pouring request for retaining wall from level (291.15 to 295.20) between axis (9-11) & (L) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42976 | 42987 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0284 | Check RFT for columns from level (291.15 to 295.20) between axis (8-10) & (K-L) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42976 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0285 | Check Top reinforcement for R.C RAFT foundation between axes (9-13) &(G-K) with (TOC = 291.15) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42976 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0286 | Pouring request for R.C RAFT foundation between axes (9-13) &(G-K) with (TOC = 291.15) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42976 | 42987 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0287 | Check Bottom reinforcement for R.C RAFT foundation between axes (1-6) &(F-L) with (TOC = 291.00) for area (P4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42976 | 42996 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0288 | Check TOP reinforcement for R.C RAFT foundation between axes (13-17) &(C-F) with (TOC = 290.75) for area (P1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42976 | 42977 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0289 | Pouring request for R.C RAFT foundation between axes (13-17) &(C-F) with (TOC = 290.75) for area (P1) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42976 | 42987 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0290 | Check bottom reinforcement for R.C sump pit between axes (16-18) & (A-C) with (TOC = 289.10) for area (P1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | FOUNDATION | 42976 | 42996 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0291 | Check RFT for retaining wall from level (291.15 to 295.20) between axis (7-11)/(F) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42987 | 42991 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0292 | Check formwork for retaining wall from level (291.15 to 295.20) between axis (7-11)/(F) for area (P3) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42987 | 42991 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0293 | Pouring request for retaining wall from level (291.15 to 295.20) between axis (7-11)/(F) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42987 | 42991 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0294 | Check top reinforcement for R.C RAFT foundation between axes (2-6) &(F-k) with (TOC = 291.00) for area (P4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42987 | 42991 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0295 | Pouring request for R.C RAFT foundation between axes (2-6) &(F-k) with (TOC = 291.00) for area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42987 | 42991 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0296 | Check formwork and level for R.C foundation between axes (3-6) & (F-J) with (TOC = 291.00) - PART (Z4) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42991 | 43003 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0297 | Check formwork and level for R.C foundation between axes (3-6) & (F-J) with (TOC = 291.00) - PART (Z4) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42991 | 43003 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0298 | Check formwork and level for tank & pump room and raft R.C foundation between axes (1-3) & (F-L) with (TOC = 291.70 & 290.70 & 291.00) - PART (Z4) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42991 | 43003 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0299 | Offset 50cm for columns and kikers at axies (F - J / 3 - 6) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42991 | 43003 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0300 | Walls of sump pit between axis (A-B / 17-18) As Per Attached Sketch. | STR | Setting out | Setting out | FOUNDATION | 42991 | 43003 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0301 | Check RFT for core wall from level (291.15 to 295.20) between axis (H-J)/(6-8) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42992 | 42996 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0302 | Check formwork for core wall from level (291.15 to 295.20) between axis (H-J)/(6-8) for area (P3) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42992 | 42996 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0303 | Pouring request for core wall from level (291.15 to 295.20) between axis (H-J)/(6-8) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42992 | 42996 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0304 | Check bottom reinforcement for R.C elevator pit between axes (3-4) & (D-E) AT area (P5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | FOUNDATION | 42992 | 42996 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0305 | Check RFT for columns from level (291.15 to 295.20) between axis (6-8) & (G-K) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42992 | 42996 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0306 | Check top reinforcement for R.C sump pit between axes (16-18) & (A-C) with (TOC = 289.10) for area (P1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | FOUNDATION | 42992 | 42996 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0307 | Pouring request for R.C sump pit between axes (16-18) & (A-C) with (TOC = 289.10) for area (P1) As Per Attached Sketch | STR | Concreting | Concreting | FOUNDATION | 42992 | 42996 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0308 | Check RFT for retaining wall from level (291.15 to 295.20) between axis (5-9)/(L) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42992 | 42996 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0309 | Check formwork for retaining wall from level (291.15 to 295.20) between axis (5-9)/(L) for area (P3) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42992 | 42996 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0310 | Pouring request for retaining wall from level (291.15 to 295.20) between axis (5-9)/(L) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42992 | 42996 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0311 | Check top reinforcement for R.C RAFT foundation between axes (1-4) &(F-L) with (TOC = 291.00) for area (P4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42992 | 42996 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0312 | Pouring request for R.C RAFT foundation between axes (1-4) &(F-L) with (TOC = 291.00) for area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42992 | 42996 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0313 | Check formwork and level for R.C foundation between axes (3-4) & (C-D) with (TOC = 290.75) - PART (Z5) As Per Attached Sketch. | STR | Levels | Levels | FOUNDATION | 42996 | 43003 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0314 | Offset 50cm for columns and kikers at axies (A - B/ 17 - 18) for area (P1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 42996 | 43003 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0315 | Check bottom reinforcement for R.C RAFT foundation between axes (2-5) &(B-E) with (TOC = 289.75) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42996 | 42998 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0316 | Check top reinforcement for R.C RAFT foundation between axes (2-5) &(B-E) with (TOC = 289.75) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 42996 | 42998 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0317 | Pouring request for R.C RAFT foundation between axes (2-5) &(B-E) with (TOC = 289.75) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 42996 | 42998 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0318 | Check bottom reinforcement for R.C elevator pit between axes (2-5) & (F-K) at area (P4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | FOUNDATION | 42996 | 42998 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0319 | Check top reinforcement for R.C elevator pit between axes (2-5) & (F-K) at area (P4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | FOUNDATION | 42996 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0320 | Check bottom reinforcement for R.C elevator pit between axes (14-17) & (C-F) at area (P1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | FOUNDATION | 42996 | 43003 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0321 | Check top reinforcement for R.C elevator pit between axes (14-17) & (C-F) at area (P1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | FOUNDATION | 42996 | 43003 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0322 | Pouring request for R.C elevator pit between axes (14-17) & (C-F) at area (P1) As Per Attached Sketch | STR | Concreting | Concreting | FOUNDATION | 42996 | 43003 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0323 | Check RFT for columns from level (289.75 to 295.20) between axis (2-4) & (A-E) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42996 | 42998 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0324 | Check formwork for columns from level (289.75 to 295.20) between axis (2-4) & (A-E) for area (P5) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42996 | 42998 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0325 | Pouring request for columns from level (289.75 to 295.20) between axis (2-4) & (A-E) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42996 | 42998 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0326 | Check RFT for retaining wall from level (291.00 to 295.20) between axis (4-7)/(L) for area (P4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42996 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0327 | Check formwork for retaining wall from level (291.00 to 295.20) between axis (4-7)/(L) for area (P4) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42996 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0328 | Pouring request for retaining wall from level (291.00 to 295.20) between axis (4-7)/(L) for area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42996 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0329 | Check RFT for retaining wall from level (291.15 to 295.20) between axis (6-8)/(D-F) for area (P3 & P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42996 | 42998 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0330 | Check formwork for retaining wall from level (291.15 to 295.20) between axis (6-8)/(D-F) for area (P3 & P5) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42996 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0331 | Pouring request for retaining wall from level (291.15 to 295.20) between axis (6-8)/(D-F) for area (P3 & P5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42996 | 43004 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0332 | Check RFT for columns from level (289.75 to 295.20) between axis (14-17) for area (P1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42996 | 42998 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0333 | Check formwork for columns from level (289.75 to 295.20) between axis (14-17) for area (P1) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42996 | 42998 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0334 | Pouring reqest for columns from level (289.75 to 295.20) between axis (14-17) for area (P1) As Per Attached | STR | Concreting | Concreting | B2 | 42996 | 42998 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0335 | Check RFT for retaining wall from level (289.75 to 295.20) between axis (13-18)/(A) for area (P1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42996 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0336 | Check RFT for columns from level (295.60 to 300.10) between axis (3-6)/(A-B) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0337 | Check formwork for columns from level (295.60 to 300.10) between axis (3-6)/(A-B) for area (P5) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0338 | Pouring request for columns from level (295.60 to 300.10) between axis (3-6)/(A-B) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0339 | Check RFT for retaining wall from level (295.60 to 300.10) between axis (2-6) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0340 | Pouring request for R.C elevator pit between axes (2-5) & (F-K) at area (P4) As Per Attached Sketch | STR | Concreting | Concreting | FOUNDATION | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0341 | Check bottom reinforcement for R.C elevator pit between axes (14-17) & (F-K) at area (P2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | FOUNDATION | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0342 | Check RFT for R.C elevator pit walls from level (291.15 - 295.60) between axes (7-9) & (G-K) at area (P3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 42997 | 43004 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0343 | Check formwork for R.C elevator pit walls from level (291.15 - 295.60) between axes (7-9) & (G-K) at area (P3) As Per Attached Sketch | STR | Formwork | Formwork | B2 | 42997 | 43004 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0344 | Pouring request for R.C elevator pit walls from level (291.15 - 295.60) between axes (7-9) & (G-K) at area (P3) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 42997 | 43004 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0345 | Check RFT for columns from level (289.75 to 295.20) between axis (14-17)/(A) for area (P1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0346 | Check formwork for columns from level (289.75 to 295.20) between axis (14-17)/(A) for area (P1) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0347 | pouring reqest for columns from level (289.75 to 295.20) between axis (14-17)/(A) for area (P1) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0348 | Check RFT for retaining wall from level (289.75 to 295.20) between axis (1- 3)/(A) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0349 | Check RFT for retaining wall from level (291.00 to 295.20) between axis (12- 15)/(L) for area (P2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0350 | Check RFT for columns from level (291.00 to 295.20) between axis (5-6)/(E-G) for area (P4&P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0351 | Check RFT for columns from level (291.15 to 295.20) between axis (7-13)/(F-K) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0352 | Check formwork for columns from level (291.15 to 295.20) between axis (7-13)/(F-K) for area (P3) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0353 | Pouring request for columns from level (291.15 to 295.20) between axis (7-13)/(F-K) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42997 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0354 | Check top reinforcement for R.C elevator pit between axes (14-17) & (F-K) at area (P2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | FOUNDATION | 42999 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0355 | Pouring request for R.C elevator pit between axes (14-17) & (F-K) at area (P2) As Per Attached Sketch | STR | Concreting | Concreting | FOUNDATION | 42999 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0356 | Check formwork for columns from level (291.15 to 295.20) between axis (9-13)/(G-K) for area (P3) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42999 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0357 | Pouring request for columns from level (291.15 to 295.20) between axis (9-13)/(G-K) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42999 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0358 | Check RFT for columns from level (291.00 to 295.20) between axis (13-14)/(F-J) for area (P2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42999 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0359 | Check RFT for columns from level (291.00 to 295.20) between axis (5-6)/(H-L) for area (P4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42999 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0360 | Check RFT for columns from level (289.75 to 295.20) between axis (13-18)/(A-E) for area (P1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42999 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0361 | Check RFT for retaining wall from level (289.75 to 295.20) between axis (1-2)/(A-D) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42999 | 43003 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0362 | Check RFT for core wall from level (291.15 to 295.20) between axis (11-13)/(H-J) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 42999 | 43003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0363 | Check formwork for retaining wall from level (291.00 to 295.20) between axis (12- 15)/(L) for area (P2) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 42999 | 43017 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0364 | Pouring request for retaining wall from level (291.00 to 295.20) between axis (12- 15)/(L) for area (P2) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 42999 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0365 | Surface preparation and repair for retaining wall from level (288.75 to 292.75) between axis (7- 12)/(L) for area (P3) As Per Attached Sketch. | STR | wall finish | wall finish | R.W | 42999 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0366 | Primer coat for retaining wall from level (288.75 to 292.75) between axis (7- 12)/(L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 42999 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0367 | Membrane coat for retaining wall from level (288.75 to 292.75) between axis (7- 12)/(L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 42999 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0368 | Surface preparation and repair for retaining wall from level (288.75 to 292.75) between axis (7- 12)/(F) for area (P3) As Per Attached Sketch. | STR | wall finish | wall finish | R.W | 42999 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0369 | Surface preparation and repair for retaining wall from level (288.75 to 292.75) between axis (7- 12)/(F) for area (P3) As Per Attached Sketch. | STR | wall finish | wall finish | R.W | 42999 | 43004 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0370 | Membrane coat for retaining wall from level (288.75 to 292.75) between axis (7- 12)/(F) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 42999 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0371 | Check formwork and drops and level for slab between axes (5-12) & (C-L) with (TOC = 295.60) - PART (Z3 & Z4 & Z5) As Per Attached Sketch. | STR | Setting out | Setting out | B2 | 43001 | 43022 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0372 | First layer of bakfilling for retaining wall from level (289.75 to 290.25) between axis (1- 6)/(A) for area (P5) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43017 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0373 | Check RFT for retaining wall from level (291.15 to 295.20) between axis (11-13)/(D-F) for area (P1&P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0374 | Check RFT for retaining wall from level (291.15 to 295.20) between axis (11-13)/(E-F) for area (P1&P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0375 | Pouring request for retaining wall from level (291.15 to 295.20) between axis (11-13)/(E-F) for area (P1&P3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0376 | Check RFT for retaining wall from level (291.00 to 295.20) between axis (16-18)/(J-L) for area (P2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0377 | Check formwork for columns from level (289.75 to 295.20) between axis (13-15)/(B-E) for area (P1) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43004 | 43025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0378 | Pouring request for columns from level (289.75 to 295.20) between axis (13-15)/(B-E) for area (P1) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43004 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0379 | Pouring request for columns from level (289.75 to 295.20) between axis (13-15)/(B-E) for area (P1) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43004 | 43025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0380 | Pouring request for columns from level (291.00 to 295.20) between axis (13-14)/(F-J) for area (P2) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43004 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0381 | Check RFT for columns from level (291.15 to 295.20) between axis (7-12)/(F-L) for area (P3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0382 | Check formwork for columns from level (291.15 to 295.20) between axis (7- 9)/(F-L) for area (P3) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43004 | 43009 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0383 | Pouring request for columns from level (291.15 to 295.20) between axis (7- 9)/(F-L) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0384 | Check bottom reinforcement for R.C slab between axes (4-9) & (E-L) with (TOC = 295.60) for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0385 | Check top reinforcement for R.C slab between axes (4-9) & (E-L) with (TOC = 295.60) for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0386 | Pouring request for R.C slab between axes (4-9) & (E-L) with (TOC = 295.60) for area (Z4) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0387 | Check bottom reinforcement for R.C slab between axes (4-7) & (A-F) with (TOC = 295.60) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0388 | Check top reinforcement for R.C slab between axes (4-7) & (A-F) with (TOC = 295.60) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43004 | 43009 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0389 | Pouring request for R.C slab between axes (4-7) & (A-F) with (TOC = 295.60) for area (Z6) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43004 | 43009 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0390 | Check formwork for columns from level (291.00 to 295.20) between axis (5-6)/(H-L) for area (P4) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0391 | Pouring request for columns from level (291.00 to 295.20) between axis (5-6)/(H-L) for area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0392 | Check RFT for columns from level (289.75 to 295.20) between axis (1-3)/(C-F) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0393 | Check formwork for columns from level (289.75 to 295.20) between axis (1-3)/(C-F) for area (P5) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0394 | Pouring request for columns from level (289.75 to 295.20) between axis (1-3)/(C-F) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0395 | Check RFT for core walls from level (289.75 to 295.20) between axis (3-4)/(B-C) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43004 | 43009 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0396 | Check formwork for retaining wall from level (289.75 to 295.20) between axis (1 - 3)/(A) for area (P5) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43004 | 43009 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0397 | Pouring reqeust for retaining wall from level (289.75 to 295.20) between axis (1 - 3)/(A) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0398 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (2-6) for area (Z6) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43004 | 43025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0399 | Pouring request for retaining wall from level (295.60 to 300.10) between axis (2-6) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43004 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0400 | Check formwork and level for R.C foundation between axes (15-16) & (D) with (TOC = 290.75) - PART (Z1) As Per Attached Sketch. | STR | Setting out | Setting out | FOUNDATION | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0401 | Check formwork and level for R.C foundation between axes (15-16) & (G-J) with (TOC = 291.00) - PART (P2) As Per Attached Sketch. | STR | Setting out | Setting out | FOUNDATION | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0402 | Check formwork and level for R.C foundation between axes (3-4) & (G-J) with (TOC = 291.00) - PART (P4) As Per Attached Sketch. | STR | Setting out | Setting out | FOUNDATION | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0403 | Check formwork and level for R.C foundation between axes (3-4) & (C-D) with (TOC = 290.75) - PART (P5) As Per Attached Sketch. | STR | Setting out | Setting out | FOUNDATION | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0404 | Offset 50cm for columns &walls for tank As Per Attached Sketch. | STR | Setting out | Setting out |  | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0405 | Offset 50cm for columns &walls As Per Attached Sketch. | STR | Setting out | Setting out |  | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0406 | Offset 50cm for columns &walls As Per Attached Sketch. | STR | Setting out | Setting out |  | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0407 | Offset 50cm for columns &walls As Per Attached Sketch. | STR | Setting out | Setting out |  | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0408 | Offset 50cm for elevator pit walls As Per Attached Sketch. | STR | Setting out | Setting out |  | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0409 | Offset 30cm for columns axis (14-17) / (B-F) for area (P1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43004 | 43005 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0410 | Offset 30cm for columns axis (2-5) / (B-E) for area (P1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43004 | 43005 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0411 | Top level of slab between axis (5-9 / A - L) As Per Attached Sketch. | STR | Setting out | Setting out | B2 | 43004 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0412 | Offset 50cm for columns at axies (L - F/ 6- 9) & (L-A/5-7) & (A-F/5-7) for area (P3, P4 & P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43005 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0413 | Check formwork and level between axes (9-12) & (L-F) with (TOC = 295.60) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43005 | 43009 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0414 | Cartonal coat for retaining wall from level (289.75 to 291.75) between axis (7- 12)/(L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43006 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0415 | First layer of backfilling for retaining wall from level (289.75 to 290.25) between axis (7- 12)/(L) for area (P3) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43006 | 43017 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0416 | Check RFT for retaining wall from level (291.00 to 295.60) between axis (17- 18)/(B-K) for area (P1&P2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43006 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0417 | Check RFT for retaining wall from level (290.75 to 295.60) between axis (1- 2)/(C-G) for area (P4&P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43006 | 43011 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0418 | Check formwork for retaining wall from level (290.75 to 295.60) between axis (1- 2)/(C-G) for area (P4&P5) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43006 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0419 | Pouring request for retaining wall from level (291.00 to 295.20) between axis (16-18)/(J-L) for area (P2) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43006 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0420 | Check formwork for retaining wall from level (290.75 to 295.20) between axis (13-18)/(A) for area (P1) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43006 | 43011 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0421 | Pouring request for retaining wall from level (290.75 to 295.20) between axis (13-18)/(A) for area (P1) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43006 | 43011 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0422 | Check formwork for core wall from level (291.15 to 295.20) between axis (11-13)/(H-J) for area (P3) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43006 | 43011 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0423 | Pouring request for core wall from level (291.15 to 295.20) between axis (11-13)/(H-J) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43006 | 43011 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0424 | Offset 30cm for columns and kikers at axies (K - G/ 16 - 17) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43009 | 43010 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0425 | Check formwork and drops and level for slab between axes (1-5) & (A-B) with (TOC = 300.10) - PART (Z4) As Per Attached Sketch. | STR | Setting out | Setting out | B1 | 43009 | 43010 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0426 | Check formwork and drops and level for slab between axes (1-5) & (A-B) with (TOC = 300.10) - PART (Z4) As Per Attached Sketch. | STR | Setting out | Setting out | B1 | 43009 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0427 | Check formwork for elevator pit walls from level (291.15 - 295.60) between axes (10-12) & (G-K) at area (P3) As Per Attached Sketch | STR | Formwork | Formwork | B2 | 43009 | 43017 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0428 | Pouring request for elevator pit walls from level (291.15 - 295.60) between axes (10-12) & (G-K) at area (P3) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43009 | 43017 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0429 | Check RFT for R.C stair core walls from level (290.75 - 295.60) between axes (15-16) & (B-C) at area (P1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43009 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0430 | Check RFT for coulmns from level (291.00 - 295.60) between axes (13-14) & (K-L) at area (P2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43009 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0431 | Check formwork for coulmns from level (291.00 - 295.60) between axes (13-14) & (K-L) at area (P2) As Per Attached Sketch | STR | Formwork | Formwork | B2 | 43009 | 43025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0432 | Pouring request for coulmns from level (291.00 - 295.60) between axes (13-14) & (K-L) at area (P2) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43009 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0433 | Check formwork for coulmns from level (290.75 - 295.60) between axes (16-18) & (A-E) at area (P1) As Per Attached Sketch | STR | Formwork | Formwork | B2 | 43009 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0434 | Pouring request for coulmns from level (290.75 - 295.60) between axes (16-18) & (A-E) at area (P1) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43009 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0435 | Surface preparation and repair for retaining wall from level (289.75 to 293.75) between axis (2- 6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43009 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0436 | rimer coat for retaining wall from level (289.75 to 293.75) between axis (2-6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43009 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0437 | Membrane coat for retaining wall from level (289.75 to 293.75) between axis (2-6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43009 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0438 | Check RFT for columns from level (289.75 to 295.20) between axis (3-4)/(E-G) for area (P4&P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43009 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0439 | Check RFT for columns from level (289.75 to 295.20) between axis (3-4)/(E-G) for area (P4&P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43009 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0440 | Check RFT for columns from level (289.75 to 295.20) between axis (3-4)/(E-G) for area (P4&P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43009 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0441 | Check RFT for columns from level (295.60 to 300.10) between axis (5-9)/(G-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43009 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0442 | Check formwork for columns from level (295.60 to 300.10) between axis (5-9)/(G-L) for area (Z4) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43009 | 43017 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0443 | Pouring request for columns from level (295.60 to 300.10) between axis (5-9)/(G-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43009 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0444 | Check RFT for columns from level (295.60 to 300.10) between axis (5-6)/(D-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43009 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0445 | Check formwork for columns from level (295.60 to 300.10) between axis (5-6)/(D-F) for area (Z6) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43009 | 43017 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0446 | Pouring request for columns from level (295.60 to 300.10) between axis (5-6)/(D-F) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43009 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0447 | Check bottom reinforcement for R.C slab between axes (9-13) & (F-K) with (TOC = 295.60) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43009 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0448 | Check TOP reinforcement for R.C slab between axes (9-13) & (F-K) with (TOC = 295.60) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0449 | Pouring request for R.C slab between axes (9-13) & (F-K) with (TOC = 295.60) for area (Z3) As Per Attached | STR | Concreting | Concreting | B2 | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0450 | Check RFT for columns from level (295.60 to 300.10) between axis (5-9)/(F-L) for area (Z4) As Per Attached Sketch.Sketch | STR | Reinforcement | Reinforcement | B1 | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0451 | Check formwork for columns from level (295.60 to 300.10) between axis (5-9)/(F-L) for area (Z4) As Per Attached Sketch.Sketch | STR | Formwork | Formwork | B1 | 43012 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0452 | Pouring request for columns from level (295.60 to 300.10) between axis (5-9)/(F-L) for area (Z4) As Per Attached Sketch.Sketch | STR | Concreting | Concreting | B1 | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0453 | Check RFT for columns from level (291.00 to 295.60) between axis (17-18)/(F-L) for area (P2) As Per Attached Sketch.Sketch | STR | Reinforcement | Reinforcement | B2 | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0454 | Check RFT for columns from level (290.75 to 295.60) between axis (13-18)/(E-F) for area (P1) As Per Attached Sketch.Sketch | STR | Reinforcement | Reinforcement | B2 | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0455 | Second layer of bakfilling for retaining wall from level (290.25 to 290.75) between axis (1- 6)/(A) for area (P5) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43017 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0456 | Third layer of bakfilling for retaining wall from level (290.75 to 291.25) between axis (1- 6)/(A) for area (P5) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43017 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0457 | First layer of bakfilling for retaining wall from level (289.75 to 290.25) between axis (16- 18)/(J-L) for area (P2) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43017 | 43040 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0458 | Membrane coat for retaining wall from level (289.75 to 293.75) between axis (1 - 6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0459 | Cartonal coat for retaining wall from level (289.75 to 293.75) between axis (1 - 6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0460 | Second layer of backfilling for retaining wall from level (290.25 to 290.75) between axis (7- 12)/(L) for area (P3) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43012 | 43017 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0461 | Third layer of backfilling for retaining wall from level (290.75 to 291.25) between axis (7- 12)/(L) for area (P3) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43012 | 43017 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0462 | Surface preparation and repair for retaining wall from level (289.75 to 293.75) between axis (4- 7)/(L) for area (P3 &P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0463 | Primer coat for retaining wall from level (289.75 to 293.75) between axis (4- 7)/(L) for area (P3 &P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0464 | Membrane coat for retaining wall from level (289.75 to 293.75) between axis (4- 7)/(L) for area (P3 &P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0465 | Cartonal coat for retaining wall from level (289.75 to 293.75) between axis (4- 7)/(L) for area (P3 &P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0466 | First layer of bakfilling for retaining wall from level (289.75 to 290.25) between axis (4- 7)/(L) for area (P3 &P4) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43012 | 43017 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0467 | Second layer of bakfilling for retaining wall from level (290.25 to 290.75) between axis (4- 7)/(L) for area (P3 &P4) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43012 | 43017 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0468 | Third layer of bakfilling for retaining wall from level (290.75 to 291.25) between axis (4- 7)/(L) for area (P3 &P4) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43012 | 43017 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0469 | Check formwork for stair core walls from level (289.75 to 295.20) between axis (3-4)/(B-C) for area (P5) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0470 | Pouring request for stair core walls from level (289.75 to 295.20) between axis (3-4)/(B-C) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0471 | Check RFT for elevator core walls from level (289.75 to 295.20) between axis (3-4)/(D-E) for area (P5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43012 | 43017 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0472 | Check formwork and drops and level for slab between axes (3-5) & (A-B) with (TOC = 299.20, 299.65 & 300.10 ) - PART (Z5) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43012 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0473 | Check top level for slab between axes (9-12) & (G-K) with (TOC = 295.60 ) - PART (Z3) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43012 | 43022 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0474 | Check formwork level and drops for slab between axes (12-14) & (F-L) with (TOC = 295.60 ) - PART (Z3&Z2) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43012 | 43022 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0475 | Offset 50cm for columns and wall on slab at axies (F - J/ 9-13) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43012 | 43022 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0476 | Pouring request for retaining wall from level (290.75 to 295.60) between axis (1- 2)/(C-G) for area (P4&P5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0477 | Check RFT for stair core walls from level (291.00 to 295.60) between axis (2-4)/(H-K) for area (P4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43016 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0478 | Check bottom reinforcement for R.C slab between axes (2-6) & (A-C) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0479 | Check top reinforcement for R.C slab between axes (2-6) & (A-C) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0480 | Pouring request for R.C slab between axes (2-6) & (A-C) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0481 | Check RFT for retaining wall from level (295.60 to 300.10) between axis (6-8)/(L) for area (Z4) As Per Attached Sketch.Sketch | STR | Reinforcement | Reinforcement | B1 | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0482 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (6-8)/(L) for area (Z4) As Per Attached Sketch.Sketch | STR | Formwork | Formwork | B1 | 43016 | 43025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0483 | Pouring request for retaining wall from level (295.60 to 300.10) between axis (6-8)/(L) for area (Z4) As Per Attached Sketch.Sketch | STR | Concreting | Concreting | B1 | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0484 | Check formwork for retaining wall from level (291.00 to 295.60) between axis (G-K)/(18) for area (P2) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0485 | Check formwork for retaining wall from level (291.00 to 295.60) between axis (G-K)/(18) for area (P2) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0486 | Surface preparation and repair for retaining wall from level (290.75 to 294.75) between axis (13-18)for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0487 | Primer coat for retaining wall from level (290.75 to 294.75) between axis (13-18)for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0488 | Membrane coat for retaining wall from level (290.75 to 294.75) between axis (13-18)for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0489 | Surface preparation and repair for retaining wall from level (291.00 to 294.00) between axis (16- 18)/(J-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0490 | Primer coat for retaining wall from level (291.00 to 294.00) between axis (16- 18)/(J-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0491 | Membrane coat for retaining wall from level (291.00 to 294.00) between axis (16- 18)/(J-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0492 | Cartonal coat for retaining wall from level (291.00 to 294.00) between axis (16- 18)/(J-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0493 | Check top level for slab between axes (3-5) & (A-B) with (TOC = 300.10 , 299.20 & 299.65 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0494 | Check formwork level and drops for slab between axes (13-18) & (A-B) with (TOC = 295.60 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43016 | 43029 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0495 | Check formwork level and drops for slab between axes (1-2) & (A-D) with (TOC = 295.60 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0496 | Check formwork level for ramp between axes (7-10) & (L-F) with (TOC = 295.60 ) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0497 | Offset 50cm for columns between axis (3-5)/(A-B) PART- (P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43016 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0498 | Second layer of bakfilling for retaining wall from level (290.25 to 290.75) between axis (16- 18)/(J-L) for area (P2) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43017 | 43040 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0499 | Third layer of bakfilling for retaining wall from level (290.75 to 291.25) between axis (16- 18)/(J-L) for area (P2) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43017 | 43040 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0500 | Fourth layer of bakfilling for retaining wall from level (291.25 to 291.75) between axis (16- 18)/(J-L) for area (P2) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43017 | 43040 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0501 | Check RFT for coulmns from level (295.60 - 300.10) between axes (6-12) & (F-K) at area (Z3 & Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43017 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0502 | Check formwork for retaining wall from level (290.75 to 295.60) between axis (17-18)/(A-F) for area (P1) As Per Attached Sketch.Sketch | STR | Formwork | Formwork | B2 | 43017 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0503 | Pouring request for retaining wall from level (290.75 to 295.60) between axis (17-18)/(A-F) for area (P1) As Per Attached Sketch.Sketch | STR | Concreting | Concreting | B2 | 43017 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0504 | Check top level for slab between axes (11-14) & (E-L) with (TOC = 299.60 ) - PART (P2.P3) As Per Attached Sketch | STR | Levels | Levels | B1 | 43020 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0505 | Check top level for slab between axes (13-18) & (A) with (TOC = 299.60 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43020 | 43025 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0506 | Check formwork for R.C stair core walls from level (290.75 - 295.60) between axes (15-16) & (B-C) at area (P1) As Per Attached Sketch | STR | Formwork | Formwork | B2 | 43023 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0507 | Pouring request for R.C stair core walls from level (290.75 - 295.60) between axes (15-16) & (B-C) at area (P1) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43023 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0508 | Surface prepration and repair for retaining wall from level (293.75 to 295.60) between axis (9-13)/(L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0509 | Primer coat for retaining wall from level (293.75 to 295.60) between axis (9-13)/(L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0510 | Membrane coat for retaining wall from level (293.75 to 295.60) between axis (9-13)/(L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0511 | Cartonal coat for retaining wall from level (293.75 to 295.60) between axis (9-13)/(L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0512 | Surface prepration and repair for retaining wall from level (289.75 to 293.75) between axis (5-7)/(A-E) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0513 | Primer coat for retaining wall from level (289.75 to 293.75) between axis (5-7)/(A-E) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0514 | Membrane coat for retaining wall from level (289.75 to 293.75) between axis (5-7)/(A-E) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0515 | Cartonal coat for retaining wall from level (289.75 to 293.75) between axis (5-7)/(A-E) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0516 | Check bottom reinforcement for R.C slab between axes (1-3) & (A-C) with (TOC = 295.60) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43023 | 43031 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0517 | Check top reinforcement for R.C slab between axes (1-3) & (A-C) with (TOC = 295.60) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0518 | Pouring request for R.C slab between axes (1-3) & (A-C) with (TOC = 295.60) for area (Z6) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0519 | Check bottom reinforcement for R.C slab between axes (10-15) & (F-L) with (TOC = 295.60) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0520 | Check top reinforcement for R.C slab between axes (10-15) & (F-L) with (TOC = 295.60) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0521 | Pouring request for R.C slab between axes (10-15) & (F-L) with (TOC = 295.60) for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0522 | Check bottom and top reinforcement for R.C Ramp and Slab between axes (9-11) & (F-H) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0523 | Pouring request for R.C Ramp and Slab between axes (9-11) & (F-H) for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0524 | Check RFT for retaining wall from level (290.75 to 295.60) between axis (17-18)/(A-B) for area (P1) As Per Attached Sketch.Sketch | STR | Reinforcement | Reinforcement | B2 | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0525 | Check formwork for retaining wall from level (290.75 to 295.60) between axis (17-18)/(A-B) for area (P1) As Per Attached Sketch.Sketch | STR | Formwork | Formwork | B2 | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0526 | Pouring request for retaining wall from level (290.75 to 295.60) between axis (17-18)/(A-B) for area (P1) As Per Attached Sketch.Sketch | STR | Concreting | Concreting | B2 | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0527 | Check RFT for retaining wall from level (291.00 to 295.60) between axis (2-5)/(L) for area (P4) As Per Attached Sketch.Sketch | STR | Reinforcement | Reinforcement | B2 | 43023 | 43031 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0528 | Check formwork for columns from level (290.75 to 295.60) between axis (14-18)/(E-F) for area (P1) As Per Attached Sketch.Sketch | STR | Formwork | Formwork | B2 | 43023 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0529 | Pouring request for columns from level (290.75 to 295.60) between axis (14-18)/(E-F) for area (P1) As Per Attached Sketch.Sketch | STR | Concreting | Concreting | B2 | 43023 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0530 | Check bottom reinforcement for R.C slab between axes (13-18) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0531 | Check Top reinforcement for R.C slab between axes (13-18) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0532 | Pouring request for R.C slab between axes (13-18) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0533 | Check formwork for coulmns from level (295.60 - 300.10) between axes (6-12) & (F-J) at area (Z3 & Z4) As Per Attached Sketch | STR | Formwork | Formwork | B1 | 43023 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0534 | Pouring request for coulmns from level (295.60 - 300.10) between axes (9-12) & (F-L) at area (Z3 & Z4) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43023 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0535 | Check RFT for elevator core walls from level (295.60 to 300.10) between axis (7-9)/(H-J) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43023 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0536 | Check formwork for elevator core walls from level (295.60 to 300.10) between axis (7-9)/(H-J) for area (Z4) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43023 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0537 | Pouring request for elevator core walls from level (295.60 to 300.10) between axis (7-9)/(H-J) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43023 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0538 | Check RFT for coulmns from level (300.10 - 304.10) between axes (2-6) & (A-B) at area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43023 | 43027 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0539 | Check formwork for coulmns from level (300.10 - 304.10) between axes (2-6) & (A-B) at area (Z6) As Per Attached Sketch | STR | Formwork | Formwork | GF | 43023 | 43027 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0540 | Pouring request for coulmns from level (300.10 - 304.10) between axes (2-6) & (A-B) at area (Z6) As Per Attached Sketch | STR | Concreting | Concreting | GF | 43023 | 43027 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0541 | Fourth layer of bakfilling for retaining wall from level (291.25 to 291.75) between axis (1- 6)/(A) for area (P5) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43023 | 43040 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0542 | Fifth layer of bakfilling for retaining wall from level (291.75 to 292.25) between axis (1- 6)/(A) for area (P5) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43023 | 43040 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0543 | Sixth layer of bakfilling for retaining wall from level (292.25 to 292.75) between axis (1- 6)/(A) for area (P5) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43023 | 43040 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0544 | Check top level for slab between axes (1-3) & (A-C) with (TOC = 295.60 ) - PART (Z5) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43023 | 43026 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0545 | Check top level for slab between axes (14-18) & (A-B) with (TOC = 295.60 ) - PART (Z1) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43023 | 43026 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0546 | Check top level for RAMP from level (291.60 - 295.60) between axes (9-10) & (K-L) - PART (Z3) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43023 | 43026 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0547 | Check top level for RAMP from level (291.60 - 295.60) between axes (9-10) & (F-G) - PART (Z3) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43023 | 43026 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0548 | Offset 50cm for columns and walls on slab (295.60) at axies (A / 14 - 17) for area (Z1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43023 | 43026 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0549 | Offset 50cm for columns and walls on slab (295.60) at axies (F-G / 9 - 10) for area (Z3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43025 | 43029 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0550 | Offset 50cm for columns and walls on slab (295.60) at axies (A-B / 1 - 2) for area (Z5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43025 | 43029 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0551 | Offset 50cm for columns on slab (295.60) at axies (A / 15- 16) for area (Z1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43025 | 43029 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0552 | Surface preparation and repair for retaining wall from level (289.75 to 293.75) between axis (B-E)/(18) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43025 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0553 | Primer coat for retaining wall from level (289.75 to 293.75) between axis (B-E)/(18) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43025 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0554 | Check RFT for retaining wall from level (291.00 to 295.60) between axis (13-16)/(L) for area (P2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43025 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0555 | Check RFT for core walls from level (291.00 to 295.60) between axis (15-17)/(G-H) for area (P2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43025 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0556 | Check RFT for elevator core walls from level (290.75 to 295.60) between axis (14-17)/(D-E) for area (P1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43025 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0557 | Surface preparation and repair for retaining wall from level (293.75 to 295.60) between axis (6-9)/(L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43025 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0558 | Primer coat for retaining wall from level (293.75 to 295.60) between axis (6-9)/(L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43025 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0559 | Membrane coat for retaining wall from level (293.75 to 295.60) between axis (6-9)/(L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43025 | 43032 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0560 | Check formwork for stair core walls from level (291.00 to 295.60) between axis (3-4)/(G-J) for area (P4) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43025 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0561 | Pouring request for stair core walls from level (291.00 to 295.60) between axis (3-4)/(G-J) for area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43025 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0562 | Offset 50cm for columns and wall on slab at axies (K - L/ 9-11) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43027 | 43031 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0563 | Check formwork level and drops for slab between axes (5-8) & (L-G) with (TOC = 300.10 ) - PART (P3) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43027 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0564 | Check top level for slab between axes (1-6) & (A-C) with (TOC = 295.60 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43027 | 43031 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0565 | Check top level for slab between axes (13-18) & (B-D) with (TOC = 295.60 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43027 | 43031 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0566 | Offset 50cm for columns and wall on slab at axies (A - C/ 14-18) for area (P1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43030 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0567 | Offset 50cm for columns and wall on slab at axies (K- L/ 3 - 5) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43030 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0568 | Check top level for slab between axes (2-5) & (K-L) with (TOC = 295.60 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43030 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0569 | Check formwork and drops and level for slab between axes (2-5) & (K-L) with (TOC = 295.60 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43030 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0570 | Check Top & bottom reinforcement for R.C slab between axes (9-10) & (F-H) with (TOC = 295.60) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0571 | Pouring request for R.C slab between axes (9-10) & (F-H) with (TOC = 295.60) for area (Z3) As Per Attached | STR | Concreting | Concreting | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0572 | Surface preparation and repair for retaining wall from level (289.75 to 291.75) between axis (H-L)/(1) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0573 | Primer coat for retaining wall from level (289.75 to 291.75) between axis (H-L)/(1) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0574 | Memprane coat for retaining wall from level (289.75 to 291.75) between axis (H-L)/(1) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0575 | First layer of bakfilling for retaining wall from level (289.75 to 290.25) between axis (13-18)for area (P1) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0576 | Second layer of bakfilling for retaining wall from level (290.25 to 290.75) between axis (13-18)for area (P1) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0577 | Third layer of bakfilling for retaining wall from level (290.75 to 291.25) between axis (13-18)for area (P1) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0578 | Check Top & bottom reinforcement for R.C slab of ramp between axes (9-11) & (G-L) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0579 | Pouring request for R.C slab of ramp between axes (9-11) & (G-L) for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0580 | Surface preparation and repair for retaining wall from level (289.75 to 293.75) between axis (B-F)/(1) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0581 | Primer coat for retaining wall from level (289.75 to 293.75) between axis (B-F)/(1) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0582 | Membrane coat for retaining wall from level (289.75 to 293.75) between axis (B-F)/(1) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0583 | Check bottom reinforcement for R.C slab between axes (14-17)/(A-B) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0584 | Check top reinforcement for R.C slab between axes (14-17)/(A-B) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0585 | Pouring request for R.C slab between axes (14-17)/(A-B) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0586 | Chek top & bottom reinforcement for R.C slab between axes (9-10)/(J-L) with (TOC = 295.60) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0587 | Pouring request for R.C slab between axes (9-10)/(J-L) with (TOC = 295.60) for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0588 | Check formwork for retaining wall from level (291.00 to 295.60) between axis (14-17)/(L) for area (P2) As Per Attached Sketch.Sketch | STR | Formwork | Formwork | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0589 | Pouring request for retaining wall from level (291.00 to 295.60) between axis (14-17)/(L) for area (P2) As Per Attached Sketch.Sketch | STR | Concreting | Concreting | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0590 | Formwork for retaining wall from level (291.00 to 295.60) between axis (3-6)/(L) for area (P4) As Per Attached Sketch.Sketch | STR | Formwork | Formwork | B2 | 43032 | 43037 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0591 | Pouring request for retaining wall from level (291.00 to 295.60) between axis (3-6)/(L) for area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0592 | Check RFT for stair core walls and columns from level (291.00 to 295.60) between axis (2-5)/(F-K) for area (P4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0593 | Check RFT for columns from level (295.60 to 300.10) between axis (1-2)/(A-B) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0594 | Check bottom reinforcement for R.C slab between axes (1-5)/(B-D) with (TOC = 295.60) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0595 | Check TOP reinforcement for R.C slab between axes (1-5)/(B-D) with (TOC = 295.60) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0596 | Pouring request for R.C slab between axes (1-5)/(B-D) with (TOC = 295.60) for area (Z6) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0597 | Check bottom reinforcement for R.C slab between axes (13-18)/(A-C) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0598 | Check TOP reinforcement for R.C slab between axes (13-18)/(A-C) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0599 | Pouring request for R.C slab between axes (13-18)/(A-C) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0600 | Check formwork for columns between axes (17-18)/(H-J) from level (291.00 to 295.60) for area (P2) As Per Attached Sketch | STR | Formwork | Formwork | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0601 | Pouring request for columns between axes (17-18)/(H-J) from level (291.00 to 295.60) for area (P2) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0602 | Check RFT for stair core wall between axes (15-16)/(H-J) from level (291.00 to 295.60) for area (P2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0603 | Check RFT for retaining wall between axes (5-7)/(L) from level (295.60 to 300.10) for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0604 | Check formwork for retaining wall between axes (5-7)/(L) from level (295.60 to 300.10) for area (Z4) As Per Attached Sketch | STR | Formwork | Formwork | B1 | 43032 | 43037 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0605 | Pouring request for retaining wall between axes (5-7)/(L) from level (295.60 to 300.10) for area (Z4) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0606 | Check formwork for stair core wall between axes (6-8)/(H-J) from level (295.60 to 300.10) for area (Z4) As Per Attached Sketch | STR | Formwork | Formwork | B1 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0607 | Pouring request for stair core wall between axes (6-8)/(H-J) from level (295.60 to 300.10) for area (Z4) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0608 | Check bottom reinforcement for R.C slab between axes (2-6)/(J-L) with (TOC = 295.60) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0609 | Check TOP reinforcement for R.C slab between axes (2-6)/(J-L) with (TOC = 295.60) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0610 | Pouring request for R.C slab between axes (2-6)/(J-L) with (TOC = 295.60) for area (Z5) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0611 | Check top & bottom reinforcement for R.C slab between axes (8-9)/(J-L) with (TOC = 295.60) for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0612 | Pouring request for R.C slab between axes (8-9)/(J-L) with (TOC = 295.60) for area (Z4) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0613 | Check formwork for columns from level (295.60 to 300.10) between axis (11-14)/(G-K) for area (Z3) As Per Attached Sketch.Sketch | STR | Formwork | Formwork | B1 | 43032 | 43039 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0614 | Pouring request for columns from level (295.60 to 300.10) between axis (11-14)/(G-K) for area (Z3) As Per Attached Sketch.Sketch | STR | Concreting | Concreting | B1 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0615 | Check RFT for columns from level (295.60 to 300.10) between axis (13-18)/(A-B) for area (Z1) As Per Attached Sketch.Sketch | STR | Reinforcement | Reinforcement | B1 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0616 | Check formwork for columns from level (295.60 to 300.10) between axis (13-18)/(A-B) for area (Z1) As Per Attached Sketch.Sketch | STR | Formwork | Formwork | B1 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0617 | Pouring request for columns from level (295.60 to 300.10) between axis (13-18)/(A-B) for area (Z1) As Per Attached Sketch.Sketch | STR | Concreting | Concreting | B1 | 43032 | 43039 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0618 | Check formwork for elevator core wall from level (290.75 to 295.60) between axis (15-16)/(B-E) for area (P1) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0619 | Pouring request for elevator core wall from level (290.75 to 295.60) between axis (15-16)/(B-E) for area (P1) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0620 | Check formwork for elevator core wall from level (291.00 to 295.60) between axis (3-4)/(H-J) for area (P4) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43032 | 43039 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0621 | Pouring request for elevator core wall from level (291.00 to 295.60) between axis (3-4)/(H-J) for area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0622 | Check RFT for elevator core wall and columns from level (291.00 to 295.60) between axis (14-17)/(F-J) for area (P2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0623 | Surface preparation and repair for retaining wall from level (293.75 to 295.60) between axis (16-18)/(J-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0624 | Primer coat for retaining wall from level (293.75 to 295.60) between axis (16-18)/(J-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0625 | Membrane coat for retaining wall from level (293.75 to 295.60) between axis (16-18)/(J-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0626 | Cartonal coat for retaining wall from level (293.75 to 295.60) between axis (16-18)/(J-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0627 | Check bottom reinforcement for R.C slab between axes (1-5)/(C-F) with (TOC = 295.60) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0628 | Check TOP reinforcement for R.C slab between axes (1-5)/(C-F) with (TOC = 295.60) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0629 | Pouring request for R.C slab between axes (1-5)/(C-F) with (TOC = 295.60) for area (Z6) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0630 | Check bottom reinforcement for R.C slab between axes (4-8)/(G-L) with (TOC = 300.10) for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0631 | Check TOP reinforcement for R.C slab between axes (4-8)/(G-L) with (TOC = 300.10) for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0632 | Pouring request for R.C slab between axes (4-8)/(G-L) with (TOC = 300.10) for area (Z4) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0633 | Check RFT for coulmns from level (295.60 - 300.10) between axes (9-14)/(H-L) at area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0634 | Check formwork for coulmns from level (295.60 - 300.10) between axes (10-14)/(G-K) at area (Z3) As Per Attached Sketch | STR | Formwork | Formwork | B1 | 43032 | 43039 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0635 | Pouring request for coulmns from level (295.60 - 300.10) between axes (10-14)/(G-K) at area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0636 | Check RFT for retaining wall from level (295.60 to 300.10) between axis (13-18) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0637 | Check RFT for retaining wall from level (295.60 to 300.10) between axis (1-4) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0638 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (1-4) for area (Z6) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43032 | 43039 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0639 | Pouring request for retaining wall from level (295.60 to 300.10) between axis (1-4) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43032 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0640 | Offset 50cm for columns and wall on slab at axies (D - E/ 1-4) for area (P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0641 | Offset 50cm for columns and wall on slab at axies (L- G/ 5-7) for area (P3&P4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0642 | Check top level for slab between axes (5-8) & (L-G) with (TOC = 300.10 ) - PART (P3&P4) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0643 | Check top level for slab between axes (1-4) & (C-E) with (TOC = 295.60 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43032 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0644 | Check top level for slab between axes (16-18) & (L-G) with (TOC = 295.60 ) - PART (P2) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43034 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0645 | Check top level for slab between axes (3-4) & (E-F) with (TOC = 295.60 ) - PART (P4) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43034 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0646 | Offset 50cm for columns on slab at axies (E-F/ 3-4) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43034 | 43066 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0647 | Check bottom reinforcement for R.C slab between axes (4-8)/(F-L) with (TOC = 300.10) for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0648 | Check TOP reinforcement for R.C slab between axes (4-8)/(F-L) with (TOC = 300.10) for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0649 | Pouring request for R.C slab between axes (4-9)/(F-L) with (TOC = 300.10) for area (Z4) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0650 | Surface preparation and repair for retaining wall from level (289.75 to 293.75) between axis (2-6)/(L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0651 | Primer coat for retaining wall from level (289.75 to 293.75) between axis (2-6)/(L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0652 | Membrane coat for retaining wall from level (289.75 to 293.75) between axis (2-6)/(L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0653 | Check RFT for retaining wall from level (295.60 to 300.10) between axis (1-2)/(A-E) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0654 | Check RFT for retaining wall from level (295.60 to 300.10) between axis (8-12)/(L) for area (Z3&Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0655 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (8-12)/(L) for area (Z3&Z4) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0656 | Pouring request for retaining wall from level (295.60 to 300.10) between axis (8-12)/(L) for area (Z3&Z4) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0657 | Check RFT for retaining wall from level (295.60 to 300.10) between axis (2-6)/(L) for area (Z4&Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0658 | Check formworkfor retaining wall from level (295.60 to 300.10) between axis (2-6)/(L) for area (Z4&Z5) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0659 | Pouring request for retaining wall from level (295.60 to 300.10) between axis (2-6)/(L) for area (Z4&Z5) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0660 | Check formwork for columns from level (295.60 to 300.10) between axis (9-12)/(F-L) for area (Z3) As Per Attached Sketch.Sketch | STR | Formwork | Formwork | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0661 | Pouring request for columns from level (295.60 to 300.10) between axis (9-12)/(F-L) for area (Z3) As Per Attached Sketch.Sketch | STR | Concreting | Concreting | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0662 | Check bottom reinforcement for R.C slab between axes (3-5)/(F-K) with (TOC = 295.60) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0663 | Check TOP reinforcement for R.C slab between axes (3-5)/(F-K) with (TOC = 295.60) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0664 | Pouring request for R.C slab between axes (3-5)/(F-K) with (TOC = 295.60) for area (Z5) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0665 | Check bottom reinforcement for R.C slab between axes (16-18)/(H-L) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0666 | Check TOP reinforcement for R.C slab between axes (16-18)/(H-L) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0667 | Pouring request for R.C slab between axes (16-18)/(H-L) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0668 | Check bottom reinforcement for R.C slab between axes (13-18)/(A-D) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0669 | Check TOP reinforcement for R.C slab between axes (13-18)/(A-D) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0670 | Pouring request for R.C slab between axes (13-18)/(A-D) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0671 | Check bottom reinforcement for R.C slab between axes (2-6)/(A-c) with (TOC = 304.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0672 | Check top reinforcement for R.C slab between axes (2-6)/(A-c) with (TOC = 304.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0673 | Pouring reuquest for R.C slab between axes (2-6)/(A-c) with (TOC = 304.10) for area (Z6) As Per Attached Sketch | STR | Concreting | Concreting | GF | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0674 | Check formwork for core wall from level (291.00 to 295.60) between axis (3-4)/(G-H) for area (P4) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0675 | Pouring request for core wall from level (291.00 to 295.60) between axis (3-4)/(G-H) for area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0676 | Check formwork for retaining wall from level (291.00 to 295.60) between axis (1-2)/(E-G) for area (P4&P5) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43036 | 43053 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0677 | Pouring request for retaining wall from level (291.00 to 295.60) between axis (1-2)/(E-G) for area (P4&P5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43036 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0678 | Check formwork for retaining wall from level (291.00 to 295.60) between axis (17-18)/(E-H) for area (P1&P2) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43036 | 43039 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0679 | Pouring request for retaining wall from level (291.00 to 295.60) between axis (17-18)/(E-H) for area (P1&P2) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0680 | Check formwork for retaining wall & columns from level (291.00 to 295.60) between axis (13-16)/(K-L) for area (P2) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0681 | Pouring request for retaining wall & columns from level (291.00 to 295.60) between axis (13-16)/(K-L) for area (P2) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0682 | Check bottom reinforcement for R.C slab between axes (2-5)/(E-G) with (TOC = 295.60) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0683 | Check TOP reinforcement for R.C slab between axes (2-5)/(E-G) with (TOC = 295.60) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0684 | Pouring request for R.C slab between axes (2-5)/(E-G) with (TOC = 295.60) for area (Z5) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0685 | Check RFT for columns from level (300.10 to 304.10) between axis (5-8)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0686 | Check formwork for columns from level (295.60 to 300.10) between axis (9-14)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0687 | Pouring request for columns from level (295.60 to 300.10) between axis (9-14)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0688 | Check RFT for stair core walls and columns from level (295.60 to 300.10) between axis (1-5)/(B-E) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0689 | Membrane coat for retaining wall from level (289.75 to 293.75) between axis (B-E)/(18) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0690 | Cartonal coat for retaining wall from level (289.75 to 293.75) between axis (B-E)/(18) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0691 | First layer of backfilling for retaining wall from level (289.75 to 290.25) between axis (B-E)/(18) for area (P1) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0692 | Second layer of backfilling for retaining wall from level (290.25 to 290.75) between axis (B-E)/(18) for area (P1) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0693 | Fourth layer of bakfilling for retaining wall from level (291.25 to 291.75) between axis (13-18)for area (P1) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43036 | 43039 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0694 | Check formwork and drops and level for slab between axes (14-16) & (E-L) with (TOC = 295.60 ) - PART (P2) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43036 | 43040 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0695 | Check formwork and drops and level for slab between axes (1-4) & (F-K) with (TOC = 295.60 ) - PART (P4) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43036 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0696 | Check top level for slab between axes (1-4) & (F-K) with (TOC = 295.60 ) - PART (P4) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43036 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0697 | Check top level for slab between axes (2-6) & (A-C) with (TOC = 304.10 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | GF | 43036 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0698 | Check top level for slab between axes (5-9) & (K-L) with (TOC = 304.10 ) - PART (P3&P4) As Per Attached Sketch. | STR | Levels | Levels | GF | 43036 | 43040 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0699 | Check top level for slab between axes (14-18) & (A-E) with (TOC = 295.60 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43036 | 43040 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0700 | Offset 50cm for columns on slab at axies (G-J/4) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43036 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0701 | Offset 50cm for columns and wall on slab at axies (J-L/17-18) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43036 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0702 | Offset 50cm for columns and wall on slab at axies (A-B/3-5) for area (P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43036 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0703 | Offset 50cm for columns and wall on slab at axies (G-K/7-9) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43036 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0704 | Offset 50cm for columns and wall on slab at axies (C-D/14-18) for area (P1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43036 | 43037 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0705 | Offset 50cm for columns and wall on slab at axies (G-J/3) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43038 | 43040 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0706 | Offset 50cm for columns and wall on slab at axies (F-H/17-18) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43038 | 43040 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0707 | Check top level for slab between axes (16-18) & (E-H) with (TOC = 295.60 ) - PART (P2) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43038 | 43040 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0708 | Check bottom reinforcement for R.C slab between axes (14-17)/(J-L) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0709 | Check TOP reinforcement for R.C slab between axes (14-17)/(J-L) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0710 | Pouring request for R.C slab between axes (14-17)/(J-L) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0711 | Check bottom reinforcement for R.C slab between axes (13-18)/(C-F) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0712 | Check TOP reinforcement for R.C slab between axes (13-18)/(C-F) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0713 | Pouring request for R.C slab between axes (13-18)/(C-F) with (TOC = 295.60) for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0714 | Check bottom reinforcement for R.C slab between axes (1-4)/(F-K) with (TOC = 295.60) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0715 | Check TOP reinforcement for R.C slab between axes (1-4)/(F-K) with (TOC = 295.60) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0716 | Pouring request for R.C slab between axes (1-4)/(F-K) with (TOC = 295.60) for area (Z5) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0717 | Check formwork for columns from level (295.60 to 300.10) between axis (13-18)/(A-E) for area (Z1) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0718 | Pouring request for columns from level (295.60 to 300.10) between axis (13-18)/(A-E) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0719 | Surface preparation and repair for retaining wall from level (289.75 to 293.75) between axis (E-G)/(17-18) for area (P1&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0720 | Primer coat for retaining wall from level (289.75 to 293.75) between axis (E-G)/(17-18) for area (P1&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0721 | Check RFT for retaining wall from level (295.60 to 300.10) between axis (C-G)/(1-2) for area (Z5&Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0722 | Check RFT for retaining wall from level (295.60 to 300.10) between axis (A-F)/(6-13) for area (Z3&Z4&Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0723 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (6-9)/(F) for area (Z4) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43039 | 43053 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0724 | pouring request for retaining wall from level (295.60 to 300.10) between axis (6-9)/(F) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43039 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0725 | Surface preparation and repair for retaining wall from level (289.75 to 293.75) between axis (1-2)/(E-G) for area (P4&P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0726 | Primer coat for retaining wall from level (289.75 to 293.75) between axis (1-2)/(E-G) for area (P4&P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0727 | Membrane coat for retaining wall from level (289.75 to 293.75) between axis (1-2)/(E-G) for area (P4&P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43039 | 43046 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0728 | Check RFT for columns from level (295.60 to 300.10) between axis (2-4)/(E-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0729 | Check formwork for stair core wall and columns columns from level (295.60 to 300.10) between axis (2-4)/(B-F) for area (Z6) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43039 | 43044 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0730 | Pouring request for stair core wall and columns columns from level (295.60 to 300.10) between axis (2-4)/(B-F) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0731 | Check formwork for core wall and columns columns from level (291.00 to 295.60) between axis (14-16)/(F-H) for area (Z2) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43039 | 43044 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0732 | Pouring request for core wall and columns columns from level (291.00 to 295.60) between axis (14-16)/(F-H) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0733 | Check bottom reinforcement for R.C slab between axes (16-18)/(E-J) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43039 | 43046 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0734 | Check TOP reinforcement for R.C slab between axes (16-18)/(E-J) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43039 | 43046 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0735 | Pouring request for R.C slab between axes (16-18)/(E-J) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43039 | 43046 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0736 | Check RFT for retaining wall and columns from level (295.60 to 300.10) between axis (13-18)/(A-D) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0737 | Check RFT for retaining wall from level (295.60 to 300.10) between axis (H-L)/(18) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0738 | Check RFT for coulmnsl from level (295.60 to 300.10) between axis (F-H)/(3-5) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0739 | Check RFT for stair core wall and coulmns from level (300.10 to 304.10) between axis (F-K)/(5-8) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0740 | Check formwork for elevator core wall from level (295.60 to 300.10) between axis (H-J)/(10-12) for area (Z3) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43039 | 43046 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0741 | Pouring request for elevator core wall from level (295.60 to 300.10) between axis (H-J)/(10-12) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43039 | 43046 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0742 | Third layer of backfilling for retaining wall from level (290.75 to 291.25) between axis (B-E)/(18) for area (P1) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0743 | Fourth layer of backfilling for retaining wall from level (291.25 to 291.75) between axis (B-E)/(18) for area (P1) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43039 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0744 | Check top level for slab between axes (13-18) & (C-F) with (TOC = 295.60 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43040 | 43046 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0745 | Check top level for slab between axes (14-17) & (J-L) with (TOC = 295.60 ) - PART (P2) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43040 | 43046 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0746 | Check top level for slab between axes (9-10) & (K-H) with (TOC = 300.10 ) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43040 | 43046 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0747 | Check top level for slab between axes (2-3) & (A) with (TOC = 300.10 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43040 | 43046 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0748 | Offset 50cm for columns and wall on slab at axies (K-L/15-16) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43040 | 43046 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0749 | Check formwork for stair core wall between axes (15-16)/(H-J) from level (291.00 to 295.60) for area (P2) As Per Attached Sketch | STR | Formwork | Formwork | B2 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0750 | Check RFT for elevator core walls from level (295.60 to 300.10) between axis (3-5)/(H-K) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0751 | Check formwork for elevator core walls from level (295.60 to 300.10) between axis (3-5)/(H-K) for area (Z5) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0752 | Pouring request for elevator core walls from level (295.60 to 300.10) between axis (3-5)/(H-K) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0753 | Surface preparation and repair for retaining wall from level (289.75 to 293.75) between axis (13/17)/(L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0754 | Primer coat for retaining wall from level (289.75 to 293.75) between axis (13/17)/(L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0755 | Check RFT for columns from level (300.10 to 304.10) between axis (5-8)/(F-K) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0756 | Check bottom reinforcement for R.C slab between axes (9-11)/(G-L) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0757 | Check TOP reinforcement for R.C slab between axes (9-11)/(G-L) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0758 | Pouring request for R.C slab between axes (9-11)/(G-L) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0759 | Check bottom reinforcement for R.C slab between axes (1-3)/(A) with (TOC = 299.20) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0760 | Check TOP reinforcement for R.C slab between axes (1-3)/(A) with (TOC = 299.20) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0761 | Pouring request for R.C slab between axes (1-3)/(A) with (TOC = 299.20) for area (Z6) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0762 | Check RFT for columns from level (304.10 to 308.10) between axis (3-4)/(A-B) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0763 | Check formwork for columns from level (304.10 to 308.10) between axis (3-4)/(A-B) for area (Z6) As Per Attached Sketch. | STR | Formwork | Formwork | 1st | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0764 | Pouring request for columns from level (304.10 to 308.10) between axis (A-B)/(3) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0765 | Check RFT for core walls from level (295.60 to 300.10) between axis (3-4)/(G-H) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0766 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (A-E)/(1) for area (Z6) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0767 | Pouring request for retaining wall from level (295.60 to 300.10) between axis (A-E)/(1) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0768 | Pouring request for stair core wall between axes (15-16)/(H-J) from level (291.00 to 295.60) for area (P2) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43041 | 43044 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0769 | Offset 50cm for columns and wall on slab at axies (C-D/3-5) for area (P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43045 | 43047 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0770 | Offset 50cm for columns and wall on slab at axies (E-G-/15-16) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43045 | 43047 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0771 | Offset 50cm for columns and wall on slab at axies (D-E/14-18) for area (P1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43045 | 43047 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0772 | Offset 50cm for columns and wall on slab at axies (H-J/10) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43045 | 43047 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0773 | Check top level for slab between axes (2-9) & (B-E) with (TOC = 300.10 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43045 | 43047 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0774 | Check top level for slab between axes (3-7) & (E-L) with (TOC = 300.10 ) - PART (P4) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43045 | 43047 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0775 | Check top level for slab between axes (6-8) & (K-I) with (TOC = 300.10 ) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43045 | 43047 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0776 | Check top level for slab between axes (13-17) & (F-H) with (TOC = 295.60 ) - PART (P2) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43045 | 43047 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0777 | Check bottom reinforcement for R.C slab between axes (3-5)/(E-K) with (TOC = 300.10) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0778 | Check TOP reinforcement for R.C slab between axes (3-5)/(E-K) with (TOC = 300.10) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0779 | Pouring request for R.C slab between axes (3-5)/(E-K) with (TOC = 300.10) for area (Z5) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0780 | Check bottom reinforcement for R.C slab between axes (4-9)/(J-L) with (TOC = 300.10) for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0781 | Check TOP reinforcement for R.C slab between axes (4-9)/(J-L) with (TOC = 300.10) for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0782 | Pouring request for R.C slab between axes (4-9)/(J-L) with (TOC = 300.10) for area (Z4) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0783 | Check bottom reinforcement for R.C slab between axes (2-6)/(B-F) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0784 | Check TOP reinforcement for R.C slab between axes (2-6)/(B-F) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0785 | Pouring request for R.C slab between axes (2-6)/(B-F) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0786 | Check bottom reinforcement for R.C slab between axes (14-17)/(E-H) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0787 | Check TOP reinforcement for R.C slab between axes (14-17)/(E-H) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0788 | Pouring request for R.C slab between axes (14-17)/(E-H) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0789 | Check formwork for stair core wall between axes (3-4)/(H-J) from level (295.60 to 300.10) for area (P2) As Per Attached Sketch | STR | Formwork | Formwork | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0790 | Pouring request for stair core wall between axes (3-4)/(H-J) from level (295.60 to 300.10) for area (Z4) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0791 | Check formwork for core wall between axes (3-4)/(G-H) from level (295.60 to 300.10) for area (Z4) As Per Attached Sketch | STR | Formwork | Formwork | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0792 | Pouring request for core wall between axes (3-4)/(G-H) from level (295.60 to 300.10) for area (Z4) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0793 | Surface preparation and repair for retaining wall from level (293.75 to 297.75) between axis (14-17) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0794 | Primer coat for retaining wall from level (293.75 to 297.75) between axis (14-17) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0795 | Membrane coat for retaining wall from level (293.75 to 297.75) between axis (14-17) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0796 | Cartonal coat for retaining wall from level (293.75 to 297.75) between axis (14-17) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0797 | Surface preparation and repair for retaining wall from level (293.75 to 297.75) between axis (1-6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0798 | Primer coat for retaining wall from level (293.75 to 297.75) between axis (1-6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0799 | Membrane coat for retaining wall from level (293.75 to 297.75) between axis (1-6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0800 | Cartonal coat for retaining wall from level (293.75 to 297.75) between axis (1-6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0801 | Membrane coat for retaining wall from level (289.75 to 293.75) between axis (1-2)/(E-G) for area (P4&P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0802 | Cartonal coat for retaining wall from level (289.75 to 293.75) between axis (1-2)/(E-G) for area (P4&P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0803 | Membrane coat for retaining wall from level (289.75 to 293.75) between axis (12-17)/(L) for area (P2&P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0804 | Cartonal coat for retaining wall from level (289.75 to 293.75) between axis (12-17)/(L) for area (P2&P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0805 | Membrane coat for retaining wall from level (289.75 to 293.75) between axis (17-18)/(E-J) for area (P1&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0806 | Cartonal coat for retaining wall from level (289.75 to 293.75) between axis (17-18)/(E-J) for area (P1&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0807 | Check formwork for elevator core wall from level (291.00 to 295.60) between axis (15-16)/(H-J) for area (P2) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0808 | Pouring request for elevator core wall from level (291.00 to 295.60) between axis (15-16)/(H-J) for area (P2) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0809 | Check RFT for columns from level (304.10 to 308.10) between axis (5-6)/(A-C) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0810 | Check RFT for retaining wall from level (295.60 to 300.10) between axis (14-17)/(L) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0811 | Check RFT for retaining wall from level (295.60 to 300.10) between axis (A-E)/(18) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0812 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (17-18) for area (Z1) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0813 | Pouring request for retaining wall from level (295.60 to 300.10) between axis (17-18) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0814 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (B-F)/(6) for area (Z6) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43045 | 43053 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0815 | Pouring request for retaining wall from level (295.60 to 300.10) between axis (B-F)/(6) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0816 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (9-12)/(F) for area (Z3) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43045 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0817 | Pouring request for retaining wall from level (295.60 to 300.10) between axis (9-12)/(F) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43045 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0818 | Check RFT for columns from level (295.60 to 300.10) between axis (13-18)/(E) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0819 | Check formwork for stair core wall from level (300.10 to 304.10) between axis (H-J)/(6-8) for area (Z4) As Per Attached Sketch. | STR | Formwork | Formwork | GF | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0820 | Pouring request for stair core wall from level (300.10 to 304.10) between axis (H-J)/(6-8) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43045 | 43045 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0821 | First layer of backfilling for retaining wall from level (289.75 to 290.25) between axis (11-17)/(L) for area (P2&P3) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0822 | First layer of backfilling for retaining wall from level (289.75 to 290.25) between axis (E-K)/(17-18) for area (P1&P2) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | B2 | 43045 | 43053 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0823 | Check top level for slab between axes (2-5) & (D-E) with (TOC = 300.10 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43046 | 43050 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0824 | Check top level for slab between axes (9-12) & (F-L) with (TOC = 300.10 ) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43046 | 43050 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0825 | Check top level for slab between axes (14-16) & (K-H) with (TOC =295.60 ) - PART (P2) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43046 | 43050 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0826 | Check Offset 50cm for columns between axes (3-4 / D-A) PART 5 As Per Attached Sketch. | STR | Setting out | Setting out |  | 43046 | 43050 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0827 | Check Offset 50cm for columns between axes (3-4 / F-J) PART 4 As Per Attached Sketch. | STR | Setting out | Setting out |  | 43046 | 43050 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0828 | Check Offset 50cm for columns between axes (5-9 / K-L) PART 4 AND 3 As Per Attached Sketch. | STR | Setting out | Setting out |  | 43046 | 43050 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0829 | Check Offset 50cm for columns between axes (10-11 / G-K) PART (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43048 | 43059 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0830 | Check top level for slab between axes (1-3) & (A-E) with (TOC = 299.20, 299.60 & 300.10) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43048 | 43059 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0831 | Check RFT for columns from level (295.60 to 300.10) between axis (15-16)/(F-G) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0832 | Check formwork for columns from level (295.60 to 300.10) between axis (15-16)/(F-G) for area (Z2) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43053 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0833 | Pouring request for columns from level (295.60 to 300.10) between axis (15-16)/(F-G) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0834 | Check bottom reinforcement for R.C slab between axes (5-6)/(A-E) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0835 | Check TOP reinforcement for R.C slab between axes (5-6)/(A-E) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0836 | Pouring request for R.C slab between axes (5-6)/(A-E) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0837 | Check bottom reinforcement for R.C slab between axes (2-5)/(E-F) with (TOC = 300.10) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0838 | Check TOP reinforcement for R.C slab between axes (2-5)/(E-F) with (TOC = 300.10) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0839 | Pouring request for R.C slab between axes (2-5)/(E-F) with (TOC = 300.10) for area (Z5) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0840 | Check bottom reinforcement for R.C slab between axes (1-3)/(A-E) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0841 | Check TOP reinforcement for R.C slab between axes (1-3)/(A-E) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0842 | Pouring request for R.C slab between axes (1-3)/(A-E) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0843 | Check bottom reinforcement for R.C slab between axes (2-5)/(J-L) with (TOC = 300.10) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0844 | Check TOP reinforcement for R.C slab between axes (2-5)/(J-L) with (TOC = 300.10) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0845 | Pouring request for R.C slab between axes (2-5)/(J-L) with (TOC = 300.10) for area (Z5) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43053 | 43062 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0846 | Check bottom reinforcement for R.C slab between axes (11-15)/(F-L) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0847 | Check TOP reinforcement for R.C slab between axes (11-15)/(F-L) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0848 | Pouring request for R.C slab between axes (11-15)/(F-L) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0849 | Check bottom reinforcement for R.C slab between axes (9-12)/(F-L) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0850 | Check top reinforcement for R.C slab between axes (9-12)/(F-L) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0851 | Pouring request for R.C slab between axes (9-12)/(F-L) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0852 | Check bottom reinforcement for R.C slab between axes (13-17)/(G-L) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0853 | Check TOP reinforcement for R.C slab between axes (13-17)/(G-L) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0854 | Pouring request for R.C slab between axes (13-17)/(G-L) with (TOC = 295.60) for area (Z2) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0855 | Check bottom reinforcement for R.C slab between axes (2-4)/(E-K) with (TOC = 300.10) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0856 | Check TOP reinforcement for R.C slab between axes (2-4)/(E-K) with (TOC = 300.10) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0857 | Pouring request for R.C slab between axes (2-4)/(E-K) with (TOC = 300.10) for area (Z5) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0858 | Check bottom reinforcement for R.C slab between axes (2-5)/(C-E) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0859 | Check TOP reinforcement for R.C slab between axes (2-5)/(C-E) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0860 | Pouring request for R.C slab between axes (2-5)/(C-E) with (TOC = 300.10) for area (Z6) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0861 | Check bottom reinforcement for R.C slab between axes (14-18) with (TOC = 299.20) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0862 | Check top reinforcement for R.C slab between axes (14-18) with (TOC = 299.20) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0863 | Pouring request for R.C slab between axes (14-18) with (TOC = 299.20) for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43053 | 43062 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0864 | Check RFT for core walls from level (295.60 to 300.10) between axis (15-16)/(G-H) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0865 | Check RFT for coulmnsl from level (295.60 to 300.10) between axis (D-F)/(13-17) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0866 | Check formwork for coulmnsl from level (295.60 to 300.10) between axis (D-F)/(13-17) for area (Z1) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43053 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0867 | Pouring request for coulmns from level (295.60 to 300.10) between axis (D-F)/(13-17) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0868 | Check formwork for columns from level (304.10 to 308.10) between axis (4-5)/(A-B) for area (Z6) As Per Attached Sketch. | STR | formwork | formwork | 1st | 43053 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0869 | Pouring request for columns from level (304.10 to 308.10) between axis (4-5)/(A-B) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0870 | Check RFT for stair core wall from level (295.60 to 300.10) between axis (B-C)/(15-16) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43053 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0871 | Check RFT for elevator core wall from level (300.10 to 304.10) between axis (H-G)/(7-9) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0872 | Check formwork for elevator core wall from level (300.10 to 304.10) between axis (H-G)/(7-9) for area (Z3) As Per Attached Sketch. | STR | Formwork | Formwork | GF | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0873 | Pouring request for elevator core wall from level (300.10 to 304.10) between axis (H-G)/(7-9) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0874 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (A-E)/(18) for area (Z1) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0875 | Pouring request for retaining wall from level (295.60 to 300.10) between axis (A-E)/(18) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43053 | 43062 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0876 | Check RFT for elevator core walls from level (295.60 to 300.10) between axis (14-16)/(D-E) for area (Z1) As Per Attached Sketch. | STR | reinforcement | reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0877 | Check RFT for columns from level (300.10 to 304.10) between axis (6-8)/(J-L) for area (Z3) As Per Attached Sketch. | STR | reinforcement | reinforcement | GF | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0878 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (9-11)/(F) for area (Z3) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43053 | CANCELLED | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0879 | Pouring request for retaining wall from level (295.60 to 300.10) between axis (9-11)/(F) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43053 | CANCELLED | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0880 | Check RFT for retaining wall and column from level (295.60 to 300.10) between axis (14-17)(G/L) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0881 | Check formwork for retaining wall and column from level (295.60 to 300.10) between axis (14-17)(G/L) for area (Z2) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43053 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0882 | Pouring request for retaining wall and column from level (295.60 to 300.10) between axis (14-17)(G/L) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0883 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (16-18)/(J-L) for area (Z2) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43053 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0884 | Pouring requests for retaining wall from level (295.60 to 300.10) between axis (16-18)/(J-L) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0885 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (10-13)/(L) for area (Z3) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43053 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0886 | Pouring request for retaining wall from level (295.60 to 300.10) between axis (10-13)/(L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0887 | Check RFT for coulmns from level (291.00 to 295.60) between axis (H-L)/(1-2) for area (P4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0888 | Check formwork for coulmnsl from level (291.00 to 295.60) between axis (H-L)/(1-2) for area (P4) As Per Attached Sketch. | STR | Formwork | Formwork | B2 | 43053 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0889 | Pouring request for coulmns from level (291.00 to 295.60) between axis (H-L)/(1-2) for area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0890 | Check RFT for coulmns from level (295.60 to 300.10) between axis (F-L)/(14-18) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0891 | Check formwork for coulmns from level (295.60 to 300.10) between axis (F-L)/(14-18) for area (Z2) As Per Attached Sketch | STR | Formwork | Formwork | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0892 | Pouring request for coulmns from level (295.60 to 300.10) between axis (F-L)/(14-18) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0893 | Check RFT for coulmns from level (295.60 to 300.10) between axis (13-18)/(E) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0894 | Check RFT for coulmns from level (295.60 to 300.10) between axis (13-18)/(E) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43053 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0895 | Pouring request for columns from level (295.60 to 300.10) between axis (13-18)/(E) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0896 | Check formwork for stair core wall from level (295.60 to 300.10) between axis (H-J)/(11-13) for area (Z3) As Per Attached Sketch. | STR | Formwork | Formwork | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0897 | Pouring request for stair core wall from level (295.60 to 300.10) between axis (H-J)/(11-13) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43053 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0898 | heck Top level for slab between axes (17-13) & (A) with (TOC = 300.10 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43057 | 43059 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0899 | Check Top level for slab between axes (6-1) & (A-F) with (TOC = 300.10 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43057 | 43059 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0900 | Check Top level for slab between axes (11-14) & (L-F) with (TOC = 300.10 ) - PART (P2&P3) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43057 | 43059 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0901 | Check Top level for slab between axes (14-17) & (A-D) with (TOC = 300.10 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43057 | 43059 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0902 | Check Top level for slab between axes (17-18) & (G-L) with (TOC = 300.10 ) - PART (P2) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43057 | 43059 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0903 | Offset 50cm for columns and walls on slab (300.10) at axies (K-L / 3 - 4) for area (Z4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43057 | 43059 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0904 | Offset 50cm for columns and walls on slab (300.10) at axies (A-E / 1- 2) for area (Z5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43057 | 43059 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0905 | Offset 50cm for columns and walls on slab (300.10) at axies (A-E / 1- 2) for area (Z5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43057 | 43059 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0906 | Offset 50cm for columns and walls on slab (300.10) at axies (L-J / 17- 18) for area (Z2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43057 | 43059 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0907 | Offset 50cm for columns and walls on slab (300.10) at axies (L-F / 14- 12) for area (Z2&Z3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43057 | 43059 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0908 | Offset 50cm for columns on slab (304.10) at axies (F-K / 5-6) for area (Z3&Z4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43060 | 43066 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0909 | Offset 50cm for columns on slab (300.10) at axies (K-L/ 15-16) for area (Z2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43060 | 43066 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0910 | Offset 50cm for columns on slab (300.10) at axies (A-B/ 14-16) for area (Z1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43060 | 43066 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0911 | Offset 50cm for columns on slab (300.10) at axies (14-16/C) for area (Z1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43060 | 43066 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0912 | Offset 50cm for columns on slab (300.10) at axies (15-16/E-G) for area (Z2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43060 | 43066 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0913 | Offset 50cm for columns on slab (304.10) at axies (B-E/5) for area (Z5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43060 | 43066 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0914 | Check Top level for slab between axes (14-17) & (E-D) with (TOC = 300.10 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43060 | 43066 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0915 | Check Top level for slab between axes (14-17) & (J-L) with (TOC = 300.10 ) - PART (P2) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43060 | 43066 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0916 | Check Top level for slab between axes (14-18) & (E-J) with (TOC = 300.10 ) - PART (P1&P2) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43060 | 43066 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0917 | Check Top level for slab between axes (4-9) & (F-L) with (TOC = 304.10 ) - PART (P3&P4) As Per Attached Sketch. | STR | Levels | Levels | GF | 43060 | 43066 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0918 | Check Top level for slab between axes (4-6) & (A-F) with (TOC = 304.10 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | GF | 43060 | 43066 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0919 | Check formwork and drops and level for slab between axes (13-18) & (A-E) with (TOC = 300.10 ) - PART (P1&P2) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43060 | 43066 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0920 | Check bottom reinforcement for R.C slab between axes (5-9) & (D-G) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0921 | Check bottom reinforcement for R.C slab between axes (5-9) & (D-G) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0922 | POURING REQUEST for R.C slab between axes (5-9) & (D-G) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0923 | check bottom reinforcement for R.C slab between axes (13-17) &( A-C) with (TOC = 300.10) for area (Z1) As Per Attached Sketch | STR | reinforcement | reinforcement | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0924 | check TOP reinforcement for R.C slab between axes (13-17) &( A-C) with (TOC = 300.10) for area (Z1) As Per Attached Sketch | STR | reinforcement | reinforcement | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0925 | POURING REQUEST for R.C slab between axes (13-17) &( A-C) with (TOC = 300.10) for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0926 | check BOTTOM rienforcement for R.C slab between axes (13-17) &( A-D) with (TOC = 300.10) for area (Z1) As Per Attached Sketch | STR | reinforcement | reinforcement | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0927 | check Top rienforcement for R.C slab between axes (13-17) &( A-D) with (TOC = 300.10) for area (Z1) As Per Attached Sketch | STR | reinforcement | reinforcement | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0928 | pouring request for R.C slab between axes (13-17) &( A-D) with (TOC = 300.10) for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0929 | check bottom reinforcement for R.C slab between axes (14-17) &( j-L) with (TOC = 300.10) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0930 | check top reinforcement for R.C slab between axes (14-17) &( j-L) with (TOC = 300.10) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0931 | pouring request for R.C slab between axes (14-17) &( j-l) with (TOC = 300.10) for area (Z2) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0932 | check bottom reinforcement for R.C slab between axes (14-17) &(E-K) with (TOC = 300.10) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0933 | check top reinforcement for R.C slab between axes (14-17) &(E-K) with (TOC = 300.10) for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0934 | pouring request for R.C slab between axes (14-17) &(E-K) with (TOC = 300.10) for area (Z2) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0935 | Check bottom reinforcement for R.C slab between axes (13-17) &(C-F) with (TOC = 300.10) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0936 | Check top reinforcement for R.C slab between axes (13-17) &(C-F) with (TOC = 300.10) for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0937 | Pouring Request for R.C slab between axes (13-17) &(C-F) with (TOC = 300.10) for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0938 | Check bottom reinforcement for R.C slab between axes (4-6) &(B-F) with (TOC = 304.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0939 | Check top reinforcement for R.C slab between axes (4-6) &(B-F) with (TOC = 304.10) for area (Z6) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0940 | Pouring request for R.C slab between axes (4-6) &(B-F) with (TOC = 304.10) for area (Z6) As Per Attached Sketch | STR | Concreting | Concreting | GF | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0941 | Check bottom reinforcement for R.C slab between axes (4-6) &(A-K) with (TOC = 304.10) for area (Z4&Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0942 | Check top reinforcement for R.C slab between axes (4-6) &(A-K) with (TOC = 304.10) for area (Z4&Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0943 | Pouring request for R.C slab between axes (4-6) &(A-K) with (TOC = 304.10) for area (Z4&Z5) As Per Attached Sketch | STR | Concreting | Concreting | GF | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0944 | Check bottom reinforcement for R.C slab between axes (6-9) &(E-L) with (TOC = 304.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0945 | Check top reinforcement for R.C slab between axes (6-9) &(E-L) with (TOC = 304.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0946 | Pouring request for R.C slab between axes (6-9) &(E-L) with (TOC = 304.10) for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | GF | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0947 | Check bottom reinforcement for R.C slab between axes (10-14) &(K-L) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0948 | Check top reinforcement for R.C slab between axes (10-14) &(K-L) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0949 | Pouring request for R.C slab between axes (10-14) &(K-L) with (TOC = 300.10) for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0950 | heck RFT for stair core wall from level (300.10 to 304.10) between axis (H-J)/(3-4) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0951 | Check formwork for stair core wall from level (300.10 to 304.10) between axis (H-J)/(3-4) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0952 | Pouring request for stair core wall from level (300.10 to 304.10) between axis (H-J)/(3-4) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0953 | Check RFT for stair and elevator core wall from level (295.60 to 300.10) between axis (H-J)/(14-16) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0954 | Check formwork for stair and elevator core wall from level (295.60 to 300.10) between axis (H-J)/(14-16) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0955 | Pouring request for stair and elevator core wall from level (295.60 to 300.10) between axis (H-J)/(14-16) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0956 | Check formwork for elevator core wall from level (295.60 to 300.10) between axis (D-E)/(15-16) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43062 | 43062 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0957 | Pouring request for elevator core wall from level (295.60 to 300.10) between axis (D-E)/(15-16) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0958 | Check RFT for columns from level (300.10 to 304.10) between axis (A-D)/(2-6) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0959 | Check formwork for stair core wall from level (300.10 to 304.10) between axis (B-D)/(3-4) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0960 | Pouring request for stair core wall from level (300.10 to 304.10) between axis (B-D)/(3-4) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0961 | Check formwork for elevator core wall from level (300.10 to 304.10) between axis (D-E)/(3-4) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0962 | Pouring request for elevator core wall from level (300.10 to 304.10) between axis (D-E)/(3-4) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0963 | Check formwork for elevator core wall from level (300.10 to 304.10) between axis (H-J)/(3-5) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0964 | Pouring request for elevator core wall from level (300.10 to 304.10) between axis (H-J)/(3-5) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0965 | Check formwork for stair and elevator core wall from level (300.10 to 304.10) between axis (H-J)/(10-13) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0966 | Pouring request for stair and elevator core wall from level (300.10 to 304.10) between axis (H-J)/(10-13) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0967 | Check formwork for columns from level (300.10 to 304.10) between axis (F-L)/(11-14) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0968 | Check formwork for columns from level (300.10 to 304.10) between axis (F-L)/(11-14) for area (Z3) As Per Attached Sketch.. | STR | FORMWORK | FORMWORK | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0969 | Check RFT for columns from level (300.10 to 304.10) between axis (A-F)/(3-6) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0970 | Check formwork for columns from level (300.10 to 304.10) between axis (A-F)/(3-6) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0971 | Pouring request for columns from level (300.10 to 304.10) between axis (A-F)/(3-6) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0972 | Check RFT for columns from level (304.10 to 308.10) between axis (F-L)/(5-6) for area (Z3) As Per Attached Sketch. | STR | reinforcement | reinforcement | 1st | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0973 | Check formwork for columns from level (304.10 to 308.10) between axis (F-L)/(5-6) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0974 | Pouring requestfor columns from level (304.10 to 308.10) between axis (F-L)/(5-6) for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | 1st | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0975 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (E-H)/(17-18) for area (Z2) As Per Attached Sketch | STR | FORMWORK | FORMWORK | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0976 | Pouring request for retaining wall from level (295.60 to 300.10) between axis (E-H)/(17-18) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0977 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (A-B)/(17-18) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0978 | Check formwork for retaining wall from level (295.60 to 300.10) between axis (A-B)/(17-18) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0979 | Check RFT for retaining wall from level (295.60 to 300.10) between axis (D-F)/(17-18) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0980 | Check formwork for stair core wall from level (295.60 to 300.10) between axis (B-D)/(15-16) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0981 | Pouring request for stair core wall from level (295.60 to 300.10) between axis (B-D)/(15-16) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43062 | 43063 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0982 | Check SURVEY of puddle flange for water tank as per attached table . | STR | Levels | Levels | B2 | 43064 |  | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0983 | Check bottom reinforcement for R.C slab between axes (1-3) &(E-G) with (TOC = 300.10) for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0984 | Check TOP reinforcement for R.C slab between axes (1-3) &(E-G) with (TOC = 300.10) for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0985 | Pouring request for R.C slab between axes (1-3) &(E-G) with (TOC = 300.10) for area (Z4) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0986 | Check bottom reinforcement for R.C slab between axes (10-14) &(G-K) with (TOC = 304.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43067 | 43075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0987 | Check TOP reinforcement for R.C slab between axes (10-14) &(G-K) with (TOC = 304.10) for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43067 | 43075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0988 | Pouring request for R.C slab between axes (10-14) &(G-K) with (TOC = 304.10) for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | GF | 43067 | 43075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0989 | Check bottom reinforcement for R.C slab between axes (13-14) &(E-G) with (TOC = 295.60 for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0990 | Check TOP reinforcement for R.C slab between axes (13-14) &(E-G) with (TOC = 295.60 for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B2 | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0991 | Pouring request for R.C slab between axes (13-14) &(E-G) with (TOC = 295.60 for area (Z2) As Per Attached Sketch | STR | Concreting | Concreting | B2 | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0992 | Check bottom reinforcement for R.C slab between axes (16-18) &(E-F) with (TOC = 300.10 for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43067 | 43075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0993 | Check TOP reinforcement for R.C slab between axes (16-18) &(E-F) with (TOC = 300.10 for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43067 | 43075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0994 | Pouring request for R.C slab between axes (16-18) &(E-F) with (TOC = 300.10 for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43067 | 43075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0995 | Check bottom reinforcement for R.C slab between axes (16-18) &(E-J) with (TOC = 300.10 for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0996 | Check TOP reinforcement for R.C slab between axes (16-18) &(E-J) with (TOC = 300.10 for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0997 | Pouring request for R.C slab between axes (16-18) &(E-J) with (TOC = 300.10 for area (Z2) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0998 | Check bottom reinforcement for R.C slab between axes (10-13) &(F-G) with (TOC = 300.10 for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-0999 | Check TOP reinforcement for R.C slab between axes (10-13) &(F-G) with (TOC = 300.10 for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | B1 | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1000 | Pouring request for R.C slab between axes (10-13) &(F-G) with (TOC = 300.10 for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | B1 | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1001 | Check bottom reinforcement for R.C slab between axes (2-5) &(E-K) with (TOC = 304.10 for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1002 | Check TOP reinforcement for R.C slab between axes (2-5) &(E-K) with (TOC = 304.10 for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1003 | Pouring request for R.C slab between axes (2-5) &(E-K) with (TOC = 304.10 for area (Z4) As Per Attached Sketch | STR | Concreting | Concreting | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1004 | Check bottom reinforcement for R.C slab between axes (2-5) &(B-F) with (TOC = 304.10 for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1005 | Check TOP reinforcement for R.C slab between axes (2-5) &(B-F) with (TOC = 304.10 for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1006 | Pouring request for R.C slab between axes (2-5) &(B-F) with (TOC = 304.10 for area (Z5) As Per Attached Sketch | STR | Concreting | Concreting | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1007 | Check RFT for coulmns from level (300.10 to 304.10) between axis (A-E)/(5-6) for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1008 | Check formwork for coulmns from level (300.10 to 304.10) between axis (A-E)/(5-6) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1009 | Pouring request for coulmns from level (300.10 to 304.10) between axis (A-E)/(5-6) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1010 | Check RFT for elevator core walls from level (300.10 to 304.10) between axis (13-14)/(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1011 | Check formwork for elevator core walls from level (300.10 to 304.10) between axis (13-14)/(H-J) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1012 | Pouring request for elevator core walls from level (300.10 to 304.10) between axis (13-14)/(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1013 | Check RFT for columns from level (304.10 to 308.10) between axis (5-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1014 | Check formwork for columns from level (304.10 to 308.10) between axis (5-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1015 | Pouring request for columns from level (304.10 to 308.10) between axis (5-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1016 | Check RFT for columns from level (300.10 to 304.10) between axis (14-18)/(F-L) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1017 | Check formwork for columns from level (300.10 to 304.10) between axis (14-18)/(F-L) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1018 | Pouring request for columns from level (300.10 to 304.10) between axis (14-18)/(F-L) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1019 | Check RFT for columns from level (300.10 to 304.10) between axis (13-18)/(A-C) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1020 | Surface preparation and repair for retaining wall from level (293.75 to 295.60) between axis (3-8)/L for area (P3&P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1021 | Primer coat for retaining wall from level (293.75 to 295.60) between axis (3-8)/L for area (P3&P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1022 | Membrane coat for retaining wall from level (293.75 to 295.60) between axis (3-8)/L for area (P3&P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43067 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1023 | Check Top level for slab between axes (16 -18) & (L-G) with (TOC = 304.10 ) - PART (P2) As Per Attached Sketch. | STR | Levels | Levels | GF | 43068 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1024 | Check Top level for slab between axes (10 -14) & (L-F) with (TOC = 304.10 ) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | GF | 43068 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1025 | Check Top level for slab between axes (17 -18) & (A-G) with (TOC = 300.10 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43068 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1026 | Check Top level for slab between axes (1-5) & (B-L) with (TOC = 304.10 ) - PART (P4&P5) As Per Attached Sketch. | STR | Levels | Levels | GF | 43068 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1027 | Check Top level for slab between axes (13-17) & (L - G) with (TOC = 304.10 ) - PART (P2 & P3) As Per Attached Sketch. | STR | Levels | Levels | GF | 43068 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1028 | Offset 50cm for columns at axies (D -E / 14 -16) for area (P1) As Per Attached Sketch. | STR | Levels | Levels |  | 43068 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1029 | Offset 50cm for columns at axies (C - D / 3 -4) for area (P5) As Per Attached Sketch. | STR | Levels | Levels |  | 43068 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1030 | Offset 50cm for columns at axies (H - L / 17 -18) for area (P2) As Per Attached Sketch. | STR | Levels | Levels |  | 43068 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1031 | Offset 50cm for columns at axies (K - L / 10 -15) for area (P3 & P2) As Per Attached Sketch. | STR | Levels | Levels |  | 43068 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1032 | Offset 50cm for columns at axies (A - E / 1 - 2) for area (P5) As Per Attached Sketch. | STR | Levels | Levels |  | 43068 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1033 | Offset 50cm for columns at axies (F - L / 6 - 9) for area (P3) As Per Attached Sketch. | STR | Levels | Levels |  | 43068 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1034 | Offset 50cm for columns at axies (F - H / 17 - 18) for area (P2) As Per Attached Sketch. | STR | Levels | Levels |  | 43068 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1035 | Check bottom reinforcement for R.C slab between axes (1-3) &(A-F) with (TOC = 304.10 for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43068 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1036 | Check Top reinforcement for R.C slab between axes (1-3) &(A-F) with (TOC = 304.10 for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43068 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1037 | Pouring Request for R.C slab between axes (1-3) &(A-F) with (TOC = 304.10 for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43068 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1038 | Check bottom reinforcement for R.C slab between axes (2-6) &(J-L) with (TOC = 304.10 for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43068 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1039 | Check Top reinforcement for R.C slab between axes (2-6) &(J-L) with (TOC = 304.10 for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43068 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1040 | Pouring Request for R.C slab between axes (2-6) &(J-L) with (TOC = 304.10 for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43068 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1041 | Check bottom reinforcement for R.C slab between axes (10-16) &(H-L) with (TOC = 304.10 for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43068 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1042 | Check Top reinforcement for R.C slab between axes (10-16) &(H-L) with (TOC = 304.10 for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43068 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1043 | Pouring Request for R.C slab between axes (10-16) &(H-L) with (TOC = 304.10 for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43068 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1044 | Check bottom reinforcement for R.C slab between axes (5-7) &(B-F) with (TOC = 304.10 for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43068 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1045 | Check Top reinforcement for R.C slab between axes (5-7) &(B-F) with (TOC = 304.10 for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43068 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1046 | Pouring Request for R.C slab between axes (5-7) &(B-F) with (TOC = 304.10 for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43068 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1047 | Check RFT for Water tank and pump room walls between axes (1-2) &(G-L) from level (291.00 - 295.60) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43069 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1048 | Check formwork for Water tank and pump room walls between axes (1-2) &(G-L) from level (291.00 - 295.60) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B2 | 43069 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1049 | Pouring Request for Water tank and pump room walls between axes (1-2) &(G-L) from level (291.00 - 295.60) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43069 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1050 | Check RFT for elevator and stair core walls from level (300.10 to 304.10) between axis (14-16)/(B - E) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43069 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1051 | Check RFT for stair core walls from level (300.10 to 304.10) between axis (15-16)/(G - J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43069 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1052 | Check formwork for stair core walls from level (300.10 to 304.10) between axis (15-16)/(G - J) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43069 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1053 | Pouring Request for stair core walls from level (300.10 to 304.10) between axis (15-16)/(G - J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43069 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1054 | Check RFT for elevator core walls from level (304.10 to 308.10) between axis (3-4)/(G - J) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43069 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1055 | Check Formwork for elevator core walls from level (304.10 to 308.10) between axis (3-4)/(G - J) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43069 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1056 | Pouring Request for elevator core walls from level (304.10 to 308.10) between axis (3-4)/(G - J) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43069 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1057 | Check RFT for elevator core walls from level (304.10 to 308.10) between axis (2-5)/(D - E) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43069 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1058 | Check RFT for stair core walls from level (304.10 to 308.10) between axis (3-4)/(B- D) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1059 | Check formwork fo stair core walls from level (304.10 to 308.10) between axis (3-4)/(B- D) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1060 | Pouring Request for stair core walls from level (304.10 to 308.10) between axis (3-4)/(B- D) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1061 | Check RFT for stair core walls from level (304.10 to 308.10) between axis (6-8)/(H- J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1062 | Check formwork for stair core walls from level (304.10 to 308.10) between axis (6-8)/(H- J) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1063 | Pouring Request for stair core walls from level (304.10 to 308.10) between axis (6-8)/(H- J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1064 | Check formwork for columns from level (300.10 to 304.10) between axis (11-18)/(A-G) for area (Z1 &Z2 & Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1065 | Pouring Request for columns from level (300.10 to 304.10) between axis (11-18)/(A-G) for area (Z1 &Z2 & Z3) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1066 | Check RFT for columns from level (304.10 to 308.10) between axis (6-9)/(H-L) for area ( Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1067 | Check formwork for columns from level (304.10 to 308.10) between axis (6-9)/(H-L) for area ( Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1068 | Pouring Request for columns from level (304.10 to 308.10) between axis (6-9)/(H-L) for area ( Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1069 | Check RFT for columns and stair core wall from level (304.10 to 308.10) between axis (2-4)/(G-L) for area ( Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1070 | Check bottom reinforcement for R.C slab between axes (10-15) &(E- H) with (TOC = 304.10 for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1071 | Check top reinforcement for R.C slab between axes (10-15) &(E- H) with (TOC = 304.10 for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43072 | 43075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1072 | Pouring Request for R.C slab between axes (10-15) &(E- H) with (TOC = 304.10 for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43072 | 43075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1073 | Check bottom reinforcement for R.C slab between axes (14-17) &(E- L) with (TOC = 304.10 for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1074 | Check top reinforcement for R.C slab between axes (14-17) &(E- L) with (TOC = 304.10 for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1075 | Pouring Request for R.C slab between axes (14-17) &(E- L) with (TOC = 304.10 for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43072 | 43076 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1076 | Check bottom reinforcement for R.C slab between axes (16-18) &(F-J) with (TOC = 304.10 for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43072 | 43075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1077 | Check top reinforcement for R.C slab between axes (16-18) &(F-J) with (TOC = 304.10 for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43072 | 43075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1078 | Pouring Request reinforcement for R.C slab between axes (16-18) &(F-J) with (TOC = 304.10 for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43072 | 43075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1079 | Surface preparation and repair for retaining wall from level (293.75 to 295.60) between axis (16-18)(J-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1080 | primer coat for retaining wall from level (293.75 to 295.60) between axis (16-18)(J-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1081 | Membrane coat for retaining wall from level (293.75 to 295.60) between axis (16-18)(J-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1082 | cartonal coat for retaining wall from level (293.75 to 295.60) between axis (16-18)(J-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1083 | Surface preparation and repair for retaining wall from level (293.75 to 297.20) between axis (1-6)for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1084 | primer coat for retaining wall from level (293.75 to 297.20) between axis (1-6)for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1085 | Membrane coat for retaining wall from level (293.75 to 297.20) between axis (1-6)for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1086 | cartonal coat for retaining wall from level (293.75 to 297.20) between axis (1-6)for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1087 | Surface preparation and repair for retaining wall from level (293.75 to 296.75) between axis (1-2)/ (A-E)for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1088 | primer coat for retaining wall from level (293.75 to 296.75) between axis (1-2)/ (A-E)for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1089 | Membrane coat for retaining wall from level (293.75 to 296.75) between axis (1-2)/ (A-E)for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1090 | cartonal coat for retaining wall from level (293.75 to 296.75) between axis (1-2)/ (A-E)for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1091 | Check formwork for elevator and stair core walls from level (300.10 to 304.10) between axis (14-16)/(B - E) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1092 | Pouring Request for elevator and stair core walls from level (300.10 to 304.10) between axis (14-16)/(B - E) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1093 | Check bottom reinforcement for R.C slab between axes (13-15) &(A-E) with (TOC = 304.10 for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1094 | Check TOP reinforcement for R.C slab between axes (13-15) &(A-E) with (TOC = 304.10 for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1095 | Pouring request for R.C slab between axes (13-15) &(A-E) with (TOC = 304.10 for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1096 | Check RFT for columns from level (304.10 to 308.10) between axis (10-14)/(H-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1097 | Check formwork for columns from level (304.10 to 308.10) between axis (10-14)/(H-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1098 | Pouring request for columns from level (304.10 to 308.10) between axis (10-14)/(H-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1099 | Check RFT for columns from level (304.10 to 308.10) between axis (1-3)/(A-E) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43074 | 43083 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1100 | Check formwork for columns and elevator core walls from level (304.10 to 308.10) between axis (1-3)/(A-E) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43074 | 43083 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1101 | Pouring request for columns and elevator core walls from level (304.10 to 308.10) between axis (1-3)/(A-E) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43074 | 43083 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1102 | Check RFT for elevator and stair core walls from level (304.10 to 308.10) between axis (10-13)/(H - J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1103 | Check formwork for elevator and stair core walls from level (304.10 to 308.10) between axis (10-13)/(H - J) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1104 | Pouring Request for elevator and stair core walls from level (304.10 to 308.10) between axis (10-13)/(H - J) for area (Z3 As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43074 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1105 | Check RFT for elevator core walls from level (304.10 to 308.10) between axis (7-9)/(H - J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1106 | Check formwork for elevator core walls from level (304.10 to 308.10) between axis (7-9)/(H - J) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1107 | Pouring Request for elevator core walls from level (304.10 to 308.10) between axis (7-9)/(H - J) for area (Z3 As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1108 | Check bottom reinforcement for R.C slab between axes (4-6) &(A-E) with (TOC = 308.10 for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1109 | Check TOP reinforcement for R.C slab between axes (4-6) &(A-E) with (TOC = 308.10 for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1110 | Pouring request for R.C slab between axes (4-6) &(A-E) with (TOC = 308.10 for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1111 | Check bottom reinforcement for R.C slab between axes (4-6) &(F-L) with (TOC = 308.10 for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1112 | Check TOP reinforcement for R.C slab between axes (4-6) &(F-L) with (TOC = 308.10 for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1113 | Pouring request for R.C slab between axes (4-6) &(F-L) with (TOC = 308.10 for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1114 | Check bottom reinforcement for R.C slab between axes (14-17) & (E-G) with (TOC = 304.10 for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1115 | Check TOP reinforcement for R.C slab between axes (14-17) & (E-G) with (TOC = 304.10 for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1116 | Pouring request for R.C slab between axes (14-17) & (E-G) with (TOC = 304.10 for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1117 | Check bottom reinforcement for R.C slab between axes (6-9) & (F-L) with (TOC = 308.10 for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1118 | Check TOP reinforcement for R.C slab between axes (6-9) & (F-L) with (TOC = 308.10 for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1119 | Pouring request for R.C slab between axes (6-9) & (F-L) with (TOC = 308.10 for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1120 | Check bottom reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 295.60 for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43075 | 43083 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1121 | Check TOP reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 295.60 for area (Z4 As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43075 | 43083 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1122 | Pouring request for R.C slab between axes (1-3) & (G-L) with (TOC = 295.60 for area (Z4 As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43075 | 43083 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1123 | Check RFT for columns from level (304.10 to 308.10) between axis (1-6)/(A-F) for area ( Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1124 | Check formwork for columns from level (304.10 to 308.10) between axis (1-6)/(A-F) for area ( Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1125 | Pouring Request for columns from level (304.10 to 308.10) between axis (1-6)/(A-F) for area ( Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1126 | Check RFT for columns from level (308.10 to 312.10) between axis (5-6)/(F-L) for area ( Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1127 | Check formwork for columns from level (308.10 to 312.10) between axis (5-6)/(F-L) for area ( Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1128 | Pouring Request for columns from level (308.10 to 312.10) between axis (5-6)/(F-L) for area ( Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1129 | Offset 50cm for columns at axies (C - D / 3 -4) for area (P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1130 | Check Top level for slab between axes (1-5) & (A-F) with (TOC = 308.12 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1131 | Check Top level for slab between axes (6-9) & (L-F) with (TOC = 308.10 ) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1132 | Check Top level for slab between axes (7-9) & (L-F) with (TOC = 308.10 ) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1133 | Check Top level for slab between axes (15-18) & (L-G) with (TOC = 308.10 ) - PART (P2) As Per Attached Sketch. | STR | Levels | Levels | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1134 | Check Top level for slab between axes (4-6) & (L-E) with (TOC = 308.10 ) - PART (P4&P5) As Per Attached Sketch. | STR | Levels | Levels | 1st | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1135 | Check Top level for slab between axes (1-3) & (L-G) with (TOC = 295.60 ) - PART (P4) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1136 | Check Top level for slab between axes (14-17) & (A-E) with (TOC = 304.10 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | GF | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1137 | Check Top level for slab between axes (17-18) & (H-F) with (TOC = 304.10 ) - PART (P2) As Per Attached Sketch. | STR | Levels | Levels | GF | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1138 | Offset 50cm for columns at axies (F - G / 10 -14) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1139 | Offset 50cm for columns at axies (L - G / 15 -16) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1140 | Offset 50cm for columns at axies (B - E / 4 -3) for area (P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1141 | Offset 50cm for columns at axies (L - H / 1 -2) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1142 | Offset 50cm for columns at axies (L - B / 5 -6) for area (P4&P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1143 | Offset 50cm for columns at axies (C - B /15 -16) for area (P1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43075 | 43079 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1144 | Check RFT for columns from level (304.10 to 308.10) between axis (10-14)/(F-L) for area ( Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1145 | Check formwork for columns from level (304.10 to 308.10) between axis (10-14)/(F-L) for area ( Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1146 | Pouring Request for columns from level (304.10 to 308.10) between axis (10-14)/(F-L) for area ( Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1147 | Check bottom reinforcement for R.C slab between axes (2-4) &(E-G) with (TOC = 304.10 for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1148 | CheckTOP reinforcement for R.C slab between axes (2-4) &(E-G) with (TOC = 304.10 for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1149 | Pouring request reinforcement for R.C slab between axes (2-4) &(E-G) with (TOC = 304.10 for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1150 | Check bottom reinforcement for R.C slab between axes (2-5) &(A-E) with (TOC = 308.10 for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1151 | Check Top Reinforcement for R.C slab between axes (2-5) &(A-E) with (TOC = 308.10 for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1152 | Pouring request for R.C slab between axes (2-5) &(A-E) with (TOC = 308.10 for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1153 | Check RFT for columns& R.W from level (295.60 to 300.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1154 | Check formwork for columns& R.W from level (295.60 to 300.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1155 | Pouring request for columns& R.W from level (295.60 to 300.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1156 | Check RFT for elevator & stair core walls from level (304.10 to 308.10) between axis (15-17)/(G-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1157 | Check formwork for elevator & stair core walls from level (304.10 to 308.10) between axis (15-17)/(G-J) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1158 | Pouring request for elevator & stair core walls from level (304.10 to 308.10) between axis (15-17)/(G-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1159 | Check RFT for columns from level (304.10 to 308.10) between axis (13-16)/(A-E) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1160 | Check formwork for columns from level (304.10 to 308.10) between axis (13-16)/(A-E) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1161 | Pouring request for columns from level (304.10 to 308.10) between axis (13-16)/(A-E) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43079 | 43090 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1162 | Check RFT for columns from level (300.10 to 304.10) between axis (16-18)/(A-E) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1163 | Check formwork for columns from level (300.10 to 304.10) between axis (16-18)/(A-E) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1164 | Pouring request for columns from level (300.10 to 304.10) between axis (16-18)/(A-E) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1165 | Check RFT for columns from level (304.10 to 308.10) between axis (13-18)/(F-L) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43079 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1166 | Check formwork for columns from level (304.10 to 308.10) between axis (13-18)/(F-L) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43079 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1167 | Pouring request for columns from level (304.10 to 308.10) between axis (13-18)/(F-L) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43079 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1168 | Check RFT for columns from level (308.10 to 312.10) between axis (6-9)/(G-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1169 | Check formwork for columns from level (308.10 to 312.10) between axis (6-9)/(G-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1170 | Pouring request for columns from level (308.10 to 312.10) between axis (6-9)/(G-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1171 | Check bottom reinforcement for R.C slab between axes (14-18) &(H-L) with (TOC = 308.10 for area (Z2) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1172 | Check TOP reinforcement for R.C slab between axes (14-18) &(H-L) with (TOC = 308.10 for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1173 | Pouring request for R.C slab between axes (14-18) &(H-L) with (TOC = 308.10 for area (Z2) As Per Attached Sketch | STR | Concreting | Concreting | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1174 | Check bottom reinforcement for R.C slab between axes (14-17) &(A-D) with (TOC = 304.10 for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1175 | Check TOP reinforcement for R.C slab between axes (14-17) &(A-D) with (TOC = 304.10 for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1176 | Pouring request for R.C slab between axes (14-17) &(A-D) with (TOC = 304.10 for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | GF | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1177 | Check bottom reinforcement for R.C slab between axes (14-18) &(A-E) with (TOC = 304.10 for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1178 | Check TOP reinforcement for R.C slab between axes (14-18) &(A-E) with (TOC = 304.10 for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1179 | Pouring request for R.C slab between axes (14-18) &(A-E) with (TOC = 304.10 for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | GF | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1180 | Check bottom reinforcement for R.C slab between axes (10-15) &(G-L) with (TOC = 308.10 for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1181 | Check TOP reinforcement for R.C slab between axes (10-15) &(G-L) with (TOC = 308.10 for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1182 | Pouring request for R.C slab between axes (10-15) &(G-L) with (TOC = 308.10 for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1183 | Check bottom reinforcement for R.C slab between axes (3-7) &(G-L) with (TOC = 308.10 for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1184 | Check TOP reinforcement for R.C slab between axes (3-7) &(G-L) with (TOC = 308.10 for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1185 | Pouring request for R.C slab between axes (3-7) &(G-L) with (TOC = 308.10 for area (Z4) As Per Attached Sketch | STR | Concreting | Concreting | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1186 | Check bottom reinforcement for R.C slab between axes (7-9) &(E-K) with (TOC = 308.10 for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1187 | Check TOP reinforcement for R.C slab between axes (7-9) &(E-K) with (TOC = 308.10 for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1188 | Pouring request for R.C slab between axes (7-9) &(E-K) with (TOC = 308.10 for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | 1st | 43079 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1189 | Check RFT for columns from level (304.10 to 308.10) between axis (15-18)/(E-H) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1190 | Check formwork fo columns from level (304.10 to 308.10) between axis (15-18)/(E-H) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43086 | 43090 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1191 | Pouring request for columns from level (304.10 to 308.10) between axis (15-18)/(E-H) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1192 | Check RFT for elevator & stair core walls from level (308.10 to 312.10) between axis (6-9)/(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1193 | Check formwork for elevator & stair core walls from level (308.10 to 312.10) between axis (6-9)/(H-J) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1194 | Pouring request for elevator & stair core walls from level (308.10 to 312.10) between axis (6-9)/(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1195 | Check RFT for stair core walls from level (308.10 to 312.10) between axis (3-4)/(B-D) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1196 | Check formwork for stair core walls from level (308.10 to 312.10) between axis (3-4)/(B-D) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1197 | Pouring request for stair core walls from level (308.10 to 312.10) between axis (3-4)/(B-D) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1198 | Check RFT for elevator core walls from level (308.10 to 312.10) between axis (3-4)/(D-E) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1199 | Check formwork for elevator core walls from level (308.10 to 312.10) between axis (3-4)/(D-E) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1200 | Pouring request for elevator core walls from level (308.10 to 312.10) between axis (3-4)/(D-E) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1201 | Check bottom reinforcement for R.C slab between axes (1-4) &(A-E) with (TOC = 308.10 for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1202 | Check TOP reinforcement for R.C slab between axes (1-4) &(A-E) with (TOC = 308.10 for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1203 | Pouring request for R.C slab between axes (1-4) &(A-E) with (TOC = 308.10 for area (Z5) As Per Attached Sketch | STR | Concreting | Concreting | 1st | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1204 | Check bottom reinforcement for R.C slab between axes (2-5) &(F-L) with (TOC = 308.10 for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1205 | Check TOP reinforcement for R.C slab between axes (2-5) &(F-L) with (TOC = 308.10 for area (Z4) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1206 | Pouring request for R.C slab between axes (2-5) &(F-L) with (TOC = 308.10 for area (Z4)) As Per Attached Sketch | STR | Concreting | Concreting | 1st | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1207 | Check bottom reinforcement for R.C slab between axes (4-7) &(A-F) with (TOC = 308.10 for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1208 | Check TOP reinforcement for R.C slab between axes (4-7) &(A-F) with (TOC = 308.10 for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1209 | Pouring request for R.C slab between axes (4-7) &(A-F) with (TOC = 308.10 for area (Z5) As Per Attached Sketch | STR | Concreting | Concreting | 1st | 43086 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1210 | Check bottom reinforcement for R.C slab between axes (4-6) &(G-L) with (TOC = 312.10 for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 2nd | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1211 | Check TOP reinforcement for R.C slab between axes (4-6) &(G-L) with (TOC = 312.10 for area (Z3) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 2nd | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1212 | Pouring request for R.C slab between axes (4-6) &(G-L) with (TOC = 312.10 for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | 2nd | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1213 | Check bottom reinforcement for R.C slab between axes (14-18) &(F-K) with (TOC = 308.10 for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1214 | Check TOP reinforcement for R.C slab between axes (14-18) &(F-K) with (TOC = 308.10 for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1215 | Pouring request for R.C slab between axes (14-18) &(F-K) with (TOC = 308.10 for area (Z2) As Per Attached Sketch | STR | Concreting | Concreting | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1216 | Check bottom reinforcement for R.C slab between axes (14-17) &(A-B) with (TOC = 304.10 for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1217 | Check TOP reinforcement for R.C slab between axes (14-17) &(A-B) with (TOC = 304.10 for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1218 | Pouring request for R.C slab between axes (14-17) &(A-B) with (TOC = 304.10 for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | GF | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1219 | Check bottom reinforcement for R.C slab between axes (17-18) &(A-E) with (TOC = 304.10 for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1220 | Check TOP reinforcement for R.C slab between axes (17-18) &(A-E) with (TOC = 304.10 for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1221 | Pouring request for R.C slab between axes (17-18) &(A-E) with (TOC = 304.10 for area (Z1) As Per Attached Sketch | STR | Concreting | Concreting | GF | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1222 | Check bottom reinforcement for R.C slab between axes (4-8) &(E-H) with (TOC = 312.10 for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1223 | Check TOP reinforcement for R.C slab between axes (4-8) &(E-H) with (TOC = 312.10 for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1224 | Pouring request for R.C slab between axes (4-8) &(E-H) with (TOC = 312.10 for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | 2nd | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1225 | Check bottom reinforcement for R.C slab between axes (14-17) &(E-J) with (TOC = 308.10 for area (Z2)As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1226 | Check TOP reinforcement for R.C slab between axes (14-17) &(E-J) with (TOC = 308.10 for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1227 | Pouring request for R.C slab between axes (14-17) &(E-J) with (TOC = 308.10 for area (Z2) As Per Attached Sketch | STR | Concreting | Concreting | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1228 | Check bottom reinforcement for R.C slab between axes (10-15) &(E-L) with (TOC = 308.10 for area (Z3)As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1229 | Check TOP reinforcement for R.C slab between axes (10-15) &(E-L) with (TOC = 308.10 for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1230 | Pouring request for R.C slab between axes (10-15) &(E-L) with (TOC = 308.10 for area (Z3) As Per Attached Sketch | STR | Concreting | Concreting | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1231 | Offset 50cm for columns at axies (H - L / 15 - 18) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1232 | Offset 50cm for columns at axies (A - D / 2 ) for area (P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1233 | Offset 50cm for columns at axies (L - H / 10 - 14 ) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1234 | Offset 50cm for columns at axies (K - H / 4 ) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1235 | Offset 50cm for columns at axies (H - L / 5 - 6 ) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1236 | Offset 50cm for columns at axies (G - F / 15 - 18 ) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1237 | Offset 50cm for columns at axies (A - F / 14 - 18 ) for area (P1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43087 | 43094 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1238 | Check Top level for slab between axes (10 - 18) & (L - F) with (TOC = 308.10 ) - PART (P2 & P3) As Per Attached Sketch. | STR | Setting out | Setting out | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1239 | Check Top level for slab between axes (2 - 4) & (L - E) with (TOC = 308.10 ) - PART (P4 As Per Attached Sketch. | STR | Setting out | Setting out | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1240 | Check Top level for slab between axes (7 - 5) & ( E - K) with (TOC = 312.10 ) - PART (P3 & P4) As Per Attached Sketch. | STR | Setting out | Setting out | 2nd | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1241 | Check Top level for slab between axes (10 - 17) & ( H -E ) with (TOC = 308.10 ) - PART (P3 & P2) As Per Attached Sketch. | STR | Setting out | Setting out | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1242 | Check Top level for slab between axes (13 - 16) & ( A -E ) with (TOC = 308.10 ) - PART (P1) As Per Attached Sketch. | STR | Setting out | Setting out | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1243 | Check Top level for slab between axes (3 - 6) & ( A -F ) with (TOC = 312.10 ) - PART (P5) As Per Attached Sketch. | STR | Setting out | Setting out | 2nd | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1244 | Check Top level for slab between axes (10 - 18) & ( L - G ) with (TOC = 312.10 ) - PART (P2 & P3) As Per Attached Sketch. | STR | Setting out | Setting out | 2nd | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1245 | Check Top level for slab between axes (1 - 3) & ( L - G ) with (TOC = 300.10 ) - PART (P4) As Per Attached Sketch. | STR | Setting out | Setting out | 1st | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1246 | Check formwork and drops and level for slab between axes (5 - 9) & (L - G) with (TOC = 312.10 ) - PART (P3 & P4) As Per Attached Sketch. | STR | Setting out | Setting out | 2nd | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1247 | Offset for axies OF Masonary (L - K / 7 - 9 ) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43087 | 43090 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1248 | Check Top level for slab between axes (16 - 18) & (A - E ) with (TOC = 308.10 ) - PART (P1) As Per Attached Sketch. | STR | Setting out | Setting out | 1st | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1249 | Check Top level for slab between axes (6 - 9) & (F - L ) with (TOC = 312.10 ) - PART (P3) As Per Attached Sketch. | STR | Setting out | Setting out | 2nd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1250 | Check Top level for slab between axes (2 - 5) & (L-F ) with (TOC = 312.10 ) - PART (P4) As Per Attached Sketch. | STR | Setting out | Setting out | 2nd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1251 | Check Top level for slab between axes (1-3) & ( B-F ) with (TOC = 312.10 ) - PART (P5) As Per Attached Sketch. | STR | Setting out | Setting out | 2nd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1252 | Check Top level for slab between axes (14-17) & ( A-H ) with (TOC = 312.10 ) - PART (P3 & P2) As Per Attached Sketch. | STR | Setting out | Setting out | 2nd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1253 | Check Top level for slab between axes (13-14) & ( F-J ) with (TOC = 312.10 ) - PART (4) As Per Attached Sketch. | STR | Setting out | Setting out | 3rd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1254 | Check Top level for slab between axes (5-7) & (K-E ) with (TOC = 316.10 ) - PART (4) As Per Attached Sketch. | STR | Setting out | Setting out | 3rd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1255 | Offset 50 cm for columns at axies ( H - K / 15 - 17 ) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1256 | Offset 50 cm for columns at axies (L- F / 6-8 ) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1257 | Offset 50 cm for columns at axies (B-D / 3-5 ) for area (P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1258 | Offset 50 cm for columns at axies (E / 15-18 ) for area (P1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1259 | Offset 50 cm for columns at axies (F-K / 10-14 ) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1260 | Surface preparation and repair for retaining wall from level ( 293.75 TO 297.75) between axis (A-G)/(17-18) for area (P1&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1261 | Primer Coat for retaining wall from level ( 293.75 TO 297.75) between axis (A-G)/(17-18) for area (P1&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1262 | Membrane Coat for retaining wall from level ( 293.75 TO 297.75) between axis (A-G)/(17-18) for area (P1&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1263 | Cartonal Coat for retaining wall from level ( 293.75 TO 297.75) between axis (A-G)/(17-18) for area (P1&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43088 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1264 | Surface preparation and repair for retaining wall from level ( 293.75 TO 297.75) between axis (A-E)/(1) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1265 | Primer Coat for retaining wall from level ( 293.75 TO 297.75) between axis (A-E)/(1) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1266 | Membrane Coat for retaining wall from level ( 293.75 TO 297.75) between axis (A-E)/(1) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1267 | Cartonal Coat for retaining wall from level ( 293.75 TO 297.75) between axis (A-E)/(1) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43088 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1268 | Check RFT for columns from level (308.10 to 312.10) between axis (1-4)/(A-D) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1269 | Check formwork for columns from level (308.10 to 312.10) between axis (1-4)/(A-D) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1270 | Pouring request for columns from level (308.10 to 312.10) between axis (1-4)/(A-D) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1271 | Check RFT for columns from level (304.10 to 308.10) between axis (14-18)/(A-D) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1272 | Check formwork for columns from level (304.10 to 308.10) between axis (14-18)/(A-D) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1273 | Pouring request for columns from level (304.10 to 308.10) between axis (14-18)/(A-D) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1274 | Check RFT for columns And elevator and stair core wall from level (308.10 to 312.10) between axis (2-5)/(G-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1275 | Check formwork for columns And elevator and stair core wall from level (308.10 to 312.10) between axis (2-5)/(G-L) for area (Z4)) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1276 | Pouring request for columns And elevator and stair core wall from level (308.10 to 312.10) between axis (2-5)/(G-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1277 | Check RFT for columns from level (308.10 to 312.10) between axis (7-9)/(F-K) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43088 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1278 | Check formwork for columns from level (308.10 to 312.10) between axis (7-9)/(F-K) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43088 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1279 | Pouring request for columns from level (308.10 to 312.10) between axis (7-9)/(F-K) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43088 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1280 | Check RFT for columns from level (312.10 to 316.10) between axis (5-6)/(E-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1281 | Check formwork for columns from level (312.10 to 316.10) between axis (5-6)/(E-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1282 | Pouring request for columns from level (312.10 to 316.10) between axis (5-6)/(E-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43088 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1283 | Check RFT for columns from level (308.10 to 312.10) between axis (11-14)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43088 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1284 | Check formwork for columns from level (308.10 to 312.10) between axis (11-14)/(F-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43088 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1285 | Pouring request for columns from level (308.10 to 312.10) between axis (11-14) / (F-L)for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43088 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1286 | Check bottom reinforcement for R.C slab between axes (13-15) &(A-E) with (TOC = 308.10 )for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1287 | Check TOP reinforcement for R.C slab between axes (13-15) &(A-E) with (TOC = 308.10 )for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1288 | Pouring request for R.C slab between axes (13-15) &(A-E) with (TOC = 308.10 )for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1289 | Check bottom reinforcement for R.C slab between axes (14-18) &(D-F) with (TOC = 304.10 )for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1290 | Check TOP reinforcement for R.C slab between axes (14-18) &(D-F) with (TOC = 304.10 for area (Z1) As Per Attached Sketch | STR | Reinforcement | Reinforcement | GF | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1291 | Pouring request for R.C slab between axes (14-18) &(D-F) with (TOC = 304.10 for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1292 | Check bottom reinforcement for R.C slab between axes (1-5) &(D-F) with (TOC = 308.10 )for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1293 | Check TOP reinforcement for R.C slab between axes (1-5) &(D-F) with (TOC = 308.10 )for area (Z5) As Per Attached Sketch | STR | Reinforcement | Reinforcement | 1st | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1294 | Pouring request for R.C slab between axes (1-5) &(D-F) with (TOC = 308.10 )for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1295 | Check RFT for elevator and stair core walls from level (308.10 to 312.10) between axis (10-13)/(H - J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1296 | Check formwork for elevator and stair core walls from level (308.10 to 312.10) between axis (10-13)/(H - J) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43089 | 43097 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1297 | Pouring Request for elevator and stair core walls from level (308.10 to 312.10) between axis (10-13)/(H - J) for area (Z3 As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1298 | Check RFT for elevator and stair core walls from level (304.10 to 308.10) between axis (14-17)/(B - E) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1299 | Check formwork for elevator and stair core walls from level (304.10 to 308.10) between axis (14-17)/(B - E) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43089 | 43097 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1300 | Pouring Request for elevator and stair core walls from level (304.10 to 308.10) between axis (14-17)/(B - E) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1301 | Check RFT for columns And elevator and stair core wall from level (308.10 to 312.10) between axis (15 - 18)/(F-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1302 | Check formwork for columns And elevator and stair core wall from level (308.10 to 312.10) between axis (15 - 18)/(F-J) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43089 | 43097 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1303 | Pouring request for columns And elevator and stair core wall from level (308.10 to 312.10) between axis (15 - 18)/(F-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43089 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1304 | Check bottom reinforcement for R.C slab between axes (11-15) &(H-L) with (TOC = 312.10 )for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1305 | Check TOP reinforcement for R.C slab between axes (11-15) &(H-L) with (TOC = 312.10 )for area (Z3 As Per Attached Sketch | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1306 | Pouring request for R.C slab between axes (11-15) &(H-L) with (TOC = 312.10 )for area (Z3 As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1307 | Check bottom reinforcement for R.C slab between axes (6-9) &(F-L) with (TOC = 312.10 )for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1308 | Check TOP reinforcement for R.C slab between axes (6-9) &(F-L) with (TOC = 312.10 ) for area (Z3 As Per Attached Sketch | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1309 | Pouring request for R.C slab between axes (6-9) &(F-L) with (TOC = 312.10 ) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1310 | Check bottom reinforcement for R.C slab between axes (1-3) & (A-E) with (TOC = 312.10 )for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1311 | Check TOP reinforcement for R.C slab between axes (1-3) & (A-E) with (TOC = 312.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1312 | Pouring request for R.C slab between axes (1-3) & (A-E) with (TOC = 312.10 )for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1313 | Check bottom reinforcement for R.C slab between axes (6-9) & (F-L) with (TOC = 312.10 )for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1314 | Check TOP reinforcement for R.C slab between axes (6-9) & (F-L) with (TOC = 312.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1315 | Pouring request for R.C slab between axes (6-9) & (F-L) with (TOC = 312.10 )for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1316 | Check bottom reinforcement for R.C slab between axes (15-18) & (F-K) with (TOC = 312.10 )for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1317 | Check TOP reinforcement for R.C slab between axes (15-18) & (F-K) with (TOC = 312.10 )for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1318 | Pouring request for R.C slab between axes (15-18) & (F-K) with (TOC = 312.10 )for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1319 | Check bottom reinforcement for R.C slab between axes (13-18) & (A-D) with (TOC = 308.10 )for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1320 | Check TOP reinforcement for R.C slab between axes (13-18) & (A-D) with (TOC = 308.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 1st | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1321 | Pouring request for R.C slab between axes (13-18) & (A-D) with (TOC = 308.10 )for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1322 | Check bottom reinforcement for R.C slab between axes (2-5) & (E - G) with (TOC = 308.10 )for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1323 | Check TOP reinforcement for R.C slab between axes (2-5) & (E - G) with (TOC = 308.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 1st | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1324 | Pouring request for R.C slab between axes (2-5) & (E - G) with (TOC = 308.10 )for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1325 | Check bottom reinforcement for R.C slab between axes (2-6) & (A-E) with (TOC = 312.10 )for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1326 | Check TOP reinforcement for R.C slab between axes (2-6) & (A-E) with (TOC = 312.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1327 | Pouring request for R.C slab between axes (2-6) & (A-E) with (TOC = 312.10 )for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1328 | Check bottom reinforcement for R.C slab between axes (14-18) & (H-L) with (TOC = 312.10 )for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1329 | Check TOP reinforcement for R.C slab between axes (14-18) & (H-L) with (TOC = 312.10 )for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1330 | Pouring request for R.C slab between axes (14-18) & (H-L) with (TOC = 312.10 )for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1331 | Check bottom reinforcement for R.C slab between axes (2-5) & (F-L) with (TOC = 312.10 )for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1332 | Check TOP reinforcement for R.C slab between axes (2-5) & (F-L) with (TOC = 312.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1333 | Pouring request for R.C slab between axes (2-5) & (F-L) with (TOC = 312.10 )for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1334 | Check Top level for slab between axes (10 - 13) & ( F- j ) with (TOC = 312.10 ) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1335 | Check Top level for slab between axes (1 - 3) & ( L- G ) with (TOC = 304.10 ) - PART (P4) As Per Attached Sketch. | STR | Levels | Levels | GF | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1336 | Check Top level for slab between axes (6-8) & ( F- L ) with (TOC = 316.10 ) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | 3rd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1337 | Check Top level for slab between axes (13-18 ) & ( G - L ) with (TOC = 316.10 ) - PART (P2) As Per Attached Sketch. | STR | Levels | Levels | 3rd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1338 | Check Top level for slab between axes (1-6 ) & ( A-C ) with (TOC = 316.10 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | 3rd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1339 | Offset 50cm for columns at axies (K-H / 5-6) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1340 | Offset 50cm for columns at axies (K-G / 5-7) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1341 | Offset 50cm for columns at axies (E-F / 1-5) for area (P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1342 | Offset 50cm for columns at axies (F-J / 16-17) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1343 | Offset 50cm for columns at axies (A-D / 1-2) for area (P5) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1344 | Offset 50cm for columns at axies (K- G/ 3-4) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1345 | Offset 50cm for columns at axies (K- F/ 10-12) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1346 | Offset 50cm for columns at axies (D- F/ 15-17) for area (P1) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1347 | Check bottom reinforcement for R.C slab between axes (4-6) & (G-L) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1348 | Check TOP reinforcement for R.C slab between axes (4-6) & (G-L) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1349 | Pouring request for R.C slab between axes (4-6) & (G-L) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1350 | Check bottom reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 300.10 )for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1351 | Check TOP reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 300.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B1 | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1352 | Pouring request for R.C slab between axes (1-3) & (G-L) with (TOC = 300.10 )for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1353 | Check bottom reinforcement for R.C slab between axes (14-16) & (F-K) with (TOC = 312.10 )for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1354 | Check TOP reinforcement for R.C slab between axes (14-16) & (F-K) with (TOC = 312.10 )for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1355 | Pouring request for R.C slab between axes (14-16) & (F-K) with (TOC = 312.10 )for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43093 | 43097 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1356 | Check bottom reinforcement for R.C slab between axes (11-15) & (F-J) with (TOC = 312.10 )for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1357 | Check TOP reinforcement for R.C slab between axes (11-15) & (F-J) with (TOC = 312.10 )for area (Z3)As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1358 | Pouring request for R.C slab between axes (11-15) & (F-J) with (TOC = 312.10 )for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1359 | Check bottom reinforcement for R.C slab between axes (13-18) & (A-C) with (TOC = 308.10 )for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1360 | Check TOP reinforcement for R.C slab between axes (13-18) & (A-C) with (TOC = 308.10 )for area (Z1)As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 1st | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1361 | Pouring request for R.C slab between axes (13-18) & (A-C) with (TOC = 308.10 )for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1362 | Check RFT for elevator & stair core walls from level (312.10 to 316.10) between axis (6-9)/(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1363 | Check formwork for elevator & stair core walls from level (312.10 to 316.10) between axis (6-9)/(H-J) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1364 | Pouring request for elevator & stair core walls from level (312.10 to 316.10) between axis (6-9)/(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1365 | Check RFT for Columns & stair core walls from level (312.10 to 316.10) between axis (1-6)/(A-D) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1366 | Check formwork for Columns & stair core walls from level (312.10 to 316.10) between axis (1-6)/(A-D) for area (Z5 As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1367 | Pouring request for Columns & stair core walls from level (312.10 to 316.10) between axis (1-6)/(A-D) for area (Z5 As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1368 | Check RFT for Columns from level (300.10 to 304.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1369 | Check formwork for Columns from level (300.10 to 304.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43096 | 43104 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1370 | Pouring request for Columns from level (300.10 to 304.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1371 | Check bottom reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 304.10 )for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1372 | Check TOP reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 304.10 )for area (Z4)As Per Attached Sketch . | STR | Reinforcement | Reinforcement | GF | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1373 | Pouring request for R.C slab between axes (1-3) & (G-L) with (TOC = 304.10 )for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1374 | Check bottom reinforcement for R.C slab between axes (1-3) & (G-H) with (TOC = 295.60 )for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1375 | Check TOP reinforcement for R.C slab between axes (1-3) & (G-H) with (TOC = 295.60 )for area (Z4))As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B2 | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1376 | Pouring request for R.C slab between axes (1-3) & (G-H) with (TOC = 295.60 )for area (Z4)As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1377 | Check bottom reinforcement for R.C slab between axes (1-6) & (C-F) with (TOC = 312.10 )for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1378 | Check TOP reinforcement for R.C slab between axes (1-6) & (C-F) with (TOC = 312.10 )for area (Z5)As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1379 | Pouring request for R.C slab between axes (1-6) & (C-F) with (TOC = 312.10 )for area (Z5)As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1380 | Check RFT for Columns from level (304.10 to 308.10) between axis (13-18)/(B-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43096 | 43104 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1381 | Check formwork for Columns from level(304.10 to 308.10) between axis (13-18)/(B-F) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43096 | 43104 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1382 | Pouring request for Columns from level (304.10 to 308.10) between axis (13-18)/(B-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43096 | 43104 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1383 | Check bottom reinforcement for R.C slab between axes (13-18) & (C-F) with (TOC = 308.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 1st | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1384 | Check TOP reinforcement for R.C slab between axes (13-18) & (C-F) with (TOC = 308.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 1st | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1385 | Pouring request for R.C slab between axes (13-18) & (C-F) with (TOC = 308.10 )for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 1st | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1386 | Check bottom reinforcement for R.C slab between axes (10-14) & (F-L) with (TOC = 312.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1387 | Check TOP reinforcement for R.C slab between axes (10-14) & (F-L) with (TOC = 312.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1388 | Pouring request for R.C slab between axes (10-14) & (F-L) with (TOC = 312.10 )for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 2nd | 43096 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1389 | Check bottom reinforcement for R.C slab between axes (14-17 & (E-G) with (TOC = 312.10 )for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1390 | Check TOP reinforcement for R.C slab between axes (14-17 & (E-G) with (TOC = 312.10 )for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1391 | Pouring request for R.C slab between axes (14-17 & (E-G) with (TOC = 312.10 )for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | 2nd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1392 | Check RFT for Columns & elevator & stair core walls from level (308.10 to 312.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43097 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1393 | Check formwork for Columns & elevator & stair core walls from level (308.10 to 312.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43097 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1394 | Pouring request for Columns & elevator & stair core walls from level (308.10 to 312.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43097 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1395 | Check RFT for Columns from level (308.10 to 312.10) between axis (1-4)/(E-G) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1396 | Check formwork for Columns from level (308.10 to 312.10) between axis (1-4)/(E-G) for area (Z4)As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1397 | Pouring request for Columns from level (308.10 to 312.10) between axis (1-4)/(E-G) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1398 | Check RFT for Columns & stair core walls from level (312.10 to 316.10) between axis (1-4)/(E-F) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1399 | Check formwork for Columns & stair core walls from level (312.10 to 316.10) between axis (1-4)/(E-F) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1400 | Pouring request for Columns & stair core walls from level(312.10 to 316.10) between axis (1-4)/(E-F) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1401 | Check bottom reinforcement for R.C slab between axes (2-5) & (E-G) with (TOC = 312.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1402 | Check TOP reinforcement for R.C slab between axes (2-5) & (E-G) with (TOC = 312.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1403 | Pouring request for R.C slab between axes (2-5) & (E-G) with (TOC = 312.10 )for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 2nd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1404 | Check bottom reinforcement for R.C slab between axes (1-6) & (A-E) with (TOC = 316.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1405 | Check TOP reinforcement for R.C slab between axes axes (1-6) & (A-E) with (TOC = 316.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1406 | Pouring request for R.C slab between axes axes (1-6) & (A-E) with (TOC = 316.10 )for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1407 | Check RFT for Columns & elevator & stair core walls from level (312.10 to 316.10) between axis (15-18)/(G_L) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1408 | Check formwork for Columns & elevator & stair core walls from level (312.10 to 316.10) between axis (15-18)/(G_L) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1409 | Pouring request for Columns & elevator & stair core walls from level (312.10 to 316.10) between axis (15-18)/(G_L) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1410 | Check bottom reinforcement for R.C slab between axes (14-18) & (G-L) with (TOC = 316.10 )for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1411 | Check TOP reinforcement for R.C slab between axes axes (14-18) & (G-L) with (TOC = 316.10 )for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1412 | Pouring request for R.C slab between axes axes (14-18) & (G-L) with (TOC = 316.10 )for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43097 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1413 | Check Top level for slab between axes (1-2) & ( F- G ) with (TOC = 300.10 ) - PART (P4) As Per Attached Sketch. | STR | Levels | Levels | B1 | 43100 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1414 | Check Top level for slab between axes (1-3) & ( G-L ) with (TOC = 312.10 ) - PART (P4) As Per Attached Sketch. | STR | Levels | Levels | 2nd | 43100 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1415 | Check Top level for slab between axes (13-14) & ( A-D ) with (TOC = 295.60 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | B2 | 43100 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1416 | Check Top level for slab between axes (16-17) & ( C-E ) with (TOC = 312.10 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | 2nd | 43100 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1417 | Check Top level for slab between axes (3-4) & ( K-F ) with (TOC = 316.10 ) - PART (P4) As Per Attached Sketch. | STR | Levels | Levels | 3rd | 43100 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1418 | Check Top level for slab between axes (10-14) & ( F-H) with (TOC = 316.10 ) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | 3rd | 43100 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1419 | Check Top level for slab between axes (1-5) & ( C-F) with (TOC = 316.10 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | 3rd | 43100 | 43104 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1420 | Check Top level for slab between axes (10-17) & ( F-L) with (TOC = 316.10 ) - PART (P2&P3) As Per Attached Sketch. | STR | Levels | Levels | 3rd | 43100 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1421 | Check Top level for slab between axes (7-9) & ( F-L) with (TOC = 316.10 ) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | 3rd | 43100 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1422 | Check Top level for slab between axes (13-14) & (A-E) with (TOC = 312.10 ) - PART (P1) As Per Attached Sketch. | STR | Levels | Levels | 2nd | 43100 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1423 | Check Top level for slab between axes (5-6) & (L-F) with (TOC = 320.10 ) - PART (P4) As Per Attached Sketch. | STR | Levels | Levels | 4th | 43100 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1424 | Offset 50 cm for columns at axies ( F-G / 11-14 ) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out | 4th | 43100 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1425 | Check RFT for columns from level (312.10.10 to 316.10) between axis (7-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1426 | Check formwork fo columns from level (312.10.10 to 316.10) between axis (7-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1427 | Pouring request for columns from level (312.10.10 to 316.10) between axis (7-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1428 | Check RFT for columns from level (316.10.10 to 320.10) between axis (1-6)/(A-D) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1429 | Check formwork fo columns from level (316.10.10 to 320.10) between axis (1-6)/(A-D) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1430 | Pouring request for columns from level (316.10.10 to 320.10) between axis (1-6)/(A-D) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1431 | Check RFT for columns from level (316.10.10 to 320.10) between axis (5-6)/(H-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1432 | Check formwork fo columns from level (316.10.10 to 320.10) between axis (5-6)/(H-L) for area (Z3 As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1433 | Pouring request for columns from level (316.10.10 to 320.10) between axis (5-6)/(H-L) for area (Z3 As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1434 | Check RFT for columns from level (312.10.10 to 316.10) between axis (15-18) / (E-H) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1435 | Check formwork fo columns from level (312.10.10 to 316.10) between axis (15-18) / (E-H) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1436 | Pouring request for columns from level (312.10.10 to 316.10) between axis (15-18) / (E-H) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1437 | Check RFT for columns from level (304.10.10 to 308.10) between axis (1-2) / (H-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1438 | Check formwork fo columns from level (304.10.10 to 308.10) between axis (1-2) / (H-L) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1439 | Pouring request for columns from level (304.10.10 to 308.10) between axis (1-2) / (H-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1440 | Check bottom reinforcement for R.C slab between axes (4-8) & (E-L) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1441 | Check TOP reinforcement for R.C slab between axes (4-8) & (E-L) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1442 | Pouring request for R.C slab between axes axes (4-8) & (E-L) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1443 | Check bottom reinforcement for R.C slab between axes (7-9) & (F-L) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1444 | Check TOP reinforcement for R.C slab between axes(7-9) & (F-L) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1445 | Pouring request for R.C slab between axes axes(7-9) & (F-L) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1446 | Check bottom reinforcement for R.C slab between axes (4-6) & (G-l) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1447 | Check TOP reinforcement for R.C slab between axes (4-6) & (G-l) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1448 | Pouring request for R.C slab between axes (4-6) & (G-l) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1449 | Check bottom reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 308.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 1st | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1450 | Check TOP reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 308.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 1st | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1451 | Pouring request for R.C slab between axes (1-3) & (G-L) with (TOC = 308.10 )for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 1st | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1452 | Check bottom reinforcement for R.C slab between axes (14-18) & (A-C) with (TOC = 312.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1453 | Check TOP reinforcement for R.C slab between axes (14-18) & (A-C) with (TOC = 312.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1454 | Pouring request for R.C slab between axes (14-18) & (A-C) with (TOC = 312.10 )for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 2nd | 43101 | 43104 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1455 | Check RFT for retaining wall from level (295.60.10 to 300.10) between axis (1-2 / (F-H) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1456 | Check formwork fo retaining walls from level (295.60.10 to 300.10) between axis (1-2 / (F-H) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1457 | Pouring request for retaining wall from level (295.60.10 to 300.10) between axis (1-2 / (F-H) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1458 | Check RFT for columns from level (312.10.10 to 316.10) between axis (10-14) / (E-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1459 | Check formwork fo columns from level (312.10.10 to 316.10) between axis (10-14) / (E-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1460 | Pouring request for columns from level (312.10.10 to 316.10) between axis (10-14) / (E-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1461 | Check RFT for elevator & stair core walls from level (312.10 to 316.10) between axis (10-13)/(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1462 | Check formwork for elevator & stair core walls from level (312.10 to 316.10) between axis (10-13)/(H-J) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1463 | Pouring request for elevator & stair core walls from level (312.10 to 316.10) between axis (10-13)/(H-J) for area (Z3)As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1464 | Check bottom reinforcement for R.C slab between axes (10-17) & (F-L) with (TOC = 316.10 )for area (Z2&Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1465 | Check TOP reinforcement for R.C slab between axes (10-17) & (F-L) with (TOC = 316.10 )for area (Z2&Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1466 | Pouring request for R.C slab between axes (10-17) & (F-L) with (TOC = 316.10 )for area (Z2&Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1467 | Check bottom reinforcement for R.C slab between axes (10-15) & (F-H) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1468 | Check TOP reinforcement for R.C slab between axes (10-15) & (F-H) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1469 | Pouring request for R.C slab between axes (10-15) & (F-H) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1470 | Check bottom reinforcement for R.C slab between axes (14-18) & (E-H) with (TOC = 316.10 )for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1471 | Check TOP reinforcement for R.C slab between axes (14-18) & (E-H) with (TOC = 316.10 )for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1472 | Pouring request for R.C slab between axes (14-18) & (E-H) with (TOC = 316.10 )for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43102 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1473 | FIRST Primer coat for Raft and blockwork under S.O.G between axis (1-7)/(A-E) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43103 | 43109 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1474 | Second Primer coat for Raft and blockwork under S.O.G between axis (1-7)/(A-E) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43103 | 43109 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1475 | Check RFT for Columns& elevator & stair core walls from level (312.10 to 316.10) between axis (2-5)/(G-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43103 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1476 | Check formwork for Columns& elevator & stair core walls from level (312.10 to 316.10) between axis (2-5)/(G-L) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43103 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1477 | Pouring request for Columns& elevator & stair core walls from level (312.10 to 316.10) between axis (2-5)/(G-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43103 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1478 | Check bottom reinforcement for R.C slab between axes (1-6) & (C-F) with (TOC = 316.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43103 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1479 | Check TOP reinforcement for R.C slab between axes (1-6) & (C-F) with (TOC = 316.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43103 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1480 | Pouring request for R.C slab between axes (1-6) & (C-F) with (TOC = 316.10 )for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43103 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1481 | Check bottom reinforcement for R.C slab between axes (2-5) & (F-L) with (TOC = 316.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43103 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1482 | Check TOP reinforcement for R.C slab between axes (2-5) & (F-L) with (TOC = 316.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43103 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1483 | Pouring request for R.C slab between axes (2-5) & (F-L) with (TOC = 316.10 )for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43103 | 43107 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1484 | Third Primer coat for Raft and blockwork under S.O.G between axis (1-7)/(A-E) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43104 | 43109 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1485 | Check bottom reinforcement for R.C slab between axes (1-3) & (F-H) with (TOC = 300.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B1 | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1486 | Check TOP reinforcement for R.C slab between axes (1-3) & (F-H) with (TOC = 300.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B1 | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1487 | Pouring request for R.C slab between axes (1-3) & (F-H) with (TOC = 300.10 )for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | B1 | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1488 | Check RFT for columns & Retainig wall from level (290.75 to 295.60) between axis (13-14)/(A-C) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1489 | Check formwork fo columns & Retainig wall from level (290.75 to 295.60) between axis (13-14)/(A-C) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B2 | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1490 | Pouring request for columns & Retainig wall from level (290.75 to 295.60) between axis (13-14)/(A-C) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1491 | Check bottom reinforcement for R.C slab between axes (13-14) & (A-B) with (TOC = 295.60 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B2 | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1492 | Check TOP reinforcement for R.C slab between axes (13-14) & (A-B) with (TOC = 295.60 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B2 | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1493 | Pouring request for R.C slab between axes (13-14) & (A-B) with (TOC = 295.60 )for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | B2 | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1494 | Check RFT for columns And elevator and stair core wall from level (316.10 to 320.10) between axis (1-6)/(B-F) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1495 | Check formwork for columns And elevator and stair core wall from level (316.10 to 320.10) between axis (1-6)/(B-F) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1496 | Pouring request for columns And elevator and stair core wall from level (316.10 to 320.10) between axis (1-6)/(B-F) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1497 | Check bottom reinforcement for R.C slab between axes (16-18) & (B-F) with (TOC = 312.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1498 | Check TOP reinforcement for R.C slab between axes (16-18) & (B-F) with (TOC = 312.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1499 | Pouring request for R.C slab between axes (16-18) & (B-F) with (TOC = 312.10 )for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 2nd | 43104 | 43109 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1500 | Check Top level for slab between axes (1-2) & ( G-L ) with (TOC = 312.10 ) - PART (P4) As Per Attached Sketch. | STR | Levels | Levels | 2nd | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1501 | Check Top level for slab between axes (14-17) & ( F-G ) with (TOC = 316.10 ) - PART (P2) As Per Attached Sketch. | STR | Levels | Levels | 3rd | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1502 | Check Top level for slab between axes (6-8) & ( L-F ) with (TOC = 320.10 ) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | 4th | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1503 | Check Top level for slab between axes (15-17) & ( L-G ) with (TOC = 320.10 ) - PART (P2) As Per Attached Sketch. | STR | Levels | Levels | 4th | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1504 | Check Top level for slab between axes (6-1) & ( D-F ) with (TOC = 320.10 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | 4th | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1505 | Check Top level for slab between axes (9-7) & ( L-F ) with (TOC = 320.10 ) - PART (P3) As Per Attached Sketch. | STR | Levels | Levels | 4th | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1506 | Check Top level for slab between axes (1-6) & ( A-E ) with (TOC = 320.10 ) - PART (P5) As Per Attached Sketch. | STR | Levels | Levels | 4th | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1507 | Offset 50cm for columns at axies (K-H / 5-6) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out | 4th | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1508 | Offset 50cm for columns at axies (K-G / 10-11) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out | 3rd | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1509 | Offset 50cm for columns at axies (C-F / 15-16) for area (P1) As Per Attached Sketch. | STR | Setting out | Setting out | 3rd | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1510 | Offset 50cm for columns at axies (k-H / 15-17) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out | 5th | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1511 | Offset 50cm for columns at axies (F-G / 1-2) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out | GF | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1512 | Offset 50cm for columns at axies (C-F/ 17-18) for area (P1) As Per Attached Sketch. | STR | Setting out | Setting out | 3rd | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1513 | Offset 50cm for columns at axies (K- G/ 13-4) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out | 4th | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1514 | Offset 50cm for columns at axies (A-C/ 13) for area (P1) As Per Attached Sketch. | STR | Setting out | Setting out | B2 | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1515 | Offset 50cm for columns at axies (L-G/ 17) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out | 5th | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1516 | Offset 50cm for columns at axies (B-D/ 2-5) for area (P5) As Per Attached Sketch. | STR | Setting out | Setting out | 5th | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1517 | Offset 50cm for columns at axies ( L-K / 11-14) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out | 5th | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1518 | Offset 50cm for columns at axies ( H-F / 15-17) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out | 4th | 43108 | 43111 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1519 | Check bottom reinforcement for R.C slab between axes (10-14) & (J-K) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1520 | Check TOP reinforcement for R.C slab between axes (10-14) & (J-K) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1521 | Pouring request for R.C slab between axes (10-14) & (J-K) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1522 | Check RFT for Columns from level (308.10 to 312.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1523 | Check formwork for Columns from level (308.10 to 312.10) between axis (1-2)/(H-L) for area (Z4)As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1524 | Pouring request for Columns from level (308.10 to 312.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43109 | 43123 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1525 | Check bottom reinforcement for R.C slab FOR Ramp between axes (8-9) & (F-L) at area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B2 | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1526 | Check TOP reinforcement for R.C slab FOR Ramp between axes (8-9) & (F-L) at area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B2 | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1527 | Pouring request for R.C slab FOR Ramp between axes (8-9) & (F-L) at area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | B2 | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1528 | Check bottom reinforcement for R.C slab between axes (10-12) & (F-L) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1529 | Check TOP reinforcement for R.C slab between axes (10-12) & (F-L) & (J-K) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1530 | Pouring request for R.C slab between axes (10-12) & (F-L) & (J-K) with (TOC = 316.10 )for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1531 | Check bottom reinforcement for R.C slab between axes (14-17) & (B-F) with (TOC = 312.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1532 | Check TOP reinforcement for R.C slab between axes (14-17) & (B-F) with (TOC = 312.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1533 | Pouring request for R.C slab between axes (14-17) & (B-F) with (TOC = 312.10 )for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 2nd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1534 | Check RFT for Columns from level (312.10 to 316.10) between axis (3-4) / (E-G) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1535 | Check formwork for Columns from level (312.10 to 316.10) between axis (3-4) / (E-G)for area (Z4)As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1536 | Pouring request for Columns from level (312.10 to 316.10) between axis (3-4) / (E-G) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1537 | Check bottom reinforcement for R.C slab between axes (2-5) & (E-G) with (TOC = 316.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1538 | Check TOP reinforcement for R.C slab between axes(2-5) & (E-G) with (TOC = 316.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1539 | Pouring request for R.C slab between axes (2-5) & (E-G) with (TOC = 316.10 )for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1540 | Check bottom reinforcement for R.C slab between axes (1-6) & (A-E) with (TOC = 320.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1541 | Check TOP reinforcement for R.C slab between axes (1-6) & (A-E) with (TOC = 320.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1542 | Pouring request for R.C slab between axes (1-6) & (A-E) with (TOC = 320.10 )for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1543 | Check RFT for Columns and elevator & stair core walls from level (316.10 to 320.10) between axis (14-18)/(F-L) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43109 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1544 | Check formwork for Columns and elevator & stair core walls from level (316.10 to 320.10) between axis (14-18)/(F-L) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43109 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1545 | Pouring request for Columns and elevator & stair core walls from level (316.10 to 320.10) between axis (14-18)/(F-L) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43109 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1546 | Check bottom reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 312.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1547 | Check TOP reinforcement for R.C slab between axes(1-3) & (G-L) with (TOC = 312.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1548 | Pouring request for R.C slab between axes (1-3) & (G-L) with (TOC = 312.10 )for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 2nd | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1549 | Check bottom reinforcement for R.C slab between axes (14-18) & (G-L) with (TOC = 320.10 )for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1550 | Check TOP reinforcement for R.C slab between axes (14-18) & (G-L) with (TOC = 320.10 )for area (Z2 As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1551 | Pouring request for R.C slab between axes (14-18) & (G-L) with (TOC = 320.10 )for area (Z2 As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43109 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1552 | Check RFT for columns from level (300.10.10 to 304.10) between axis (1-2)/(F-G) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43113 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1553 | Check formwork fo columns from level (300.10.10 to 304.10) between axis (1-2)/(F-G) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43113 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1554 | Pouring request for columns from level (300.10.10 to 304.10) between axis (1-2)/(F-G) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43113 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1555 | Check bottom reinforcement for R.C slab between axes (1-6) & (C-F) with (TOC = 320.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43113 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1556 | Check TOP reinforcement for R.C slab between axes (1-6) & (C-F) with (TOC = 320.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43113 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1557 | Pouring request for R.C slab between axes (1-6) & (C-F) with (TOC = 320.10 )for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43113 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1558 | Check bottom reinforcement for R.C slab between axes (1-3) & (F-C) with (TOC = 304.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | GF | 43113 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1559 | Check TOP reinforcement for R.C slab between axes (1-3) & (F-C) with (TOC = 304.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | GF | 43113 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1560 | Pouring request for R.C slab between axes (1-3) & (F-C) with (TOC = 304.10 )for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | GF | 43113 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1561 | Check RFT for Columns & elevator & stair core walls from level (316.10 to 320.10) between axis (5-9)/(L-E) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43113 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1562 | Check formwork for Columns & elevator & stair core walls from level (316.10 to 320.10) between axis (5-9)/(L-E) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43113 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1563 | Pouring request for Columns & elevator & stair core walls from level (316.10 to 320.10) between axis (5-9)/(L-E) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43113 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1564 | Check RFT for Columns from level (316.10 to 320.10) between axis (11-14)/(E-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43113 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1565 | Check formwork for Columns from level (316.10 to 320.10) between axis (11-14)/(E-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43113 | 43123 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1566 | Pouring request for Columns from level (316.10 to 320.10) between axis (11-14)/(E-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43113 | 43123 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1567 | Check bottom reinforcement for R.C slab between axes (10-15) & (J-L) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1568 | Check TOP reinforcement for R.C slab between axes (10-15) & (J-L) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1569 | Pouring request for R.C slab between axes (10-15) & (J-L) with (TOC = 320.10 )for area (Z3)As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1570 | Check bottom reinforcement for R.C slab between axes (4-8) & (E-L) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1571 | Check TOP reinforcement for R.C slab between axes (4-8) & (E-L) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1572 | Pouring request for R.C slab between axes (4-8) & (E-L) with (TOC = 320.10 )for area (Z3)As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1573 | Check bottom reinforcement for R.C slab between axes (7-9) & (E-L) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1574 | Check TOP reinforcement for R.C slab between axes (7-9) & (E-L) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1575 | Pouring request for R.C slab between axes (7-9) & (E-L) with (TOC = 320.10 )for area (Z3)As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1576 | Check bottom reinforcement for R.C slab between axes (13-17) & (F-K) with (TOC = 320.10 )for area (Z2&Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1577 | Check TOP reinforcement for R.C slab between axes (13-17) & (F-K) with (TOC = 320.10 )for area (Z2&Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1578 | Pouring request for R.C slab between axes (13-17) & (F-K) with (TOC = 320.10 )for area (Z2&Z3)As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1579 | Check RFT for Columns from level (312.10 to 316.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43116 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1580 | Check formwork for Columns from level (312.10 to 316.10) between axis (13-18)/(A-F) for area (Z1)As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43116 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1581 | Pouring request for Columns from level (312.10 to 316.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43116 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1582 | Check bottom reinforcement for R.C slab between axes (13-17) & (A-D) with (TOC = 316.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1583 | Check TOP reinforcement for R.C slab between axes (13-17) & (A-D) with (TOC = 316.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1584 | Pouring request for R.C slab between axes (13-17) & (A-D) with (TOC = 316.10 )for area (Z1)As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1585 | Check bottom reinforcement for R.C slab between axes (11-15) & (E-H) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1586 | Check TOP reinforcement for R.C slab between axes (11-15) & (E-H) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1587 | Pouring request for R.C slab between axes (11-15) & (E-H) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43116 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1588 | Check RFT for Columns and elevator & stair core walls from level (320.10 to 324.10) between axis (1-6)/(A-F) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1589 | Check formwork for Columns and elevator & stair core walls from level (320.10 to 324.10) between axis (1-6)/(A-F) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43118 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1590 | Pouring request for Columns and elevator & stair core walls from level (320.10 to 324.10) between axis (1-6)/(A-F) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43118 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1591 | Check RFT for elevator & stair core walls from level (312.10 to 316.10) between axis (14-17)/(B-E) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1592 | Check formwork for elevator & stair core walls from level(312.10 to 316.10) between axis (14-17)/(B-E) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43118 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1593 | Pouring request for elevator & stair core walls from level(312.10 to 316.10) between axis (14-17)/(B-E) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1594 | Check RFT for COLUMNS from level (312.10 to 316.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1595 | Check formwork for COLUMNS from level(312.10 to 316.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43118 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1596 | Pouring request for COLUMNS from level(312.10 to 316.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1597 | Check bottom reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 316.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1598 | Check TOP reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 316.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1599 | Pouring request for R.C slab between axes (1-3) & (G-L) with (TOC = 316.10 )for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1600 | Check bottom reinforcement for R.C slab between axes (13-18) & (A-E) with (TOC = 316.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1601 | Check TOP reinforcement for R.C slab between axes(13-18) & (A-E) with (TOC = 316.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1602 | Pouring request for R.C slab between axes (13-18) & (A-E) with (TOC = 316.10 )for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1603 | Check RFT for Columns and elevator & stair core walls from level (316.10 to 320.10) between axis (10-13)/(G-K) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1604 | Check formwork for Columns and elevator & stair core walls from level (316.10 to 320.10) between axis (10-13)/(G-K) for area (Z3)) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43118 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1605 | Pouring request for Columns and elevator & stair core walls from level (316.10 to 320.10) between axis (10-13)/(G-K) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43118 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1606 | Check RFT for COLUMNS from level (304.10 to 308.10) between axis (1-3)/(E-G) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1607 | Check formwork for COLUMNS from level (304.10 to 308.10) between axis (1-3)/(E-G) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1608 | Pouring request for COLUMNS from level (304.10 to 308.10) between axis (1-3)/(E-G) for area (Z4)As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1609 | Check bottom reinforcement for R.C slab between axes (1-3) & (E-H) with (TOC = 308.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 1st | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1610 | Check TOP reinforcement for R.C slab between axes(1-3) & (E-H) with (TOC = 308.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 1st | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1611 | Pouring request for R.C slab between axes(1-3) & (E-H) with (TOC = 308.10 )for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 2nd | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1612 | Check bottom reinforcement for R.C slab between axes (10-13) & (F-L) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1613 | Check TOP reinforcement for R.C slab between axes(10-13) & (F-L) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1614 | Pouring request for R.C slab between axes (10-13) & (F-L) with (TOC = 320.10 )for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43118 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1615 | Check RFT for COLUMNS from level (316.10 to 320.10) between axis (15-16)/(E-G) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43120 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1616 | Check formwork for COLUMNS from level(316.10 to 320.10) between axis (15-16)/(E-G) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43120 | 43123 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1617 | Pouring request for COLUMNS from level(316.10 to 320.10) between axis (15-16)/(E-G) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43120 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1618 | Check bottom reinforcement for R.C slab between axes (13-18) & (E-H) with (TOC = 320.10 )for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43120 | 43123 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1619 | Check TOP reinforcement for R.C slab between axes(13-18) & (E-H) with (TOC = 320.10 )for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43120 | 43123 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1620 | Pouring request for R.C slab between axes (13-18) & (E-H) with (TOC = 320.10 )for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43120 | 43123 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1621 | Check bottom reinforcement for R.C slab between axes (2-6) & (A-F) with (TOC = 324.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43120 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1622 | Check TOP reinforcement for R.C slab between axes(2-6) & (A-F) with (TOC = 324.10 )for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43120 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1623 | Pouring request for R.C slab between axes (2-6) & (A-F) with (TOC = 324.10 )for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43120 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1624 | Check bottom reinforcement for R.C slab between axes (14-18) & (B-F) with (TOC = 316.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43120 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1625 | Check TOP reinforcement for R.C slab between axes(14-18) & (B-F) with (TOC = 316.10 )for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43120 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1626 | Pouring request for R.C slab between axes (14-18) & (B-F) with (TOC = 316.10 )for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43120 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1627 | Check Top level for slab between axes (11-12) & ( A-C ) with (TOC = 300.10 ) - PART (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | B1 | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1628 | Check Top level for slab between axes (14-18) & ( H-L ) with (TOC = 324.10 ) - PART (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1629 | Check Top level for slab between axes (10-13) & ( F-L) with (TOC = 320.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 4th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1630 | Check Top level for slab between axes (3-4) & ( G-L) with (TOC = 320.10 ) - PART (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | 4th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1631 | Check Top level for slab between axes (5-6) & ( F-L) with (TOC = 324.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1632 | Check Top level for slab between axes (6-8) & ( L-F) with (TOC = 324.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1633 | Check Top level for slab between axes (2-4) & ( B-E) with (TOC = 324.10 ) - PART (P5) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1634 | Check Top level for slab between axes (3-5) & ( B-E) with (TOC = 324.10 ) - PART (P5) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1635 | Check Top level for slab between axes (12-15) & ( G-K) with (TOC = 324.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1636 | Check Top level for slab between axes (11-15) & ( N-J) with (TOC = 324.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1637 | Check Top level for slab between axes (1-3) & ( N-G) with (TOC = 316.10 ) - PART (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | 3rd | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1638 | Check Top level for slab between axes (13-18) & ( A-E) with (TOC = 316.10 ) - PART (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | 3rd | 43120 | 43122 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1639 | Check Top level for slab between axes (2-5) & ( E-G) with (TOC = 320.10 ) - PART (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | 4th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1640 | Offset 50cm for columns at axies (H-L / 16-18) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out | 6th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1641 | Offset 50cm for columns at axies (F-L / 5-6) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out | 6th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1642 | Offset 50cm for columns at axies (K-L / 10-14) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out | 6th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1643 | Offset 50cm for columns at axies (F-K / 10-13) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out | 5th | 43120 | 43122 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1644 | Offset 50cm for columns at axies (F-G / 14-17) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out | 5th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1645 | Offset 50cm for columns at axies (G-K / 3-4) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out | 5th | 43120 | 43122 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1646 | Check RFT for Columns from level (320.10 to 324.10) between axis (5-6)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1647 | Check formwork for Columns from level (320.10 to 324.10) between axis (5-6)/(F-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1648 | Pouring request for Columns from level (320.10 to 324.10) between axis (5-6)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1649 | Check bottom reinforcement for R.C slab between axes (4-6) & (E-L) with (TOC = 324.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1650 | Check TOP reinforcement for R.C slab between axes (4-6) & (E-L) with (TOC = 324.10 )for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1651 | Pouring request for R.C slab between axes (4-6) & (E-L) with (TOC = 324.10 )for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1652 | Check RFT for Columns and elevator & stair core walls from level (316.10 to 320.10) between axis (2-5)/(E-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1653 | Check formwork for Columns and elevator & stair core walls from level (316.10 to 320.10) between axis (2-5)/(E-L) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43121 | 43123 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1654 | Pouring request for Columns and elevator & stair core walls from level (316.10 to 320.10) between axis (2-5)/(E-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43121 | 43123 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1655 | Check bottom reinforcement for R.C slab between axes (2-5) & (F-L) with (TOC = 320.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1656 | Check TOP reinforcement for R.C slab between axes (2-5) & (F-L) with (TOC = 320.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1657 | Pouring request for R.C slab between axes (2-5) & (F-L) with (TOC = 320.10 )for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1658 | Check bottom reinforcement for R.C slab between axes (2-5) & (E-G) with (TOC = 320.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1659 | Check TOP reinforcement for R.C slab between axes (2-5) & (E-G) with (TOC = 320.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1660 | Pouring request for R.C slab between axes (2-5) & (E-G) with (TOC = 320.10 )for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1661 | Check RFT for Columns from level (316.10 to 320.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1662 | Check formwork for Columns from level (316.10 to 320.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1663 | Pouring request for Columns from level (316.10 to 320.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1664 | Check bottom reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 320.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1665 | Check TOP reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 320.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1666 | Pouring request for R.C slab between axes (1-3) & (G-L) with (TOC = 320.10 )for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1667 | Check RFT for Columns from level (320.10 to 324.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1668 | Check formwork for Columns from level (320.10 to 324.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1669 | Pouring request for Columns from level (320.10 to 324.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1670 | Check RFT for Columns and elevator & stair core walls from level (320.10 to 324.10) between axis (2-5)/(G-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1671 | Check formwork for Columns and elevator & stair core walls from level (320.10 to 324.10) between axis (2-5)/(G-L) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43121 | 43123 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1672 | Pouring request for Columns and elevator & stair core walls from level (320.10 to 324.10) between axis (2-5)/(G-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43121 | 43123 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1673 | Check RFT for Columns from level (308.10 to 312.10) between axis (1-2)/(E-G) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1674 | Check formwork for Columns from level (308.10 to 312.10) between axis (1-2)/(E-G) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1675 | Pouring request for Columns from level (308.10 to 312.10) between axis (1-2)/(E-G) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1676 | Check bottom reinforcement for R.C slab between axes (1-3) & (E-H) with (TOC = 312.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1677 | Check TOP reinforcement for R.C slab between axes (1-3) & (E-H) with (TOC = 312.10 )for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1678 | Pouring request for R.C slab between axes (1-3) & (E-H) with (TOC = 312.10 )for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 2nd | 43121 | 43123 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1679 | Check RFT for Columns from level (320.10 to 324.10) between axis (15-18)/(H-L) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1680 | Check formwork for Columns from level (320.10 to 324.10) between axis (15-18)/(H-L) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43123 | 43134 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1681 | Pouring request for Columns from level (320.10 to 324.10) between axis (15-18)/(H-L) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1682 | Check bottom reinforcement for R.C slab between axes (14-18) & (G-L) with (TOC = 324.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1683 | Check TOP reinforcement for R.C slab between axes (14-18) & (G-L) with (TOC = 324.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1684 | Pouring request for R.C slab between axes (14-18) & (G-L) with (TOC = 324.10 ) for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1685 | Check bottom reinforcement for R.C slab between axes (1-5) & (A-F) with (TOC = 324.10 ) for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1686 | Check TOP reinforcement for R.C slab between axes (1-5) & (A-F) with (TOC = 324.10 ) for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1687 | Pouring request for R.C slab between axes (1-5) & (A-F) with (TOC = 324.10 ) for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1688 | Check RFT for Columns from level (320.10 to 324.10) between axis (10-14)/(J-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1689 | Check formwork for Columns from level (320.10 to 324.10) between axis (10-14)/(J-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1690 | Pouring request for Columns from level (320.10 to 324.10) between axis (10-14)/(J-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1691 | Check bottom reinforcement for R.C slab between axes (10-15) & (J-L) with (TOC = 324.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1692 | Check TOP reinforcement for R.C slab between axes (10-15) & (J-L) with (TOC = 324.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1693 | Pouring request for R.C slab between axes (10-15) & (J-L) with (TOC = 324.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43123 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1694 | Check RFT for Columns & elevator & stair core walls from level (316.10 to 320.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43130 | 43134 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1695 | Check formwork for Columns & elevator & stair core walls from level (316.10 to 320.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43130 | 43134 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1696 | Pouring request for Columns & elevator & stair core walls from level (316.10 to 320.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43130 | 43134 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1697 | Check RFT for Columns & elevator & stair core walls from level (320.10 to 324.10) between axis (10-14)/(E-K) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1698 | Check formwork for Columns & elevator & stair core walls from level (320.10 to 324.10) between axis (10-14)/(E-K) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1699 | Pouring request for Columns & elevator & stair core walls from level (320.10 to 324.10) between axis (10-14)/(E-K) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1700 | Check bottom reinforcement for R.C slab between axes (2-5) & (F-L) with (TOC = 324.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1701 | Check TOP reinforcement for R.C slab between axes (2-5) & (F-L) with (TOC = 324.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1702 | Pouring request for R.C slab between axes (2-5) & (F-L) with (TOC = 324.10 ) for area (Z4)) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1703 | Check bottom reinforcement for R.C slab between axes (11-15) & (F-K) with (TOC = 324.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1704 | Check TOP reinforcement for R.C slab between axes (11-15) & (F-K) with (TOC = 324.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1705 | Pouring request for R.C slab between axes (11-15) & (F-K) with (TOC = 324.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1706 | Check bottom reinforcement for R.C slab between axes (13-18) & (A-E) with (TOC = 320.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1707 | Check TOP reinforcement for R.C slab between axes (13-18) & (A-E) with (TOC = 320.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1708 | Pouring request for R.C slab between axes (13-18) & (A-E) with (TOC = 320.10 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1709 | Check RFT for Columns & BEAM from level (295.60 to 300.10) between axis (13)/(A-D) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1710 | Check formwork for Columns & BEAM from level (295.60 to 300.10) between axis (13)/(A-D) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1711 | Pouring request for Columns & BEAM from level (295.60 to 300.10) between axis (13)/(A-D) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1712 | Check bottom reinforcement for R.C slab between axes (13-14) & (A-D) with (TOC = 300.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B1 | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1713 | Check TOP reinforcement for R.C slab between axes (13-14) & (A-D) with (TOC = 300.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B1 | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1714 | Pouring request for R.C slab between axes (13-14) & (A-D) with (TOC = 300.10 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | B1 | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1715 | Check bottom reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 324.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1716 | Check TOP reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 324.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1717 | Pouring request for R.C slab between axes (1-3) & (G-L) with (TOC = 324.10 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1718 | Check RFT for Columns & elevator & stair core walls from level (320.10 to 324.10) between axis (6-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1719 | Check formwork for Columns & elevator & stair core walls from level (320.10 to 324.10) between axis (6-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1720 | Pouring request for Columns & elevator & stair core walls from level (320.10 to 324.10) between axis (6-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1721 | Check bottom reinforcement for R.C slab between axes (6-8) & (F-L) with (TOC = 324.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1722 | Check TOP reinforcement for R.C slab between axes (6-8) & (F-L) with (TOC = 324.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1723 | Pouring request for R.C slab between axes (6-8) & (F-L) with (TOC = 324.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1724 | Check bottom reinforcement for R.C slab between axes (7-9) & (E-L) with (TOC = 324.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1725 | Check TOP reinforcement for R.C slab between axes (7-9) & (E-L) with (TOC = 324.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1726 | Pouring request for R.C slab between axes (7-9) & (E-L) with (TOC = 324.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1727 | Check RFT for Columns & elevator core walls from level (320.10 to 324.10) between axis (14-18)/(E-K) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1728 | Check formwork for Columns & elevator core walls from level (320.10 to 324.10) between axis (14-18)/(E-K) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43130 | 43134 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1729 | Pouring request for Columns & elevator core walls from level (320.10 to 324.10) between axis (14-18)/(E-K) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43130 | 43134 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1730 | Check Top level for slab between axes (10-15) & (L-J) with (TOC = 328.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1731 | Check Top level for slab between axes (2-5) & (B-E) with (TOC = 328.10 ) - PART (P5) As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1732 | Check Top level for slab between axes (1-5) & (F-L) with (TOC = 328.10 ) - PART (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43135 | 43138 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1733 | Check Top level for slab between axes (7-8) & (F-L) with (TOC = 328.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1734 | Check Top level for slab between axes (10-12) & (F-K) with (TOC = 324.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1735 | Check Top level for slab between axes (1-3) & (L-G) with (TOC = 324.10 ) - PART (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1736 | Check Top level for slab between axes (2-5) & (E-F) with (TOC = 324.10 ) - PART (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43135 | 43138 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1737 | Check Top level for slab between axes (3-4) & (G-K) with (TOC = 324.10 ) - PART (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1738 | Check Top level for slab between axes (14-17) & (B-D) with (TOC = 324.10 ) - PART (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43135 | 43138 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1739 | Check Top level for slab between axes (12-14) & (E-G) with (TOC = 300.10 ) - PART (P2&P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | B1 | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1740 | Check Top level for slab between axes (5-6) & (F-K) with (TOC = 328.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1741 | Check Top level for slab between axes (15-18) & (L-H) with (TOC = 328.10 ) - PART (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1742 | Check Top level for slab between axes (15-17) & (E-C) with (TOC = 320.10 ) - PART (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | 4th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1743 | Check Top level for slab between axes (14-17) & (B-E) with (TOC = 320.10 ) - PART (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | 4th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1744 | Check Top level for slab between axes (2-3) & (G-F) with (TOC = 316.10 ) - PART (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | 3rd | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1745 | Offset 50cm for columns at axies (f-l / 5) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out | 7th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1746 | Offset 50cm for columns at axies (l-f /7-8) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out | 7th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1747 | Offset 50cm for columns at axies (G-K /2-4) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out | 7th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1748 | Offset 50cm for columns at axies (H-J/11) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out | 6th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1749 | Offset 50cm for columns at axies (L-H/11-17) for area (P3&P2) As Per Attached Sketch. | STR | Setting out | Setting out | 6th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1750 | Offset 50cm for columns at axies (L-K/7-8) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out | 6th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1751 | Offset 50cm for columns at axies (G-F/1-2) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out | 5th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1752 | Offset 50cm for columns at axies (G-F/1-2) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out | 4th | 43135 | 43138 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1753 | Check RFT for Columns & elevator & stair core walls from level (324.10 to 328.10) between axis (2-5)/(B-E) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1754 | Check formwork for Columns & elevator & stair core walls from level (324.10 to 328.10) between axis (2-5)/(B-E) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1755 | Pouring request for Columns & elevator & stair core walls from level (324.10 to 328.10) between axis (2-5)/(B-E) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1756 | Check bottom reinforcement for R.C slab between axes (2-5) & (A-F) with (TOC = 328.10 ) for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1757 | Check TOP reinforcement for R.C slab between axes (2-5) & (A-F) with (TOC = 328.10 ) for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1758 | Pouring request for R.C slab between axes (2-5) & (A-F) with (TOC = 328.10 ) for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1759 | Check RFT for Columns & elevator & stair core walls from level (324.10 to 328.10) between axis (5-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1760 | Check formwork for Columns & elevator & stair core walls from level (324.10 to 328.10) between axis (5-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1761 | Pouring request for Columns & elevator & stair core walls from level (324.10 to 328.10) between axis (5-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1762 | Check RFT for Columns & elevator & stair core walls from level (324.10 to 328.10) between axis (10-14)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1763 | Check formwork for Columns & elevator & stair core walls from level (324.10 to 328.10) between axis (10-14)/(F-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1764 | Pouring request for Columns & elevator & stair core walls from level (324.10 to 328.10) between axis (10-14)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1765 | Check RFT for Columns from level (324.10 to 328.10) between axis (15-18)/(H-L) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1766 | Check formwork for Columns from level (324.10 to 328.10) between axis (15-18)/(H-L) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1767 | Pouring request for Columns from level (324.10 to 328.10) between axis (15-18)/(H-L) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1768 | Check RFT for Columns from level (324.10 to 328.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1769 | Check formwork for Columns from level (324.10 to 328.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1770 | Pouring request for Columns from level (324.10 to 328.10) between axis (1-2)/(H-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1771 | Check RFT for Columns & elevator & stair core walls from level (324.10 to 328.10) between axis (2-5)/(G-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1772 | Check formwork for Columns & elevator & stair core walls from level (324.10 to 328.10) between axis (2-5)/(G-L) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1773 | Pouring request for Columns & elevator & stair core walls from level (324.10 to 328.10) between axis (2-5)/(G-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1774 | Check bottom reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 328.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1775 | Check TOP reinforcement for R.C slab between axes (1-3) & (G-L) with (TOC = 328.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1776 | Pouring request for R.C slab between axes (1-3) & (G-L) with (TOC = 328.10 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1777 | Check bottom reinforcement for R.C slab between axes (10-15) & (G-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1778 | Check TOP reinforcement for R.C slab between axes (10-15) & (G-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1779 | Pouring request for R.C slab between axes (10-15) & (G-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1780 | Check bottom reinforcement for R.C slab between axes (14-18) & (G-L) with (TOC = 328.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1781 | Check TOP reinforcement for R.C slab between axes (14-18) & (G-L) with (TOC = 328.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1782 | Pouring request for R.C slab between axes (14-18) & (G-L) with (TOC = 328.10 ) for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1783 | Check bottom reinforcement for R.C slab between axes (2-5) & (F-L) with (TOC = 328.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1784 | Check TOP reinforcement for R.C slab between axes (2-5) & (F-L) with (TOC = 328.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1785 | Pouring request for R.C slab between axes (2-5) & (F-L) with (TOC = 328.10 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1786 | Check bottom reinforcement for R.C slab between axes (4-6) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1787 | Check TOP reinforcement for R.C slab between axes (4-6) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1788 | Pouring request for R.C slab between axes (4-6) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1789 | Check bottom reinforcement for R.C slab between axes (6-8) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1790 | Check TOP reinforcement for R.C slab between axes (6-8) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1791 | Pouring request for R.C slab between axes (6-8) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1792 | Check bottom reinforcement for R.C slab between axes (7-9) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1793 | Check TOP reinforcement for R.C slab between axes (7-9) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1794 | Pouring request for R.C slab between axes (7-9) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1795 | Check RFT for Columns from level (312.10 to 316.10) between axis (1-2)/(E-G) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1796 | Check formwork for Columns from level (312.10 to 316.10) between axis (1-2)/(E-G) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1797 | Pouring request for Columns from level (312.10 to 316.10) between axis (1-2)/(E-G) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1798 | Check bottom reinforcement for R.C slab between axes (1-3) & (E-H) with (TOC = 316.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1799 | Check TOP reinforcement for R.C slab between axes (1-3) & (E-H) with (TOC = 316.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1800 | Pouring request for R.C slab between axes (1-3) & (E-H) with (TOC = 316.10 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43135 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1801 | FIRST Primer coat for Raft and blockwork under S.O.G between axis (2-7)/(E-L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43138 | 1/3/20118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1802 | Second Primer coat for Raft and blockwork under S.O.G between axis (2-7)/(E-L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43138 | 1/3/20118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1803 | Third Primer coat for Raft and blockwork under S.O.G between axis (2-7)/(E-L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43138 | 1/3/20118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1804 | FIRST Primer coat for Raft and blockwork under S.O.G between axis (6-13)/(F-L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43138 | 1/3/20118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1805 | Second Primer coat for Raft and blockwork under S.O.G between axis (6-13)/(F-L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43138 | 1/3/20118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1806 | Third Primer coat for Raft and blockwork under S.O.G between axis (6-13)/(F-L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43138 | 1/3/20118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1807 | FIRST Primer coat for Raft and blockwork under S.O.G between axis (12-18)/(E-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43138 | 1/3/20118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1808 | Second Primer coat for Raft and blockwork under S.O.G between axis (12-18)/(E-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43138 | 1/3/20118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1809 | Third Primer coat for Raft and blockwork under S.O.G between axis (12-18)/(E-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43138 | 1/3/20118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1810 | Check RFT for columns from level (300.10.10 to 304.10) between axis (A-C)/13 for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1811 | Check formwork fo columns from level (300.10.10 to 304.10) between axis (A-C)/13 for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43138 | 43144 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1812 | Pouring request for columns from level (300.10.10 to 304.10) between axis (A-C)/13 for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1813 | Check RFT for columns from level (316.10.10 to 320.10) between axis (1-2)/(E-G) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1814 | Check formwork fo columns from level (316.10.10 to 320.10) between axis (1-2)/(E-G) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43138 | 43144 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1815 | Pouring request for columns from level (316.10.10 to 320.10) between axis (1-2)/(E-G) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1816 | Check bottom reinforcement for R.C slab between axes (12-14) & (A-B) with (TOC = 304.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | GF | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1817 | Check TOP reinforcement for R.C slab between axes (12-14) & (A-B) with (TOC = 304.10 ) for area (Z1)As Per Attached Sketch . | STR | Reinforcement | Reinforcement | GF | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1818 | Pouring request for R.C slab between axes (12-14) & (A-B) with (TOC = 304.10 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | GF | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1819 | Check bottom reinforcement for R.C slab between axes (1-3) & (E-H) with (TOC = 320.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1820 | Check TOP reinforcement for R.C slab between axes (1-3) & (E-H) with (TOC = 320.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1821 | Pouring request for R.C slab between axes (1-3) & (E-H) with (TOC = 320.10 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1822 | Check bottom reinforcement for R.C slab between axes (14-18) & (E-H) with (TOC = 324.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1823 | Check TOP reinforcement for R.C slab between axes (14-18) & (E-H) with (TOC = 324.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1824 | Pouring request for R.C slab between axes (14-18) & (E-H) with (TOC = 324.10 ) for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1825 | Check RFT for Columns & elevator & stair core walls from level (320.10 to 324.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1826 | Check formwork for Columns & elevator & stair core walls from level (320.10 to 324.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43138 | 43144 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1827 | Pouring request for Columns & elevator & stair core walls from level (320.10 to 324.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1828 | Check bottom reinforcement for R.C slab between axes (13-16) & (A-E) with (TOC = 324.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1829 | Check TOP reinforcement for R.C slab between axes (13-16) & (A-E) with (TOC = 324.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1830 | Pouring request for R.C slab between axes (13-16) & (A-E) with (TOC = 324.10 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1831 | Check bottom reinforcement for R.C slab between axes (15-18) & (A-E) with (TOC = 324.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1832 | Check TOP reinforcement for R.C slab between axes (15-18) & (A-E) with (TOC = 324.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1833 | Pouring request for R.C slab between axes (15-18) & (A-E) with (TOC = 324.10 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43138 | 43144 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1834 | Check RFT for Columns from level (320.10 to 324.10) between axis (1-2)/(E-G) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1835 | Check formwork for Columns from level (320.10 to 324.10) between axis (1-2)/(E-G) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43139 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1836 | Pouring request for Columns from level (320.10 to 324.10) between axis (1-2)/(E-G) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1837 | Check RFT for Columns from level (304.10 to 308.10) between axis (A-C)/13 for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1838 | Check formwork for Columns from level (304.10 to 308.10) between axis (A-C)/13 for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43139 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1839 | Pouring request for Columns from level (304.10 to 308.10) between axis (A-C)/13 for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1840 | Check RFT for ParaPet from level (324.10 to 325.70) between axis(1-6)/ (A-f) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1841 | Check formwork for ParaPet from level (324.10 to 325.70) between axis(1-6)/ (A-f) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43139 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1842 | Pouring request for ParaPet from level (324.10 to 325.70) between axis(1-6)/ (A-f) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1843 | Check bottom reinforcement for R.C slab between axes (1-3) & (E-H) with (TOC = 324.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1844 | Check TOP reinforcement for R.C slab between axes (1-3) & (E-H) with (TOC = 324.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1845 | Pouring request for R.C slab between axes (1-3) & (E-H) with (TOC = 324.10 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1846 | Check bottom reinforcement for R.C slab between axes (12-14) & (A-D) with (TOC = 308.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 1st | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1847 | Check TOP reinforcement for R.C slab between axes (12-14) & (A-D) with (TOC = 308.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 1st | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1848 | Pouring request for R.C slab between axes (12-14) & (A-D) with (TOC = 308.10 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 1st | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1849 | Check bottom reinforcement for R.C slab between axes (8-9) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1850 | Check TOP reinforcement for R.C slab between axes (8-9) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1851 | Pouring request for R.C slab between axes (8-9) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43139 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1852 | Check RFT for Columns & elevator core walls from level (324.10 to 328.10) between axis (14-18)/(f-l) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1853 | Check formwork for Columns & elevator core walls from level (324.10 to 328.10) between axis (14-18)/(f-l) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1854 | Pouring request for Columns & elevator core walls from level (324.10 to 328.10) between axis (14-18)/(f-l) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1855 | Check RFT for Columns from level (324.10 to 328.10) between axis (1-3)/(E-H) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1856 | Check formwork for Columns from level (324.10 to 328.10) between axis (1-3)/(E-H) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1857 | Pouring request for Columns from level (324.10 to 328.10) between axis (1-3)/(E-H) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1858 | Check bottom reinforcement for R.C slab between axes (1-3) & (F-H) with (TOC = 328.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1859 | Check TOP reinforcement for R.C slab between axes (1-3) & (F-H) with (TOC = 328.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1860 | Pouring request for R.C slab between axes (1-3) & (F-H) with (TOC = 328.10 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1861 | Check bottom reinforcement for R.C slab between axes (10-15) & (E-H) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1862 | Check TOP reinforcement for R.C slab between axes (10-15) & (E-H) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1863 | Pouring request for R.C slab between axes (10-15) & (E-H) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1864 | Check bottom reinforcement for R.C slab between axes (14-18) & (F-H) with (TOC = 328.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1865 | Check TOP reinforcement for R.C slab between axes (14-18) & (F-H) with (TOC = 328.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1866 | Pouring request for R.C slab between axes (14-18) & (F-H) with (TOC = 328.10 ) for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1867 | Check bottom reinforcement for R.C slab between axes (14-17) & (B-E) with (TOC = 324.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1868 | Check TOP reinforcement for R.C slab between axes (14-17) & (B-E) with (TOC = 324.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1869 | Pouring request for R.C slab between axes (14-17) & (B-E) with (TOC = 324.10 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1870 | Check bottom reinforcement for R.C slab between axes (10-14) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1871 | Check TOP reinforcement for R.C slab between axes (10-14) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1872 | Pouring request for R.C slab between axes (10-14) & (F-L) with (TOC = 328.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1873 | Check RFT for Parapet from level (328.80 to 329.55) between axis (2-5)/(A-F) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1874 | Check formwork for Parapet from level (328.80 to 329.55) between axis (2-5)/(A-F) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43143 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1875 | Pouring request for Parapet from level (328.80 to 329.55) between axis (2-5)/(A-F) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1876 | Check RFT for Columns & elevator & stair core walls from level (328.10 to 333.10) between axis (1-5)/(F-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 7th | 43143 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1877 | Check formwork for Columns & elevator & stair core walls from level (328.10 to 333.10) between axis (1-5)/(F-L) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 7th | 43143 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1878 | Pouring request for Columns & elevator & stair core walls from level (328.10 to 333.10) between axis (1-5)/(F-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43143 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1879 | Check RFT for Columns & elevator & stair core walls from level (328.10 to 333.10) between axis (5-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 7th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1880 | Check formwork for Columns & elevator & stair core walls from level (328.10 to 333.10) between axis (5-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 7th | 43143 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1881 | Pouring request for Columns & elevator & stair core walls from level (328.10 to 333.10) between axis (5-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43143 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1882 | Check bottom reinforcement for R.C slab between axes (4-6) & (F-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1883 | Check TOP reinforcement for R.C slab between axes (4-6) & (F-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1884 | Pouring request for R.C slab between axes (4-6) & (F-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 7th | 43143 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1885 | Check Top level for slab between axes (2-4) & (K-G) with (TOC = 333.10 ) - PART (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | 7th | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1886 | Check Top level for slab between axes (6-8) & (L-F) with (TOC = 333.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 7th | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1887 | Check Top level for slab between axes (5-7) & (A-G) with (TOC = 333.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 7th | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1888 | Check Top level for slab between axes (1-2) & (F-G) with (TOC = 328.10 ) - PART (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1889 | Check Top level for slab between axes (10-13) & (F-K) with (TOC = 328.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1890 | Check Top level for slab between axes (8-9) & (K-G) with (TOC = 328.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1891 | Check Top level for slab between axes (14-17) & (F-H) with (TOC = 328.10 ) - PART (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1892 | Check Top level for slab between axes (1-3) & (F-G) with (TOC = 324.10 ) - PART (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1893 | Check Top level for slab between axes (13) & (A-D) with (TOC = 308.10 ) - PART (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | 1st | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1894 | Check Top level for slab between axes (13-14) & (E-G) with (TOC = 308.10 ) - PART (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | 1st | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1895 | Check Top level for slab between axes (13-14) & (E-G) with (TOC = 304.10 ) - PART (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | GF | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1896 | Offset 50cm for columns at axies (E-G/1-3) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1897 | Offset 50cm for columns at axies (F-G/11-12) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1898 | Offset 50cm for columns at axies (F-G/15-18) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1899 | Offset 50cm for columns at axies (K-F/10-13) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43145 | 1/3/20118 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1900 | FIRST Primer coat for Raft and blockwork under S.O.G between axis (14-18)/(A-F) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1901 | SECOND Primer coat for Raft and blockwork under S.O.G between axis (14-18)/(A-F) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1902 | Check bottom reinforcement for R.C slab between axes (1-5) & (F-L) with (TOC = 333.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1903 | Check TOP reinforcement for R.C slab between axes (1-5) & (F-L) with (TOC = 333.10 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1904 | Pouring request for R.C slab between axes (1-5) & (F-L) with (TOC = 333.10 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 7th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1905 | Check bottom reinforcement for R.C slab between axes (7-9) & (E-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1906 | Check TOP reinforcement for R.C slab between axes (7-9) & (E-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1907 | Pouring request for R.C slab between axes (7-9) & (E-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 7th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1908 | Check bottom reinforcement for R.C slab between axes (8-9) & (F-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1909 | Check TOP reinforcement for R.C slab between axes (8-9) & (F-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1910 | Pouring request for R.C slab between axes (8-9) & (F-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 7th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1911 | Check RFT for Columns from level (290.75 to 295.60) between axis (D-E)/13 for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1912 | Check formwork for Columns from level (290.75 to 295.60) between axis (D-E)/13 for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B2 | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1913 | Pouring request for Columns from level (290.75 to 295.60) between axis (D-E)/13 for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1914 | Check bottom reinforcement for R.C slab between axes (13-14) & (C-F) with (TOC = 295.60 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B2 | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1915 | Check TOP reinforcement for R.C slab between axes (13-14) & (C-F) with (TOC = 295.60 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B2 | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1916 | Pouring request for R.C slab between axes (13-14) & (C-F) with (TOC = 295.60 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | B2 | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1917 | Check RFT for stair core walls from level (320.10 to 324.10) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1918 | Check formwork for stair core walls from level (320.10 to 324.10) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1919 | Pouring request for stair core walls from level (320.10 to 324.10) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1920 | Check bottom reinforcement for R.C slab between axes (15-17) & (G-K) with (TOC = 324.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1921 | Check TOP reinforcement for R.C slab between axes (15-17) & (G-K) with (TOC = 324.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1922 | Pouring request for R.C slab between axes (15-17) & (G-K) with (TOC = 324.10 ) for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1923 | Check RFT for stair core walls from level (324.10 to 328.10) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1924 | Check formwork for stair core walls from level (324.10 to 328.10) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1925 | Pouring request for stair core walls from level (324.10 to 328.10) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1926 | Check bottom reinforcement for R.C slab between axes (15-17) & (G-H) with (TOC = 328.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1927 | Check TOP reinforcement for R.C slab between axes (15-17) & (G-H) with (TOC = 328.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1928 | Pouring request for R.C slab between axes (15-17) & (G-H) with (TOC = 328.10 ) for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43150 | 43156 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1929 | Check Top level for slab between axes (10-13) & (F-K) with (TOC = 333.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 7th | 43153 | 43158 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1930 | Check Top level for slab between axes (8-9) & (K-G) with (TOC = 333.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 7th | 43153 | 43158 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1931 | Check Top level for slab between axes (2-4) & (K-J) with (TOC = 333.10 ) - PART (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | 7th | 43153 | 43158 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1932 | Check Top level for slab between axes (10-15) & (L-G) with (TOC = 333.10 ) - PART (P2&P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 7th | 43153 | 43158 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1933 | Check Top level for slab between axes (15-16) & (J-G) with (TOC = 328.10 ) - PART (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43153 | 43158 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1934 | Check Top level for slab between axes (14) & (E-F) with (TOC = 316.10 ) - PART (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | 3rd | 43153 | 43158 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1935 | Check Top level for slab between axes (14) & (E-F) with (TOC = 312.10 ) - PART (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | 2nd | 43153 | 43158 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1936 | Check Top level for slab between axes (12-14) & (D-F) with (TOC = 300.10 ) - PART (P1&P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | B1 | 43153 | 43158 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1937 | Offset 50cm for columns at axies (L-F/6-9) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43153 | 43158 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1938 | Offset 50cm for columns at axies (G-K/2-5) for area (P4) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43153 | 43158 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1939 | Offset 50cm for columns at axies (K-F/10) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43153 | 43158 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1940 | Offset 50cm for columns at axies (K-F/11-15) for area (P3) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43153 | 43158 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1941 | Offset 50cm for columns at axies (G/15-17) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out |  | 43153 | 43158 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1942 | Check RFT for Columns & elevator & stair core walls from level (328.10 to 333.10) between axis (10-14)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 7th | 43157 | 43164 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1943 | Check formwork for Columns & elevator & stair core walls from level (328.10 to 333.10) between axis (10-14)/(F-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 7th | 43157 | 43164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1944 | Pouring request for Columns & elevator & stair core walls from level (328.10 to 333.10) between axis (10-14)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43157 | 43164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1945 | Check RFT for Columns & elevator & stair core walls from level (328.10 to 333.10) between axis (15-18)/(F-L) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 7th | 43157 | 43164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1946 | Check formwork for Columns & elevator & stair core walls from level (328.10 to 333.10) between axis (15-18)/(F-L) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 7th | 43157 | 43164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1947 | Pouring request for Columns & elevator & stair core walls from level (328.10 to 333.10) between axis (15-18)/(F-L) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43157 | 43164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1948 | Check RFT for Columns & elevator & stair core walls from level (324.10 to 328.80) between axis (14-17)/(A-E) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43157 | 43164 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1949 | Check formwork for Columns & elevator & stair core walls from level (324.10 to 328.80) between axis (14-17)/(A-E) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43157 | 43164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1950 | Pouring request for Columns & elevator & stair core walls from level (324.10 to 328.80) between axis (14-17)/(A-E) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43157 | 43164 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1951 | Check bottom reinforcement for R.C slab between axes (14-17) & (A-E) with (TOC = 328.80 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43157 | 43164 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1952 | Check TOP reinforcement for R.C slab between axes (14-17) & (A-E) with (TOC = 328.80 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43157 | 43164 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1953 | Pouring request for R.C slab between axes (14-17) & (A-E) with (TOC = 328.80 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43157 | 43164 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1954 | Check bottom reinforcement for R.C slab between axes (10-15) & (F-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43157 | 43164 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1955 | Check TOP reinforcement for R.C slab between axes (10-15) & (F-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43157 | 43164 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1956 | Pouring request for R.C slab between axes (10-15) & (F-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 7th | 43157 | 43164 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1957 | Check bottom reinforcement for R.C slab between axes (14-18) & (F-H) with (TOC = 333.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43157 | 43164 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1958 | Check TOP reinforcement for R.C slab between axes (14-18) & (F-H) with (TOC = 333.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43157 | 43164 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1959 | Pouring request for R.C slab between axes (14-18) & (F-H) with (TOC = 333.10 ) for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | 7th | 43157 | 43164 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1960 | Check bottom reinforcement for R.C slab between axes (10-12) & (E-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43157 | 43164 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1961 | Check TOP reinforcement for R.C slab between axes (10-12) & (E-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43157 | 43164 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1962 | Pouring request for R.C slab between axes (10-12) & (E-L) with (TOC = 333.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 7th | 43157 | 43164 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1963 | Check bottom reinforcement for R.C slab between axes (14-18) & (G-L) with (TOC = 333.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43157 | 43164 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1964 | Check TOP reinforcement for R.C slab between axes (14-18) & (G-L) with (TOC = 333.10 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43157 | 43164 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1965 | Pouring request for R.C slab between axes (14-18) & (G-L) with (TOC = 333.10 ) for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | 7th | 43157 | 43164 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1966 | Check RFT for Columns & Retaining wall from level (295.60 to 300.10) between axis (C-F)/13 for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43157 | 43164 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1967 | Check formwork for Columns & Retaining wall from level (295.60 to 300.10) between axis (C-F)/13 for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43157 | 43164 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1968 | Pouring request for Columns & Retaining wall from level (295.60 to 300.10) between axis (C-F)/13 for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43157 | 43164 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1969 | Check bottom reinforcement for R.C slab between axes (13-14) & (C-F) with (TOC = 300.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B1 | 43157 | 43164 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1970 | Check TOP reinforcement for R.C slab between axes (13-14) & (C-F) with (TOC = 300.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B1 | 43157 | 43164 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1971 | Pouring request for R.C slab between axes (13-14) & (C-F) with (TOC = 300.10 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | B1 | 43157 | 43164 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1972 | Check Top level for slab between axes (10-12) & (L-F) with (TOC = 344.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 9th | 43172 | 43174 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1973 | Check Top level for slab between axes (7-9) & (L-F) with (TOC = 344.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 9th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1974 | Check Top level for slab between axes (10-12) & (F-G) with (TOC = 338.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 8th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1975 | Check Top level for slab between axes (10-12) & (L-F) with (TOC = 338.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 8th | 43172 | 43174 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1976 | Check Top level for slab between axes (6-9) & (L-F) with (TOC = 338.10 ) - PART (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | 8th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1977 | Check Top level for slab between axes (15-18) & (H-K) with (TOC = 333.10 ) - PART (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | 7th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1978 | Check Top level for slab between axes (14-17) & (B-E) with (TOC = 328.10 ) - PART (P4)As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43172 | 43174 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1979 | Check Top level for slab between axes (13-15) & (D-F) with (TOC = 308.10 ) - PART (P2)As Per Attached Sketch. | STR | LEVELS | LEVELS | 1st | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1980 | Check Top level for slab between axes (13-14) & (D-E) with (TOC = 304.10 ) - PART (P1)As Per Attached Sketch. | STR | LEVELS | LEVELS | GF | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1981 | Check Top level for slab between axes (13-15) & (E-G) with (TOC = 320.10 ) - PART (P1)As Per Attached Sketch. | STR | LEVELS | LEVELS | 4th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1982 | Check formwork for stair from level (291.60 to 295.60) for area (Z4) As Per Attached Sketch. | STR | LEVELS | LEVELS | B2 | 43172 | 43174 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1983 | Check formwork for stair from level (291.60 to 295.60) for area (Z5) As Per Attached Sketch. | STR | LEVELS | LEVELS | B2 | 43172 | 43174 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1984 | Check RFT for Columns & elevator & stair core walls from level (333.10 to 338.10) between axis (6-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 8th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1985 | Check formwork for Columns & elevator & stair core walls from level (333.10 to 338.10) between axis (6-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 8th | 43172 | 43174 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1986 | Pouring request for Columns & elevator & stair core walls from level (333.10 to 338.10) between axis (6-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 8th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1987 | Check bottom reinforcement for R.C slab between axes (7-9) & (F-L) with (TOC = 338.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 8th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1988 | Check TOP reinforcement for R.C slab between axes (7-9) & (F-L) with (TOC = 338.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 8th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1989 | Pouring request for R.C slab between axes (7-9) & (F-L) with (TOC = 338.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 8th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1990 | Check RFT for Columns & elevator & stair core walls from level (333.10 to 338.10) between axis (10-13)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 8th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1991 | Check formwork for Columns & elevator & stair core walls from level (333.10 to 338.10) between axis (10-13)/(F-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 8th | 43172 | 43174 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1992 | Pouring request for Columns & elevator & stair core walls from level (333.10 to 338.10) between axis (10-13)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 8th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1993 | Check bottom reinforcement for R.C slab between axes (10-12) & (F-L) with (TOC = 338.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 8th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1994 | Check TOP reinforcement for R.C slab between axes (10-12) & (F-L) with (TOC = 338.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 8th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1995 | Pouring request for R.C slab between axes (10-12) & (F-L) with (TOC = 338.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 8th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1996 | Check RFT for Columns & elevator & stair core walls from level (338.10 to 344.10) between axis (6-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 9th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1997 | Check formwork for Columns & elevator & stair core walls from level (338.10 to 344.10) between axis (6-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 9th | 43172 | 43174 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1998 | Pouring request for Columns & elevator & stair core walls from level (338.10 to 344.10) between axis (6-9)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 9th | 43172 | 43174 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-1999 | Check bottom reinforcement for R.C slab between axes (7-9) & (F-L) with (TOC = 344.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 9th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2000 | Check TOP reinforcement for R.C slab between axes (7-9) & (F-L) with (TOC = 344.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 9th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2001 | Pouring request for R.C slab between axes (7-9) & (F-L) with (TOC = 344.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 9th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2002 | Check RFT for Columns & elevator & stair core walls from level (338.10 to 344.10) between axis (10-13)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 9th | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2003 | Check formwork for Columns & elevator & stair core walls from level (338.10 to 344.10) between axis (10-13)/(F-L) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 9th | 43172 | 43174 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2004 | Pouring request for Columns & elevator & stair core walls from level (338.10 to 344.10) between axis (10-13)/(F-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 9th | 43172 | 43174 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2005 | Check bottom reinforcement for R.C slab between axes (10-13) & (F-L) with (TOC = 344.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 9th | 43172 | 43183 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2006 | Check TOP reinforcement for R.C slab between axes (10-13) & (F-L) with (TOC = 344.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 9th | 43172 | 43183 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2007 | Pouring request for R.C slab between axes (10-13) & (F-L) with (TOC = 344.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 9th | 43172 | 43183 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2008 | FIRST Primer coat for Raft and blockwork under S.O.G between axis (6-13)/(F-H) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2009 | Second Primer coat for Raft and blockwork under S.O.G between axis (6-13)/(F-H) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43172 | 43174 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2010 | Third Primer coat for Raft and blockwork under S.O.G between axis(6-13)/(F-H) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43172 | 43174 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2011 | Third Primer coat for Raft and blockwork under S.O.G between axis (14-18)/(A-E) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43172 | 43174 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2012 | Check installation for PVC membrane arround columns at water tank as per attached drawing | STR | water proofing | water proofing | B2 | 43172 | 43174 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2013 | Check RFT for Columns from level (312.10 to 316.10) between axis (14-15)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43179 | 43183 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2014 | Check formwork for Columns from level (312.10 to 316.10) between axis (14-15)&(E-F) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43179 | 43183 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2015 | Check bottom reinforcement for R.C slab between axes (5-6) & (A-F) with (TOC = 291.80 ) for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | S.O.G | 43179 | 43202 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2016 | Check TOP reinforcement for R.C slab between axes (5-6) & (A-F) with (TOC = 291.80 ) for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | S.O.G | 43179 | 43202 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2017 | Pouring request for R.C slab between axes (5-6) & (A-F) with (TOC = 291.80 ) for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43179 | 43202 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2018 | Pouring request for Columns from level (312.10 to 316.10) between axis (14-15)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43179 | 43183 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2019 | Check RFT for Columns & elevator & stair core walls from level (333.10 to 337.80) between axis (14-17)&(G-K) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 8th | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2020 | Check formwork for Columns & elevator & stair core walls from level (333.10 to 337.80) between axis (14-17)&(G-K) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 8th | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2021 | Pouring request for Columns & elevator & stair core walls from level (333.10 to 337.80) between axis (14-17)&(G-K) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 8th | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2022 | Check RFT for Columns & elevator & stair core walls from level (333.10 to 337.80) between axis (2-5)&(G-K) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 8th | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2023 | Check formwork for Columns & elevator & stair core walls from level (333.10 to 337.80) between axis (2-5)&(G-K) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 8th | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2024 | Pouring request for Columns & elevator & stair core walls from level (333.10 to 337.80) between axis (2-5)&(G-K) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 8th | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2025 | Check bottom reinforcement for R.C slab between axes (14-17) & (G-K) with (TOC = 337.80 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 8th | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2026 | Check TOP reinforcement for R.C slab between axes (14-17) & (G-K) with (TOC = 337.80 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 8th | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2027 | Pouring request for R.C slab between axes (14-17) & (G-K) with (TOC = 337.80 ) for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | 8th | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2028 | Check bottom reinforcement for R.C slab between axes (2-5) & (G-K) with (TOC = 337.80 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 8th | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2029 | Check TOP reinforcement for R.C slab between axes (2-5) & (G-K) with (TOC = 337.80 ) for area (Z4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 8th | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2030 | Pouring request for R.C slab between axes (2-5) & (G-K) with (TOC = 337.80 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | 8th | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2031 | Check RFT for stair NO.(4) from level (291.90 to 295.80) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2032 | Pouring request for stair NO.(4) from level (291.90 to 295.80) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2033 | Check RFT for stair NO.(2) from level (291.90 to 295.80) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2034 | Pouring request for stair NO.(2) from level (291.90 to 295.80) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2035 | Check RFT for stair NO.(3) from level (291.90 to 295.80) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2036 | Pouring request for stair NO.(3) from level (291.90 to 295.80) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2037 | Check RFT for stair NO.(5) from level (291.90 to 295.80) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2038 | Pouring request for stair NO.(5) from level (291.90 to 295.80) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2039 | Check RFT for Columns after PVC membrane in water tank from level (291.10 to 295.60) between axis (1-2)&(H-L) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2040 | Check formwork for Columns after PVC membrane in water tank from level (291.10 to 295.60) between axis (1-2)&(H-L) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B2 | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2041 | Pouring request for Columns after PVC membrane in water tank from level (291.10 to 295.60) between axis (1-2)&(H-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43181 | 43186 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2042 | Check RFT for stair NO.(2) from level (295.80 to 300.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43191 | 43192 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2043 | Pouring request for stair NO.(2) from level (295.80 to 300.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43191 | 43194 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2044 | Check RFT for stair NO.(17) from level (300.20 to 304.20) between axis (3-4)&(E-F) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43191 | 43194 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2045 | Pouring request for stair NO.(17) from level (300.20 to 304.20) between axis (3-4)&(E-F) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43191 | 43194 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2046 | Check RFT for Columns from level (344.10 to 347.10) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 10th Floor | 43191 | 43194 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2047 | Check formwork for Columns from level (344.10 to 347.10) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 10th Floor | 43191 | 43194 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2048 | pouring for Columns from level (344.10 to 347.10) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 10th Floor | 43191 | 43194 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2049 | Check RFT for Columns from level (344.10 to 347.10) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 10th Floor | 43191 | 43194 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2050 | Check formwork for Columns from level (344.10 to 347.10) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 10th Floor | 43191 | 43194 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2051 | pouring for Columns from level (344.10 to 347.10) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 10th Floor | 43191 | 43194 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2052 | Check reinforcement for R.C slab between axes (6-8) & (H-J) with (TOC = 347.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 10th Floor | 43191 | 43194 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2053 | Pouring request for R.C slab between axes (6-8) & (H-J) with (TOC = 347.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 10th Floor | 43191 | 43194 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2054 | Check reinforcement for R.C slab between axes (11-13) & (H-J) with (TOC = 347.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 10th Floor | 43191 | 43194 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2055 | Pouring request for R.C slab between axes (11-13) & (H-J) with (TOC = 347.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 10th Floor | 43191 | 43194 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2056 | Check Top level for slab between axes (14-17) & (G-K) with (TOC = 338.10 ) - PART (P2)As Per Attached Sketch. | STR | LEVELS | LEVELS | 9th | 43192 | 43202 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2057 | Check Top level for slab between axes (14-17) & (G-K) with (TOC = 338.10 ) - PART (P4)As Per Attached Sketch. | STR | LEVELS | LEVELS | 9th | 43192 | 43202 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2058 | Check formwork for stair no.(5) axes (16) from level (291.90 to 295.80) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B2 | 43192 | 43202 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2059 | Check formwork for stair no.(1) axes (16) from level (291.90 to 295.80) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B2 | 43192 | 43202 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2060 | Check formwork for stair no.(7) axes (7) from level (291.90 to 295.80) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B2 | 43192 | 43202 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2061 | Check formwork for stair no.(17) axes (E&4) from level (300.10 to 304.10) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43192 | 43202 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2062 | WATER TEST FOR TANK between axes (1-2) & (G-L) As Per Attached Sketch. | STR | water proofing | water proofing | B2 | 43198 | 43214 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2063 | Check bottom reinforcement for R.C slab on grade between axes (17-18) & (A-F) with (TOC = 291.80 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | S.O.G | 43200 | 43219 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2064 | Check TOP reinforcement for R.C slab on grade between axes (17-18) & (A-F) with (TOC = 291.80 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | S.O.G | 43200 | 43219 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2065 | Pouring request for R.C slab on grade between axes (17-18) & (A-F) with (TOC = 291.80 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43200 | 43219 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2066 | Check bottom reinforcement for R.C slab on grade between axes (15-18) & (F-l) with (TOC = 291.80 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | S.O.G | 43200 | 43219 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2067 | Check TOP reinforcement for R.C slab on grade between axes (15-18) & (F-l) with (TOC = 291.80 ) for area (Z2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | S.O.G | 43200 | 43219 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2068 | Pouring request for R.C slab on grade between axes (15-18) & (F-L) with (TOC = 291.80 ) for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43200 | 43219 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2069 | Check bottom reinforcement for R.C slab on grade between axes (3-4) & (B-F) with (TOC = 291.80 ) for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | S.O.G | 43200 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2070 | Check TOP reinforcement for R.C slab on grade between axes (3-4) & (B-F) with (TOC = 291.80 ) for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | S.O.G | 43200 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2071 | Pouring request for R.C slab on grade between axes (3-4) & (B-F) with (TOC = 291.80 ) for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43200 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2072 | Check RFT for Columns from level (316.10 to 320.10) between axis (14-15)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2073 | Check formwork for Columns from level (316.10 to 320.10) between axis (14-15)&(E-F) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2074 | Pouring request for Columns from level (316.10 to 320.10) between axis (14-15)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2075 | Check RFT for Columns from level (320.10 to 324.10) between axis (14-15)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2076 | Check formwork for Columns from level (320.10 to 324.10) between axis (14-15)&(E-F) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2077 | Pouring request for Columns from level (320.10 to 324.10) between axis (14-15)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2078 | Check RFT for Columns from level (338.10 to 344.10) between axis (G-K)/9 for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 9th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2079 | Check formwork for Columns from level (338.10 to 344.10) between axis (G-K)/9 for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 9th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2080 | Pouring request for Columns from level (338.10 to 344.10) between axis (G-K)/9 for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 9th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2081 | Check bottom reinforcement for R.C slab between axes (8-9) & (F-L) with (TOC = 344.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 9th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2082 | Check TOP reinforcement for R.C slab between axes (8-9) & (F-L) with (TOC = 344.10 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 9th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2083 | Pouring request for R.C slab between axes (8-9) & (F-L) with (TOC = 344.10 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 9th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2084 | Check bottom reinforcement for R.C slab between axes (13-16) & (D-F) with (TOC = 316.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2085 | Check TOP reinforcement for R.C slab between axes (13-16) & (D-F) with (TOC = 316.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2086 | Pouring request for R.C slab between axes (13-16) & (D-F) with (TOC = 316.10 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2087 | Check bottom reinforcement for R.C slab between axes (13-16) & (D-F) with (TOC = 320.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2088 | Check TOP reinforcement for R.C slab between axes (13-16) & (D-F) with (TOC = 320.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2089 | Pouring request for R.C slab between axes (13-16) & (D-F) with (TOC = 320.10 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2090 | Check bottom reinforcement for R.C slab between axes (13-16) & (D-F) with (TOC = 324.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2091 | Check TOP reinforcement for R.C slab between axes (13-16) & (D-F) with (TOC = 324.10 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2092 | Pouring request for R.C slab between axes (13-16) & (D-F) with (TOC = 324.10 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2093 | Check bottom reinforcement for R.C slab between axes (14-17) & (C-F) with (TOC = 328.80 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43201 | 43205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2094 | Check TOP reinforcement for R.C slab between axes (14-17) & (C-F) with (TOC = 328.80 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43201 | 43205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2095 | Pouring request for R.C slab between axes (14-17) & (C-F) with (TOC = 328.80 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43201 | 43205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2096 | Check RFT for Columns from level (324.10 to 328.80) between axis(14-17)/E for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2097 | Check formwork for Columns from level (324.10 to 328.80) between axis(14-17)/E for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2098 | Pouring request for Columns from level (324.10 to 328.80) between axis(14-17)/E for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43201 | 43205 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2099 | Check RFT for stair NO.(2) from level (300.20 to 304.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43205 | 43211 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2100 | Pouring request for stair NO.(2) from level (300.20 to 304.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43205 | 43211 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2101 | Check RFT for stair NO.(2) from level (304.20 to 308.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43205 | 43211 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2102 | Pouring request for stair NO.(2) from level (304.20 to 308.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43205 | 43211 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2103 | Check RFT for stair NO.(4) from level (295.80 to 300.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43205 | 43211 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2104 | Pouring request for stair NO.(4) from level (295.80 to 300.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43205 | 43211 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2105 | Check RFT for stair NO.(4) from level (300.20to 304.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43205 | 43211 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2106 | Pouring request for stair NO.(4) from level (300.20 to 304.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43205 | 43211 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2107 | Check RFT for Columns from level (344.10 to 350.40) between axis(G-K)&(7-9) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | RF | 43205 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2108 | Check formwork for Columns from level (344.10 to 350.40) between axis(G-K)&(7-9) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | RF | 43205 | 43211 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2109 | Pouring request for Columns from level (344.10 to 350.40) between axis(G-K)&(7-9) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | RF | 43205 | 43211 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2110 | Check formwork for stair no.(7) axes (12) from level (295.80 to 300.20) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43207 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2111 | Check formwork for stair no.(1) axes (3) from level (295.80 to 300.20) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43207 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2112 | Check formwork for stair no.(1) axes (16) from level (295.80 to 300.20) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43207 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2113 | Check formwork for stair no.(1) axes (16) from level (300.20 to 304.20) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43207 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2114 | Check formwork for stair no.(3) axes (7) from level (300.20 to 304.20) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43207 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2115 | Check formwork for stair no.(17) axes (E&15) from level (300.10 to 304.10) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43207 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2116 | Check formwork for stair no.(1) axes (3) from level (300.20 to 304.20) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43207 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2117 | Check Top level for slab between axes (14-17) & (B) with (TOC = 328.10 ) - PART (P1)As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43207 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2118 | Check Top level for slab between axes (K-G)/(9) with (TOC = 344.10 ) - PART (P3)As Per Attached Sketch. | STR | LEVELS | LEVELS | 9th | 43207 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2119 | Check bottom reinforcement for R.C slab on grade between axes (14-11) & (F-J) with (TOC = 291.80 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | S.O.G | 43207 | 43219 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2120 | Check TOP reinforcement for R.C slab on grade between axes (14-11) & (F-J) with (TOC = 291.80 ) for area (Z3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | S.O.G | 43207 | 43219 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2121 | Pouring request for R.C slab on grade between axes (14-11) & (F-J) with (TOC = 291.80 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43207 | 43219 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2122 | Check bottom reinforcement for R.C slab on grade between axes (1-4) & (A-F) with (TOC = 291.80 ) for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | S.O.G | 43207 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2123 | Check TOP reinforcement for R.C slab on grade between axes (1-4) & (A-F) with (TOC = 291.80 ) for area (Z5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | S.O.G | 43207 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2124 | Pouring request for R.C slab on grade between axes (1-4) & (A-F) with (TOC = 291.80 ) for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43207 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2125 | Check RFT for stair NO.(1) from level (291.90 to 295.80) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2126 | Pouring request for stair NO.(1) from level (291.90 to 295.80) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2127 | Check RFT for stair NO.(1) from level (295.80 to 300.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2128 | Pouring request for stair NO.(1) from level (295.80 to 300.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2129 | Check RFT for stair NO.(1) from level (300.20 to 304.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2130 | Pouring request for stair NO.(1) from level (300.20 to 304.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2131 | Check RFT for stair NO.(3B) from level (295.80 to 300.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2132 | Pouring request for stair NO.(3B) from level (295.80 to 300.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2133 | Check RFT for stair NO.(3B) from level (300.20 to 304.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43209 | 43214 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2134 | Pouring request for stair NO.(3B) from level (300.20 to 304.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43209 | 43214 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2135 | Check RFT for stair NO.(5) from level (295.80 to 300.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2136 | Pouring request for stair NO.(5) from level (295.80 to 300.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2137 | Check RFT for stair NO.(5) from level (300.20 to 304.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2138 | Pouring request for stair NO.(5) from level (300.20 to 304.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2139 | Check RFT for stair NO.(17) from level (304.20 to 308.20) between axis (3-4)&(E-F) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2140 | Pouring request for stair NO.(17) from level (304.20 to 308.20) between axis (3-4)&(E-F) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2141 | Check RFT for stair NO.(17) from level (308.20 to 312.20) between axis (3-4)&(E-F) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2142 | Pouring request for stair NO.(17) from level (308.20 to 312.20) between axis (3-4)&(E-F) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2143 | Check RFT for stair NO.(17) from level (312.20 to 316.20) between axis (3-4)&(E-F) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2144 | Pouring request for stair NO.(17) from level (312.20 to 316.20) between axis (3-4)&(E-F) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2145 | Check RFT for stair NO.(3A) from level (291.90 to 295.80) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2146 | Pouring request for stair NO.(3A) from level (291.90 to 295.80) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2147 | Check RFT for stair NO.(3A) from level (295.80 to 300.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2148 | Pouring request for stair NO.(3A) from level (295.80 to 300.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2149 | Check formwork for Plain concrete for external ramp axes (16-18)/L from level (294.20 to 297.645) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | P.C | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2150 | Pouring request for Plain concrete for external ramp axes (16-18)/L from level (294.20 to 297.645) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43209 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2151 | Excavation level for extention (289.10) for area (5&14)(A&F) As Per Attached Sketch. | STR | LEVELS | LEVELS | Excavation | 43211 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2152 | Excavation level for RAMP (293.60 TO 297.045) for area (15-18)(K-L) As Per Attached Sketch. | STR | LEVELS | LEVELS | FOUNDATION | 43211 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2153 | First Layer For Replacement For EXTENTION Area (5&14)(A&F) At Level (289.35) As Per Sketch Attached. | STR | Levels | Levels | Rep. | 43211 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2154 | Second Layer For Replacement For EXTENTION Area (5&14)(A&F) At Level (289.60) As Per Sketch Attached. | STR | Levels | Levels | Rep. | 43211 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2155 | First Layer For Replacement For ramp Area (15-18)(K-L) At Level (293.85 TO 297.295) As Per Sketch Attached. | STR | Levels | Levels | Rep. | 43211 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2156 | Second Layer For Replacement For ramp Area (15-18)(K-L) At Level (294.10 TO 297.545) As Per Sketch Attached. | STR | Levels | Levels | Rep. | 43211 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2157 | Plane concrete (p.c) for area extention at level (289.70) As Per Attached Sketch. | STR | Levels | Levels | P.C | 43211 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2158 | Plane concrete (p.c) for area ramp at level (294.20 TO 297.645)As Per Attached Sketch. | STR | Levels | Levels | P.C | 43211 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2159 | Please check level for backfilling of S.O.G level (291.60) between axis (1-6)&(E-F) for area (P5) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | S.O.G | 43211 | 43214 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2160 | Please check TOP level FOR S.O.G level (291.80) between axis (1-6)&(E-F) for area (P5) As Per Attached Sketch. | STR | Levels | Levels | S.O.G | 43211 | 43214 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2161 | Check formwork for stair no.(7) axes (12) from level (300.20 to 304.20) for area (Z3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43211 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2162 | Check formwork for stair no.(17) axes (E&15) from level (304.10 to 308.10) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43211 | 43214 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2163 | Check formwork for stair no.(5) axes (3) from level (304.20 to 308.20) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2164 | Check formwork for stair no.(5) axes (16) from level (308.20 to 312.20) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2165 | Check formwork for stair no.(1) axes (16) from level (304.20 to 308.20) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2166 | Check formwork for stair no.(17) axes (E&4) from level (316.10 to 320.10) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2167 | Please check (R.C) for area ramp at level (294.75 TO 298.195)As Per Attached Sketch. | STR | Setting out | Setting out | R.C | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2168 | Offset 50cm for wall on RAMP at axies (L/ 16-18) As Per Attached Sketch. | STR | Setting out | Setting out | R.W | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2169 | Please check level for backfilling of S.O.G level (291.60) between axis (15-16)&(G-J) for area (P2) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | S.O.G | 43222 | 43225 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2170 | Please check level for backfilling of S.O.G level (291.60) between axis (12-13)&(F-G) for area (P3) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | S.O.G | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2171 | Please check level for backfilling of S.O.G level (291.60) between axis (15-18)&(B-F) for area (P1) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | S.O.G | 43222 | 43225 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2172 | Please check TOP level FOR S.O.G level (291.80) between axis(15-16)&(G-J) for area (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43222 | 43225 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2173 | Please check TOP level FOR S.O.G level (291.80) between axis (12-13)&(F-G) for area (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2174 | Please check TOP level FOR S.O.G level (291.80) between axis (15-18)&(B-F) for area (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43222 | 43225 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2175 | Check formwork for stair no.(5) axes (3) from level (295.20 to 300.20) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2176 | Check formwork for stair no.(5) axes (3) from level ( 300.20to 304.20) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2177 | Check formwork for stair no.(7) axes (12) from level ( 291.90.20to 295.80) for area (Z3,A) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B2 | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2178 | Check formwork for stair no.(5) axes (16) from level ( 295.80 to 300.20) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2179 | Check formwork for stair no.(5) axes (16) from level ( 300.20to 304.20) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2180 | Check formwork for stair no.(5) axes (16) from level ( 304.20to 308.20) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2181 | Check formwork for stair no.(17) axes (E&15) from level (308.10 to 312.10) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2182 | Check formwork for stair no.(7) axes (7) from level ( 295.80 to 300.20) for area (Z3,B) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43222 | 43225 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2183 | Check RFT for stair NO.(1) from level (304.20 to 308.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2184 | Pouring request for stair NO.(1) from level (304.20 to 308.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2185 | Check RFT for stair NO.(1) from level (308.20 to 312.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2186 | Pouring request for stair NO.(1) from level (308.20 to 312.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2187 | Check RFT for stair NO.(2) from level (308.20 to 312.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2188 | Pouring request for stair NO.(2) from level (308.20 to 312.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2189 | Check RFT for stair NO.(3B) from level (304.20 to 308.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2190 | Pouring request for stair NO.(3B) from level (304.20 to 308.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2191 | Check RFT for stair NO.(5) from level (304.20 to 308.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2192 | Pouring request for stair NO.(5) from level (304.20 to 308.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2193 | Check RFT for stair NO.(5) from level (308.20 to 312.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2194 | Pouring request for stair NO.(5) from level (308.20 to 312.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2195 | Check RFT for stair NO.(17) from level (316.20 to 320.20) between axis (3-4)&(E-F) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2196 | Pouring request for stair NO.(17) from level (316.20 to 320.20) between axis (3-4)&(E-F) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2197 | Check RFT for stair NO.(17) from level (300.20 to 304.20) between axis (15-16)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2198 | Pouring request for stair NO.(17) from level (300.20 to 304.20) between axis (15-16)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2199 | Check RFT for stair NO.(17) from level (304.20 to 308.20) between axis (15-16)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2200 | Pouring request for stair NO.(17) from level (304.20 to 308.20) between axis (15-16)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2201 | Check RFT for stair NO.(17) from level (308.20 to 312.20) between axis (15-16)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2202 | Pouring request for stair NO.(17) from level (308.20 to 312.20) between axis (15-16)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2203 | Primer coat for Plain concrete for external ramp axes (16-18)/L from level (294.20 to 297.645) for area (Z2) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2204 | Membrane coat for Plain concrete for external ramp axes (16-18)/L from level (294.20 to 297.645) for area (Z2) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2205 | Protection Board For Membrane coat for Plain concrete for external ramp axes (16-18)/L from level (294.20 to 297.645) for area (Z2) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2206 | Check RFT For R.C Foundation For external ramp axes (16-18)/L from level (294.20 to 297.645) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.C | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2207 | Pouring request For R.C Foundation For external ramp axes (16-18)/L from level (294.20 to 297.645) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | R.C | 43223 | 43226 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2208 | Check RFT For retaining wall of external ramp between axes (16-18)/L from level (299.495 to 300.40) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43229 | 43232 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2209 | Check formwork For retaining wall of external ramp between axes (16-18)/L from level (299.495 to 300.40) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | R.W | 43229 | 43232 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2210 | pouring request For retaining wall of external ramp between axes (16-18)/L from level (299.495 to 300.40) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43229 | 43232 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2211 | Check RFT For R.C SLAB For external ramp between axes (16-18)/L at LEVEL(299.30) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43229 | 43232 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2212 | pouring request For R.C SLAB For external ramp between axes (16-18)/L at LEVEL(299.30) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | SLAB | 43229 | 43232 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2213 | Check RFT for stair NO.(1) from level (312.20 to 316.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43229 | 43232 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2214 | Pouring request for stair NO.(1) from level (312.20 to 316.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43229 | 43232 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2215 | Check RFT for stair NO.(2) from level (312.20 to 316.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43229 | 43232 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2216 | Pouring request for stair NO.(2) from level (312.20 to 316.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43229 | 43232 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2217 | Check RFT for stair NO.(2) from level (316.20 to 320.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43229 | 43232 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2218 | Pouring request for stair NO.(2) from level (316.20 to 320.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43229 | 43232 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2219 | Check RFT for stair NO.(3A) from level ( 300.20 to 304.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43229 | 43232 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2220 | Pouring request for stair NO.(3A) from level ( 300.20 to 304.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43229 | 43232 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2221 | Check RFT for stair NO.(3A) from level ( 304.20 to 308.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2222 | Pouring request for stair NO.(3A) from level ( 304.20 to 308.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2223 | Check RFT for stair NO.(3A) from level ( 308.20 to 312.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2224 | Pouring request for stair NO.(3A) from level ( 308.20 to 312.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2225 | Check RFT for stair NO.(3B) from level (308.20 to 312.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2226 | Pouring request for stair NO.(3B) from level (308.20 to 312.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2227 | Check RFT for stair NO.(4) from level (304.20to 308.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2228 | Pouring request for stair NO.(4) from level (304.20 to 308.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2229 | Check RFT for stair NO.(4) from level (308.20to 312.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2230 | Pouring request for stair NO.(4) from level (308.20 to 312.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2231 | Check RFT for stair NO.(5) from level (312.20 to 316.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2232 | Pouring request for stair NO.(5) from level (312.20 to 316.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2233 | Check RFT for stair NO.(17) from level (312.20 to 316.20) between axis (15-16)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2234 | Pouring request for stair NO.(17) from level (312.20 to 316.20) between axis (15-16)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43229 | 43234 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2235 | Check formwork for stair no.(5) axes (3) from level (308.20 to 312.20) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2236 | Check formwork for stair no.(5) axes (3) from level (312.20 to 316.20) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2237 | Check formwork for stair no.(5) axes (16) from level (312.20 to 316.20) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2238 | Check formwork for stair no.(5) axes (16) from level (316.20 to 320.20) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2239 | Check formwork for stair no.(1) axes (3) from level (316.20 to 320.20) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2240 | Check formwork for stair no.(17) axes (E&4) from level (304.10 to 308.10) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2241 | Check formwork for stair no.(17) axes (E&4) from level (308.10 to 312.10) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2242 | Check formwork for stair no.(17) axes (E&4) from level (312.10 to 316.10) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2243 | Check formwork for stair no.(5) axes (16) from level (320.20 to 324.20) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2244 | Check formwork for stair no.(1) axes (3) from level (312.20 to 316.20) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2245 | Check formwork for stair no.(17) axes (E&4) from level (320.10 to 324.10) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2246 | Check formwork for stair no.(1) axes (3) from level (304.20 to 308.20) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2247 | Check formwork for stair no.(1) axes (3) from level (308.20 to 312.20) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2248 | Check formwork for stair no.(1) axes (16) from level (308.20 to 312.20) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2249 | Check formwork for stair no.(1) axes (16) from level (312.20 to 316.20) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2250 | Check formwork for stair no.(1) axes (16) from level (316.20 to 320.20) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2251 | Check formwork for stair no.(1) axes (16) from level (320.20 to 324.20) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2252 | Check formwork for stair no.(17) axes (E&15) from level (312.10 to 316.10) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2253 | Check formwork for stair no.(17) axes (E&15) from level (316.10 to 320.10) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2254 | Check formwork for stair no.(7) axes (12) from level (304.20 to 308.20) for area (Z3A) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2255 | Check formwork for stair no.(7) axes (12) from level (308.20 to 312.20) for area (Z3A) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2256 | Check formwork for stair no.(7) axes (12) from level (312.20 to 316.20) for area (Z3A) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2257 | Check formwork for stair no.(7) axes (7) from level (304.20 to 308.20) for area (Z3B) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2258 | Check formwork for stair no.(7) axes (7) from level (308.20 to 312.20) for area (Z3B) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2259 | Check formwork for stair no.(7) axes (7) from level (312.20 to 316.20) for area (Z3B) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2260 | Please check SLAB for area ramp at level (299.30&300.40 ) For area ZONE(2) As Per Attached Sketch. | STR | LEVELS | LEVELS | SLAB | 43235 | 43240 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2261 | Surface preparation and repair for External ramp foundation and retaining wall under S.O.G between axis (16-18)/(L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | COLD APP | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2262 | FIRST Primer coat for External ramp foundation and retaining wall under S.O.G between axis (16-18)/(L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | COLD APP | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2263 | second Primer coat for External ramp foundation and retaining wall under S.O.G between axis (16-18)/(L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | COLD APP | 43236 | 43247 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2264 | Check RFT for stair NO.(1) from level (316.20 to 320.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2265 | Pouring request for stair NO.(1) from level (316.20 to 320.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2266 | Check RFT for stair NO.(1) from level (320.20 to 324.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2267 | Pouring request for stair NO.(1) from level (320.20 to 324.20) between axis (15-16)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2268 | Check RFT for stair NO.(2) from level (320.20 to 324.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2269 | Pouring request for stair NO.(2) from level (320.20 to 324.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2270 | Check RFT for stair NO.(2) from level (324.20 to 328.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2271 | Pouring request for stair NO.(2) from level (324.20 to 328.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2272 | Check RFT for stair NO.(3A) from level ( 312.20 to 316.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2273 | Pouring request for stair NO.(3A) from level ( 312.20 to 316.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2274 | Check RFT for stair NO.(3A) from level ( 316.20 to 320.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2275 | Pouring request for stair NO.(3A) from level ( 316.20 to 320.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2276 | Check RFT for stair NO.(3B) from level ( 312.20 to 316.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2277 | Pouring request for stair NO.(3B) from level ( 312.20 to 316.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2278 | Check RFT for stair NO.(3B) from level ( 316.20 to 320.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2279 | Pouring request for stair NO.(3B) from level ( 316.20 to 320.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2280 | Check RFT for stair NO.(4) from level (312.20to 316.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2281 | Pouring request for stair NO.(4) from level (312.20 to 316.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2282 | Check RFT for stair NO.(4) from level (316.20to 320.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2283 | Pouring request for stair NO.(4) from level (316.20 to 320.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2284 | Check RFT for stair NO.(5) from level (316.20 to 320.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2285 | Pouring request for stair NO.(5) from level (316.20 to 320.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2286 | Check RFT for stair NO.(17) from level (316.20 to 320.20) between axis (15-16)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2287 | Pouring request for stair NO.(17) from level (316.20 to 320.20) between axis (15-16)&(E-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43236 | 43241 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2288 | Membrane coat for External ramp foundation and retaining wall under S.O.G between axis (16-18)/(L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43247 | 43251 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2289 | Check DRILLING and Cleaning for holes of anchor bolts of steel structure for beams at second floor (308.10) for area Z3 as Per Attached Sketch. | STR | Steel | Steel | 1st | 43250 | 43256 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2290 | Check Location for holes of anchor bolts of steel structure for beams at second floor (308.10) for area Z3 as Per Attached Sketch. | STR | Steel | Steel | 1st | 43250 | 43256 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2291 | Check formwork for stair no.(5) axes (16) from level (324.20 to 328.20) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2292 | Check formwork for stair no.(7) axes (7) from level (316.20 to 320.20) for area (Z3B) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2293 | Check formwork for stair no.(7) axes (7) from level (320.20 to 324.20) for area (Z3B) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2294 | Check formwork for stair no.(1) axes (3) from level (320.20 to 324.20) for area (Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2295 | Check formwork for stair no.(5) axes (3) from level (316.20 to 320.20) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2296 | Check formwork for stair no.(5) axes (3) from level (320.20 to 324.20) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2297 | Check formwork for stair no.(7) axes (12) from level (316.20 to 320.20) for area (Z3A) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2298 | Check formwork for stair no.(7) axes (12) from level (320.20 to 324.20) for area (Z3A) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2299 | Check formwork for stair no.(17) axes (E&15) from level (320.10 to 324.10) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2300 | Check formwork for stair no.(5) axes (16) from level (328.20 to 333.20) for area (Z2) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 7th | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2301 | Pouring request for plain concrete at level (289.70) between axis (5-14)&(A-F) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43251 | 43258 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2302 | Surface preparaiton and repair for plain concrete at level (289.70) between axis (5-14)&(A-F) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43251 | 43258 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2303 | primer coat for plain concrete at level (289.70) between axis (5-14)&(A-F) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43251 | 43258 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2304 | membrane coat for plain concrete at level (289.70) between axis (5-14)&(A-F) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43251 | 43258 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2305 | protection board(3mm) for membrane of plain concrete at level (289.70) between axis (5-14)&(A-F) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43251 | 43258 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2306 | Pouring request for plain concrete (screed 5cm) at level (289.75) between axis (5-14)&(A-F) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43251 | 43258 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2307 | Pouring request for R.C Foundation at level (290.55) between axis (10-13)&(A-C) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | R.C | 43251 | 43258 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2308 | Plane concrete (p.c) for area extention at level (290.25) As Per Attached Sketch. | STR | LEVELS | LEVELS | P.C | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2309 | Please check (R.C) for area Extention at level (290.55 ) between axis (10-13)&(A-B) As Per Attached Sketch. | STR | LEVELS | LEVELS | R.C | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2310 | Excavation level for extention OF SUM PIT (287.65) As Per Attached Sketch. | STR | LEVELS | LEVELS | Excavation | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2311 | First Layer For Replacement For EXTENTION of SUM PIT At Level (287.90) As Per Sketch Attached. | STR | LEVELS | LEVELS | Rep. | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2312 | Second Layer For Replacement For EXTENTION of SUM PIT At Level (288.15) As Per Sketch Attached. | STR | LEVELS | LEVELS | Rep. | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2313 | Plane concrete (p.c) for area extention of SUM PIT at level (288.25) As Per Attached Sketch. | STR | LEVELS | LEVELS | P.C | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2314 | Please check (R.C) for area Extention of SUM PIT at level (289.05 ) As Per Attached Sketch. | STR | LEVELS | LEVELS | R.C | 43251 | 43255 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2315 | Check planting of anchor bolts of steel structure for beams at second floor (308.10) for area Z3 as Per Attached Sketch. | STR | Steel | Steel | 1st | 43254 | 43258 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2316 | Check RFT for retaining wall from level (290.55 to 295.60) between axis (10-13) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43256 | 43258 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2317 | Check formwork fo retaining walls from level (290.55 to 295.60) between axis (10-13) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | R.W | 43256 | 43258 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2318 | Pouring request for retaining wall from level (290.55 to 295.60) between axis (10-13) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43256 | 43258 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2319 | Check RFT for Columns from level (290.55 to 295.60) between axis(A-B)&(10-13) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | COL. | 43256 | 43258 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2320 | Check formwork for Columns from level (290.55 to 295.60) between axis(A-B)&(10-13) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | COL. | 43256 | 43258 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2321 | Pouring request for Columns from level (290.55 to 295.60) between axis(A-B)&(10-13) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | COL. | 43256 | 43258 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2322 | Check RFT for stair NO.(3A) from level ( 320.20 to 324.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43264 | 43275 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2323 | Pouring request for stair NO.(3A) from level ( 320.20 to 324.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43264 | 43275 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2324 | Check RFT for stair NO.(3A) from level ( 324.20 to 328.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43264 | 43275 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2325 | Pouring request for stair NO.(3A) from level ( 324.20 to 328.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43264 | 43275 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2326 | Check RFT for stair NO.(3B) from level ( 320.20 to 324.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43264 | 43275 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2327 | Pouring request for stair NO.(3B) from level ( 320.20 to 324.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43264 | 43275 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2328 | Check RFT for stair NO.(3B) from level ( 324.20 to 328.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43264 | 43275 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2329 | Pouring request for stair NO.(3B) from level ( 324.20 to 328.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43264 | 43275 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2330 | Check RFT for stair NO.(4) from level (320.20to 324.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43264 | 43275 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2331 | Pouring request for stair NO.(4) from level (320.20 to 324.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43264 | 43275 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2332 | Check RFT for stair NO.(4) from level (324.20to 328.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43264 | 43275 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2333 | Pouring request for stair NO.(4) from level (324.20 to 328.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43264 | 43275 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2334 | FIRST Primer coat for Raft and blockwork under S.O.G between axis (13-14)/(A-E) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43264 | 43275 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2335 | Second Primer coat for Raft and blockwork under S.O.G between axis (13-14)/(A-E) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43264 | 43275 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2336 | Third Primer coat for Raft and blockwork under S.O.G between axis (13-14)/(A-E) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43264 | 43275 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2337 | Pouring request for S.O.G between axes (1-7) & (F-L) with (TOC = 291.80 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43277 | 43291 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2338 | Pouring request for S.O.G between axes (12-18) & (0-A) with (TOC = 291.80 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43277 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2339 | Pouring request for S.O.G between axes (1-6) & (0-A) with (TOC = 291.80 ) for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43276 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2340 | Pouring request for S.O.G between axes (4-6) & (B-F) with (TOC = 291.80 ) for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43278 | 43289 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2341 | Pouring request for S.O.G between axes (1-3) & (B-F) with (TOC = 291.80 ) for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43279 | 43289 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2342 | Pouring request for S.O.G between axes (13-18) & (0-B) with (TOC = 291.80 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43279 | 43289 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2343 | Pouring request for S.O.G between axes (16-18) & (A-F) with (TOC = 291.80 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43282 | 43289 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2344 | Check formwork for stair no.(7) axes (7) from level (328.20 to 333.20) for area (Z3B) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 7th | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2345 | Check formwork for stair no.(7) axes (12) from level (324.20 to 328.20) for area (Z3A) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2346 | Check formwork for stair no.(7) axes (7) from level (324.20 to 328.20) for area (Z3B) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2347 | Please check level for backfilling of S.O.G level (291.60) between axis (1-6)&(0-A) for area (P5) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2348 | Please check TOP level FOR S.O.G level (291.80) between axis (1-6)&(0-A) for area (P5) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2349 | Please check level for backfilling of S.O.G level (291.60) between axis (3-6)&(G-L) for area (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2350 | Please check TOP level FOR S.O.G level (291.80) between axis (3-6)&(G-L) for area (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2351 | Please check level for backfilling of S.O.G level (291.60) between axis (12-17)&(0-A) for area (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2352 | Please check TOP level FOR S.O.G level (291.80) between axis (12-17)&(0-A) for area (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2353 | Please check level for backfilling of S.O.G level (291.60) between axis (4-6)&(B-F) for area (P5) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2354 | Please check TOP level FOR S.O.G level (291.80) between axis (4-6)&(B-F) for area (P5) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2355 | Check Level and Location for of anchor bolts of steel structure for beams at second floor (308.10) for area Z3 as Per Attached Sketch. | STR | LEVELS | LEVELS | 1st | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2356 | Check Sloped concrete level for the roof level (324.10) between axis (A-F)&(1-6) for area (P5) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2357 | Check Sloped concrete level for the roof level (324.10) between axis (A-F)&(13-18) for area (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | 5th | 43283 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2358 | Pouring Request For Plain concrete (10cm) For Zone (1&2&3&4&5) With T.O.C = 289.70 As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2359 | Pouring Request For Plain concrete (5cm) For Zone (3&4&5) With T.O.C = 289.75 As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2360 | Check RFT for columns And Core wall from level (291.00 to 295.60) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2361 | Check formwork for columns And Core wall from level (291.00 to 295.60) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B2 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2362 | Pouring request for columns And Core wall from level (291.00 to 295.60) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2363 | Check RFT for Retainig wall from level (291.00 to 295.60) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2364 | Check formwork fo Retainig wall from level (291.00 to 295.60) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B2 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2365 | Pouring request for Retainig wall from level (291.00 to 295.60) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2366 | Check bottom reinforcement for R.C slab between axes (13-18) & (B-E) with (TOC = 295.60 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B2 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2367 | Check TOP reinforcement for R.C slab between axes (13-18) & (B-E) with (TOC = 295.60 ) for area (Z1) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B2 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2368 | Pouring request for R.C slab between axes (13-18) & (B-E) with (TOC = 295.60 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | B2 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2369 | Check RFT for columns And Core wall from level (295.60 to 300.10) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2370 | Check formwork for columns And Core wall from level (295.60 to 300.10) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2371 | Pouring request for columns And Core wall from level (295.60 to 300.10) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2372 | Check RFT for Retainig wall from level (295.60 to 300.10) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2373 | Check formwork fo Retainig wall from level (295.60 to 300.10) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2374 | Pouring request for Retainig wall from level (295.60 to 300.10) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2375 | Check bottom reinforcement for R.C slab between axes (1-18) & (A-L) with (TOC = 300.10 ) for area ZONE (1&2&3&4&5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B1 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2376 | Check TOP reinforcement for R.C slab between axes (1-18) & (A-L) with (TOC = 300.10 ) for area ZONE (1&2&3&4&5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | B1 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2377 | Pouring request for R.C slab between axes (1-18) & (A-L) with (TOC = 300.10 ) for area ZONE (1&2&3&4&5) As Per Attached Sketch . | STR | Concreting | Concreting | B1 | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2378 | Check RFT for columns And Core wall from level (300.10 to 304.10) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2379 | Check formwork for columns And Core wall from level(300.10 to 304.10) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2380 | Pouring request for columns And Core wall from level (300.10 to 304.10)) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2381 | Check bottom reinforcement for R.C slab between axes (4-18) & (A-L) with (TOC = 304.10 ) for area ZONE (1&2&3&4&5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | GF | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2382 | Check TOP reinforcement for R.C slab between axes (4-18) & (A-L) with (TOC = 304.10 ) for area ZONE (1&2&3&4&5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | GF | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2383 | Pouring request for R.C slab between axes (4-18) & (A-L) with (TOC = 304.10 ) for area ZONE (1&2&3&4&5) As Per Attached Sketch . | STR | Concreting | Concreting | GF | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2384 | Check RFT for columns And Core wall from level (304.10 to 308.10) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2385 | Check formwork for columns And Core wall from level(304.10 to 308.10) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2386 | Pouring request for columns And Core wall from level (304.10 to 308.10)) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2387 | Check bottom reinforcement for R.C slab between axes (1-14) & (C-L) with (TOC = 308.10 ) for area ZONE (1&3&4&5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 1st | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2388 | Check TOP reinforcement for R.C slab between axes (1-14) & (C-L) with (TOC = 308.10 ) for area ZONE (1&3&4&5) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 1st | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2389 | Pouring request for R.C slab between axes (1-14) & (C-L) with (TOC = 308.10 ) for area ZONE (1&3&4&5) As Per Attached Sketch . | STR | Concreting | Concreting | 1st | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2390 | Check RFT for columns And Core wall from level (308.10 to 312.10) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 2nd | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2391 | Check formwork for columns And Core wall from level(308.10 to 312.10) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 2nd | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2392 | Pouring request for columns And Core wall from level (308.10 to 312.10) between axis (1-18)/(A-L) for area ZONE (1&2&3&4&5) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2393 | Check bottom reinforcement for R.C slab between axes (5-17) & (A-L) with (TOC = 312.10 ) for area ZONE (1&2&3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2394 | Check TOP reinforcement for R.C slab between axes (5-17) & (A-L) with (TOC = 312.10 ) for area ZONE (1&2&3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 2nd | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2395 | Pouring request for R.C slab between axes (5-17) & (A-L) with (TOC = 312.10 ) for area ZONE (1&2&3) As Per Attached Sketch . | STR | Concreting | Concreting | 2nd | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2396 | Check RFT for columns from level (312.10 to 316.10) between axis (1-17)/(D-F) for area ZONE (1&4&5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 3rd | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2397 | Check formwork for columns from level (312.10 to 316.10) between axis (1-17)/(D-F) for area ZONE (1&4&5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 3rd | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2398 | Pouring request for columns from level (312.10 to 316.10) between axis (1-17)/(D-F) for area ZONE (1&4&5) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2399 | Check bottom reinforcement for R.C slab between axes (5-16) & (E-K) with (TOC = 316.10 ) for area ZONE (1&2&3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2400 | Check TOP reinforcement for R.C slab between axes (5-16) & (E-K) with (TOC = 316.10 ) for area ZONE (1&2&3) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 3rd | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2401 | Pouring request for R.C slab between axes (5-16) & (E-K) with (TOC = 316.10 ) for area ZONE (1&2&3) As Per Attached Sketch . | STR | Concreting | Concreting | 3rd | 43283 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2402 | Check RFT for columns And Core wall from level (316.10 to 320.10) between axis (5-18)/(A-L) for area ZONE (1&2&3&4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2403 | Check formwork for columns And Core wall from level (316.10 to 320.10) between axis (5-18)/(A-L) for area ZONE (1&2&3&4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 4th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2404 | Pouring request for columns And Core wall from level (316.10 to 320.10) between axis (5-18)/(A-L) for area ZONE (1&2&3&4) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2405 | Check bottom reinforcement for R.C slab between axes (10-18) & (B-K) with (TOC = 320.10 ) for area ZONE (1&2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2406 | Check TOP reinforcement for R.C slab between axes (10-18) & (B-K) with (TOC = 320.10 ) for area ZONE (1&2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 4th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2407 | Pouring request for R.C slab between axes (10-18) & (B-K) with (TOC = 320.10 ) for area ZONE (1&2) As Per Attached Sketch . | STR | Concreting | Concreting | 4th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2408 | Check RFT for columns And Core wall from level (320.10 to 324.10) between axis (2-17)/(B-K) for area ZONE (1&2&4&5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2409 | Check formwork for columns And Core wall from level (320.10 to 324.10) between axis (2-17)/(B-K) for area ZONE (1&2&4&5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2410 | Pouring request for columns And Core wall from level (320.10 to 324.10) between axis (2-17)/(B-K) for area ZONE (1&2&4&5) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2411 | Check bottom reinforcement for R.C slab between axes (2-18) & (D-L) with (TOC = 324.10 ) for area ZONE (1&2&3&4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2412 | Check TOP reinforcement for R.C slab between axes (2-18) & (D-L) with (TOC = 324.10 ) for area ZONE (1&2&3&4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 5th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2413 | Pouring request for R.C slab between axes (2-18) & (D-L) with (TOC = 324.10 ) for area ZONE (1&2&3&4) As Per Attached Sketch . | STR | Concreting | Concreting | 5th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2414 | Check RFT for columns from level (324.10 to 328.10) between axis (3-5)/(F-G) for area (4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2415 | Check formwork for columns from level (324.10 to 328.10) between axis (3-5)/(F-G) for area (4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2416 | Pouring request for columns from level (324.10 to 328.10) between axis (3-5)/(F-G) for area (4) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2417 | Check bottom reinforcement for R.C slab between axes (14-16) & (G-K) with (TOC = 328.10 ) for area Z (2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2418 | Check TOP reinforcement for R.C slab between axes (14-16) & (G-K) with (TOC = 328.10 ) for area Z (2) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 6th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2419 | Pouring request for R.C slab between axes (14-16) & (G-K) with (TOC = 328.10 ) for area Z (2) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2420 | Check RFT for columns and core wall from level (328.10 to 333.10) between axis (3-18)/(G-L) for area (2&3&4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 7th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2421 | Check formwork for columns And Core wall from level (328.10 to 333.10) between axis (3-18)/(G-L) for area (2&3&4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 7th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2422 | Pouring request for columns And Core wall from level (328.10 to 333.10) between axis (3-18)/(G-L) for area (2&3&4) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2423 | Check bottom reinforcement for R.C slab between axes (3-16) & (G-K) with (TOC = 333.10 ) for area Z (2&4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2424 | Check TOP reinforcement for R.C slab between axes (3-16) & (G-K) with (TOC = 333.10 ) for area Z (2&4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 7th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2425 | Pouring request for R.C slab between axes (3-16) & (G-K) with (TOC = 333.10 ) for area Z (2&4) As Per Attached Sketch . | STR | Concreting | Concreting | 7th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2426 | Check bottom reinforcement for R.C slab between axes (3-16) & (F-L) with (TOC = 338.10 ) for area Z (2&3&4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 8th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2427 | Check TOP reinforcement for R.C slab between axes (3-16) & (F-L) with (TOC = 338.10 ) for area Z (2&3&4) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | 8th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2428 | Pouring request for R.C slab between axes (3-16) & (F-L) with (TOC = 338.10 ) for area Z (2&3&4) As Per Attached Sketch . | STR | Concreting | Concreting | 8th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2429 | Check RFT for core wall from level (338.10 to 344.10) between axis (6-13)/(H-J) for area (3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 9th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2430 | Check formwork for core wall from level (338.10 to 344.10) between axis (6-13)/(H-J) for area (3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 9th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2431 | Pouring request for core wall from level (338.10 to 344.10) between axis (6-13)/(H-J) for area (3) As Per Attached Sketch. | STR | Concreting | Concreting | 9th | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2432 | Check RFT for columns from level (344.10 to 350.40) between axis (8-12)/(G-K) for area (3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | RF | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2433 | Check formwork for columns from level (344.10 to 350.40) between axis (8-12)/(G-K) for area (3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | RF | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2434 | Pouring request for columns from level (344.10 to 350.40) between axis (8-12)/(G-K) for area (3) As Per Attached Sketch. | STR | Concreting | Concreting | RF | 43284 | 43289 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2435 | Please check level for backfilling of S.O.G level (291.60) between axis (1-4)&(A-F) for area (P5) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43285 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2436 | Please check TOP level FOR S.O.G level (291.80) between axis (1-4)&(A-F) for area (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43285 | 43288 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2437 | Please check level for backfilling of S.O.G level (291.60) between axis (15-16)&(A-B) for area (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43285 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2438 | Please check TOP level FOR S.O.G level (291.80) between axis (15-16)&(A-B) for area (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43285 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2439 | Check Level of steel structure Plates for beams at second floor (308.10) for area Z3 as Per Attached Sketch. | STR | LEVELS | LEVELS | 1st | 43285 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2440 | Excavation level of AREA (Z1) from axes (14-17 / A) (289.10) as per sketch attached. | STR | LEVELS | LEVELS | FOUNDATION | 43285 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2441 | First Layer For Replacement For AREA (Z1) from axes (14-17 / A) (289.35) as per sketch attached. | STR | LEVELS | LEVELS | FOUNDATION | 43285 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2442 | SECOND Layer For Replacement For AREA (Z1) from axes (14-17 / A) (289.35) as per sketch attached. | STR | LEVELS | LEVELS | FOUNDATION | 43285 | 43288 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2443 | Pouring request for S.O.G between axes (16-17) & (A-F) with (TOC = 291.80 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43285 | 43289 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2444 | Pouring request for GROUT Under steel plates for steel beams between axes (9-10) & (G-K) AT SECOND FLOOR (308.10) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 1st | 43285 | 43288 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2445 | INSTALLATION AND FIXATION OF STEEL BEAMS between axes (9-10) & (G-K) AT SECOND FLOOR (308.10) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 1st | 43285 | 43289 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2446 | Pouring request for S.O.G between axes (15-18) & (E-L) with (TOC = 291.80 ) for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43289 | 43292 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2447 | Pouring request for S.O.G between axes (9-12) & (F-L) with (TOC = 291.80 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43290 | 43296 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2448 | Pouring request for S.O.G between axes (2-6) & (E-L) with (TOC = 291.80 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43290 | 43296 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2449 | Pouring request for S.O.G between axes (12-16) & (B-F) with (TOC = 291.80 ) for area (Z1) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43290 | 43300 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2450 | Pouring request for S.O.G between axes (12-16) & (E-L) with (TOC = 291.80 ) for area (Z2) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43290 | 43300 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2451 | Check RFT for Columns from level (290.55 to 295.60) between axis(6-9)&(0-C) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | COL. | 43292 | 43296 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2452 | Check formwork for Columns from level (290.55 to 295.60) between axis(6-9)&(0-C) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | COL. | 43292 | 43296 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2453 | Pouring request for Columns from level (290.55 to 295.60) between axis(6-9)&(0-C) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | COL. | 43292 | 43296 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2454 | Check bottom reinforcement for R.C Foundation at level (290.55) between axis (6-9)&(0-D) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.C | 43292 | 43296 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2455 | Check TOP reinforcement for R.C Foundation at level (290.55) between axis (6-9)&(0-D) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.C | 43292 | 43296 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2456 | Pouring request for R.C Foundation at level (290.55) between axis (6-9)&(0-D) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | R.C | 43292 | 43296 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2457 | Check DRILLING and Cleaning for holes of anchor bolts of steel structure for beams at SEVENTH floor (328.10) for area Z3 as Per Attached Sketch. | STR | Steel | Steel | 6th | 43292 | 43300 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2458 | Check planting of anchor bolts of steel structure for beams at SEVENTH floor (328.10) for area Z3 as Per Attached Sketch. | STR | Steel | Steel | 6th | 43292 | 43305 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2459 | Pouring request for S.O.G between axes (3-5) & (E-K) with (TOC = 291.80 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43293 | 43300 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2460 | Pouring request for S.O.G between axes (9-14) & (G-K) with (TOC = 291.80 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43296 | 43300 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2461 | Pouring request for S.O.G between axes (9-10) & (F-L) with (TOC = 291.80 ) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43296 | 43300 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2462 | Pouring request for S.O.G between axes (1-10) & (E-L) with (TOC = 291.80 ) for area (Z3,Z4) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43297 | 43305 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2463 | Pouring request for S.O.G between axes (1-8) & (E-G) with (TOC = 291.80 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43299 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2464 | Pouring request for plain concrete at level (289.70) between axis (8-11)&(B-E) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2465 | Surface preparaiton and repair for plain concrete at level (289.70) between axis (8-11)&(B-E) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43300 | 43305 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2466 | primer coat for plain concrete at level (289.70) between axis (8-11)&(B-E) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2467 | membrane coat for plain concrete at level (289.70) between axis (8-11)&(B-E) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2468 | protection board(3mm) for membrane of plain concrete at level (289.70) between axis (8-11)&(B-E) (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2469 | Pouring request for plain concrete (screed 5cm) at level (289.75) between axis (8-11)&(B-E) for area for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2470 | Check bottom reinforcement for R.C Foundation at level (290.55) between axis (6-13)&(B-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.C | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2471 | Check TOP reinforcement for R.C Foundation at level (290.55) between axis (6-13)&(B-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.C | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2472 | Pouring request for R.C Foundation at level (290.55) between axis (6-13)&(B-F) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | R.C | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2473 | Check RFT for Columns from level (290.55 to 295.60) between axis(6-7)& (A-C) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | COL. | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2474 | Check formwork for Columns from level (290.55 to 295.60) between axis(6-7)&(A-C) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | COL. | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2475 | Pouring request for Columns from level (290.55 to 295.60) between axis(6-7)&(A-C) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | COL. | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2476 | Check RFT for Retaining wall from level (290.55 to 295.60) between axis (6-9)/(0-A) for area ZONE (6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2477 | Check formwork foR Retaining wall from level (290.55 to 295.60) between axis (6-9)/(0-A) for area ZONE (6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | R.W | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2478 | Pouring request for Retaining wall from level (290.55 to 295.60) between axis (6-9)/(0-A) for area ZONE (6) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2479 | Check RFT for stair NO.(2) from level (328.20 to 333.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 7th | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2480 | Pouring request for stair NO.(2) from level (328.20 to 333.20) between axis (15-16)&(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2481 | Check RFT for stair NO.(4) from level (328.20to 333.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 7th | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2482 | Pouring request for stair NO.(4) from level (328.20 to 333.20) between axis (3-4)&(H-J) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43300 | 43302 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2483 | Pouring request for S.O.G between axes (1-6) & (A-B) with (TOC = 291.80 ) for area (Z5) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43300 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2484 | Pouring request for S.O.G between axes (2-4) & (G-L) with (TOC = 291.80 ) for area (Z4) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43303 | 43309 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2485 | Check DRILLING and Cleaning for holes of anchor bolts of steel structure for beams at 8TH floor (333.10) for area Z3 as Per Attached Sketch. | STR | Steel | Steel | 7th | 43305 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2486 | Check planting of anchor bolts of steel structure for beams at 8TH floor (333.10) for area Z3 as Per Attached Sketch. | STR | Steel | Steel | 7th | 43305 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2487 | Check Level and Location for of anchor bolts of steel structure for beams at 7th floor (328.10) for area Z3 as Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43305 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2488 | Check Level of steel structure Plates for beams at 7th floor (328.10) for area Z3 as Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43305 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2489 | Please check level for backfilling of S.O.G level (291.60) between axis (9-13)&(F-L) for area (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43305 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2490 | Please check TOP level FOR S.O.G level (291.80) between axis (9-13)&(F-L) for area (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43305 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2491 | Please check level for backfilling of S.O.G level (291.60) between axis (12-15)&(C-F) for area (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43305 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2492 | Please check TOP level FOR S.O.G level (291.80) between axis (12-15)&(C-F) for area (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43305 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2493 | Please check level for backfilling of S.O.G level (291.60) between axis (15-18)&(E-L) for area (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43305 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2494 | Please check TOP level FOR S.O.G level (291.80) between axis (15-18)&(E-L) for area (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43305 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2495 | Check RFT for stair NO.(5) from level (320.20 to 324.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43305 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2496 | Pouring request for stair NO.(5) from level (320.20 to 324.20) between axis (3-4)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43305 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2497 | protection board(3mm) for membrane of plain concrete at level (289.70) between axis (3-14)&(D-L) (Z3,Z4,Z5) As Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2498 | Check RFT for columns from level (295.60 to 300.10) between axis (2-6)/(C-D) for area (5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2499 | Check formwork for columns from level (295.60 to 300.10) between axis (2-6)/(C-D) for area (5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B1 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2500 | Pouring request for columns from level (295.60 to 300.10) between axis (2-6)/(C-D) for area (5) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2501 | Check RFT for columns from level (290.75 to 295.60) between axis (1-10)/(A-G) for area (3&5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2502 | Check formwork for columns from level (290.75 to 295.60) between axis (1-10)/(A-G) for area (3&5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B2 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2503 | Pouring request for columns from level (290.75 to 295.60) between axis (1-10)/(A-G) for area (3&5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2504 | Check RFT for columns from level (300.10 to 304.10) between axis (6)/(L) for area (3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2505 | Check formwork for columns from level (300.10 to 304.10) between axis (6)/(L) for area (3) for area (3&5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | GF | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2506 | Pouring request for columns from level (300.10 to 304.10) between axis (6)/(L) for area (3) for area (3&5) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2507 | Check RFT for R.W from level (290.75.10 to 295.60) between axis (10-12)/(L) for area (3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2508 | Check formwork for R.W from level (290.75.10 to 295.60) between axis (10-12)/(L) for area (3) for area (3&5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | B2 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2509 | Pouring request for R.W from level (290.75.10 to 295.60) between axis (10-12)/(L) for area (3) for area (3&5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2510 | Check bottom reinforcement for R.C SLAB at level (295.60) between axis (1-14)&(A-L) for area (Z1,2,3,4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2511 | Check TOP reinforcement for R.C SLAB at level (295.60) between axis (1-14)&(A-L) for area (Z1,2,3,4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B2 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2512 | Pouring request for R.C SLAB at level (295.60) between axis (1-14)&(A-L) for area (Z1,2,3,4)As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2513 | Check bottom reinforcement for R.C SLAB at level (300.10) between axis (17-18)&(E-G) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2514 | Check TOP reinforcement for R.C SLAB at level (300.10) between axis (17-18)&(E-G) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | B1 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2515 | Pouring request for R.C SLAB at level (300.10) between axis (17-18)&(E-G) for area (Z2)As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2516 | FIRST Primer coat for Raft and blockwork under S.O.G between axis (1-17)/(A-L) for area (P1,2,3,4,5) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2517 | Second Primer coat for Raft and blockwork under S.O.G between axis (1-17)/(A-L) for area (P1,2,3,4,5) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2518 | Third Primer coat for Raft and blockwork under S.O.G between axis (1-17)/(A-L) for area (P1,2,3,4,5) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43306 | 43309 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2519 | Check RFT for Columns from level (290.55 to 295.60) between axis(6-12)& (C-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | COL. | 43311 | 43312 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2520 | Check formwork for Columns from level (290.55 to 295.60) between axis(6-12)&(C-F) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | COL. | 43311 | 43312 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2521 | Pouring request for Columns from level (290.55 to 295.60) between axis(6-12)&(C-F) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | COL. | 43311 | 43312 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2522 | Check bottom reinforcement for R.C SLAB at level (295.60) between axis (6-10)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43311 | 43312 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2523 | Check TOP reinforcement for R.C SLAB at level (295.60) between axis (6-10)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43311 | 43312 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2524 | Pouring request for R.C SLAB at level (295.60) between axis (6-10)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | SLAB | 43311 | 43312 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2525 | Check DRILLING and Cleaning for holes of anchor bolts of steel structure for beams at 9TH floor (338.10) for area Z3 as Per Attached Sketch. | STR | Steel | Steel | 8th | 43311 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2526 | Check planting of anchor bolts of steel structure for beams at 9TH floor (338.10) for area Z3 as Per Attached Sketch. | STR | Steel | Steel | 8th | 43311 | 43314 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2527 | INSTALLATION of Polyethelen sheet (400micron) under S.O.G between axes (13-18) & (A-F) for area (Z1) As Per Attached Sketch . | STR | Polyethelen sheet | Polyethelen sheet | S.O.G | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2528 | INSTALLATION of Polyethelen sheet (400micron) under S.O.G between axes (13-18) & (E-L) for area (Z2) As Per Attached Sketch . | STR | Polyethelen sheet | Polyethelen sheet | S.O.G | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2529 | INSTALLATION of Polyethelen sheet (400micron) under S.O.G between axes (6-13) & (F-L) for area (Z3) As Per Attached Sketch . | STR | Polyethelen sheet | Polyethelen sheet | S.O.G | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2530 | INSTALLATION of Polyethelen sheet (400micron) under S.O.G between axes (1-6) & (E-L) for area (Z4) As Per Attached Sketch . | STR | Polyethelen sheet | Polyethelen sheet | S.O.G | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2531 | INSTALLATION of Polyethelen sheet (400micron) under S.O.G between axes (1-6) & (A-F) for area (Z5) As Per Attached Sketch . | STR | Polyethelen sheet | Polyethelen sheet | S.O.G | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2532 | Check Level and Location for of anchor bolts of steel structure for beams at 8th floor (333.10) for area Z3 as Per Attached Sketch. | STR | LEVELS | LEVELS | 7th | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2533 | Check Level and Location for of anchor bolts of steel structure for beams at 9th floor (338.10) for area Z3 as Per Attached Sketch. | STR | LEVELS | LEVELS | 8th | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2534 | Check Level of steel structure Plates for beams at 8th floor (333.10) for area Z3 as Per Attached Sketch. | STR | LEVELS | LEVELS | 7th | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2535 | Check Level of steel structure Plates for beams at 9th floor (338.10) for area Z3 as Per Attached Sketch. | STR | LEVELS | LEVELS | 8th | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2536 | Offset 50cm for columns at axies (6-10)&(A-F) for area (P6) As Per Attached Sketch. | STR | LEVELS | LEVELS | COL. | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2537 | Please check TOP level FOR SLAB level (295.60) between axis (6-10)&(A-F) for area (P6) As Per Attached Sketch. | STR | LEVELS | LEVELS | SLAB | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2538 | Check RFT for stair NO.(3A) from level ( 328.20 to 333.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 7th | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2539 | Pouring request for stair NO.(3A) from level ( 328.20 to 333.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2540 | Check RFT for stair NO.(3B) from level ( 328.20 to 333.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 7th | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2541 | Pouring request for stair NO.(3B) from level ( 328.20 to 333.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2542 | Check RFT for stair NO.(3B) from level ( 333.20 to 338.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 8th | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2543 | Pouring request for stair NO.(3B) from level ( 333.20 to 338.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 8th | 43312 | 43314 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2544 | Check DRILLING and Cleaning for holes of anchor bolts of steel structure for beams at 10TH floor (344.10) for area Z3 as Per Attached Sketch. | STR | Steel | Steel | 9th | 43317 | 43337 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2545 | Check planting of anchor bolts of steel structure for beams at 10TH floor (344.10) for area Z3 as Per Attached Sketch. | STR | Steel | Steel | 9th | 43317 | 43337 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2546 | Check bottom reinforcement for R.C SLAB at level (295.60) between axis (9-13)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43317 | 43320 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2547 | Check TOP reinforcement for R.C SLAB at level (295.60) between axis (9-13)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43317 | 43320 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2548 | Pouring request for R.C SLAB at level (295.60) between axis (9-13)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | SLAB | 43317 | 43320 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2549 | Pouring request for S.O.G between axes (1-18) & (A-L) with (TOC = 291.80 ) for area (Z1,2,3,5) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43319 | 43320 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2550 | FIRST Primer coat for Raft and blockwork under S.O.G between axis (13-14)/(B-C) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43321 | 43349 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2551 | Second Primer coat for Raft and blockwork under S.O.G between axis (13-14)/(B-C) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43321 | 43349 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2552 | Third Primer coat for Raft and blockwork under S.O.G between axis (13-14)/(B-C) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | S.O.G | 43321 | 43349 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2553 | Pouring request for GROUT Under steel plates for steel beams between axes (9-10) & (G-K) AT 7th FLOOR (328.10) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43325 | 43337 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2554 | Pouring request for GROUT Under steel plates for steel beams between axes (9-10) & (G-K) AT 8th FLOOR (333.10) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 7th | 43325 | 43337 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2555 | INSTALLATION AND FIXATION OF STEEL BEAMS between axes (9-10) & (G-K) AT 7th FLOOR (328.10) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 6th | 43325 | 43337 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2556 | INSTALLATION AND FIXATION OF STEEL BEAMS between axes (9-10) & (G-K) AT 8th FLOOR (333.10) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 7th | 43325 | 43337 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2557 | Check Level and Location for anchor bolts of steel structure for beams at 10th floor (344.10) for area Z3 as Per Attached Sketch. | STR | LEVELS | LEVELS | 9th | 43327 | 43330 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2558 | Check Level of steel structure Plates for beams at 10th floor (344.10) for area Z3 as Per Attached Sketch. | STR | LEVELS | LEVELS | 9th | 43327 | 43330 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2559 | Pouring request for GROUT Under steel plates for steel beams between axes (9-10) & (G-K) AT 9th FLOOR (338.10) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 8th | 43328 | 43344 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2560 | INSTALLATION AND FIXATION OF STEEL BEAMS between axes (9-10) & (G-K) AT 9th FLOOR (338.10) for area (Z3) As Per Attached Sketch . | STR | Concreting | Concreting | 8th | 43328 | 43340 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2561 | Check RFT for Retaining wall from level (295.60 to 299.00) between axis (6-9)/(0-A) for area ZONE (6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43328 | 43344 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2562 | Check formwork foR Retaining wall from level (295.60 to 299.00) between axis (6-9)/(0-A) for area ZONE (6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | R.W | 43328 | 43344 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2563 | Pouring request for Retaining wall from level (295.60 to 299.00) between axis (6-9)/(0-A) for area ZONE (6) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43328 | 43344 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2564 | Check RFT for Columns from level (295.60 to 299.00) between axis(6-13)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | COL. | 43328 | 43344 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2565 | Check formwork for Columns from level (295.60 to 299.00) between axis(6-13)&(0-F) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | COL. | 43328 | 43344 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2566 | Pouring request for Columns from level (295.60 to 299.00) between axis(6-13)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | COL. | 43328 | 43344 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2567 | Surface preparation and repair for retaining wall from level (289.75 to 295.60) between axis (17-18)&(E-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2568 | Primer coat for retaining wall from level (289.75 to 295.60) between axis (17-18)&(E-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2569 | Membrane coat for retaining wall from level (289.75 to 295.60) between axis (17-18)&(E-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2570 | cartonal coat for retaining wall from level (289.75 to 295.60) between axis (17-18)&(E-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2571 | Surface preparation and repair for retaining wall from level (289.75 to 295.60) between axis (13-18)&(0-F) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2572 | Primer coat for retaining wall from level (289.75 to 295.60) between axis (13-18)&(0-F) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2573 | Membrane coat for retaining wall from level (289.75 to 295.60) between axis (13-18)&(0-F) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2574 | cartonal coat for retaining wall from level (289.75 to 295.60) between axis (13-18)&(0-F) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2575 | Surface preparation and repair for retaining wall from level (289.75 to 295.60) between axis (1-6)&(0-F) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2576 | Primer coat for retaining wall from level (289.75 to 295.60) between axis (1-6)&(0-F) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2577 | Membrane coat for retaining wall from level (289.75 to 295.60) between axis (1-6)&(0-F) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2578 | cartonal coat for retaining wall from level (289.75 to 295.60) between axis (1-6)&(0-F) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2579 | Surface preparation and repair for retaining wall from level (289.75 to 291.25) between axis (1-2)&(E-L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2580 | Primer coat for retaining wall from level (289.75 to 291.25) between axis (1-2)&(E-L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2581 | Membrane coat for retaining wall from level (289.75 to 291.25) between axis (1-2)&(E-L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2582 | cartonal coat for retaining wall from level (289.75 to 291.25) between axis (1-2)&(E-L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2583 | Surface preparation and repair for retaining wall from level (289.75 to 290.75) between axis (3-7)/L for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2584 | Primer coat for retaining wall from level (289.75 to 290.75) between axis (3-7)/L for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2585 | Membrane coat for retaining wall from level (289.75 to 290.75) between axis (3-7)/L for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2586 | cartonal coat for retaining wall from level (289.75 to 290.75) between axis (3-7)/L for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2587 | Surface preparation and repair for retaining wall from level (289.75 to 295.60) between axis (7-11)/L for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2588 | Primer coat for retaining wall from level (289.75 to 295.60) between axis (7-11)/L for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2589 | Membrane coat for retaining wall from level (289.75 to 295.60) between axis (7-11)/L for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2590 | cartonal coat for retaining wall from level (289.75 to 295.60) between axis (7-11)/L for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2591 | Surface preparation and repair for retaining wall from level (289.75 to 291.75) between axis (11-16)/L for area (P3&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2592 | Primer coat for retaining wall from level (289.75 to 291.75) between axis (11-16)/L for area (P3&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2593 | Membrane coat for retaining wall from level (289.75 to 291.75) between axis (11-16)/L for area (P3&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2594 | cartonal coat for retaining wall from level (289.75 to 291.75) between axis (11-16)/L for area (P3&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43339 | 43356 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2595 | Check bottom reinforcement for R.C RAFT foundation between axes (5-6) &(0-A) with (TOC = 290.75) for area (P6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.C | 43341 | 43344 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2596 | Check top reinforcement for R.C RAFT foundation between axes (5-6) &(0-A) with (TOC = 290.75) for area (P6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.C | 43341 | 43344 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2597 | Pouring request for R.C RAFT foundation between axes (5-6) &(0-A) with (TOC = 290.75) for area (P6) As Per Attached Sketch. | STR | Concreting | Concreting | R.C | 43341 | 43344 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2598 | Check bottom reinforcement for R.C SLAB at level (299.0) between axis (6-10)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43341 | 43344 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2599 | Check TOP reinforcement for R.C SLAB at level (299.0) between axis (6-10)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43341 | 43344 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2600 | Pouring request for R.C SLAB at level (299.0) between axis (6-10)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | SLAB | 43341 | 43344 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2601 | Pouring request for S.O.G between axes (1-18) & (A-L) with (TOC = 291.80 ) for area (Z1,2,3,5) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43341 | 43344 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2602 | Check bottom reinforcement for R.C SLAB at level (299.0) between axis (9-13)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43347 | 43349 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2603 | Check TOP reinforcement for R.C SLAB at level (299.0) between axis (9-13)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43347 | 43349 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2604 | Pouring request for R.C SLAB at level (299.0) between axis (9-13)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | SLAB | 43347 | 43349 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2605 | Check RFT For R.C SLAB For external ramp between axes (6-7)&(A-C) at LEVEL(300.10) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43347 | 43349 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2606 | pouring request For R.C SLAB For external ramp between axes (6-7)&(A-C) at LEVEL(300.10) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | SLAB | 43347 | 43349 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2607 | Check injection for water tank walls between axies (G-L) (1-2) at second basement for area (Z4) As Per Attached Sketch. | STR | water proofing | water proofing | B2 | 43355 | 43373 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2608 | Please check TOP level FOR S.O.G level (291.80) between axis (2-5)&(A-B) for area (P5) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43358 | 43359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2609 | Please check level for backfilling of S.O.G level (291.60) between axis (2-5)&(A-B) for area (P5) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43358 | 43359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2610 | Please check TOP level FOR S.O.G level (291.80) between axis (2-10)&(L-F) for area (P3,P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43358 | 43359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2611 | Please check level for backfilling of S.O.G level (291.60) between axis (2-10)&(L-F) for area (P3,P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43358 | 43359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2612 | Please check TOP level FOR S.O.G level (291.80) between axis (13-15)&(L-F) for area (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43358 | 43359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2613 | Please check level for backfilling of S.O.G level (291.60) between axis (13-15)&(L-F) for area (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43358 | 43359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2614 | Please check TOP level FOR S.O.G level (291.80) between axis (13-17)&(F-A) for area (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43358 | 43359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2615 | Please check level for backfilling of S.O.G level (291.60) between axis (13-17)&(F-A) for area (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43358 | 43359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2616 | Plane concrete (p.c) for area extention at level (290.25) between axis (9-10)&(A-B) As Per Attached Sketch. | STR | LEVELS | LEVELS | P.C | 43358 | 43359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2617 | Offset 50cm for columns at axies (11-13)&(A-F) for area (P6) As Per Attached Sketch. | STR | Setting out | Setting out | COL. | 43358 | 43359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2618 | Check Top level for slab between axes (10-13) & (A-F) with (TOC = 299.00 ) - PART (P6)As Per Attached Sketch. | STR | LEVELS | LEVELS | SLAB | 43358 | 43359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2619 | Check Top level for slab between axes (6-10) & (A-F) with (TOC = 299.00 ) - PART (P6)As Per Attached Sketch. | STR | LEVELS | LEVELS | SLAB | 43358 | 43359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2620 | Check fixation of corrugated sheets of steel structure at 8th floor (333.10) between axies (F-L)&(9-10) AT (Zone 3) )As Per Attached Sketch.. | STR | Steel | Steel | 7th | 43360 | 43368 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2621 | Check fixation of corrugated sheets of steel structure at 9th floor (338.10) between axies (F-L)&(9-10) AT (Zone 3) )As Per Attached Sketch.. | STR | Steel | Steel | 8th | 43361 | 43372 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2622 | Check Reinforcement for R.C deck of steel structure at 8th floor (333.10) between axies (F-L)&(9-10) AT (Zone 3) )As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 7th | 43361 | 43368 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2623 | Check Reinforcement for R.C deck of steel structure at 9th floor (338.10) between axies (F-L)&(9-10) AT (Zone 3) )As Per Attached Sketch.. | STR | Reinforcement | Reinforcement | 8th | 43361 | 43372 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2624 | Pouring request for slab deck of steel structure at 8th floor (333.10) between axies (F-L)&(9-10) AT (Zone 3) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43361 | 43368 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2625 | Pouring request for slab deck of steel structure at 9th floor (338.10) between axies (F-L)&(9-10) AT (Zone 3) As Per Attached Sketch. | STR | Concreting | Concreting | 8th | 43361 | 43372 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2626 | INSTALLATION AND FIXATION OF STEEL BEAMS between axes (9-10) & (F-K) AT 10th FLOOR (344.10) for area (Z3) As Per Attached Sketch . | STR | Steel | Steel | 9th | 43363 | 43368 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2627 | Check fixation of corrugated sheets of steel structure at 7th floor (328.10) between axies (F-L)&(9-10) AT (Zone 3) )As Per Attached Sketch.. | STR | Steel | Steel | 6th | 43365 | 43372 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2628 | Check RFT for retaining wall from level (290.55 to 295.60) between axis (5-7) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2629 | Check formwork fo retaining walls from level (290.55 to 295.60) between axis (5-7) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | R.W | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2630 | Pouring request for retaining wall from level (290.55 to 295.60) between axis (5-7) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2631 | Pouring request for plain concrete at level (289.70) between axis (9-10)&(0-B) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2632 | Surface preparaiton and repair for plain concrete at level (289.70) between axis (9-10)&(0-B) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2633 | primer coat for plain concrete at level (289.70) between axis (9-10)&(0-B) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2634 | membrane coat for plain concrete at level (289.70) between axis (9-10)&(0-B) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2635 | protection board(3mm) for membrane of plain concrete at level (289.70) between axis (9-10)&(0-B) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2636 | Pouring request for plain concrete (screed 5cm) at level (289.75) between axis (9-10)&(0-B) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2637 | Check bottom reinforcement for R.C RAFT foundation between axes (8-11) &(0-C) with (TOC = 290.55) for area (P6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.C | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2638 | Check top reinforcement for R.C RAFT foundation between axes (8-11) &(0-C) with (TOC = 290.55) for area (P6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.C | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2639 | Pouring request for R.C RAFT foundation between axes (8-11) &(0-C) with (TOC = 290.55) for area (P6) As Per Attached Sketch. | STR | Concreting | Concreting | R.C | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2640 | Check RFT for Columns from level (290.55 to 295.60) between axis(6-10)&(0-B) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | COL. | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2641 | Check formwork for Columns from level (290.55 to 295.60) between axis(6-10)&(0-B) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | COL. | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2642 | Pouring request for Columns from level (290.55 to 295.60) between axis(6-10)&(0-B) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | COL. | 43366 | 43368 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2643 | Check Top level for slab deck of steel structure between axes (9-10) & (G-K) with (TOC = 328.10 ) - PART (P3)As Per Attached Sketch. | STR | LEVELS | LEVELS | 6th | 43372 | 43376 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2644 | Check Top level for slab deck of steel structure between axes (9-10) & (G-K) with (TOC = 333.10 ) - PART (P3)As Per Attached Sketch. | STR | LEVELS | LEVELS | 7th | 43372 | 43376 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2645 | Check Top level for slab deck of steel structure between axes (9-10) & (G-K) with (TOC = 338.10 ) - PART (P3)As Per Attached Sketch. | STR | LEVELS | LEVELS | 8th | 43372 | 43376 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2646 | Check setting out of points from axis for façade elevation 3-Z4 as per Attached Sketch. | STR | Setting out | Setting out | - | 43372 | 43376 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2647 | Check setting out of points from axis for façade elevation 2-Z4 as per Attached Sketch. | STR | Setting out | Setting out | - | 43372 | 43376 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2648 | Check setting out of points from axis for façade elevation 4-Z1 as per Attached Sketch. | STR | Setting out | Setting out | - | 43372 | 43376 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2649 | Check RFT For R.C SLAB For external ramp between axes (12-13)&(A-C) at LEVEL(300.10) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43372 | 43374 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2650 | pouring request For R.C SLAB For external ramp between axes (12-13)&(A-C) at LEVEL(300.10) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | SLAB | 43372 | 43374 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2651 | Check bottom reinforcement for R.C RAFT foundation between axes (12-14) &(0-A) with (TOC = 290.75) for area (P6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.C | 43372 | 43374 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2652 | Check top reinforcement for R.C RAFT foundation between axes (12-14) &(0-A) with (TOC = 290.75) for area (P6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.C | 43372 | 43374 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2653 | Pouring request for R.C RAFT foundation between axes (12-14) &(0-A) with (TOC = 290.75) for area (P6) As Per Attached Sketch. | STR | Concreting | Concreting | R.C | 43372 | 43374 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2654 | Check fixation of corrugated sheets of steel structure at 10th floor (344.10) between axies (F-L)&(9-10) AT (Zone 3) )As Per Attached Sketch.. | STR | Steel | Steel | 9th | 43374 | 43376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2655 | Check Reinforcement for R.C deck of steel structure at 7th floor (328.10) between axies (F-L)&(9-10) AT (Zone 3) )As Per Attached Sketch.. | STR | Reinforcement | Reinforcement | 6th | 43379 | 43383 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2656 | Pouring request for slab deck of steel structure at 7th floor (328.10) between axies (F-L)&(9-10) AT (Zone 3) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43379 | 43383 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2657 | Check Reinforcement for R.C deck of steel structure at 10th floor (344.10) between axies (F-L)&(9-10) AT (Zone 3) )As Per Attached Sketch.. | STR | Reinforcement | Reinforcement | 9th | 43379 | 43383 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2658 | Pouring request for slab deck of steel structure at 10th floor (344.10) between axies (F-L)&(9-10) AT (Zone 3) As Per Attached Sketch. | STR | Concreting | Concreting | 9th | 43379 | 43383 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2659 | Check bottom reinforcement for R.C SLAB at level (295.60) between axis (8-11)&(0-C) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43381 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2660 | Check TOP reinforcement for R.C SLAB at level (295.60) between axis (8-11)&(0-C) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43381 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2661 | Pouring request for R.C SLAB at level (295.60) between axis (8-11)&(0-C) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | SLAB | 43381 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2662 | Check RFT for Columns from level (295.60 to 299.00) between axis(9-10)&(0-B) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | COL. | 43381 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2663 | Check formwork for Columns from level (295.60 to 299.00) between axis(9-10)&(0-B) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | COL. | 43381 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2664 | Pouring request for Columns from level (295.60 to 299.00) between axis(9-10)&(0-B) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | COL. | 43381 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2665 | Check RFT for Retaining wall from level (290.55 to 295.60) between axis (8-11) for area ZONE (6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43381 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2666 | Check formwork fo Retaining wall from level (290.55 to 295.60) between axis (8-11) for area ZONE (6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | R.W | 43381 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2667 | Pouring request for Retaining wall from level (290.55 to 295.60) between axis (8-11) for area ZONE (6) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43381 | 43390 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2668 | Check RFT for Retaining wall from level (295.60 to 299.00) between axis (8-11) for area ZONE (6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43381 | 43390 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2669 | Check formwork fo Retaining wall from level (295.60 to 299.00) between axis (8-11) for area ZONE (6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | R.W | 43381 | 43390 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2670 | Pouring request for Retaining wall from level (295.60 to 299.00) between axis (8-11) for area ZONE (6) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43381 | 43390 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2671 | Check RFT for stair NO.(3B) from level ( 338.20 to 344.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 9th | 43381 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2672 | Pouring request for stair NO.(3B) from level ( 338.20 to 344.20) between axis (6-8)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 9th | 43381 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2673 | Pouring request for Plain concrete for external ramp (2) axes (1-3)/L from level (294.20 to 297.18) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43383 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2674 | Surface preparation and repair for Plain concrete foundation of External ramp (2) between axis (1-3)/(L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43383 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2675 | Primer coat for Plain concrete for external ramp (2) axes (1-3)/L from level (294.20 to 297.18) for area (Z4) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43383 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2676 | Membrane coat for Plain concrete for external ramp (2) axes (1-3)/L from level (294.20 to 297.18) for area (Z4) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43383 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2677 | Protection Board For Membrane coat for Plain concrete for external ramp (2) axes (1-3)/L from level (294.20 to 297.18) for area (Z4) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43383 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2678 | Pouring request for plain concrete (screed 5cm) for external ramp (2) at level (294.25 TO 297.23) between axis (1-3)/(L) for area for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43383 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2679 | Check bottom reinforcement for R.C SLAB at level (299.00) between axis (8-11)&(0-C) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43383 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2680 | Check TOP reinforcement for R.C SLAB at level (299.00) between axis (8-11)&(0-C) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43383 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2681 | Pouring request for R.C SLAB at level (299.00) between axis (8-11)&(0-C) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | SLAB | 43383 | 43387 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2682 | Please check TOP level FOR S.O.G level (291.80) between axis (15-17)&(E-F) for area (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43390 | 43395 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2683 | Please check level for backfilling of S.O.G level (291.60) between axis (15-17)&(E-F) for area (P1) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | S.O.G | 43390 | 43395 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2684 | Please check TOP level FOR S.O.G level (291.80) between axis (15-18)&(F-L) for area (P2) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43390 | 43395 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2685 | Please check level for backfilling of S.O.G level (291.60) between axis (15-18)&(F-L) for area (P2) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | S.O.G | 43390 | 43395 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2686 | Please check TOP level FOR S.O.G level (291.80) between axis (6-14)&(F-L) for area (P3) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43390 | 43395 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2687 | Please check level for backfilling of S.O.G level (291.60) between axis (6-14)&(F-L) for area (P3) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | S.O.G | 43390 | 43395 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2688 | Please check TOP level FOR S.O.G level (291.80) between axis (3-4)&(G-J) for area (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43390 | 43395 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2689 | Please check level for backfilling of S.O.G level (291.60) between axis (3-4)&(G-J) for area (P4) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | S.O.G | 43390 | 43395 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2690 | Please check TOP level FOR S.O.G level (291.80) between axis (1-6)&(E-G) for area (P5) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43390 | 43395 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2691 | Please check level for backfilling of S.O.G level (291.60) between axis (1-6)&(E-G) for area (P5) As Per Attached Sketch. | STR | BACKFILLING | BACKFILLING | S.O.G | 43390 | 43395 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2692 | Excavation level for EXTERNAL RAMP (293.58 TO 293.60) for area (1-3)(K-L) AT ZONE(4) As Per Attached Sketch. | STR | LEVELS | LEVELS | Excavation | 43396 | 43398 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2693 | First Layer For Replacement For EXTERNAL ramp Area (1-3)(K-L) At Level (296.83 TO 294.15) AT ZONE(4) As Per Sketch Attached. | STR | LEVELS | LEVELS | Rep. | 43396 | 43398 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2694 | Second Layer For Replacement For EXTERNAL ramp Area (1-3)(K-L) At Level (297.08 TO 294.40) AT ZONE (4) As Per Sketch Attached. | STR | LEVELS | LEVELS | Rep. | 43396 | 43398 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2695 | Plane concrete (p.c) for area EXTERNAL ramp at level (297.23 TO 294.25) AT ZONE (4) As Per Attached Sketch. | STR | LEVELS | LEVELS | P.C | 43396 | 43398 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2696 | Please check (R.C) for area EXTERNAL ramp at level (297.73 TO 294.75) AT ZONE (4) As Per Attached Sketch. | STR | LEVELS | LEVELS | R.C | 43396 | 43398 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2697 | Check RFT For R.C Foundation For external ramp (2) axes (1-3)/L from level (294.75 to 297.73) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.C | 43396 | 43398 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2698 | Pouring request For R.C Foundation For external ramp (2) axes (1-3)/L from level (294.75 to 297.73) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | R.C | 43396 | 43398 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2699 | Check RFT for stair NO.(3A) from level ( 333.20 to 338.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 8th | 43407 | 43409 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2700 | Pouring request for stair NO.(3A) from level ( 333.20 to 338.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 8th | 43407 | 43409 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2701 | Check RFT for stair NO.(3A) from level ( 338.20 to 344.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 9th | 43407 | 43409 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2702 | Pouring request for stair NO.(3A) from level ( 338.20 to 344.20) between axis (11-13)&(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 9th | 43407 | 43409 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2703 | Check setting out of points from axis for façade elevation 1-Z1 as per Attached Sketch. | STR | Setting out | Setting out | - | 43407 | 43409 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2704 | Check setting out of points from axis for façade elevation 6-Z1 as per Attached Sketch. | STR | Setting out | Setting out | - | 43407 | 43409 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2705 | Check setting out of points from axis for façade elevation 1-Z2 as per Attached Sketch. | STR | Setting out | Setting out | - | 43407 | 43409 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2706 | Check setting out of points from axis for façade elevation 2-Z2 as per Attached Sketch. | STR | Setting out | Setting out | - | 43407 | 43409 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2707 | Check setting out of points from axis for façade elevation 4-Z5 as per Attached Sketch. | STR | Setting out | Setting out | - | 43407 | 43409 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2708 | Check setting out of points from axis for façade elevation 3-Z5 as per Attached Sketch. | STR | Setting out | Setting out | - | 43407 | 43409 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2709 | Check setting out of points from axis for façade elevation 5-Z5 as per Attached Sketch. | STR | Setting out | Setting out | - | 43407 | 43409 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2710 | Check RFT For retaining wall of external ramp (2) between axes (1-3)/L from level (299.22 to 299.985) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43412 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2711 | Check formwork For retaining wall of external ramp (2) between axes (1-3)/L from level (299.22 to 299.985) for area (Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | R.W | 43412 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2712 | pouring request For retaining wall of external ramp (2) between axes (1-3)/L from level (299.22 to 299.985) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43412 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2713 | Check RFT For R.C SLAB For external ramp (2) between axes (1-3)/L at LEVEL(299.30) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | SLAB | 43412 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2714 | pouring request For R.C SLAB For external ramp (2) between axes (1-3)/L at LEVEL(299.30) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | SLAB | 43412 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2715 | Check RFT for retaining wall from level (290.75 to 295.60) between axis (0-A)/13 for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43412 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2716 | Check formwork for retaining wall from level (290.75 to 295.60) between axis (0-A)/13 for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | R.W | 43412 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2717 | Pouring request for retaining wall from level (290.75 to 295.60) between axis (0-A)/13 for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43412 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2718 | Check RFT for Columns from level (290.75 to 295.60) between axis(0-A)/(13) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | COL. | 43412 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2719 | Check formwork for Columns from level (290.75 to 295.60) between axis(0-A)/(13) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | COL. | 43412 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2720 | Pouring request for Columns from level (290.75 to 295.60) between axis(0-A)/(13) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | COL. | 43412 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2721 | Please check SLAB for area ramp (2) at level (299.22&299.985&299.30 ) For area ZONE(4) As Per Attached Sketch. | STR | Setting out | Setting out | SLAB | 43414 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2722 | Please check axis of internal masonary second floor between axis (A-F)&(1-7) For area Zone (5) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43414 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2723 | Please check axis of internal masonary second floor between axis (F-L)&(1-7) For area Zone (4) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43414 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2724 | Please check axis of internal masonary second floor between axis (F-L)&(12-18) For area Zone (2) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43414 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2725 | Please check axis of internal masonary second floor between axis (A-F)&(12-18) For area Zone (1) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43414 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2726 | Please check axis of internal masonary THIRD floor between axis (A-F)&(1-7) For area Zone (5) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43414 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2727 | Please check axis of internal masonary THIRD floor between axis (F-L)&(1-7) For area Zone (4) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43414 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2728 | Please check axis of internal masonary THIRD floor between axis (F-L)&(6-9) For area Zone (3) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43414 | 43418 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2729 | Pouring Sloped plain concrete with fiber for the roof level (324.10) between axis (A-F)&(1-6) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43417 | 43422 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2730 | Pouring Sloped plain concrete with fiber for the roof level (324.10) between axis (A-F)&(13-18) for area (P1) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43417 | 43422 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2731 | Check Sloped concrete level for the Upper roof level (328.80) between axis (B-E)&(3-4) for area (P5) As Per Attached Sketch. | STR | LEVELS | LEVELS | 7th | 43422 | 43428 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2732 | Check Sloped concrete level for the Upper roof level (338.10) between axis (G-K)&(2-5) for area (P4) As Per Attached Sketch. | STR | LEVELS | LEVELS | 9th | 43422 | 43428 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2733 | Check Level and Location for anchor bolts of steel structure for Canopy between axis (G-K)&(7-12) for area Z3 as Per Attached Sketch. | STR | LEVELS | LEVELS | canopy | 43422 | 43428 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2734 | Check fixation of corrugated sheets of steel structure at 2ND floor (308.10) between axies (G-K)&(9-10) AT (Zone 3) )As Per Attached Sketch. | STR | Steel | Steel | 1st | 43425 | 43429 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2735 | Check Reinforcement for R.C deck of steel structure at 2ND floor (308.10) between axies (G-K)&(9-10) AT (Zone 3) )As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43425 | 43429 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2736 | Pouring request for slab deck of steel structure at 2ND floor (308.10) between axies (G-K)&(9-10) AT (Zone 3) )As Per Attached Sketch.. | STR | Concreting | Concreting | 1st | 43425 | 43429 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2737 | Check Top level for slab deck of steel structure between axes (9-10) & (G-K) with (TOC = 308.10 ) - PART (P3)As Per Attached Sketch. | STR | LEVELS | LEVELS | 1st | 43430 | 43437 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2738 | Check Sloped concrete level for the Upper roof level (328.10) between axis (B-E)&(15-16) for area (P1) As Per Attached Sketch. | STR | LEVELS | LEVELS | 7th | 43430 | 43437 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2739 | Please check axis of internal masonary First floor between axis (A-F)&(12-18) For area Zone (1) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43430 | 43437 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2740 | Please check axis of internal masonary First floor between axis (L-F)&(13-18) For area Zone (2) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43430 | 43437 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2741 | Please check axis of internal masonary First floor between axis (L-F)&(10-13) For area Zone (3) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43430 | 43437 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2742 | Please check axis of internal masonary First floor between axis (A-F)&(1-6) For area Zone (5) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43430 | 43437 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2743 | Please check axis of internal masonary Third floor between axis (F-L)&(10-13) For area Zone (3) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2744 | Please check axis of internal masonary Third floor between axis (F-L)&(13-18) For area Zone (2) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2745 | Please check axis of internal masonary Third floor between axis (A-F)&(13-18) For area Zone (1) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2746 | Please check axis of internal masonary FIRST floor between axis (F-L)&(1-6) For area Zone (4) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2747 | Please check axis of internal masonary FIRST floor between axis (F-L)&(7-9) For area Zone (3) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2748 | Surface preparation and repair for retaining wall from level (295.60 to 298.85) between axis (17-18)&(E-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2749 | Primer coat for retaining wall from level (295.60 to 298.85) between axis (17-18)&(E-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2750 | Membrane coat for retaining wall from level (295.60 to 298.85) between axis (17-18)&(E-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2751 | cartonal coat for retaining wall from level (295.60 to 298.85) between axis (17-18)&(E-L) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2752 | Surface preparation and repair for retaining wall from level (295.60 to 298.85) between axis (17-18)&(0-F) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2753 | Primer coat for retaining wall from level (295.60 to 298.85) between axis (17-18)&(0-F) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2754 | Membrane coat for retaining wall from level (295.60 to 298.85) between axis (17-18)&(0-F) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2755 | cartonal coat for retaining wall from level (295.60 to 298.85) between axis (17-18)&(0-F) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2756 | Surface preparation and repair for retaining wall from level (295.60 to 297.50) between axis (13-18)/0 for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2757 | Primer coat for retaining wall from level (295.60 to 297.50) between axis (13-18)/0 for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2758 | Membrane coat for retaining wall from level (295.60 to 297.50) between axis (13-18)/0 for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2759 | cartonal coat for retaining wall from level (295.60 to 297.50) between axis (13-18)/0 for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2760 | Surface preparation and repair for retaining wall from level (295.60 to 297.50) between axis (1-6)&(0-F) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2761 | Primer coat for retaining wall from level (295.60 to 297.50) between axis (1-6)&(0-F) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2762 | Membrane coat for retaining wall from level (295.60 to 297.50) between axis (1-6)&(0-F) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2763 | cartonal coat for retaining wall from level (295.60 to 297.50) between axis (1-6)&(0-F) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2764 | Surface preparation and repair for retaining wall from level (291.25 to 297.10) between axis (1-2)&(E-L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2765 | Primer coat for retaining wall from level (291.25 to 297.10) between axis (1-2)&(E-L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2766 | Membrane coat for retaining wall from level (291.25 to 297.10) between axis (1-2)&(E-L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2767 | cartonal coat for retaining wall from level (291.25 to 297.10) between axis (1-2)&(E-L) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2768 | Surface preparation and repair for retaining wall from level (295.60 to 297.00) between axis (7-11)/L for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2769 | Primer coat for retaining wall from level (295.60 to 297.00) between axis (7-11)/L for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2770 | Membrane coat for retaining wall from level (295.60 to 297.00) between axis (7-11)/L for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2771 | cartonal coat for retaining wall from level (295.60 to 297.00) between axis (7-11)/L for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2772 | Surface preparation and repair for retaining wall from level (291.75 to 299.00) between axis (11-16)/L for area (P3&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2773 | Primer coat for retaining wall from level (291.75 to 299.00) between axis (11-16)/L for area (P3&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2774 | Membrane coat for retaining wall from level (291.75 to 299.00) between axis (11-16)/L for area (P3&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2775 | cartonal coat for retaining wall from level (291.75 to 299.00) between axis (11-16)/L for area (P3&P2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2776 | Pouring Sloped plain concrete with fiber for the upper roof at level (337.80) between axis (G-K)&(2-5) for area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | 9th | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2777 | Pouring Sloped plain concrete with fiber for the upper roof at level (328.80) between axis (A-F)&(2-5) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2778 | Pouring Sloped plain concrete with fiber for the roof at level (333.10) between axis (G-K)&(2-5) for area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | 8th | 43432 | 43442 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2779 | Please check axis of internal masonary Fourth floor between axis (F-L)&(10-13) For area Zone (3A) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43435 | 43437 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2780 | Please check axis of internal masonary Fourth floor between axis (F-L)&(13-18) For area Zone (2) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43435 | 43437 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2781 | Please check axis of internal masonary Fourth floor between axis (A-F)&(13-18) For area Zone (1) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43435 | 43437 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2782 | Please check axis of internal masonary Fourth floor between axis (F-L)&(7-9) For area Zone (3B) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43435 | 43437 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2783 | Please check axis of internal masonary Fourth floor between axis (F-L)&(1-6) For area Zone (4) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43435 | 43437 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2784 | Please check axis of internal masonary Fourth floor between axis (A-F)&(1-6) For area Zone (5) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43435 | 43437 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2785 | Check Sloped concrete level for the Upper roof level (338.80) between axis (G-K)&(14-17) for area (P5) As Per Attached Sketch. | STR | Setting out | Setting out | 9th | 43435 | 43437 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2786 | Please check axis of internal masonary fifth floor between axis (A-F)&(1-6) For area Zone (5) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43443 | 43450 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2787 | Please check axis of internal masonary fifth floor between axis (F-L)&(1-6) For area Zone (4) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43443 | 43450 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2788 | Please check axis of internal masonary fifth floor between axis (F-L)&(6-9) For area Zone (3) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43443 | 43450 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2789 | Please check axis of internal masonary fifth floor between axis (F-L)&(10-13) For area Zone (3) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43443 | 43450 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2790 | Please check axis of internal masonary fifth floor between axis (F-L)&(13-18) For area Zone (2) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43443 | 43450 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2791 | Please check axis of internal masonary fifth floor between axis (A-F)&(13-18) For area Zone (1) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43443 | 43450 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2792 | Check Sloped concrete level for the roof level (333.10) between axis (G-K)&(14-17) for area (P2) As Per Attached Sketch. | STR | Setting out | Setting out | 8th | 43443 | 43450 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2793 | Please check axis of internal masonary sixth floor between axis (F-L)&(1-9) For area Zone (3B&4) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43443 | 43450 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2794 | Please check axis of internal masonary sixth floor between axis (F-L)&(10-18) For area Zone (3A&2) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43443 | 43450 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2795 | Please check axis of internal masonary seventh floor between axis (L-G)&(1-6) For area Zone (3B&4) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43454 | 43459 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2796 | Please check axis of internal masonary seventh floor between axis (L-F)&(10-18) For area Zone (3A&2) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43454 | 43459 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2797 | Please check axis of internal masonary 8th floor between axis (L-F)&(7-13) For area Zone (3A&3B) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43454 | 43459 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2798 | Please check axis of internal masonary ground floor between axis (A-L)&(1-9) For area Zone (4&5&3B) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43454 | 43459 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2799 | Please check axis of internal masonary ground floor between axis (A-L)&(10-18) For area Zone (1&2&3A) As Per Attached Sketch. | STR | Setting out | Setting out | - | 43454 | 43459 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2800 | Check tighting torque for anchor bolts of steel beams of canopy for roof at level (350.600) at zone(3) As Per Attached Sketch. | STR | Steel | Steel | canopy | 43458 | 43467 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2801 | FIRST Primer coat for Raft and blockwork under S.O.G between axis (5-14)/(A-F) for area (P6) As Per Attached Sketch. | STR | water proofing | water proofing | COLD APP | 43465 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2802 | Second Primer coat for Raft and blockwork under S.O.G between axis (5-14)/(A-F) for area (P6) As Per Attached Sketch. | STR | water proofing | water proofing | COLD APP | 43465 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2803 | Third Primer coat for Raft and blockwork under S.O.G between axis (5-14)/(A-F) for area (P6) As Per Attached Sketch. | STR | water proofing | water proofing | COLD APP | 43465 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2804 | Surface preparation and repair for retaining wall from level (289.70 to 291.75) between axis (5-14)/A for area (P6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43465 | 43480 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2805 | Primer coat for retaining wall from level (289.70 to 291.75) between axis (5-14)/A for area (P6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43465 | 43480 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2806 | Membrane coat for retaining wall from level (289.70 to 291.75) between axis (5-14)/A for area (P6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43465 | 43480 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2807 | cartonal coat for retaining wall from level (289.70 to 291.75) between axis (5-14)/A for area (P6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43465 | 43480 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2808 | Surface preparation and repair for retaining wall & foundation of External ramp between axis (16-18)/(L) for area (P2) from foundation level to (295.60) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2809 | Primer coat for retaining wall & foundation of External ramp between axis (16-18)/(L) for area (P2) from foundation level to (295.60) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2810 | Membrane coat for retaining wall & foundation of External ramp between axis (16-18)/(L) for area (P2) from foundation level to (295.60) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2811 | cartonal coat for retaining wall & foundation of External ramp between axis (16-18)/(L) for area (P2) from foundation level to (295.60) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2812 | Surface preparation and repair for retaining wall & foundation of External ramp between axis (16-18)/(L) for area (P2) from level(295.60 to 298.10) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2813 | Primer coat for retaining wall & foundation of External ramp between axis (16-18)/(L) for area (P2) from level(295.60 to 298.10) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2814 | Membrane coat for retaining wall & foundation of External ramp between axis (16-18)/(L) for area (P2) from level(295.60 to 298.10) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2815 | cartonal coat for retaining wall & foundation of External ramp between axis (16-18)/(L) for area (P2) from level(295.60 to 298.10) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2816 | Surface preparation and repair for retaining wall & foundation of External ramp between axis (1-3)/(L) for area (P4) from foundation level to (295.60) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2817 | Primer coat for retaining wall & foundation of External ramp between axis (1-3)/(L) for area (P4) from foundation level to (295.60) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2818 | Membrane coat for retaining wall & foundation of External ramp between axis (1-3)/(L) for area (P4) from foundation level to (295.60) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2819 | cartonal coat for retaining wall & foundation of External ramp between axis (1-3)/(L) for area (P4) from foundation level to (295.60) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2820 | Surface preparation and repair for retaining wall of External ramp between axis (1-3)/(L) for area (P4) from level(295.60 to 298.10) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2821 | Primer coat for retaining wall of External ramp between axis (1-3)/(L) for area (P4) from level(295.60 to 298.10) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2822 | Membrane coat for retaining wall of External ramp between axis (1-3)/(L) for area (P4) from level(295.60 to 298.10) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2823 | cartonal coat for retaining wall of External ramp between axis (1-3)/(L) for area (P4) from level(295.60 to 298.10) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2824 | first Primer coat for retaining wall & foundation for external ramp between axes (1-3)/L from level (294.20 to 297.18) for area (Z4) As Per Attached Sketch. | STR | water proofing | water proofing | COLD APP | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2825 | second Primer coat for retaining wall & foundation for external ramp between axes (1-3)/L from level (294.20 to 297.18) for area (Z4) As Per Attached Sketch. | STR | water proofing | water proofing | COLD APP | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2826 | third Primer coat for retaining wall & foundation for external ramp between axes (1-3)/L from level (294.20 to 297.18) for area (Z4) As Per Attached Sketch. | STR | water proofing | water proofing | COLD APP | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2827 | Check RFT for Columns from level (290.55 to 295.60) between axis(A-F)/(10-13) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | COL. | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2828 | Check formwork for Columns from level (290.55 to 295.60) between axis(A-F)/(10-13) for area (Z6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | COL. | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2829 | Pouring request for Columns from level (290.55 to 295.60) between axis(A-F)/(10-13) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | COL. | 43466 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2830 | Surface preparation and repair for retaining wall between axis (3-7)/(L) for area (P4) from level(290.75 to 295.60) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43475 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2831 | Primer coat for retaining wall between axis (3-7)/(L) for area (P4) from level(290.75 to 295.60) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43475 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2832 | Membrane coat for retaining wall between axis (3-7)/(L) for area (P4) from level(290.75 to 295.60) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43475 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2833 | cartonal coat for retaining wall between axis (3-7)/(L) for area (P4) from level(290.75 to 295.60) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43475 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2834 | Surface preparation and repair for retaining wall between axis (1-3)/(L) for area (P4) and between axis (16-18)/(L) for area (P2) from level(289.75 to 295.60) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43475 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2835 | Primer coat for retaining wall between axis (1-3)/(L) for area (P4) and between axis (16-18)/(L) for area (P2) from level(289.75 to 295.60) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43475 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2836 | Membrane coat for retaining wall between axis (1-3)/(L) for area (P4) and between axis (16-18)/(L) for area (P2) from level(289.75 to 295.60) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43475 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2837 | cartonal coat for retaining wall between axis (1-3)/(L) for area (P4) and between axis (16-18)/(L) for area (P2) from level(289.75 to 295.60) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43475 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2838 | Surface preparation and repair for retaining wall between axis (1-2)/(L) for area (P4) from level(295.60 to 297.10) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43475 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2839 | Primer coat for retaining wall between axis (1-2)/(L) for area (P4) from level(295.60 to 297.10) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43475 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2840 | Membrane coat for retaining wall between axis (1-2)/(L) for area (P4) from level(295.60 to 297.10) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43475 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2841 | cartonal coat for retaining wall between axis (1-2)/(L) for area (P4) from level(295.60 to 297.10) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43475 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2842 | Surface preparation and repair for retaining wall between axis (17-18)/(L) for area (P2) from level(295.60 to 298.85) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43477 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2843 | Primer coat for retaining wall between axis (17-18)/(L) for area (P2) from level(295.60 to 298.85) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43477 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2844 | Membrane coat for retaining wall between axis (17-18)/(L) for area (P2) from level(295.60 to 298.85) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43477 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2845 | cartonal coat for retaining wall between axis (17-18)/(L) for area (P2) from level(295.60 to 298.85) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43477 | 43480 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2846 | Pouring Sloped plain concrete with fiber for the upper roof level (328.85) between axis (A-F)&(14-17) for area (P1) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43479 | 43484 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2847 | Pouring Sloped plain concrete with fiber for the roof level (333.15) between axis (G-K)&(14-17) for area (P2) As Per Attached Sketch. | STR | Concreting | Concreting | 8th | 43479 | 43484 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2848 | Primer coat for Sloped plain concrete with fiber for the upper roof level (337.85) between axis (G-K)&(2-5) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | 9th | 43479 | 43484 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2849 | Membrane coat for Sloped plain concrete with fiber for the upper roof level (337.85) between axis (G-K)&(2-5) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | 9th | 43479 | 43484 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2850 | Primer coat for Sloped plain concrete with fiber for the upper roof level (328.85) between axis (A-F)&(2-5) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43479 | 43484 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2851 | Membrane coat for Sloped plain concrete with fiber for the upper roof level (328.85) between axis (A-F)&(2-5) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43479 | 43484 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2852 | Primer coat for Sloped plain concrete with fiber for the upper roof level (328.85) between axis (A-F)&(14-17) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43479 | 43484 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2853 | Membrane coat for Sloped plain concrete with fiber for the upper roof level (328.85) between axis (A-F)&(14-17) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43479 | 43484 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2854 | Pouring Sloped plain concrete with fiber for the upper roof level (337.85) between axis (G-K)&(14-17) for area (P2) As Per Attached Sketch. | STR | Concreting | Concreting | 9th | 43479 | 43484 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2855 | Primer coat for Sloped plain concrete with fiber for the upper roof level (337.85) between axis (G-K)&(14-17) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | 9th | 43479 | 43484 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2856 | Membrane coat for Sloped plain concrete with fiber for the upper roof level (337.85) between axis (G-K)&(14-17) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | 9th | 43479 | 43484 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2857 | Pouring request for concrete with fiber steel for pavement at second basement at level (291.90) between axis(A-F)/(12-18) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43495 | 43505 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2858 | Pouring request for concrete with fiber steel inside rooms at second basement at level (291.90) between axis(A-F)/(12-18) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43495 | 43505 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2859 | Surface preparation and repair for corrugated sheets and steel beams at 7th floor Z3 as Per attached sketch. | STR | steel structure | steel structure | 6th | 43496 | 43500 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2860 | cementious fire protection coat for corrugated sheets and steel beams at 7th floor Z3 as Per attached sketch. | STR | steel structure | steel structure | 6th | 43496 | 43500 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2861 | Surface preparation and repair for corrugated sheets and steel beams at 2nd floor Z3 as Per attached sketch. | STR | steel structure | steel structure | 1st | 43499 | 43505 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2862 | cementious fire protection coat for corrugated sheets and steel beams at 2nd floor Z3 as Per attached sketch. | STR | steel structure | steel structure | 1st | 43499 | 43505 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2863 | Please check axis of internal masonary nineth floor between axis (F-L)&(6-13) For area Zone3 As Per Attached Sketch. | STR | Setting out | Setting out | - | 43500 | 43507 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2864 | Level and location for concrete with fiber steel for pavement at second basement at level (291.90) between axis(A-L)/(9-18) for area (Z1,2,3) As Per Attached Sketch. | STR | LEVELS | LEVELS | B2 | 43500 | 43507 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2865 | water test for the upper roof level (337.85) between axis (G-K)&(2-5) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | 9th | 43503 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2866 | water test for the upper roof level (328.85) between axis (A-F)&(2-5) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43503 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2867 | Foam coat for the upper roof level (337.85) between axis (G-K)&(2-5) for area (P4) As Per Attached Sketch. | STR | Thermal Ins. | Thermal Ins. | 9th | 43503 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2868 | Foam coat for the upper roof level (328.85) between axis (A-F)&(2-5) for area (P5) As Per Attached Sketch. | STR | Thermal Ins. | Thermal Ins. | 7th | 43503 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2869 | Geotextil for the upper roof level (337.85) between axis (G-K)&(2-5) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | 9th | 43503 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2870 | Geotextil for the upper roof level (328.85) between axis (A-F)&(2-5) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43503 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2871 | Top level of backfilling under P.C for area Extention at level (290.15 ) between axis (6-13)&(A-F) As Per Attached Sketch. | STR | LEVELS | LEVELS | Backfilling | 43505 | 43507 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2872 | Surface preparation and repair for corrugated sheets and steel beams at 9th floor Z3 as Per attached sketch. | STR | steel structure | steel structure | 8th | 43507 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2873 | cementious fire protection coat for corrugated sheets and steel beams at 9th floor Z3 as Per attached sketch. | STR | steel structure | steel structure | 8th | 43507 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2874 | Pouring request for concrete with fiber steel for pavement at second basement at level (291.90) between axis(E-L)/(6-13) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43508 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2875 | Pouring request for concrete with fiber steel for floors inside rooms at second basement at level (291.90) between axis(E-L)/(6-13) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43508 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2876 | Pouring request for concrete with fiber steel for pavement at second basement at level (291.90) between axis(E-L)/(12-18) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43508 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2877 | Pouring request for concrete with fiber steel for floors inside rooms at second basement at level (291.90) between axis(E-L)/(12-18) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43508 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2878 | Pouring request for concrete with fiber steel for pavement at second basement at level (291.90) between axis(E-L)/(1-7) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43508 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2879 | Pouring request for concrete with fiber steel for floors inside rooms at second basement at level (291.90) between axis(E-L)/(1-7) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43508 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2880 | Surface preparation and repair for corrugated sheets and steel beams at 8th floor Z3 as Per attached sketch. | STR | steel structure | steel structure | 7th | 43517 | 43520 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2881 | cementious fire protection coat for corrugated sheets and steel beams at 8th floor Z3 as Per attached sketch. | STR | steel structure | steel structure | 7th | 43517 | 43520 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2882 | Pouring request for concrete with fiber steel for pavement at second basement at level (291.90) between axis(A-F)/(1-7) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43520 | 43522 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2883 | Pouring request for concrete with fiber steel for floors inside rooms at second basement at level (291.90) between axis(A-F)/(1-7) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 43520 | 43522 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2884 | Surface preparation and repair for corrugated sheets and steel beams at 10th floor Z3 as Per attached sketch. | STR | steel structure | steel structure | 9th | 43521 | 43526 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2885 | cementious fire protection coat for corrugated sheets and steel beams at 10th floor Z3 as Per attached sketch. | STR | steel structure | steel structure | 9th | 43521 | 43526 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2886 | Check fixation of steel beams for canopy between axies (F-L)&(7-12) AT (Zone 3) )As Per Attached Sketch. | STR | steel structure | steel structure | canopy | 43524 | 43528 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2887 | Check RFT for stair from level ( 291.80 to 295.80) between axis (13-14)&(B--C) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Stair | 43537 | 43542 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2888 | Pouring request for stair from level ( 291.80 to 295.80) between axis (13-14)&(B--C) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | Stair | 43537 | 43542 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2889 | water test for the upper roof level (337.85) between axis (G-K)&(14-17) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | 9th | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2890 | Foam coat for the upper roof level (337.85) between axis (G-K)&(14-17) for area (P2) As Per Attached Sketch. | STR | Thermal Ins. | Thermal Ins. | 9th | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2891 | Geotextil for the upper roof level (337.85) between axis (G-K)&(14-17) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | 9th | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2892 | Check RFT for slab and retaining wall and column at level (295.60) between axis (5-14)/(0-A) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement |  | 43557 | 43563 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2893 | pouring request for slab and retaining wall and column at level (295.60) between axis (5-14)/(0-A) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting |  | 43557 | 43563 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2894 | Check RFT for slab and retaining wall and column at level (299.10) between axis (5-14)/(0-A) for area (Z6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement |  | 43557 | 43563 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2895 | pouring request for slab and retaining wall and column at level (299.10) between axis (5-14)/(0-A) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting |  | 43557 | 43563 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2896 | Check Touchup for painting of steel beams for canopy between axies (F-L)&(7-12) AT (Zone 3) )As Per Attached Sketch. | STR | steel structure | steel structure | canopy | 43564 | 43585 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2897 | Check RFT for stair from level ( 291.80 to 295.80) between axis (5-6)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Stair | 43564 | 43566 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2898 | Pouring request for stair from level ( 291.80 to 295.80) between axis (5-6)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | Stair | 43564 | 43566 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2899 | Check RFT for stair from level ( 295.80 to 300.10) between axis (13-14)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Stair | 43564 | 43566 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2900 | Pouring request for stair from level ( 295.80 to 300.10) between axis (13-14)&(B-C) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | Stair | 43564 | 43566 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2901 | Check RFT for stair from level ( 295.80 to 300.10) between axis (5-6)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Stair | 43564 | 43566 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2902 | Pouring request for stair from level ( 295.80 to 300.10) between axis (5-6)&(B-C) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | Stair | 43564 | 43566 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2903 | Pouring request for S.O.G between axes (5-14) & (0-F) with (TOC = 291.80 ) for area (Z6) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43572 | 43575 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2904 | Please check level for backfilling of S.O.G level (291.60) between axis (6-13)&(F-A) for area (P6) As Per Attached Sketch. | STR | LEVELS | LEVELS | Backfilling | 43578 | 43583 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2905 | Please check top level for S.O.G level (291.80) between axis (6-13)&(F-A) for area (P6) As Per Attached Sketch. | STR | LEVELS | LEVELS | Backfilling | 43578 | 43583 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2906 | Level and location for concrete with fiber steel for pavement at first basement at level (295.80) between axis(A-L)/(12-18) for area (Z1,2) As Per Attached Sketch. | STR | LEVELS | LEVELS | B1 | 43578 | 43583 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2907 | Level and location for concrete with fiber steel for pavement at first basement at level (295.80) between axis(F-L)/(5-11) for area (Z3) As Per Attached Sketch. | STR | LEVELS | LEVELS | B1 | 43578 | 43583 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2908 | Level and location for concrete with fiber steel for pavement at first basement at level (295.80) between axis(A-L)/(1-5) for area (Z4,5) As Per Attached Sketch. | STR | LEVELS | LEVELS | B1 | 43578 | 43583 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2909 | Level and location for concrete with fiber steel for pavement at first basement at level (295.80) between axis(F-L)/(6-13) for area (Z6) As Per Attached Sketch. | STR | LEVELS | LEVELS | B1 | 43578 | 43583 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2910 | Pouring request for concrete with fiber steel for pavement at first basement at level (295.80) between axis(0-L)/(1-18) for area (Z1,2,3,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43582 | 43596 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2911 | Check RFT of R.C slab of elevator pit at level (288.80) between axis (3-4)/(G-H) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2912 | pouring request of R.C slab of elevator pit at level (288.80) between axis (3-4)/(G-H) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2913 | Check RFT of R.C slab of elevator pit at level (288.80) between axis (3-4)/(H-J) for area (Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2914 | pouring request of R.C slab of elevator pit at level (288.80) between axis (3-4)/(H-J) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2915 | Check RFT of R.C slab of elevator pit at level (288.80) between axis (8-9)/(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2916 | pouring request of R.C slab of elevator pit at level (288.80) between axis (8-9)/(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2917 | Check RFT of R.C slab of elevator pit at level (288.80) between axis (10-11)/(H-J) for area (Z3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2918 | pouring request of R.C slab of elevator pit at level (288.80) between axis (10-11)/(H-J) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2919 | Check RFT of R.C slab of elevator pit at level (288.80) between axis (15-16)/(H-J) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2920 | pouring request of R.C slab of elevator pit at level (288.80) between axis (15-16)/(H-J) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2921 | Check RFT of R.C slab of elevator pit at level (288.80) between axis (15-16)/(G-H) for area (Z2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2922 | pouring request of R.C slab of elevator pit at level (288.80) between axis (15-16)/(G-H) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2923 | Check RFT of R.C slab of elevator pit at level (288.80) between axis (15-16)/(D-E) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2924 | pouring request of R.C slab of elevator pit at level (288.80) between axis (15-16)/(D-E) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | Elev. Pit | 43594 | 43597 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2925 | Pouring request for concrete with plastic fiber (screed 10cm) at first basment (295.80) between axis (13-18)&(0-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43631 | 43636 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2926 | Pouring request for concrete with plastic fiber (screed 10cm) at first basment (295.80) between axis (12-18)&(E-L) for area (Z2) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43631 | 43636 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2927 | Pouring request for concrete with plastic fiber (screed 10cm) at first basment (295.80) between axis (6-13)&(E-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43631 | 43636 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2928 | Pouring request for concrete with plastic fiber (screed 10cm) at first basment (295.80) between axis (1-7)&(E-L) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43631 | 43636 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2929 | Pouring request for concrete with plastic fiber (screed 10cm) at first basment (295.80) between axis (1-7)&(0-F) for area (Z5) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43631 | 43636 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2930 | Pouring request for concrete with plastic fiber (screed 10cm) at first basment (295.80) between axis (5-14)&(0-F) for area (Z6) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 43631 | 43636 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2931 | Pouring request for concrete with plastic fiber (screed 10cm) at first floor (304.10) between axis (15-16)&(C-D) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43634 | 43636 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2932 | Pouring request for concrete with plastic fiber (screed 10cm) at second floor (308.10) between axis (15-16)&(C-D) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43634 | 43636 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2933 | Pouring request for concrete with plastic fiber (screed 10cm) at third floor (312.10) between axis (15-16)&(C-D) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43634 | 43636 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2934 | Pouring request for concrete with plastic fiber (screed 10cm) at fourth floor (316.10) between axis (15-16)&(C-D) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43634 | 43636 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2935 | Pouring request for concrete with plastic fiber (screed 10cm) at fifth floor (320.10) between axis (15-16)&(C-D) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43634 | 43636 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2936 | Check RFT for upstand at level (300.10) between axis (7-12)/(C-E) for area (6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Upstand | 43634 | 43636 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2937 | Check formwork for upstand at level (300.10) between axis (7-12)/(C-E) for area (6) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | Upstand | 43634 | 43636 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2938 | Pouring request for upstand at level (300.10) between axis (7-12)/(C-E) for area (6) As Per Attached Sketch. | STR | Concreting | Concreting | Upstand | 43634 | 43636 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2939 | Surface preparation and repair for retaining wall between axis (5-14)/(0) for area (P6) from level(249.60 to 295.60) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43638 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2940 | Primer coat for retaining wall between axis (5-14)/(0) for area (P6) from level(249.60 to 295.60) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43638 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2941 | Membrane coat for retaining wall between axis (5-14)/(0) for area (P6) from level(249.60 to 295.60) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43638 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2942 | cartonal coat for retaining wall between axis (5-14)/(0) for area (P6) from level(249.60 to 295.60) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43638 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2943 | water test for the upper roof level (328.85) between axis (E-B)&(15-16) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43640 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2944 | Foam coat for the upper roof level (328.85) between axis (B-E)&(15-16) for area (P1) As Per Attached Sketch. | STR | Thermal Ins. | Thermal Ins. | 7th | 43640 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2945 | Geotextil for the upper roof level (328.85) between axis (B-E)&(15-16) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43640 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2946 | INSTALLATION of Polyethelen sheet (400micron) under S.O.G between axes (5-14) & (0-F) for area (Z6) As Per Attached Sketch . | STR | Polyethelen sheet | Polyethelen sheet | Polyethelen | 43641 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2947 | Pouring Request For Plain concrete For Walkway of landscape As Per Attached Sketch. | STR | Concreting | Concreting | walkway | 43667 | 43671 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2948 | Pouring Request For Plain concrete For Walkway of landscape As Per Attached Sketch. | STR | Concreting | Concreting | walkway | 43667 | 43671 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2949 | Check RFT for sumbit slab at second basement at level (291.80) for zone (1,2,3,4,5) as per Attached Sketch. | STR | Reinforcement | Reinforcement | Sump Pit | 43675 | 43680 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2950 | Pouring Request for sumbit slab at second basement at level (291.80) for zone (1,2,3,4,5) as per Attached Sketch. | STR | Concreting | Concreting | Sump Pit | 43675 | 43680 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2951 | Pouring Request for S.O.G for external ramp of zone(2) as per Attached Sketch. | STR | Concreting | Concreting | S.O.G | 43675 | 43680 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2952 | Surface preparation and repair for retaining wall from level (297.50 to 299.90) between axis (1-2)&(0-F) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43682 | 43684 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2953 | Primer coat for retaining wall from level (297.50 to 299.90) between axis (1-2)&(0-F) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43682 | 43684 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2954 | Membrane coat for retaining wall from level (297.50 to 299.90) between axis (1-2)&(0-F) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43682 | 43684 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2955 | cartonal coat for retaining wall from level (297.50 to 299.90) between axis (1-2)&(0-F) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43682 | 43684 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2956 | Surface preparation and repair for retaining wall between axis (0-7)/(E-L) for area (P4) from level(295.60 to 299.90) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43682 | 43684 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2957 | Primer coat for retaining wall between axis (0-7)/(E-L) for area (P4) from level(295.60 to 299.90) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43682 | 43684 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2958 | Membrane coat for retaining wall between axis (0-7)/(E-L) for area (P4) from level(295.60 to 299.90) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43682 | 43684 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2959 | cartonal coat for retaining wall between axis(0-7)/(E-L) for area (P4) from level(295.60 to 299.90) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43682 | 43684 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2960 | Check RFT for Parapet at level (308.10) between axis (1-18)/(A-L) for area (Z1,Z2,Z3,Z4,Z5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43703 | 43705 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2961 | Check formwork for Parapetat level (308.10) between axis (1-18)/(A-L) for area (Z1,Z2,Z3,Z4,Z5) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 1st | 43703 | 43705 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2962 | Pouring request for Parapetat level (308.10) between axis (1-18)/(A-L) for area (Z1,Z2,Z3,Z4,Z5) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43703 | 43705 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2963 | Check RFT for Parapet at level (324.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43703 | 43705 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2964 | Check formwork for Parapetat level(324.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 5th | 43703 | 43705 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2965 | Pouring request for Parapetat level (324.10) between axis (13-18)/(A-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43703 | 43705 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2966 | Surface preparation and repair for retaining wall between axis (5-14)/(0) for area (P6) from level(295.60 to 300.10) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2967 | Primer coat for retaining wall between axis (5-14)/(0) for area (P6) from level(295.60 to 300.10) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2968 | Membrane coat for retaining wall between axis (5-14)/(0) for area (P6) from level(295.60 to 300.10) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2969 | cartonal coat for retaining wall between axis (5-14)/(0) for area (P6) from level(295.60 to 300.10) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2970 | Check RFT for Parapet at level (328.10) between axis (14-17)/(A-F) for area (Z1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2971 | Check formwork for Parapetat level(328.10) between axis (14-17)/(A-F) for area (Z1) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 6th | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2972 | Pouring request for Parapetat level (328.10) between axis (14-17)/(A-F) for area (Z1) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2973 | Check RFT for Parapet at level (333.10) between axis (1-18)/(F-L) for area (Z2,Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 7th | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2974 | Check formwork for Parapetat level (333.10) between axis (1-18)/(F-L) for area (Z2,Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 7th | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2975 | Pouring request for Parapetat level (333.10) between axis (1-18)/(F-L) for area (Z2,Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2976 | Check RFT for Parapet at level (338.10) between axis (1-18)/(G-K) for area (Z2,Z4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 8th | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2977 | Check formwork for Parapet at level (338.10) between axis (1-18)/(G-K) for area (Z2,Z4) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 8th | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2978 | Pouring request for Parapet at level (338.10) between axis (1-18)/(G-K) for area (Z2,Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 8th | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2979 | Check RFT for Parapet at level (347.10) between axis (H-J)/(7) & (H-J)/(12) for area (3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 9th | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2980 | Check formwork for Parapet at level (347.10) between axis (H-J)/(7) & (H-J)/(12) for area (3) As Per Attached Sketch. | STR | FORMWORK | FORMWORK | 9th | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2981 | Pouring request for Parapet at level(347.10) between axis (H-J)/(7) & (H-J)/(12) for area (3) As Per Attached Sketch. | STR | Concreting | Concreting | 9th | 43704 | 43711 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2982 | Pouring request for P.C concrete for irrigation tank foundation at level (291.25) as Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43711 | 43715 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2983 | Primer coat for P.C concrete for irrigation tank foundation at level 291.25 as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43711 | 43715 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2984 | Membrane coat for P.C concrete for irrigation tank foundation at level (291.25) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43711 | 43715 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2985 | protection board(3mm) for membrane for P.C concrete for irrigation tank foundation at level (291.25) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43711 | 43715 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2986 | Pouring request for plain concrete (screed 5cm) for irrigation tank foundation at level (291.30) as Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43711 | 43715 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2987 | Pouring request for P.C concrete for fountain foundation at level (299.90) as Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43711 | 43715 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2988 | Check RFT for R.C of fountain foundation and walls at level (299.25) as Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 43711 | 43715 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2989 | Pouring request for R.C of fountain foundation and walls at level (299.25) as Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 43711 | 43715 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2990 | Check RFT for R.C walls for water feature at level (301.00) between axis (A-F)/(8-11) at area Z6 as Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43711 | 43715 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2991 | Pouring request for R.C walls for water feature at level (301.00) between axis (A-F)/(8-11) at area Z6 as Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43711 | 43715 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2992 | Pouring request for P.C concrete for water feature foundation at level (298.645) as Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 43711 | 43715 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2993 | Check RFT for R.C foundation and walls for water feature at level (298.845) as Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 43711 | 43715 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2994 | Pouring request for R.C foundation and walls for water feature at level (298.845) as Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 43711 | 43715 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2995 | Primer coat for Sloped plain concrete with fiber for the roof between axis (E-L)&(13-18) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | 8th | 43711 | 43719 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2996 | Membrane coat for Sloped plain concrete with fiber for the roof between axis (E-L)&(13-18) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | 8th | 43711 | 43719 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2997 | water test for the roof between axis (E-L)&(13-18) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | 8th | 43711 | 43719 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2998 | Foam coat for the roof between axis (E-L)&(13-18) for area (P2) As Per Attached Sketch. | STR | Thermal Ins. | Thermal Ins. | 8th | 43711 | 43727 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-2999 | Geotextil for the roof between axis (E-L)&(13-18) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | 8th | 43711 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3000 | protection board(3mm) for the roof between axis (E-L)&(13-18) for area (P2) As Per Attached Sketch. | STR | water proofing | water proofing | 8th | 43711 | 43719 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3001 | Primer coat for Sloped plain concrete with fiber for the roof between axis (E-L)&(1-6) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | 8th | 43711 | 43719 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3002 | Membrane coat for Sloped plain concrete with fiber for the roof between axis (E-L)&(1-6) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | 8th | 43711 | 43719 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3003 | water test for the roof between axis (E-L)&(1-6) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | 8th | 43711 | 43719 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3004 | Foam coat for the roof between axis (E-L)&(1-6) for area (P4) As Per Attached Sketch. | STR | Thermal Ins. | Thermal Ins. | 8th | 43711 | 43719 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3005 | Geotextil for the roof between axis (E-L)&(1-6) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | 8th | 43711 | 43719 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3006 | protection board(3mm) for the roof between axis (E-L)&(1-6) for area (P4) As Per Attached Sketch. | STR | water proofing | water proofing | 8th | 43711 | 43719 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3007 | Check fixation and welding for steel brackets and bracing for interface installment from 7th to 10th floor As Per Attached Sketch. | STR | Steel | Steel | bridges | 43716 | 43720 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3008 | Check fixation and welding canopy handrail at level (350.600) As Per Attached Sketch. | STR | Steel | Steel | canopy | 43716 | 43720 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3009 | Check RFT for R.C foundation of irrigation tank at level (292.50)-(291.25) as Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 43717 | 43719 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3010 | Pouring request for R.C foundation of irrigation tank at level (292.50)-(291.25) as Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 43717 | 43719 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3011 | Primer coat for Sloped plain concrete with fiber for the roof between axis (A-F)&(13-18) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43718 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3012 | Membrane coat for Sloped plain concrete with fiber for the roof between axis (A-F)&(13-18) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43718 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3013 | water test for the roof between axis (A-F)&(13-18) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43718 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3014 | Foam coat for the roof between axis (A-F)&(13-18) for area (P1) As Per Attached Sketch. | STR | Thermal Ins. | Thermal Ins. | 6th | 43718 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3015 | Geotextil for the roof between axis (A-F)&(13-18) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43718 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3016 | protection board(3mm) for the roof between axis (A-F)&(13-18) for area (P1) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43718 | 43727 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3017 | Primer coat for Sloped plain concrete with fiber for the roof between axis (A-F)&(1-6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43718 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3018 | Membrane coat for Sloped plain concrete with fiber for the roof between axis (A-F)&(1-6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43718 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3019 | water test for the roof between axis (A-F)&(1-6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43718 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3020 | Foam coat for the roof between axis (A-F)&(1-6) for area (P5) As Per Attached Sketch. | STR | Thermal Ins. | Thermal Ins. | 6th | 43718 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3021 | Geotextil for the roof between axis (A-F)&(1-6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43718 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3022 | protection board(3mm) for the roof between axis (A-F)&(1-6) for area (P5) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43718 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3023 | Pouring Request For Plain concrete For Walkway of landscape As Per Attached Sketch. | STR | Concreting | Concreting | walkway | 43720 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3024 | Pouring Request For Plain concrete For Walkway of landscape between axis (G-L)/(1-2) As Per Attached Sketch. | STR | Concreting | Concreting | walkway | 43720 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3025 | Membrane coat for retaining wall from level (295.60 to 299.80) between axis (7-12)/(L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43720 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3026 | cartonal coat for retaining wall from level (295.60 to 299.80) between axis (7-12)/(L) for area (P3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43720 | 43725 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3027 | INSTALLATION of Polyethelen sheet (400micron) under S.O.G for external ramp zone(2) As Per Attached Sketch . | STR | Polyethelen sheet | Polyethelen sheet | Polyethelen | 43723 | 43731 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3028 | INSTALLATION of Polyethelen sheet (400micron) under P.C for walkway of landscape As Per Attached Sketch . | STR | Polyethelen sheet | Polyethelen sheet | Polyethelen | 43723 | 43731 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3029 | INSTALLATION of Polyethelen sheet (400micron) under P.C for walkway of landscape between axis (G-L)/(1-2) As Per Attached Sketch. | STR | Polyethelen sheet | Polyethelen sheet | Polyethelen | 43723 | 43731 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3030 | Level and location for p.c at hars scape As Per Attached Sketch. | STR | LEVELS | LEVELS | P.C | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3031 | Level and location for p.c at hars scape part 1 As Per Attached Sketch. | STR | LEVELS | LEVELS | P.C | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3032 | Level and location for p.c at hars scape part 2 As Per Attached Sketch. | STR | LEVELS | LEVELS | P.C | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3033 | Check Location and level for walls in water feature 1 As Per Attached Sketch. | STR | LEVELS | LEVELS | R.W | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3034 | Check Location and level for P.C water feature 2 As Per Attached Sketch. | STR | LEVELS | LEVELS | P.C | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3035 | Check Location and level for foundation water feature 2 As Per Attached Sketch. | STR | LEVELS | LEVELS | FOUNDATION | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3036 | Check Location and level for P.C water feature 3&5 As Per Attached Sketch. | STR | LEVELS | LEVELS | P.C | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3037 | Check Location and level for foundation and walls water feature 3&5 As Per Attached Sketch. | STR | LEVELS | LEVELS | R.W | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3038 | Check Location and level for irrigation tank befor replacement As Per Attached Sketch. | STR | LEVELS | LEVELS | rep. | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3039 | Check Location and level for irrigation tank first layer replacement As Per Attached Sketch. | STR | LEVELS | LEVELS | rep. | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3040 | Check Location and level for irrigation tank second layer replacement As Per Attached Sketch. | STR | LEVELS | LEVELS | rep. | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3041 | Check Location and level for P.C irrigation tank As Per Attached Sketch. | STR | LEVELS | LEVELS | P.C | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3042 | Check Location and level for foundation and walls irrigation tank As Per Attached Sketch. | STR | LEVELS | LEVELS | R.W | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3043 | Check Location and level for PUMP ROOM 1 befor replacement As Per Attached Sketch. | STR | LEVELS | LEVELS | rep. | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3044 | check axis for pipes in irrigation tank As Per Attached Sketch. | STR | LEVELS | LEVELS |  | 43726 | 43733 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3045 | check fixition of steel nose for stairs between axes (c-b) (17-15)area p (1) from basement (2) to Sixth floor as per attached sketch . | STR | STAIRS | STAIRS | Z1 | 43729 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3046 | check fixition of steel nose for stairs between axes (h-k) (17-15)area p (2) from basement (2) to eighth floor as per attached sketch. | STR | STAIRS | STAIRS | Z2 | 43729 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3047 | check fixition of steel nose for stairs between axes (h-k) (13-6) area p (3) from basement (2) to tenth floor as per attached sketch. | STR | STAIRS | STAIRS | Z3 | 43729 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3048 | check fixition of steel nose for stairs between axes (k-h) (2-4) area p (4) from basement (2) to eighth floor as per attached sketch. | STR | STAIRS | STAIRS | Z4 | 43729 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3049 | check fixition of steel nose for stairs between axes (b-c) (2-4) area p (5) from basement (2) to sixth floor as per attached sketch. | STR | STAIRS | STAIRS | Z5 | 43729 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3050 | INSTALLATION of Polyethelen sheet (400micron) under P.C for walkway of landscape between axis (A-E)/(1) As Per Attached Sketch. | STR | Polyethelen sheet | Polyethelen sheet | Polyethelen | 43733 | 43739 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3051 | pouring requst of P.C for walkway of landscape between axis (A-E)/(1) As Per Attached Sketch. | STR | Concreting | Concreting | walkway | 43733 | 43739 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3052 | Check RFT for retaning wall of irrigation tank to level (298.15) as Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43733 | 43739 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3053 | Check formwork for retaning wall of irrigation tank to level (298.15) as Per Attached Sketch. | STR | FORMWORK | FORMWORK | R.W | 43733 | 43739 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3054 | pouring request of R.C for retaIning wall of irrigation tank to level (298.15) as Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43733 | 43739 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3055 | Check RFT for R.C slab of irrigation tank at level (298.45) as Per Attached Sketch. | STR | Reinforcement | Reinforcement | Slab | 43741 | 43748 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3056 | pouring request for R.C slab of irrigation tank at level (298.45) as Per Attached Sketch. | STR | Concreting | Concreting | Slab | 43741 | 43748 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3057 | Surface preparation and repair for slab and walls of water feature As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43741 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3058 | Primer coat for slab and walls of water feature As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43741 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3059 | Membrane coat for slab and walls of water feature As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43741 | 43760 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3060 | cartonal coat for slab and walls of water feature As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43741 | 43760 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3061 | check fixation of EPDM for slab and walls of water feature between axis (A-L) (9-11) AT ZONE (6) As Per Attached Sketch. | STR | water proofing | water proofing | EPDM | 43741 | 43748 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3062 | WATER TEST FOR EPDM for slab and walls of water feature between axis (A-L) (9-11) AT ZONE (6) As Per Attached Sketch. | STR | water proofing | water proofing | EPDM | 43741 | 43748 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3063 | pouring request for P.C of foundation of Pump room(1) at level (295.180) as Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43744 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3064 | Surface preparation and repair for P.C of foundation of Pump room(1) at level (295.180) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43744 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3065 | Primer coat for P.C of foundation of Pump room(1) at level (295.180) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43744 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3066 | Membrane coat for P.C of foundation of Pump room(1) at level (295.180) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43744 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3067 | protection board(3mm) on membrane for P.C of foundation of Pump room(1) at level (295.180) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43744 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3068 | pouring request for P.C (5cm) screed of foundation of Pump room(1) at level (295.230) as Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43744 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3069 | Check RFT for foundation of pump room (1) at level (295.83-295.330) as Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 43744 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3070 | pouring request for R.C OF foundation of pump room (1) at level (295.83-295.330) as Per Attached Sketch. | STR | water proofing | water proofing | FOUNDATION | 43744 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3071 | Primer coat for slab and walls of water feature As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43745 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3072 | Membrane coat for slab and walls of water feature As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43745 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3073 | cartonal coat for slab and walls of water feature As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43745 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3074 | check fixation of EPDM for slab and walls of water feature for pump room(2) between axis (A-F) (6-9) AT ZONE (6) As Per Attached Sketch. | STR | water proofing | water proofing | EPDM | 43745 | 43750 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3075 | WATER TEST FOR EPDM for slab and walls of water feature for pump room(2) between axis (A-F) (6-9) AT ZONE (6) As Per Attached Sketch. | STR | water proofing | water proofing | EPDM | 43745 | 43750 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3076 | check fixation of EPDM for slab and walls of water feature between axis (A-D) (7-10) AT ZONE (6) As Per Attached Sketch. | STR | water proofing | water proofing | EPDM | 43748 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3077 | WATER TEST FOR EPDM for slab and walls of water feature between axis (A-D) (7-10) AT ZONE (6) As Per Attached Sketch. | STR | water proofing | water proofing | EPDM | 43748 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3078 | Check RFT for footing for machine for HVAC between axis (J-G)/(12-14) at ground floor as Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43748 | 43751 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3079 | pouring request for footing for machine for HVAC between axis (J-G)/(12-14) at ground floor as Per Attached Sketch. | STR | Concreting | Concreting | GF | 43748 | 43751 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3080 | Check RFT for footing for machine for HVAC between axis (C-D)/(17-14) at first floor as Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43748 | 43751 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3081 | pouring request for footing for machine for HVAC between axis (C-D)/(17-14) at first floor as Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43748 | 43751 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3082 | Check RFT for walls of pump room (1) from level (295.83) to (298.73) as Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43748 | 43751 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3083 | pouring request for R.C walls of pump room (1) from level (295.83) to (298.73) as Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43748 | 43751 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3084 | pouring request for P.C of foundation of Pump room(2) at level (295.23) as Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43748 | 43751 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3085 | Check RFT for foundation and walls water feature 3&5 As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 43750 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3086 | pouring request for foundation and walls water feature 3&5 As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 43750 | 43753 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3087 | Membrane coat for foundation and walls water feature 3&5 As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43750 | 43760 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3088 | cartonal coat for foundation and walls water feature 3&5 As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43750 | 43760 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3089 | Check RFT for R.C slab of pump room 1 with T.O.C (298.73) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Slab | 43753 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3090 | pouring request for R.C slab of pump room 1 with T.O.C (298.73) As Per Attached Sketch. | STR | Concreting | Concreting | Slab | 43753 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3091 | Check RFT for footing for machine for HVAC between axis (C-D)/(2-5) at first floor Z5 as Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43753 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3092 | pouring request for footing for machine for HVAC between axis (C-D)/(2-5) at first floor Z5 as Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43753 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3093 | Check RFT for footing for machine for HVAC between axis (G-J)/(5-7) at first floor Z4 as Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43753 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3094 | pouring request for footing for machine for HVAC between axis (G-J)/(5-7) at first floor Z4 as Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43753 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3095 | Check RFT for footing for machine for HVAC between axis (G-K)/(12-14) at fourth floor Z2 as Per Attached Sketch. | STR | Reinforcement | Reinforcement | 4th | 43757 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3096 | pouring request for footing for machine for HVAC between axis (G-K)/(12-14) at fourth floor Z2 as Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43757 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3097 | pouring request for P.C of foundation of Pump room(3) at level (295.245) as Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43757 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3098 | Check RFT for foundation of pump room (2) at level (295.330) as Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 43757 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3099 | pouring request for R.C OF foundation of pump room (2) at level (295.330) as Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 43757 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3100 | INSTALLATION of Polyethelen sheet (400micron) under P.C for walkway of landscape between axis (A-L) / (18) As Per Attached Sketch . | STR | Polyethelen sheet | Polyethelen sheet | Polyethelen | 43759 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3101 | pouring requst of P.C for walkway of landscape between axis (A-L)/(18) As Per Attached Sketch. | STR | Concreting | Concreting | walkway | 43759 | 43765 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3102 | Check RFT for footing for machine for HVAC between axis (G-J)/(5-7) at ground floor Z4 as Per Attached Sketch. | STR | Reinforcement | Reinforcement | GF | 43760 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3103 | pouring request for footing for machine for HVAC between axis (G-J)/(5-7) at ground floor Z4 as Per Attached Sketch. | STR | Concreting | Concreting | GF | 43760 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3104 | Check RFT for footing for machine for HVAC between axis (G-J)/(12-14) at fifth floor Z2 as Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43760 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3105 | pouring request for footing for machine for HVAC between axis (G-J)/(12-14) at fifth floor Z2 as Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43760 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3106 | Check RFT for footing for machine for HVAC between axis (C-D)/(14-17) at fifth floor Z1 as Per Attached Sketch. | STR | Reinforcement | Reinforcement | 5th | 43760 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3107 | pouring request for footing for machine for HVAC between axis (C-D)/(14-17) at fifth floor Z1 as Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43760 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3108 | Check RFT for footing for machine for HVAC between axis (G-K)/(12-14) at sixth floor Z2 as Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43760 | 43766 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3109 | pouring request for footing for machine for HVAC between axis (G-K)/(12-14) at sixth floor Z2 as Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43760 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3110 | Check RFT for footing for machine for HVAC between axis (H-J)/(5-7) at sixth floor Z4 as Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43766 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3111 | pouring request for footing for machine for HVAC between axis (H-J)/(5-7) at sixth floor Z2 as Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43766 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3112 | Surface preparation and repair for P.C of foundation of Pump room(3) at level (295.245) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43768 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3113 | Primer coat for P.C of foundation of Pump room(3) at level (295.245) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43768 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3114 | Membrane coat for P.C of foundation of Pump room(3) at level (295.245) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43768 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3115 | protection board(3mm) on membrane for P.C of foundation of Pump room(3) at level (295.245) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43768 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3116 | pouring request for P.C (5cm) screed of foundation of Pump room(3) at level (295.295) as Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43768 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3117 | Check RFT for foundation of pump room (3) at level (295.845) as Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 43768 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3118 | pouring request for R.C OF foundation of pump room (3) at level (295.845) as Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 43768 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3119 | Check RFT for R.C walls of pump room (3) at level (298.345) as Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43768 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3120 | pouring request for R.C walls of pump room (3) at level (298.345) as Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43768 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3121 | Check RFT for R.C walls of pump room (2) at level (297.83) as Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43768 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3122 | pouring request for R.C walls of pump room (2) at level (297.83) as Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43768 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3123 | Check RFT for R.C slab of pump room 2 with T.O.C (298.230) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Slab | 43768 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3124 | pouring request for R.C slab of pump room 2 with T.O.C (298.230) As Per Attached Sketch. | STR | Concreting | Concreting | Slab | 43768 | 43773 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3125 | Primer coat for terrace slab at second floor zone(4) between axis(F-L) (1-7) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43769 | 43779 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3126 | Membrane coat for terrace slab at second floor zone(4) between axis(F-L) (1-7) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43769 | 43779 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3127 | water test for terrace slab at second floor zone(4) between axis(F-L) (1-7) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43769 | 43779 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3128 | Pouring Sloped p.c second floor for terrace between axis (A-F)&(12-18) for area (P1) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3129 | Pouring Sloped p.c second floor for terrace between axis (E-L)&(12-18) for area (P2) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3130 | Pouring Sloped p.c second floor for terrace between axis (E-L)&(1-7) for area (P4) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3131 | Pouring Sloped p.c second floor for terrace between axis (A-F)&(1-7) for area (P5) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3132 | Check RFT for R.C slab of pump room 3 with T.O.C (298.745) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Slab | 43783 | 43794 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3133 | pouring request for R.C slab of pump room 3 with T.O.C (298.745) As Per Attached Sketch. | STR | Concreting | Concreting | Slab | 43783 | 43794 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3134 | Check RFT for water feature slab between axis (A-D)&(8-10) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Slab | 43783 | 43794 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3135 | pouring request for R.C of water feature slab between axis (A-D)&(8-10) As Per Attached Sketch. | STR | Concreting | Concreting | Slab | 43783 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3136 | Check RFT for water feature slab between axis (A-D)&(9-11) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Slab | 43783 | 43794 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3137 | pouring request for R.C of water feature slab between axis (A-D)&(9-11) As Per Attached Sketch. | STR | Concreting | Concreting | Slab | 43783 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3138 | Check RFT for footings of pergoula As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 43785 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3139 | pouring request for R.C footings of pergoula As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 43785 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3140 | Check RFT for footings of pergoula As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 43785 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3141 | pouring request for R.C footings of pergoula As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 43785 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3142 | Check RFT for footings of pergoula As Per Attached Sketch. | STR | Reinforcement | Reinforcement | FOUNDATION | 43785 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3143 | pouring request for R.C footings of pergoula As Per Attached Sketch. | STR | Concreting | Concreting | FOUNDATION | 43785 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3144 | Primer coat for R.C external walls of Pump room(1) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43787 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3145 | Membrane coat for R.C external walls of Pump room(1) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43787 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3146 | cartonal for R.C external walls of Pump room(1) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43787 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3147 | Primer coat for R.C external walls of Pump room(2) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43787 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3148 | Membrane coat for R.C external walls of Pump room(2) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43787 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3149 | cartonal for R.C external walls of Pump room(2) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43787 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3150 | Pouring request for concrete with plastic fiber (screed 10cm) for das room at ground floor (300.10) between axis (3-4)&(G-H) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43789 | 43800 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3151 | Pouring request for concrete with plastic fiber (screed 10cm) for das room at first floor (304.10) between axis (3-4)&(G-H) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43789 | 43800 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3152 | Pouring request for concrete with plastic fiber (screed 10cm) for das room at second floor (308.10) between axis (3-4)&(G-H) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43789 | 43800 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3153 | Pouring request for concrete with plastic fiber (screed 10cm) for das room at third floor (312.10) between axis (3-4)&(G-H) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43794 | 43802 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3154 | Pouring request for concrete with plastic fiber (screed 10cm) for das room at fourth floor (316.10) between axis (3-4)&(G-H) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43794 | 43802 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3155 | Pouring request for concrete with plastic fiber (screed 10cm) for das room at fifth floor (320.10) between axis (3-4)&(G-H) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43794 | 43802 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3156 | Pouring request for concrete with plastic fiber (screed 10cm) for das room at sixth floor (324.10) between axis (3-4)&(G-H) for area (Z4) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43794 | 43802 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3157 | Primer coat for R.C external walls of Pump room(3) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43796 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3158 | Membrane coat for R.C external walls of Pump room(3) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43796 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3159 | cartonal for R.C external walls of Pump room(3) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43796 | 43800 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3160 | water test for pump room(1) as per attached sktetch. | STR | water proofing | water proofing |  | 43806 | 43814 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3161 | water test for pump room(2) as per attached sktetch. | STR | water proofing | water proofing |  | 43806 | 43814 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3162 | water test for pump room(3) as per attached sktetch. | STR | water proofing | water proofing |  | 43806 | 43814 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3163 | Water test for irrigation tank as per attached sketch. | STR | water proofing | water proofing |  | 43806 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3164 | Primer coat for external walls of irrigation tank as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43806 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3165 | Membrane coat for external walls of irrigation tank as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43806 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3166 | cartonal for external walls of irrigation tank as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43806 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3167 | Primer coat for terrace slab at second floor zone(2) between axis(F-L) (12-18) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43808 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3168 | Membrane coat for terrace slab at second floor zone(2) between axis(F-L) (12-18) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43808 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3169 | water test for terrace slab at second floor zone(2) between axis(F-L) (12-18) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43808 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3170 | Primer coat for terrace slab at second floor zone(1) between axis(A-F) (12-18) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43808 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3171 | Membrane coat for terrace slab at second floor zone(1) between axis(A-F) (12-18) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43808 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3172 | water test for terrace slab at second floor zone(1) between axis(A-F) (12-18) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43808 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3173 | RFT for walkway of landscape As Per Attached Sketch. | STR | Reinforcement | Reinforcement | walkway | 43809 | 43814 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3174 | Pouring request for walkway of landscape As Per Attached Sketch. | STR | Concreting | Concreting | walkway | 43809 | 43814 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3175 | Pouring Request for S.O.G for external ramp of zone(4) between axis(1-3)(L) as per Attached Sketch. | STR | Concreting | Concreting | S.O.G | 43813 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3176 | INSTALLATION of Polyethelen sheet (400micron) under S.O.G for external ramp zone(4)between axis(1-3)(L) As Per Attached Sketch . | STR | Polyethelen sheet | Polyethelen sheet | Polyethelen | 43813 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3177 | Pouring request for concrete with plastic fiber (screed 10cm) for FTR room at ground floor for area (Z1,2,3B,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 43814 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3178 | Pouring request for concrete with plastic fiber (screed 10cm) for FTR room at first floor for area (Z1,2,3B,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43814 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3179 | Pouring request for concrete with plastic fiber (screed 10cm) for FTR room at second floor for area (Z1,2,3B,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43814 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3180 | Pouring request for concrete with plastic fiber (screed 10cm) for FTR room at third floor for area (Z1,2,3B,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 43814 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3181 | Pouring request for concrete with plastic fiber (screed 10cm) for FTR room at fourth floor for area (Z1,2,3B,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 43814 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3182 | Pouring request for concrete with plastic fiber (screed 10cm) for FTR room at fifth floor for area (Z1,2,3B,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 43814 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3183 | Pouring request for concrete with plastic fiber (screed 10cm) for FTR room at sixth floor for area (Z2,3B,4) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43814 | 43816 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3184 | Primer coat for terrace slab at second floor zone(5) between axis(A-F) (1-7) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43818 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3185 | Membrane coat for terrace slab at second floor zone(5) between axis(A-F) (1-7) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43818 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3186 | water test for terrace slab at second floor zone(5) between axis(A-F) (1-7) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43818 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3187 | Check RFT for machine concret base at roof for zone(1,5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | RF | 43818 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3188 | pouring request for machine concret base at roof for zone(1,5) As Per Attached Sketch. | STR | Concreting | Concreting | RF | 43818 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3189 | Check RFT for machine concret base at upper roof for zone(1,5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | UR | 43818 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3190 | pouring request for machine concret base at upper roof for zone(1,5) As Per Attached Sketch. | STR | Concreting | Concreting | UR | 43818 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3191 | Check RFT for machine concrete base at roof for zone(2,4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | RF | 43818 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3192 | pouring request for machine concrete base at roof for zone(2,4) As Per Attached Sketch. | STR | Concreting | Concreting | RF | 43818 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3193 | Check RFT for machine concrete base at upper roof for zone(2,4) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | UR | 43818 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3194 | pouring request for machine concrete base at upper roof for zone(2,4) As Per Attached Sketch. | STR | Concreting | Concreting | UR | 43818 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3195 | INSTALLATION of Polyethelen sheet (400micron) under R.C for walkway of landscape between axis (E-G) / (0-2) As Per Attached Sketch . | STR | Polyethelen sheet | Polyethelen sheet | Polyethelen | 43820 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3196 | Check RFT for walkway of landscape between axis (E-G)/(0-2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | walkway | 43820 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3197 | pouring requst of R.C for walkway of landscape between axis (E-G)/(0-2) As Per Attached Sketch. | STR | Concreting | Concreting | walkway | 43820 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3198 | check fixation of EPDM for slab at ground floor at level (299.00) between axis (A-G) (7-12) AT ZONE (6) As Per Attached Sketch. | STR | water proofing | water proofing | EPDM | 43824 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3199 | water test of EPDM for slab at ground floor at level (299.00) between axis (A-G) (7-12) AT ZONE (6) As Per Attached Sketch. | STR | water proofing | water proofing | EPDM | 43824 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3200 | check fixation of geotextile for slab at ground floor at level (299.00) between axis (A-G) (7-12) AT ZONE (6) As Per Attached Sketch. | STR | water proofing | water proofing |  | 43824 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3201 | pouring request for P.C (Screed 5cm) on geotextile for slab at ground floor at level (299.00) between axis (A-G) (7-12) AT ZONE (6) As Per Attached Sketch. | STR | Concreting | Concreting |  | 43824 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3202 | check RFT for R.C slab (15 cm) at ground floor at level (299.50) between axis (A-G) (7-12) AT ZONE (6) As Per Attached Sketch. | STR | Reinforcement | Reinforcement |  | 43824 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3203 | pouring request for R.C slab (15 cm) at ground floor at level (299.50) between axis (A-G) (7-12) AT ZONE (6) As Per Attached Sketch. | STR | Concreting | Concreting |  | 43824 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3204 | Check RFT for water feature slab between axis (0-A)&(8-11) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Slab | 43824 | 43845 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3205 | pouring request for R.C of water feature slab between axis (0-A)&(8-11) As Per Attached Sketch. | STR | Concreting | Concreting | Slab | 43824 | 43845 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3206 | protection board(3mm) for terrace slab at second floor zone(4) between axis(F-L) (1-7) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43825 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3207 | Foam coat for terrace slab at second floor zone(4) between axis(F-L) (1-7) As Per Attached Sketch. | STR | Thermal Ins. | Thermal Ins. | 2nd | 43825 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3208 | Geotextil for terrace slab at second floor zone(4) between axis(F-L) (1-7) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43825 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3209 | INSTALLATION of Polyethelen sheet (400micron) under R.C slab for walkway of landscape Z2 as per attached sketch. | STR | Polyethelen sheet | Polyethelen sheet | Polyethelen | 43830 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3210 | check RFT for R.C slab for walkway of landscape Z2 as per attached sketch. | STR | Reinforcement | Reinforcement | walkway | 43830 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3211 | pouring request for R.C slab for walkway of landscape Z2 as per attached sketch. | STR | Concreting | Concreting | walkway | 43830 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3212 | INSTALLATION of Polyethelen sheet (400micron) under R.C slab for walkway under marble of landscape Z6 as per attached sketch. | STR | Polyethelen sheet | Polyethelen sheet | Polyethelen | 43830 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3213 | check RFT for R.C slab for walkway under marble of landscape Z6 as per attached sketch. | STR | Reinforcement | Reinforcement | walkway | 43830 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3214 | pouring request for R.C slab for walkway under marble of landscape Z6 as per attached sketch. | STR | Concreting | Concreting | walkway | 43830 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3215 | check fixation of EPDM for slab at ground floor at level (299.00) between axis (0-A) (1-7) AT ZONE (5) As Per Attached Sketch. | STR | water proofing | water proofing | EPDM | 43830 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3216 | water test of EPDM for slab at ground floor at level (299.00) between axis (0-A) (1-7) AT ZONE (5) As Per Attached Sketch. | STR | water proofing | water proofing | EPDM | 43830 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3217 | check fixation of geotextile for slab at ground floor at level (299.00) between axis (0-A) (1-7) AT ZONE (5) As Per Attached Sketch. | STR | water proofing | water proofing |  | 43830 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3218 | pouring request for P.C (Screed 5cm) on geotextile for slab at ground floor at level (299.00) between axis (0-A) (1-7) AT ZONE (5) As Per Attached Sketch. | STR | Concreting | Concreting |  | 43830 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3219 | check fixation and leveling for inerlock for walkway of landscape | STR | LEVELS | LEVELS | walkway | 43831 | 43837 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3220 | Pouring Sloped plain concrete with fiber for second floor level (308.10) between axis (G-K)&(9-10) for area (P3) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 43831 | 43834 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3221 | pouring request for P.C of fuel tank footing at zone 5 As Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43834 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3222 | check fixation and leveling for inerlock for walkway of landscape As Per Attached Sketch. | STR |  |  | walkway | 43834 | 43843 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3223 | Primer coat for P.C of fuel tank footing at zone 5 As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43837 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3224 | Membrane coat for P.C of fuel tank footing at zone 5 As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43837 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3225 | protection board(3mm) for P.C of fuel tank footing at zone 5 As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43837 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3226 | pouring request for P.C (screed 5cm) of fuel tank footing at zone 5 As Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43837 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3227 | check RFT for R.C of fuel tank footing at zone 5 As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Raft | 43837 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3228 | pouring request for R.C of fuel tank footing at zone 5 As Per Attached Sketch. | STR | Concreting | Concreting | Raft | 43837 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3229 | check RFT for R.C slab for walkway under marble of landscape as per attached sketch. | STR | Reinforcement | Reinforcement | walkway | 43837 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3230 | pouring request for R.C slab for walkway under marble of landscape as per attached sketch. | STR | Concreting | Concreting | walkway | 43837 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3231 | Check Location and level for R.C slab under marble As Per Attached Sketch. | STR | LEVELS | LEVELS |  | 43838 | 43846 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3232 | Check Location and level for R.C slab under marble As Per Attached Sketch. | STR | LEVELS | LEVELS |  | 43838 | 43846 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3233 | Check Location and level for R.C slab under marble As Per Attached Sketch. | STR | LEVELS | LEVELS |  | 43838 | 43846 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3234 | Check Location and level for R.C slab under marble As Per Attached Sketch. | STR | LEVELS | LEVELS |  | 43838 | 43846 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3235 | Check Location and level formwork for water feature(1) As Per Attached Sketch. | STR | LEVELS | LEVELS | P.C | 43838 | 43846 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3236 | Check Location and level P.C for water feature(2) As Per Attached Sketch. | STR | LEVELS | LEVELS | P.C | 43838 | 43846 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3237 | Check Location and level formwork for water feature(2) As Per Attached Sketch. | STR | LEVELS | LEVELS | R.W | 43838 | 43846 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3238 | pouring request for P.C of irrigation tank footing at level (295.45) As Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43842 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3239 | Primer coat for P.C of irrigation tank footing at level (295.45) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43842 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3240 | Membrane coat for P.C of irrigation tank footing at level (295.45) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43842 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3241 | protection board(3mm) for P.C of irrigation tank footing at level (295.45) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43842 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3242 | pouring request for P.C (screed 5cm) of irrigation tank footing at level (295.50) As Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43842 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3243 | check RFT for irrigation tank footing at level (295.75) as per attached sketch. | STR | Reinforcement | Reinforcement | Raft | 43842 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3244 | pouring request for R.C of irrigation tank footing at level (295.75) as per attached sketch. | STR | Concreting | Concreting | Raft | 43842 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3245 | check RFT for walls of irrigation tank as per attached sketch. | STR | Reinforcement | Reinforcement | R.W | 43842 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3246 | pouring request for R.C of irrigation tank walls as per attached sketch. | STR | Concreting | Concreting | R.W | 43842 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3247 | check RFT for irrigation tank slab at level (298.45) as per attached sketch. | STR | Reinforcement | Reinforcement | Slab | 43842 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3248 | pouring request for R.C of irrigation tank slab at level (298.45) as per attached sketch. | STR | Concreting | Concreting | Slab | 43842 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3249 | protection board(3mm) for terrace slab at second floor zone(1) between axis(A-F) (12-18) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43843 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3250 | Foam coat for terrace slab at second floor zone(1) between axis(A-F) (12-18) As Per Attached Sketch. | STR | Thermal Ins. | Thermal Ins. | 2nd | 43843 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3251 | Geotextil for terrace slab at second floor zone(1) between axis(A-F) (12-18) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43843 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3252 | protection board(3mm) for terrace slab at second floor zone(2) between axis(A-F) (12-18) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43843 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3253 | Foam coat for terrace slab at second floor zone(2) between axis(A-F) (12-18) As Per Attached Sketch. | STR | Thermal Ins. | Thermal Ins. | 2nd | 43843 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3254 | Geotextil for terrace slab at second floor zone(2) between axis(A-F) (12-18) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43843 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3255 | protection board(3mm) for terrace slab at second floor zone(5) between axis(A-F) (12-18) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43843 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3256 | Foam coat for terrace slab at second floor zone(5) between axis(A-F) (12-18) As Per Attached Sketch. | STR | Thermal Ins. | Thermal Ins. | 2nd | 43843 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3257 | Geotextil for terrace slab at second floor zone(5) between axis(A-F) (12-18) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43843 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3258 | check Level and location for inerlock for walkway of landscape As Per Attached Sketch. | STR | LEVELS | LEVELS | walkway | 43843 | 43846 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3259 | check Level and location for inerlock for walkway of landscape As Per Attached Sketch. | STR | LEVELS | LEVELS | walkway | 43843 | 43846 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3260 | check Level and location for Marble for walkway of landscape As Per Attached Sketch. | STR | LEVELS | LEVELS | walkway | 43843 | 43846 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3261 | check Level and location for Marble for walkway of landscape As Per Attached Sketch. | STR | LEVELS | LEVELS | walkway | 43843 | 43846 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3262 | INSTALLATION of Polyethelen sheet (400micron) under S.O.G at second basement between axes (1-18) & (A-L) for area (Z1,2,3,4,5,6) As Per Attached Sketch . | STR |  |  | S.O.G | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3263 | Pouring request for S.O.G between axes (1-18) & (A-L) with (TOC = 291.80 ) for area (Z1,2,3,4,5,6) As Per Attached Sketch . | STR | Concreting | Concreting | S.O.G | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3264 | Surface preparaiton and repair for retaining wall from level (289.70) to (300.10) between axis (5-14)/(0) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3265 | primer coat for retaining wall from level (289.70) to (300.10) between axis (5-14)/(0) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3266 | membrane coat for retaining wall from level (289.70) to (300.10) between axis (5-14)/(0) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3267 | Cartonal coat for retaining wall from level (289.70) to (300.10) between axis (5-14)/(0) for area (Z6) As Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3268 | Surface preparaiton and repair for retaining wall from level (299.00) to (300.10) between axis (11-16)/(L) for area (Z2,3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3269 | primer coat for retaining wall from level (299.00) to (300.10) between axis (11-16)/(L) for area (Z2,3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3270 | membrane coat for retaining wall from level (299.00) to (300.10) between axis (11-16)/(L) for area (Z2,3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3271 | Cartonal coat for retaining wall from level (299.00) to (300.10) between axis (11-16)/(L) for area (Z2,3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3272 | Surface preparaiton and repair for retaining wall from level (297.00) to (300.10) between axis (7-12)/(L) for area (Z3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3273 | primer coat for retaining wall from level (297.00) to (300.10) between axis (7-12)/(L) for area (Z3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3274 | membrane coat for retaining wall from level (297.00) to (300.10) between axis (7-12)/(L) for area (Z3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3275 | Cartonal coat for retaining wall from level (297.00) to (300.10) between axis (7-12)/(L) for area (Z3) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3276 | Surface preparaiton and repair for retaining wall from level (289.70) to (300.10) between axis (1-7)&(17-18) / (L) for area (Z2,4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3277 | primer coat for retaining wall from level (289.70) to (300.10) between axis (1-7)&(17-18) / (L) for area (Z2,4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3278 | membrane coat for retaining wall from level (289.70) to (300.10) between axis (1-7)&(17-18) / (L) for area (Z2,4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3279 | Cartonal coat for retaining wall from level (289.70) to (300.10) between axis (1-7)&(17-18) / (L) for area (Z2,4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3280 | Surface preparaiton and repair for retaining wall from level (297.10) to (300.10) between axis (F-L)/(1) for area (Z4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3281 | primer coat for retaining wall from level (297.10) to (300.10) between axis (F-L)/(1) for area (Z4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3282 | membrane coat for retaining wall from level (297.10) to (300.10) between axis (F-L)/(1) for area (Z4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3283 | Cartonal coat for retaining wall from level (297.10) to (300.10) between axis (F-L)/(1) for area (Z4) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3284 | Surface preparaiton and repair for retaining wall from level (297.50) to (300.10) between axis (0-F)/(1-17) for area (Z1,5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3285 | primer coat for retaining wall from level (297.50) to (300.10) between axis (0-F)/(1-17) for area (Z1,5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3286 | membrane coat for retaining wall from level (297.50) to (300.10) between axis (0-F)/(1-17) for area (Z1,5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3287 | Cartonal coat for retaining wall from level (297.50) to (300.10) between axis (0-F)/(1-17) for area (Z1,5) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3288 | Surface preparaiton and repair for retaining wall from level (298.55) to (300.10) between axis (0-L)/(17-18) for area (Z1,2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3289 | primer coat for retaining wall from level (298.55) to (300.10) between axis (0-L)/(17-18) for area (Z1,2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3290 | membrane coat for retaining wall from level (298.55) to (300.10) between axis (0-L)/(17-18) for area (Z1,2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3291 | Cartonal coat for retaining wall from level (298.55) to (300.10) between axis (0-L)/(17-18) for area (Z1,2) As Per Attached Sketch. | STR | water proofing | water proofing | R.W | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3292 | INSTALLATION of Polyethelen sheet (400micron) for R.C slab at ground floor under marble between axis (0-A) (1-7) AT ZONE (5) As Per Attached Sketch. | STR | water proofing | water proofing |  | 43848 | 43856 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3293 | check RFT for R.C slab at ground floor under marble between axis (0-A) (1-7) AT ZONE (5) As Per Attached Sketch. | STR | Reinforcement | Reinforcement |  | 43848 | 43856 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3294 | pouring request for R.C slab at ground floor under marble between axis (0-A) (1-7) AT ZONE (5) As Per Attached Sketch. | STR | Concreting | Concreting |  | 43848 | 43856 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3295 | check fixation of EPDM for R.C slab at ground floor between axis (A-F) (11-13) AT ZONE (6) As Per Attached Sketch. | STR | water proofing | water proofing | EPDM | 43848 | 43856 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3296 | water test of EPDM for R.C slab at ground floor between axis (A-F) (11-13) AT ZONE (6) As Per Attached Sketch. | STR | water proofing | water proofing | EPDM | 43848 | 43856 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3297 | check fixation of Geotextil for R.C slab at ground floor between axis (A-F) (11-13) AT ZONE (6) As Per Attached Sketch. | STR | water proofing | water proofing |  | 43848 | 43856 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3298 | pouring request for P.C (Screed 5cm) on geotextile for R.C slab at ground floor between axis (A-F) (11-13) AT ZONE (6) As Per Attached Sketch. | STR | water proofing | water proofing |  | 43848 | 43856 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3299 | INSTALLATION of Polyethelen sheet (400micron) under P.C for walkway of landscape As Per Attached Sketch . | STR | Polyethelen sheet | Polyethelen sheet | walkway | 43850 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3300 | RFT for walkway of landscape As Per Attached Sketch. | STR | Reinforcement | Reinforcement | walkway | 43850 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3301 | Pouring request for walkway of landscape As Per Attached Sketch. | STR | Concreting | Concreting | walkway | 43850 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3302 | protection board(3mm) for bridge at second floor zone(3) between axis(G-K) (9-10) As Per Attached Sketch. | STR | water proofing | water proofing | 2nd | 43852 | 43856 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3303 | RFT for footing and retaining wall of water feature(1) between axis(A-F) (8-11) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43852 | 43855 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3304 | Pouring request for footing and retaining wall of water feature(1) between axis(A-F) (8-11) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43852 | 43855 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3305 | RFT for footing and retaining wall of water feature(2) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43852 | 43855 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3306 | Pouring request for footing and retaining wall of water feature(2) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43852 | 43855 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3307 | Primer coat for Roof at Sixth floor between axis (14-17)/(E-F) for area (Z1) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43859 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3308 | Membrane coat for Roof at Sixth floor for zone(1) between axis (14-17)/(E-F) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43859 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3309 | water test for Roof at Sixth floor for zone(1) between axis (14-17)/(E-F) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43859 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3310 | protection board(3mm) for Roof at Sixth floor for zone(1) between axis (14-17)/(E-F) As Per Attached Sketch. | STR | water proofing | water proofing | 6th | 43859 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3311 | Please check level for backfilling of S.O.G level (291.60) As Per Attached Sketch. | STR | LEVELS | LEVELS | S.O.G | 43865 | 43870 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3312 | Check RFT for Parapet at second floor between axis (G-K)/(9-10) for area (3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 1st | 43869 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3313 | Pouring request for Parapet at second floor between axis (G-K)/(9-10) for area (3) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 43869 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3314 | Check RFT for Parapet at seventh floor between axis (F-L)/(9-10) for area (3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 6th | 43869 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3315 | Pouring request for Parapet at seventh floor between axis (F-L)/(9-10) for area (3) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 43869 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3316 | Check RFT for Parapet at Eighth floor between axis (F-L)/(9-10) for area (3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 7th | 43869 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3317 | Pouring request for Parapet at Eighth floor between axis (F-L)/(9-10) for area (3) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 43869 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3318 | Check RFT for Parapet at ninth floor between axis (F-L)/(9-10) for area (3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | 8th | 43869 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3319 | Pouring request for Parapet at ninth floor between axis (F-L)/(9-10) for area (3) As Per Attached Sketch. | STR | Concreting | Concreting | 8th | 43869 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3320 | Check RFT for Parapet at roof floor between axis (F-L)/(9-10) for area (3) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | RF | 43869 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3321 | Pouring request for Parapet at roof floor between axis (F-L)/(9-10) for area (3) As Per Attached Sketch. | STR | Concreting | Concreting | RF | 43869 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3322 | INSTALLATION of Polyethelen sheet (400micron) for R.C slab for walkway of landscape at zone (1) As Per Attached Sketch . | STR | water proofing | water proofing | walkway | 43876 | 43885 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3323 | RFT for R.C slab for walkway of landscape at zone (1) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | walkway | 43876 | 43885 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3324 | Pouring request ror R.C slab for walkway of landscape at zone (1) As Per Attached Sketch. | STR | Concreting | Concreting | walkway | 43876 | 43885 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3325 | Pouring request for P.C concrete for water feature (3) foundation at level (298.90) as Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43877 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3326 | RFT for R.C foundation for water feature (4) at level (299.20) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Raft | 43877 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3327 | pouring request for R.C foundation for water feature (4) at level (299.20) As Per Attached Sketch. | STR | Concreting | Concreting | Raft | 43877 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3328 | RFT for R.C walls for water feature (4) at level (299.70) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43877 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3329 | pouring request for R.C walls for water feature (4) at level (299.70) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43877 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3330 | Pouring request for P.C concrete for water feature (5) foundation at level (299.05) as Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43877 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3331 | Pouring request for P.C concrete for water feature (6) foundation at level (298.95) as Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43877 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3332 | RFT for R.C foundation for water feature (6) at level (299.15) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Raft | 43877 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3333 | pouring request for R.C foundation for water feature (6) at level (299.15) As Per Attached Sketch. | STR | Concreting | Concreting | Raft | 43877 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3334 | RFT for R.C walls for water feature (6) at level (299.65) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.W | 43877 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3335 | pouring request for R.C walls for water feature (6) at level (299.65) As Per Attached Sketch. | STR | Concreting | Concreting | R.W | 43877 | 43895 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3336 | level of excavation befor replacement for pump room(2) as per attached sketch. | STR | LEVELS | LEVELS | Excavation | 43878 | 43890 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3337 | level of excavation befor replacement for pump room(3) as per attached sketch. | STR | LEVELS | LEVELS | Excavation | 43878 | 43890 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3338 | Check Location and level for pump room(2) first layer replacement As Per Attached Sketch. | STR | LEVELS | LEVELS | Rep. | 43878 | 43890 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3339 | Check Location and level for pump room(3) first layer replacement As Per Attached Sketch. | STR | LEVELS | LEVELS | Rep. | 43878 | 43890 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3340 | Check Location and level for pump room(2) Second layer replacement As Per Attached Sketch. | STR | LEVELS | LEVELS | Rep. | 43878 | 43890 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3341 | Check Location and level for pump room(3) Second layer replacement As Per Attached Sketch. | STR | LEVELS | LEVELS | Rep. | 43878 | 43890 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3342 | level of excavation befor replacement for pump room(2) as per attached sketch. | STR | LEVELS | LEVELS | Excavation | 43878 | 43890 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3343 | RFT for R.C slab between axis (C-E)/(7-8) at level (299.65) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Slab | 43884 | 43891 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3344 | pouring request for R.C slab between axis (C-E)/(7-8) at level (299.65) As Per Attached Sketch. | STR | Concreting | Concreting | Slab | 43884 | 43891 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3345 | RFT for R.C slab between axis (C-E)/(10-12) at level (299.65) As Per Attached Sketch. | STR | Reinforcement | Reinforcement | Slab | 43884 | 43891 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3346 | pouring request for R.C slab between axis (C-E)/(10-12) at level (299.65) As Per Attached Sketch. | STR | Concreting | Concreting | Slab | 43884 | 43891 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3347 | Check Location and level for pump room(1) first layer replacement As Per Attached Sketch. | STR | LEVELS | LEVELS | Rep. | 43892 | 43895 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3348 | Check Location and level for pump room(1) Second layer replacement As Per Attached Sketch. | STR | LEVELS | LEVELS | Rep. | 43892 | 43904 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3349 | INSTALLATION of Polyethelen sheet (400micron) for R.C slab for walkway of landscape between axis (0-G)/(6-9) at zone (6) As Per Attached Sketch . | STR | water proofing | water proofing | walkway | 43892 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3350 | RFT for R.C slab for walkway of landscape between axis (0-G)/(6-9) at zone (6) As Per Attached Sketch . | STR | Reinforcement | Reinforcement | walkway | 43892 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3351 | Pouring request ror R.C slab for walkway of landscape between axis (0-G)/(6-9) at zone (6) As Per Attached Sketch . | STR | Concreting | Concreting | walkway | 43892 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3352 | Surface preparation and repair for P.C of foundation of Pump room(2) at level (295.180) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43892 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3353 | Primer coat for P.C of foundation of Pump room(2) at level (295.180) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43892 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3354 | Membrane coat for P.C of foundation of Pump room(2) at level (295.180) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43892 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3355 | protection board(3mm) on membrane for P.C of foundation of Pump room(2) at level (295.180) as Per Attached Sketch. | STR | water proofing | water proofing | SBS | 43892 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3356 | pouring request for P.C (5cm) screed of foundation of Pump room(2) at level (295.230) as Per Attached Sketch. | STR | Concreting | Concreting | P.C | 43892 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3357 | INSTALLATION of Polyethelen sheet (400micron) for walkway of landscape As Per Attached Sketch . | STR | water proofing | water proofing | walkway | 43929 | 43934 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3358 | RFT for walkway of landscape As Per Attached Sketch . | STR | Reinforcement | Reinforcement | walkway | 43929 | 43934 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3359 | Pouring request for walkway of landscape As Per Attached Sketch . | STR | Concreting | Concreting | walkway | 43929 | 43934 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3360 | INSTALLATION of Polyethelen sheet (400micron) for walkway of landscape As Per Attached Sketch . | STR | water proofing | water proofing | walkway | 43939 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3361 | RFT for walkway of landscape As Per Attached Sketch . | STR | Reinforcement | Reinforcement | walkway | 43939 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3362 | Pouring request for walkway of landscape As Per Attached Sketch . | STR | Concreting | Concreting | walkway | 43939 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3363 | start demolish of electerical manholls and ductbank between them at road 16 As Per Attached Sketch . | STR | Concreting | Concreting | walkway | 43939 | 43946 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3364 | INSTALLATION of Polyethelen sheet (400micron) for walkway of landscape As Per Attached Sketch . | STR | water proofing | water proofing | walkway | 43958 | 43965 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3365 | RFT for walkway of landscape As Per Attached Sketch . | STR | Reinforcement | Reinforcement | walkway | 43958 | 43965 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3366 | Pouring request for walkway of landscape As Per Attached Sketch . | STR | Concreting | Concreting | walkway | 43958 | 43965 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3367 | Primer coat for terrace slab at Fifth floor zone(4) between axis(E-G) (2-6) As Per Attached Sketch. | STR | water proofing | water proofing | 5th | 43964 | 43969 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3368 | Membrane coat for terrace slab at Fifth floor zone(4) between axis(E-G) (2-6) As Per Attached Sketch. | STR | water proofing | water proofing | 5th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3369 | water test for terrace slab at Fifth floor zone(4) between axis(E-G) (2-6) As Per Attached Sketch. | STR | water proofing | water proofing | 5th | 43964 | 43969 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3370 | protection board(3mm) for terrace slab at Fifth floor zone(4) between axis(E-G) (2-6) As Per Attached Sketch. | STR | water proofing | water proofing | 5th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3371 | Primer coat for terrace slab at Fifth floor zone(2) between axis(E-G) (13-17) As Per Attached Sketch. | STR | water proofing | water proofing | 5th | 43964 | 43969 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3372 | Membrane coat for terrace slab at Fifth floor zone(2) between axis(E-G) (13-17) As Per Attached Sketch. | STR | water proofing | water proofing | 5th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3373 | water test for terrace slab at Fifth floor zone(2) between axis(E-G) (13-17) As Per Attached Sketch. | STR | water proofing | water proofing | 5th | 43964 | 43969 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3374 | protection board(3mm) for terrace slab at Fifth floor zone(2) between axis(E-G) (13-17) As Per Attached Sketch. | STR | water proofing | water proofing | 5th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3375 | Primer coat for terrace slab at Seventh floor zone(2) between axis(F-L) (11-14) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43964 | 43969 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3376 | Membrane coat for terrace slab at Seventh floor zone(2) between axis(F-L) (11-14) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3377 | water test for terrace slab at Seventh floor zone(2) between axis(F-L) (11-14) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43964 | 43969 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3378 | protection board(3mm) for terrace slab at Seventh floor zone(2) between axis(F-L) (11-14) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3379 | Primer coat for terrace slab at Roof zone(3) between axis(E-L) (7-12) As Per Attached Sketch. | STR | water proofing | water proofing | RF | 43964 | 43969 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3380 | Membrane coat for terrace slab at Roof zone(3) between axis(E-L) (7-12) As Per Attached Sketch. | STR | water proofing | water proofing | RF | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3381 | water test for terrace slab at Roof zone(3) between axis(E-L) (7-12) As Per Attached Sketch. | STR | water proofing | water proofing | RF | 43964 | 43969 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3382 | protection board(3mm) for terrace slab at Roof zone(3) between axis(E-L) (7-12) As Per Attached Sketch. | STR | water proofing | water proofing | RF | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3383 | Foam coat for terrace slab at Fifth floor zone(4) between axis(E-G) (2-6) As Per Attached Sketch. | STR | water proofing | water proofing | 5th | 43968 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3384 | Geotextil for terrace slab at Fifth floor zone(4) between axis(E-G) (2-6) As Per Attached Sketch. | STR | water proofing | water proofing | 5th | 43968 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3385 | Foam coat for terrace slab at Fifth floor zone(2) between axis(E-G) (13-17) As Per Attached Sketch. | STR | water proofing | water proofing | 5th | 43968 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3386 | Geotextil for terrace slab at Fifth floor zone(2) between axis(E-G) (13-17) As Per Attached Sketch. | STR | water proofing | water proofing | 5th | 43968 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3387 | foam coat for terrace slab at Seventh floor zone(2) between axis(F-L) (11-14) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43968 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3388 | Geotextil for terrace slab at Seventh floor zone(2) between axis(F-L) (11-14) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 43968 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3389 | foam coat for terrace slab at Roof zone(3) between axis(E-L) (7-12) As Per Attached Sketch. | STR | water proofing | water proofing | RF | 43968 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3390 | Geotextil for terrace slab at Roof zone(3) between axis(E-L) (7-12) As Per Attached Sketch. | STR | water proofing | water proofing | RF | 43968 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3391 | start demolish of electerical manholls and ductbank between them at road 13 As Per Attached Sketch . | STR | Concreting | Concreting | walkway | 43968 | 43991 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3392 | start demolish for main irrigation pipe line at road 13 As Per Attached Sketch . | STR | Concreting | Concreting |  | 43992 | 43997 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3393 | Primer coat for terrace slab at seventh floor zone(4) between axis(F-H) (5-8) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 44003 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3394 | Membrane coat for terrace slab at seventh floor zone(4) between axis(F-H) (5-8) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 44003 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3395 | water test for terrace slab at seventh floor zone(4) between axis(F-H) (5-8) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 44003 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3396 | protection board(3mm) for terrace slab at seventh floor zone(4) between axis(F-H) (5-8) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 44003 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3397 | Foam coat for terrace slab at seventh floor zone(4) between axis(F-H) (5-8) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 44003 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3398 | Geotextil for terrace slab at seventh floor zone(4) between axis(F-H) (5-8) As Per Attached Sketch. | STR | water proofing | water proofing | 7th | 44003 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3399 | Geotextil for water feature between axis (6-12)(A-F) As Per Attached Sketch. | STR | water proofing | water proofing | EX | 44006 | 44012 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3400 | INSTALLATION of Polyethelen sheet (400micron) for walkway of landscape As Per Attached Sketch . | STR | water proofing | water proofing | walkway | 44016 | 44034 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3401 | RFT for walkway of landscape As Per Attached Sketch . | STR | Reinforcement | Reinforcement | walkway | 44016 | 44035 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3402 | Pouring request for walkway of landscape As Per Attached Sketch . | STR | Concreting | Concreting | walkway | 44016 | 44047 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3403 | start demolish for Subsurface pipes line at road 13,16,17,22 As Per Attached Sketch . | STR | Concreting | Concreting |  | 44033 | 44039 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3404 | start demolish for Irrigation pipes line at road 16,17 As Per Attached Sketch . | STR | Concreting | Concreting |  | 44033 | 44039 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3405 | start demolish for Duct banck for LC manholls at road 16 As Per Attached Sketch . | STR | Concreting | Concreting |  | 44033 | 44039 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3406 | start demolish for marble and interlocking peverc at road 13,16 As Per Attached Sketch . | STR | Concreting | Concreting |  | 44033 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3407 | start desmintale for LC man holes at road 13,16 As Per Attached Sketch . | STR | Concreting | Concreting |  | 44033 | 44039 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3408 | start demolish for R.C Concrete at road 13,16 As Per Attached Sketch . | STR | Concreting | Concreting |  | 44039 | 44051 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3409 | Check RFT for slab and walls for water meter valve at landscape As Per Attached Sketch. | STR | Reinforcement | Reinforcement |  | 44072 | 44109 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3410 | Pouring request for slab and walls for water meter valve at landscape As Per Attached Sketch. | STR | Concreting | Concreting |  | 44072 | 44109 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3411 | check level and location for R.C water meter at landscape As Per Attached Sketch. | STR | Concreting | Concreting |  | 44073 | 44077 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3412 | check level and location for P.C water meter at landscape As Per Attached Sketch. | STR | Concreting | Concreting |  | 44073 | 44077 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3413 | check level and location for Replacement water meter at landscape As Per Attached Sketch. | STR | Concreting | Concreting |  | 44073 | 44077 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3414 | check level and location for Excavation water meter at landscape As Per Attached Sketch. | STR | Concreting | Concreting |  | 44073 | 44077 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3415 | check installation of siesmic support for (Mechanical works) firefighing pipes and duct work for First floor for area Z(1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 1st | 44084 | 44109 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3416 | check installation of siesmic support for (Mechanical works) firefighing pipes and duct work for Second floor for area Z(1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 2nd | 44084 | 44109 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3417 | check installation of siesmic support for firefighing pipes and duct work for (Mechanical works) at Third floor for area Z(1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 3rd | 44084 | 44109 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3418 | check installation of siesmic support for firefighing pipes and duct work for Eighth floor for area Z(2,3,4) accordding to the attached sketch. | STR | siesmic | siesmic | 8th | 44084 | 44109 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3419 | check installation of siesmic support for firefighing pipes and duct work for Ninth floor for area Z(3) accordding to the attached sketch. | STR | siesmic | siesmic | 9th | 44084 | 44109 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3420 | INSTALLATION of Polyethelen sheet (400micron) for walkway of landscape As Per Attached Sketch . | STR | water proofing | water proofing | walkway | 44091 | 44109 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3421 | RFT for walkway of landscape As Per Attached Sketch . | STR | Reinforcement | Reinforcement | walkway | 44091 | 44109 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3422 | Pouring request for walkway of landscape As Per Attached Sketch . | STR | Concreting | Concreting | walkway | 44091 | 44109 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3423 | INSTALLATION of Polyethelen sheet (400micron) for walkway of landscape As Per Attached Sketch . | STR | water proofing | water proofing | walkway | 44121 | 44140 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3424 | RFT for walkway of landscape As Per Attached Sketch . | STR | Reinforcement | Reinforcement | walkway | 44121 | 44140 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3425 | Pouring request for walkway of landscape As Per Attached Sketch . | STR | Concreting | Concreting | walkway | 44121 | 44140 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3426 | Check bracing and welding for Galvanaized Steel chassis of canopy between axies (E-F)&(8-11) AT (Zone 3) )As Per Attached Sketch. | STR | steel structure | steel structure | RF | 44135 | 44178 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3427 | Check bracing and welding for Galvanaized Steel chassis of canopy between axies (E-H)&(6-13) AT (Zone 3) )As Per Attached Sketch. | STR | steel structure | steel structure | RF | 44135 | 44178 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3428 | INSTALLATION of Polyethelen sheet (400micron) for walkway of landscape As Per Attached Sketch . | STR | water proofing | water proofing | walkway | 44147 | 44178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3429 | RFT for walkway of landscape As Per Attached Sketch . | STR | Reinforcement | Reinforcement | walkway | 44147 | 44178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3430 | Pouring request for walkway of landscape As Per Attached Sketch . | STR | Concreting | Concreting | walkway | 44147 | 44178 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3431 | check Level and location for Slab for walkway of landscape As Per Attached Sketch. | STR | LEVELS | LEVELS | walkway | 44147 | 44164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3432 | INSTALLATION of Polyethelen sheet (400micron) for R.C slab of walkway at landscape As Per Attached Sketch . | STR | water proofing | water proofing | walkway | 44170 | 44187 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3433 | RFT for R.C slab of walkway at landscape As Per Attached Sketch . | STR | Reinforcement | Reinforcement | walkway | 44170 | 44187 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3434 | Pouring request for R.C slab of walkway at landscape As Per Attached Sketch . | STR | Concreting | Concreting | walkway | 44170 | 44187 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3435 | check installation of siesmic support for (Electrical works) Structure cabling and power system at First floor for Zone (1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 1st | 44179 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3436 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Second floor for Zone (1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 2nd | 44179 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3437 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Third floor for Zone (1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 3rd | 44179 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3438 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Fourth floor for Zone (1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 4th | 44179 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3439 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Fifth floor for Zone (1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 5th | 44179 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3440 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Sixth floor for Zone (1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 6th | 44179 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3441 | Check RFT for R.C Footing of External signage As Per Attached Sketch . | STR | Reinforcement | Reinforcement | EX | 44186 | 44359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3442 | Pouring request for R.C Footing of External signage As Per Attached Sketch . | STR | Reinforcement | Reinforcement | EX | 44186 | 44359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3443 | Check RFT for retaining wall of External signage As Per Attached Sketch . | STR | Reinforcement | Reinforcement | EX | 44186 | 44359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3444 | Pouring request for retaining wall of External signage As Per Attached Sketch . | STR | Reinforcement | Reinforcement | EX | 44186 | 44359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3445 | check installation of siesmic support for firefighing pipes& HVAC and Plumbing works for Eighth floor for area Z(2,3,4) accordding to the attached sketch. | STR | siesmic | siesmic | 8th | 44194 | 44359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3446 | check installation of siesmic support for firefighing pipes& HVAC and Plumbing works for Ninth floor for area Z(3) accordding to the attached sketch. | STR | siesmic | siesmic | 9th | 44194 | 44359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3447 | check installation of siesmic support for firefighing pipes& HVAC and Plumbing works for Seventh floor for area Z(1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 7th | 44198 | 44359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3448 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Fourth floor for Zone (3B,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 4th | 44220 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3449 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Fifth floor for Zone (3B,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 5th | 44220 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3450 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Sixth floor for Zone (3B,4) accordding to the attached sketch. | STR | siesmic | siesmic | 6th | 44220 | 44233 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3451 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Third floor for Zone (3B,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 3rd | 44222 | 44233 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3452 | Check bracing and welding for Galvanaized Steel chassis of canopy between axies (E-L)&(6-13) AT (Zone 3) )As Per Attached Sketch. | STR | steel structure | steel structure | RF | 44227 | 44359 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3453 | check installation of siesmic support for (Electrical works) Structure cabling and power system at First floor for Zone (3B,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 1st | 44273 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3454 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Second floor for Zone (3B,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 2nd | 44273 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3455 | check level and location interlocking concrete and P.C at Road 13,16 accordding to the attached sketch. | STR | LEVELS | LEVELS | EX | 44277 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3456 | check level and location for Road Curb at road 13,16 accordding to the attached sketch. | STR | LEVELS | LEVELS | EX | 44277 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3457 | check installation of siesmic support for (Electrical works) Structure cabling and power system at First floor for Zone (1,2,3A) accordding to the attached sketch. | STR | siesmic | siesmic | 1st | 44285 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3458 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Second floor for Zone (1,2,3A) accordding to the attached sketch. | STR | siesmic | siesmic | 2nd | 44285 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3459 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Third floor for Zone (1,2,3A) accordding to the attached sketch. | STR | siesmic | siesmic | 3rd | 44292 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3460 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Fourth floor for Zone (1,2,3A) accordding to the attached sketch. | STR | siesmic | siesmic | 4th | 44292 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3461 | check installation of siesmic support for (Mechanical works) at Fourth floor for area Z(1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 4th | 44294 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3462 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Fifth floor for Zone (1,2,3A) accordding to the attached sketch. | STR | siesmic | siesmic | 5th | 44297 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3463 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Sixth floor for Zone (1,2,3A) accordding to the attached sketch. | STR | siesmic | siesmic | 6th | 44298 | 44361 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3464 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Ground floor for Zone (1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | GF | 44304 | 44361 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3465 | Check RFT for Columns and Slab from Level (308.10) to (309.90) between Axis ( 1_5 ) & (A_L ) for Area Z (4,5) AT Second Floor accordding to the attached sketch. | STR | Reinforcement | Reinforcement | ML | 44307 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3466 | Pouring Request for Columns and Slab from Level (308.10) to (309.90) between Axis ( 1_5 ) & (A_L ) for Area Z (4,5) AT Second Floor accordding to the attached sketch. | STR | Concreting | Concreting | ML | 44307 | 44413 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3467 | check installation of siesmic support for (Mechanical works) at Fifth floor for area Z(1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 5th | 44320 | 44361 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3468 | check installation of siesmic support for (Mechanical works) at Sixth floor for area Z(1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | 6th | 44320 | 44361 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3469 | Check RFT for Columns and Slab from Level (308.10) to (309.90) between Axis ( 13_18 ) & (A_L ) for Area Z (1,2) AT Second Floor accordding to the attached sketch. | STR | Reinforcement | Reinforcement | 2nd | 44339 | 44413 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3470 | Pouring Request for Columns and Slab from Level (308.10) to (309.90) between Axis ( 13_18 ) & (A_L ) for Area Z (1,2) AT Second Floor accordding to the attached sketch. | STR | Concreting | Concreting | 2nd | 44339 | 44413 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3471 | check installation of siesmic support for (Mechanical works) at Ground floor for area Z(1,2,3,4,5) accordding to the attached sketch. | STR | siesmic | siesmic | GF | 44349 | 44361 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3472 | Water test for Slab from Level (308.10) to (309.90) between Axis ( 1_5 ) & (A_L ) for Area Z (4,5) AT Second Floor accordding to the attached sketch. | STR | water proofing | water proofing | 2nd | 44360 | 44374 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3473 | Cement based for Slab from Level (308.10) to (309.90) between Axis ( 1_5 ) & (A_L ) for Area Z (4,5) AT Second Floor accordding to the attached sketch. | STR | water proofing | water proofing | 2nd | 44360 | 44374 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3474 | Pouring request for Parapet at roof floor between axis (F-L)/(9-10) for area (3) As Per Attached Sketch. | STR | Concreting | Concreting | RF | 44360 | 44361 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3475 | Water test for Slab from Level (308.10) to (309.90) between Axis ( 14_18 ) & (A_L ) for Area Z (1,2) AT Second Floor accordding to the attached sketch. | STR | water proofing | water proofing | 2nd | 44362 | 44374 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3476 | Cement based for Slab from Level (308.10) to (309.90) between Axis ( 14_18 ) & (A_L ) for Area Z (1,2) AT Second Floor accordding to the attached sketch. | STR | water proofing | water proofing | 2nd | 44362 | 44374 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3477 | Membrane coat for Roof between axis(F-L) (9-10) for area (Z3) As Per Attached Sketch. | STR | water proofing | water proofing | RF | 44422 | 44430 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3478 | Water test for Roof between axis(F-L) (9-10) for area (Z3) As Per Attached Sketch. | STR | water proofing | water proofing | RF | 44422 | 44430 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3479 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Seventh floor for Zone (2,3,4) accordding to the attached sketch. | STR | siesmic | siesmic | 7th | 44425 | 44452 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3480 | check installation of siesmic support for (Electrical works) Structure cabling and power system at Eighth floor for Zone (2,3,4) accordding to the attached sketch. | STR | siesmic | siesmic | 8th | 44425 | 44452 | A
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3481 | Check RFT for Columns and Slab from Level (308.10) to (309.90) between Axis ( 1_5 ) & (A_L ) for Area Z (4,5) AT Second Floor accordding to the attached sketch. | STR | Reinforcement | Reinforcement | ML | 44436 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3482 | Pouring request for concrete with plastic fiber (screed 10cm) at Second bassment between axis (1-18)&(A-L) for area (Z1,2,3,4,5,6) As Per Attached Sketch. | STR | Concreting | Concreting | B2 | 44558 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3483 | Pouring request for concrete with plastic fiber (screed 10cm) at First bassment between axis (1-18)&(A-L) for area (Z1,2,3,4,5,6) As Per Attached Sketch. | STR | Concreting | Concreting | B1 | 44558 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3484 | Pouring request for concrete with plastic fiber (screed 10cm) at Ground floor between axis (1-18)&(A-L) for area (Z1,2,3,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | GF | 44558 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3485 | Pouring request for concrete with plastic fiber (screed 10cm) at First floor between axis (1-18)&(A-L) for area (Z1,2,3,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | 1st | 44558 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3486 | Pouring request for concrete with plastic fiber (screed 10cm) at Second floor between axis (1-18)&(A-L) for area (Z1,2,3,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | 2nd | 44558 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3487 | Pouring request for concrete with plastic fiber (screed 10cm) at Third floor between axis (1-18)&(A-L) for area (Z1,2,3,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | 3rd | 44558 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3488 | Pouring request for concrete with plastic fiber (screed 10cm) at Fourth floor between axis (1-18)&(A-L) for area (Z1,2,3,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | 4th | 44558 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3489 | Pouring request for concrete with plastic fiber (screed 10cm) at Fifth floor between axis (1-18)&(A-L) for area (Z1,2,3,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | 5th | 44558 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3490 | Pouring request for concrete with plastic fiber (screed 10cm) at Sixth floor between axis (1-18)&(A-L) for area (Z1,2,3,4,5) As Per Attached Sketch. | STR | Concreting | Concreting | 6th | 44558 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3491 | Pouring request for concrete with plastic fiber (screed 10cm) at Seventh floor between axis (3-16)&(G-L) for area (Z2,3,4) As Per Attached Sketch. | STR | Concreting | Concreting | 7th | 44558 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3492 | Pouring request for concrete with plastic fiber (screed 10cm) at Eighth floor between axis (2-16)&(G-K) for area (Z2,3,4) As Per Attached Sketch. | STR | Concreting | Concreting | 8th | 44558 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3493 | Pouring request for concrete with plastic fiber (screed 10cm) at Ninth floor between axis (7-12)&(G-K) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | 9th | 44558 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3494 | Pouring request for concrete with plastic fiber (screed 10cm) at Roof between axis (6-13)&(E-L) for area (Z3) As Per Attached Sketch. | STR | Concreting | Concreting | RF | 44558 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3495 | INSTALLATION of Polyethelen sheet (400micron) under P.C for walkway of landscape As Per Attached Sketch . | STR | Polyethelen sheet | Polyethelen sheet | walkway | 44579 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3496 | Pouring request for P.C concrete for walkway as Per Attached Sketch. | STR | Concreting | Concreting | P.C | 44579 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-STR-3497 | Check Pouring request R.C For walkway As Per Attached Sketch. | STR | Reinforcement | Reinforcement | R.C | 44579 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0001 | Check SAMPLE FOR PUDDLE BLACK STEAL FOR WATER TANK | MECH |  |  | B2 | 43023 | 43025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0002 | Check fabrication of puddle flange for water tank as per attached table to send it to be galvanized. | MECH |  |  | B2 | 43055 | 43059 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0003 | Check INSTALLTION of puddle flange for water tank as per attached table . | MECH |  |  | B2 | 43064 | 43068 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0004 | CHECK FABRICATION OF MOCK UP OF HIGH DENSITY POLY ETHELENE | MECH |  |  | B2 | 43152 | 43153 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0005 | Check instlation and test for under ground HDPE pipes at axis (A-E) with axis (1-5) accordding to the attached sketch. (Zone 5) | MECH | Z5 | Z5 | B2 | 43170 | 43172 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0006 | Check instlation and test for under ground HDPE pipes at axis (F-L) with axis (7-12) accordding to the attached sketch. (Zone 3) | MECH | Z3 | Z3 | B2 | 43184 | 43186 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0007 | Check instlation and test for under ground HDPE pipes at axis (F-L) with axis (1-5) accordding to the attached sketch. (Zone 4 | MECH | Z4 | Z4 | B2 | 43194 | 43200 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0008 | Check instlation and test for under ground HDPE pipes at axis (A-E) with axis (13-18) accordding to the attached sketch. (Zone 1) | MECH | Z1 | Z1 | B2 | 43201 | 43207 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0009 | Check instlation and test for under ground HDPE pipes at axis (L-G) with axis (13-18) accordding to the attached sketch. (Zone 2) | MECH | Z2 | Z2 | B2 | 43219 | 43226 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0010 | Check Fabrication of mockup of UPVC | MECH |  |  | B2 | 43311 | 43317 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0011 | Check fabrication of mockup for P.P. pipe line | MECH |  |  | B2 | 43325 | 43327 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0012 | Check Fabrication of mockup of HVAC DUCT | MECH |  |  | B1 | 43345 | 43348 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0013 | Check installation and test for ST160mmᶲ UPVC pipes at upper first basement at axis (G-k) with axis (12-18) accordding to the attached sketch. (Zone1,2,3) | MECH | Z1,2,3 | Z1,2,3 | B1 | 43347 | 43351 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0014 | Check installation and test for wast stack UPVC pipes at upper first basement at axis (C-k) with axis (12-18) accordding to the attached sketch. (Zone1,2,3) | MECH | Z1,2,3 | Z1,2,3 | B1 | 43356 | 43360 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0015 | Check installation and test for wast stack UPVC pipes at upper first basement at axis (C-L) with axis (3-7) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | B1 | 43360 | 43363 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0016 | Check installation and test for ST UPVC pipes at upper first basement at axis (G-L) with axis (2-7) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | B1 | 43360 | 43365 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0017 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43363 | 43368 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0018 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43367 | 43370 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0019 | Check installation and test for ST UPVC pipes at upper Ground floor at axis (C-K) with axis (2-7) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | GF | 43369 | 43374 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0020 | Check fabrication of mockup for fire fighting network | MECH | Z5 | Z5 | GF | 43370 | 43377 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0021 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43375 | 43377 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0022 | Check installation and test for ST UPVC pipes at upper Ground floor at axis (C-K) with axis (12-16) accordding to the attached sketch. (Zone1,2) | MECH | Z1,2 | Z1,2 | GF | 43376 | 43383 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0023 | Check installation and test for VP UPVC pipes at upper first basement at axis (F-L) with axis (2-10) accordding to the attached sketch. (Zone3,4) | MECH | Z3,4 | Z3,4 | B1 | 43377 | 43382 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0024 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43381 | 43383 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0025 | Check installation and test for FM HDPE pipes Pressure H/L at upper first basement at axis (A-J) with axis (16-18) accordding to the attached sketch. (Zone1,2) | MECH | Z1,2 | Z1,2 | B1 | 43386 | 43393 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0026 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43388 | 43391 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0027 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43388 | 43391 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0028 | Check installation and SMOKE test for duct work in first basement at axis(14-17) with axis (A-F) AT ZONE 1 | MECH | Z1 | Z1 | B1 | 43388 | 43393 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0029 | Check installation and test for HDPE pipes at upper first basement at axis (H-L) with axis (9-18) accordding to the attached sketch. (Zone2,3) | MECH | Z2,3 | Z2,3 | B1 | 43394 | 43398 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0030 | Check installation and test for UPVC pipes SP(8") at upper first basement at axis (F-K) with axis (12-18) accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | B1 | 43394 | 43398 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0031 | Check installation and test for UPVC pipes VP(4") at upper first basement at axis (L-J) with axis (9-17) accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | B1 | 43394 | 43398 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0032 | Check installation and test for HDPE pipes at upper first basement at axis (A-K) with axis (1-6) accordding to the attached sketch. (Zone4,5) | MECH | Z4,5 | Z4,5 | B1 | 43401 | 43405 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0033 | Check installation and test for drainge pipe toilet in first floor at axis AT ZONE(4) | MECH | Z4 | Z4 | 1st | 43404 | 43408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0034 | Check installation for drainge pipe mockup toilet in second floor at axis AT ZONE(4) | MECH | Z4 | Z4 | 2nd | 43404 | 43408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0035 | Check installation and test for water supply PPR pipe toilet in first floor at axis AT ZONE(4) | MECH | Z4 | Z4 | 1st | 43404 | 43408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0036 | Check installation for water supply PPR pipe mockup toilet in SECOND floor at axis AT ZONE(4) | MECH | Z4 | Z4 | 2nd | 43404 | 43408 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0037 | Check installation and test for HDPE pipes at upper first basement at axis (J-L) with axis (6-2) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | B1 | 43409 | 43412 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0038 | Check installation and test for water supply pipes DCW PPR (H-L) at upper first basement at axis (A-L) with axis (1-8) accordding to the attached sketch. (Zone3,4,5) | MECH | Z3,4,5 | Z3,4,5 | B1 | 43411 | 43416 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0039 | Check installation and test for WP UPVC pipes H/L at Second basement at axis (L-G) with axis (7-10) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | B2 | 43411 | 43416 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0040 | Check installation and test for UPVC pipes ST at H/L Second floor at axis (C-L) with axis (2-7)&(12-18) accordding to the attached sketch. (Zone1,2,3,4,5) | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43416 | 43419 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0041 | Check installation and test for UPVC pipes ST at H/L Third floor at axis (C-L) with axis (2-7)&(12-18) accordding to the attached sketch. (Zone1,2,3,4,5) | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43416 | 43419 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0042 | Check installation and test for WP UPVC pipes H/L at Second basement at axis (A-E) with axis (14-18) accordding to the attached sketch. (Zone1) | MECH | Z1 | Z1 | B2 | 43418 | 43425 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0043 | Check installation and test for WP UPVC pipes H/L at Second basement at axis (A-E) with axis (1-5) accordding to the attached sketch. (Zone5) | MECH | Z5 | Z5 | B2 | 43418 | 43425 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0044 | Check installation and test for UPVC pipes WP at H/L fourth floor at axis (C-L)/ (2-7)& Axis(C-K)/(2-7) accordding to the attached sketch. (Zone1,2,3,4,5) | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43421 | 43425 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0045 | Check installation and test for water supply pipes DCW PPR (H-L) at Second basement at axis (A-L) with axis (1-5) accordding to the attached sketch. (Zone4,5) | MECH | Z4,5 | Z4,5 | B2 | 43422 | 43425 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0046 | Check installation and SMOKE test for duct work in first basement FOR IC-B2-CPFF-04 and IC-B1-CPFF-05 &SECOND basement for IC-B2-CPFF-05 AND IC-B2-CPFF-06 | MECH |  |  | ML | 43422 | 43426 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0047 | Check installation and test for WP UPVC pipes H/L at Second basement at axis (L-F) with axis (13-18) accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | B2 | 43425 | 43429 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0048 | Check installation and test for WP UPVC pipes H/L at Second basement at axis (L-G) with axis (1-6) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | B2 | 43425 | 43429 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0049 | Check installation and test for UPVC pipes ST at H/L FIFTH floor at axis (A-L) with axis(2-7) accordding to the attached sketch. (Zone3,4,5) | MECH | Z3,4,5 | Z3,4,5 | 5th | 43425 | 43429 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0050 | Check installation and test for water supply pipes DCW PPR (H-L) at Second basement at axis (A-L) with axis (13-18) accordding to the attached sketch. (Zone1,2) | MECH | Z1,2 | Z1,2 | B2 | 43432 | 43437 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0051 | Check installation test for water supply PPR pipe toilet in SECOND floor at axis AT ZONE(4) | MECH | Z4 | Z4 | 2nd | 43432 | 43437 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0052 | Check installation and SMOKE test for duct work in first basement FOR IC-B1-CPFF-01 and IC-B1-CPFF-02 | MECH |  |  | B1 | 43433 | 43437 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0053 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43436 | 43439 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0054 | Check installation and test for UPVC pipes ST at H/L FIFTH floor at axis (A-L) with axis(12-18) accordding to the attached sketch. (Zone1,2,3) | MECH | Z1,2,3 | Z1,2,3 | 5th | 43436 | 43439 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0055 | Check installation and SMOKE test for duct work in second basement for IC-B2-CPFF-01 and IC-B2-CPFF-02 and IC-B2-CPFF-03 | MECH |  |  | B2 | 43443 | 43445 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0056 | Check installation and test for drainge pipe toilet in second floor at axis AT ZONE(4) | MECH | Z4 | Z4 | 2nd | 43443 | 43445 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0057 | Check installation and SMOKE test for duct work in first basement for IC-B1-CPEF-05 and IC-B1-CPEF-06 | MECH |  |  | B1 | 43444 | 43449 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0058 | Check instlation and test for under ground HDPE vent pipes at axis (G-L) with axis (13-18) accordding to the attached sketch. (Zone 2) | MECH | Z2 | Z2 | B2 | 43445 | 43451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0059 | Check instlation and test for under ground HDPE vent pipes at axis (L-G) with axis (9-10) accordding to the attached sketch. (Zone 3) | MECH | Z3 | Z3 | B2 | 43445 | 43451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0060 | Check instlation and test for under ground HDPE vent pipes at axis (L-G) with axis (2-3) accordding to the attached sketch. (Zone 4) | MECH | Z4 | Z4 | B2 | 43445 | 43451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0061 | Check installation and SMOKE test for duct work in first basement for IC-B1-CPFF-04 and IC-B1-CPEF-04 & second basement for IC-B2-CPFF-04 and IC-B2-CPEF-05 | MECH |  |  | ML | 43446 | 43451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0062 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43446 | 43451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0063 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43446 | 43451 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0064 | Check installation and test for UPVC pipes VP(4") at upper first basement at axis (A-H) with axis (1-6) accordding to the attached sketch. (Zone5) | MECH | Z5 | Z5 | B1 | 43450 | 43458 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0065 | Check instlation and test for under ground HDPE vent pipes at second basement at axis (A-H) with axis (1-6) accordding to the attached sketch. (Zone 5) | MECH | Z5 | Z5 | B2 | 43450 | 43458 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0066 | Check installation and test for UPVC pipes ST at H/L sixth floor at axis (E-L)/ (10-18)& Axis(E-L)/(1-9) accordding to the attached sketch. (Zone2,3,4) | MECH | Z2,3,4 | Z2,3,4 | 6th | 43456 | 43461 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0067 | Check installation and test for drainge pipe toilet in third floor at axis AT ZONE(4) | MECH | Z4 | Z4 | 3rd | 43457 | 43461 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0068 | Check installation and test for water supply PPR pipe toilet in third floor at axis AT ZONE(4) | MECH | Z4 | Z4 | 3rd | 43457 | 43461 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0069 | Check installation and test for UPVC pipes SP(8") at upper first basement at axis (F-K) with axis (2-7) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | B1 | 43459 | 43467 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0070 | Check installation and SMOKE test for duct work in first basement for IC-B1-CPFF-03 & IC-B1-CPEF-03 & IC-B1-CPEF-02 and IC-B1-CPEF-01 and second basement for IC-B2-CPFF-03 | MECH |  |  | ML | 43460 | 43467 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0071 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43460 | 43467 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0072 | Check instlation and test for under ground HDPE FM pipes at B2 accordding to the attached sketch. (Zone 3) | MECH | Z3 | Z3 | B2 | 43461 | 43467 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0073 | Check instlation and test for under ground HDPE FM pipes at B2 accordding to the attached sketch. (Zone 2) | MECH | Z2 | Z2 | B2 | 43461 | 43467 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0074 | Check installation and test for HDPE FM pipes H/L at upper first basement accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | B1 | 43461 | 43467 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0075 | Check instlation and test for under ground HDPE vent pipes at B2 accordding to the attached sketch. (Zone 1) | MECH | Z1 | Z1 | B2 | 43465 | 43474 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0076 | Check installation and test for UPVC FM pipes H/L at upper first basement at axis (1-5) with axis (E-J) & axis (A-J) with axis (14-18) accordding to the attached sketch. (Zone1&2&4) | MECH | Z1,2,4 | Z1,2,4 | B1 | 43465 | 43474 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0077 | Check sand blasting & primer coating &painting for chilled water pipes | MECH |  |  | ML | 43465 | 43467 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0078 | Check instlation of main loop for fire fighting network in ground floor at Zone (3B,4,5) | MECH | Z3B,4,5 | Z3B,4,5 | GF | 43465 | 43474 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0079 | Check instlation and test for Roof drian UPVC ST pipes at upper roof at zone(1,2) accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | TR | 43466 | 43474 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0080 | Check instlation and test for under ground HDPE FM pipes at B2 accordding to the attached sketch. (Zone 4) | MECH | Z4 | Z4 | B2 | 43466 | 43477 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0081 | Check installation and test for drainge pipe toilet in fourth floor AT ZONE(4) | MECH | Z4 | Z4 | 4th | 43466 | 43474 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0082 | Check installation and test for water supply PPR pipe toilet in fourth floor at ZONE(4) | MECH | Z4 | Z4 | 4th | 43466 | 43474 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0083 | Check installation and test for UPVC pipes ST at H/L First floor at axis (A-L) with axis(1-6) accordding to the attached sketch. (Zone4,5) | MECH | Z4,5 | Z4,5 | 1st | 43467 | 43477 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0084 | Check installation and test for UPVC pipes ST at H/L seventh floor at axis (F-L) with axis(1-7)&(12-18) accordding to the attached sketch. (Zone2,3,4) | MECH | Z2,3,4 | Z2,3,4 | 7th | 43473 | 43479 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0085 | Check installation and test for UPVC pipes WP drainage for ablution at upper first basement at axis (B-G) with axis (14-16) & axis (B-D) with axis (4-5) accordding to the attached sketch. (Zone1,2,5) | MECH | Z1,2,5 | Z1,2,5 | B1 | 43484 | 43489 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0086 | Check installation and test for drainge pipe toilet in Fifth floor AT ZONE(4) | MECH | Z4 | Z4 | 5th | 43484 | 43487 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0087 | Check installation and test for water supply PPR pipe toilet in fifth floor at ZONE(4) | MECH | Z4 | Z4 | 5th | 43484 | 43487 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0088 | Check installation and test for UPVC pipes ST at H/L First floor at axis (A-L) with axis(12-18) accordding to the attached sketch. (Zone1,2) | MECH | Z1,2 | Z1,2 | 1st | 43486 | 43496 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0089 | Check installation for UPVC sleeves pipe sumpit 2nd. Basement at zone (2,3,4) | MECH | Z2,3,4 | Z2,3,4 | B2 | 43488 | 43492 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0090 | Check installation and test for drainge pipe tepical toilet in first floor AT ZONE(2) | MECH | Z2 | Z2 | 1st | 43494 | 43499 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0091 | Check installation and test for water supply PPR pipe tepical toilet in first floor at ZONE(2) | MECH | Z2 | Z2 | 1st | 43494 | 43506 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0092 | Check instlation and test for Roof drain UPVC ST pipes at roof at 8th floor for area zone(2,4) accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | RF | 43494 | 43506 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0093 | Check instlation and test for garage drain and Clean out (6"&4"&3") ductile gosam at second basement for area zone(1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | B2 | 43494 | 43499 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0094 | Check instlation and test for Roof drian UPVC ST pipes at upper roof at zone(4,5) accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | TR | 43495 | 43506 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0095 | Check installation for UPVC sleeves pipe sumpit 2nd. Basement at zone (1,5) | MECH | Z1,5 | Z1,5 | B2 | 43496 | 43499 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0096 | Check installation and test for UPVC pipes ST at H/L First floor at axis (H-L) with axis(5-11) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | 1st | 43500 | 43507 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0097 | Check installation and test for flush valve Water supply pipe tepical toilet in second floor AT ZONE(4) | MECH | Z4 | Z4 | 2nd | 43500 | 43506 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0098 | Check installation and test for drainge pipe tepical toilet in THIRD floor AT ZONE(2) | MECH | Z2 | Z2 | 3rd | 43501 | 43507 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0099 | Check installation and test for water supply PPR pipe tepical toilet in THIRD floor at ZONE(2) | MECH | Z2 | Z2 | 3rd | 43501 | 43507 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0100 | Check instlation and test for under ground HDPE WP pipes at B2 accordding to the attached sketch. (Zone 6) | MECH | Z6 | Z6 | B2 | 43503 | 43507 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0101 | Check instlation and test for Roof drain UPVC ST pipes at roof at 6th floor for area zone(1-5) accordding to the attached sketch. | MECH | Z1,5 | Z1,5 | RF | 43506 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0102 | Check installation and test for drainge pipe tepical toilet in second floor AT ZONE(2) | MECH | Z2 | Z2 | 2nd | 43507 | 43513 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0103 | Check installation and test for water supply PPR pipe tepical toilet in second floor at ZONE(2) | MECH | Z2 | Z2 | 2nd | 43507 | 43513 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0104 | Check installation and test of pressured fire fighting network for (ZCV-3) in first basement | MECH |  |  | B1 | 43508 | 43510 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0105 | Check installation and test for drainge pipe tepical toilet in fourth floor AT ZONE(2) | MECH | Z2 | Z2 | 4th | 43514 | 43519 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0106 | Check installation and test for water supply PPR pipe tepical toilet in fourth floor at ZONE(2) | MECH | Z2 | Z2 | 4th | 43514 | 43519 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0107 | Check instlation and test for under ground HDPE VP pipes at B2 accordding to the attached sketch. (Zone 6) | MECH | Z6 | Z6 | B2 | 43515 | 43524 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0108 | Check installation and test for DWS pipes H/L at upper first basement at axis (16-18) with axis (A-L) accordding to the attached sketch. (Zone1,2) | MECH | Z1,2 | Z1,2 | B1 | 43519 | 43529 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0109 | Check installation and test for drainge pipe tepical toilet in fifth floor AT ZONE(2) | MECH | Z2 | Z2 | 5th | 43521 | 43524 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0110 | Check installation and test for water supply PPR pipe tepical toilet in fifth floor at ZONE(2) | MECH | Z2 | Z2 | 5th | 43521 | 43524 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0111 | Check mockup of internal insulation for HVAC duct work include (duct & elbow & reducer) | MECH |  |  | 1st | 43521 | 43524 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0112 | Check mockup of external insulation for HVAC duct work include (duct & elbow & reducer) | MECH |  |  | B1 | 43521 | 43524 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0113 | Check installation and test for DCW pipes H/L at first floor accordding to the attached sketch. (Zone1,2,3,4,5) | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43522 | 43529 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0114 | Check installation and test for flush valve Water supply pipe tepical toilet in first floor AT ZONE(4) | MECH | Z4 | Z4 | 1st | 43522 | 43527 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0115 | Check installation and test for DCW pipes H/L at second floor accordding to the attached sketch. (Zone1,2,3,4,5) | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43523 | 43538 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0116 | Check installation and SMOKE test for HVAC duct work in second floor for IC-2F-AHU-06 | MECH |  |  | 2nd | 43523 | 43527 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0117 | Check installation and test of pressured fire fighting network for (ZCV-01) in first basement | MECH |  |  | B1 | 43523 | 43529 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0118 | Check installation and test for flush valve Water supply pipe tepical toilet in third floor AT ZONE(4) | MECH | Z4 | Z4 | 3rd | 43524 | 43527 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0119 | Check installation and test of pressured fire fighting network for fire DEPT. inlet connection and hydrant outlet connection | MECH |  |  | ML | 43529 | 43534 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0120 | Check installation and SMOKE test for HVAC duct work in second floor for IC-2F-AHU-05 & first basement for IC-B1-CBEF-04 & second basement for IC-B2-CPEF-06 | MECH |  |  | ML | 43529 | 43534 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0121 | Check installation and test for drainge UPVC pipes H/L at 7th. floor at axis (10-13) with axis (F-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | 7th | 43530 | 43538 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0122 | Check installation and test for DWS pipes H/L at upper first basement at axis (5-13) with axis (F-L) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | B1 | 43530 | 43538 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0123 | Check installation for HVAC duct work in first basement for IC-8F-EF-06 & IC-6F-FAHU-02 and second baesment for IC-6F-FAHU-02 | MECH |  |  | B1 | 43530 | 43535 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0124 | Check installation and test for DCW pipes H/L at third floor accordding to the attached sketch. (Zone1,2,3,4,5) | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43537 | 43544 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0125 | Check installation and test for drainge UPVC pipes H/L at 7th. floor at axis (6-9) with axis (F-L) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | 7th | 43537 | 43544 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0126 | Check installation and test for drainge UPVC pipes H/L at 8th. floor at axis (6-13) with axis (F-L) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | 8th | 43537 | 43544 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0127 | Check installation and test for drainge UPVC pipes toilet at first basement at axis (17-18) with axis (D-E) & axis (1-2) with axis (D-E) accordding to the attached sketch. (Zone1,5) | MECH | Z1,5 | Z1,5 | B1 | 43537 | 43541 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0128 | Check installation and test for water supply PPR pipes toilet at first basement at axis (17-18) with axis (D-E) & axis (1-2) with axis (D-E) accordding to the attached sketch. (Zone1,5) | MECH | Z1,5 | Z1,5 | B1 | 43537 | 43541 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0129 | Check installation and test for flush valve Water supply pipe tepical toilet in fourth floor AT ZONE(4) | MECH | Z4 | Z4 | 4th | 43541 | 43544 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0130 | Check installation and test for flush valve Water supply pipe tepical toilet in fifth floor AT ZONE(4) | MECH | Z4 | Z4 | 5th | 43541 | 43544 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0131 | Check installation and test for flush valve Water supply pipe tepical toilet in first floor AT ZONE(2) | MECH | Z2 | Z2 | 1st | 43541 | 43544 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0132 | Check installation and test for drainge UPVC pipes SP & WP and VP at sixth floor at axis (8-11) with axis (F-L) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | 6th | 43542 | 43552 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0133 | Check instlation and test for under ground HDPE FM pipes at B2 accordding to the attached sketch. (Zone 6) | MECH | Z6 | Z6 | B2 | 43547 | 43552 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0134 | Check installation and test for flush valve Water supply pipe tepical toilet in second floor AT ZONE(2) | MECH | Z2 | Z2 | 2nd | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0135 | Check installation and test for flush valve Water supply pipe tepical toilet in third floor AT ZONE(2) | MECH | Z2 | Z2 | 3rd | 43547 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0136 | Check sand blasting & primer coating &painting for chilled water pipes | MECH |  |  | ML | 43548 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0137 | Check installation and SMOKE test for HVAC duct work in second floor for IC-2F-AHU-04 & third floor for IC-3F-AHU-05 and IC-3F-AHU-06 and second basement for IC-B2-CPEF-04 | MECH |  |  | 3rd | 43549 | 43552 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0138 | Check installation and test for DCW pipes H/L at fourth floor accordding to the attached sketch. (Zone1,2,3,4,5) | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43550 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0139 | Check installation and test for drainge UPVC pipes H/L at fourth floor accordding to the attached sketch. (Zone2,4) | MECH | Z2,4 | Z2,4 | 4th | 43550 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0140 | Check installation and test for flush valve Water supply pipe tepical toilet in third floor AT ZONE(2) | MECH | Z2 | Z2 | 3rd | 43551 | 43556 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0141 | Check installation and SMOKE test for HVAC duct work in first basement for IC-6F-FAHU-01 & IC-B2-CPEF-03 (B1 section) and second basement for IC-6F-FAHU-01 & IC-B2-CPEF-02 | MECH |  |  | ML | 43551 | 43556 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0142 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43551 | 43556 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0143 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43551 | 43556 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0144 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43552 | 43556 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0145 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43555 | 43557 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0146 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43556 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0147 | Check installation of internal insulation for HVAC duct work in first floor for IC-1F-AHU-01 & IC-1F-AHU-02 & IC-1F-AHU-03 | MECH |  |  | 1st | 43556 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0148 | Check installation of internal insulation for HVAC duct work in second floor for IC-2F-AHU-01 & IC-2F-AHU-02 & IC-2F-AHU-03 | MECH |  |  | 2nd | 43556 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0149 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43557 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0150 | Check installation and SMOKE test for HVAC duct work in third floor for IC-3F-AHU-04 | MECH |  |  | 3rd | 43557 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0151 | Check installation and SMOKE test for HVAC duct work in second floor for IC-2F-AHU-01 & IC-2F-AHU-02 & IC-2F-AHU-03 | MECH |  |  | 2nd | 43557 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0152 | Check installation and test for drainge UPVC pipes toilet (TD 10) at sixth floor at axis (2-5) with axis (F-H) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | 6th | 43557 | 43563 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0153 | Check installation and test for water supply PPR pipes toilet (TD 10) at sixth floor at axis (2-5) with axis (F-H) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | 6th | 43557 | 43563 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0154 | Check installation and test for DCW pipes H/L at seventh floor accordding to the attached sketch. (Zone3B,4) | MECH | Z3B,4,5 | Z3B,4,5 | 7th | 43557 | 43566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0155 | Check installation for drainge trench drain UPVC pipes under ground at second basement accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | B2 | 43557 | 43563 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0156 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43557 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0157 | Check installation and hydroulic test for fire fighting network for fire for second basement | MECH |  |  | ML | 43558 | 43563 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0158 | Check installation and SMOKE test for HVAC duct work in second basement for IC-B2-CBEF-01 & IC-B2-CBEF-03 | MECH |  |  | 2nd | 43559 | 43563 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0159 | Check installation for fire fighting network (main loop) for first floor | MECH |  |  | 1st | 43562 | 43564 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0160 | Check installation and test for DCW & DHW pipes H/L and embeded at first basement garbage room accordding to the attached sketch. (Zone2,4) | MECH | Z2,4 | Z2,4 | B1 | 43563 | 43565 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0161 | Check installation and test for drainge UPVC (SP&WP) pipes H/L at second floor at axis (C-G)/ (13-18) accordding to the attached sketch. (Zone1,2) | MECH | Z1,2 | Z1,2 | 2nd | 43564 | 43570 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0162 | Check installation and test for drainge UPVC (SP&WP) pipes H/L at first floor at axis (D-L)/ (1-6) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | 1st | 43564 | 43583 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0163 | Check installation and test for drainge UPVC pipes toilet (TD 10) at seventh floor at axis (2-5) with axis (F-H) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | 7th | 43565 | 43570 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0164 | Check installation and test for water supply PPR pipes toilet (TD 10) at seventh floor at axis (2-5) with axis (F-H) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | 7th | 43565 | 43569 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0165 | Check installation for fire fighting network (main loop) for fifth floor | MECH |  |  | 5th | 43565 | 43569 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0166 | Check installation of internal insulation for HVAC duct work in third floor for IC-3F-AHU-04 & IC-3F-AHU-05 & IC-3F-AHU-06 | MECH |  |  | 3rd | 43566 | 43570 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0167 | Check installation of internal insulation for HVAC duct work in third floor for IC-3F-AHU-01 & IC-3F-AHU-02 & IC-3F-AHU-03 | MECH |  |  | 3rd | 43566 | 43570 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0168 | Check installation and hydraulic test for chilled water network in second basement from axis (10-17) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | B2 | 43571 | 43577 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0169 | Check Mockup of external insulation for chilled water pipes in second basement | MECH |  |  | B2 | 43572 | 43576 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0170 | Check Mockup of horizontal support for chilled water pipes less than 2 inch in second basement | MECH |  |  | B2 | 43572 | 43576 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0171 | Check Mockup of vertical support for chilled water pipes in riser | MECH |  |  | ML | 43572 | 43576 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0172 | Check installation and SMOKE test for HVAC duct work in fourth floor for IC-4F-AHU-04 & IC-4F-AHU-05 & IC-4F-AHU-06 | MECH |  |  | 4th | 43573 | 43580 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0173 | Check installation and SMOKE test for HVAC duct work in second basement for IC-B2-CPEF-04 | MECH |  |  | B2 | 43573 | 43583 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0174 | Check installation and SMOKE test for HVAC duct work in first basement for IC-B1-CPFF-04 | MECH |  |  | B1 | 43573 | 43583 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0175 | Check installation for fire fighting network (main loop) for second floor | MECH |  |  | 2nd | 43579 | 43585 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0176 | Check installation for the fire department and fire hydrant conections genral mockup at ground floor ZONE(5) | MECH | Z5 | Z5 | GF | 43579 | 43586 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0177 | Check installation and test for drainge UPVC pipes toilet (TD 8) (allocation) at (4th & 5th & 6th) floor including risers pipe at axis (8-9) with axis (G-K) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | ML | 43584 | 43590 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0178 | Check installation and test for water supply PPR pipes toilet (TD 8) (allocation) at (4th & 5th & 6th) floor at axis (8-9) with axis (G-K) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | ML | 43584 | 43590 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0179 | Check installation and test for drainge UPVC (SP&WP) pipes H/L at third floor at axis (E-G)/ (2-5) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | 3rd | 43584 | 43597 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0180 | Check installation and test for drainge riser UPVC (ST) pipes from first basement to fifth floor at axis (F-H)/ (2-5) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | ML | 43584 | 43590 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0181 | Check installation and test for water supply PPR pipes toilet (TD 8) (allocation) at first floor at axis (8-9) with axis (G-K) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | 1st | 43591 | 43593 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0182 | Check installation and test for water supply PPR pipes toilet (TD 8) (allocation) at third floor at axis (8-9) with axis (G-K) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | 3rd | 43591 | 43593 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0183 | Check installation and test for drainge UPVC pipes toilet (TD 10) at sixth floor at axis (14-17) with axis (F-H) accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | 6th | 43591 | 43593 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0184 | Check installation and test for water supply PPR pipes toilet (TD 10) at sixth floor at axis (14-17) with axis (F-H) accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | 6th | 43591 | 43593 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0185 | Check installation and test for drainge UPVC pipes toilet (TD 10) at seventh floor at axis (14-17) with axis (F-H) accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | 7th | 43591 | 43593 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0186 | Check installation and test for water supply PPR pipes toilet (TD 10) at seventh floor at axis (14-17) with axis (F-H) accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | 7th | 43591 | 43593 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0187 | Check installation and test for DCW pipes H/L at seventh floor accordding to the attached sketch. (Zone3A,2) | MECH | Z2,3A | Z2,3A | 7th | 43591 | 43596 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0188 | Check installation for UPVC sleeves pipe sumpit 2nd. Basement at zone (6) | MECH | Z6 | Z6 | B2 | 43591 | 43597 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0189 | Check Mockup of external insulation for vertical chilled water pipes in riser | MECH |  |  | ML | 43591 | 43593 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0190 | Check installation and hydraulic test for chilled water network in second basement from axis (1-9) accordding to the attached sketch. | MECH | 3B,4,5 | 3B,4,5 | 2nd | 43591 | 43593 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0191 | Check installation of external insulation for HVAC duct work in second floor for IC-2F-AHU-04 & IC-2F-AHU-05 & IC-2F-AHU-06 | MECH |  |  | 2nd | 43591 | 43593 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0192 | Check installation and test for drainge riser stack UPVC (WP&SP) pipes from 6th to 8th floor incluoding wall hang toilet & toilet wall mounted (special need) at axis (F-H)/ (2-5) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | ML | 43591 | 43594 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0193 | Check installation and hydroulic test for fire fighting network at second basement (Z4,Z5) | MECH | Z4,Z5 | Z4,Z5 | B2 | 43592 | 43596 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0194 | Check installation and test for DCW pipes H/L at fifth floor accordding to the attached sketch. (Zone1,2,3,4,5) | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43592 | 43596 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0195 | Check installation and test for drainge riser stack UPVC (WP&SP) pipes from B1 to 5th floor incluoding wall hang toilet & toilet wall mounted (special need) at axis (F-H)/ (2-5) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | ML | 43592 | 43594 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0196 | Check installation and SMOKE test for HVAC duct work in fifth floor for IC-5F-AHU-04 & IC-5F-AHU-05 IC-5F-AHU-06 | MECH |  |  | 5th | 43593 | 43598 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0197 | Check installation for the galvnaized drain riser for fire fighting at zone5 from ground floor to nineth floor | MECH | Z5 | Z5 | ML | 43594 | 43598 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0198 | Check installation and SMOKE test for HVAC duct work in fifth floor for IC-5F-AHU-01 & IC-5F-AHU-02 | MECH |  |  | 5th | 43601 | 43605 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0199 | Check Mockup of galvanized sleevEs for HVAC duct work in first basement | MECH |  |  | B1 | 43601 | 43607 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0200 | Check installation and SMOKE test for HVAC duct work in sixth floor for IC-6F-AHU-01 | MECH |  |  | 6th | 43601 | 43607 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0201 | Check instlation and test for garage drain (4") ductile gosam at first basement for area zone(1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43605 | 43611 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0202 | Check installation for fire fighting network (main loop) for sixth floor | MECH |  |  | 6th | 43607 | 43611 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0203 | Check installation and test for DCW pipes H/L at sixth floor accordding to the attached sketch. (Zone2,3,4) | MECH | Z2,3,4 | Z2,3,4 | 6th | 43607 | 43613 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0204 | Check installation and SMOKE test for HVAC duct work in sixth floor for IC-6F-AHU-03 & IC-6F-AHU-04 | MECH |  |  | 6th | 43607 | 43611 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0205 | Check installation of internal insulation for HVAC duct work in fifth floor for IC-5F-AHU-01 & IC-5F-AHU-02 & IC-5F-AHU-03 | MECH |  |  | 5th | 43607 | 43611 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0206 | Check installation of external insulation for HVAC duct work in first basement for IC-6F-FAHU-01 & second basement for IC-6F-FAHU-01 | MECH |  |  | B1 | 43607 | 43611 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0207 | Check installation and test for drainge UPVC (ST) pipes H/L at 9TH floor accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | 9th | 43608 | 43789 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0208 | Check installation and test for drainge riser stack UPVC (WP&SP) pipes from 6th to 8th floor incluoding wall hang toilet & toilet wall mounted (special need) at axis (F-H)/ (14-17) accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | ML | 43612 | 43618 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0209 | Check installation and SMOKE test for HVAC duct work in sixth floor for IC-6F-AHU-02 | MECH |  |  | 6th | 43612 | 43615 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0210 | Check installation and SMOKE test for HVAC duct work in eighth floor for IC-8F-AHU-05 to roof floor | MECH |  |  | 8th | 43612 | 43615 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0211 | Check installation of internal insulation for HVAC duct work in fourth floor for IC-4F-AHU-01 & IC-4F-AHU-02 & IC-4F-AHU-03 | MECH |  |  | 4th | 43614 | 43618 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0212 | Check installation for fire fighting network (main loop) for fourth floor (z4-z5-3B) | MECH | Z3B,4,5 | Z3B,4,5 | 4th | 43617 | 43619 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0213 | Check mockup of installation for DCW steel box hosebibe at first basement Z3 | MECH | Z3 | Z3 | B1 | 43617 | 43619 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0214 | Check installation of internal insulation for HVAC duct work in second floor for IC-2F-AHU-04 & IC-2F-AHU-05 & IC-2F-AHU-06 | MECH |  |  | 2nd | 43627 | 43631 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0215 | Check mockup of installation for fire hose cabinet at first floor Z1 | MECH | Z1 | Z1 | 1st | 43631 | 43638 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0216 | Check installation and test for drainge UPVC pipes toilet (TD 8) (allocation) at (3rd & 4th & 5th & 6th) floor including risers pipe at axis (10-12) with axis (F-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | ML | 43632 | 43635 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0217 | Check installation and test for water supply PPR pipes toilet (TD 8) (allocation) at ( 5th & 6th) floor at axis (10-12) with axis (F-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | ML | 43632 | 43635 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0218 | Check installation and SMOKE test for HVAC duct work in fifth floor for IC-5F-AHU-03 | MECH |  |  | 5th | 43633 | 43638 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0219 | Check installation and test for water supply PPR pipes toilet (TD 8) (allocation) at ( 3rd & 4th ) floor at axis (10-12) with axis (F-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | ML | 43634 | 43638 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0220 | Check installation of internal insulation for HVAC duct work in fifth floor for IC-5F-AHU-04 & IC-5F-AHU-05 & IC-5F-AHU-06 | MECH |  |  | 5th | 43636 | 43640 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0221 | Check mockup for internal insulation with perforated sheet in medium pressure duct work | MECH |  |  | B1 | 43636 | 43640 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0222 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43639 | 43641 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0223 | Check installation and test for drainge UPVC pipes toilet (TD 12) (allocation) at (3rd & 4th) floor including risers pipe at axis (13-18) with axis (L-E)(316.10) accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | ML | 43639 | 43641 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0224 | Check installation and test for water supply PPR pipes toilet (TD 12) (allocation) at ( 3rd & 4th ) floor at axis (13-18) (316.10) with axis (L-E) accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | ML | 43639 | 43641 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0225 | Check installation and test for water supply PPR risr pipes toilet (TD 8) (allocation) from ( ground to 6th) floor at axis (8-9) with axis (G-K) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | ML | 43639 | 43643 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0226 | Check installation of external insulation for HVAC duct work in fourth floor for IC-4F-AHU-04 & IC-4F-AHU-05 & IC-4F-AHU-06 | MECH |  |  | 4th | 43639 | 43641 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0227 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43640 | 43642 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0228 | Check installation of internal insulation for HVAC duct work in fourth floor for IC-4F-AHU-04 & IC-4F-AHU-05 & IC-4F-AHU-06 | MECH |  |  | 4th | 43640 | 43642 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0229 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43641 | 43643 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0230 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43642 | 43648 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0231 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43646 | 43649 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0232 | Check installation of external insulation for HVAC duct work in sixth floor for IC-6F-AHU-01 & IC-6F-AHU-02 . | MECH |  |  | 6th | 43646 | 43649 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0233 | Check installation and SMOKE test for HVAC duct work in nineth floor for IC-9F-AHU-06 & second basement for IC-B1-CPFF-08 . | MECH |  |  | 9th | 43649 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0234 | Check installation and hydraulic test for the firefighting main feeding line (8",6") at second basement . | MECH |  |  | B2 | 43653 | 43656 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0235 | Check installation and SMOKE test for HVAC duct work in third floor for IC-3F-AHU-01 & IC-3F-AHU-02 & IC-3F-AHU-03. | MECH |  |  | 3rd | 43653 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0236 | Check installation and SMOKE test for HVAC duct work in first basement for IC-B1-CPFF-09 | MECH |  |  | B1 | 43653 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0237 | Check installation of internal insulation for HVAC duct work in sixth floor for IC-6F-AHU-03 & IC-6F-AHU-04 | MECH |  |  | 6th | 43653 | 43656 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0238 | Check installation of internal insulation for HVAC duct work in seventh floor for IC-8F-AHU-02 | MECH |  |  | 7th | 43653 | 43656 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0239 | Check installation of external insulation for HVAC duct work in fifth floor for IC-5F-AHU-01 & IC-5F-AHU-02 & IC-5F-AHU-03 | MECH |  |  | 5th | 43654 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0240 | Check Mockup of installation volume damper for hvac duct work in first floor | MECH |  |  | 1st | 43655 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0241 | Check installation for fire fighting network (main loop) for Third floor (z4-z5-3B) | MECH | Z3B,4,5 | Z3B,4,5 | 3rd | 43655 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0242 | Check installation for fire fighting network (main loop) for Fourth floor (z4-z5-3B) | MECH | Z3B,4,5 | Z3B,4,5 | 4th | 43655 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0243 | Check installation for fire fighting network (main loop) for Seventh floor . | MECH |  |  | 7th | 43657 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0244 | Check installation for fire fighting network (main loop) for ninth floor . | MECH |  |  | 9th | 43657 | 43663 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0245 | Check installation of internal insulation for HVAC duct work in First floor for IC-1F-AHU-04 & IC-1F-AHU-05 & IC-1F-AHU-06 . | MECH |  |  | 1st | 43657 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0246 | Check Installaion Location and Level for Perforated Pipes as Per Attached Sketch. | MECH | L.S | L.S | EX | 43660 | 43664 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0247 | Check installation and test for flush valve Water supply pipe tepical toilet (TD 10) in 6th&7th floor AT ZONE(4) | MECH | Z4 | Z4 | ML | 43660 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0248 | Check installation and test for flush valve Water supply pipe tepical toilet (TD 10) in 6th&7th floor AT ZONE(2) | MECH | Z4 | Z4 | ML | 43660 | 43662 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0249 | Check Mockup of Transfer Duct for HVAC Duct Work in Second Floor . | MECH |  |  | 2nd | 43660 | 43663 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0250 | Check Installaion location and Level For Subsurface Pipes . | MECH | L.S | L.S | EX | 43661 | 43664 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0251 | Check installation of external insulation for HVAC duct work in Third floor for IC-3F-AHU-04 & IC-3F-AHU-05 & IC-3F-AHU-06 | MECH |  |  | 3rd | 43661 | 43668 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0252 | Check installation and SMOKE test for HVAC duct work in Seventh for IC-8F-AHU-02 & IC-RF-AHU-04 | MECH |  |  | 7th | 43661 | 43668 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0253 | Check installation and test for drainge UPVC pipes toilet (TD 12) (allocation) at (2nd & 3rd & 4th) floor including risers pipe at axis (4-7) with axis (E-F) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | ML | 43663 | 43669 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0254 | Check installation and test for water supply PPR pipes toilet (TD 12) (allocation) at (2nd & 3rd & 4th ) floor at axis (4-7) with axis (E-F) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | ML | 43663 | 43669 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0255 | Check Installation Pipe Location and Level for Perforated Pipes as Per Attached Sketch. | MECH | L.S | L.S | EX | 43663 | 43668 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0256 | Check installation and test for drainge UPVC pipes toilet (TD 1) (allocation) at (8 th) floor including risers pipe at axis (8-9) with axis (J-K) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | 8th | 43666 | 43669 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0257 | Check installation and test for water supply PPR pipes toilet (TD 1) (Core) at (8 th) floor at axis (8-9) with axis (J-K) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | 8th | 43666 | 43669 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0258 | Check installation and test for drainge UPVC pipes toilet (TD 3) (allocation) at (8 th) floor including risers pipe at axis (8-9) with axis (K-L) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | 8th | 43666 | 43669 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0259 | Check installation and test for water supply PPR pipes toilet (TD 3) (allocation) at (8 th ) floor at axis (8-9) with axis (K-L) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | 8th | 43666 | 43669 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0260 | Check installation and test for flush valve Water supply pipe toilet Diatel (TD 8) in( 5th ) floor Including Isolating Valve at axis (8-9) with axis (G-K) at ZONE (3B) . | MECH | Z3B | Z3B | 5th | 43667 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0261 | Check installation and SMOKE test for HVAC duct work in Fourth floor forIC-4F-AHU-01 & IC-4F-AHU-02 & IC-4F-AHU-03 . | MECH |  |  | 4th | 43668 | 43673 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0262 | Check installation of external insulation for HVAC duct work in Second floor for IC-2F-AHU-01 & IC-2F-AHU-02 & IC-2F-AHU-03 . | MECH |  |  | 2nd | 43668 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0263 | Check installation and test storm All Pipe at Nineth Floor at axis (9-12) with axis (F-K) AT Zone (3B) . | MECH | Z3B | Z3B | 9th | 43668 | 43673 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0264 | Check installation for fire fighting network (Branches) at second floor (Z4&Z5&3B) . | MECH | Z3B,4,5 | Z3B,4,5 | 2nd | 43669 | 43674 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0265 | Check installation for fire fighting network (Branches) at second floor (Z1&Z2&3A) . | MECH | Z1,2,3A | Z1,2,3A | 2nd | 43669 | 43673 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0266 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part2 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43669 | 43673 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0267 | Check installation and test for drainge UPVC pipes toilet (TD 9) (allocation) at (2nd & 3rd & 4th & 5th & 6th ) floor including risers pipe at axis (8-9) with axis (J-L) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | ML | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0268 | Check installation and test for water supply PPR pipes toilet (TD 9) (allocation) at (2nd & 3rd & 4th & 5th & 6th ) floor at axis (8-9) with axis (J-L) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | ML | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0269 | Check installation of external insulation for HVAC duct work in Fifth floor for IC-5F-AHU-04 & IC-5F-AHU-05 & IC-5F-AHU-06 . | MECH |  |  | 5th | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0270 | Check installation of external insulation for HVAC duct work in Sixth floor for IC-6F-AHU-03 & IC-6F-AHU-04 . | MECH |  |  | 6th | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0271 | Check installation and SMOKE test for HVAC duct work in First Floor for IC-1F-AHU-01 & IC-1F-AHU-02 & IC-1F-AHU-03 . | MECH |  |  | 1st | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0272 | Check installation and SMOKE test for HVAC duct work in First Floor for IC-1F-AHU-04 & IC-1F-AHU-05 & IC-1F-AHU-06 . | MECH |  |  | 1st | 43669 | 43675 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0273 | Check installation for chilled water network in first basement accordding to the attached sketch. | MECH |  |  | B1 | 43670 | 43681 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0274 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part2 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43674 | 43677 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0275 | Check installation of internal insulation for HVAC duct work in Eighth floor for IC-RF-AHU-05 | MECH |  |  | 8th | 43674 | 43681 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0276 | Check installation and test for drainge UPVC (SP&WP) pipes H/L at 1ST floor t axis (8-11) with axis (F-L) AT (Zone3A&3B) accordding to the attached sketch. | MECH | Z3 | Z3 | 1st | 43675 | 43681 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0277 | Check installation and test for drainge UPVC pipes toilet (TD 9) (allocation) at (2nd & 3rd ) floor including risers pipe at axis (8-9) with axis (F-J) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | ML | 43675 | 43681 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0278 | Check installation and test for water supply PPR pipes toilet (TD 9) (allocation) at (2nd & 3rd) floor at axis (8-9) with axis (F-J) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | ML | 43675 | 43681 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0279 | Check installation and test for flush valve Water supply pipe toilet Diatel (TD 8) in( 5th&6th ) floor Including Isolating Valve at axis (10-11) with axis (G-K) at ZONE (3A) . | MECH | Z3A | Z3A | ML | 43676 | 43681 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0280 | Check installation and test for flush valve Water supply pipe toilet Diatel (TD 8) in( 3rd&4th ) floor Including Isolating Valve at axis (10-11) with axis (G-K) at ZONE (3A) . | MECH | Z3A | Z3A | ML | 43677 | 43681 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0281 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part2 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43678 | 43681 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0282 | Check Installaion location and Level For irrigation main line UPVC ᶲ110 pipes network part 2 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43678 | 43682 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0283 | Check installation of internal insulation for HVAC duct work in nineth floor for IC-9F-AHU-06 to roof floor | MECH |  |  | 9th | 43680 | 43685 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0284 | Check installation and test for flush valve Water supply pipe toilet Diatel (TD 3) in( 8th ) floor Including Isolating Valve at axis (8-9) with axis (J-L) at ZONE (3B) . | MECH | Z3B | Z3B | 8th | 43681 | 43685 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0285 | Check installation and test for flush valve Water supply pipe toilet Diatel (TD 1) in( 8th ) floor Including Isolating Valve at axis (8-9) with axis (E-L) at ZONE (3B) . | MECH | Z3B | Z3B | 8th | 43681 | 43685 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0286 | Check installation and test for drainge UPVC pipes toilet (TD 12) (allocation) at (5th) floor including risers pipe at axis (1-7) with axis (A-F) accordding to the attached sketch. (Zone5) | MECH | Z5 | Z5 | 5th | 43681 | 43685 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0287 | Check installation and test for water supply PPR pipes toilet (TD 12) (allocation) at (5th ) floor at axis (1-7) with axis (A-F) accordding to the attached sketch. (Zone5) | MECH | Z5 | Z5 | 5th | 43681 | 43696 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0288 | Check installation and test for drainge UPVC pipes toilet (TD 8) (allocation) at (2nd) floor including risers pipe at axis (8-9) with axis (E-L) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | 2nd | 43681 | 43685 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0289 | Check installation and test for water supply PPR pipes toilet (TD 8) (allocation) at ( 2nd) floor at axis (8-9) with axis (E-L) accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | 2nd | 43681 | 43685 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0290 | Check hydraulic test for the firefighting zone (main + branches) at second floor at zone(4,5,3B) | MECH | Z3B,4,5 | Z3B,4,5 | 2nd | 43682 | 43685 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0291 | Check installation for fire fighting network (Branches) at FIFTH floor AT ZONE (4,5,3B) | MECH | Z3B,4,5 | Z3B,4,5 | 5th | 43682 | 43685 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0292 | Check installation for fire fighting network (main loop) for first basement at zone 6 . | MECH | Z6 | Z6 | B1 | 43682 | 43685 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0293 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43682 | 43685 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0294 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43684 | 43695 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0295 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43684 | 43695 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0296 | Check installation and test for drainge UPVC pipes toilet (TD 8) (allocation) at (1st & 2nd) floor including risers pipe at axis (10-12) with axis (F-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | ML | 43684 | 43696 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0297 | Check installation and test for water supply PPR pipes toilet (TD 8) (allocation) at (1st & 2nd) floor including risers pipe at axis (10-12) with axis (F-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | ML | 43684 | 43696 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0298 | Check installation and test for flush valve Water supply pipe toilet Diatel (TD 8) in( 1st & 2nd ) floor Including Isolating Valve at axis (10-11) with axis (G-K) at ZONE (3A) . | MECH | Z3A | Z3A | ML | 43684 | 43696 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0299 | Check installation and test for flush valve Water supply pipe toilet Diatel (TD 8) in( 1st&2nd&3rd&4th&6th ) floor Including Isolating Valve at axis (8-9) with axis (G-K) at ZONE (3B) . | MECH | Z3B | Z3B | ML | 43684 | 43696 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0300 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part1 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43684 | 43692 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0301 | Check installation and test for flush TANK Water supply pipe toilet Diatel (TD 9) in( 2nd ) floor Including Isolating Valve at axis (8-9) with axis (G-K) at ZONE (3B) . | MECH | Z3B | Z3B | 2nd | 43684 | 43696 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0302 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43684 | 43695 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0303 | Check installation for fire fighting network (Branches) at fifth floor (Z1&Z2&Z3A) . | MECH |  |  | 5th | 43684 | 43692 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0304 | Check Mockup of installation VAV for HVAC Duct Work in Second Floor . | MECH |  |  | 2nd | 43694 | 43698 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0305 | Check installation and test for drainge UPVC pipes toilet (TD 9) (allocation) at (5th &6th ) floor including risers pipe and H/L pipes (4th ) floor at axis (10-11) with axis (F-J) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | ML | 43697 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0306 | Check installation and test for water supply PPR pipes toilet (TD 9) (allocation) at (5th &6th) floor at axis (10-11) with axis (F-J) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | ML | 43697 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0307 | Check Mockup of installation for fire fighting zone control at first floor zone4 | MECH | Z4 | Z4 | 1st | 43698 | 43705 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0308 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part1 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43703 | 43705 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0309 | Check hydraulic test for the firefighting zone (main + branches) at second floor at zone(1,2,3A) | MECH | Z1,2,3A | Z1,2,3A | 2nd | 43703 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0310 | Check installation and test UPVC pipes water features (3,5) including electric conduit for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43703 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0311 | Check Installaion and test pipe location and Level For irregation network Pipes (sprinkler & dripping) part 4 (00,01,02,03) for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43704 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0312 | Check Mockup of installation hookup for fan coil unit in second basement | MECH |  |  | B2 | 43705 | 43713 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0313 | flushing for fire fighting pipes at second floor at zone(1,2,3A) | MECH | Z1,2,3A | Z1,2,3A | 2nd | 43705 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0314 | Check installation for fire fighting network (Branches) for third floor at zone(3B,4,5) . | MECH | Z3B,4,5 | Z3B,4,5 | 3rd | 43705 | 43718 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0315 | flushing for fire fighting pipes at second floor at zone(3B,4,5) | MECH | Z3B,4,5 | Z3B,4,5 | 2nd | 43706 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0316 | Check installation of fan coil unit for HVAC duct work in first basement | MECH |  |  | B1 | 43708 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0317 | Check installation of fan coil unit for HVAC duct work in second basement | MECH |  |  | B2 | 43708 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0318 | Check installation of vav unit for HVAC duct work in first floor | MECH |  |  | 1st | 43708 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0319 | Check installation of vav unit for HVAC duct work in second floor | MECH |  |  | 2nd | 43708 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0320 | Check installation of vav unit for HVAC duct work in third floor | MECH |  |  | 3rd | 43708 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0321 | Check installation of vertical pipes for chilled water risers in zone5 | MECH | Z5 | Z5 | ML | 43708 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0322 | Check installation of vertical pipes for chilled water risers in zone3B | MECH | 3B | 3B | ML | 43708 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0323 | Check installation of vertical pipes for chilled water risers in zone1 | MECH | Z1 | Z1 | ML | 43708 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0324 | Check installation of external insulation for HVAC duct work in third floor for IC-3F-AHU-01 & IC-3F-AHU-02 & IC-3F-AHU-03 . | MECH |  |  | 3rd | 43709 | 43719 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0325 | Check installation of external insulation for HVAC duct work in fourth floor for IC-4F-AHU-01 & IC-4F-AHU-02 & IC-4F-AHU-03 . | MECH |  |  | 4th | 43709 | 43719 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0326 | Check installation of external insulation for chilled water pipes in second basement . | MECH |  |  | B2 | 43709 | 43720 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0327 | Check quantity of galvanized duct work for HVAC duct | MECH |  |  | ML | 43709 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0328 | Check quantity of internal and external insulation for HVAC duct work | MECH |  |  | ML | 43709 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0329 | Check quantity of chilled water pipe for HVAC | MECH |  |  | ML | 43709 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0330 | Check installation and test for drainge UPVC pipes toilet (TD 9) (allocation) at (2nd & 3rd & 4th & 5th & 6th ) floor including risers pipe at axis (10-13 ) with axis (F-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | ML | 43709 | 43711 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0331 | Check installation and test for water supply PPR pipes toilet (TD 9) (allocation) at (2nd & 3rd & 4th & 5th & 6th ) floor including risers pipe at axis (10-13 ) with axis (F-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | ML | 43709 | 43711 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0332 | Check hydraulic test for the firefighting zone (main + branches) at FIFTH floor at zone(3B,4,5) | MECH | Z3B,4,5 | Z3B,4,5 | 5th | 43709 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0333 | Check installation and test for drainge UPVC pipes toilet (TD 5) (allocation) at (9th ) floor including risers pipe at axis (9-10 ) with axis (H-K) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | 9th | 43709 | 43711 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0334 | Check installation and test for water supply PPR pipes toilet (TD 5) (allocation) at (9th ) floor including risers pipe at axis (9-10 ) with axis (H-K) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | 9th | 43709 | 43711 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0335 | Check flushing for the firefighting zone (main + branches) at FIFTH floor at zone(3B,4,5) | MECH | Z3B,4,5 | Z3B,4,5 | 5th | 43710 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0336 | Check installation and test for drainge pipe tepical toilet detail (TD 11) in ground floor AT ZONE(2) | MECH | Z2 | Z2 | GF | 43710 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0337 | Check installation and test for water supply PPR pipe tepical toilet detail (TD 11) in ground floor AT ZONE(2) | MECH | Z2 | Z2 | GF | 43710 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0338 | Check installation and test for drainge UPVC pipes toilet (TD 12) (allocation) at (4th) floor including risers pipe at axis (5-6) with axis (E-F) accordding to the attached sketch. (Zone5) | MECH | Z5 | Z5 | 4th | 43710 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0339 | Check installation and test for water supply PPR pipes toilet (TD 12) (allocation) at (4th ) floor at axis (5-6) with axis (E-F) accordding to the attached sketch. (Zone5) | MECH | Z5 | Z5 | 4th | 43710 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0340 | Check Installaion and test location and Level For irrigation main line UPVC ᶲ110 pipes network part 3 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43711 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0341 | Check Installaion and test pipe location and Level For irregation network Pipes (sprinkler & dripping) part 04 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43711 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0342 | Check Installaion and test pipe location and Level For irregation network Pipes (dripping &sleeves) part 06 & 07 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43711 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0343 | Check installation and test for drainge UPVC pipes toilet (TD 12) (allocation) at (3rd) floor including risers pipe at axis (13-18) with axis (E-F) accordding to the attached sketch. (Zone1) | MECH | Z1 | Z1 | 3rd | 43711 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0344 | Check installation and test for water supply PPR pipes toilet (TD 12) (allocation) at (3rd ) floor at axis (13-18) with axis (E-F) accordding to the attached sketch. (Zone1) | MECH | Z1 | Z1 | 3rd | 43711 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0345 | Check installation and test for drainge UPVC pipes toilet (TD 9) (allocation) at (2nd) floor including risers pipe at axis (12-13 ) with axis (F-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | 2nd | 43711 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0346 | Check installation and test for water supply PPR pipes toilet (TD 9) (allocation) at (2nd ) floor including risers pipe at axis (12-13 ) with axis (F-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | 2nd | 43711 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0347 | Check installation and test for drainge UPVC pipes toilet (TD 4 ) (allocation) at (9th ) floor including risers pipe at axis (9-10 ) with axis (G-K) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | 9th | 43712 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0348 | Check installation and test for water supply PPR pipes toilet (TD 4) (allocation) at (9th ) floor including risers pipe at axis (9-10 ) with axis (G-K) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | 9th | 43712 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0349 | Check installation and test for drainge UPVC pipes toilet (TD 6 ) (allocation) at (9th ) floor including risers pipe at axis (9-10 ) with axis (G-K) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | 9th | 43712 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0350 | Check installation and test for water supply PPR pipes toilet (TD 6) (allocation) at (9th ) floor including risers pipe at axis (9-10 ) with axis (G-K) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | 9th | 43712 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0351 | Check hydraulic test for the firefighting zone (main + branches) at FIFTH floor at zone(1,2,3A) | MECH | Z1,2,3A | Z1,2,3A | 5th | 43715 | 43718 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0352 | Check installation and test for drainge UPVC pipes toilet (TD 12) (allocation) at (2nd) floor including risers pipe at axis (1-2) with axis (E-G) accordding to the attached sketch. (Zone4,5) | MECH | Z4,5 | Z4,5 | 2nd | 43717 | 43720 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0353 | Check installation and test for water supply PPR pipes toilet (TD 12) (allocation) at (2nd) floor including risers pipe at axis (1-2) with axis (E-G) accordding to the attached sketch. (Zone4,5) | MECH | Z4,5 | Z4,5 | 2nd | 43717 | 43720 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0354 | Check installation and test for drainge UPVC pipes toilet (TD 12) (allocation) at (4th) floor including risers pipe at axis (10-12) with axis (J-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | 4th | 43717 | 43720 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0355 | Check installation and test for water supply PPR pipes toilet (TD 12) (allocation) at(4th) floor including risers pipe at axis (10-12) with axis (J-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | 4th | 43717 | 43720 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0356 | Check installation and test UPVC pipes water features NO.(4) for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43717 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0357 | Check installation and test for flush TANK Water supply pipe toilet Diatel (TD 5) in( 9th ) floor Including Isolating Valve at axis (9-10) with axis (E-L) at ZONE (3) . | MECH | Z3 | Z3 | 9th | 43717 | 43720 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0358 | Check installation and test for flush valve Water supply pipe toilet Diatel (TD 4,6) in( 9th ) floor Including Isolating Valve at axis (9-10) with axis (E-L) at ZONE (3) . | MECH | Z3 | Z3 | 9th | 43717 | 43720 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0359 | Check Installaion location and Level For irrigation main line (Branches) UPVC ᶲ63 pipes including sleeves ᶲ50 network part 4 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43717 | 43720 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0360 | Check hydraulic test for the firefighting zone (main + branches) at third floor at zone(3B,4,5) . | MECH | Z3B,4,5 | Z3B,4,5 | 3rd | 43718 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0361 | check flushing for the firefighting zone (main + branches) at third floor at zone(3B,4,5) . | MECH | Z3B,4,5 | Z3B,4,5 | 3rd | 43718 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0362 | check flushing for the firefighting zone (main + branches) at fifth floor at zone(1,2,3A) . | MECH | Z1,2,3A | Z1,2,3A | 5th | 43718 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0363 | Check installation and test for drainge UPVC pipes toilet (TD 12) (allocation) at ( 3rd ) floor at axis (16-18) with axis (C-D) accordding to the attached sketch. (Zone1) | MECH | Z1 | Z1 | 3rd | 43719 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0364 | Check installation and test for water supply PPR pipes toilet (TD 12) (allocation) at ( 3rd ) floor at axis (16-18) with axis (C-D) accordding to the attached sketch. (Zone1) | MECH | Z1 | Z1 | 3rd | 43719 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0365 | Check installation and test for drainge UPVC pipes toilet (TD 12) (allocation) at (5th) floor at axis (14-15) with axis (D-E) accordding to the attached sketch. (Zone1) | MECH | Z1 | Z1 | 5th | 43719 | 43724 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0366 | Check installation and test for water supply PPR pipes toilet (TD 12) (allocation) at (5th) floor at axis (14-15) with axis (D-E) accordding to the attached sketch. (Zone1) | MECH | Z1 | Z1 | 5th | 43719 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0367 | Check installation and test for drainge external UPVC pipes under ground (SP & WP &ST ) at ground floor at axis (4-7) with axis (K-L) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | GF | 43719 | 43732 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0368 | Check installation for water supply galvanize pipes H/L at (B1& B2) at axis (12-18) with axis (F-L) & (1-7) with axis (F-L) accordding to the attached sketch. (Zone2,4) | MECH | Z2,4 | Z2,4 | ML | 43719 | 43730 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0369 | Check installation and test for flush TANK Water supply pipe toilet Diatel (TD 12) (allocation) in(2nd & 3rd & 4th & 5th) floor Including Isolating Valve at ZONE (1,2,4,5) . | MECH | Z1,2,4,5 | Z1,2,4,5 | ML | 43719 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0370 | Check installation and test for flush TANK Water supply pipe toilet Diatel (TD 9) (allocation) in (3rd & 4th & 5th & 6th) floor Including Isolating Valve at ZONE (3B) . | MECH | Z3B | Z3B | ML | 43719 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0371 | Check Installaion and test location and Level For irrigation main line UPVC ᶲ110 pipes including sleeves cable control ᶲ50 (16 bar) network part 3 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43723 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0372 | Check installation and test for flush TANK Water supply pipe toilet Diatel (TD 9) (allocation) in(2nd & 3rd & 4th & 5th & 6th) floor Including Isolating Valve at ZONE (3A) . | MECH | Z3A | Z3A | ML | 43723 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0373 | Check installation and test for flush TANK Water supply pipe toilet Diatel (TD 12) (allocation) in( 3rd & 4th & 5th) floor Including Isolating Valve at ZONE (1,2) . | MECH | Z1,2 | Z1,2 | ML | 43723 | 43725 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0374 | Check installation for fire fighting network (main loop) for ground floor (Z1.2.3A) | MECH | Z1,2,3A | Z1,2,3A | GF | 43724 | 43727 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0375 | Check installation of internal insulation for HVAC duct work in ninth floor for IC-RF-AHU-03 | MECH |  |  | 9th | 43724 | 43732 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0376 | Check installation of internal insulation for HVAC duct work in eight floor for IC-RF-AHU-01 | MECH |  |  | 8th | 43724 | 43732 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0377 | Check installation of internal insulation for HVAC duct work in seventh floor for IC-RF-AHU-02 and IC-8F-AHU-01 | MECH |  |  | 7th | 43724 | 43732 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0378 | Check installation and test for drainge UPVC pipes garbage room at first basement between axis (14-18)&(1-5) with axis (G-H) accordding to the attached sketch. (Zone2,4) | MECH | Z2,4 | Z2,4 | B1 | 43724 | 43732 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0379 | Check installation and test for water supply PPR pipes garbage room at first basement between axis (14-18)&(1-5) with axis (G-H) accordding to the attached sketch. (Zone2,4) | MECH | Z2,4 | Z2,4 | B1 | 43724 | 43732 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0380 | Check installation for puddle flange for irrigation tank | MECH | L.S | L.S | EX | 43725 | 43727 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0381 | Check installation and test for drainge riser stack UPVC (WP&SP) pipes from B1 to 6th floor including wall hang toilet & toilet wall mounted (special need) at axis (F-H)/ (14-17) accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | ML | 43725 | 43732 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0382 | Check instlation and test for garage drain (4") and clean out(6") ductile gosam at second basement for area zone(6) accordding to the attached sketch. | MECH | Z6 | Z6 | B2 | 43725 | 43732 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0383 | check instllation for the firefighting zone (branches) at ninth floor . | MECH | Z3 | Z3 | 9th | 43727 | 43732 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0384 | Check installation and test for drainge UPVC pipes toilet (TD 2) (CORE) at (8 th) floor including risers pipe at axis (10-11) with axis (J-K) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | 8th | 43729 | 43732 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0385 | Check installation and test for water supply PPR pipes toilet (TD 2) (Core) at (8 th) floor at axis (10-11) with axis (J-K) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | 8th | 43729 | 43732 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0386 | Check installation and test for drainge UPVC pipes toilet (TD 3) (allocation) at (8 th) floor including risers pipe at axis (10-11) with axis (K-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | 8th | 43729 | 43732 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0387 | Check installation and test for water supply PPR pipes toilet (TD 3) (allocation) at (8 th ) floor at axis (10-11) with axis (K-L) accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | 8th | 43729 | 43732 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0388 | Check installation and test for drainge UPVC pipes H/L at ground floor at axis (6-12) with axis (E-L) accordding to the attached sketch. (Zone3) | MECH | z3 | z3 | GF | 43730 | 43738 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0389 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part1&2 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43731 | 43734 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0390 | Check instlation and test for Roof drain UPVC ST pipes at roof at second floor for area zone(2,4) accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | 2nd | 43731 | 43734 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0391 | check instllation for the firefighting pipes (main+branches) at third floor at zone(1,2,3A). | MECH | Z1,2,3A | Z1,2,3A | 3rd | 43731 | 43738 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0392 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43733 | 43738 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0393 | Check installation and test for drainge external UPVC pipes and HDPE under ground (SP & WP &ST ) at ground floor at axis (K-H)/(18) accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | EX | 43733 | 43740 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0394 | Check sand blasting & primer coating for chilled water pipes | MECH |  |  | ML | 43734 | 43738 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0395 | Check hydraulic test for the firefighting zone (main + branches) at third floor at zone(3A,1,2) . | MECH | Z1,2,3A | Z1,2,3A | 3rd | 43734 | 43738 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0396 | Check installation for fire fighting network (Branches) at sixth floor AT ZONE (4,5,3B) | MECH | Z3B,4,5 | Z3B,4,5 | 6th | 43736 | 43747 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0397 | Check installation for fire fighting network (Branches) at sixth floor AT ZONE (1,2,3A) | MECH | Z1,2,3A | Z1,2,3A | 6th | 43736 | 43747 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0398 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43736 | 43738 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0399 | Check Installaion and test location and Level For irrigation main line UPVC ᶲ110 pipes and sleeves cable control by (50MM) network part 2 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43737 | 43740 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0400 | Check Installaion and test pipe location and Level For irrigation network Pipes (dripping &sleeves) part 08 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43737 | 43740 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0401 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part (4) for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43740 | 43745 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0402 | Check installation of sleeves & Transfer Duct for HVAC Duct Work in second Floor to attached sketch . | MECH |  |  | 2nd | 43740 | 43745 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0403 | Check installation of sleeves & Transfer Duct for HVAC Duct Work in third Floor to attached sketch . | MECH |  |  | 3rd | 43740 | 43745 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0404 | Check installation of vertical pipes for chilled water risers in zone 3A to attached sketch. | MECH | Z3A | Z3A | ML | 43740 | 43745 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0405 | Check installation of vav unit for HVAC duct work in fourth floor to attached sketch. | MECH |  |  | 4th | 43740 | 43745 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0406 | Check Mockup of external insulation in pantry for black steel with rook wool in Second Floor to attached sketch . | MECH |  |  | 2nd | 43740 | 43745 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0407 | Check installation of sleeves & Transfer Duct for HVAC Duct Work in first Floor to attached sketch . | MECH |  |  | 1st | 43740 | 43745 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0408 | Check flushing for the firefighting zone (main + branches) at THIRD floor at zone(1.2.3A) | MECH | Z1,2,3A | Z1,2,3A | 3rd | 43741 | 43746 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0409 | Check installation for fire fighting network (Branches) at FIRST floor AT ZONE (1.2.3A) | MECH | Z1,2,3A | Z1,2,3A | 1st | 43741 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0410 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part (4) for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43741 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0411 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part (3,1) for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43745 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0412 | Check installation and test for drainge pipe tepical toilet detail (TD 11) in ground floor AT ZONE(4) | MECH | Z4 | Z4 | GF | 43745 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0413 | Check installation and test for water supply PPR pipe tepical toilet detail (TD 11) in ground floor AT ZONE(4) | MECH | Z4 | Z4 | GF | 43745 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0414 | Check installation and test for water supply PPR pipe H/L in ground floor AT ZONE(3B,4,5) | MECH | Z3B,4,5 | Z3B,4,5 | GF | 43745 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0415 | Check installation and test for drainge UPVC pipes toilet (TD 12) (allocation) at (6th&7th) floor at axis (2-3) with axis (G-H) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | ML | 43746 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0416 | Check installation and test for water supply PPR pipes toilet (TD 12) (allocation) at (6th&7th) floor at axis (2-3) with axis (G-H) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | ML | 43746 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0417 | Check Installaion and test pipe location and Level For irregation network Pipes (sprinkler & dripping) part 05 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43746 | 43748 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0418 | Check installation for fire fighting network (Branches) at fourth floor AT ZONE (3B,4,5) | MECH | Z3B,4,5 | Z3B,4,5 | 4th | 43746 | 43754 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0419 | Check installation for ref pipes for crack units (IC-GF-CRAC-02) for main telecom room at ground floor at Zone 5 from ground floor to sixth floor NO. 3 Units . | MECH | L.S | L.S | EX | 43746 | 43751 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0420 | Check installation and test for drainge UPVC pipes force main external from water feature pump room to slow down champer at part 2 accordding to the attached sketch. | MECH | L.S | L.S | EX | 43747 | 43751 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0421 | Check installation and test UPVC pipes from water features (5) to pump room for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43747 | 43753 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0422 | Check installation and test UPVC pipes water features (5) for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43747 | 43751 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0423 | Check Installaion location and Level For puddle flange for wall water feature pump room NO.2 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43747 | 43751 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0424 | Check hydraulic test for the firefighting zone (main + branches) at sixth floor at zone(3B,4,5) . | MECH | Z3,4,5 | Z3,4,5 | 6th | 43747 | 43751 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0425 | Check installation for fire fighting network (Branches) at FIRST floor AT ZONE (4.5.3B). | MECH | Z3,4,5 | Z3,4,5 | 1st | 43751 | 43761 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0426 | Check hydraulic test for the firefighting zone (main + branches) at sixth floor at zone(3A,1,2) . | MECH | Z1,2,3A | Z1,2,3A | 6th | 43752 | 43760 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0427 | Check installation and test for drainge UPVC pipes force main external from water feature pump room to slow down champer at part 2 accordding to the attached sketch. | MECH | L.S | L.S | EX | 43752 | 43758 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0428 | Check installation and test UPVC pipes over flow around water features (3) for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43753 | 43758 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0429 | Check Installaion and test pipe location and Level For irrIgation network Pipes (sprinkler & dripping) part 3 (Z10) for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43754 | 43761 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0430 | Check installation and test for drainge UPVC pipes toilet (TD 3) (allocation) at (7th & 9th) floor including risers pipe at axis (8-11) with axis (F-L) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | ML | 43754 | 43760 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0431 | Check installation and test for water supply PPR pipes toilet (TD 3) (allocation) at (7th & 9th ) floor at axis (8-11) with axis (F-L) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | ML | 43754 | 43760 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0432 | Check installation and test for drainge UPVC pipes toilet (TD 14&TD 15) (allocation) at (9 th) floor including risers pipe at axis (8-11) with axis (F-L) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | 9th | 43754 | 43760 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0433 | Check installation and test for water supply PPR pipes toilet (TD 14&TD 15) (Core) at (9 th) floor at axis (8-11) with axis (F-L) accordding to the attached sketch. (Zone3) | MECH | Z3 | Z3 | 9th | 43754 | 43760 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0434 | Check flushing for the firefighting zone (main + branches) at first floor at zone(1.2.3A) | MECH | Z1,2,3A | Z1,2,3A | 1st | 43755 | 43760 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0435 | Check installation for ref pipes for crack units (IC-GF-CRAC-01) for main telecom room at ground floor at Zone 1 from ground floor to sixth floor NO. 2 Units . | MECH |  |  | ML | 43755 | 43761 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0436 | Check installation and test UPVC pipes from water features (Shalal Number 1-2) for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43759 | 43761 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0437 | Check hydraulic test for the firefighting zone (main + branches) at first floor at zone(3B,4,5) . | MECH | Z3B,4,5 | Z3B,4,5 | 1st | 43759 | 43765 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0438 | Check installation for the firefighting zone (main + branches) at eighth floor at zone(2) . | MECH | Z2 | Z2 | 8th | 43759 | 43761 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0439 | Check installation for the firefighting zone (main + branches) at eighth floor at zone(3,4) . | MECH | Z3,4 | Z3,4 | 8th | 43759 | 43767 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0440 | Check installation for the firefighting risers at zone(1,2,3,4,5) | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 43759 | 43767 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0441 | Check Installaion location and Level For puddle flange for wall water feature pump room NO.1 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43759 | 43761 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0442 | Check Installaion and test pipe location and Level For irrIgation network Pipes (sprinkler & dripping) part 3 (Z12) for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43759 | 43761 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0443 | Check hydraulic test for the firefighting zone (main + branches) at first floor at zone(1.2.3A) | MECH | Z1,2,3A | Z1,2,3A | 1st | 43760 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0444 | Check installation and test for water supply PPR pipe H/L in ground floor AT ZONE(3A,1,2) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | GF | 43760 | 43765 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0445 | Check installation and test for flush valve Water supply pipe toilet Detail (TD 11) in ground floor at ZONE (2,4) accordding to the attached sketch. . | MECH | Z2,4 | Z2,4 | GF | 43760 | 43765 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0446 | Check installation and test for flush valve Water supply pipe toilet Detail (TD 14) at 9th floor at ZONE (3B) accordding to the attached sketch. . | MECH | Z3B | Z3B | 9th | 43762 | 43765 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0447 | Check installation and test for flush valve Water supply pipe toilet Detail (TD 3) at 9th floor at ZONE (3B) accordding to the attached sketch. | MECH | Z3B | Z3B | 9th | 43762 | 43766 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0448 | Check hydraulic test for the firefighting zone (main + branches) at eight floor at zone(2) | MECH | Z2 | Z2 | 8th | 43765 | 43767 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0449 | Check installation and test UPVC pipes from water features (5 NO.2) to pump room for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43766 | 43769 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0450 | Check Installaion location and Level For puddle flange for wall water feature pump room NO.3 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43766 | 43769 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0451 | Check Installaion and test location and Level For irrigation main line UPVC ᶲ110 pipes network part 2 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43767 | 43769 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0452 | Check Installaion and test location and Level For irrigation network quick coupler 1" part 2 for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43767 | 43769 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0453 | Check installation for water supply Galvanize pipe riser stack from Basemnet 1 to Seventh floor zone(2&4) accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | ML | 43768 | 43781 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0454 | Check installation and test for drainge UPVC pipes toilet (TD 7) (allocation) at (7th) floor at zone(3A&3B) accordding to the attached sketch. | MECH | Z3 | Z3 | 7th | 43768 | 43772 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0455 | Check installation and test for water supply PPR pipes toilet (TD 7) (allocation) at (7th) floor at zone(3A&3B) accordding to the attached sketch. | MECH | Z3 | Z3 | 7th | 43768 | 43772 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0456 | Check installation of internal insulation for HVAC duct work in ground floor for IC-GF-AHU-01 & IC-GF-AHU-02 & IC-GF-AHU-03 . | MECH |  |  | GF | 43769 | 43774 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0457 | Check installation of internal insulation for HVAC duct work in ground floor for IC-GF-AHU-04 & IC-GF-AHU-05 & IC-GF-AHU-06 . | MECH |  |  | GF | 43769 | 43774 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0458 | Check installation and SMOKE test for HVAC duct work in ground Floor for IC-GF-AHU-01 & IC-GF-AHU-02 & IC-GF-AHU-03 . | MECH |  |  | GF | 43769 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0459 | Check installation and SMOKE test for HVAC duct work in ground Floor for IC-GF-AHU-04 & IC-GF-AHU-05 & IC-GF-AHU-06 . | MECH |  |  | GF | 43769 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0460 | Check installation and test for flush valve Water supply pipe toilet Detail (TD 3 & TD 16) at 8th & 9th floor at ZONE (3A) accordding to the attached sketch. . | MECH | Z3A | Z3A | ML | 43771 | 43775 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0461 | Check installation and test for flush valve Water supply pipe toilet Detail (TD 2 & TD 15 ) at 8th & 9th floor at ZONE (3A) accordding to the attached sketch. | MECH | Z3A | Z3A | ML | 43771 | 43775 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0462 | Check installation and test for drainge UPVC pipes VP&WP (H/L&TD) at ( 2nd&3rd&4th&5th&7th) floor at zone (1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 43772 | 43775 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0463 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part (4) for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43772 | 43775 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0464 | Check installation and test for drainge riser stack UPVC (WP) ᶲ75MM pipes from B1 to 7th floor accordding to the attached sketch. (Zone2,4) | MECH | Z2,4 | Z2,4 | ML | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0465 | Check installation and test for drainge riser stack UPVC (ST) 6" pipes from B1 to 5th floor accordding to the attached sketch. (Zone2) | MECH | Z2 | Z2 | ML | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0466 | Check hydraulic test for the firefighting zone (main + branches) at eight floor at zone(3,4) | MECH | Z3,4 | Z3,4 | 8th | 43772 | 43775 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0467 | Check hydraulic test for the firefighting zone (main + branches) at ninth floor accordding to the attached sketch. | MECH | Z3 | Z3 | 9th | 43772 | 43781 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0468 | Check installation of external insulation for chilled water pipes in second basement accordding to the attached sketch. | MECH |  |  | B2 | 43772 | 43789 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0469 | Check installation of external insulation for HVAC duct work in first floor for IC-1F-AHU-01 & IC-1F-AHU-02 & IC-1F-AHU-03 . | MECH |  |  | 1st | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0470 | Check installation of external insulation for HVAC duct work in first floor for IC-1F-AHU-04 & IC-1F-AHU-05 & IC-1F-AHU-06 . | MECH |  |  | 1st | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0471 | Check installation and SMOKE test for HVAC duct work in seventh Floor for IC-8F-AHU-01 & IC-RF-AHU-01 . | MECH |  |  | 7th | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0472 | Check installation and SMOKE test for HVAC duct work in eighth Floor for IC-RF-AHU-02 . | MECH |  |  | 8th | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0473 | Check installation and SMOKE test for HVAC duct work in ninth Floor for IC-RF-AHU-03 . | MECH |  |  | 9th | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0474 | Check installation of external insulation for HVAC duct work in seventh floor for IC-8F-AHU-01 & IC-RF-AHU-01 . | MECH |  |  | 7th | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0475 | Check installation of external insulation for HVAC duct work in eighth Floor for IC-RF-AHU-02 . | MECH |  |  | 8th | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0476 | Check installation of external insulation for HVAC duct work in ninth Floor for IC-RF-AHU-03 . | MECH |  |  | 9th | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0477 | Check installation of external insulation for HVAC duct work in first basement for IC-6F-FAHU-02 & in second basement for IC-6F-FAHU-02 . | MECH |  |  | B1 | 43772 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0478 | Check installation and SMOKE test for HVAC duct work in first basement for IC-B1-CPEF-07 & IC-B1-CPEF-08 . | MECH |  |  | B1 | 43773 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0479 | Check installation and SMOKE test for HVAC duct work in rieser from seventh to roof floor for IC-RF-AHU-04 & IC-RF-AHU-05 & IC-RF-AHU-06 . | MECH |  |  | ML | 43773 | 43793 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0480 | Check installation of chilled water pumps (tertiary pump) in ETS room for first basement . | MECH |  |  | B1 | 43773 | 43783 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0481 | Check installation of heat exchenger in ETS room for first basement . | MECH |  |  | B1 | 43773 | 43783 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0482 | Check installation of vav unit for HVAC duct work in ground floor | MECH |  |  | GF | 43773 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0483 | Check installation of vav unit for HVAC duct work in fifth floor | MECH |  |  | 5th | 43773 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0484 | Check installation of vav unit for HVAC duct work in sixth floor | MECH |  |  | 6th | 43773 | 43782 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0485 | Check installation of vav unit for HVAC duct work in seventh floor | MECH |  |  | 7th | 43773 | 43782 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0486 | Check installation of sleeves & Transfer Duct for HVAC Duct Work in ground Floor to attached sketch . | MECH |  |  | GF | 43773 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0487 | Check installation of sleeves & Transfer Duct for HVAC Duct Work in fourth Floor to attached sketch . | MECH |  |  | 4th | 43773 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0488 | Check installation of sleeves & Transfer Duct for HVAC Duct Work in fifth Floor to attached sketch . | MECH |  |  | 5th | 43773 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0489 | Check installation of sleeves & Transfer Duct for HVAC Duct Work in sixth Floor to attached sketch . | MECH |  |  | 6th | 43773 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0490 | Check hydraulic test for the firefighting zone (main + branches) at fourth floor at zone(3B,4,5) | MECH | Z3B,4,5 | Z3B,4,5 | 4th | 43773 | 43775 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0491 | Check installation and test for drainge UPVC pipes H/L VP pipes from first basement to second basement accordding to the attached sketch. (Zone3B&6) | MECH | Z3B,6 | Z3B,6 | ML | 43775 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0492 | check installation for split units at second basement (indoor unit) as per attached sketch. | MECH |  |  | B2 | 43779 | 43787 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0493 | Check installation and test UPVC pipes from water features (chalal Number 2) for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43781 | 43789 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0494 | check insallation mockup for valve champer for drainge force main by sumbit for second basement at zone(3) to the attached sketch. | MECH | Z3 | Z3 | B2 | 43781 | 43793 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0495 | Check installation and test UPVC pipes from water features (chalal Number 1) for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43783 | 43789 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0496 | Check installation for thrust support for fire fighting pipes at first basement accordding to the attached sketch. | MECH |  |  | B1 | 43786 | 43794 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0497 | Check vaccum test for split units ref pipes at second basement accordding to the attached sketch. | MECH |  |  | B2 | 43786 | 43793 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0498 | Check installation and test for flush valve Water supply pipe toilet Detail (TD 3) at 7th floor at ZONE (3A) accordding to the attached sketch. | MECH | Z3A | Z3A | 7th | 43787 | 43789 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0499 | Check installation and test for flush valve Water supply pipe toilet Detail (TD 7) at 7th floor at ZONE (3A,3B) accordding to the attached sketch. | MECH | Z3 | Z3 | 7th | 43787 | 43789 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0500 | Check installation and test for drainge riser stack UPVC (WP) 4" pipes from B1 to 5th floor accordding to the attached sketch. (Zone1,5) | MECH | Z1,5 | Z1,5 | ML | 43787 | 43789 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0501 | Check installation and test for drainge UPVC (SP&WP) pipes H/L at 3rd floor accordding to the attached sketch. (Zone3A) | MECH | Z3A | Z3A | 3rd | 43787 | 43795 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0502 | Check Mockup of installation hookup(chilled water pipes)for air handling unit in second floor for IC-2F-AHU-04&IC-2F-AHU-05 accordding to the attached sketch. | MECH |  |  | 2nd | 43789 | 43802 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0503 | Check installation for thrust support for fire fighting pipes at second floor accordding to the attached sketch. | MECH |  |  | 2nd | 43790 | 43795 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0504 | Check installation for thrust support for fire fighting pipes at third floor accordding to the attached sketch. | MECH |  |  | 3rd | 43790 | 43795 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0505 | Check installation for thrust support for fire fighting pipes at fifth floor accordding to the attached sketch. | MECH |  |  | 5th | 43790 | 43795 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0506 | Check installation and test for flush TANK Water supply pipe toilet Diatel (TD 12) (allocation) in( 6th & 7th) floor Including Isolating Valve at ZONE (4) . | MECH | Z4 | Z4 | ML | 43793 | 43802 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0507 | Check installation for fire fighting network (Main line+Branches) at Fourth floor AT ZONE (1,2,3A). | MECH | Z1,2,3A | Z1,2,3A | 4th | 43793 | 43797 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0508 | Check installation for thrust support for fire fighting pipes at sixth floor accordding to the attached sketch. | MECH |  |  | 6th | 43793 | 43795 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0509 | Check flushing for the firefighting zone (main + branches) at first basement at zone(3B,4,5) | MECH | Z3B,4,5 | Z3B,4,5 | B1 | 43794 | 43797 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0510 | Check installation for fire fighting network (Branches) at seventh floor AT ZONE (2,3,4) | MECH | Z2,3,4 | Z2,3,4 | 7th | 43795 | 43797 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0511 | Check installation EWH (30L & 50L & 80L & 100L) for water supply pipe toilet Diatel (TD 13) & (TD 8) & (TD 9) &(TD 12) and garbage sink and jenator sink at Zone (1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43801 | 43808 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0512 | Check installation EWH (30L & 50L & 80L & 100L) for water supply pipe toilet Diatel (TD 13) & (TD 8) & (TD 9) &(TD 12) and garbage sink and jenator sink for third floor at Zone (1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43801 | 43808 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0513 | Check installation for fire fighting network (Branches) at first basement at ZONE (6) | MECH | Z6 | Z6 | B1 | 43802 | 43808 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0514 | Check flushing for the firefighting (main + branches) at first floor at zone(3B,4,5) | MECH | Z3B,4,5 | Z3B,4,5 | 1st | 43802 | 43804 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0515 | Check installation and test for drainge UPVC (WP) pipes H/L at second basement accordding to the attached sketch. (Zone6) | MECH | Z6 | Z6 | B2 | 43802 | 43808 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0516 | Check installation and test for drainge UPVC pipes toilet (TD 14) (allocation) at ground floor at axis (5-7) with axis (J-L) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | GF | 43802 | 43804 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0517 | Check installation and test for water supply PPR pipes toilet (TD 14) (allocation) at ground floor at axis (5-7) with axis (J-L) accordding to the attached sketch. (Zone4) | MECH | Z4 | Z4 | GF | 43802 | 43804 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0518 | Check installation and test for drainge UPVC (VP) pipes H/L at second basement accordding to the attached sketch. (Zone6) | MECH | Z6 | Z6 | B2 | 43804 | 43809 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0519 | Check installation EWH (30L) for water supply pipe toilet Diatel (TD 9) &(TD 10) and garbage sink for first basement at Zone (1,2,4,5) accordding to the attached sketch. | MECH | Z1,2,4,5 | Z1,2,4,5 | B1 | 43804 | 43808 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0520 | Check installation and test for drainge UPVC pipes force main external from water feature pump room (1,2) to slow down champer at part 2 accordding to the attached sketch. | MECH | L.S | L.S | EX | 43804 | 43811 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0521 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43807 | 43809 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0522 | check intsatllation for upright sprinklers at second floor accordding to the attached sketch. | MECH |  |  | 2nd | 43807 | 43810 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0523 | check intsatllation for upright sprinklers at fifth floor accordding to the attached sketch. | MECH |  |  | 5th | 43807 | 43810 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0524 | Check installation for thrust support for fire fighting pipes at seventh floor accordding to the attached sketch. | MECH |  |  | 7th | 43807 | 43810 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0525 | Check installation for thrust support for fire fighting pipes at eight floor accordding to the attached sketch. | MECH |  |  | 8th | 43807 | 43810 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0526 | Check installation for thrust support for fire fighting pipes at ninth floor accordding to the attached sketch. | MECH |  |  | 9th | 43807 | 43810 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0527 | Check flushing for the firefighting (main + branches) at first basement at zone(1,2,3A) | MECH | Z1,2,3A | Z1,2,3A | B1 | 43807 | 43810 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0528 | Check installation and test UPVC pipes from water features (chalal Number 1) plan (1,2) for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43808 | 43815 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0529 | Check installation UPVC pipes from water features NO.4 to pump room NO.2 for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43808 | 43815 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0530 | Check installation and test for water supply Galvanize pipe riser stack from Basemnet 1 to Seventh floor zone(4) accordding to the attached sketch. | MECH | Z4 | Z4 | ML | 43814 | 43818 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0531 | Check installation and test for water supply PPR pipes ablution ground floor at axis (1-7) with axis (A-F) accordding to the attached sketch. (Zone5) | MECH | Z5 | Z5 | GF | 43814 | 43818 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0532 | Check installation of flexible connection for fire fighting pipes at first floor accordding to the attached sketch. | MECH |  |  | 1st | 43815 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0533 | Check installation of flexible connection for fire fighting pipes at second floor accordding to the attached sketch. | MECH |  |  | 2nd | 43815 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0534 | Check installation of flexible connection for fire fighting pipes at third floor accordding to the attached sketch. | MECH |  |  | 3rd | 43815 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0535 | Check installation of flexible connection for fire fighting pipes at fourth floor accordding to the attached sketch. | MECH |  |  | 4th | 43815 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0536 | Check installation and test for water supply(PPR) pipe H/L first Basemnet zone(6) accordding to the attached sketch. | MECH | Z6 | Z6 | B1 | 43815 | 43817 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0537 | Check installation and test for water supply(PPR) pipe H/L ninth floor zone(3) accordding to the attached sketch. | MECH | Z3 | Z3 | 9th | 43815 | 43817 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0538 | Check installation for water supply galvanize and PPR pipes H/L at first basement at axis (1-18) with axis (F-L) accordding to the attached sketch. (Zone5,4,3,2,1) | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43815 | 43818 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0539 | Check installation for thrust support for fire fighting pipes at first floor accordding to the attached sketch. | MECH |  |  | 1st | 43815 | 43821 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0540 | Check installation and test UPVC pipes complet water features (chalal Number 1) plan 2 for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43816 | 43818 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0541 | Check installation for water supply isolating valve and water hamer excluid (PRV) at second & third floor all toilet detail zone(1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 43816 | 43829 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0542 | Check installation for the galvnaized drain riser for fire fighting for zone(2,4,3B) accordding to the attached sketch. | MECH | Z2,3B,4 | Z2,3B,4 | ML | 43818 | 43823 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0543 | Check flushing for the firefighting (main + branches) at ninth floor at zone(3) accordding to the attached sketch. | MECH | Z3 | Z3 | 9th | 43818 | 43823 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0544 | Check hydraulic test for the firefighting zone (main + branches) at seventh floor at zone(3B,4) | MECH | Z3B,4,5 | Z3B,4,5 | 7th | 43818 | 43825 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0545 | Check installation and test UPVC pipes complet water features (chalal Number 1) plan 1 for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43821 | 43825 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0546 | Check installation EWH (30L & 50L & 80L & 100L) for water supply pipe toilet Diatel (TD 11) & (TD 8) & (TD 9) &(TD 12) and garbage sink and jenator sink for fourth floor and fifth at Zone (1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 43822 | 43829 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0547 | Check installation for water supply isolating valve and water hammer excluid (PRV) at fourth & fifth floor all toilet detail zone(1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 43822 | 43829 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0548 | Check installation UPVC pipes water features (3,5) to pump room no.3 for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43823 | 43829 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0549 | Check installation and test for drainge riser stack UPVC (SP&WP&ST) (4"&6''&3'') pipes from B1 to 7th floor accordding to the attached sketch. (Zone3A,3B) | MECH | Z3 | Z3 | ML | 43823 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0550 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part (4) for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43823 | 43829 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0551 | Check installation for water supply galvanize pipes H/L at (B2) at axis (12-18) with axis (F-L) & (1-7) with axis (F-L) accordding to the attached sketch. (Zone2,3,4,5). | MECH | Z2,3,4,5 | Z2,3,4,5 | B2 | 43823 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0552 | Check installation and test for water supply(PPR) pipe H/L at second Basemnet zone(6) accordding to the attached sketch. | MECH | Z6 | Z6 | B2 | 43823 | 43829 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0553 | Check Installaion location and Level For Subsurface Drainge perfrated network Clean out part (1,2) for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43825 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0554 | Check installation UPVC pipes from water features NO(4)and chalal No(2) plan(2) to pump room NO.2 for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43825 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0555 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43828 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0556 | Check installation and test for water supply Galvanize pipe riser stack from first Basemnet to Seventh floor zone(2) accordding to the attached sketch. | MECH | Z2 | Z2 | ML | 43828 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0557 | Check installation and test for water supply PPR pipes ablution ground floor at axis (12-18) with axis (A-F) accordding to the attached sketch. (Zone1) | MECH | Z1 | Z1 | GF | 43828 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0558 | Check installation and test for water supply PPR pipes 90mm under ground filling line from first basement to pump room water feature N.o 3 for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43829 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0559 | check intsatllation for upright sprinklers at first floor for area(Z4,5,3B) accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 1st | 43830 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0560 | check intsatllation for upright sprinklers at Third floor for area(Z4,5,3B) accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 3rd | 43830 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0561 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part (4) for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43830 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0562 | Check installation and test for drainge UPVC pipes force main external from water feature pump room (3) to slow down champer at part 2 accordding to the attached sketch. | MECH | L.S | L.S | EX | 43830 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0563 | Check hydraulic test for the firefighting zone (main + branches) at seventh floor at zone(3A,2) | MECH | Z2,3A | Z2,3A | 7th | 43831 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0564 | Check installation for EXHAUST HVAC duct work in ground floor for IC-8F-EF-01 & IC-8F-EF-03 & IC-8F-EF-08 . | MECH |  |  | GF | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0565 | Check installation for EXHAUST HVAC duct work in first floor for IC-8F-EF-01 & IC-8F-EF-03 & IC-8F-EF-08 . | MECH |  |  | 1st | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0566 | Check installation for EXHAUST HVAC duct work in second floor for IC-8F-EF-01 & IC-8F-EF-03 & IC-8F-EF-08 . | MECH |  |  | 2nd | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0567 | Check installation for EXHAUST HVAC duct work in third floor for IC-8F-EF-01 & IC-8F-EF-03 & IC-8F-EF-08 . | MECH |  |  | 3rd | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0568 | Check installation for EXHAUST HVAC duct work in fourth floor for IC-8F-EF-01 & IC-8F-EF-03 & IC-8F-EF-08 . | MECH |  |  | 4th | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0569 | Check installation for EXHAUST HVAC duct work in ground floor for IC-8F-EF-04 & IC-8F-EF-06 & IC-8F-EF-09 . | MECH |  |  | GF | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0570 | Check installation for EXHAUST HVAC duct work in first floor for IC-8F-EF-04 & IC-8F-EF-06 & IC-8F-EF-09 . | MECH |  |  | 1st | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0571 | Check installation for EXHAUST HVAC duct work in second floor for IC-8F-EF-04 & IC-8F-EF-06 & IC-8F-EF-09 . | MECH |  |  | 2nd | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0572 | Check installation for EXHAUST HVAC duct work in third floor for IC-8F-EF-04 & IC-8F-EF-06 & IC-8F-EF-09 . | MECH |  |  | 3rd | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0573 | Check installation for EXHAUST HVAC duct work in fourth floor for IC-8F-EF-04 & IC-8F-EF-06 & IC-8F-EF-09 . | MECH |  |  | 4th | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0574 | Check installation for black steel duct work in ground floor for IC-8F-EF-02 (in pantry) | MECH |  |  | GF | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0575 | Check installation for black steel duct work in first floor for IC-8F-EF-02 (in pantry) | MECH |  |  | 1st | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0576 | Check installation for black steel duct work in second floor for IC-8F-EF-02 (in pantry) | MECH |  |  | 2nd | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0577 | Check installation for black steel duct work in third floor for IC-8F-EF-02 (in pantry) | MECH |  |  | 3rd | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0578 | Check installation for black steel duct work in fourth floor for IC-8F-EF-02 (in pantry) | MECH |  |  | 4th | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0579 | Check installation for black steel duct work in ground floor for IC-8F-EF-05 (in pantry) | MECH |  |  | GF | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0580 | Check installation for black steel duct work in first floor for IC-8F-EF-05 (in pantry) | MECH |  |  | 1st | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0581 | Check installation for black steel duct work in second floor for IC-8F-EF-05 (in pantry) | MECH |  |  | 2nd | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0582 | Check installation for black steel duct work in third floor for IC-8F-EF-05 (in pantry) | MECH |  |  | 3rd | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0583 | Check installation for black steel duct work in fourth floor for IC-8F-EF-05 (in pantry) | MECH |  |  | 4th | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0584 | Check installation for black steel duct work in ground floor for IC-6F-EF-03 | MECH |  |  | GF | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0585 | Check installation for EXHAUST HVAC duct work in ground floor for IC-6F-EF-01 & IC-6F-EF-02. | MECH |  |  | GF | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0586 | Check installation for pressurized HVAC duct work in ground floor for IC-PF-EF-01. | MECH |  |  | GF | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0587 | Check installation of external insulation in pantry for black steel with rook wool in ground Floor for IC-8F-EF-02 & IC-8F-EF-05 . | MECH |  |  | GF | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0588 | Check installation of external insulation in pantry for black steel with rook wool in first Floor for IC-8F-EF-02 & IC-8F-EF-05 . | MECH |  |  | 1st | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0589 | Check installation of external insulation in pantry for black steel with rook wool in second Floor for IC-8F-EF-02 & IC-8F-EF-05 . | MECH |  |  | 2nd | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0590 | Check installation of external insulation in pantry for black steel with rook wool in third Floor for IC-8F-EF-02 & IC-8F-EF-05 . | MECH |  |  | 3rd | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0591 | Check installation of external insulation in pantry for black steel with rook wool in fourth Floor for IC-8F-EF-02 & IC-8F-EF-05 . | MECH |  |  | 4th | 43835 | 43839 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0592 | Check instlation and test for garage drain (4") ductile gosam at first basement for area zone(6) accordding to the attached sketch. | MECH | Z6 | Z6 | B1 | 43836 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0593 | Check installation and test for drainge UPVC pipes kitchen sink at (9th) floor at zone(3B) accordding to the attached sketch. | MECH | Z3B | Z3B | 9th | 43836 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0594 | Check installation and test for water supply PPR pipes kitchen sink at (9th) floor at zone(3B) accordding to the attached sketch. | MECH | Z3B | Z3B | 9th | 43836 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0595 | Check installation EWH (30L & 50L & 80L & 100L) for water supply pipe toilet Diatel (TD 11) & (TD 8) & (TD 9) &(TD 12) and garbage sink and jenator sink for ground & first & sixth & seventh and eighth floor at Zone (1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 43836 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0596 | Check installation for water supply isolating valve and water hammer excluid (PRV) at ground & first & sixth & seventh and eighth floor at Zone (1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 43836 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0597 | Check installation for fire fighting network (main loop) for second basement (Z6) | MECH | Z6 | Z6 | B2 | 43837 | 43839 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0598 | Check installation and test for flush valve Water supply pipe toilet Detail (TD 14) at ground floor at ZONE (4) accordding to the attached sketch. | MECH | Z4 | Z4 | GF | 43839 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0599 | Check installation for fuel tank on the concrete base at zone(1,5) accordding to the attached sketch. | MECH | Z1,5 | Z1,5 | EX | 43842 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0600 | Check Mockup of installation of fire damper for hvac duct work in Second floor accordding to the attached sketch. | MECH |  |  | 2nd | 43842 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0601 | Check installation of Volume damper for hvac duct work in Ground floor accordding to the attached sketch. | MECH |  |  | GF | 43842 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0602 | Check installation of Volume damper for hvac duct work in First floor accordding to the attached sketch. | MECH |  |  | 1st | 43842 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0603 | Check installation of Volume damper for hvac duct work in Second floor accordding to the attached sketch. | MECH |  |  | 2nd | 43842 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0604 | Check installation of Volume damper for hvac duct work in Third floor accordding to the attached sketch. | MECH |  |  | 3rd | 43842 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0605 | check flushing for drainge pipe storm from Ground floor to Roof riser and H/L accordding to the attached sketch. | MECH |  |  | 4th | 43842 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0606 | Check installation of Volume damper for hvac duct work in Fifth floor accordding to the attached sketch. | MECH |  |  | 5th | 43842 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0607 | Check of installation of fire damper for hvac duct work in First floor accordding to the attached sketch. | MECH |  |  | 1st | 43843 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0608 | Check of installation of fire damper for hvac duct work in Second floor accordding to the attached sketch. | MECH |  |  | 2nd | 43843 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0609 | Check of installation of fire damper for hvac duct work in Third floor accordding to the attached sketch. | MECH |  |  | 3rd | 43843 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0610 | check intsatllation for upright sprinklers at ninth floor accordding to the attached sketch. | MECH |  |  | 9th | 43843 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0611 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part (3) for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43843 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0612 | Check Mockup of installation of air outlet for hvac duct work in Second floor accordding to the attached sketch. | MECH |  |  | 2nd | 43843 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0613 | Check installation for hvac duct work of pressurized riser at zone(1) for IC-7F-PF-02 from lower basement to seventh floor accordding to the attached sketch. | MECH | Z1 | Z1 | ML | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0614 | Check installation for hvac duct work of EXHAUST riser for IC-6F-EF-01 from ground to sixth floor accordding to the attached sketch. | MECH |  |  | ML | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0615 | Check installation for hvac duct work of EXHAUST riser for IC-8F-EF-04 from ground to eighth floor accordding to the attached sketch. | MECH |  |  | ML | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0616 | Check installation for hvac duct work of EXHAUST riser for IC-8F-EF-06 from ground to eighth floor accordding to the attached sketch. | MECH |  |  | ML | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0617 | Check installation for hvac duct work of EXHAUST riser for IC-8F-EF-09 from ground to eighth floor accordding to the attached sketch. | MECH |  |  | ML | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0618 | Check installation for hvac duct work of total fresh air riser for IC-6F-FAHU-02 from lower basement to sixth floor accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | ML | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0619 | Check installation for hvac duct work of total fresh air riser for IC-8F-FAHU-02 from ground to eighth floor accordding to the attached sketch. | MECH |  |  | ML | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0620 | Check installation for hvac duct work of smoke riser (black steel) for IC-6F-SF-02 from ground to sixth floor accordding to the attached sketch. | MECH |  |  | ML | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0621 | Check installation for hvac duct work of smoke riser (black steel) for IC-RF-SF-02 from ground to roof floor accordding to the attached sketch. | MECH |  |  | ML | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0622 | Check installation for hvac duct work of EXHAUST riser (black steel) for IC-6F-EF-03 from ground to sixth floor accordding to the attached sketch. | MECH |  |  | ML | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0623 | Check installation of air outlet (diffuser & grille) for hvac duct work in Second floor accordding to the attached sketch. | MECH |  |  | 2nd | 43844 | 43849 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0624 | Check installation of flexible connection for fire fighting pipes at fifth floor accordding to the attached sketch. | MECH |  |  | 5th | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0625 | Check installation of flexible connection for fire fighting pipes at sixth floor accordding to the attached sketch. | MECH |  |  | 6th | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0626 | Check installation and test for water supply PPR pipes 75mm under ground filling line from first basement Zone(6) to pump room water feature N.o (1,2) for landscape accordding to the attached sketch. | MECH |  |  | ML | 43844 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0627 | Check installation and test for ref pipes at ninth floor accordding to the attached sketch. | MECH |  |  | 9th | 43845 | 43857 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0628 | Check installation and test for split unit and fan coil unit condensat drain for ninth floor accordding to the attached sketch. | MECH |  |  | 9th | 43850 | 43852 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0629 | Check hydraulic test for fire fighting network (Main line+Branches) at Fourth floor AT ZONE (1,2,3A). | MECH |  |  | 4th | 43850 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0630 | Check installation and test for funnel floor drain for drainge pipe at HVAC room for building from ground floor to sixth floor Zone(1,3A,3B,5) accordding to the attached sketch. | MECH |  |  | ML | 43851 | 43853 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0631 | Check installation for GARBAGE CHUTE RISERS at zone (2,4) accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | ML | 43851 | 43853 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0632 | Check installation of flexible connection for fire fighting pipes at first basement accordding to the attached sketch. | MECH |  |  | B1 | 43851 | 43853 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0633 | check intsatllation for pendant sprinklers at second floor z(1,2,3A) accordding to the attached sketch. | MECH |  |  | 2nd | 43851 | 43853 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0634 | Check haydraulic test for GARBAGE CHUTE RISERS at zone (2,4) accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | ML | 43852 | 43857 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0635 | Check Flushing for GARBAGE CHUTE RISERS at zone (2,4) accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | ML | 43856 | 43860 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0636 | check intsatllation for upright sprinklers at third floor for zone(1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 3rd | 43856 | 43860 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0637 | Check flushing for the firefighting (main + branches) at fourth floor at zone(4,5,3B) accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 4th | 43857 | 43860 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0638 | Check flushing for the firefighting (main + branches) at Seventh floor at zone(4,3B) accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 7th | 43857 | 43860 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0639 | Check flushing for the firefighting (main + branches) at Eighth floor at zone(4,3) accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 8th | 43857 | 43860 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0640 | Check installation and test for HDPE FM pipes H/L at first&Second basement (Zone6) accordding to the attached sketch. | MECH | Z6 | Z6 | ML | 43858 | 43864 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0641 | check intsatllation for upright sprinklers at Fourth floor for zone(4,5,3B) accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 4th | 43859 | 43863 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0642 | Check flushing for the firefighting (main + branches) at fourth floor at zone(1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 4th | 43863 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0643 | check intsatllation for upright sprinklers at seventh floor for zone(3B,4) accordding to the attached sketch. | MECH | Z3B,4 | Z3B,4 | 7th | 43863 | 43872 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0644 | check intsatllation for upright sprinklers at eighth floor for zone(3B,4) accordding to the attached sketch. | MECH | Z3B,4 | Z3B,4 | 8th | 43863 | 43872 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0645 | Check installation UPVC pipes from water features chalal No(2) plan(1) to pump room NO.1 for landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43863 | 43872 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0646 | Check instlation and test for Roof drain UPVC ST pipes at roof at second floor for area zone(1,2,3) accordding to the attached sketch. | MECH | Z1,2,3 | Z1,2,3 | 2nd | 43863 | 43866 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0647 | Check instllation of hookup(chilled water pipes)for air handling unit in second floor for IC-2F-AHU-01 & IC-2F-AHU-02 & IC-2F-AHU-03 & IC-2F-AHU-04 & IC-2F-AHU-05 and IC-2F-AHU-06 accordding to the attached sketch. | MECH |  |  | 2nd | 43864 | 43867 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0648 | Check instllation of hookup(chilled water pipes)for air handling unit in third floor for IC-3F-AHU-01 & IC-3F-AHU-02 & IC-3F-AHU-03 & IC-3F-AHU-04 & IC-3F-AHU-05 and IC-3F-AHU-06 accordding to the attached sketch. | MECH |  |  | 3rd | 43864 | 43867 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0649 | Check instllation of hookup(chilled water pipes)for air handling unit in fourth floor for IC-4F-AHU-01 & IC-4F-AHU-02 & IC-4F-AHU-03 & IC-4F-AHU-04 & IC-4F-AHU-05 and IC-4F-AHU-06 accordding to the attached sketch. | MECH |  |  | 4th | 43864 | 43867 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0650 | Check instllation of hookup(chilled water pipes)for air handling unit in fifth floor for IC-5F-AHU-01 & IC-5F-AHU-02 & IC-5F-AHU-03 & IC-5F-AHU-04 & IC-5F-AHU-05 and IC-5F-AHU-06 accordding to the attached sketch. | MECH |  |  | 5th | 43864 | 43867 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0651 | Check instllation of hookup(chilled water pipes)for air handling unit in sixth floor for IC-6F-AHU-01 & IC-6F-AHU-02 & IC-6F-AHU-03 and IC-6F-AHU-04 accordding to the attached sketch. | MECH |  |  | 6th | 43864 | 43867 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0652 | Check installation of chilled water pipes in ETS room for first basement accordding to the attached sketch. . | MECH |  |  | B1 | 43864 | 43867 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0653 | Check flushing for the firefighting (main + branches) at seventh floor for zone(2,3A) accordding to the attached sketch. | MECH | Z2,3A | Z2,3A | 7th | 43864 | 43867 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0654 | Check installation of flexible connection for fire fighting pipes at ground floor accordding to the attached sketch. | MECH |  |  | GF | 43864 | 43867 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0655 | Check instllation of hookup(chilled water pipes)for air handling unit in first floor for IC-1F-AHU-01 & IC-1F-AHU-02 & IC-1F-AHU-03 & IC-1F-AHU-04 & IC-1F-AHU-05 and IC-1F-AHU-06 accordding to the attached sketch. | MECH |  |  | 1st | 43864 | 43867 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0656 | Check mockup of motorized fire smoke damper connected to black steel riser in first floor accordding to the attached sketch. | MECH |  |  | 1st | 43864 | 43867 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0657 | Check installation and test for water supply PPR pipe H/L at roof floor zone(1&5) accordding to the attached sketch. | MECH | Z1,5 | Z1,5 | RF | 43866 | 43872 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0658 | Check installation and test for drainge riser stack UPVC (VP) pipes from B1 to 8th floor at zone (2&4) accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | ML | 43866 | 43872 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0659 | Check installation of internal insulation for HVAC duct work in seventh floor for IC-RF-AHU-04 to the attached sketch. | MECH |  |  | 7th | 43871 | 43877 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0660 | Check installation of internal insulation for HVAC duct work in sixth floor for IC-6F-AHU-01&IC-6F-AHU-02 to the attached sketch. | MECH |  |  | 6th | 43871 | 43877 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0661 | Check installation of External insulation for HVAC duct work in Ground floor for IC-GF-AHU-04&IC-GF-AHU-05&IC-GF-AHU-06 to the attached sketch. | MECH |  |  | GF | 43871 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0662 | Check installation of External insulation for HVAC duct work in Seventh floor for IC-RF-AHU-04&IC-8F-AHU-02 to the attached sketch. | MECH |  |  | 7th | 43871 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0663 | Check installation of External insulation for HVAC duct work in Eighth floor for IC-RF-AHU-05 to the attached sketch. | MECH |  |  | 8th | 43871 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0664 | Check installation of External insulation for HVAC duct work in Ninth floor for IC-9F-AHU-06 to roof floor to the attached sketch. | MECH |  |  | 9th | 43871 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0665 | Check installation of External insulation for HVAC duct work in Ground floor for IC-GF-AHU-01&IC-GF-AHU-02&IC-GF-AHU-03 to roof floor to the attached sketch. | MECH | Z4,5 | Z4,5 | GF | 43871 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0666 | check insallation mockup for sumpirsable pump for drainge by sumbit for second basement at zone(3) to the attached sketch. | MECH | Z3 | Z3 | B2 | 43871 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0667 | Check installation of sleeves & Transfer Duct for HVAC Duct Work in ninth Floor to attached sketch . | MECH |  |  | 9th | 43872 | 43874 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0668 | Check installation of vav unit for HVAC duct work in ninth floor to attached sketch . | MECH |  |  | 9th | 43872 | 43874 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0669 | Check installation of Volume damper for hvac duct work in ninth floor accordding to the attached sketch. | MECH |  |  | 9th | 43872 | 43874 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0670 | Check of installation of fire damper for hvac duct work in ninth floor accordding to the attached sketch. | MECH |  |  | 9th | 43872 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0671 | Check installation for EXHAUST HVAC duct work in ninth floor for IC-RF-EF-01 & IC-RF-EF-02 accordding to the attached sketch. | MECH |  |  | 9th | 43872 | 43874 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0672 | Check installation of motorized Volume damper for hvac duct work in ninth floor accordding to the attached sketch. | MECH |  |  | 9th | 43872 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0673 | Check installation of motorized fire smoke damper for hvac duct work in ninth floor accordding to the attached sketch. | MECH |  |  | 9th | 43872 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0674 | Check installation of plenum linear slot for hvac duct work in ninth floor accordding to the attached sketch. | MECH |  |  | 9th | 43872 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0675 | Check installation of air outlet (diffuser & grille) for hvac duct work in Third floor accordding to the attached sketch. | MECH |  |  | 3rd | 43872 | 43877 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0676 | Check installation Plumbing fixture for the toilet detail (TD 8,9,11,12) at Second floor Zone(1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43872 | 43880 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0677 | Check installation of plenum linear slot for hvac duct work in ground floor accordding to the attached sketch. | MECH |  |  | GF | 43873 | 43877 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0678 | Check installation of sleeves & Transfer Duct for HVAC Duct Work in seventh Floor to attached sketch . | MECH |  |  | 7th | 43873 | 43877 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0679 | Check installation of sleeves & Transfer Duct for HVAC Duct Work in Eighth Floor to attached sketch . | MECH |  |  | 8th | 43873 | 43877 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0680 | Check installation of vav unit for HVAC duct work in Eighth floor to attached sketch . | MECH |  |  | 8th | 43873 | 43877 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0681 | Check installation of Volume damper for hvac duct work in sixth floor accordding to the attached sketch. | MECH |  |  | 6th | 43873 | 43877 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0682 | Check installation of Volume damper for hvac duct work in seventh floor accordding to the attached sketch. | MECH |  |  | 7th | 43873 | 43877 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0683 | Check installation of Volume damper for hvac duct work in Eighth floor accordding to the attached sketch. | MECH |  |  | 8th | 43873 | 43877 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0684 | Check of installation of fire damper for hvac duct work in ground floor accordding to the attached sketch. | MECH |  |  | GF | 43873 | 43877 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0685 | Check of installation of fire damper for hvac duct work in fourth floor accordding to the attached sketch. | MECH |  |  | 4th | 43873 | 43877 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0686 | Check of installation of fire damper for hvac duct work in fifth floor accordding to the attached sketch. | MECH |  |  | 5th | 43873 | 43877 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0687 | Check installation insulation for Fiber Glass water supply(hot water) (PPR) pipes H/L at Ninth floor zone(3) accordding to the attached sketch. | MECH | Z3 | Z3 | 9th | 43873 | 43880 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0688 | Check installation insulation for Fiber Glass Drainge UPVC storm pipes H/L at Ninth floor zone(3) accordding to the attached sketch. | MECH | Z3 | Z3 | 9th | 43873 | 43880 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0689 | check insallation for combonant valve champer for drainge force main by sumpit for second basement at zone(1,2,3,4,5,6) to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B2 | 43873 | 43880 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0690 | Check of installation of fire damper for hvac duct work in sixth floor accordding to the attached sketch. | MECH |  |  | 6th | 43874 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0691 | Check of installation of fire damper for hvac duct work in seventh floor accordding to the attached sketch. | MECH |  |  | 7th | 43874 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0692 | Check of installation of fire damper for hvac duct work in Eighth floor accordding to the attached sketch. | MECH |  |  | 8th | 43874 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0693 | Check installation of internal insulation for HVAC duct work in first floor for IC-1F-AHU-01&IC-1F-AHU-02 and IC-1F-AHU-03 inside AHU room accordding to the attached sketch. | MECH |  |  | 1st | 43874 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0694 | Check installation of internal insulation for HVAC duct work in second floor for IC-2F-AHU-01&IC-2F-AHU-02 and IC-2F-AHU-03 inside AHU room accordding to the attached sketch. | MECH |  |  | 2nd | 43874 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0695 | Check installation of internal insulation for HVAC duct work in third floor for IC-3F-AHU-01& IC-3F-AHU-02 and IC-3F-AHU-03 inside AHU room accordding to the attached sketch. | MECH |  |  | 3rd | 43874 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0696 | Check installation of internal insulation for HVAC duct work in fourth floor for IC-4F-AHU-01& IC-4F-AHU-02 and IC-4F-AHU-03 inside AHU room accordding to the attached sketch. | MECH |  |  | 4th | 43874 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0697 | Check installation of internal insulation for HVAC duct work in first floor for IC-1F-AHU-04 & IC-1F-AHU-05 and IC-1F-AHU-06 inside AHU room accordding to the attached sketch. | MECH |  |  | 1st | 43874 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0698 | Check installation of internal insulation for HVAC duct work in second floor for IC-2F-AHU-04 & IC-2F-AHU-05 and IC-2F-AHU-06 inside AHU room accordding to the attached sketch. | MECH |  |  | 2nd | 43874 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0699 | Check installation of internal insulation for HVAC duct work in third floor for IC-3F-AHU-04 & IC-3F-AHU-05 and IC-3F-AHU-06 inside AHU room accordding to the attached sketch. | MECH |  |  | 3rd | 43874 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0700 | Check installation of internal insulation for HVAC duct work in fourth floor for IC-4F-AHU-04 & IC-4F-AHU-05 and IC-4F-AHU-06 inside AHU room accordding to the attached sketch. | MECH |  |  | 4th | 43874 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0701 | check intsatllation for upright sprinklers at fourth floor for zone(1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 4th | 43874 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0702 | check intsatllation for upright sprinklers at seventh floor for zone(2,3A) accordding to the attached sketch. | MECH | Z2,3A | Z2,3A | 7th | 43874 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0703 | Check flushing for the firefighting zone (main + branches) at Sixth floor at zone(1.2.3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 6th | 43877 | 43880 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0704 | Check flushing for the firefighting zone (main + branches) at Eighth floor at zone(2) accordding to the attached sketch. | MECH | Z2 | Z2 | 8th | 43878 | 43880 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0705 | Check installation of flexible connection for fire fighting pipes at seventh floor accordding to the attached sketch. | MECH |  |  | 7th | 43878 | 43880 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0706 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part (3) for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43879 | 43885 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0707 | Check installation of motorized fire smoke damper for hvac duct work in first floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43880 | 43885 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0708 | Check installation of motorized fire smoke damper for hvac duct work in third floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43880 | 43885 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0709 | Check installation of air outlet (diffuser & grille) for hvac duct work in first floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43880 | 43887 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0710 | Check installation of plenum linear slot for hvac duct work in first floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43880 | 43885 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0711 | Check installation of plenum linear slot for hvac duct work in third floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43880 | 43885 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0712 | check intsatllation for upright sprinklers at sixth floor for zone(1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 6th | 43880 | 43885 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0713 | Check installation of flexible connection for fire fighting pipes at Ninth floor accordding to the attached sketch. | MECH | Z3 | Z3 | 9th | 43886 | 43892 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0714 | Check installation of flexible connection for fire fighting pipes at Eighth floor accordding to the attached sketch. | MECH | Z3 | Z3 | 8th | 43887 | 43893 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0715 | Check installation of plenum linear slot for hvac duct work in second floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43887 | 43894 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0716 | Check installation of motorized fire smoke damper for hvac duct work in second floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43887 | 43892 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0717 | Check installation of plenum linear slot for hvac duct work in fourth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43888 | 43894 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0718 | Check installation of plenum linear slot for hvac duct work in fifth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43888 | 43894 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0719 | Check installation of motorized fire smoke damper for hvac duct work in ground floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | GF | 43888 | 43892 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0720 | Check installation of motorized fire smoke damper for hvac duct work in fourth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43888 | 43892 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0721 | Check installation for hvac duct work of total fresh air riser for IC-6F-FAHU-01 from lower basement to sixth floor accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | ML | 43888 | 43894 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0722 | Check installation of External insulation for HVAC duct work of total fresh air riser for IC-6F-FAHU-01 from lower basement to sixth floor accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | ML | 43888 | 43894 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0723 | Check installation for hvac duct work of EXHAUST riser for IC-6F-EF-02 from ground to sixth floor accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | ML | 43888 | 43894 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0724 | Check installation for hvac duct work of pressurized riser at for IC-6F-PF-01 from higher basement to sixth floor accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | ML | 43888 | 43894 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0725 | Check the installation of HVAC sheet metal duct work for mechanical rooms (AHU rooms) at Second floor accordding to the attached approved drawing Zone(1,2,) . | MECH | Z1,2 | Z1,2 | 2nd | 43890 | 43892 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0726 | Check the installation of HVAC sheet metal duct work for mechanical rooms (AHU rooms) at First floor accordding to the attached approved drawing Zone(1,2) . | MECH | Z1,2 | Z1,2 | 1st | 43890 | 43892 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0727 | Check installation for EXHAUST HVAC duct work in fifth floor for IC-8F-EF-01 & IC-8F-EF-03 & IC-8F-EF-08 . | MECH | Z3B,4,5 | Z3B,4,5 | 5th | 43890 | 43895 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0728 | Check installation for EXHAUST HVAC duct work in Eighth floor for IC-RF-EF-02 accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 8th | 43890 | 43895 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0729 | Check installation for EXHAUST HVAC duct work in seventh floor for IC-8F-EF-09 & IC-8F-EF-07 & IC-8F-EF-06 and IC-8F-EF-04 accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 7th | 43890 | 43895 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0730 | Check installation for water supply isolating valve and water hammer excluid (PRV) at B1 & B2 and Ninth floor at Zone (1,2,3,4,5,6) accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | ML | 43891 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0731 | Check installation Plumbing fixture for the toilet detail (TD 8,9,11,12) at First and Third floor Zone(1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 43891 | 43895 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0732 | Check installation insulation for Fiber Glass water supply(hot water) (PPR) pipes H/L at Ground & 1st & 2nd &3rd & 4th and 5th floor TD (11) zone (2,4) accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | ML | 43891 | 43893 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0733 | check installation of fire hose cabinet at B1 accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43891 | 43893 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0734 | check installation of fire hose cabinet at B2 accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | B2 | 43891 | 43893 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0735 | check intsatllation for pendant sprinklers at First floor z(4,5,3B) accordding to the attached sketch. | MECH | Z4,5,3B | Z4,5,3B | 1st | 43893 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0736 | Check installation for hvac duct work of smoke riser (black steel) for IC-RF-SF-01 from ground to ninth floor accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | ML | 43893 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0737 | Check installation for hvac duct work of EXHAUST riser for IC-8F-EF-01 from first basement to seventh floor accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | ML | 43893 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0738 | Check installation for hvac duct work of EXHAUST riser for IC-8F-EF-02 from ground to seventh floor accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | ML | 43893 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0739 | Check installation for hvac duct work of EXHAUST riser for IC-8F-EF-03 from fisrt basement to seventh floor accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | ML | 43893 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0740 | Check installation of internal insulation for HVAC duct work in fifth floor for IC-5F-AHU-04 & IC-5F-AHU-05 and IC-5F-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 5th | 43894 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0741 | Check installation of internal insulation for HVAC duct work in sixth floor for IC-6F-AHU-03 & IC-6F-AHU-04 inside AHU room accordding to the attached sketch. | MECH | Z2 | Z2 | 6th | 43894 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0742 | Check installation of internal insulation for HVAC duct work in fifth floor for IC-5F-AHU-01 & IC-5F-AHU-02 and IC-5F-AHU-03 inside AHU room accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 5th | 43894 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0743 | Check installation of internal insulation for HVAC duct work in sixth floor for IC-6F-AHU-01 & IC-6F-AHU-02 inside AHU room accordding to the attached sketch. | MECH | Z4 | Z4 | 6th | 43894 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0744 | Check installation for HVAC Galvanize sheet metal duct work for mechanical room (AHU room) at first floor for IC-1F-AHU-01 & IC-1F-AHU-02 and IC-1F-AHU-03 accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 1st | 43895 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0745 | Check installation for HVAC Galvanize sheet metal duct work for mechanical room (AHU room) at second floor for IC-2F-AHU-01 & IC-2F-AHU-02 and IC-2F-AHU-03 accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 2nd | 43895 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0746 | Check installation for HVAC Galvanize sheet metal duct work for mechanical room (AHU room) at third floor for IC-3F-AHU-01 & IC-3F-AHU-02 and IC-3F-AHU-03 accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 3rd | 43895 | 43904 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0747 | Check installation for HVAC Galvanize sheet metal duct work for mechanical room (AHU room) at third floor for IC-3F-AHU-04 & IC-3F-AHU-05 and IC-3F-AHU-06 accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 3rd | 43895 | 43904 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0748 | Check installation for HVAC Galvanize sheet metal duct work for mechanical room (AHU room) at fourth floor for IC-4F-AHU-01 & IC-4F-AHU-02 and IC-4F-AHU-03 accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 4th | 43895 | 43904 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0749 | Check installation for HVAC Galvanize sheet metal duct work for mechanical room (AHU room) at fourth floor for IC-4F-AHU-04 & IC-4F-AHU-05 and IC-4F-AHU-06 accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 4th | 43895 | 43904 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0750 | Check installation for HVAC Galvanize sheet metal duct work for mechanical room (AHU room) at fifth floor for IC-5F-AHU-01 & IC-5F-AHU-02 and IC-5F-AHU-03 accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 5th | 43895 | 43904 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0751 | Check installation for HVAC Galvanize sheet metal duct work for mechanical room (AHU room) at fifth floor for IC-5F-AHU-04 & IC-5F-AHU-05 and IC-5F-AHU-06 accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 5th | 43895 | 43904 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0752 | Check installation for HVAC Galvanize sheet metal duct work for mechanical room (AHU room) at sixth floor for IC-6F-AHU-01 and IC-6F-AHU-02 accordding to the attached sketch. | MECH | Z4 | Z4 | 6th | 43895 | 43904 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0753 | Check installation for HVAC Galvanize sheet metal duct work for mechanical room (AHU room) at sixth floor for IC-6F-AHU-03 and IC-6F-AHU-04 accordding to the attached sketch. | MECH | Z2 | Z2 | 6th | 43895 | 43904 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0754 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at first floor for IC-1F-AHU-01 & IC-1F-AHU-02 and IC-1F-AHU-03 accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 1st | 43895 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0755 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at first floor for IC-1F-AHU-04 & IC-1F-AHU-05 and IC-1F-AHU-06 accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 1st | 43895 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0756 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at second floor for IC-2F-AHU-01 & IC-2F-AHU-02 and IC-2F-AHU-03 accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 2nd | 43895 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0757 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at second floor for IC-2F-AHU-04 & IC-2F-AHU-05 and IC-2F-AHU-06 accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 2nd | 43895 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0758 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at third floor for IC-3F-AHU-01 & IC-3F-AHU-02 and IC-3F-AHU-03 accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 3rd | 43895 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0759 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at third floor for IC-3F-AHU-04 & IC-3F-AHU-05 and IC-3F-AHU-06 accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 3rd | 43895 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0760 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at fourth floor for IC-4F-AHU-01 & IC-4F-AHU-02 and IC-4F-AHU-03 accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 4th | 43895 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0761 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at fourth floor for IC-4F-AHU-04 & IC-4F-AHU-05 and IC-4F-AHU-06 accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 4th | 43895 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0762 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at fifth floor for IC-5F-AHU-01 & IC-5F-AHU-02 and IC-5F-AHU-03 accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 5th | 43895 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0763 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at fifth floor for IC-5F-AHU-04 & IC-5F-AHU-05 and IC-5F-AHU-06 accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 5th | 43895 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0764 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at sixth floor for IC-6F-AHU-01 and IC-6F-AHU-02 accordding to the attached sketch. | MECH | Z4 | Z4 | 6th | 43895 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0765 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at sixth floor for IC-6F-AHU-03 and IC-6F-AHU-04 accordding to the attached sketch. | MECH | Z2 | Z2 | 6th | 43895 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0766 | Check installation for internal insulation for fan coil unit for HVAC duct work in First basement (B1) accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B1 | 43895 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0767 | Check installation for internal insulation for fan coil unit for HVAC duct work in Second basement (B2) accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B2 | 43895 | 43899 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0768 | Check installation for thrust support for fire fighting pipes at fourth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43895 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0769 | check intsatllation for upright and pendant sprinklers at first floor for zone(1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 1st | 43898 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0770 | Check installation of External insulation for HVAC duct work in first floor for IC-1F-AHU-04 & IC-1F-AHU-05 and IC-1F-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 1st | 43899 | 43904 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0771 | Check installation of External insulation for HVAC duct work in second floor for IC-2F-AHU-04 & IC-2F-AHU-05 and IC-2F-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 2nd | 43899 | 43904 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0772 | check intsatllation for pendant sprinklers at fourth floor for zone(3B,4,5) accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 4th | 43899 | 43901 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0773 | check intsatllation for upright sprinklers at first basement for zone(1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | B1 | 43899 | 43901 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0774 | Check flushing for the firefighting zone (main + branches) at sixth floor at zone(4,5,3B) accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 6th | 43900 | 43904 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0775 | Check installation of air outlet (diffuser & grille) for hvac duct work in Fourth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43901 | 43908 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0776 | Check installation and test for drainge pantry UPVC (WP&VP) pipes from 7th to 9th floor accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | ML | 43901 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0777 | Check installation and test for water supply pantry PPR pipes from 7th to 9th floor accordding to the attached sketch. (Zone3B) | MECH | Z3B | Z3B | ML | 43901 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0778 | Check test of vertical pipes for chilled water risers in zone1 accordding to the attached sketch. | MECH |  |  | ML | 43901 | 43906 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0779 | Check installation for hvac duct work of pressurized riser at for IC-9F-PF-01 from higher basement to Ninth floor accordding to the attached sketch. | MECH |  |  | ML | 43906 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0780 | Check installation for hvac duct work of pressurized riser at for IC-7F-PF-01 from higher basement to Seventh floor accordding to the attached sketch. | MECH |  |  | ML | 43906 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0781 | Check installation for hvac duct work of pressurized riser at for IC-UR-PF-01 from higher basement to Upper Roof accordding to the attached sketch. | MECH |  |  | ML | 43906 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0782 | Check installation for hvac duct work of total fresh air riser for IC-8F-FAHU-01 from Ground floor to Eighth floor accordding to the attached sketch. | MECH |  |  | ML | 43906 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0783 | Check installation for hvac duct work of smoke riser (black steel) for IC-6F-SF-01 from ground to Sixth floor accordding to the attached sketch. | MECH |  |  | ML | 43906 | 43911 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0784 | Check installation of internal insulation for HVAC duct work in ground floor for IC-GF-AHU-04 & IC-GF-AHU-05 and IC-GF-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | GF | 43908 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0785 | Check installation for HVAC Galvanize sheet metal duct work for mechanical room (AHU room) at ground floor for IC-GF-AHU-04 & IC-GF-AHU-05 and IC-GF-AHU-06 accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | GF | 43908 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0786 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part (2,3) for Landscape accordding to the attached sketch. | MECH | L.S | L.S | EX | 43911 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0787 | Check installation for fire fighting network (Branches) at Ground floor AT ZONE (1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | GF | 43912 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0788 | check intsatllation for pendant sprinklers at Third floor for zone(3B,4,5) accordding to the attached sketch. | MECH | Z4,5,3B | Z4,5,3B | 3rd | 43912 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0789 | check installation of Electrical fire pumb and diesel fire pumb at B2 for area(4) accordding to the attached sketch. | MECH | Z4 | Z4 | B2 | 43913 | 43915 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0790 | check intsatllation for window type sprinklers at first floor for VIP enterance zone(3) accordding to the attached sketch. | MECH | Z3 | Z3 | 1st | 43925 | 43930 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0791 | check installation for split units from Ground to Ninth Floor (indoor unit) accordding to the attached sketch. | MECH |  |  | ML | 43926 | 43930 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0792 | Check installation for crack units (indoor) CRAC 01&02 for main telecom room at ground floor at Zone (1&5) accordding to the attached sketch. | MECH | Z1,5 | Z1,5 | GF | 43928 | 43936 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0793 | Check installation for crack units (outdoor) CRAC 02 for main telecom room at sixth floor at Zone (5) accordding to the attached sketch. | MECH | Z5 | Z5 | 6th | 43929 | 43936 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0794 | Pls Check the release for mechanical trades above false ceilling at the first floor according to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43932 | 43934 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0795 | Pls Check the release for mechanical trades above false ceilling at the Second floor according to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43932 | 43934 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0796 | Pls Check the release for mechanical trades above false ceilling at the Third floor according to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43932 | 43934 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0797 | Check instllation of chilled water network for air handling unit room in first floor for IC-1F-AHU-01 & IC-1F-AHU-02 & IC-1F-AHU-03 & IC-1F-AHU-04 & IC-1F-AHU-05 and IC-1F-AHU-06 accordding to the attached sketch. | MECH | Z1,2,4,5 | Z1,2,4,5 | 1st | 43933 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0798 | Check instllation of chilled water network for air handling unit room in second floor for IC-2F-AHU-01 & IC-2F-AHU-02 & IC-2F-AHU-03 & IC-2F-AHU-04 & IC-2F-AHU-05 and IC-2F-AHU-06 accordding to the attached sketch. | MECH | Z1,2,4,5 | Z1,2,4,5 | 2nd | 43933 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0799 | Check instllation of chilled water network for air handling unit room in third floor for IC-3F-AHU-01 & IC-3F-AHU-02 & IC-3F-AHU-03 & IC-3F-AHU-04 & IC-3F-AHU-05 and IC-3F-AHU-06 accordding to the attached sketch. | MECH | Z1,2,4,5 | Z1,2,4,5 | 3rd | 43933 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0800 | Check instllation of chilled water network for air handling unit room in fourth floor for IC-4F-AHU-01 & IC-4F-AHU-02 & IC-4F-AHU-03 & IC-4F-AHU-04 & IC-4F-AHU-05 and IC-4F-AHU-06 accordding to the attached sketch. | MECH | Z1,2,4,5 | Z1,2,4,5 | 4th | 43933 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0801 | Check instllation of chilled water network for air handling unit room in fifth floor for IC-5F-AHU-01 & IC-5F-AHU-02 & IC-5F-AHU-03 & IC-5F-AHU-04 & IC-5F-AHU-05 and IC-5F-AHU-06 accordding to the attached sketch. | MECH | Z1,2,4,5 | Z1,2,4,5 | 5th | 43933 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0802 | Check instllation of chilled water network for air handling unit room in sixth floor for IC-6F-AHU-01 & IC-6F-AHU-02 & IC-6F-AHU-03 and IC-6F-AHU-04 accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | 6th | 43933 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0803 | Check installation of External insulation for HVAC duct work in third floor for IC-3F-AHU-04 & IC-3F-AHU-05 and IC-3F-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 3rd | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0804 | Check installation of External insulation for HVAC duct work in fourth floor for IC-4F-AHU-04 & IC-4F-AHU-05 and IC-4F-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 4th | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0805 | Check installation of External insulation for HVAC duct work in fifth floor for IC-5F-AHU-04 & IC-5F-AHU-05 and IC-5F-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 5th | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0806 | Check installation of External insulation for HVAC duct work in sixth floor for IC-6F-AHU-03 and IC-6F-AHU-04 inside AHU room accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | 6th | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0807 | Check installation of External insulation for HVAC duct work in first floor for IC-1F-AHU-01 & IC-1F-AHU-02 and IC-1F-AHU-03 inside AHU room accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 1st | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0808 | Check installation of External insulation for HVAC duct work in second floor for IC-2F-AHU-01 & IC-2F-AHU-02 and IC-2F-AHU-03 inside AHU room accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 2nd | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0809 | Check installation of External insulation for HVAC duct work in third floor for IC-3F-AHU-01 & IC-3F-AHU-02 and IC-3F-AHU-03 inside AHU room accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 3rd | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0810 | Check installation of External insulation for HVAC duct work in fourth floor for IC-4F-AHU-01 & IC-4F-AHU-02 and IC-4F-AHU-03 inside AHU room accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 4th | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0811 | Check installation of External insulation for HVAC duct work in fifth floor for IC-5F-AHU-01 & IC-5F-AHU-02 and IC-5F-AHU-03 inside AHU room accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 5th | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0812 | Check installation of External insulation for HVAC duct work in sixth floor for IC-6F-AHU-01 and IC-6F-AHU-02 inside AHU room accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | 6th | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0813 | Check installation of car park fresh fans in upper basement | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43934 | 43943 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0814 | Check installation of car park fresh fans in lower basement | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | B2 | 43934 | 43943 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0815 | Check installation of car park Exhaust fans in upper basement | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43934 | 43943 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0816 | Check installation of car park Exhaust fans in lower basement | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | B2 | 43934 | 43943 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0817 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes part (1) for Landscape accordding to the attached sketch. | MECH | part1 | part1 | EX | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0818 | Check installation Plumbing fixture for the toilet detail (TD 8,9,11,12) at Fourth and Fifth floor Zone(1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0819 | Check installation insulation for Fiber Glass water supply(hot water) (PPR) pipes H/L at 6th & 7th& 8th and 9th floor TD (1,2,10) zone (2,3,4) accordding to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | ML | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0820 | Check installation pumps and filters without conniction for pump room water feature No (1,2) for landscape accordding to the attached sketch. | MECH |  |  | EX | 43934 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0821 | Check installation of internal insulation for HVAC duct work in ground floor for IC-GF-AHU-01 & IC-GF-AHU-02 and IC-GF-AHU-03 inside AHU room accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | GF | 43935 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0822 | Check installation for HVAC Galvanize sheet metal duct work for mechanical room (AHU room) at ground floor for IC-GF-AHU-01 & IC-GF-AHU-02 and IC-GF-AHU-03 accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | GF | 43935 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0823 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at ground floor for IC-GF-AHU-04 & IC-GF-AHU-05 and IC-GF-AHU-06 accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | GF | 43935 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0824 | Check installation of damper (volume & motorized volume & fire & motorized fire smoke) for HVAC duct work for mechanical room (AHU room) at ground floor for IC-GF-AHU-01 & IC-GF-AHU-02 and IC-GF-AHU-03 accordding to the attached sketch. | MECH | Z4,5 | Z4,5 | GF | 43935 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0825 | Check installation for black steel duct work in fifth floor for IC-8F-EF-02 and IC-8F-EF-05 (in pantry) | MECH | Z2,4 | Z2,4 | 5th | 43935 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0826 | Check installation for black steel duct work in sixth floor for IC-8F-EF-02 and IC-8F-EF-05 (in pantry) | MECH | Z2,4 | Z2,4 | 6th | 43935 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0827 | Check installation for black steel duct work in seventh floor for IC-8F-EF-02 and IC-8F-EF-05 (in pantry) | MECH | Z2,4 | Z2,4 | 7th | 43935 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0828 | Check installation of external insulation in pantry for black steel with rook wool in fifth Floor for IC-8F-EF-02 & IC-8F-EF-05 . | MECH | Z2,4 | Z2,4 | 5th | 43935 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0829 | Check installation of external insulation in pantry for black steel with rook wool in sixth Floor for IC-8F-EF-02 & IC-8F-EF-05 . | MECH | Z2,4 | Z2,4 | 6th | 43935 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0830 | Check installation of external insulation in pantry for black steel with rook wool in seventh Floor for IC-8F-EF-02 & IC-8F-EF-05 . | MECH | Z2,4 | Z2,4 | 7th | 43935 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0831 | Pls Check the release for mechanical trades above false ceilling at the Fourth floor for zone(1) according to the attached sketch. | MECH | Z1 | Z1 | 4th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0832 | Pls Check the release for mechanical trades above false ceilling at the Fourth floor for zone(2) according to the attached sketch. | MECH | Z2 | Z2 | 4th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0833 | Pls Check the release for mechanical trades above false ceilling at the Fourth floor for zone(3A) according to the attached sketch. | MECH | Z3A | Z3A | 4th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0834 | Pls Check the release for mechanical trades above false ceilling at the Fourth floor for zone(3B) according to the attached sketch. | MECH | Z3B | Z3B | 4th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0835 | Pls Check the release for mechanical trades above false ceilling at the Fourth floor for zone(4) according to the attached sketch. | MECH | Z4 | Z4 | 4th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0836 | Pls Check the release for mechanical trades above false ceilling at the Fourth floor for zone(5) according to the attached sketch. | MECH | Z5 | Z5 | 4th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0837 | Pls Check the release for mechanical trades above false ceilling at the Fifth floor for zone(1) according to the attached sketch. | MECH | Z1 | Z1 | 5th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0838 | Pls Check the release for mechanical trades above false ceilling at the Fifth floor for zone(2) according to the attached sketch. | MECH | Z2 | Z2 | 5th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0839 | Pls Check the release for mechanical trades above false ceilling at the Fifth floor for zone(3A) according to the attached sketch. | MECH | Z3A | Z3A | 5th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0840 | Pls Check the release for mechanical trades above false ceilling at the Fifth floor for zone(3B) according to the attached sketch. | MECH | Z3B | Z3B | 5th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0841 | Pls Check the release for mechanical trades above false ceilling at the Fifth floor for zone(4) according to the attached sketch. | MECH | Z4 | Z4 | 5th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0842 | Pls Check the release for mechanical trades above false ceilling at the Fifth floor for zone(5) according to the attached sketch. | MECH | Z5 | Z5 | 5th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0843 | Check installation for thrust support for fire fighting pipes at Ground floor for area(1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | GF | 43936 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0844 | Check installation for thrust support for fire fighting pipes at Ground floor for area(4,5,3B) accordding to the attached sketch. | MECH | Z4,5,3B | Z4,5,3B | GF | 43936 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0845 | Check installation of plenum linear slot for hvac duct work in sixth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 6th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0846 | Check installation of plenum linear slot for hvac duct work in seventh floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 7th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0847 | Check installation of plenum linear slot for hvac duct work in eighth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 8th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0848 | Check installation for EXHAUST HVAC duct work in fifth floor for IC-8F-EF-04 & IC-8F-EF-06 & IC-8F-EF-09 . | MECH | Z1,2,3A | Z1,2,3A | 5th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0849 | Check installation for EXHAUST HVAC duct work in sixth floor for IC-8F-EF-04 & IC-8F-EF-06 & IC-8F-EF-09 . | MECH | Z2,3A | Z2,3A | 6th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0850 | Check installation for EXHAUST HVAC duct work in sixth floor for IC-8F-EF-01 & IC-8F-EF-03 & IC-8F-EF-08 . | MECH | Z3B,4 | Z3B,4 | 6th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0851 | Check installation for EXHAUST HVAC duct work in seventh floor for IC-8F-EF-01 & IC-8F-EF-03 & IC-8F-EF-08 and IC-RF-EF-01 . | MECH | Z3B,4 | Z3B,4 | 7th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0852 | Check installation for EXHAUST HVAC duct work in eighth floor for IC-RF-EF-01 accordding to the attached sketch. | MECH | Z3B,4 | Z3B,4 | 8th | 43936 | 43943 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0853 | Check installation for EXHAUST HVAC duct work in eighth floor for IC-RF-EF-01 accordding to the attached sketch. | MECH | Z3B,4 | Z3B,4 | 8th | 43936 | 43949 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0854 | Check installation of motorized fire smoke damper for hvac duct work in fifth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43937 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0855 | Check installation of motorized fire smoke damper for hvac duct work in sixth floor accordding to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | 6th | 43937 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0856 | Check installation of motorized fire smoke damper for hvac duct work in seventh floor accordding to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | 7th | 43937 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0857 | Check installation of motorized fire smoke damper for hvac duct work in eighth floor accordding to the attached sketch. | MECH | Z3 | Z3 | 8th | 43937 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0858 | Check Installaion and test pipe location and Level For irrIgation network Pipes (sprinkler & dripping) part 2 (Z6) for Landscape accordding to the attached sketch. | MECH | Z6 | Z6 | EX | 43940 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0859 | check intsatllation for upright sprinklers at sixth floor for zone(3B,4,5) accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 6th | 43940 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0860 | Check installation of internal insulation for HVAC duct work in Eighth floor for IC-8F-AHU-02 and IC-8F-FAHU-02 accordding to the attached sketch. | MECH | Z4 | Z4 | 8th | 43942 | 43949 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0861 | Check installation of internal insulation for HVAC duct work in Eighth floor for IC-8F-AHU-01 and IC-8F-FAHU-01 accordding to the attached sketch. | MECH | Z2 | Z2 | 8th | 43942 | 43949 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0862 | Check installation for HVAC duct work in Eighth floor for IC-8F-AHU-02 and IC-8F-FAHU-02 accordding to the attached sketch. | MECH | Z4 | Z4 | 8th | 43942 | 43949 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0863 | Check installation for HVAC duct work in Eighth floor for IC-8F-AHU-01 and IC-8F-FAHU-01 accordding to the attached sketch. | MECH | Z2 | Z2 | 8th | 43942 | 43949 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0864 | check installation for drainge pipe vent cap 2"&3"&4" and 6" (SP&WP&ST&VP) stack riser for the roof at Eighth floor&Tenth floor Z(2,3,4) accordding to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | ML | 43944 | 43949 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0865 | Check installation of internal insulation for HVAC duct work in Sixth floor for IC-6F-FAHU-01 accordding to the attached sketch. | MECH |  |  | 6th | 43944 | 43949 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0866 | Check installation for HVAC duct work in sixth floor for IC-6F-FAHU-01 accordding to the attached sketch. | MECH |  |  | 6th | 43944 | 43949 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0867 | Check installation of internal insulation for HVAC duct work in Sixth floor for IC-6F-FAHU-02 accordding to the attached sketch. | MECH |  |  | 6th | 43944 | 43949 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0868 | Check installation for HVAC duct work in sixth floor for IC-6F-FAHU-02 accordding to the attached sketch. | MECH |  |  | 6th | 43944 | 43949 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0869 | check hydraulic test for carck unit ref pipes at Z5 from Ground floor to Six floor accordding to the attached sketch. | MECH | Z5 | Z5 | ML | 43947 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0870 | Check installation for fire fighting network (Branches) at Ground floor AT ZONE (3B,4,5) accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | GF | 43949 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0871 | Check installation of componant for AHU in ground floor for IC-GF-AHU-04 & IC-GF-AHU-05 and IC-GF-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | GF | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0872 | Check installation of componant for AHU in ground floor for IC-GF-AHU-01 & IC-GF-AHU-02 and IC-GF-AHU-03 inside AHU room accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | GF | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0873 | Check installation of componant for AHU in first floor for IC-1F-AHU-04 & IC-1F-AHU-05 and IC-1F-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 1st | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0874 | Check installation of componant for AHU in first floor for IC-1F-AHU-01 & IC-1F-AHU-02 and IC-1F-AHU-03 inside AHU room accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 1st | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0875 | Check installation of componant for AHU in second floor for IC-2F-AHU-04 & IC-2F-AHU-05 and IC-2F-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 2nd | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0876 | Check installation of componant for AHU in second floor for IC-2F-AHU-01 & IC-2F-AHU-02 and IC-2F-AHU-03 inside AHU room accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 2nd | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0877 | Check installation of componant for AHU in third floor for IC-3F-AHU-04 & IC-3F-AHU-05 and IC-3F-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 3rd | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0878 | Check installation of componant for AHU in third floor for IC-3F-AHU-01 & IC-3F-AHU-02 and IC-3F-AHU-03 inside AHU room accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 3rd | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0879 | Check installation of componant for AHU in fourth floor for IC-4F-AHU-04 & IC-4F-AHU-05 and IC-4F-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 4th | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0880 | Check installation of componant for AHU in fourth floor for IC-4F-AHU-01 & IC-4F-AHU-02 and IC-4F-AHU-03 inside AHU room accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 4th | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0881 | Check installation of componant for AHU in fifth floor for IC-5F-AHU-04 & IC-5F-AHU-05 and IC-5F-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 5th | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0882 | Check installation of componant for AHU in fifth floor for IC-5F-AHU-01 & IC-5F-AHU-02 and IC-5F-AHU-03 inside AHU room accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 5th | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0883 | Check installation of componant for AHU in sixth floor for IC-6F-AHU-03 and IC-6F-AHU-04 inside AHU room accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 6th | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0884 | Check installation of componant for AHU in sixth floor for IC-6F-AHU-01 and IC-6F-AHU-02 inside AHU room accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 6th | 43949 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0885 | Check installation of internal insulation of fresh fans with perforated sheet in upper basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B1 | 43950 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0886 | Check installation of internal insulation of exhaust fans with perforated sheet in upper basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B1 | 43950 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0887 | Check installation of air outlet (diffuser & grille) for hvac duct work in Fifth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43951 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0888 | Check instllation of chilled water network for air handling unit room in ground floor for IC-GF-AHU-01 & IC-GF-AHU-02 & IC-GF-AHU-03 & IC-GF-AHU-04 & IC-GF-AHU-05 and IC-GF-AHU-06 accordding to the attached sketch . | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | GF | 43951 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0889 | Check instllation of hookup(chilled water pipes)for air handling unit in Ground floor for IC-GF-AHU-01 & IC-GF-AHU-02 & IC-GF-AHU-03 & IC-GF-AHU-04 & IC-GF-AHU-05 and IC-GF-AHU-06 accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | GF | 43951 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0890 | check insallation for submersible pump for drainge by sumbit for second basement at zone(1&2&3&4&5&6) accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B2 | 43951 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0891 | Check test of vertical pipes for chilled water risers in zone 3A to attached sketch. | MECH | Z3A | Z3A | ML | 43951 | 43957 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0892 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH |  |  | ML | 43954 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0893 | Check installation for hvac duct work of EXHAUST riser for IC-RF-EF-01 from seventh floor to upper roof accordding to the attached sketch. | MECH | Z4 | Z4 | ML | 43954 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0894 | Check installation for hvac duct work of EXHAUST riser for IC-8F-EF-08 from first floor to Eighth floor accordding to the attached sketch. | MECH |  |  | ML | 43954 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0895 | Check installation for hvac duct work of EXHAUST riser for IC-8F-EF-07 from seventh floor to Eighth floor accordding to the attached sketch. | MECH |  |  | ML | 43954 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0896 | Check installation for hvac duct work of EXHAUST riser for IC-RF-EF-02 from seventh floor to roof floor accordding to the attached sketch. | MECH |  |  | ML | 43954 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0897 | Check installation for hvac duct work of EXHAUST riser for IC-8F-EF-05 from Ground floor to Eighth floor accordding to the attached sketch. | MECH |  |  | ML | 43954 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0898 | Check installation for hvac duct work of pressurized riser at for IC-9F-PF-02 from Second basement to Eighth floor accordding to the attached sketch. | MECH |  |  | ML | 43954 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0899 | Check installation for hvac duct work of pressurized riser at for IC-UF-PF-02 from Second basement to roof floor accordding to the attached sketch. | MECH |  |  | ML | 43954 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0900 | check installation for split units at First basement (indoor unit) accordding to the attached sketch. | MECH |  |  | B1 | 43955 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0901 | Pls Check the release for mechanical trades above false ceilling at the Ground floor for zone(1) according to the attached sketch. | MECH | Z1 | Z1 | GF | 43956 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0902 | Pls Check the release for mechanical trades above false ceilling at the Ground floor for zone(2) according to the attached sketch. | MECH | Z2 | Z2 | GF | 43956 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0903 | Pls Check the release for mechanical trades above false ceilling at the Ground floor for zone(3A) according to the attached sketch. | MECH | Z3A | Z3A | GF | 43956 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0904 | Pls Check the release for mechanical trades above false ceilling at the Ground floor for zone(3B) according to the attached sketch. | MECH | Z3B | Z3B | GF | 43956 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0905 | Pls Check the release for mechanical trades above false ceilling at the Ground floor for zone(4) according to the attached sketch. | MECH | Z4 | Z4 | GF | 43956 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0906 | Pls Check the release for mechanical trades above false ceilling at the Ground floor for zone(5) according to the attached sketch. | MECH | Z5 | Z5 | GF | 43956 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0907 | Check installation for cladding of duct work inside mechanical room (AHU room) at First floor for IC-1F-AHU-04 & IC-1F-AHU-05 and IC-1F-AHU-06 accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 1st | 43957 | 43968 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0908 | Check installation for cladding of duct work inside mechanical room (AHU room) at Second floor for IC-2F-AHU-04 & IC-2F-AHU-05 and IC-2F-AHU-06 accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 2nd | 43957 | 43968 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0909 | Check installation for cladding of duct work inside mechanical room (AHU room) at Third floor for IC-3F-AHU-04 & IC-3F-AHU-05 and IC-3F-AHU-06 accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 3rd | 43957 | 43968 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0910 | Pls Check the release for mechanical trades above false ceilling at the Sixth floor for zone(2) according to the attached sketch. | MECH | Z2 | Z2 | 6th | 43958 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0911 | Pls Check the release for mechanical trades above false ceilling at the Sixth floor for zone(3A) according to the attached sketch. | MECH | Z3A | Z3A | 6th | 43958 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0912 | Pls Check the release for mechanical trades above false ceilling at the Sixth floor for zone(3B) according to the attached sketch. | MECH | Z3B | Z3B | 6th | 43958 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0913 | Pls Check the release for mechanical trades above false ceilling at the Sixth floor for zone(4) according to the attached sketch. | MECH | Z4 | Z4 | 6th | 43958 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0914 | Pls Check the release for mechanical trades above false ceilling at the ninth floor for zone(3A) according to the attached sketch. | MECH | Z3A | Z3A | 9th | 43958 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0915 | Pls Check the release for mechanical trades above false ceilling at the ninth floor for zone(3B) according to the attached sketch. | MECH | Z3B | Z3B | 9th | 43958 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0916 | check intsatllation for upright sprinklers at Ground floor for zone(1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3a | Z1,2,3a | GF | 43960 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0917 | check intsatllation for upright sprinklers at Ground floor for zone(4,5,3B) accordding to the attached sketch. | MECH | Z4,5,3B | Z4,5,3B | GF | 43960 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0918 | Check installation EWH (30L) and isolating valve for water supply pipe Pantry sink for 7Th&8Th floor Z3B accordding to the attached sketch. | MECH | Z3b | Z3b | Ml | 43960 | 43968 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0919 | Check external insulation of vertical pipes for chilled water risers in zone(3A) to attached sketch. | MECH | Z3A | Z3A | EX | 43961 | 43968 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0920 | Check external insulation of vertical pipes for chilled water risers in zone(1) to attached sketch. | MECH | Z1 | Z1 | EX | 43961 | 43968 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0921 | Check external insulation of vertical pipes for chilled water risers in zone(5) to attached sketch. | MECH | Z5 | Z5 | EX | 43961 | 43968 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0922 | Check installation Plumbing fixture for the toilet detail (TD 8,9,10,12) at Sixth floor Zone(2,3,4) accordding to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | 6th | 43964 | 43968 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0923 | Check installation of plenum linear slot for hvac duct work in first basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B1 | 43965 | 43982 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0924 | Check installation of plenum linear slot for hvac duct work in Second basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B2 | 43965 | 43982 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0925 | Check of installation of fire damper for hvac duct work in first basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B1 | 43965 | 43982 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0926 | Check of installation of fire damper for hvac duct work in Second basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B2 | 43965 | 43982 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0927 | Check installation of motorized fire smoke damper for hvac duct work in First basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B1 | 43965 | 43982 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0928 | Check installation of Volume damper for hvac duct work in First basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B1 | 43965 | 43982 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0929 | Check installation of Volume damper for hvac duct work in Second basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B2 | 43965 | 43982 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0930 | Check installation of air outlet ( grille) for hvac duct work in First basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B1 | 43965 | 43982 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0931 | Check installation of air outlet ( grille) for hvac duct work in Second basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B2 | 43965 | 43982 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0932 | Check installation of air outlet (diffuser & grille) for hvac duct work in sixth floor accordding to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | 6th | 43965 | 43982 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0933 | Check installation for crack units (outdoor) CRAC 01 for main telecom room at sixth floor at Zone (1) accordding to the attached sketch. | MECH | Z1 | Z1 | 6th | 43965 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0934 | Check installation of air outlet (diffuser & grille) for hvac duct work in Eighth floor accordding to the attached sketch. | MECH | Z3 | Z3 | 8th | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0935 | Check installation of air outlet (diffuser & grille) for hvac duct work in Ninth floor accordding to the attached sketch. | MECH | Z3 | Z3 | 9th | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0936 | Check installation of linear slot for hvac duct work in first floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43969 | 43981 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0937 | Check installation of linear slot for hvac duct work in second floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43969 | 43981 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0938 | Check installation of linear slot for hvac duct work in third floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43969 | 43981 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0939 | Check installation of linear slot for hvac duct work in fourth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43969 | 43981 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0940 | Check installation of linear slot for hvac duct work in Eighth floor accordding to the attached sketch. | MECH | Z3 | Z3 | 8th | 43969 | 43981 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0941 | Check installation of linear slot for hvac duct work in Ninth floor accordding to the attached sketch. | MECH | Z3 | Z3 | 9th | 43969 | 43981 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0942 | Check installation of External insulation for HVAC duct work in ground floor for IC-GF-AHU-04 & IC-GF-AHU-05 and IC-GF-AHU-06 inside AHU room accordding to the attached sketch. | MECH | Z1,2 | Z1,2 | GF | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0943 | Check installation of flexible connection for drainge UPVC pipes at second basement accordding to the attached sketch. | MECH | Z3 | Z3 | B2 | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0944 | Check mockup of installation for cladding of duct work inside mechanical room (AHU room) at Third floor for IC-3F-AHU-04 & IC-3F-AHU-05 and IC-3F-AHU-06 accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 3rd | 43982 | 43989 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0945 | Check mockup of installation of linear slot for hvac duct work in second floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43982 | 43986 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0946 | check intsatllation for pendant sprinklers at Ninth floor accordding to the attached sketch. | MECH | Z3 | Z3 | 9th | 43983 | 43989 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0947 | Check installation and test for drainge UPVC (H/L) condensat drain pipes (FCU&SBU) HVAC including insolation fiber glass at Second basement for area(Z1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | B2 | 43989 | 44003 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0948 | Check installation for super matic 12KG in ( FTR & ELEC ) room at first basement accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0949 | Check installation for super matic 12KG in ( FTR & ELEC ) room at ground floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | GF | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0950 | Check installation for super matic 12KG in ( FTR & ELEC ) room at first floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0951 | Check installation for super matic 12KG in ( FTR & ELEC ) room at second floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0952 | Check installation for super matic 12KG in ( FTR & ELEC ) room at third floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0953 | Check installation for super matic 12KG in ( FTR & ELEC ) room at fourth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0954 | Check installation for super matic 12KG in ( FTR & ELEC ) room at fifth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0955 | Check installation for super matic 12KG in ( FTR & ELEC ) room at sixth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 6th | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0956 | Check installation for super matic 12KG in ( FTR & ELEC ) room at seventh floor accordding to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | 7th | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0957 | Check installation for super matic 12KG in ( FTR & ELEC ) room at eighth floor accordding to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | 8th | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0958 | Check installation for super matic 12KG in ( FTR & ELEC ) room at ninth floor accordding to the attached sketch. | MECH | Z3 | Z3 | 9th | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0959 | check installation of jockey and Booster triple pumb at B2 for area(4) accordding to the attached sketch. | MECH | Z4 | Z4 | B2 | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0960 | Check installation of horizontal pipes for chilled water in first basement between axis (11-18) to attached sketch. | MECH | Z1,2,3A | Z1,2,3A | B1 | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0961 | Check test of horizontal pipes for chilled water in first basement between axis (11-18) to attached sketch. | MECH | Z1,2,3A | Z1,2,3A | B1 | 43991 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0962 | Check flushing for the firefighting (main + branches) at Ground floor at zone(1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | GF | 43992 | 44012 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0963 | Check installation and test for drainge galvanized AHU for HVAC room condensat drain pipes from Ground to sixth floor for area(Z1,3A) including insolation fiber glass pipe accordding to the attached sketch. | MECH | Z1,3A | Z1,3A | ML | 43995 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0964 | check intsatllation for pendant sprinklers at Eighth floor for area (3) accordding to the attached sketch. | MECH | Z3 | Z3 | 8th | 43996 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0965 | check intsatllation for pendant sprinklers at Fifth floor for area (1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 5th | 43996 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0966 | check intsatllation for upright sprinklers at Eighth floor for area(2) accordding to the attached sketch. | MECH | Z2 | Z2 | 8th | 43996 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0967 | Check test of vertical pipes for chilled water risers in zone (5) to attached sketch. | MECH | Z5 | Z5 | Ml | 43998 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0968 | Check installation and SMOKE test for HVAC duct work in Second basement for area Z(6) IC-B2-CPEF-07 to attached sketch. | MECH | Z6 | Z6 | B2 | 43998 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0969 | check intsatllation for pendant sprinklers at Third floor for area (1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 3rd | 44000 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0970 | Check installation and test for drainge galvanized AHU for HVAC room condensat drain pipes from Ground to sixth floor for area(Z5,3B) including insolation fiber glass pipe accordding to the attached sketch. | MECH | Z5,3B | Z5,3B | ML | 44003 | 44012 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0971 | Check sand blasting & primer coating &painting for fire fighting pipes | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 44003 | 44012 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0972 | check installation of isolating valves for firefighting network at second basment accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | B2 | 44003 | 44012 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0973 | check intsatllation for pendant sprinklers at Fourth floor for area (1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 4th | 44004 | 44020 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0974 | Check instlation and test for Roof drain UPVC ST pipes at roof at Fifth &Sixth and Seventh floor for area zone(2,3,4) accordding to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | 5th | 44006 | 44013 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0975 | check intsatllation for pendant sprinklers at Fifth floor for area (3B,4,5) accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 5th | 44006 | 44012 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0976 | check intsatllation for pendant sprinklers at Sixth floor for area (1,2,3A) accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 6th | 44006 | 44012 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0977 | check insallation mockup for mixer between two sumbirsable pump for drainge by sumbit for second basement at zone(3) to the attached sketch. | MECH | Z3 | Z3 | B2 | 44006 | 44013 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0978 | check intsatllation for pendant sprinklers at Seventh floor for area (2,3,4) accordding to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | 7th | 44013 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0979 | Check Installaion GR pipe ᶲ16mm For Irrigation network Pipes (dripping) part 2 (Z6,7) for Landscape accordding to the attached sketch. | MECH | Z6,7 | Z6,7 | EX | 44019 | 44023 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0980 | Check installation for water supply (PRV) at B1 & B2 at Zone (1,2,3,4,5,6) accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | ML | 44019 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0981 | check installation of foam system (foam tank-foam tank accessories-valves-pipes) for gemertor rooms at zone (1&5) accordding to the attached sketch. | MECH | Z1,5 | Z1,5 | GF | 44019 | 44028 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0982 | Check installation and SMOKE test for HVAC duct work in Second basement for area Z(6) IC-B2-CPFF-07 to attached sketch. | MECH | Z6 | Z6 | B2 | 44019 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0983 | Check mockup of cladding for HVAC duct work in first basement for IC-6F-FAHU-02 to attached sketch. | MECH |  |  | B1 | 44019 | 44023 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0984 | Check mockup of cladding for horizontal pipes for chilled water in first basement between axis (11-18) to attached sketch. | MECH |  |  | B1 | 44019 | 44023 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0985 | Check installation for External insulation for fan coil unit for HVAC duct work in First basement (B1) accordding to the attached sketch. | MECH |  |  | B1 | 44019 | 44023 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0986 | Check installation for External insulation for fan coil unit for HVAC duct work in Second basement (B2) accordding to the attached sketch. | MECH |  |  | B2 | 44019 | 44023 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0987 | Check installation and test for drainge UPVC pipes U/G External at land scape for sewage from I.C to MH (-8-3) and storm from I.C to MH (-2-2)net work accordding to the attached sketch. | MECH |  |  | EX | 44020 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0988 | Check Installaion and test For Irrigation network Pipes (dripping) part 1,2 at water feature 1,2 for Landscape accordding to the attached sketch. | MECH |  |  | EX | 44020 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0989 | check flushing for drainge pipe storm from Ground floor to Roof riser and H/L accordding to the attached sketch. | MECH |  |  | ML | 44020 | 44027 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0990 | Check installation for fire fighting network for Roof floor (Z3) accordding to the attached sketch. | MECH | Z3 | Z3 | RF | 44024 | 44027 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0991 | check intsatllation for pendant sprinklers at Sixth floor for area (3B,4) accordding to the attached sketch. | MECH | Z3B,4 | Z3B,4 | 6th | 44024 | 44027 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0992 | Check hydraulic test for fire fighting network (Main line+Branches) at Roof floor AT ZONE (3) accordding to the attached sketch. | MECH | Z3 | Z3 | RF | 44025 | 44030 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0993 | check installation for split and Ref Pipes (outdoor units) at second basement as per attached sketch. | MECH |  |  | B2 | 44025 | 44030 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0994 | check installation for split and Ref Pipes (outdoor units) at First basement as per attached sketch. | MECH |  |  | B1 | 44025 | 44030 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0995 | Check installation of pressurization fans with all accessories and seismic support of IC-6F-PF-01&IC-7F-PF-01&IC-7F-PF-02&IC-9F-PF-01&IC_9F-PF-02&IC-UR-PF-01 and IC-UR-PF-02 accordding to the attached sketch. | MECH |  |  | ML | 44026 | 44030 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0996 | Check installation of linear slot for hvac duct work in Fifth floor accordding to the attached sketch. | MECH |  |  | 5th | 44028 | 44033 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0997 | Check installation of linear slot for hvac duct work in Sixth floor accordding to the attached sketch. | MECH |  |  | 6th | 44028 | 44033 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0998 | Check installation of linear slot for hvac duct work in Seventh floor accordding to the attached sketch. | MECH |  |  | 7th | 44028 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-0999 | Check installation of air outlet (diffuser & grille) for hvac duct work in Seventh floor accordding to the attached sketch. | MECH |  |  | 7th | 44028 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1000 | check installation for split and Ref Pipes (outdoor units) at First Floor as per attached sketch. | MECH |  |  | 1st | 44031 | 44035 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1001 | check installation for split and Ref Pipes (outdoor units) at Ground Floor as per attached sketch. | MECH |  |  | GF | 44031 | 44035 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1002 | Check instllation of External insulation of chilled water network and hookup for air handling unit room in first floor for IC-1F-AHU-01 & IC-1F-AHU-02 & IC-1F-AHU-03 & IC-1F-AHU-04 & IC-1F-AHU-05 and IC-1F-AHU-06 accordding to the attached sketch. | MECH |  |  | 1st | 44031 | 44038 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1003 | Check instllation of External insulation for chilled water network and hookup for air handling unit room in second floor for IC-2F-AHU-01 & IC-2F-AHU-02 & IC-2F-AHU-03 & IC-2F-AHU-04 & IC-2F-AHU-05 and IC-2F-AHU-06 accordding to the attached sketch. | MECH |  |  | 2nd | 44031 | 44038 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1004 | Check instllation of chilled water network and hookup for air handling unit room in third floor for IC-3F-AHU-01 & IC-3F-AHU-02 & IC-3F-AHU-03 & IC-3F-AHU-04 & IC-3F-AHU-05 and IC-3F-AHU-06 accordding to the attached sketch. | MECH |  |  | 3rd | 44031 | 44038 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1005 | Check instllation of External insulation of chilled water network and hookup for air handling unit room in fourth floor for IC-4F-AHU-01 & IC-4F-AHU-02 & IC-4F-AHU-03 & IC-4F-AHU-04 & IC-4F-AHU-05 and IC-4F-AHU-06 accordding to the attached sketch. | MECH |  |  | 4th | 44031 | 44038 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1006 | Check instllation of External insulation of chilled water network and hookup for air handling unit room in fifth floor for IC-5F-AHU-01 & IC-5F-AHU-02 & IC-5F-AHU-03 & IC-5F-AHU-04 & IC-5F-AHU-05 and IC-5F-AHU-06 accordding to the attached sketch. | MECH |  |  | 5th | 44031 | 44038 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1007 | Check instllation of External insulation of chilled water network and hookup for air handling unit room in sixth floor for IC-6F-AHU-01 & IC-6F-AHU-02 & IC-6F-AHU-03 and IC-6F-AHU-04 accordding to the attached sketch. | MECH |  |  | 6th | 44031 | 44038 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1008 | Check installation of Internal insulation for car park fresh fans in lower basement accordding to the attached sketch. | MECH |  |  | B2 | 44031 | 44035 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1009 | Check installation of Internal insulation for car park Exhaust fans in lower basement accordding to the attached sketch. | MECH |  |  | B2 | 44031 | 44035 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1010 | Check installation of smoke fans with all accessories and seismic support of IC-6F-SF-02&IC-6F-SF-03&IC-6F-SF-01&IC-RF-SF-01 and IC_RF-SF-02 accordding to the attached sketch. | MECH |  |  | ML | 44031 | 44038 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1011 | Check installation of Exhaust fans with all accessories and seismic support of IC-6F-EF-02&IC-6F-EF-01&IC-6F-EF-03&IC-8F-EF-08& IC_8F-EF-01&IC-8F-EF-02 and IC-8F-EF-03 accordding to the attached sketch. | MECH |  |  | ML | 44031 | 44038 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1012 | Check installation of Exhaust fans with all accessories and seismic support of IC-8F-EF-04&IC-8F-EF-05&IC-8F-EF-06&IC-8F-EF-07& IC_8F-EF-09&IC-RF-EF-01 and IC-RF-EF-02 and accordding to the attached sketch. | MECH |  |  | ML | 44031 | 44038 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1013 | Check installation of External insulation for HVAC duct work in Sixth floor for IC-6F-FAHU-01 and IC_6F_FAHU_02 accordding to the attached sketch. | MECH |  |  | 6th | 44031 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1014 | Check installation of External insulation for HVAC duct work in Eighth floor for IC-8F-AHU-02 and IC-8F-FAHU-02 accordding to the attached sketch. | MECH |  |  | 8th | 44031 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1015 | Check installation of internal insulation for HVAC duct work in Roof for IC-RF-AHU-01&IC-RF-AHU-02&IC-RF-AHU-03&IC-RF-AHU-04&IC-RF-AHU-05&IC-RF-AHU-01 and IC-RF-FAHU-01 accordding to the attached sketch. | MECH |  |  | RF | 44031 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1016 | Check installation of External insulation for hvac duct work of total fresh air riser with for IC-8F-FAHU-01 and IC-8F-FAHU-02 from ground to eighth floor accordding to the attached sketch. | MECH |  |  | Ml | 44032 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1017 | Check installation of External insulation for hvac duct work of EXHAUST riser (Pantry) with rook wool for IC-8F-EF-02 and IC-8F-EF-05 from Ground floor to Eighth floor accordding to the attached sketch. | MECH |  |  | Ml | 44032 | 44038 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1018 | Check instllation and test of chilled water network and hookup for air handling unit room in ROOF for IC-RF-AHU-01 & IC-RF-AHU-02 & IC-RF-AHU-03&IC-RF-AHU-04&IC-RF-AHU-05&IC-RF-AHU-06 and IC-RF-FAHU-01 accordding to the attached sketch. | MECH |  |  | RF | 44032 | 44040 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1019 | Check installation of External insulation for HVAC duct work in Eighth floor for IC-8F-AHU-01 and IC-8F-FAHU-01 accordding to the attached sketch. | MECH |  |  | 8th | 44032 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1020 | Check installation of HVAC duct work in Roof for IC-RF-AHU-01&IC-RF-AHU-02&IC-RF-AHU-03&IC-RF-AHU-04&IC-RF-AHU-05&IC-RF-AHU-01 and IC-RF-FAHU-01 accordding to the attached sketch. | MECH |  |  | RF | 44032 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1021 | Check installation of componant for AHU in sixth floor for IC-6F-FAHU-01 and IC-6F-FAHU-02 accordding to the attached sketch. | MECH |  |  | 6th | 44032 | 44038 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1022 | Check installation of componant for AHU in Eighth floor for IC-8F-FAHU-01&IC-8F-AHU-01&IC-8F-FAHU-02 and IC-8F-AHU-02 accordding to the attached sketch. | MECH |  |  | 8th | 44032 | 44038 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1023 | Check installation of componant for AHU in ROOF for IC-RF-AHU-01&IC-RF-AHU-02&IC-RF-AHU-03&IC-RF-AHU-04&IC-RF-AHU-05&IC-RF-AHU-01 and IC-RF-FAHU-01 accordding to the attached sketch. | MECH |  |  | RF | 44032 | 44038 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1024 | check installation for split and Ref Pipes (outdoor units) at Second Floor as per attached sketch. | MECH |  |  | 2nd | 44034 | 44040 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1025 | check installation for split and Ref Pipes (outdoor units) at Third Floor as per attached sketch. | MECH |  |  | 3rd | 44034 | 44040 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1026 | Check sand blasting & primer coating &painting for fire fighting pipes as per attached sketch. | MECH |  |  | ML | 44034 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1027 | check insallation for mixer between two sumbirsable pump for drainge by sumbit for second basement at zone(1,2,3,4,5,6) to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B2 | 44034 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1028 | check installation of fire hose cabinet at Fifth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 44038 | 44047 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1029 | check installation of fire hose cabinet at Sixth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 6th | 44038 | 44047 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1030 | check installation of fire hose cabinet at Seventh floor accordding to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | 7th | 44038 | 44047 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1031 | check installation of fire hose cabinet at Eighth floor accordding to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | 8th | 44038 | 44047 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1032 | check installation of fire hose cabinet at Ninth floor accordding to the attached sketch. | MECH | Z3 | Z3 | 9th | 44038 | 44047 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1033 | Check installation for fuel tank sump and vent pipe, suction and return pipes at Ground floor for area(1,5) accordding to the attached sketch. | MECH | Z1,5 | Z1,5 | GF | 44038 | 44047 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1034 | Check instllation and test of chilled water network and hookup for air handling unit in Eighth floor for IC-8F-AHU-01 & IC-8F-FAHU-01 & IC-8F-AHU-02 and IC-8F-FAHU-02 accordding to the attached sketch. | MECH | Z3 | Z3 | 8th | 44038 | 44047 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1035 | Check installation of External insulation HVAC duct work in Roof for IC-RF-AHU-01&IC-RF-AHU-02&IC-RF-AHU-03&IC-RF-AHU-04&IC-RF-AHU-05&IC-RF-AHU-01 and IC-RF-FAHU-01 accordding to the attached sketch. | MECH |  |  | RF | 44038 | 44047 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1036 | check intsatllation for pendant sprinklers at Second floor for area (4,5,3B) accordding to the attached sketch. | MECH | 4,5,3B | 4,5,3B | 2nd | 44052 | 44060 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1037 | Check installation and test for drainge UPVC pipes U/G External at land scape for sewage from I.C to (RD-22) MH (-2-3) and storm from I.C to MH(-5A-1-1) net work accordding to the attached sketch. | MECH |  |  | EX | 44053 | 44060 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1038 | Check installation for water supply (PRV) at Ground&First&Second and Third floor at Zone (2,4) in TD(11) accordding to the attached sketch. | MECH |  |  | ML | 44053 | 44060 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1039 | Check installation and test for drainge UPVC H/L storm pipes at ROOF for area zone(3) accordding to the attached sketch. | MECH | Z3 | Z3 | RF | 44055 | 44060 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1040 | check installation for pipe connection between F.H.C and fire fighting risers accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 44056 | 44066 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1041 | Check installation for super matic 12KG in ( FTR & ELEC ) room at Second basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B2 | 44056 | 44066 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1042 | Check installation of flexible connection for fire fighting pipes at Second Basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B2 | 44062 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1043 | check installation of fire hose cabinet at Ground floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | GF | 44062 | 44070 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1044 | check installation of fire hose cabinet at First floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 44062 | 44070 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1045 | check installation of fire hose cabinet at Second floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 44062 | 44070 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1046 | check installation of fire hose cabinet at third floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 44062 | 44070 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1047 | check installation of fire hose cabinet at Fourth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 44062 | 44070 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1048 | Check installation and test for drainge galvanized AHU for HVAC room condensat drain pipes At Roof for sixth and Eighth floor for area(Z1,2,4,5) including insolation fiber glass pipe accordding to the attached sketch. | MECH | Z1,2,4,5 | Z1,2,4,5 | ML | 44065 | 44075 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1049 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes modification main line part (1,2,3,4) for Landscape accordding to the attached sketch. | MECH | Z1,2,3,4 | Z1,2,3,4 | EX | 44065 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1050 | Check Installaion and test For Irrigation network Pipes modification main line part (1,2,3,4) for Landscape accordding to the attached sketch. | MECH | Z1,2,3,4 | Z1,2,3,4 | EX | 44065 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1051 | Check installation of air outlet (diffuser & grille) for hvac duct work in Ground floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | GF | 44067 | 44075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1052 | Check installation of linear slot for hvac duct work in Ground floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | GF | 44067 | 44075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1053 | Check instllation of External insulation for chilled water network and hookup for air handling unit room in Ground floor for IC-GF-AHU-01 & IC-GF-AHU-02 & IC-GF-AHU-03 & IC-GF-AHU-04 & IC-GF-AHU-05 and IC-GF-AHU-06 accordding to the attached sketch. | MECH |  |  | GF | 44067 | 44075 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1054 | Check installation of pressure gauge,thermostat,airvent and drain valve in chilled water pipes of handling unit room in Ground floor for IC-GF-AHU-01 & IC-GF-AHU-02 & IC-GF-AHU-03 & IC-GF-AHU-04 & IC-GF-AHU-05 and IC-GF-AHU-06 accordding to the attached sketch. | MECH |  |  | GF | 44067 | 44075 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1055 | Check installation of pressure gauge,thermostat,airvent and drain valve in chilled water pipes of handling unit room in First floor for IC-1F-AHU-01 & IC-2F-AHU-02 & IC-3F-AHU-03 & IC-4F-AHU-04 & IC-5F-AHU-05 and IC-6F-AHU-06 accordding to the attached sketch. | MECH |  |  | 1st | 44067 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1056 | Check installation of pressure gauge,thermostat,airvent and drain valve in chilled water pipes of handling unit room in Second floor for IC-2F-AHU-01 & IC-2F-AHU-02 & IC-2F-AHU-03 & IC-2F-AHU-04 & IC-2F-AHU-05 and IC-2F-AHU-06 accordding to the attached sketch. | MECH |  |  | 2nd | 44067 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1057 | Check installation of pressure gauge,thermostat,airvent and drain valve in chilled water pipes of handling unit room in Third floor for IC-3F-AHU-01 & IC-3F-AHU-02 & IC-3F-AHU-03 & IC-3F-AHU-04 & IC-3F-AHU-05 and IC-3F-AHU-06 accordding to the attached sketch. | MECH |  |  | 3rd | 44067 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1058 | Check installation of pressure gauge,thermostat,airvent and drain valve in chilled water pipes of handling unit room in Fourth floor for IC-4F-AHU-01 & IC-4F-AHU-02 & IC-4F-AHU-03 & IC-4F-AHU-04 & IC-4F-AHU-05 and IC-4F-AHU-06 accordding to the attached sketch. | MECH |  |  | 4th | 44067 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1059 | Check installation of pressure gauge,thermostat,airvent and drain valve in chilled water pipes of handling unit room in Fifth floor for IC-5F-AHU-01 & IC-5F-AHU-02 & IC-5F-AHU-03 & IC-5F-AHU-04 & IC-5F-AHU-05 and IC-5F-AHU-06 accordding to the attached sketch. | MECH |  |  | 5th | 44067 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1060 | Check installation of pressure gauge,thermostat,airvent and drain valve in chilled water pipes of handling unit room in Sixth floor for IC-6F-AHU-01 & IC-6F-AHU-02 & IC-6F-AHU-03 and IC-6F-AHU-04 accordding to the attached sketch. | MECH |  |  | 6th | 44067 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1061 | check instllation for the firefighting pipes (branches) at Second basement at zone(6)accordding to the attached sketch. | MECH | Z6 | Z6 | B2 | 44070 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1062 | Check Installaion location and Level For Subsurface Drainge perfrated network Pipes modification main line part (4) for Landscape accordding to the attached sketch. | MECH |  |  | EX | 44070 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1063 | check installation of siesmic support for firefighing pipes and duct work for First floor for area Z(1,2,3,4,5) accordding to the attached sketch. | MECH | 1,2,3,4,5 | 1,2,3,4,5 | 1st | 44073 |  | cancelled
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1064 | check installation of siesmic support for firefighing pipes and duct work for Second floor for area Z(1,2,3,4,5) accordding to the attached sketch. | MECH | 1,2,3,4,5 | 1,2,3,4,5 | 2nd | 44073 |  | cancelled
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1065 | check installation of siesmic support for firefighing pipes and duct work for Third floor for area Z(1,2,3,4,5) accordding to the attached sketch. | MECH | 1,2,3,4,5 | 1,2,3,4,5 | 3rd | 44073 |  | cancelled
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1066 | check installation of siesmic support for firefighing pipes and duct work for Eighth floor for area Z(2,3,4) accordding to the attached sketch. | MECH | 2,3,4 | 2,3,4 | 8th | 44073 |  | cancelled
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1067 | check installation of siesmic support for firefighing pipes and duct work for Ninth floor for area Z(1,2,3,4,5) accordding to the attached sketch. | MECH | 3 | 3 | 9th | 44073 |  | cancelled
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1068 | Check Installaion and test For Irrigation network Pipes modification main line part (2) for Landscape accordding to the attached sketch. | MECH |  |  | EX | 44074 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1069 | Check Installaion location and Level For Subsurface Drainge Tie in connection Pipes from Sedimentation champer to storm manhole(MH-2-3)&(MH-5A-3-1* and (GOV1-8) accordding to the attached sketch. | MECH |  |  | EX | 44075 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1070 | Check installation and test plumbing fixture for drainge and water supply PPR pipes ablution ground floor at axis (1-7) with axis (A-F) accordding to the attached sketch. (Zone1,5) | MECH |  |  | GF | 44075 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1071 | Check installation Plumbing fixture for the toilet detail (TD 8,9,10,12) From Seventh to Ninth floor Zone(2,3,4) accordding to the attached sketch. | MECH | 2,3,4 | 2,3,4 | ML | 44075 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1072 | check flushing for drainge (SP&WP) pipe from Ground floor to Roof and riser and H/L and embided and Toilet Detail for area Z(4,5,3B) accordding to the attached sketch. | MECH | 4,5,3B | 4,5,3B | ML | 44075 | 44083 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1073 | Check installation of flexible connection for Chilled water pipes at First Basement for area Z(1,2) accordding to the attached sketch. | MECH | 1,2 | 1,2 | B1 | 44075 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1074 | check flushing for Water supply (Galvanized&PPR) pipe from Ground floor to Roof and riser and H/L and embided and Toilet Detail for area Z(4,5,3B) accordding to the attached sketch. | MECH | 4,5,3B | 4,5,3B | ML | 44075 | 44083 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1075 | check insallation mockup for hose bibb and steel box for water supply pipes at pump room at Second basement for area Z (4) to the attached sketch. | MECH | 4 | 4 | B2 | 44076 | 44083 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1076 | check insallation mockup for wall clean out 4"&2" for drainge pipe for Toilet Detail(8)&(11) at Second Floor for area Z (3B) to the attached sketch. | MECH | 3B | 3B | 2nd | 44076 | 44083 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1077 | Check sand blasting & primer coating &painting for fire fighting pipes as per attached sketch. | MECH |  |  | ML | 44076 | 44080 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1078 | Check installation of Axial fans at first basement accordding to the attached sketch. | MECH |  |  | B1 | 44076 | 44083 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1079 | Check installation of Axial fans at Second basement accordding to the attached sketch. | MECH |  |  | B2 | 44076 | 44083 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1080 | check request of snag list for HVAC at Ninth floor accordding to the attached sketch. | MECH |  |  | 9th | 44076 | 44083 | D
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1081 | check insallation for wall clean out 4"&2" for drainge pipe for all Toilet Detail from First basement to Ninth Floor According to the attached sketch. | MECH |  |  | ML | 44084 | 44088 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1082 | Check Installaion location and Level For Subsurface Drainge perfrated network Clean out part (3,4) for Landscape accordding to the attached sketch. | MECH |  |  | EX | 44087 | 44098 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1083 | check insallation for Vent cap 6"&4"&3" and 2" for drainge pipe riser at Eighth Floor for area Z(2,3,4) According to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | 8th | 44087 | 44091 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1084 | Check installation and test for drainge UPVC (H/L) condensat drain pipes (FCU&SBU) HVAC including insolation fiber glass at First basement for area(Z1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 44087 | 44091 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1085 | Check installation and test for floor drain 4" for drainge pipe U/G for first basement&Second basment and Ground floor for area Zone(1,2,4,5) accordding to the attached sketch. | MECH | Z1,2,4,5 | Z1,2,4,5 | ML | 44087 | 44091 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1086 | check galvanized drain connection between zone control and drain riser for all zone stations accordding to the attached sketch. | MECH |  |  | ML | 44088 | 44091 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1087 | Check installation and test UPVC pipes water features No(4) to pump room No(1) for landscape accordding to the attached sketch. | MECH |  |  | EX | 44088 | 44094 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1088 | Check installation pipes and valves pump room water features No(1,2,3) for landscape accordding to the attached sketch. | MECH |  |  | EX | 44088 | 44097 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1089 | Check Installaion location and Level For Subsurface Drainge pipes perfrated network part (3,4) for Landscape accordding to the attached sketch. | MECH |  |  | EX | 44088 | 44098 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1090 | Check Installaion and test For Irrigation main line Pipes and sleeves cable control modification main line part (3) for Landscape accordding to the attached sketch. | MECH |  |  | EX | 44088 | 44098 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1091 | Check installation and test for filling line the water supply pipe 4" EXternal U/G HDPE pipes accordding to the attached sketch. | MECH |  |  | EX | 44090 | 44094 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1092 | check intsatllation for bendant sprinklers at Ground floor for zone(1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | GF | 44091 | 44098 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1093 | check intsatllation for sprinklers at First basement for zone(3B,4,5,6) accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | B1 | 44091 | 44098 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1094 | check intsatllation for sprinklers at Second basement for zone(1,2,3,4,5,6) accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B2 | 44091 | 44098 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1095 | check intsatllation for fire extinguisher at First basement for zone(1,2,3,4,5,6) accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B1 | 44091 | 44098 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1096 | check intsatllation for fire extinguisher at Second basement for zone(1,2,3,4,5,6) accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B2 | 44091 | 44098 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1097 | check intsatllation for fire extinguisher at Typical floors for zone(1,2,3,4,5,6) accordding to the attached sketch. | MECH |  |  | ML | 44091 | 44098 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1098 | Check installation of flexible connection for Chilled water pipes at First Basement for area Z(3B,4,5) accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | B1 | 44095 | 44102 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1099 | check flushing for drainge (SP&WP) pipe from Ground floor to Roof and riser and H/L and embided and Toilet Detail for area Z(1,2,3A) accordding to the attached sketch. | MECH | (1,2,3A) | (1,2,3A) | ML | 44096 | 44109 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1100 | check flushing for Water supply (Galvanized&PPR) pipe from Ground floor to Roof and riser and H/L and embided and Toilet Detail for area Z(1,2,3A) accordding to the attached sketch. | MECH | (1,2,3A) | (1,2,3A) | ML | 44096 | 44109 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1101 | Check installation of air separator and Expantion tank in ETS room for first basement accordding to the attached sketch. . | MECH |  |  | B1 | 44098 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1102 | Check installation of water circulation pump at Second basement accordding to the attached sketch. | MECH |  |  | B2 | 44098 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1103 | Check installation for cladding of duct work inside mechanical room (AHU room) at Fifth floor for IC-5F-AHU-04 & IC-5F-AHU-05 and IC-5F-AHU-06 accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 5th | 44102 | 44109 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1104 | Check installation for cladding of duct work inside mechanical room (AHU room) at Sixth floor for IC-6F-AHU-03 and IC-6F-AHU-04 accordding to the attached sketch. | MECH | Z2,3A | Z2,3A | 6th | 44102 | 44109 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1105 | Check Installaion and test For Irrigation main line Pipes and sleeves cable control modification main line part (1,3) for Landscape accordding to the attached sketch. | MECH |  |  | EX | 44103 | 44109 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1106 | Check Installaion location and Level For Subsurface Drainge pipes perfrated network part (1,3) for Landscape accordding to the attached sketch. | MECH |  |  | EX | 44103 | 44109 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1107 | Check hydraulic test for fire fighting network (Main line+Branches) at Second basement for area Zone(6) accordding to the attached sketch. | MECH | Z6 | Z6 | B2 | 44103 | 44109 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1108 | Check installation for cladding of duct work inside mechanical room (AHU room) at Third floor for IC-3F-AHU-04& IC-3F-AHU-05 and IC-3F-AHU-06 accordding to the attached sketch. | MECH | Z1,2,3A | Z1,2,3A | 3rd | 44103 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1109 | Check installation of air handing unit at (AHU ROOM) with Seismic Restraints & Vibration isolators at Ground Floor of IC-GF-AHU-01&IC-GF-AHU-02&IC-GF-AHU-03&IC-GF-AHU-04&IC-GF-AHU-05 and IC-GF-AHU-06 accordding to the attached sketch. | MECH |  |  | GF | 44104 | 44116 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1110 | Check installation of air handing unit at (AHU ROOM) with Seismic Restraints & Vibration isolators at First Floor of IC-1F-AHU-01&IC-1F-AHU-02&IC-1F-AHU-03&IC-1F-AHU-05 and IC-1F-AHU-06 accordding to the attached sketch. | MECH |  |  | 1st | 44104 | 44116 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1111 | Check installation of air handing unit at (AHU ROOM) with Seismic Restraints & Vibration isolators at Second Floor of IC-2F-AHU-01&IC-2F-AHU-02&IC-2F-AHU-03 and IC-2F-AHU-05 accordding to the attached sketch. | MECH |  |  | 2nd | 44104 | 44116 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1112 | Check installation of air handing unit at (AHU ROOM) with Seismic Restraints & Vibration isolators at Thirdd Floor of IC-3F-AHU-01&IC-3F-AHU-02&IC-3F-AHU-03 and IC-3F-AHU-05 accordding to the attached sketch. | MECH |  |  | 3rd | 44104 | 44116 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1113 | Check installation of air handing unit at (AHU ROOM) with Seismic Restraints & Vibration isolators at Fourth Floor of IC-4F-AHU-01&IC-4F-AHU-02&IC-4F-AHU-03&IC-4F-AHU-05 and IC-4F-AHU-06 accordding to the attached sketch. | MECH |  |  | 4th | 44104 | 44116 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1114 | Check installation of air handing unit at (AHU ROOM) with Seismic Restraints & Vibration isolators at Fifth Floor of IC-5F-AHU-01&IC-5F-AHU-02&IC-5F-AHU-04&IC-5F-AHU-05 and IC-5F-AHU-06 accordding to the attached sketch. | MECH |  |  | 5th | 44104 | 44116 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1115 | Check installation of air handing unit at (AHU ROOM) with Seismic Restraints & Vibration isolators at Sixth Floor of IC-6F-AHU-01&IC-6F-AHU-02&IC-6F-AHU-03 and IC-6F-AHU-04 accordding to the attached sketch. | MECH |  |  | 6th | 44104 | 44116 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1116 | Check installation of air handing unit at (AHU ROOM) with Seismic Restraints & Vibration isolators at Eighth Floor of IC-8F-AHU-01 and IC-8F-AHU-02 accordding to the attached sketch. | MECH |  |  | 8th | 44104 | 44116 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1117 | Check installation of air handing unit at (AHU ROOM) with Seismic Restraints & Vibration isolators at Roof Floor of IC-RF-AHU-01&IC-RF-AHU-02&IC-RF-AHU-03&IC-RF-AHU-04&IC-RF-AHU-05 and IC-RF-AHU-06 accordding to the attached sketch. | MECH |  |  | RF | 44104 | 44116 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1118 | Check installation for water supply isolating valve for Garbage shoot at Seventh floor at Zone (2,4) accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | 7th | 44107 | 44116 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1119 | Check installation for gutter ductile iron for trench drain under ground at First and second basement for area (Zone2,3,4,) accordding to the attached sketch. | MECH | Z2,3,4 | Z2,3,4 | ML | 44107 | 44116 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1120 | Check hydraulic test for fire fighting network (Main line+Branches) at First basement for area Zone(6) accordding to the attached sketch. | MECH | Z6 | Z6 | B1 | 44108 | 44116 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1121 | Check flushing for the firefighting (main + branches) at Second basement at zone(6) accordding to the attached sketch. | MECH | Z6 | Z6 | B2 | 44110 | 44116 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1122 | Check installation of car park fresh fans for IC-B1-CPFF-03&IC-B1-CPFF-04 and IC-B1-CPFF-05 at First basemnet accordding to the attached sketch. | MECH |  |  | B1 | 44111 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1123 | Check installation of car park fresh fans for IC-B2-CPFF-01&IC-B2-CPFF-02&IC-B2-CPFF-03&IC-B2-CPFF-04 and IC-B2-CPFF-07 at Second basemnet accordding to the attached sketch. | MECH |  |  | B2 | 44111 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1124 | Check installation of car park Exhaust fans for IC-B1-CPEF-01&IC-B1-CPEF-02&IC-B1-CPEF-03&IC-B1-CPEF-04&IC-B1-CPEF-05 and IC-B1-CPEF-08 at First basemnet accordding to the attached sketch. | MECH |  |  | B1 | 44111 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1125 | Check installation of car park Exhaust fans for IC-B2-CPEF-03 and IC-B2-CPEF-04 at Second basemnet accordding to the attached sketch. | MECH |  |  | B2 | 44111 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1126 | Check flushing for the firefighting (main + branches) at First basement at zone(6) accordding to the attached sketch. | MECH | Z6 | Z6 | B1 | 44114 | 44117 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1127 | check installation benching and cover inspection champer(Sewage&Storm&Gullytrap) and Slow down champer drainge pipe at Landscape for area Z(2,4) accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | L.S | 44118 | 44143 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1128 | Check installation for water supply Automatic Air vent at Sixth&Ninth and Ten floor at Zone (2,3A,3B) accordding to the attached sketch. | MECH | Z2,3A,3B | Z2,3A,3B | ML | 44125 | 44143 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1129 | Check installation of car park fresh and Exhaust fans for IC-B1-CPFF-06&IC-B1-CPFF-07&IC-B1-CPFF-08&IC-B1-CPFF-09 and IC-B1-CPEF-07 at First basemnet accordding to the attached sketch. | MECH |  |  | B1 | 44128 | 44143 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1130 | Check installation of car park fresh and Exhaust fans for IC-B2-CPFF-05&IC-B2-CPFF-06&IC-B2-CPEF-05 and IC-B2-CPEF-06 at Second basemnet accordding to the attached sketch. | MECH |  |  | B2 | 44128 | 44143 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1131 | check installation mock up of propeller exhaust fan IC-B1-EF-07 accordding to the attached sketch. | MECH |  |  | B1 | 44131 | 44143 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1132 | Check installation and test for filling line Pipe HDPE 4" U/G from Irrigation valve champer to Pump room accordding to the attached sketch. | MECH |  |  | EX | 44132 | 44143 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1133 | Check Installaion and test For Irrigation Net work Sprinklers and dripping Pipes part (1) Z(11) for Landscape accordding to the attached sketch. | MECH | Z11 | Z11 | EX | 44137 | 44144 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1134 | Check Installaion and test For Irrigation Net work rotor Sprinklers 5000 and dripping Pipe GR 16M part (2,4) Z(2,3,4,5) for Landscape accordding to the attached sketch. | MECH | Z2,3,4,5 | Z2,3,4,5 | EX | 44137 | 44144 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1135 | Check installation of fan coil unit for HVAC duct work in first basement and Second basement accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | ML | 44138 | 44143 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1136 | Check installation for water supply hose spray handing at all toilet detail TD(1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17) at Zone (1,2,3,4,5) from First basement to Ninth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 44140 |  | cancelled
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1137 | check installation for gate and balance valves for HVAC rooms and chilled water risers accordding to the attached sketch. | MECH |  |  | ML | 44145 | 44153 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1138 | Check installation for cladding of duct work inside mechanical room (AHU room) at Fourth floor for IC-4F-AHU-04& IC-4F-AHU-05 and IC-4F-AHU-06 accordding to the attached sketch. | MECH |  |  | 4th | 44145 | 44153 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1139 | Check installation and test for drainge Pipe U/G UPVC from Irrigation Pump room to slow down champer and from Slow down champer to sewage Manhole (MH1/R22) at landscape accordding to the attached sketch. | MECH |  |  | EX | 44146 | 44157 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1140 | check mockup for FCU hook up insulation at First basement for area Z(4) accordding to the attached sketch. | MECH | Z4 | Z4 | B1 | 44151 | 44164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1141 | Check installation combonant for Valve room before irrigation tank at landscape accordding to the attached sketch. | MECH |  |  | EX | 44153 | 44164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1142 | Check installation for Two float Valve for irrigation tank at landscape accordding to the attached sketch. | MECH |  |  | EX | 44153 | 44164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1143 | Check Installaion and test For Irrigation main line Pipes and sleeves cable control modification main line part (2) for Landscape accordding to the attached sketch. | MECH |  |  | EX | 44157 | 44164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1144 | Check sand blasting & primer coating &painting for fire fighting pipes as per attached sketch. | MECH |  |  | ML | 44157 | 44164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1145 | check installation for manual isolation butterfly valves at DCP main connection with ETS Room accordding to the attached sketch. | MECH |  |  | B1 | 44157 | 44164 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1146 | Check installation EWH (30L(6) & (50L(2) & (80L(1) for water supply pipe toilet Detail (TD 1) & (TD 2) & (TD 3) &(TD 4) & (TD 5) and (TD 6) Kitchen and Pantry sink and At Ninth floor For Area Zone (3) accordding to the attached sketch. | MECH | Z3 | Z3 | 9th | 44159 | 44168 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1147 | Check Installaion location and Level For Subsurface Drainge Tie in connection Pipes from Sedimentation champer to storm manhole(MH to (GOV1-13) accordding to the attached sketch. | MECH |  |  | EX | 44165 | 44168 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1148 | check pre-flushing for chilled water system accordding to the attached sketch. | MECH |  |  | ML | 44166 | 44205 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1149 | Check installation for cladding of duct work inside mechanical room (AHU room) at Ground floor for IC-GF-AHU-04& IC-GF-AHU-05 and IC-GF-AHU-06 accordding to the attached sketch. | MECH |  |  | GF | 44166 | 44173 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1150 | Check Installaion location and Level For Subsurface Drainge Tie in connection Pipes from Sedimentation champer (SC-03) to another Sedinmentation champer(SC-02) to (SC_01) accordding to the attached sketch. | MECH |  |  | EX | 44173 | 44181 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1151 | Check installation for water supply hose spray handing at all toilet detail TD(1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17) at Zone (1,2,3,4,5) from First basement to Ninth floor accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 44181 | 44195 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1152 | Check Installaion and test For Irrigation Net work Sprinklers and dripping Pipes part (2) Z(00,01,06,07,11,12,16,17,18,19) for Landscape accordding to the attached sketch. | MECH | Z00,01,06,07,11, 12,16,17,18,19 | Z00,01,06,07,11, 12,16,17,18,19 | EX | 44195 | 44216 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1153 | check hydraulic test and flushing for firefighting risers Zone (1,2,3,4,5) accordding to the attached sketch. | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 44196 | 44216 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1154 | Check Installaion and test For Irrigation Net work Sprinklers and dripping Pipes part (1,3) Z(12,15,16) for Landscape accordding to the attached sketch. | MECH | Z12,15,16 | Z12,15,16 | EX | 44198 | 44216 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1155 | Check Installaion GR pipe ᶲ16mm For Irrigation network Pipes (dripping) part (1,3) Z(18,19) for Landscape accordding to the attached sketch. | MECH | Z18,19 | Z18,19 | EX | 44199 | 44212 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1156 | Check installation for the fire department and fire hydrant conections genral mockup at ground floor ZONE(1) accordding to the attached sketch. | MECH | Z1 | Z1 | GF | 44199 | 44212 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1157 | Check Flushing for drainge (SP&WP) pipe for First and Second basment and H/L and embided and toilet detail for area Z(1,2,3,4,5) according to attached sketch . | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 44199 | 44212 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1158 | Check Flushing for Water supply (SP&WP) pipe for First and Second basment and H/L and embided and toilet detail for area Z(1,2,3,4,5) according to attached sketch . | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 44199 | 44212 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1159 | Check Installaion for split unit (Indoor unit) for FTR room from Ground to Fifth floor for area Z(1,5) according to attached sketch . | MECH | Z1,5 | Z1,5 | ML | 44201 | 44212 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1160 | Check installation of Air vent Valve for firefighting risers for all zones according to attached sketch . | MECH | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 44201 | 44212 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1161 | Check External insulation for Deisel fire pump chimney from Second Basement to Second floor for area Z(4) according to attached sketch . | MECH | Z4 | Z4 | ML | 44201 | 44212 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1162 | check insallation for submersible pump for water feature (1,2,3)& irrigation Pump room No (4)accordding to the attached sketch. | MECH |  |  | EX | 44202 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1163 | check insallation of Ventilation fans for fire closet EF-F.C.V-01 accordding to the attached sketch. | MECH |  |  | ML | 44206 | 44216 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1164 | check insallation of Ventilation fans for Water feature and irrigation rooms EF-01 accordding to the attached sketch. | MECH |  |  | EX | 44206 | 44216 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1165 | check installation of all combonant for pump room irrigation including piping connection accordding to the attached sketch. | MECH |  |  | EX | 44208 | 44216 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1166 | Check Cladding for Deisel fire pump chimney from Second basement to Second floor for area Z(4) according to attached sketch . | MECH |  |  | ML | 44210 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1167 | Check installation drainge pipe under ground for Bollard system at ramb Zone (4) according to attached sketch . | MECH | Z4 | Z4 | GF | 44216 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1168 | Check installation for cladding of duct work inside mechanical room (AHU room) at First floor for IC-1F-AHU-01& IC-1F-AHU-02 and IC-1F-AHU-03 accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 1st | 44217 | 44231 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1169 | Check installation for cladding of duct work inside mechanical room (AHU room) at Third floor for IC-3F-AHU-01& IC-3F-AHU-02 and IC-3F-AHU-03 accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 3rd | 44217 | 44231 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1170 | Check installation for cladding of duct work inside mechanical room (AHU room) at Fourth floor for IC-4F-AHU-01& IC-4F-AHU-02 and IC-4F-AHU-03 accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 4th | 44217 | 44231 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1171 | Check installation for cladding of duct work inside mechanical room (AHU room) at Fifth floor for IC-5F-AHU-01& IC-5F-AHU-02 and IC-5F-AHU-03 accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 5th | 44217 | 44231 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1172 | Check installation for cladding of duct work inside mechanical room (AHU room) at Sixth floor for IC-6F-AHU-01& IC-6F-AHU-02 and IC-6F-AHU-03 accordding to the attached sketch. | MECH | Z3B,4 | Z3B,4 | 6th | 44217 | 44231 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1173 | Check installation of fuel filling for Diesel fire pump fuel tank accordding to the attached sketch. | MECH |  |  | ML | 44217 | 44242 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1174 | Check installation for cladding of duct work inside mechanical room (AHU room) at Ground floor for IC-GF-AHU-01& IC-GF-AHU-02 and IC-GF-AHU-03 accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | GF | 44222 | 44231 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1175 | Check installation for cladding of duct work inside mechanical room (AHU room) at Second floor for IC-2F-AHU-01& IC-2F-AHU-02 and IC-2F-AHU-03 accordding to the attached sketch. | MECH | Z3B,4,5 | Z3B,4,5 | 2nd | 44222 | 44231 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1176 | Check installation for cladding of duct work inside mechanical room (AHU room) at Eighth floor for IC-8F-AHU-01 and IC-8F-AHU-02 accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | 8th | 44222 | 44231 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1177 | Check installation of pressure reducing valve for garbage chute riser at Second basement Z(2,4) accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | B2 | 44222 | 44231 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1178 | Check installation for zone control valve for fire fighting network from Ground to Ninth floor accordding to the attached sketch. | MECH |  |  | ML | 44227 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1179 | Check installation for firefighting pipes Inside elevators core at Second basemnet accordding to the attached sketch. | MECH | Z1,2,3,4,5,6 | Z1,2,3,4,5,6 | B2 | 44229 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1180 | Check installation drainge pipe under ground for Bollard system at ramb Zone (2) according to attached sketch . | MECH | Z2 | Z2 | GF | 44234 | 44242 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1181 | Check installation Plumbing fixture for the Garbage main collection room (First Basment 019,051,006,028) for area Z(2,4) accordding to the attached sketch. | MECH | Z2,4 | Z2,4 | B1 | 44235 | 44242 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1182 | Check first fix for Electrical work for foam system at Generator room for area Z (1,5) accordding to the attached sketch. | MECH | Z1,5 | Z1,5 | GF | 44247 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1183 | Check Installaion and test For Electrical solenoid valve including all accessories Irrigation Net work main line all parts at landscape accordding to the attached sketch. | MECH |  |  | EX | 44249 | 44264 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1184 | Check Installaion and test For gate&air&wash and valve including all accessories and rooms Irrigation Net work main line all parts at landscape accordding to the attached sketch. | MECH |  |  | EX | 44249 | 44264 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1185 | Check Installaion and test For quick coupler for Irrigation Net work at landscape accordding to the attached sketch. | MECH |  |  | EX | 44249 | 44264 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1186 | Check Installaion and test For GR pipes 16MM&sprinklers rotary 5000 Irrigation Net work part (1,2,3,4,5) at landscape accordding to the attached sketch. | MECH |  |  | EX | 44249 | 44264 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1187 | Check Installaion and test For Flow meter&check valve irrigation net work including all accessories for all parts at landscape accordding to the attached sketch. | MECH |  |  | EX | 44249 | 44264 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1188 | Check Installaion and test For Bubbler 120 Litre/HR& 100 Litre/HR irrigation net work including all accessories for all parts at landscape accordding to the attached sketch. | MECH |  |  | EX | 44249 | 44264 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1189 | Check Installaion and test For Automatic controller including Cables 1.5"&2.5" irrigation net work including all accessories for all parts at landscape accordding to the attached sketch. | MECH |  |  | EX | 44249 | 44264 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1190 | Check Installaion and test For UPVC pipes&sleeves irrigation net work for all parts at landscape accordding to the attached sketch. | MECH |  |  | EX | 44249 | 44264 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1191 | Check Installaion and test For master valve for irrigation net work including all accessories for all parts at landscape accordding to the attached sketch. | MECH |  |  | EX | 44249 | 44264 | cancelled
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1192 | check flushing for subsurrface drainge pipe at all parts for landscape accordding to the attached sketch. | MECH |  |  | EX | 44249 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1193 | check quantity and adding chemical treatment (NEUTAZOL) to chilled water system according to attached sketch . | MECH |  |  | B1 | 44252 | 44268 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1194 | check quantity and adding of chemical Second stage (Tapegard) to chilled water system according to attached sketch . | MECH |  |  | ML | 44259 | 44268 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1195 | check insallation mockup for Electric solenoid Valve (2") including filter&regelator and manual valve UPVC operating pressure up to 220 PSI for irrigation net work accordding to the attached sketch. | MECH |  |  | EX | 44262 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1196 | check installation cover and Ladder (Ductile Iron) Sedimentation champer(Subsurface drainge) Quantity (6) at Landscape accordding to the attached sketch. | MECH |  |  | EX | 44262 | 44268 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1197 | Check Installaion and test For Cables Controller 1.5MM 2.5MM irrigation net work including all accessories for all parts at landscape accordding to the attached sketch. | MECH |  |  | EX | 44272 | 44280 | cancelled
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1198 | Check installation of side stream Filter at ETS rooms At First Basement accordding to the attached sketch. | MECH |  |  | B1 | 44279 | 44299 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1199 | Check Second fix Installation for foam system Cables (Generator Room) at Ground Floor for Area Z (1,5) accordding to the attached sketch. | MECH |  |  | GF | 44298 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1200 | Check installation for hose pip At First and Second basement accordding to the attached sketch. | MECH |  |  | ML | 44314 | 44333 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1201 | Check installation for side wall sprinklers inside elevators at Seventh & Ninth Floors accordding to the attached sketch. | MECH |  |  | ML | 44352 | 44369 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1202 | Check installation of insulation and cladding for condensate drain pipes at First&Second Basement accordding to the attached sketch. | MECH |  |  | ML | 44371 | 44405 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1203 | Check startup and check list for saiver AHU from Ground floor To Sixth floor . | MECH |  |  | ML | 44424 | 44438 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1204 | Check startup and check list for Chilled water Pumps At ETS Room At First Basement . | MECH |  |  | B1 | 44424 | 44461 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1205 | Check startup and check list for Pressurization fans . | MECH |  |  | ML | 44439 | 44461 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1206 | Check startup and check list for Car Park Fresh Fans . | MECH |  |  | ML | 44439 | 44461 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1207 | Check startup and check list for Car Park Exhaust Fans . | MECH |  |  | ML | 44439 | 44461 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1208 | Check startup and check list for SMOKE FANS . | MECH |  |  | ML | 44439 | 44461 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1209 | Check Checklist & Startup & Performance for Firefighting Pumps at Second basement for area (Z4) accordding to the attached sketch. | MECH | Z4 | Z4 | B2 | 44481 | 44503 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-MECH-1210 | check installation for foam system at generator rooms zone (1&5) ground floor as per attached sketch. | MECH | Z (1&5) | Z (1&5) | GF | 44525 | 44542 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0001 | Check first fixtion for electrical work in stair core & elevator core at axis (B-E) with axis (15-16) accordding to the attached sketch. | ELEC | Z1 | Z1 | B2 | 43010 | 43278 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0002 | Check first fixtion for electrical work in stair cores at axis (A-D) & (G-J) with axis (2-4) accordding to the attached sketch. | ELEC | Z4,5 | Z4,5 | B2 | 43010 | 43278 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0003 | Check first fixtion for electrical works for elevators cores at axis (D-E) with axis (2-4) accordding to the attached sketch. | ELEC | Z5 | Z5 | B2 | 43010 | 43278 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0004 | CHECH FIRST FIX FOR CONDUITS AND SPACE FOR EARTHING SYSTEM AT AXIS 5 BASEMENT 1 ACCORDIN TO THE ATTACHED SCHECTCH. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43007 | 43010 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0005 | Check first fixtion for electrical works in stairs cores at axis (H-J) with axis (6-8) accordding to the attached sketch. | ELEC | Z4 | Z4 | B2 | 43011 | 43278 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0006 | Check installations for conduits for earthing system and space for foundation earthing in concret wall at axis (3-9) with axis (L) accordding to the attached sketch. | ELEC | Z3A,4 | Z3A,4 | B1 | 43015 | 43417 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0007 | Check first fixtion for electrical work in stair core & elevator core at axis (H-J) with axis (6-9) accordding to the attached sketch. | ELEC | Z3B,4 | Z3B,4 | B1 | 43016 | 43018 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0008 | Check first fixtion for electrical work in ramps at axis (F- L) with axis (7-11) accordding to the attached sketch. | ELEC | Z3 | Z3 | B2 | 43017 | 43027 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0009 | Check first fixtion for electrical work in stair core & elevator core at axis (H-J) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | B2 | 43020 | 43027 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0010 | Check first fixtion for electrical work in elevator core at axis (G-J) with axis (3-4) accordding to the attached sketch. | ELEC | Z4 | Z4 | B2 | 43023 | 43027 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0011 | Check first fixtion for electrical work in STAIR core at axis (B-C with axis (3-4) accordding to the attached sketch. | ELEC | Z5 | Z5 | B2 | 43034 | 43040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0012 | Check installations of down conductor for lightning protection system in concrete column in B1-G according to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43046 | 43053 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0013 | Check first fixation for electrical work in stair cores and core elevator at axis (B-E) with axis (15-17) according to the attached sketch. | ELEC | Z1 | Z1 | B1 | 43046 | 43053 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0014 | Check first fixtion for electrical work in stair cores and core elevator at axis (G- K) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | B1 | 43051 | 43055 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0015 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN B1- G ACCORDING TO THE ATTACHED SHETCH. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43051 | 43055 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0016 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN B1- G ACCORDING TO THE ATTACHED SHETCH. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43053 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0017 | Check first fixation for electrical work in core elevator at axis (G-K) with axis (3-4) according to the attached sketch. | ELEC | Z4 | Z4 | GF | 43053 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0018 | Check first fixation for electrical work in core elevator at axis (G-K) with axis (10-12) according to the attached sketch. | ELEC | Z3 | Z3 | GF | 43053 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0019 | Check first fixation for electrical work in stair core at axis (G-K) with axis (11-13) according to the attached sketch. | ELEC | Z3 | Z3 | GF | 43054 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0020 | Check first fixation for electrical work in stair core at axis (B-D) and (G-J) with axis (3-4) according to the attached sketch. | ELEC | Z4,5 | Z4,5 | GF | 43054 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0021 | Check first fixation for routes for electrical work in concrete ceeiling (lighting and smallpower and light current system) at axis (F-L) with axis (4-8) according to the attached sketch. | ELEC | Z4 | Z4 | GF | 43057 | 43062 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0022 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN B1- G ACCORDING TO THE ATTACHED SHETCH. | ELEC | Z3 | Z3 | B1 | 43060 | 43066 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0023 | check first fixtion for routes for electrical work in concrete ceiling (lighting and smallpower and light current systems) at axis (B-L)with axis (2-6) according to the attached sketch | ELEC | Z4,5 | Z4,5 | GF | 43060 | 43066 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0024 | check instllation of down conductor for lighting protection system in concrete coloumn in first floor according to the attached sketch | ELEC | Z5 | Z5 | 1st | 43060 | 43066 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0025 | Check first fixtion for routes for electrical work in concrete ceiling ( lighting and smallpower and fire alarmand fire evacuation - cctv- data systems ) at axis (F-L) with axis 10 - 18) accordding to the attached sketch. | ELEC | Z2,3 | Z2,3 | GF | 43062 | 43078 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0026 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTING PROTECTION SYSTEM IN CONCRETE COLOUMN IN FIRST FLOOR ACCORDING TO THE ATTACHED SHETCH | ELEC | Z5 | Z5 | 1st | 43065 | 43074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0027 | check first fixtion race way for electrical work in concrete ceiling (fire alarm and fire evacuation -cctv- data system )at axis (F-L) with axis (17-18) according to the attached skettch . | ELEC | Z2 | Z2 | GF | 43066 | 43074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0028 | ckeck first fixtion for race ways for electrical work in concrete ceiling (lighting -small power and telecom systems) at axis (F-L) with axis (15-17) according to the attached sketch . | ELEC | Z2 | Z2 | GF | 43066 | 43074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0029 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A -F) with axis (13 - 16) accordding to the attached sketch. | ELEC | Z1 | Z1 | GF | 43072 | 43078 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0030 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A -F) with axis (16 -18) accordding to the attached sketch. | ELEC | Z1 | Z1 | GF | 43072 | 43078 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0031 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (4 - 7) accordding to the attached sketch. | ELEC | Z4 | Z4 | 1st | 43072 | 43078 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0032 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (7 - 9) accordding to the attached sketch. | ELEC | Z3 | Z3 | 1st | 43073 | 43078 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0033 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN FIRST FLOOR ACCORDING TO THE ATTACHED SHETCH. | ELEC | Z1 | Z1 | 1st | 43073 | 43078 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0034 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN SECOND FLOOR ACCORDING TO THE ATTACHED SHETCH. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43073 | 43078 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0035 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (14 - 18) accordding to the attached sketch. | ELEC | Z2 | Z2 | 1st | 43074 | 43083 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0036 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (10 - 14) accordding to the attached sketch. | ELEC | Z3 | Z3 | 1st | 43074 | 43083 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0037 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (1 - 4) accordding to the attached sketch. | ELEC | Z4 | Z4 | 1st | 43074 | 43083 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0038 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A-F) with axis (1 - 4) accordding to the attached sketch. | ELEC | Z5 | Z5 | 1st | 43074 | 43083 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0039 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (5 - 9) accordding to the attached sketch. | ELEC | Z3 | Z3 | 2nd | 43080 | 43083 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0040 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN SECOND FLOOR ACCORDING TO THE ATTACHED SHETCH. | ELEC | Z1,5 | Z1,5 | 2nd | 43086 | 43090 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0041 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (3-9) accordding to the attached sketch. | ELEC | Z3,4 | Z3,4 | 2nd | 43086 | 43090 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0042 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A - F) with axis (1-6) accordding to the attached sketch. | ELEC | Z5 | Z5 | 2nd | 43086 | 43090 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0043 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN SECOND FLOOR ACCORDING TO THE ATTACHED SHETCH. | ELEC | B1 | B1 | 2nd | 43086 | 43090 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0044 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F - L) with axis (14 - 18) accordding to the attached sketch. | ELEC | Z2 | Z2 | 2nd | 43086 | 43288 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0045 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F - L) with axis (10 - 14) accordding to the attached sketch. | ELEC | Z3A | Z3A | 2nd | 43086 | 43090 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0046 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A - F) with axis (13 - 18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 2nd | 43086 | 43288 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0047 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A - F) with axis (13 - 18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 1st | 43086 | 43090 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0048 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (5-9) accordding to the attached sketch. | ELEC | Z4 | Z4 | 3rd | 43088 | 43104 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0049 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (10-18) accordding to the attached sketch. | ELEC | Z3B,4 | Z3B,4 | 3rd | 43088 | 43104 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0050 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A-C) with axis (1-7) accordding to the attached sketch. | ELEC | Z5 | Z5 | 3rd | 43093 | 43104 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0051 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (14-18) accordding to the attached sketch. | ELEC | Z2 | Z2 | 3rd | 43093 | 43111 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0052 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (10-14) accordding to the attached sketch. | ELEC | Z3A,2 | Z3A,2 | 3rd | 43096 | 43111 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0053 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (4-9) accordding to the attached sketch. | ELEC | Z3B,4 | Z3B,4 | 4th | 43096 | 43111 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0054 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (3-5) accordding to the attached sketch. | ELEC | Z4 | Z4 | 3rd | 43096 | 43111 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0055 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN THIRD FLOOR ACCORDING TO THE CLOUDED ATTACHED SHETCH. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43096 | 43111 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0056 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN FOURTH FLOOR ACCORDING TO THE CLOUDED ATTACHED SHETCH. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43096 | 43120 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0057 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F - L) with axis (10 -18) accordding to the attached sketch. | ELEC | Z2,3A | Z2,3A | 4th | 43101 | 43111 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0058 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A-F) with axis (1 - 5) accordding to the attached sketch. | ELEC | Z5 | Z5 | 4th | 43101 | 43111 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0059 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A-F) with axis (12 - 18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 3rd | 43109 | 43120 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0060 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (1- 5) accordding to the attached sketch. | ELEC | Z5 | Z5 | 4th | 43110 | 43120 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0061 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (5-9) accordding to the attached sketch. | ELEC | Z3B,4 | Z3B,4 | 5th | 43111 | 43129 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0062 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (12-18) accordding to the attached sketch. | ELEC | Z2 | Z2 | 5th | 43111 | 43120 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0063 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A-F) with axis (1-7) accordding to the attached sketch. | ELEC | Z5 | Z5 | 5th | 43114 | 43129 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0064 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A-F) with axis (12-18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 3rd | 43114 | 43129 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0065 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN FIFTH FLOOR ACCORDING TO THE CLOUDED ATTACHED SHETCH. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43118 | 43129 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0066 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (L - F) with axis (1 - 5) accordding to the attached sketch. | ELEC | Z4 | Z4 | 5th | 43121 | 43129 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0067 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (9 - 12) accordding to the attached sketch. | ELEC | Z3B | Z3B | 5th | 43121 | 43129 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0068 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A-C) with axis (14 - 18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 4th | 43121 | 43129 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0069 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (C-F) with axis (14 - 18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 4th | 43123 | 43129 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0070 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems) at axis (F-L) with axis (5 - 7) accordding to the attached sketch. | ELEC | Z4 | Z4 | 6th | 43123 | 43129 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0071 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems) at axis (A-F) with axis (1-7) accordding to the attached sketch. | ELEC | Z5 | Z5 | 6th | 43129 | 43137 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0072 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (1 - 5) accordding to the attached sketch. | ELEC | Z4 | Z4 | 6th | 43129 | 43137 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0073 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN SIX FLOOR ACCORDING TO THE CLOUDED ATTACHED SHETCH. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 6th | 43131 | 43137 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0074 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (12 - 18) accordding to the attached sketch. | ELEC | Z2 | Z2 | 6th | 43131 | 43144 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0075 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A-F) with axis (7 - 9) accordding to the attached sketch. | ELEC | Z3 | Z3 | 6th | 43131 | 43137 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0076 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A-F) with axis (14 - 18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 5th | 43137 | 43144 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0077 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (5-7) accordding to the attached sketch. | ELEC | Z4 | Z4 | 7th | 43138 | 43144 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0078 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (7-9) accordding to the attached sketch. | ELEC | Z3 | Z3 | 7th | 43138 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0079 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (1-5) accordding to the attached sketch. | ELEC | Z4 | Z4 | 7th | 43138 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0080 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F - L) with axis (12 - 15) accordding to the attached sketch. | ELEC | Z2 | Z2 | 7th | 43145 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0081 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F - L) with axis (10 - 12) accordding to the attached sketch. | ELEC | Z3 | Z3 | 7th | 43145 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0082 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (A - F) with axis (13 - 18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 6th | 43145 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0083 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN SEVEN FLOOR ACCORDING TO THE CLOUDED ATTACHED SHETCH. | ELEC | Z2,3,4 | Z2,3,4 | 7th | 43145 | 43156 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0084 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F - L with axis (14 - 18) accordding to the attached sketch. | ELEC | Z2 | Z2 | 7th | 43150 | 43162 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0085 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN EIGHT FLOOR ACCORDING TO THE CLOUDED ATTACHED SHETCH. | ELEC | Z3 | Z3 | 8th | 43155 | 43162 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0086 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F - L )with axis (7 - 9) accordding to the attached sketch. | ELEC | Z3 | Z3 | 8th | 43157 | 43170 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0087 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN NINE FLOOR ACCORDING TO THE CLOUDED ATTACHED SHETCH. | ELEC | Z3 | Z3 | 9th | 43159 | 43170 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0088 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F - L )with axis (10 - 12) accordding to the attached sketch. | ELEC | Z3A | Z3A | 8th | 43159 | 43170 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0089 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F - L )with axis (7 - 9) accordding to the attached sketch. | ELEC | Z3B | Z3B | 8th | 43166 | 43170 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0090 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (10-12) accordding to the attached sketch. | ELEC | Z3A | Z3A | 9th | 43170 | 43183 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0091 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (1-7) accordding to the attached sketch. | ELEC | Z4 | Z4 | 8th | 43172 | 43183 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0092 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (F-L) with axis (18-12) accordding to the attached sketch. | ELEC | Z2 | Z2 | 8th | 43172 | 43183 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0093 | Check first fixtion for race ways for electrical work in slab on grade at axis (A-F) with axis (1-7) accordding to the attached sketch. | ELEC | Z5 | Z5 | B2 | 43185 | 43187 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0094 | Check first fixtion for race ways for electrical work in slabe on grade at axis(A_F) with axis (1_7) accordding to the attached | ELEC | Z5 | Z5 | B2 | 43192 | 43195 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0095 | Check first fixtion for race ways for electrical work in ladders (H-J) with axis (10-12) accordding to the attached sketch | ELEC | Z3A | Z3A | B2 | 43192 | 43195 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0096 | Check first fixtion for race ways for electrical work in ladder at axis (D-F) with axis (3-4) accordding to the attached sketch. | ELEC | Z5 | Z5 | 1st | 43192 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0097 | Check first fixtion for race ways for electrical work in ladder at axis (H_J) with axis (3-4) accordding to the attached sketch. | ELEC | Z4 | Z4 | B1 | 43195 | 43202 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0098 | Check first fixtion for race ways for electrical work in ladder at axis (H_J) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | GF | 43195 | 43202 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0099 | Check first fixtion for race ways for electrical work(small power) in slab on grade at axis (A_F) with axis (17-18) accordding to the attached sketch. | ELEC | Z1 | Z1 | B2 | 43200 | 43202 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0100 | Check first fixtion for race ways for electrical work(small power) in slab on grade at axis (F_G) with axis (17-18) accordding to the attached sketch. | ELEC | Z2 | Z2 | B2 | 43201 | 43208 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0101 | Check first fixtion for race ways for electrical work(small power) in slab on grade at axis (G_K) with axis (14-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | B2 | 43201 | 43208 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0102 | CHECK INSTALLATION OF DOWN CONDUCTOR FOR LIGHTINING PROTECTION SYSTEM IN CONCERT COLOUMN IN ROOF FLOOR ACCORDING TO THE CLOUDED ATTACHED SHETCH. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | RF | 43201 | 43208 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0103 | Check first fixtion for race ways for electrical work (small power) in slab on grade at axis (F_J) with axis (12-14) accordding to the attached sketch. | ELEC | Z2 | Z2 | B2 | 43205 | 43221 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0104 | Check first fixtion for race ways for electrical work (small power) in slab on grade at axis (D_E) with axis (15-16) accordding to the attached sketch. | ELEC | Z1 | Z1 | B2 | 43205 | 43221 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0105 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (H_J) with axis (3-4) accordding to the attached sketch. | ELEC | Z4 | Z4 | 1st | 43206 | 43221 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0106 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (H_J) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | 2nd | 43206 | 43221 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0107 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (B_C) with axis (15-16) accordding to the attached sketch. | ELEC | Z1 | Z1 | 1st | 43206 | 43221 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0108 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (B_C) with axis (3-4) accordding to the attached sketch. | ELEC | Z5 | Z5 | 1st | 43206 | 43221 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0109 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (D_F) with axis (15-16) accordding to the attached sketch. | ELEC | Z1 | Z1 | 1st | 43206 | 43221 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0110 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (E_F) with axis (3-4) accordding to the attached sketch. | ELEC | Z4 | Z4 | 4th | 43207 | 43221 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0111 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (H_J) with axis (11-13) accordding to the attached sketch. | ELEC | Z3B | Z3B | GR | 43209 | 43218 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0112 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (E_F) with axis (15-16) accordding to the attached sketch. | ELEC | Z4 | Z4 | 2nd | 43212 | 43221 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0113 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (E_F) with axis (3-4) accordding to the attached sketch. | ELEC | Z4 | Z4 | 5th | 43212 | 43221 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0114 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (H_J) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | 3rd | 43214 | 43225 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0115 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (B_C) with axis (3-4) accordding to the attached sketch. | ELEC | Z5 | Z5 | 2nd | 43214 | 43225 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0116 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (B_C) with axis (15-16) accordding to the attached sketch. | ELEC | Z1 | Z1 | 2nd | 43214 | 43225 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0117 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (H_J) with axis (7-8) accordding to the attached sketch. | ELEC | Z3B | Z3B | 2nd | 43216 | 43221 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0118 | Check first fixtion for race ways for electrical work(lighting _low current) in ladder at axis (H_J) with axis (3-4) accordding to the attached sketch. | ELEC | Z4 | Z4 | 2nd | 43216 | 43221 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0119 | Check first fixtion for race ways for electrical work(lighting system) in ladder at axis (E_F) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | 2nd | 43216 | 43221 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0120 | Check first fixtion for race ways for electrical work(lighting system_fire alarm) in ladder at axis (B_C) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | 2nd | 43219 | 43226 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0121 | Check first fixtion for race ways for electrical work(lighting system_fire alarm) in ladder at axis (H_J) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | 3rd | 43219 | 43226 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0122 | Check first fixtion for race ways for electrical work(lighting system_fire alarm) in ladder at axis (B_C) with axis (3-4) accordding to the attached sketch. | ELEC | Z5 | Z5 | 3rd | 43221 | 43226 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0123 | Check first fixtion for race ways for electrical work(lighting system_fire alarm) in ladder at axis (H_J) with axis (6-8) accordding to the attached sketch. | ELEC | Z3B | Z3B | 3rd | 43222 | 43229 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0124 | Check first fixtion for race ways for electrical work(lighting system) in Ramb 1 accordding to the attached sketch. | ELEC | RAMP | RAMP | EX | 43222 | 43229 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0125 | Check first fixtion for race ways for electrical work(lighting system) in ladder at axis (E_F) with axis (15-16) accordding to the attached sketch. | ELEC | Z1,2 | Z1,2 | 4th | 43223 | 43229 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0126 | Check first fixtion for race ways for electrical work(lighting system) in ladder at axis (H_J) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | 5th | 43225 | 43229 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0127 | Check first fixtion for race ways for electrical work(lighting system) in ladder at axis (H_J) with axis (3-4) accordding to the attached sketch. | ELEC | Z4 | Z4 | 3rd | 43225 | 43229 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0128 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (B_C) with axis (15-16) accordding to the attached sketch. | ELEC | Z1 | Z1 | 4th | 43226 | 43229 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0129 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (11-13) accordding to the attached sketch. | ELEC | Z3A | Z3A | 3rd | 43226 | 43229 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0130 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (6-8) accordding to the attached sketch. | ELEC | Z3B | Z3B | 4th | 43226 | 43234 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0131 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (B_C) with axis (3-4) accordding to the attached sketch. | ELEC | Z5 | Z5 | 4th | 43226 | 43229 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0132 | Check first fixtion for race ways for electrical work(lighting system) in ladder at axis (E_F) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | 5th | 43228 | 43234 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0133 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (B_C) with axis (15-16) accordding to the attached sketch. | ELEC | Z1 | Z1 | 5th | 43228 | 43234 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0134 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | 6th | 43229 | 43234 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0135 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (3-4) accordding to the attached sketch. | ELEC | Z4 | Z4 | 4th | 43229 | 43234 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0136 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (11-13) accordding to the attached sketch. | ELEC | Z3A | Z3A | 4th | 43230 | 43239 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0137 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (B_C) with axis (3-4) accordding to the attached sketch. | ELEC | Z5 | Z5 | 5th | 43230 | 43239 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0138 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (B_C) with axis (15-16) accordding to the attached sketch. | ELEC | Z1 | Z1 | 6th | 43234 | 43239 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0139 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (6-8) accordding to the attached sketch. | ELEC | Z3B | Z3B | 5th | 43235 | 43239 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0140 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | 7th | 43235 | 43239 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0141 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (3-4) accordding to the attached sketch. | ELEC | Z4 | Z4 | 5th | 43236 | 43246 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0142 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (11-13) accordding to the attached sketch. | ELEC | Z2 | Z2 | 5th | 43236 | 43246 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0143 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (B_C) with axis (3-4) accordding to the attached sketch. | ELEC | Z5 | Z5 | 6th | 43240 | 43246 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0144 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | 8th | 43240 | 43246 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0145 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (6-8) accordding to the attached sketch. | ELEC | Z4 | Z4 | 6th | 43241 | 43246 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0146 | Check first fixtion for (EMT) race ways for electrical work( lighting system)for (Z1,Z2,Z3a) at axis (A_L) with axis (10-18) accordding to the attached sketch. | ELEC | Z1,2,3A | Z1,2,3A | 1st | 43241 | 43246 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0147 | Check first fixtion for (EMT) race ways for electrical work( lighting system) for (Z2) at axis (F_H) with axis (15-16) accordding to the attached sketch. | ELEC | Z2 | Z2 | ML | 43241 | 43246 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0148 | Check first fixtion for (EMT) race ways for electrical work( lighting system) for (Z4) at axis (F_H) with axis (3-4) accordding to the attached sketch. | ELEC | Z4 | Z4 | ML | 43241 | 43250 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0149 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (11-13) accordding to the attached sketch. | ELEC | Z2 | Z2 | 6th | 43244 | 43250 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0150 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (3-4) accordding to the attached sketch. | ELEC | Z2 | Z2 | 6th | 43247 | 43255 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0151 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (6-8) accordding to the attached sketch. | ELEC | Z4 | Z4 | 7th | 43250 | 43263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0152 | Check first fixtion for (EMT) race ways for electrical work( lighting system)for (Z3b,Z4,Z5) at axis (A_L) with axis (1-9) accordding to the attached sketch. | ELEC | Z3B,4,5 | Z3B,4,5 | 1st | 43256 | 43263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0153 | Check first fixtion for (EMT) race ways for electrical work( lighting system)for (Z2) at axis (F_K) with axis (16-18) accordding to the attached sketch. | ELEC | Z2 | Z2 | B1 | 43256 | 43263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0154 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (11-13) accordding to the attached sketch. | ELEC | Z2 | Z2 | 7th | 43261 | 43270 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0155 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (3-4) accordding to the attached sketch. | ELEC | Z4 | Z4 | 7th | 43261 | 43270 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0156 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(0_A) with axis (1_6) accordding to the attached sketch. | ELEC | Z5 | Z5 | B2 | 43274 | 43278 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0157 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(F-J) with axis (3-9),(K-L) with axis (4-6) and (E-G) with axis (1-2) accordding to the attached sketch. | ELEC | Z4,5 | Z4,5 | B2 | 43277 | 43285 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0158 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(0-A) with axis (12-18) accordding to the attached sketch. | ELEC | Z1 | Z1 | B2 | 43277 | 43285 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0159 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (3-4)(Z4)(level 1) accordding to the attached sketch. | ELEC | Z4 | Z4 | 7th | 43286 | 43298 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0160 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (11-12)(Z3a)(level 1) accordding to the attached sketch. | ELEC | Z3A | Z3A | 8th | 43286 | 43298 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0161 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in ladder at axis (H_J) with axis (9-8)(Z3b)(level 2) accordding to the attached sketch. | ELEC | Z3B | Z3B | 8th | 43286 | 43298 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0162 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(A_c) with axis (13_18) accordding to the attached sketch. | ELEC | Z1 | Z1 | B2 | 43289 | 43299 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0163 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and low current systems ) at axis (G-K) with axis (14-16) (Z2)accordding to the attached | ELEC | Z2 | Z2 | 8th | 43290 | 43298 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0164 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(K_L) with axis (9_11) and(F_G) with axis(9_11) accordding to the attached sketch. | ELEC | Z4 | Z4 | B2 | 43290 | 43299 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0165 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(C_E) with axis (13_16) and) accordding to the attached sketch. | ELEC | Z1 | Z1 | B2 | 43291 | 43298 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0166 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(F_L) with axis (13_16) and) accordding to the attached sketch. | ELEC | Z2 | Z2 | B2 | 43291 | 43298 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0167 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(F_G) with axis (9_11) and) accordding to the attached sketch. | ELEC | Z3 | Z3 | B2 | 43292 | 43299 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0168 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(H_K) with axis (10_12) (Z3) accordding to the attached sketch. | ELEC | Z3 | Z3 | B2 | 43296 | 43299 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0169 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in stair at axis (H_J) with axis (3-4)(Z4)(level 2) accordding to the attached sketch. | ELEC | Z4 | Z4 | 7th | 43297 | 43299 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0170 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(B_F) with axis (1_3) (z5) accordding to the attached sketch. | ELEC | Z5 | Z5 | B2 | 43297 | 43299 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0171 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(0_B) with axis (13_18) (z1) accordding to the attached sketch. | ELEC | Z1 | Z1 | B2 | 43297 | 43299 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0172 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(A_F) with axis (16_17) (z1) accordding to the attached sketch. | ELEC | Z1 | Z1 | B2 | 43297 | 43299 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0173 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(A_F) with axis (16_18) (z1) accordding to the attached sketch. | ELEC | Z1 | Z1 | B2 | 43297 | 43299 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0174 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(B_F) with axis (4_6) (z5) accordding to the attached sketch. | ELEC | Z5 | Z5 | B2 | 43297 | 43303 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0175 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(F_H) with axis (4_8) (z3_z4) accordding to the attached sketch. | ELEC | Z3,4 | Z3,4 | B2 | 43298 | 43303 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0176 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in stair at axis (H_J) with axis (12-13)(Z3a)(level 2) accordding to the attached sketch. | ELEC | Z3A | Z3A | 8th | 43298 | 43303 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0177 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(K_L) with axis (5_6) accordding to the attached sketch. | ELEC | Z4 | Z4 | B2 | 43298 | 43303 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0178 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in stair at axis (H_J) with axis (6-8)(Z3b)(level 1) accordding to the attached sketch. | ELEC | Z3B | Z3B | 9th | 43302 | 43314 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0179 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(A_B) with axis (1_5) accordding to the attached sketch. | ELEC | Z5 | Z5 | B2 | 43302 | 43314 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0180 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and telecom systems ) at axis (H-K) with axis (3-4)(Z4) accordding to the attached sketch. | ELEC | Z4 | Z4 | 8th | 43302 | 43314 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0181 | Check first fixtion for race ways for electrical work(small power) in slabe on grade at axis(J_L) with axis (2_4) accordding to the attached sketch. | ELEC | Z4 | Z4 | B2 | 43303 | 43314 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0182 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and light curret systems ) at axis (0-F) with axis (6-10) accordding to the attached sketch. _Lighting Outlets A(47) _Lighting OutletsA1 (5) _Exit Outlets(5) _Small Power Outlets(12) _Fire Alarm Outlets(56) _CCTV Outlets(2) _Access Door (1) _Data outlets(8). | ELEC | Z6 | Z6 | B2 | 43311 | 43314 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0183 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and light curret systems ) at axis (0-F) with axis (9-13) accordding to the attached sketch. _Lighting Outlets A(38) _Lighting OutletsA1 (5) _Exit Outlets(5) _Small Power Outlets(8) _Fire Alarm Outlets(48) _CCTV Outlets(3) _Access Door Outlets (5) _Data outlets(6). | ELEC | Z6 | Z6 | B2 | 43317 | 43321 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0184 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in stair at axis (H_J) with axis (6-8)(Z3b)(level 2) accordding to the attached sketch. _Lighting Outlets A=(2) _Lighting Outlets (S) =(2) _Fire Alarm Outlets =(5) | ELEC | Z3B | Z3B | 9th | 43317 | 43321 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0185 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in stair at axis (H_J) with axis (11-13)(Z3a)(level 1) accordding to the attached sketch. _Lighting Outlets A=(2) _Lighting Outlets (S) =(2) _Fire Alarm Outlets =(3) | ELEC | 3A | 3A | 9th | 43321 | 43325 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0186 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and light curret systems ) at axis (0-F) with axis (6-10) accordding to the attached sketch. _Lighting OutletsA1 (44) _Exit Outlets(6) _Small Power Outlets(8) _Fire Alarm Outlets(43) _Access Door Outlets (2) _Data outlets(9). | ELEC | Z6 | Z6 | B1 | 43324 | 43327 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0187 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting and fire alarm systems)at axis (B-F) with axis (9-10) accordding to the attached sketch. | ELEC | Z6 | Z6 | B1 | 43339 | 43344 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0188 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and light curret systems ) at axis (0-F) with axis (9-13) accordding to the attached sketch. _Lighting Outlets A(38) _Lighting OutletsA1 (5) _Exit Outlets(6) _Small Power Outlets(11) _Fire Alarm Outlets(45) _CCTV Outlets(3) _Access Door Outlets (10) _Data outlets(8). | ELEC | Z6 | Z6 | B1 | 43344 | 43349 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0189 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in stair at axis (H_J) with axis (11-13)(Z3a)(level 1) accordding to the attached sketch. _Lighting Outlets A=(2) _Lighting Outlets (S) =(2) _Fire Alarm Outlets =(3) | ELEC | Z3A | Z3A | 9th | 43345 | 43348 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0190 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in stair at axis (H_J) with axis (6-8)(Z3b)(level 1) accordding to the attached sketch. | ELEC | Z3B | Z3B | 9th | 43347 | 43349 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0191 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and light curret systems ) at axis (0-B) with axis (9-10) accordding to the attached sketch. | ELEC | Z6 | Z6 | B2 | 43369 | 43372 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0192 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in stair at axis (H_J) with axis (06-09)(Z3B)(level 2) accordding to the attached sketch. _Lighting Outlets A=(2) _Lighting Outlets (S) =(2) _Fire Alarm Outlets =(3) | ELEC | Z3B | Z3B | Z3B | 43380 | 43382 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0193 | Check first fixtion for race ways for electrical work in concrete ceiling (lighting - small power and light curret systems ) at axis (0-B) with axis (9-10) accordding to the attached sketch. _Lighting Outlets A( 15) _Lighting Outlets A1(1) _Small Power Outlet _Fire Alarm Outlets(26) _CCTV Outlets(1) _Data outlets(5) . | ELEC | Z3 | Z3 | B1 | 43382 | 43384 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0194 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in stair at axis (H_J) with axis (11-12)(Z3a)(level 1) accordding to the attached sketch. _Lighting Outlets A=(2) _Lighting Outlets (S) =(2) _Fire Alarm Outlets =(3) | ELEC | Z3A | Z3A | 9th | 43382 | 43396 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0195 | Pls Check Installation for Cable Trunks In Basement 1 at axis (0_L) with axis (13_18) ( Zone1,Zone2) according to the attached Clouded sketch. _Cable Trunk Size( 20*10cm)= (460 m) _Cable Trunk size(10*10cm)= (85 m) | ELEC | Z1,2 | Z1,2 | B1 | 43390 | 43396 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0196 | Pls Check Installation for Cable Trunks In Basement 1 at axis (0_L) with axis (2_8)(Zone4,Zone5) according to the attached Clouded sketch. _Cable Trunk Size( 20*10cm)= (421 m) _Cable Trunk size(10*10cm)= (270 m) | ELEC | Z4,5 | Z4,5 | B1 | 43390 | 43396 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0197 | Pls Check Installation for Cable Trunks In Basement 1 at axis (G_K) with axis (8_13)(Zone3) according to the attached Clouded sketch. _Cable Trunk Size( 20*10cm)= (303 m) _Cable Trunk size(10*10cm)= (120 m) | ELEC | Z3 | Z3 | B1 | 43390 | 43396 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0198 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in stair at axis (H_J) with axis (12-13)(Z3a)(level 2) accordding to the attached sketch. _Lighting Outlets A=(2) _Lighting Outlets (S) =(2) _Fire Alarm Outlets =(3) _EMT Race Way In Meter =1950 m | ELEC | Z3A | Z3A | RF | 43405 | 43411 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0199 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in RAMP2 accordding to the attached sketch. _Lighting Outlets =24 _Fire Alarm Outlets =1 -CCTV outlets =1 | ELEC | Z2,4 | Z2,4 | RAMP | 43409 | 43411 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0200 | Check the installation of TWO Generators at Generator rooms in ground floor (zone1&zone5) accordding to the attached sketch. | ELEC | Z1,5 | Z1,5 | GF | 43461 | 43472 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0201 | Check first fix for race ways for electrical work (Power and light Current Systems) at axis (A-F) with axis (9-14) accordding to the attached sketch. | ELEC | Z6 | Z6 | B1 | 43505 | 43509 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0202 | PLS Check first fixation for electrical works For (Power and lighting Systems) In Block Works at axis (A-E) with axis (1-7) Zone 5 accordding to the attached sketch. _one way one gung switch= 48 _ one way one gung switch (wp)=2 _small power outlets =60 _small power outlets (wp)= 2 _ small power duplex outlets =2 | ELEC | Z5 | Z5 | 2nd | 43513 | 43517 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0203 | PLS Check first fixation for electrical works For (Power and lighting Systems) In Block Works at axis (A-E) with axis (13-18) Zone 1 accordding to the attached sketch. _one way one gung switch =48 _ one way one gung switch (wp)=2 _small power outlets=69 _small power (wp)=2 _small powe Duplex =2 | ELEC | Z1 | Z1 | 2nd | 43513 | 43517 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0204 | PLS Check first fixation for electrical works For (Power and light Current Systems) In Block Works at axis (A-L) with axis (10-18) Zone1,2,3a accordding to the attached sketch. -Lighting outlets=103 -power outlets=86 -thermostat outlets=27 -data outlets=36 | ELEC | Z1,2,3A | Z1,2,3A | B1 | 43513 | 43517 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0205 | PLS Check first fixation for electrical works For (Power and light Current Systems) In Block Works at axis (A-L) with axis (1-10) Zone3a,4,5 accordding to the attached sketch. -Lighting outlets=102 -power outlets=85 -thermostat outlets=26 -data outlets=36 | ELEC | Z3B,4,5 | Z3B,4,5 | B1 | 43513 | 43517 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0206 | PLS Check first fixation for electrical works For (Power and light Current Systems) In Block Works at axis (0-L) with axis (10-18) Zone1,2,3a accordding to the attached sketch. -Lighting outlets=77 -power outlets=92 -thermostat outlets=15 -data outlets=25 | ELEC | Z1,2,3A | Z1,2,3A | B2 | 43515 | 43517 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0207 | PLS Check first fixation for electrical works For (Power and light Current Systems) In Block Works at axis (0-L) with axis (1-10) Zone3b,4,5 accordding to the attached sketch. -Lighting outlets=77 -power outlets=92 -thermostat outlets=14 -data outlets=25 | ELEC | Z3B,4,5 | Z3B,4,5 | B2 | 43515 | 43517 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0208 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in transformer room stair at axis (B_C) with axis (13-14) at zone 1 accordding to the attached sketch. _lighting outlets (A)=2 _lighting outlets (s) =2 _fire alarm outlets =2 | ELEC | Z1 | Z1 | B2 | 43515 | 43517 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0209 | Check first fixtion for EMT race way for electrical work(lighting system) in second floor at axis (A_F) with axis (1-6) at zone (Z5) refer to electrical room (ID) accordding to the attached sketch. _normal lighting outlets= 200 _emergency lighting outlets(CB) =11 _exit outlets=7 _PD outlets=21 | ELEC | Z5 | Z5 | 2nd | 43530 | 43534 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0210 | Check first fixtion for EMT race way for electrical work(lighting system) in third floor at axis (F_L) with axis (1-9) at zones (z3b-z4) refer to electrical room (IC) accordding to the attached sketch. _normal lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets=37 | ELEC | Z3B,4 | Z3B,4 | 3rd | 43530 | 43534 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0211 | Check first fixtion for EMT race way for electrical work(lighting system) in third floor at axis (A_F) with axis (1-6) at zone (Z5) refer to electrical room (ID) accordding to the attached sketch. _normal lighting outlets= 179 _emergency lighting outlets(CB) =17 _exit outlets=15 _PD outlets=37 | ELEC | Z5 | Z5 | 3rd | 43534 | 43538 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0212 | Check first fixtion for EMT race way for electrical work(lighting system) in third floor at axis (F_L) with axis (1-9) at zones (z3b-z4) refer to electrical room (IC) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets=37 | ELEC | Z3B,4 | Z3B,4 | 3rd | 43534 | 43538 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0213 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in transformer room stair at axis (B_C) with axis (5-6) at zone 5 accordding to the attached sketch. _lighting outlets (A)=2 _lighting outlets (s) =2 _fire alarm outlets =2 | ELEC | Z5 | Z5 | B2 | 43536 | 43538 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0214 | Check first fixtion for EMT race way for electrical work(lighting system) in first floor at axis (F_L) with axis (1-9) at zones (z3b-z4) refer to electrical room (IC) accordding to the attached sketch. _Normal &emergency lighting outlets =359 _Central battary outlets =23 _PD outlets =37 _Exit outlets= 15 | ELEC | Z3B,4 | Z3B,4 | 1st | 43536 | 43543 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0215 | Check first fixtion for EMT race way for electrical work(lighting system) in first floor at axis (A_F) with axis (1-6) at zone (Z5) refer to electrical room (ID) accordding to the attached sketch. _normal lighting outlets= 179 _emergency lighting outlets(CB) =17 _exit outlets=15 _PD outlets=37 | ELEC | Z5 | Z5 | 1st | 43543 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0216 | Check first fixtion for EMT race way for electrical work(lighting system) in fourth floor at axis (A_F) with axis (13-18) at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _normal lighting outlets= 179 _emergency lighting outlets(CB) =17 _exit outlets=15 _PD outlets=37 | ELEC | Z1 | Z1 | 4th | 43543 | 43549 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0217 | Check first fixtion for EMT race way for electrical work(lighting system) in second floor at axis (F_L) with axis (10-18) at zones (z2-z3a) refer to electrical room (IB) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets=37 | ELEC | Z2,3A | Z2,3A | 2nd | 43543 | 43549 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0218 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (A-E) with axis (13-18) Zone 1 accordding to the attached sketch. _one way one gung switch =40 _ one way one gung switch (wp)=2 _small power outlets=46 _small power (wp)=2 _small powe Duplex =2 _Data outlets =22 _thermostat outlets =26 | ELEC | Z1 | Z1 | 1st | 43545 | 43549 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0219 | PLS Check first fixation for electrical works For (Power, lighting andlight current Systems) In Block Works at axis (F-L) with axis (13-18) Zone 2 accordding to the attached sketch. _one way one gung switch =26 _ one way one gung switch (wp)=6 _small power outlets=48 _small power (wp)=5 _small powe Duplex =4 _data outlets =17 _thermostst outlets =26 | ELEC | Z2 | Z2 | 1st | 43545 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0220 | Check first fixtion for race ways for electrical work(lighting system_fire alarm system) in transformer room stair at axis (B_C) with axis (13-14) at zone 1 accordding to the attached sketch. _lighting outlets (A)=2 _lighting outlets (s) =2 _fire alarm outlets =2 | ELEC | Z1 | Z1 | B1 | 43548 | 43551 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0221 | Check first fixtion for EMT race way for electrical work(lighting system) in third floor at axis (F_L) with axis (10-18) at zones (z2-z3a) refer to electrical room (IB) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets=37 | ELEC | Z2,3A | Z2,3A | 3rd | 43550 | 43555 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0222 | Check first fixtion for EMT race way for electrical work(lighting system) in second floor at axis (A_F) with axis (13-18) at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _normal lighting outlets= 200 _emergency lighting outlets(CB) =11 _exit outlets=7 _PD outlets=21 | ELEC | Z1 | Z1 | 2nd | 43550 | 43555 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0223 | Check first fixtion for race way for EMT electrical work(lighting system) in fourth floor at axis (F_L) with axis (10-18) at zones (z2-z3a) refer to electrical room (IB) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets =37 | ELEC | Z2,3A | Z2,3A | 4th | 43555 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0224 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at secound floor at axis (F-L) with axis (1-7) Zone 4 accordding to the attached sketch. _one way one gung switch =26 _ one way one gung switch (wp)=6 _small power outlets=48 _small power (wp)=5 _small powe Duplex =4 _data outlets =17 _thermostst outlets =26 | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43555 | 43559 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0225 | Check first fixtion for race way for EMT electrical work(lighting system) in sixth floor at axis (F_L) with axis (10-18) at zones (z2-z3a) refer to electrical room (IB) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets =37 | ELEC | Z2,3A | Z2,3A | 6th | 43556 | 43566 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0226 | Check first fixtion for EMT race way for electrical work(lighting system) in sixth floor at axis (F_L) with axis (1-9) at zones (z3b-z4) refer to electrical room (IC) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets=37 | ELEC | Z3B,4 | Z3B,4 | 6th | 43556 | 43563 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0227 | Check first fixtion for EMT race way for electrical work(lighting system) in first floor at axis (A_F) with axis (13-18) at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _normal lighting outlets= 179 _emergency lighting outlets(CB) =17 _exit outlets=15 _PD outlets=37 | ELEC | Z1 | Z1 | 1st | 43563 | 43568 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0228 | Check first fixtion for EMT race way for electrical work(lighting system) in third floor at axis (A_F) with axis (13-18) at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _normal lighting outlets= 179 _emergency lighting outlets(CB) =17 _exit outlets=15 _PD outlets=37 | ELEC | Z1 | Z1 | 3rd | 43566 | 43573 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0229 | Check first fixtion for EMT race way for electrical work(lighting system) in fifth floor at axis (F_L) with axis (1-9) at zones (z3b-z4) refer to electrical room (IC) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets=37 | ELEC | Z3B,4 | Z3B,4 | 5th | 43566 | 43573 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0230 | Check first fixtion for EMT race way for electrical work(lighting system) in fourth floor at axis (F_L) with axis (1-9) at zones (z3b-z4) refer to electrical room (IC) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets=37 | ELEC | Z3B,4 | Z3B,4 | 4th | 43569 | 43573 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0231 | Check first fixtion for EMT race way for electrical work(lighting system) in fourth floor at axis (A_F) with axis (1-6) at zone (Z5) refer to electrical room (ID) accordding to the attached sketch. _normal lighting outlets= 200 _emergency lighting outlets(CB) =11 _exit outlets=7 _PD outlets=21 | ELEC | Z5 | Z5 | 4th | 43569 | 43573 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0232 | Check first fixtion for EMT race way for electrical work(lighting system) in first floor at axis (F_L) with axis (10-18) at zones (z2-z3a) refer to electrical room (IB) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets=37 | ELEC | Z2,3A | Z2,3A | 1st | 43571 | 43579 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0233 | Check first fixtion for EMT race way for electrical work(lighting system) in 5-th floor at axis (A_F) with axis (1-6) at zone (Z5) refer to electrical room (ID) accordding to the attached sketch. _normal lighting outlets= 200 _emergency lighting outlets(CB) =11 _exit outlets=7 _PD outlets=21 | ELEC | Z5 | Z5 | 5th | 43575 | 43579 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0234 | Check first fixtion for EMT race way for electrical work(lighting system) in 7-th floor at axis (F_L) with axis (1-9) at zones (z3b-z4) refer to electrical room (IC) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets=37 | ELEC | Z3B,4 | Z3B,4 | 7th | 43575 | 43579 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0235 | PLS Check first fixation for electrical works For (Power, lighting andlight current Systems) In Block Works at axis (F-L) with axis (7-12) Zone 3 accordding to the attached sketch. _one way one gung switch =26 _ one way one gung switch (wp)=6 _small power outlets=48 _small power (wp)=5 _small powe Duplex =4 _data outlets =17 _thermostst outlets =18 | ELEC | Z3 | Z3 | 1st | 43578 | 43586 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0236 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (F-L) with axis (1-6) Zone 4 accordding to the attached sketch. _one way one gung switch =26 _ one way one gung switch (wp)=6 _small power outlets=48 _small power (wp)=5 _small powe Duplex =4 _data outlets =17 _thermostst outlets =26 | ELEC | Z4 | Z4 | 1st | 43578 | 43586 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0237 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (A-E) with axis (13-18) Zone 1 accordding to the attached sketch. _one way one gung switch =40 _ one way one gung switch (wp)=2 _small power outlets=46 _small power (wp)=2 _small powe Duplex =2 _Data outlets =22 _thermostat outlets =26 | ELEC | Z1 | Z1 | 3rd | 43578 | 43586 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0238 | PLS Check first fixation for electrical works For (Power, lighting andlight current Systems) In Block Works at axis (F-L) with axis (13-18) Zone 2 accordding to the attached sketch. _one way one gung switch =26 _ one way one gung switch (wp)=6 _small power outlets=48 _small power (wp)=5 _small powe Duplex =4 _data outlets =17 _thermostst outlets =26 | ELEC | Z2 | Z2 | 3rd | 43578 | 43586 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0239 | PLS Check first fixation for electrical works For (Power, lighting andlight current Systems) In Block Works at axis (F-L) with axis (7-12) Zone 3 accordding to the attached sketch. _one way one gung switch =26 _ one way one gung switch (wp)=6 _small power outlets=48 _small power (wp)=5 _small powe Duplex =4 _data outlets =17 _thermostst outlets =18 | ELEC | Z3 | Z3 | 2nd | 43601 | 43607 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0240 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (F-L) with axis (1-6) Zone 4 accordding to the attached sketch. _one way one gung switch =26 _ one way one gung switch (wp)=6 _small power outlets=48 _small power (wp)=5 _small powe Duplex =4 _data outlets =17 _thermostst outlets =26 | ELEC | Z4 | Z4 | 2nd | 43601 | 43607 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0241 | PLS Check first fixation for electrical works For (Power and lighting Systems) In Block Works at axis (A-E) with axis (1-7) Zone 5 accordding to the attached sketch. _one way one gung switch= 48 _ one way one gung switch (wp)=2 _small power outlets =60 _small power outlets (wp)= 2 _ small power duplex outlets =2 _thirmostat outlets= 26 | ELEC | Z5 | Z5 | 1st | 43601 | 43611 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0242 | Check first fixtion for race way for EMT electrical work(fire alarm system) in sixth floor at axis (F_L) with axis (10-18) at zones (z2-z3a) accordding to the attached sketch. _fire alarm outlets= 248 | ELEC | Z2,3A | Z2,3A | 6th | 43601 | 43611 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0243 | Check first fixtion for race way for EMT electrical work(fire alarm system) in sixth floor at axis (F_L) with axis (1-9) at zones (z3b-z4) accordding to the attached sketch. _fire alarm outlets= 248 | ELEC | Z3B,4 | Z3B,4 | 6th | 43601 | 43611 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0244 | PLS Check first fixation for electrical works For (Power, lighting andlight current Systems) In Block Works at axis (F-L) with axis (7-12) Zone 3 accordding to the attached sketch. _one way one gung switch =26 _ one way one gung switch (wp)=6 _small power outlets=48 _small power (wp)=5 _small powe Duplex =4 _data outlets =17 _thermostst outlets =18 | ELEC | Z3 | Z3 | 3rd | 43618 | 43632 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0245 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (F-L) with axis (1-6) Zone 4 accordding to the attached sketch. _one way one gung switch =26 _ one way one gung switch (wp)=6 _small power outlets=48 _small power (wp)=5 _small powe Duplex =4 _data outlets =17 _thermostst outlets =26 | ELEC | Z4 | Z4 | 3rd | 43618 | 43632 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0246 | PLS Check first fixation for electrical works For (Power and lighting Systems) In Block Works at axis (A-E) with axis (1-7) Zone 5 accordding to the attached sketch. _one way one gung switch= 48 _ one way one gung switch (wp)=2 _small power outlets =60 _small power outlets (wp)= 2 _ small power duplex outlets =2 | ELEC | Z5 | Z5 | 3rd | 43618 | 43632 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0247 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (A-E) with axis (13-18) Zone 1 accordding to the attached sketch. _one way one gung switch =40 _ one way one gung switch (wp)=2 _small power outlets=46 _small power (wp)=2 _small powe Duplex =2 _Data outlets =22 _thermostat outlets =26 | ELEC | Z1 | Z1 | 4th | 43618 | 43632 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0248 | PLS Check first fixation for electrical works For (Power, lighting andlight current Systems) In Block Works at axis (F-L) with axis (13-18) Zone 2 accordding to the attached sketch. _one way one gung switch =26 _ one way one gung switch (wp)=6 _small power outlets=48 _small power (wp)=5 _small powe Duplex =4 _data outlets =17 _thermostst outlets =26 | ELEC | Z2 | Z2 | 4th | 43618 | 43632 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0249 | PLS Check first fixation for electrical works For (Power, lighting andlight current Systems) In Block Works at axis (F-L) with axis (7-12) Zone 3 accordding to the attached sketch. _one way one gung switch =26 _ one way one gung switch (wp)=6 _small power outlets=48 _small power (wp)=5 _small powe Duplex =4 _data outlets =17 _thermostst outlets =18 | ELEC | Z3 | Z3 | 4th | 43618 | 43632 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0250 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (F-L) with axis (1-6) Zone 4 accordding to the attached sketch. _one way one gung switch =26 _ one way one gung switch (wp)=6 _small power outlets=48 _small power (wp)=5 _small powe Duplex =4 _data outlets =17 _thermostst outlets =26 | ELEC | Z4 | Z4 | 4th | 43618 | 43632 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0251 | PLS Check first fixation for electrical works For (Power and lighting Systems) In Block Works at axis (A-E) with axis (1-7) Zone 5 accordding to the attached sketch. _one way one gung switch= 48 _ one way one gung switch (wp)=2 _small power outlets =60 _small power outlets (wp)= 2 _ small power duplex outlets =2 | ELEC | Z5 | Z5 | 4th | 43618 | 43632 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0252 | Pls Check first fix Installation for Cable Ladder in Basement 1 according to the attached Clouded sketch. _Cable Ladder Size( 60*10cm)= 300 mt _Cable Ladder size(30*10cm)= 40 mt | ELEC | Z1,4,5,6 | Z1,4,5,6 | B1 | 43625 | 43632 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0253 | PLS Check the installation for Distribution Transformers at transformer roms in B1 (Z1,Z5) accordding to the attached sketch. _No.of Transformers = 6 _Rating 1600 k.v.a . | ELEC | Z1,5 | Z1,5 | B1 | 43635 | 43641 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0254 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (F-L) with axis (10-18) Zone 3b,z4 accordding to the attached sketch. _one way one gung switch =46 _ one way one gung switch (wp)=12 _small power outlets=63 _small power (wp)=11 _small powe Duplex =7 _data outlets =28 _thermostst outlets =26 | ELEC | Z3,4 | Z3,4 | 7th | 43636 | 43645 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0255 | Pls Check first fix Installation for Cable Trunks In second floor at axis (0_E) with axis (1_5) ( Zone5) according to the attached Clouded sketch. _2 Cable Trunks(N1&N3) Size( 30*10cm)= (153 m) _GSM Cable Trunk size(10*10cm)= (80 m) _power cable trunk size (20*10) =100 m. | ELEC | Z5 | Z5 | 2nd | 43646 | 43649 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0256 | Pls Check first fix Installation for Cable Trunks In second floor at axis (A_E) with axis (14_18) ( Zone1) according to the attached Clouded sketch. _2 Cable Trunks(N1&N3) Size( 30*10cm)= (192 m) _GSM Cable Trunk size(10*10cm)= (80 m) _power cable trunk size(20*10) =105 m | ELEC | Z1 | Z1 | 2nd | 43646 | 43649 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0257 | PLS Check first fix and set in place to floor boxies at first floor in (Z4) accordding to the attached sketch. | ELEC | Z4 | Z4 | 1st | 43649 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0258 | PLS Check first fix and set in place to floor boxies at second floor in (Z4) at axis(1-5) with axis (f-l) accordding to the attached sketch. | ELEC | Z4 | Z4 | 2nd | 43653 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0259 | PLS Check first fix and set in place to floor boxies at 2-nd floor in (Z5) at axis (A-E) with axis (1-5) accordding to the attached sketch. | ELEC | Z5 | Z5 | 2nd | 43653 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0260 | PLS Check first fix and set in place to floor boxies at first floor in (Z1) at axis (A-E) with axis (12-18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 1st | 43653 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0261 | PLS Check first fix and set in place to floor boxies at first floor in (Z2) at axis (F-L) with axis (14-18) accordding to the attached sketch. | ELEC | Z2 | Z2 | 1st | 43653 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0262 | PLS Check first fix and set in place to floor boxies at first floor in (Z5) at axis (A-F) with axis (1-9) accordding to the attached sketch. | ELEC | Z5 | Z5 | 1st | 43653 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0263 | PLS Check first fix and set in place to floor boxies at first floor in (Z3b) at axis (G-L) with axis (5-9) accordding to the attached sketch. | ELEC | Z3B | Z3B | 1st | 43654 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0264 | PLS Check first fix and set in place to floor boxies at 2-nd floor in (Z1) at axis (A-E) with axis (12-18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 2nd | 43654 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0265 | PLS Check first fix and set in place to floor boxies at 2-nd floor in (Z2) at axis (F-L) with axis (14-18) accordding to the attached sketch. | ELEC | Z2 | Z2 | 2nd | 43654 | 43661 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0266 | PLS Check second fix for medium voltage cables at B1 floor from medium voltage room to transformer rooms accordding to the attached sketch. _Cable lengths =3400 m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43654 | 43661 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0267 | PLS Check first fix and set in place to floor boxies at first floor in (Z3A) at axis (F-G) with axis (10-12) accordding to the attached sketch. | ELEC | Z3A | Z3A | 1st | 43661 | 43668 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0268 | PLS Check first fix and set in place to floor boxies at 2-nd floor in (Z3A) at axis (F-G) with axis (10-12) accordding to the attached sketch. | ELEC | Z3A | Z3A | 2nd | 43661 | 43668 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0269 | PLS Check first fix and set in place to floor boxies at 2-nd floor in (Z3B) at axis (G-L) with axis (5-9) accordding to the attached sketch. | ELEC | Z3B | Z3B | 2nd | 43661 | 43668 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0270 | PLS Check first fix and set in place to floor boxies at 3-rd floor in (Z5) at axis (A-E) with axis (1-5) accordding to the attached sketch. | ELEC | Z5 | Z5 | 3rd | 43663 | 43668 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0271 | PLS Check first fix and set in place to floor boxies at third floor in (Z4) at axis(1-6) with axis (f-l) accordding to the attached sketch. | ELEC | Z4 | Z4 | 3rd | 43663 | 43668 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0272 | PLS Check first fix and set in place to floor boxies at 3-rd floor in (Z3b) at axis (G-L) with axis (6-9) accordding to the attached sketch. | ELEC | Z3B | Z3B | 3rd | 43663 | 43668 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0273 | PLS Check first fix and set in place to floor boxies at 3-rd floor in (Z2) at axis (F-L) with axis (13-18) accordding to the attached sketch. | ELEC | Z2 | Z2 | 3rd | 43663 | 43668 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0274 | PLS Check first fix and set in place to floor boxies at 3-rd floor in (Z3a) at axis (F-G) with axis (7-9) accordding to the attached sketch. | ELEC | Z3A | Z3A | 3rd | 43667 | 43671 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0275 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (F-L) with axis (7-10) Zone 3a accordding to the attached sketch. _one way one gung switch =28 _ one way one gung switch (wp)=9 _small power outlets=38 _small power(wp)=6 _small powe Duplex =3 _data outlets =18 _thermostst outlets =17 | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 8th | 43667 | 43671 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0276 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (F-L) with axis (10-12) Zone 3b accordding to the attached sketch. _one way one gung switch =29 _ one way one gung switch (wp)=7 _small power outlets=32 _small power (wp)=7 _small powe Duplex =3 _data outlets =14 _thermostst outlets =11 | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 8th | 43667 | 43671 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0277 | PLS Check first fix and set in place to floor boxies at 3-rd floor in (Z1) at axis (A-E) with axis (12-18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 3rd | 43670 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0278 | PLS Check first fix and set in place to floor boxies at 5-th floor in (Z4) at axis(1-6) with axis (f-l) accordding to the attached sketch. | ELEC | Z4 | Z4 | 5th | 43670 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0279 | PLS Check first fix and set in place to floor boxies at 5-th floor in (Z3b) at axis (G-L) with axis (6-9) accordding to the attached sketch. | ELEC | Z3B | Z3B | 5th | 43670 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0280 | PLS Check first fix and set in place to floor boxies at 5-th floor in (Z5) at axis (A-E) with axis (1-5) accordding to the attached sketch. | ELEC | Z5 | Z5 | 5th | 43673 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0281 | PLS Check first fix and set in place to floor boxies at 4-th floor in (Z1) at axis (A-E) with axis (12-18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 4th | 43673 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0282 | PLS Check first fix and set in place to floor boxies at 4-th floor in (Z1) at axis (A-E) with axis (12-18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 4th | 43674 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0283 | PLS Check first fix and set in place to floor boxies at 4-th floor in (Z2) at axis (F-L) with axis (13-18) accordding to the attached sketch. | ELEC | Z2 | Z2 | 4th | 43674 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0284 | Pls Check first fix Installation for Cable Trunks In 2-nd floor at axis (f_l) with axis (1_6) ( Zone4) according to the attached Clouded sketch. _2 Cable Trunks(N1&N3) Size( 30*10cm)= (192 m) _GSM Cable Trunk size(10*10cm)= (80 m) _power cable trunk size(20*10) =105 m | ELEC | Z4 | Z4 | 2nd | 43676 | 43684 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0285 | Pls Check first fix Installation for Cable Trunks In 2-nd floor at axis (f_l) with axis (13_18) ( Zone2) according to the attached Clouded sketch. _2 Cable Trunks(N1&N3) Size( 30*10cm)= (192 m) _GSM Cable Trunk size(10*10cm)= (80 m) _power cable trunk size(20*10) =105 m | ELEC | Z2 | Z2 | 2nd | 43676 | 43684 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0286 | Pls Check first fix Installation for Cable Trunks In first floor at axis (f_l) with axis (10_13) ( Zone3a) according to the attached Clouded sketch. _2 Cable Trunks(N1&N3) Size( 30*10cm)= (110 m) _GSM Cable Trunk size(10*10cm)= (60 m) _power cable trunk size(20*10) =80 m | ELEC | Z3A | Z3A | 1st | 43676 | 43684 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0287 | Pls Check first fix Installation for Cable Trunks In first floor at axis (f_l) with axis (6_9) ( Zone3b) according to the attached Clouded sketch. _2 Cable Trunks(N1&N3) Size( 30*10cm)= (90 m) _GSM Cable Trunk size(10*10cm)= (70 m) _power cable trunk size(20*10) =85 m | ELEC | Z3B | Z3B | 1st | 43676 | 43684 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0288 | PLS Check first fix and set in place to floor boxies at 4-th floor in (Z3a) at axis (F-G) with axis (7-9) accordding to the attached sketch. | ELEC | Z3A | Z3A | 4th | 43678 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0289 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (F-L) with axis (9-18) Zone 2,3a 7-th floor accordding to the attached sketch. _one way one gung switch =46 _ one way one gung switch (wp)=12 _small power outlets=63 _small power (wp)=11 _small powe Duplex =7 _data outlets =28 _thermostst outlets =26 | ELEC | Z2,3A | Z2,3A | 7th | 43678 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0290 | PLS Check first fix and set in place to floor boxies at 5-th floor in (Z1) at axis (A-E) with axis (12-18) accordding to the attached sketch. | ELEC | Z1 | Z1 | 5th | 43682 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0291 | PLS Check first fix and set in place to floor boxies at 5-th floor in (Z2) at axis (F-L) with axis (13-18) accordding to the attached sketch. | ELEC | Z2 | Z2 | 5th | 43682 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0292 | PLS Check first fix and set in place to floor boxies at 5-th floor in (Z3a) at axis (F-G) with axis (7-9) accordding to the attached sketch | ELEC | Z3A | Z3A | 5th | 43682 | 43699 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0293 | Check first fixtion for race way for EMT electrical work(fire alarm system) in first floor at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _fire alarm outlets= 218 . | ELEC | Z1,2,3A | Z1,2,3A | 1st | 43697 | 43705 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0294 | Check first fixtion for race way for EMT electrical work(fire alarm system) in first floor at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch._fire alarm outlets= 220. | ELEC | Z3B,4,5 | Z3B,4,5 | 1st | 43697 | 43705 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0295 | Check first fixtion for race way for EMT electrical work(fire alarm system) in 2-nd floor at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch._fire alarm outlets= 218 . | ELEC | Z1,2,3A | Z1,2,3A | 2nd | 43697 | 43705 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0296 | Check first fixtion for race way for EMT electrical work(fire alarm system) in 2-nd floor at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch._fire alarm outlets= 223. | ELEC | Z3B,4,5 | Z3B,4,5 | 2nd | 43697 | 43705 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0297 | Check first fixtion for race way for EMT electrical work(fire alarm system) in 3-rd floor at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _fire alarm outlets= 446 . | ELEC | Z1,2,3A | Z1,2,3A | 3rd | 43705 | 43713 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0298 | Check first fixtion for race way for EMT electrical work(fire alarm system) in 3-rd floor at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch. _fire alarm outlets= 402. | ELEC | Z3B,4,5 | Z3B,4,5 | 3rd | 43705 | 43713 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0299 | Check first fixtion for race way for EMT electrical work(fire alarm system) in 4-th floor at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _fire alarm outlets= 459 . | ELEC | Z1,2,3A | Z1,2,3A | 4th | 43705 | 43713 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0300 | Check first fixtion for race way for EMT electrical work(fire alarm system) in 4-th floor at axis (A_L) with axis (1-9) at zones (z3b-z4-z5) accordding to the attached sketch. _fire alarm outlets= 453 . | ELEC | Z3B,4,5 | Z3B,4,5 | 4th | 43705 | 43713 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0301 | Check first fixtion for race way for EMT electrical work(fire alarm system) in 5-th floor at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _fire alarm outlets= 459 . | ELEC | Z1,2,3A | Z1,2,3A | 5th | 43705 | 43713 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0302 | Check first fixtion for race way for EMT electrical work(fire alarm system) in 5-th floor at axis (A_L) with axis (1-9) at zones (z3b-z4-z5) accordding to the attached sketch. _fire alarm outlets= 402 . | ELEC | Z3B,4,5 | Z3B,4,5 | 5th | 43705 | 43713 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0303 | Check first fixtion for race way for EMT electrical work(fire alarm system) in 7-th floor at axis (F_L) with axis (10-18) at zones (z2-z3a) accordding to the attached sketch. _fire alarm outlets= 265 . | ELEC | Z2,3A | Z2,3A | 7th | 43705 | 43713 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0304 | Check first fixtion for race way for EMT electrical work(fire alarm system) in 7-th floor at axis (F_L) with axis (1-10) at zones (z3b-4) accordding to the attached sketch. _fire alarm outlets= 263 . | ELEC | Z3B,4 | Z3B,4 | 7th | 43705 | 43713 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0305 | Check first fixtion for race way for EMT electrical work(fire alarm system) in 8-th floor at axis (F_L) with axis (1-18) at zones (z2-z3-4) accordding to the attached sketch. _fire alarm outlets= 295 . | ELEC | Z2,3,4 | Z2,3,4 | 8th | 43705 | 43713 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0306 | Check first fixtion for race way for EMT electrical work(fire alarm system) in 9-th floor at axis (F_L) with axis (1-18) at zones (z3) accordding to the attached sketch. _fire alarm outlets= 210 . | ELEC | Z3 | Z3 | 9th | 43705 | 43713 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0307 | Check first fixtion for race way for EMT electrical work(fire alarm system) in Ground floor floor at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _fire alarm outlets= 302 . | ELEC | Z1,2,3A | Z1,2,3A | GF | 43705 | 43715 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0308 | Check first fixtion for race way for EMT electrical work(fire alarm system) in Ground floor at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch. _fire alarm outlets= 304. | ELEC | Z3B,4,5 | Z3B,4,5 | GF | 43705 | 43715 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0309 | Check first fixtion for race way for EMT electrical work(fire alarm system) in B1 floor floor at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _fire alarm outlets= 302 . | ELEC | Z1,2,3A | Z1,2,3A | B1 | 43705 | 43715 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0310 | Check first fixtion for race way for EMT electrical work(fire alarm system) in B1 floor at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch. _fire alarm outlets= 304. | ELEC | Z3B,4,5 | Z3B,4,5 | B1 | 43705 | 43715 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0311 | Check first fixtion for race way for EMT electrical work(fire alarm system) in B2 floor floor at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _fire alarm outlets= 302 . | ELEC | Z1,2,3A | Z1,2,3A | B2 | 43705 | 43715 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0312 | Check first fixtion for race way for EMT electrical work(fire alarm system) in B2 floor at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch. _fire alarm outlets= 305. | ELEC | Z3B,4,5 | Z3B,4,5 | B2 | 43705 | 43715 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0313 | Check first fixtion for EMT race way for electrical work(lighting system) in 7-th floor at axis (F_L) with axis (9-18) at zones (z2-3a) refer to electrical room (IB) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets=37 | ELEC | Z2,3A | Z2,3A | 7th | 43706 | 43717 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0314 | Check first fixtion for EMT race way for electrical work(lighting system) in 8-th floor at axis (F_L) with axis (7-12) at zones (3) refer to electrical room (IB) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets=37 | ELEC | Z3 | Z3 | 8th | 43706 | 43713 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0315 | Check first fixtion for EMT race way for electrical work(lighting system) in 9-th floor at axis (F_L) with axis (7-12) at zone (3) refer to electrical room (IB) accordding to the attached sketch. _normal &emergency lighting outlets=256 _emergency lighting outlets(CB) = 25 _exit outlets=15 _PD outlets=37 | ELEC | Z3 | Z3 | 9th | 43706 | 43717 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0316 | Check first fixtion for EMT race way for electrical work(lighting system) in Ground floor at axis (A_F) with axis (13-18) at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _normal lighting outlets= 179 _emergency lighting outlets(CB) =17 _exit outlets=15 _PD outlets=37 | ELEC | Z1 | Z1 | GF | 43706 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0317 | Check first fixtion for EMT race way for electrical work(lighting system) in Ground floor at axis (F_L) with axis (10-18) at zones (z2-z3a) refer to electrical room (IB) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets=37 | ELEC | Z2,3A | Z2,3A | GF | 43706 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0318 | Check first fixtion for EMT race way for electrical work(lighting system) in Ground Floor at axis (F_L) with axis (1-9) at zones (z3b-z4) refer to electrical room (IC) accordding to the attached sketch. _Normal &emergency lighting outlets =359 _Central battary outlets =23 _PD outlets =37 _Exit outlets= 15 | ELEC | Z3B,4 | Z3B,4 | GF | 43706 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0319 | Check first fixtion for EMT race way for electrical work(lighting system) in Ground floor at axis (A_F) with axis (1-6) at zone (Z5) refer to electrical room (ID) accordding to the attached sketch. _normal lighting outlets= 179 _emergency lighting outlets(CB) =17 _exit outlets=15 _PD outlets=37 | ELEC | Z5 | Z5 | GF | 43706 | 43717 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0320 | Check first fixtion for EMT race way for electrical work(lighting system) in B1 floor at axis (A_F) with axis (13-18) at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _normal lighting outlets= 118 _emergency lighting outlets(CB) =106 _emergency outlets=67 . | ELEC | Z1 | Z1 | B1 | 43706 | 43717 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0321 | Check first fixtion for EMT race way for electrical work(lighting system) in B1 floor at axis (F_L) with axis (10-18) at zones (z2-z3a) refer to electrical room (IB) accordding to the attached sketch. _normal &emergency lighting outlets= 105 _emergency lighting outlets(CB) =65 _Emergency outlets=108 | ELEC | Z2,3A | Z2,3A | B1 | 43706 | 43717 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0322 | Check first fixtion for EMT race way for electrical work(lighting system) in B1 Floor at axis (F_L) with axis (1-9) at zones (z3b-z4) refer to electrical room (IC) accordding to the attached sketch. _Normal &emergency lighting outlets =129 _Central battary outlets =111 _Emergency outlets= 72 . | ELEC | Z3B,4 | Z3B,4 | B1 | 43706 | 43717 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0323 | Check first fixtion for EMT race way for electrical work(lighting system) in B1 floor at axis (A_F) with axis (1-6) at zone (Z5) refer to electrical room (ID) accordding to the attached sketch. _normal lighting outlets= 179 _emergency lighting outlets(CB) =118 _Emergency outlets=108 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43706 | 43717 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0324 | Check first fixtion for EMT race way for electrical work(lighting system) in B2 floor at axis (A_F) with axis (13-18) at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _normal lighting outlets= 143 _emergency lighting outlets(CB) =78 _emergency outlets=67 . | ELEC | Z1 | Z1 | B2 | 43706 | 43723 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0325 | Check first fixtion for EMT race way for electrical work(lighting system) in B2 floor at axis (F_L) with axis (10-18) at zones (z2-z3a) refer to electrical room (IB) accordding to the attached sketch. _normal &emergency lighting outlets= 159 _emergency lighting outlets(CB) =72 _Emergency outlets=95 | ELEC | Z2,3A | Z2,3A | B2 | 43706 | 43723 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0326 | Check first fixtion for EMT race way for electrical work(lighting system) in B2 Floor at axis (F_L) with axis (1-9) at zones (z3b-z4) refer to electrical room (IC) accordding to the attached sketch. _Normal &emergency lighting outlets =129 _Central battary outlets =111 _Emergency outlets= 72 . | ELEC | Z3B,4 | Z3B,4 | B2 | 43706 | 43723 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0327 | Check first fixtion for EMT race way for electrical work(lighting system) in B2 floor at axis (A_F) with axis (1-6) at zone (Z5) refer to electrical room (ID) accordding to the attached sketch. _normal lighting outlets= 166 _emergency lighting outlets(CB) =80 _Emergency outlets=78 . | ELEC | Z5 | Z5 | B2 | 43706 | 43723 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0328 | Pls Check first fix Installation for Cable Trunks In Basement 2 at axis (0_L) with axis (12_18) ( Zone1,Zone2) according to the attached Clouded sketch. _Cable Trunk Size( 20*10cm)= (760 m) _Cable Trunk size(10*10cm)= (370 m) | ELEC | Z1,2 | Z1,2 | B2 | 43706 | 43717 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0329 | Pls Check first fix Installation for Cable Trunks In Basement 2 at axis (0_L) with axis (8_11) (Zone3) according to the attached Clouded sketch. _Cable Trunk Size( 20*10cm)= (550 m) _Cable Trunk size(10*10cm)= (200 m) | ELEC | Z3 | Z3 | B2 | 43706 | 43717 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0330 | Pls Check Installation for Cable Trunks In Basement 2 at axis (A_L) with axis (1_8)(Zones 4,5) according to the attached Clouded sketch. _Cable Trunk Size( 20*10cm)= (730 m) _Cable Trunk size(10*10cm)= (320 m) | ELEC | Z4,5 | Z4,5 | B2 | 43706 | 43717 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0331 | PLS Check the installation For ATS Pannels at B1 floor in (Z5), (Z1) inside MDB rooms accordding to the attached sketch at Main low voltage rooms. _No. of pannels =4 . | ELEC | Z5 | Z5 | B1 | 43706 | 43713 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0332 | Check first fixtion for race way for EMT electrical work(Power for HVAC system) in 2-nd floor at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _Hvac outlets= 96 . | ELEC | Z1,2,3A | Z1,2,3A | 2nd | 43710 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0333 | Check first fixtion for race way for EMT electrical work(Power For Hvac system) in 2-nd floor at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch. _HVAC outlets= 96. | ELEC | Z3B,4,5 | Z3B,4,5 | 2nd | 43710 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0334 | Check first fixtion for race way for EMT electrical work(Power for Hvac system) in 3-rd floor at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _Hvac outlets= 96 . | ELEC | Z1,2,3A | Z1,2,3A | 3rd | 43710 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0335 | Check first fixtion for race way for EMT electrical work(Power for Hvac system) in 3-rd floor at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch. _Hvac outlets= 96. | ELEC | Z3B,4,5 | Z3B,4,5 | 3rd | 43710 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0336 | PLS Check first fix and set in place to floor boxies at 4-th floor in (Z3b) at axis (G-L) with axis (6-9) accordding to the attached sketch. | ELEC | Z3B | Z3B | 4th | 43710 | 43723 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0337 | PLS Check first fix and set in place to floor boxies at fourth floor in (Z4) at axis(1-6) with axis (f-l) accordding to the attached sketch. | ELEC | Z4 | Z4 | 4th | 43710 | 43723 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0338 | PLS Check first fix and set in place to floor boxies at 3-rd floor in (Z5) at axis (A-E) with axis (1-5) accordding to the attached sketch. | ELEC | Z5 | Z5 | 3rd | 43710 | 43723 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0339 | Check first fixtion for race way for EMT electrical work(Power for Hvac system) in 1-st floor at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _Hvac outlets= 70 . | ELEC | Z1,2,3A | Z1,2,3A | 1st | 43710 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0340 | Check first fixtion for race way for EMT electrical work(Power Hvac system) in 1-st floor at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch. _Hvac outlets= 70. | ELEC | Z3B,4,5 | Z3B,4,5 | 1st | 43710 | 43723 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0341 | Check first fixtion for race way for EMT electrical work(Power for Hvac system) in 4-th floor at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _Hvac outlets= 96 . | ELEC | Z1,2,3A | Z1,2,3A | 4th | 43710 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0342 | Check first fixtion for race way for EMT electrical work(Power for Hvac system) in 4-th floor at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch. _Hvac outlets= 96. | ELEC | Z3B,4,5 | Z3B,4,5 | 4th | 43710 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0343 | Check first fixtion for race way for EMT electrical work(Power for Hvac system) in 5-th floor at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _Hvac outlets= 92 . | ELEC | Z1,2,3A | Z1,2,3A | 5th | 43710 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0344 | Check first fixtion for race way for EMT electrical work(Power for Hvac system) in 5-th floor at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch. _Hvac outlets= 90. | ELEC | Z3B,4,5 | Z3B,4,5 | 5th | 43710 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0345 | Check fixation for Earthing System Main Grade in Ground floor at axis (0_L) with axis (0-1) at zones (z4,5) accordding to the attached sketch. _Earthing Rods no.=13 _Cable Size 240 mm=110 m _Cable Size 95 mm=110 m . | ELEC | Z4,5 | Z4,5 | GF | 43717 | 43723 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0346 | Check first fixtion for race way for EMT electrical work(Power for Hvac system) in 7-th floor at axis (F_L) with axis (10-18) at zones (z2-z3a) accordding to the attached sketch. _Hvac outlets= 48 . | ELEC | Z2,3A | Z2,3A | 7th | 43732 | 43737 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0347 | Check first fixtion for race way for EMT electrical work(Power for Hvac system) in 7-th floor at axis (F_L) with axis (1-9) at zones (z3b-z4) accordding to the attached sketch. _Hvac outlets= 48. | ELEC | Z3B,4 | Z3B,4 | 7th | 43732 | 43737 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0348 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (A-E) with axis (13-18) Zone 1 accordding to the attached sketch. _Lighting switchs =52 _small power outlets=55 _Data outlets =6 _Telephone outlets=7 _thermostat outlets =30 | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43737 | 43741 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0349 | PLS Check first fixation for electrical works For (Power, lighting andlight current Systems) In Block Works at axis (F-L) with axis (13-18) Zone 2 accordding to the attached sketch. _Lighting switches=52. _small power outlets= 55 . _H.D outlets=4 _data outlets =17. _Telephone outlets=7 . _thermostst outlets =30 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43737 | 43741 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0350 | Pls Check first fix Installation for Cable Trunks In 3-rd floor at axis (f_l) with axis (6_9) ( Zone3b) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (90 m) _GSM Cable Trunk size(10*10cm)= (70 m) | ELEC | Z3B | Z3B | 3rd | 43743 | 43750 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0351 | Pls Check first fix Installation for Cable Trunks In 3-rd floor at axis (f_l) with axis (1_6) ( Zone4) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (197 m) _GSM Cable Trunk size(10*10cm)= (78 m) | ELEC | Z4 | Z4 | 3rd | 43743 | 43750 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0352 | Pls Check first fix Installation for Cable Trunks In 3-rd floor at axis (0_E) with axis (1_5) ( Zone5) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (153 m) _GSM Cable Trunk size(10*10cm)= (80 m) | ELEC | Z5 | Z5 | 3rd | 43743 | 43750 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0353 | Check fixation for Main Grade Earthing System in Ground floor at axis (A_L) with axis (17-18) at zones (z1,2) accordding to the attached sketch. _Earthing Rods no.=12 _Cable Size 240 mm=110 m _Cable Size 95 mm=110 m . | ELEC | Z1,2 | Z1,2 | GF | 43744 | 43752 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0354 | Pls Check first fix Installation for Cable Trunks In 3-rd floor at axis (A_E) with axis (14_18) ( Zone1) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (192 m) _GSM Cable Trunk size(10*10cm)= (80 m) | ELEC | Z1 | Z1 | 3rd | 43746 | 43752 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0355 | Pls Check first fix Installation for Cable Trunks In 3-rd floor at axis (f_l) with axis (13_18) ( Zone2) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (192 m) _GSM Cable Trunk size(10*10cm)= (80 m) | ELEC | Z2 | Z2 | 3rd | 43746 | 43752 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0356 | Pls Check first fix Installation for Cable Trunks In 3-rd floor at axis (f_l) with axis (10_13) ( Zone3a) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (110 m) _GSM Cable Trunk size(10*10cm)= (60 m) | ELEC | Z3A | Z3A | 3rd | 43746 | 43752 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0357 | Pls Check first fix Installation for Cable Trunks In fourth floor at axis (A_E) with axis (14_18) ( Zone1) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (195 m) _GSM Cable Trunk size(10*10cm)= (86 m) _power cable trunk size(20*10) =108 m | ELEC | Z1 | Z1 | 4th | 43746 | 43752 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0358 | Pls Check first fix Installation for Cable Trunks In fourth floor at axis (f_l) with axis (13_18) ( Zone2) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (192 m) _GSM Cable Trunk size(10*10cm)= (80 m) _power cable trunk size(20*10) =105 m | ELEC | Z2 | Z2 | 4th | 43746 | 43752 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0359 | Pls Check first fix Installation for Cable Trunks In fourth floor at axis (f_l) with axis (10_13) ( Zone3a) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (110 m) _GSM Cable Trunk size(10*10cm)= (60 m) _power cable trunk size(20*10) =80 m | ELEC | Z3A | Z3A | 4th | 43746 | 43752 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0360 | Pls Check first fix Installation for Cable Trunks In fourth floor at axis (f_l) with axis (6_9) ( Zone3b) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (90 m) _GSM Cable Trunk size(10*10cm)= (70 m) _power cable trunk size(20*10) =85 m | ELEC | Z3B | Z3B | 4th | 43746 | 43750 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0361 | Pls Check first fix Installation for Cable Trunks In fourth floor at axis (f_l) with axis (1_6) ( Zone4) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (192 m) _GSM Cable Trunk size(10*10cm)= (80 m) _power cable trunk size(20*10) =105 m | ELEC | Z4 | Z4 | 4th | 43746 | 43750 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0362 | Pls Check first fix Installation for Cable Trunks In fourth floor at axis (0_E) with axis (1_5) ( Zone5) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (153 m) _GSM Cable Trunk size(10*10cm)= (80 m) _power cable trunk size (20*10) =100 m. | ELEC | Z5 | Z5 | 4th | 43746 | 43750 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0363 | Pls Check first fix Installation for Cable Trunks In first floor at axis (A_E) with axis (14_18) ( Zone1) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (195 m) _GSM Cable Trunk size(10*10cm)= (86 m) _power cable trunk size(20*10) =108 m | ELEC | Z1 | Z1 | 1st | 43747 | 43752 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0364 | Pls Check first fix Installation for Cable Trunks In first floor at axis (f_l) with axis (13_18) ( Zone2) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (192 m) _GSM Cable Trunk size(10*10cm)= (80 m) _power cable trunk size(20*10) =105 m | ELEC | Z2 | Z2 | 1st | 43747 | 43752 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0365 | Pls Check first fix Installation for Cable Trunks In first floor at axis (f_l) with axis (10_13) ( Zone3a) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (110 m) _GSM Cable Trunk size(10*10cm)= (60 m) _power cable trunk size(20*10) =80 m | ELEC | Z3A | Z3A | 1st | 43747 | 43752 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0366 | Pls Check first fix Installation for Cable Trunks In first floor at axis (f_l) with axis (6_9) ( Zone3b) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (90 m) _GSM Cable Trunk size(10*10cm)= (70 m) _power cable trunk size(20*10) =85 m | ELEC | Z3B | Z3B | 1st | 43747 | 43752 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0367 | Pls Check first fix Installation for Cable Trunks In first floor at axis (f_l) with axis (1_6) ( Zone4) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (192 m) _GSM Cable Trunk size(10*10cm)= (80 m) _power cable trunk size(20*10) =105 m | ELEC | Z4 | Z4 | 1st | 43747 | 43752 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0368 | Pls Check first fix Installation for Cable Trunks In first floor at axis (0_E) with axis (1_5) ( Zone5) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (153 m) _GSM Cable Trunk size(10*10cm)= (80 m) _power cable trunk size (20*10) =100 m. | ELEC | Z5 | Z5 | 1st | 43747 | 43752 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0369 | PLS Check first fix and set in place to floor boxies at 6-th floor in (Z2,3a) at axis (F-L) with axis (10-18) accordding to the attached sketch. | ELEC | Z2,3A | Z2,3A | 6th | 43753 | 43758 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0370 | PLS Check first fixation for electrical works For (Power, lighting andlight current Systems) In Block Works at axis (F-L) with axis (10-18) Zone 2,3a accordding to the attached sketch. _Lighting switches=68. _small power outlets= 56 . _H.D outlets=4 _data outlets =28. _Telephone outlets=14 . _thermostst outlets =48 . | ELEC | Z2,3A | Z2,3A | 6th | 43753 | 43758 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0371 | Check first fixtion for race way cable tray (Power for mcc) at 1-st floor z1,2,3a at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _cable tray size(10*10cm)= 65 m . _ cable tray size(20*10cm)=25 m | ELEC | Z1,2,3A | Z1,2,3A | 1st | 43754 | 43758 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0372 | Check first fixtion for race way cable tray (power for mcc) in 1-st floor at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch. _cable tray size (10*10 cm)=25 m. _cable tray size(20*10cm)=6 m . | ELEC | Z3B,4,5 | Z3B,4,5 | 1st | 43754 | 43758 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0373 | Check first fixtion for race way cable tray (Power for mcc) at 2-nd floor z1,2,3a at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _cable tray size(10*10cm)=26 m . | ELEC | Z1,2,3A | Z1,2,3A | 2nd | 43754 | 43758 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0374 | Check first fixtion for race way cable tray (power for mcc) in 2-nd floor z3b,4,5 at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch. _cable tray size (10*10 cm)=22 m. | ELEC | Z3B,4,5 | Z3B,4,5 | 2nd | 43754 | 43758 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0375 | Check first fixtion for race way cable tray (Power for mcc) at 3-rd floor z1,2,3a at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _cable tray size(10*10cm)= 29m . | ELEC | Z1,2,3A | Z1,2,3A | 3rd | 43754 | 43758 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0376 | Check first fixtion for race way cable tray (power for mcc) in 3-rd floor z3b,4,5 at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch. _cable tray size (10*10 cm)=20 m | ELEC | Z3B,4,5 | Z3B,4,5 | 3rd | 43754 | 43758 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0377 | Check first fixtion for race way cable tray (Power for mcc) at 4-th floor z1,2,3a at axis (A_L) with axis (10-18) at zones (z1-z2-z3a) accordding to the attached sketch. _cable tray size(10*10cm)=62 m . _cable tray size(20*10cm)=21 m . | ELEC | Z1,2,3A | Z1,2,3A | 4th | 43754 | 43758 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0378 | Check first fixtion for race way cable tray (power for mcc) in 4-th floor z3b,4,5 at axis (A_L) with axis (1-9) at zones (z3b-z4,5) accordding to the attached sketch. _cable tray size (10*10 cm)=60 m. | ELEC | Z3B,4,5 | Z3B,4,5 | 4th | 43754 | 43758 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0379 | PLS Check first fixation for electrical works For (Power, lighting andlight current Systems) In Block Works at axis (F-L) with axis (7-12) Zone 3 accordding to the attached sketch. _Lighting switches =52 _small power outlets=55 _data outlets =6 _Telephone Outlets=7 _thermostst outlets =30 . | ELEC | Z3 | Z3 | 5th | 43758 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0380 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (F-L) with axis (1-6) Zone 4 accordding to the attached sketch. _Lighting switch =52 _small power outlets=55 _ H.D outlets =4 _data outlets =6 _Telephone outlets =7 _thermostst outlets =30 . | ELEC | Z4 | Z4 | 5th | 43758 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0381 | PLS Check first fixation for electrical works For (Power and lighting Systems) In Block Works at axis (A-E) with axis (1-7) Zone 5 accordding to the attached sketch. _Lighting switches= 52 _small power outlets =55 _ Data outlets =6 _Telephone outlets =7 _thermostst outlets =30 . | ELEC | Z5 | Z5 | 5th | 43758 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0382 | PLS Check first fix and set in place to floor boxies at 6-th floor in (Z3b,4) at axis (F-L) with axis (1-9) accordding to the attached sketch. | ELEC | Z3B,4 | Z3B,4 | 6th | 43758 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0383 | Check first fixation for facad lighting in second floor at zones (z1,z2,z3,z4,z5) accordding to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43759 | 43766 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0384 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at second floor at axis (A_E) with axis (14_18) ( Zone1) Refer to FTR (02-001) according to the attached sketch. _Number of points = 205. | ELEC | Z1 | Z1 | 2nd | 43765 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0385 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at second floor at axis (F_L) with axis (10_18) ( Zone2,3a) Refer to FTR (02-010) according to the attached sketch. _Number of points = 283 . | ELEC | Z2,3A | Z2,3A | 2nd | 43765 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0386 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at second floor at axis (F_L) with axis (1_9) ( Zone3b,4) Refer to FTR (02-026) according to the attached sketch. _Number of points =310 | ELEC | Z3B,4 | Z3B,4 | 2nd | 43765 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0387 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at second floor at axis (A_E) with axis (1_9) ( Zone5) Refer to FTR (02-041) according to the attached sketch. _Number of points = 132 . | ELEC | Z5 | Z5 | 2nd | 43765 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0388 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) In Block Works at axis (F-L) with axis (1-9) Zone 3b,4 accordding to the attached sketch. _Lighting switch =52 _small power outlets=55 _ H.D outlets =4 _data outlets =6 _Telephone outlets =7 _thermostst outlets =30 . | ELEC | Z3B,4 | Z3B,4 | 6th | 43765 | 43771 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0389 | PLS Check finalaization and megger test For ATS flanges at B1 floor at (Z5), (Z1) accordding to the attached sketch at Main low voltage rooms. _No. of pannels =4 | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43765 | 43768 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0390 | PLS Check Installation for medium voltage switsh gear in (Z4) at axis (J-L) with axis (0-2) accordding to the attached sketch. | ELEC | Z4 | Z4 | 2nd | 43769 | 43772 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0391 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in second floor at axis (A_F) with axis (1-6) at zone (Z5) LP_ID_2 refer to electrical room (ID) accordding to the attached sketch. _normal Lighting lines= 11 _normal lighting outlets =130 . | ELEC | Z5 | Z5 | 2nd | 43769 | 43772 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0392 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in second floor at axis (A_F) with axis (1-6) at zone (Z5) ELP_ID_CB_2 refer to electrical room (ID) accordding to the attached sketch. _central battary lines=5 . _central battary outlets =10 _exit outlets =8 | ELEC | Z5 | Z5 | 2nd | 43774 | 43780 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0393 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in second floor at axis (A_F) with axis (12-18) at zone (Z1) LP_IA_2 refer to electrical room (IA) accordding to the attached sketch. _normal Lighting lines= 11 _normal lighting outlets =118 | ELEC | Z1 | Z1 | 2nd | 43774 | 43780 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0394 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in second floor at axis (A_F) with axis (12-18) at zone (Z1) ELP_CB_2 refer to electrical room (IA) accordding to the attached sketch. _central battary lines=6 . _central battary outlets =12 _exit outlets =8. | ELEC | Z1 | Z1 | 2nd | 43774 | 43780 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0395 | PLS Check first fixation for electrical works For (Power, lighting andlight current Systems) In Block Works at axis (A-F) with axis (2-5) roof of Zone 1 And roof of zone 5 at axis (A-F) with axis (14-18) accordding to the attached sketch. _Lighting switches=26. _small power outlets= 46 . _data outlets =8. _cctvoutlets =10 . _lighting outlets (wall mounted) =48 . | ELEC | Z1 | Z1 | RF | 43775 | 43780 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0396 | Check first fixtion for EMT race way for electrical work(lighting system) in fifth floor at axis (A_F) with axis (13-18) at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _normal lighting outlets= 179 _emergency lighting outlets(CB) =17 _exit outlets=15 _PD outlets=37 | ELEC | Z1 | Z1 | 5th | 43775 | 43787 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0397 | Check first fixtion for EMT race way for electrical work(lighting system) in fifth floor at axis (F_L) with axis (1-9) at zones (z3b-z4) refer to electrical room (IC) accordding to the attached sketch. _normal &emergency lighting outlets= 359 _emergency lighting outlets(CB) =23 _exit outlets=15 _PD outlets=37 | ELEC | Z3B,4 | Z3B,4 | 5th | 43775 | 43787 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0398 | PLS Check first fixation for electrical works For (Power, lighting and light current Systems) at at ninth floor Block Work at axis (F-L) with axis (7-12) Zone 3 accordding to the attached sketch. _Lighting switshes and wall mounted otlets= 76 _small power outlets =132 -H.D outlets =5 _data outlets =92 _thermostst outlets =37 | ELEC | Z3 | Z3 | 9th | 43775 | 43783 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0399 | PLS Check first fix for race way to floor boxies in seventh floor at axis (F-L) with axis (1-18) accordding to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 7th | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0400 | PLS Check first fix for race way to floor boxies in 8-th floor at axis (F-L) with axis (7-12) accordding to the attached sketch. | ELEC | Z3 | Z3 | 8th | 43776 | 43783 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0401 | PLS Check first fix for race way to floor boxies in 9-th floor at axis (F-L) with axis (7-12) accordding to the attached sketch. | ELEC | Z3 | Z3 | 9th | 43776 | 43783 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0402 | Check first fixtion for EMT race way to electrical work(Power for Hvac system) in 6-th floor accordding to the attached sketch. _Hvac outlets= 126 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 6th | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0403 | Check first fixtion for EMT race way to electrical work(Power for Hvac system) in 8-th floor accordding to the attached sketch. _Hvac outlets= 51 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 8th | 43776 | 43783 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0404 | Check first fixtion for EMT race way to electrical work(Power for Hvac system) in 9-th floor accordding to the attached sketch. _Hvac outlets= 58 . | ELEC | Z3 | Z3 | 9th | 43776 | 43783 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0405 | Check second fixtion for lighting and power systems (Pulling of wires for lighting and power circuits ) in second floor at axis (A_F) with axis (14-18) at zone (Z1) ELP_IA_2 refer to electrical room (IA) accordding to the attached sketch. _Emergency lighting lines=9 . _emergency lighting outlets =52 _power lines =3 _power outlets =4 . | ELEC | Z1 | Z1 | 2nd | 43776 | 43780 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0406 | Check second fixtion for lighting and power systems (Pulling of wires for lighting and power circuits ) in second floor at axis (A_F) with axis (1-6) at zone (Z5) ELP_ID_2 refer to electrical room (ID) accordding to the attached sketch. _Emergency lines=9 . _Emergency outlets =68 _Power lines=4 _Power outlets =9 | ELEC | Z5 | Z5 | 2nd | 43776 | 43780 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0407 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in second floor pannel LP_IB_02 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _normal Lighting lines= 24 _normal lighting outlets =226 . | ELEC | Z2,3A | Z2,3A | 2nd | 43779 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0408 | Check second fixtion for lighting and power systems (Pulling of wires for lighting and power circuits) in second floor Pannel ELP_IB_02 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _emergency lighting lines =31 _emergencey lighting outlets=144 _emergency power outlets =18. | ELEC | Z2,3A | Z2,3A | 2nd | 43779 | 43783 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0409 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in second floor pannel ELP_CB_IB_02 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _central battary lines=9 _central battary outlets =21 _exit outlets =14 . | ELEC | Z2,3A | Z2,3A | 2nd | 43779 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0410 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in second floor pannel LP_IC_02 at axis (F_L) with axis (1-9) at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _normal Lighting lines= 29 _normal lighting outlets =250 . | ELEC | Z3B,4 | Z3B,4 | 2nd | 43779 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0411 | Check second fixtion for lighting and power systems (Pulling of wires for lighting and power circuits) in second floor pannel ELP_IC_02 at axis (F_L) with axis (1-9) at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _emergency lighting lines =30 _emergencey lighting outlets=146 _emergency power outlets =13 . | ELEC | Z3B,4 | Z3B,4 | 2nd | 43779 | 43783 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0412 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in second floor pannel ELP_CB_IC_02 at axis (F_L) with axis (1-9) at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _central battary lines=8 _central battary outlets =24 _exit outlets =14. | ELEC | Z3B,4 | Z3B,4 | 2nd | 43779 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0413 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in third floor at axis (A_F) with axis (12-18) at zone (Z1) LP_IA_03 refer to electrical room (IA) accordding to the attached sketch. _normal Lighting lines= 12 _normal lighting outlets =100. | ELEC | Z1 | Z1 | 3rd | 43779 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0414 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in third floor at axis (A_F) with axis (14-18) at zone (Z1) ELP_IA_03 refer to electrical room (IA) accordding to the attached sketch. _Emergency lighting lines=19 _emergency lighting outlets =63 _power outlets =10 . | ELEC | Z1 | Z1 | 3rd | 43779 | 43783 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0415 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in third floor pannel ELP_CB_IA_03 at axis (A_F) with axis (12-18) at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _central battary lines=6 _central battary outlets =11 _exit outlets =7. | ELEC | Z1 | Z1 | 3rd | 43779 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0416 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in third floor at axis (A_F) with axis (1-6) at zone (Z5) LP_ID_03 refer to electrical room (ID) accordding to the attached sketch. _normal Lighting lines= 12 _normal lighting outlets =113 . | ELEC | Z5 | Z5 | 3rd | 43779 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0417 | Check second fixtion for lighting and power systems (Pulling of wires for lighting and power circuits) in third floor at axis (A_F) with axis (1-6) at zone (Z5) ELP_ID_03 refer to electrical room (ID) accordding to the attached sketch. _Emergency lines=14 . _Emergency lighting outlets =64 _Power outlets =7. | ELEC | Z5 | Z5 | 3rd | 43779 | 43783 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0418 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in third floor at axis (A_F) with axis (1-6) at zone (Z5) ELP_ID_CB_03 refer to electrical room (ID) accordding to the attached sketch. _central battary lines=6 _central battary outlets =13 _exit outlets =9. | ELEC | Z5 | Z5 | 3rd | 43779 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0419 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in third floor pannel LP_IB_03 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _normal Lighting lines= 24 _normal lighting outlets =235 . | ELEC | Z2,3A | Z2,3A | 3rd | 43779 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0420 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in third floor Pannel ELP_IB_03 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _emergenc lines =26 _emergencey lighting outlets=135 _emergency power outlets =6. | ELEC | Z2,3A | Z2,3A | 3rd | 43779 | 43783 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0421 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in third floor pannel ELP_CB_IB_03 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _central battary lines=9 _central battary outlets =23 _exit outlets =18 . | ELEC | Z2,3A | Z2,3A | 3rd | 43779 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0422 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in third floor pannel LP_IC_03 at axis (F_L) with axis (1-9) at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _normal Lighting lines= 26 _normal lighting outlets =244 . | ELEC | Z3B,4 | Z3B,4 | 3rd | 43779 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0423 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in third floor pannel ELP_IC_03 at axis (F_L) with axis (1-9) at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _emergency lines =35 _emergencey lighting outlets=160 _emergency power outlets =18 . | ELEC | Z3B,4 | Z3B,4 | 3rd | 43779 | 43783 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0424 | Check second fixtion for lighting system (Pulling of wires for lighting circuits and outlets ) in third floor pannel ELP_CB_IC_03 at axis (F_L) with axis (1-9) at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _central battary lines=89 _central battary outlets =24 _exit outlets =13. | ELEC | Z3B,4 | Z3B,4 | 3rd | 43779 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0425 | Please Check first fixtion for power cable trunk in first floor accordding to the attached sketch. Power Cable Trunk = 621 m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43779 | 43787 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0426 | Please Check first fixtion for power cable trunk in second floor accordding to the attached sketch. Power Cable Trunk = 642 m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43779 | 43787 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0427 | Please Check first fixtion for power cable trunk in third floor accordding to the attached sketch. Power Cable Trunk = 600 m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43779 | 43787 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0428 | Check installation for distribution pannel boards at first floor inside electrical room (IA) accordding to the attached sketch. _LP_IA_01 _ELP_IA_01 _ELP_CB_IA_01 _ELP_LS_IA_01 _PP_IA_1-1 _PP_IA_1-2 _EPP_UPS_IA_1-1 _EPP_UPS_IA_1-2 | ELEC | Z1 | Z1 | 1st | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0429 | Check installation for distribution pannel boards at first floor inside electrical room (IB) accordding to the attached sketch. _LP_IB_01 _ELP_IB_01 _ELP_CB_IB_01 _ELP_LS_IB_01 _PP_IB_1-1 _PP_IB_1-2 _EPP_UPS_IB_1-1 _EPP_UPS_IB_1-2 | ELEC | Z2,3A | Z2,3A | 1st | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0430 | Check installation for distribution pannel boards at first floor inside electrical room (IC) accordding to the attached sketch. _LP_IC_01 _ELP_IC_01 _ELP_CB_IC_01 _ELP_LS_IC_01 _PP_IC_1-1 _PP_IC_1-2 _EPP_UPS_IC_1-1 _EPP_UPS_IC_1-2 | ELEC | Z2,3A | Z2,3A | 1st | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0431 | Check installation for distribution pannel boards at first floor inside electrical room (ID) accordding to the attached sketch. _LP_ID_01 _ELP_ID_01 _ELP_CB_ID_01 _ELP_LS_ID_01 _PP_ID_1-1 _PP_ID_1-2 _EPP_UPS_ID_1-1 _EPP_UPS_ID_1-2 | ELEC | Z2,3A | Z2,3A | 1st | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0432 | Check installation for distribution pannel boards at second floor inside electrical room (IA) accordding to the attached sketch. _LP_IA_02 _ELP_IA_02 _ELP_CB_IA_02 _EDB_IA_02 _PP_IA_02 _EPP_UPS_IA_02 | ELEC | Z1 | Z1 | 2nd | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0433 | Check installation for distribution pannel boards at second floor inside electrical room (IB) accordding to the attached sketch. _LP_IB_02 _ELP_IB_02 _ELP_CB_IB_02 _PP_IB_02-1 _PP_IB_02-2 _EPP_UPS_IB_02 | ELEC | Z2,3A | Z2,3A | 2nd | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0434 | Check installation for distribution pannel boards at second floor inside electrical room (IC) accordding to the attached sketch. _LP_IC_02 _ELP_IC_02 _ELP_CB_IC_02 _PP_IC_2-1 _PP_IC_2-2 _EPP_UPS_IC_2 . | ELEC | Z2,3A | Z2,3A | 2nd | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0435 | Check installation for distribution pannel boards at second floor inside electrical room (ID) accordding to the attached sketch. _LP_ID_02 _ELP_ID_02 _ELP_CB_ID_02 _EDB_ID_02 _PP_ID_02 _EPP_UPS_ID_02 | ELEC | Z2,3A | Z2,3A | 2nd | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0436 | Check fixation for Main Grade Earthing System in Ground floor at axis (J_E) with axis (15-18) at zones (z2) accordding to the attached sketch. _Earthing Rods no.=10 _Cable Size 240 mm=100 m _Cable Size 95 mm=130 m . | ELEC | Z2 | Z2 | GF | 43786 | 43803 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0437 | Check installation for distribution pannel boards at third floor inside electrical room (IA) accordding to the attached sketch. _LP_IA_03 _ELP_IA_03 _ELP_CB_IA_03 _PP_IA_03 _EPP_UPS_IA_03 | ELEC | Z1 | Z1 | 3rd | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0438 | Check installation for distribution pannel boards at third floor inside electrical room (IB) accordding to the attached sketch. _LP_IB_03 _ELP_IB_03 _ELP_CB_IB_03 _PP_IB_03-1 _PP_IB_03-2 _EPP_UPS_IB_03 | ELEC | Z2,3A | Z2,3A | 3rd | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0439 | Check installation for distribution pannel boards at third floor inside electrical room (IC) accordding to the attached sketch. _LP_IC_03 _ELP_IC_03 _ELP_CB_IC_03 _PP_IC_03-1 _PP_IC_03-2 _EPP_UPS_IC_03 . | ELEC | Z2,3A | Z2,3A | 3rd | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0440 | Check installation for distribution pannel boards at third floor inside electrical room (ID) accordding to the attached sketch. _LP_ID_03 _ELP_ID_03 _ELP_CB_ID_03 _PP_ID_03 _EPP_UPS_ID_03 | ELEC | Z2,3A | Z2,3A | 3rd | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0441 | Check installation for distribution pannel boards at fourth floor inside electrical room (IA) accordding to the attached sketch. _LP_IA_04 _ELP_IA_04 _ELP_CB_IA_04 _PP_IA_02 _EPP_UPS_IA_02 _ELP_LS_IA_04 | ELEC | Z1 | Z1 | 4th | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0442 | Check installation for distribution pannel boards at fourth floor inside electrical room (IB) accordding to the attached sketch. _LP_IB_04 _ELP_IB_04 _ELP_CB_IB_04 _PP_IB_04-1 _PP_IB_04-2 _EPP_UPS_IB_04 _ELP_LS_IB_04 | ELEC | Z2,3A | Z2,3A | 4th | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0443 | Check installation for distribution pannel boards at fourth floor inside electrical room (IC) accordding to the attached sketch. _LP_IC_04 _ELP_IC_04 _ELP_CB_IC_04 _PP_IC_04-1 _PP_IC_04-2 _EPP_UPS_IC_04 _ELP_LS_IC_04 . | ELEC | Z2,3A | Z2,3A | 4th | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0444 | Check installation for distribution pannel boards at fourth floor inside electrical room (ID) accordding to the attached sketch. _LP_ID_04 _ELP_ID_04 _ELP_CB_ID_04 _PP_ID_04 _EPP_UPS_ID_04 _ELP_LS_ID_04 | ELEC | Z2,3A | Z2,3A | 4th | 43786 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0445 | Check installation for distribution pannel boards at fifth floor inside electrical room (IA) accordding to the attached sketch. _LP_IA_05 _ELP_IA_05 _ELP_CB_IA_05 _PP_IA_05 _EPP_UPS_IA_05 | ELEC | Z1 | Z1 | 5th | 43787 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0446 | Check installation for distribution pannel boards at fifth floor inside electrical room (IB) accordding to the attached sketch. _LP_IB_05 _ELP_IB_05 _ELP_CB_IB_05 _PP_IB_05-1 _PP_IB_05-2 _EPP_UPS_IB_05 | ELEC | Z2,3A | Z2,3A | 5th | 43787 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0447 | Check installation for distribution pannel boards at fifth floor inside electrical room (IC) accordding to the attached sketch. _LP_IC_05 _ELP_IC_05 _ELP_CB_IC_05 _PP_IC_05-1 _PP_IC_05-2 _EPP_UPS_IC_05 . | ELEC | Z2,3A | Z2,3A | 5th | 43787 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0448 | Check installation for distribution pannel boards at fifth floor inside electrical room (ID) accordding to the attached sketch. _LP_ID_05 _ELP_ID_05 _ELP_CB_ID_05 _PP_ID_05 _EPP_UPS_ID_05 | ELEC | Z2,3A | Z2,3A | 5th | 43787 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0449 | Check installation for distribution pannel boards at sixth floor inside electrical room (IA) accordding to the attached sketch. _LP_IA_06 _PP_IA_06 | ELEC | Z1 | Z1 | 6th | 43787 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0450 | Check installation for distribution pannel boards at sixth floor inside electrical room (IB) accordding to the attached sketch. _LP_IB_06 _ELP_IB_06 _ELP_CB_IB_06 _PP_IB_06-1 _PP_IB_06-2 _EPP_UPS_IB_06 | ELEC | Z2,3A | Z2,3A | 6th | 43787 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0451 | Check installation for distribution pannel boards at sixth floor inside electrical room (IC) accordding to the attached sketch. _LP_IC_026 _ELP_IC_06 _ELP_CB_IC_06 _PP_IC_06-1 _PP_IC_06-2 _EPP_UPS_IC_06 . | ELEC | Z2,3A | Z2,3A | 6th | 43787 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0452 | Check installation for distribution pannel boards at sixth floor inside electrical room (ID) accordding to the attached sketch. _LP_ID_06 _PP_ID_06 . | ELEC | Z2,3A | Z2,3A | 6th | 43787 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0453 | Check second fix for cable pulling for electrical work(Power for Hvac system) in second floor accordding to the attached sketch. _Hvac outlets= 192 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43787 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0454 | Check second fix for cable pulling for electrical work(Power for Hvac system) in third floor accordding to the attached sketch. _Hvac outlets= 192 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43787 | 43789 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0455 | Please Check first fixtion for power cable trunk in fourth floor accordding to the attached sketch. Power Cable Trunk = 635 m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43794 | 43803 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0456 | Please Check first fixtion for power cable trunk in fifth floor accordding to the attached sketch. Power Cable Trunk = 644 m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43794 | 43803 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0457 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at third floor at axis (A_E) with axis (14_18) ( Zone1) Refer to FTR (03-001) according to the attached sketch. _Number of points =144 . | ELEC | Z1 | Z1 | 3rd | 43794 | 43796 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0458 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at third floor at axis (F_L) with axis (10_18) ( Zone2,3a) Refer to FTR (03-010) according to the attached sketch. _Number of points =296 . | ELEC | Z2,3A | Z2,3A | 3rd | 43794 | 43796 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0459 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at third floor at axis (F_L) with axis (1_9) ( Zone3b,4) Refer to FTR (03-026) according to the attached sketch. _Number of points =279 | ELEC | Z3B,4 | Z3B,4 | 3rd | 43794 | 43796 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0460 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at third floor at axis (A_E) with axis (1_9) ( Zone5) Refer to FTR (03-041) according to the attached sketch. _Number of points =193 . | ELEC | Z5 | Z5 | 3rd | 43794 | 43796 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0461 | Check the termination of lighting system wires in second floor at axis (A_F) with axis (12-18) at zone (Z1) inside pannel LP_IA_2 refer to electrical room (IA) accordding to the attached sketch. _normal Lighting lines= 11 _normal lighting outlets =118 . | ELEC | Z1 | Z1 | 2nd | 43807 | 43810 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0462 | Check the termination of lighting system wires in second floor at axis (A_F) with axis (14-18) at zone (Z1) inside pannel ELP_IA_2 refer to electrical room (IA) accordding to the attached sketch. _Emergency lighting lines=9 _emergency lighting outlets =52 _power lines =2. _power outlets =3 . | ELEC | Z1 | Z1 | 2nd | 43807 | 43810 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0463 | Check the termination of lighting system wires in second floor at axis (A_F) with axis (12-18) at zone (Z1) inside pannel ELP_CB_IA_2 refer to electrical room (IA) accordding to the attached sketch. _central battary lines=6 _central battary outlets =12 _exit outlets =8. | ELEC | Z1 | Z1 | 2nd | 43807 | 43810 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0464 | Check the termination of lighting system wires in second floor at axis (A_F) with axis (1-6) at zone (Z5) inside pannel LP_ID_2 refer to electrical room (ID) accordding to the attached sketch. _normal Lighting lines= 11 _normal lighting outlets =130 . | ELEC | Z5 | Z5 | 2nd | 43807 | 43810 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0465 | Check the termination of lighting system wires in second floor at axis (A_F) with axis (1-6) at zone (Z5) inside pannel ELP_ID_2 refer to electrical room (ID) accordding to the attached sketch. _Emergency lines=9 _Emergency outlets =68 _Power lines=4 _Power outlets =9. | ELEC | Z5 | Z5 | 2nd | 43807 | 43810 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0466 | Check the termination of lighting system wires in second floor at axis (A_F) with axis (1-6) at zone (Z5) inside pannel ELP_ID_CB_2 refer to electrical room (ID) accordding to the attached sketch. _central battary lines=5 _central battary outlets =10 _exit outlets =8. | ELEC | Z5 | Z5 | 2nd | 43807 | 43810 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0467 | PLS Check Installation of low voltage main distribution board inside first substation in (Z1) at axis (C-F) with axis (12-14) accordding to the attached sketch. _MDBI1 _EMDBI11 _EMDBI12 _C.B I11 _C.B i12 _C.B i13 _G.P.B I1 | ELEC | Z1 | Z1 | B1 | 43822 | 43844 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0468 | PLS Check Installation of low voltage main distribution board inside second substation in (Z5) at axis (C-F) with axis (5-6) accordding to the attached sketch. _MDBI2 _EMDBI21 _EMDBI22 _C.B I21 _C.B i22 _C.B i23 _G.P.B I2 | ELEC | Z5 | Z5 | B1 | 43822 | 43844 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0469 | Check second fix,continuity test,megger test and pannel installation for lighting system in first floor at axis (A_F) with axis (1-6) at zone (Z5) for pannel LP_ID_01 refer to electrical room (ID) accordding to the attached sketch. _normal Lighting lines= 14 _normal lighting outlets =180 . | ELEC | Z5 | Z5 | 1st | 43822 | 43825 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0470 | Check second fix,continuity test,megger test and pannel installation for lighting system in first floor at axis (A_F) with axis (1-6) at zone (Z5) for pannel ELP_CB_ID_01 refer to electrical room (ID) accordding to the attached sketch. _C.B Lighting lines= 14 _C.B lighting outlets =38 . | ELEC | Z5 | Z5 | 1st | 43822 | 43825 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0471 | Check second fix,continuity test,megger test and pannel installation for lighting system in first floor pannel ELP_CB_IC_01 at axis (F_L) with axis (1-9) at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _central battary lines= 14 _central battary outlets =62 . | ELEC | Z3B,4 | Z3B,4 | 1st | 43822 | 43828 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0472 | Check second fix,continuity test,megger test and pannel installation for lighting system in first floor pannel LP_IC_01 at axis (F_L) with axis (1-9) at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _normal Lighting lines= 26 _normal lighting outlets =287 . | ELEC | Z3B,4 | Z3B,4 | 1st | 43822 | 43828 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0473 | Pls Check first fix Installation for Cable Trunks In fifth floor at axis (A_F) with axis (12_18) ( Zone1,2,3a) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (497 m) _GSM Cable Trunk size(10*10cm)= (226 m). | ELEC | Z1,2,3A | Z1,2,3A | 5th | 43823 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0474 | Pls Check first fix Installation for Cable Trunks In fifth floor at axis (0_E) with axis (1_12) ( Zone3b,4,5) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (435 m) _GSM Cable Trunk size(10*10cm)= (233 m) . | ELEC | Z3B,4,5 | Z3B,4,5 | 5th | 43823 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0475 | Pls Check first fix Installation for Cable Trunks In sixth floor at axis (A_F) with axis (12_18) ( Zone1,2,3a) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (340 m) _GSM Cable Trunk size(10*10cm)= (155 m). | ELEC | Z1,2,3A | Z1,2,3A | 6th | 43823 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0476 | Pls Check first fix Installation for Cable Trunks In sixth floor at axis (0_E) with axis (1_12) ( Zone3b,4,5) according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (345 m) _GSM Cable Trunk size(10*10cm)= (160 m) . | ELEC | Z3B,4,5 | Z3B,4,5 | 6th | 43823 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0477 | Please Check first fixtion for power routing system in first Basement floor accordding to the attached sketch. _ Cable Tray(10*10cm) =360 m _Cable Tray(15*10cm) =115m _Cable Tray(20*10cm) =250m _Cable Tray(30*10cm) =15m _Cable Tray(40*10cm) =145m _Cable Tray(50*10cm) =15m _Cable Tray(60*10cm) =160m _Cable Tray(80*10cm) =65m . _ Cable Tray(90*10cm) =85 _Cable Tray(100*10cm) =15m. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | B1 | 43823 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0478 | Please Check first fixtion for power routing system in the second basement floor accordding to the attached sketch. __ Cable Tray(10*10cm) =660 m _Cable Tray(20*10cm) =100m _Cable Tray(30*10cm) =95m _Cable Tray(40*10cm) =50m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | B2 | 43823 | 43844 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0479 | Please Check first fixtion for power cable trunk in sixth floor accordding to the attached sketch. _ Power Cable Trunk = 270 m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 6th | 43823 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0480 | Check first fixtion for race way for EMT electrical work(Power for Hvac system) in 7-th floor above bridge zone accordding to the attached sketch. _Hvac outlets= 4 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 7th | 43823 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0481 | Check first fixtion for race way cable tray (Power for mcc) at 5-th floor accordding to the attached sketch. _cable tray size(10*10cm)=50 m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43828 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0482 | Check first fixtion for race way cable tray (Power for mcc) at 6-th floor accordding to the attached sketch. _cable tray size(10*10cm)=115 m _cable tray size(20*10cm)=62m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 6th | 43828 | 43835 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0483 | Check second fix,continuity test,megger test and pannel installation for lighting system in first floor at axis (A_F) with axis (12-18) at zone (Z1) LP_IA_01 refer to electrical room (IA) accordding to the attached sketch. _normal Lighting lines= 20 _normal lighting outlets 150 . | ELEC | Z1 | Z1 | 1st | 43828 | 43835 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0484 | Check second fix,continuity test,megger test and pannel installation for lighting system in first floor pannel ELP_CB_IA_01 at axis (A_F) with axis (12-18) at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _central battary lines=11 _central battary outlets =46. | ELEC | Z1 | Z1 | 1st | 43828 | 43835 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0485 | Check second fix,continuity test ,megger test and pannel installation for lighting system in first floor pannel LP_IB_01 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _normal Lighting lines= 31 _normal lighting outlets =474 . | ELEC | Z2,3A | Z2,3A | 1st | 43828 | 43835 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0486 | Check second fix,continuity test,megger test and pannel installation for lighting system in first floor pannel ELP_CB_IB_01 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _central battary lines=14 _central battary outlets =82 . | ELEC | Z2,3A | Z2,3A | 1st | 43828 | 43835 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0487 | Check second fix,continuity test ,megger test and pannel installation for lighting system in first floor Pannel ELP_IB_01 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _emergency lines =29 _emergencey lighting outlets=210 . | ELEC | Z2,3A | Z2,3A | 1st | 43828 | 43835 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0488 | Check the secondary earth fixation for Earthing System in second floor accordding to the attached sketch. _Cable Size 240 mm2=80 m _Cable Size 35 mm2=65 m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43830 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0489 | Check the secondary earth fixation for Earthing System in third floor accordding to the attached sketch. _Cable Size 35 mm2=65 m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43830 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0490 | Check the secondary earth fixation for Earthing System in first floor accordding to the attached sketch. _Cable Size 240 mm2=110 m _Cable Size 35 mm2=35 m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43830 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0491 | Check the secondary earth fixation for Earthing System in fourth floor accordding to the attached sketch. _Cable Size 240 mm2=75 m _Cable Size 35 mm2=70 m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43830 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0492 | Check first fixtion for race way and block work for electrical works(lighting system,small power system,power for hvac,fire alarm system and structure cabling system) inside HVAC,ELEC and FTR rooms at second floor accordding to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43836 | 43844 | Cancelled
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0493 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fourth floor at axis (A_E) with axis (14_18) ( Zone1) Refer to FTR (04-001) according to the attached sketch. _Number of points =137 _total length=9442 m . | ELEC | Z1 | Z1 | 4th | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0494 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fourth floor at axis (F_L) with axis (10_18) ( Zone2,3a) Refer to FTR (04-010) according to the attached sketch. _Number of points =275 _total length=20504 m . | ELEC | Z2,3A | Z2,3A | 4th | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0495 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fourth floor at axis (F_L) with axis (1_9) ( Zone3b,4) Refer to FTR (04-026) according to the attached sketch. _Number of points =246 _total length =18065 m . | ELEC | Z3B,4 | Z3B,4 | 4th | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0496 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fourth floor at axis (A_E) with axis (1_9) ( Zone5) Refer to FTR (03-041) according to the attached sketch. _Number of points =184 _total length= 11700 m . | ELEC | Z5 | Z5 | 4th | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0497 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fifth floor at axis (A_E) with axis (14_18) ( Zone1) Refer to FTR (05-001) according to the attached sketch. _Number of points =170 _total lengths =12226 m . | ELEC | Z1 | Z1 | 5th | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0498 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fifth floor at axis (F_L) with axis (10_18) ( Zone2,3a) Refer to FTR (05-010) according to the attached sketch. _Number of points = 225 _total lengths =16200 m . | ELEC | Z2,3A | Z2,3A | 5th | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0499 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fifth floor at axis (F_L) with axis (1_9) ( Zone3b,4) Refer to FTR (05-026) according to the attached sketch. _Number of points =282 _total lengths =20593 m . | ELEC | Z3B,4 | Z3B,4 | 5th | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0500 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fifth floor at axis (A_E) with axis (1_9) ( Zone5) Refer to FTR (05-041) according to the attached sketch. _Number of points =155 _total lengths =10398 m . | ELEC | Z5 | Z5 | 5th | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0501 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at first floor at axis (A_E) with axis (14_18) ( Zone1) Refer to FTR (01-001) according to the attached sketch. _Number of points =239 _total length = 18404 m . | ELEC | Z1 | Z1 | 1st | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0502 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at first floor at axis (F_L) with axis (10_18) ( Zone2,3a) Refer to FTR (01-010) according to the attached sketch. _Number of points =556 _total length =43761 m . | ELEC | Z2,3A | Z2,3A | 1st | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0503 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at first floor at axis (F_L) with axis (1_9) ( Zone3b,4) Refer to FTR (01-026) according to the attached sketch. _Number of points =556 _total length =43761 m . | ELEC | Z3B,4 | Z3B,4 | 1st | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0504 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at first floor at axis (A_E) with axis (1_9) ( Zone5) Refer to FTR (01-041) according to the attached sketch. _Number of points =137 _total length =21881 m . | ELEC | Z5 | Z5 | 1st | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0505 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at sixth floor at axis (F_L) with axis (10_18) ( Zone2,3a) Refer to FTR (06-010) according to the attached sketch. _Number of points = 245 _total lengths =16961 m . | ELEC | Z2,3A | Z2,3A | 6th | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0506 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fifth floor at axis (F_L) with axis (1_9) ( Zone3b,4) Refer to FTR (06-026) according to the attached sketch. _Number of points =269 _total lengths =17638 m . | ELEC | Z3B,4 | Z3B,4 | 5th | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0507 | Pls Check first fix Installation for Cable Trunks In 7-th floor according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (604 m) _GSM Cable Trunk size(10*10cm)= (318 m). | ELEC | Z2,3,4 | Z2,3,4 | 7th | 43836 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0508 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at 7-th floor Refer to FTR (07-006) , FTR (07-020) according to the attached sketch. _Number of points =531 _total lengths =37708 m . | ELEC | Z2,3,4 | Z2,3,4 | 7th | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0509 | Pls Check first fix Installation for Cable Trunks In 8-th floor according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (215 m) _GSM Cable Trunk size(10*10cm)= (125 m). | ELEC | Z3 | Z3 | 8th | 43836 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0510 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at 8-th floor according to the attached sketch. _Number of points =188 _total lengths =12554 m . | ELEC | Z3 | Z3 | 8th | 43836 | 43843 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0511 | Please Check first fixtion for power cable trunk in 7-th floor accordding to the attached sketch. _ Power Cable Trunk = 335 m . | ELEC | Z2,3,4 | Z2,3,4 | 7th | 43836 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0512 | Please Check first fixtion for power cable trunk in 8-th floor accordding to the attached sketch. _ Power Cable Trunk = 155 m . | ELEC | Z3 | Z3 | 8th | 43836 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0513 | Pls Check first fix Installation for Power Cable Trunks In 9-th floor according to the attached Clouded sketch. _Power Cable Trunk = 125 m. | ELEC | Z3 | Z3 | 9th | 43836 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0514 | Pls Check first fix Installation for Cable Trunks In 9-th floor according to the attached Clouded sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (215 m) _GSM Cable Trunk size(10*10cm)= (115 m). | ELEC | Z3 | Z3 | 9th | 43836 | 43843 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0515 | Check second fixt,continuity test,megger test and pannel installation for lighting system in first floor at axis (A_F) with axis (1-6) at zone (Z5) ELP_ID_01 refer to electrical room (ID) accordding to the attached sketch. _No. of lines=12 . _Emergency lighting outlets =73 _Single Socket Power outlets =3. | ELEC | Z5 | Z5 | 1st | 43838 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0516 | Check second fixt,continuity test,megger test and pannel installation for small powe system in first floor pannel PP_ID_1_1 at zone (5) refer to electrical room (ID) according to the attached sketch. _No.of lines=51 _single Socket (16A) Outlets=50 _Duplex Socket (16A)=61 _Disconnect Switch(20A/220v)=7 . | ELEC | Z5 | Z5 | 1st | 43838 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0517 | Check second fixt,continuity test,megger test and pannel installation for small power system in first floor pannel PP_ID_1_2 at zone (5) refer to electrical room (ID) according to the attached sketch. _No.of lines=58 _single Socket (16A) Outlets=57 _Duplex Socket (16A)=83 _Disconnect Switch(20A/220v)=14 . | ELEC | Z5 | Z5 | 1st | 43838 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0518 | Check second fixt,continuity test,megger test and pannel installation for small power system in first floor pannel EPP_UPS_ID_1_1 at zone (5) refer to electrical room (ID) according to the attached sketch. _No.of lines=43 _single Socket (16A) Outlets=122 . | ELEC | Z5 | Z5 | 1st | 43838 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0519 | Check second fixt,continuity test,megger test and pannel installation for small power system in first floor pannel EPP_ID_1_2 at zone (5) refer to electrical room (ID) according to the attached sketch. _No.of lines=55 _Single Socket (16A) Outlets=151 _Duplex Socket (16A)=9 _Duplex Socket (32A)=4 _EO Outlets=1 . | ELEC | Z5 | Z5 | 1st | 43838 | 43844 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0520 | Check second fixt,continuity test,megger test and pannel installation for small power system in first floor pannel PP_IC_1_1 at zone (3b,4) refer to electrical room (IC) according to the attached sketch. _No.of lines=54 _single Socket (16A) Outlets=62 _Duplex Socket (16A)=92 _Disconnect Switch(20A/220v)=17 . | ELEC | Z3B,4 | Z3B,4 | 1st | 43838 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0521 | Check second fixt,continuity test,megger test and pannel installation for small power system in first floor pannel PP_IC_1_2 at zone (3b,4) refer to electrical room (IC) according to the attached sketch. _No.of lines=59 _single Socket (16A) Outlets=58 _Duplex Socket (16A)=125 _Disconnect Switch(20A/220v)=30 _H.D =5 _Duplex Socket (32A)=2. | ELEC | Z3B,4 | Z3B,4 | 1st | 43838 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0522 | Check second fixt,continuity test,megger test and pannel installation for small power system in first floor pannel EPP_UPS_IC_1_1 at zone (3b,4) refer to electrical room (IC) according to the attached sketch. _No.of lines=51 _single Socket (16A) Outlets=191 _Duplex Socket (16A)=5 . | ELEC | Z3B,4 | Z3B,4 | 1st | 43838 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0523 | Check second fixt,continuity test,megger test and pannel installation for small power system in first floor pannel EPP_UPS_IC_1_2 at zone (3b,4) refer to electrical room (IC) according to the attached sketch. _No.of lines=45 _single Socket (16A) Outlets=173 _Duplex Socket (16A)=11 _Disconnect switch(20A/220)=2 _ Duplex Socket (32A)=4. | ELEC | Z3B,4 | Z3B,4 | 1st | 43838 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0524 | Check second fix,continuity test,megger test and pannel installation for lighting system in first floor pannel ELP_IC_01 at axis (F_L) with axis (1-9) at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _emergency lines =27 _emergencey lighting outlets=162 _Single socket(16A) =8 _Duplex Socket (16A)=3 . | ELEC | Z3B,4 | Z3B,4 | 1st | 43838 | 43845 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0525 | Check second fixt,continuity test,megger test and pannel installation for small power system in first floor pannel EPP_UPS_IB_1_1 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=34 _single Socket (16A) Outlets=223 _Duplex Socket (16A)=1 . | ELEC | Z2,3A | Z2,3A | 1st | 43838 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0526 | Check second fixt,continuity test,megger test and pannel installation for small power system in first floor pannel EPP_UPS_IB_1_2 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=42 _single Socket (16A) Outlets=217 _Duplex Socket (16A)=10 _Duplex Socket (32A)=5 _single Socket (20A) Outlets=1 _EO=1 . | ELEC | Z2,3A | Z2,3A | 1st | 43838 | 43844 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0527 | Check second fix,continuity test,megger test and pannel installation for small power system in 6-th floor pannel PP_IB_6_1 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=35 _single Socket (16A) Outlets=50 _Duplex Socket (16A)=62 _Dissconnect Switch(20A/220v)=24 . | ELEC | Z2,3A | Z2,3A | 6th | 43839 | 43851 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0528 | Check second fix,continuity test,megger test and pannel installation for small power system in 6-th floor pannel PP_IB_6_2 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=35 _single Socket (16A) Outlets=41 _Duplex Socket (16A)=31 _Dissconnect Switch(20A/220v)=32 _H.D =4 _Duplex Socket (32A)=1 _Duplex Socket (20A)=1 . | ELEC | Z2,3A | Z2,3A | 6th | 43839 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0529 | Check second fix,continuity test,megger test and pannel installation for small power system in 6-th floor pannel EPP_UPS_IB_6 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=39 _single Socket (16A) Outlets=168 _Duplex Socket (16A)=12 _Duplex Socket (32A)=3 _Duplex Socket (20A)=2 . | ELEC | Z2,3A | Z2,3A | 6th | 43839 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0530 | Check second fix,continuity test,megger test and pannel installation for small power system in 6-th floor pannel PP_IC_6_1 at zone (3b,4) refer to electrical room (IC) according to the attached sketch. _No.of lines=45 _single Socket (16A) Outlets=45 _Duplex Socket (16A)=86 _Dissconnect Switch(20A/220v)=30 . | ELEC | Z3B,4 | Z3B,4 | 6th | 43839 | 43851 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0531 | Check second fix,continuity test,megger test and pannel installation for small power system in 6-th floor pannel PP_IC_6_2 at zone (3b,4) refer to electrical room (IC) according to the attached sketch. _No.of lines=39 _single Socket (16A) Outlets=40 _Duplex Socket (16A)=24 _Dissconnect Switch(20A/220v)=28 _H.D (20A)=4 _Duplex Socket (32A)=1 _Duplex Socket (20A)=1 . | ELEC | Z3B,4 | Z3B,4 | 6th | 43839 | 43853 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0532 | Check second fix,continuity test,megger test and pannel installation for small power system in 6-th floor pannel EPP_UPS_IC_6 at zone (3b,4) refer to electrical room (IC) according to the attached sketch. _No.of lines=51 _single Socket (16A) Outlets=178 _Duplex Socket (16A)=22 _Duplex Socket (32A)=3 _Duplex Socket (20A)=2 . | ELEC | Z3B,4 | Z3B,4 | 6th | 43839 | 43851 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0533 | Check second fix,continuity test,megger test and pannel installation for lighting system in 6-th floor pannel LP_IB_06 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _No. of lines=20 _Lighting outlets =195 . | ELEC | Z2,3A | Z2,3A | 6th | 43839 | 43846 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0534 | Check second fix,continuity test,megger test and pannel installation for lighting system in 6-th floor pannel ELP_CB_IB_06 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _No. of lines=9 _Exit outlets =9 _C.B outlets=25 . | ELEC | Z2,3A | Z2,3A | 6th | 43839 | 43851 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0535 | Check second fix,continuity test,megger test and pannel installation for lighting system in 6-th floor pannel ELP_CB_IB_06 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _No. of lines=9 _Exit outlets =9 _C.B outlets=25 . | ELEC | Z2,3A | Z2,3A | 6th | 43839 | 43851 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0536 | Check second fix,continuity test,megger test and pannel installation for lighting system in 6-th floor pannel LP_Ic_06 at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _No. of lines=26 _Lighting outlets =236 . | ELEC | Z3B,4 | Z3B,4 | 6th | 43839 | 43851 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0537 | Check second fix,continuity test,megger test and pannel installation for lighting system in 6-th floor pannel ELP_Ic_06 at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _No. of lines=36 _Lighting outlets =136 _Duplex socket(16A)=8 _Single socket(16A)=7 _3ph S.U=2 . | ELEC | Z3B,4 | Z3B,4 | 6th | 43839 | 43851 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0538 | Check second fix,continuity test,megger test and pannel installation for lighting system in 6-th floor pannel ELP-CB_Ic_06 at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _No. of lines=8 _Exit outlets =12 _C.B Outlets=23 . | ELEC | Z3B,4 | Z3B,4 | 6th | 43839 | 43851 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0539 | Check second fix,continuity test,megger test for small power system second floor at axis (A_F) with axis (12-18) at zone (Z1) for PP-IA-2 refer to electrical room (IA) accordding to the attached sketch. _No. of lines=59 . _Duplex socket(16A) =102 _single socket (16A)=65 _Disconnect switsh(20A)=23. | ELEC | Z1 | Z1 | 2nd | 43845 | 43852 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0540 | Check second fix,continuity test,megger test for small power system second floor at axis (A_F) with axis (12-18) at zone (Z1) for pannel EPP-UPS-IA-2 refer to electrical room (IA) accordding to the attached sketch. _No. of lines=45 . _Duplex socket(16A) =2 _single socket (16A)=208 _Duplex socket(32A)=3 _Duplex socket(20A)=2. | ELEC | Z1 | Z1 | 2nd | 43845 | 43852 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0541 | Check second fix,continuity test,megger test for small power system in second floor at zone (Z2,3a) for PP-Ib-2-1 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=41. _Duplex socket(16A) =81 _single socket (16A)=58 _Disconnect switsh(20A)=29. | ELEC | Z2,3A | Z2,3A | 2nd | 43845 | 43852 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0542 | Check second fix,continuity test,megger test for small power system in second floor at zone (Z2,3a) for PP-Ib-2-2 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=31. _Duplex socket(16A) =22 _single socket (16A)=37 _Disconnect switsh(20A)=30 _H.D =4 _Duplex socket(32A) =1 _Duplex socket(20A) =1. | ELEC | Z2,3A | Z2,3A | 2nd | 43845 | 43852 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0543 | Check fixation for Main Grade Earthing System in Ground floor at axis (0_L) with axis (11-12) at zones (z3a) accordding to the attached sketch. _Earthing Rods no.=2 _Cable Size 240 mm=40 m _Cable Size 95 mm=50 m . | ELEC | Z3A | Z3A | GF | 43845 | 43855 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0544 | Check second fix,continuity test,megger test for small power system in second floor at zone (Z3b,4) for PP-IC-2-1 refer to electrical room (IC) accordding to the attached sketch. _No. of lines=50. _Duplex socket(16A) =103 _single socket (16A)=53 _Disconnect switsh(20A)=31. | ELEC | Z3B,4 | Z3B,4 | 2nd | 43845 | 43853 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0545 | Check second fix,continuity test,megger test for small power system in second floor at zone (Z3b,4) for PP-IC-2-2 refer to electrical room (IC) accordding to the attached sketch. _No. of lines=33. _Duplex socket(16A) =26 _single socket (16A)=53 _Disconnect switsh(20A)=26 _H,D=4 _Duplex socket(32A)=1 _Duplex socket(20A)=1. | ELEC | Z3B,4 | Z3B,4 | 2nd | 43845 | 43853 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0546 | Check second fix,continuity test,megger test for small power system in second floor at zone (3b,4) for EPP-UPS-IC-2 refer to electrical room (IC) accordding to the attached sketch. _No. of lines=52. _Duplex socket(16A) =18 _single socket (16A)=218 _Duplex socket(32A) =3 _Duplex socket(20A) =3. | ELEC | Z3B,4 | Z3B,4 | 2nd | 43845 | 43853 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0547 | Check second fix,continuity test,megger test for small power system second floorat zone (Z5) for PP-ID-2 refer to electrical room (ID) accordding to the attached sketch. _No. of lines=38 . _Duplex socket(16A) =52 _single socket (16A)=67 _Disconnect switsh(20A)=33. | ELEC | Z5 | Z5 | 2nd | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0548 | Check second fix,continuity test,megger test for small power system second floor at zone (Z5) for pannel EPP-UPS-ID-2 refer to electrical room (ID) accordding to the attached sketch. _No. of lines=24 . _Duplex socket(16A) =30 _single socket (16A)=58 _Duplex socket(32A)=3 _Duplex socket(20A)=2. | ELEC | Z5 | Z5 | 2nd | 43845 | 43852 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0549 | Check second fix,continuity test,megger test for small power system in the third floor at zone (Z1) for PP-IA-3 refer to electrical room (IA) accordding to the attached sketch. _No. of lines=43 . _Duplex socket(16A) =58 _single socket (16A)=78 _Disconnect switsh(20A)=38. | ELEC | Z1 | Z1 | 3rd | 43845 | 43853 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0550 | Check second fix,continuity test,megger test for small power system in third floor at zone (Z1) for pannel EPP-UPS-IA-3 refer to electrical room (IA) accordding to the attached sketch. _No. of lines=27 . _Duplex socket(16A) =27 _single socket (16A)=72 _Duplex socket(32A)=3 _Duplex socket(20A)=2. | ELEC | Z1 | Z1 | 3rd | 43845 | 43853 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0551 | Check second fix,continuity test,megger test for small power system in third floor at zone (Z2,3a) for PP-Ib-3-1 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=41. _Duplex socket(16A) =87 _single socket (16A)=56 _Disconnect switsh(20A)=30. | ELEC | Z2,3A | Z2,3A | 3rd | 43845 | 43853 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0552 | Check second fix,continuity test,megger test for small power system in the third floor at zone (Z2,3a) for PP-Ib-3-2 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=37. _Duplex socket(16A) =32 _single socket (16A)=42 _Disconnect switsh(20A)=26 _H.D =4 _Duplex socket(32A) =1 _Duplex socket(20A) =1. | ELEC | Z2,3A | Z2,3A | 3rd | 43845 | 43853 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0553 | Check second fix,continuity test,megger test for small power system in the third floor at zone (Z2,3a) for EPP-UPS-IB-3 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=46. _Duplex socket(16A) =18 _single socket (16A)=192 _Duplex socket(32A) =3 _Duplex socket(20A) =2. | ELEC | Z2,3A | Z2,3A | 3rd | 43845 | 43853 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0554 | Check second fix,continuity test,megger test for small power system in the third floor at zone (Z3b,4) for PP-IC-3-1 refer to electrical room (IC) accordding to the attached sketch. _No. of lines=37. _Duplex socket(16A) =62 _single socket (16A)=70 _Disconnect switsh(20A)=28. | ELEC | Z3B,4 | Z3B,4 | 3rd | 43845 | 43853 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0555 | Check second fix,continuity test,megger test for small power system in the third floor at zone (Z3b,4) for PP-IC-3-2 refer to electrical room (IC) accordding to the attached sketch. _No. of lines=30. _Duplex socket(16A) =22 _single socket (16A)=43 _Disconnect switsh(20A)=29 _H,D=4 _Duplex socket(32A)=1 _Duplex socket(20A)=1. | ELEC | Z3B,4 | Z3B,4 | 3rd | 43845 | 43853 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0556 | Check second fix,continuity test,megger test for small power system in the third floor at zone (3b,4) for EPP-UPS-IC-3 refer to electrical room (IC) accordding to the attached sketch. _No. of lines=34. _Duplex socket(16A) =36 _single socket (16A)=108 _Duplex socket(32A) =3 _Duplex socket(20A) =3. | ELEC | Z3B,4 | Z3B,4 | 3rd | 43845 | 43853 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0557 | Check second fix,continuity test,megger test for small power system in the third floor at zone (Z5) for PP-ID-3 refer to electrical room (ID) accordding to the attached sketch. _No. of lines=52 . _Duplex socket(16A) =86 _single socket (16A)=75 _Disconnect switsh(20A)=34. | ELEC | Z5 | Z5 | 3rd | 43845 | 43853 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0558 | Check second fix,continuity test,megger test for small power system in the third floor at zone (Z5) for pannel EPP-UPS-ID-3 refer to electrical room (ID) accordding to the attached sketch. _No. of lines=37 . _Duplex socket(16A) =19 _single socket (16A)=142 _Duplex socket(32A)=3 _Duplex socket(20A)=2. | ELEC | Z5 | Z5 | 3rd | 43845 | 43853 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0559 | Check second fix,continuity test,megger test for small power system in second floor at zone (Z2,3a) for EPP-UPS-IB-2 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=38. _Duplex socket(16A) =27 _single socket (16A)=168 _Duplex socket(32A) =3 _Duplex socket(20A) =3. | ELEC | Z2,3A | Z2,3A | 2nd | 43845 | 43852 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0560 | Check second fix,continuity test,megger test and pannel installation for small power system in 7-th floor pannel PP_IB_7 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=59 _single Socket (16A) Outlets=82 _Duplex Socket (16A)=100 _Dissconnect Switch(20A/220v)=50 _H.D=4 _Duplex Socket (32A)=1 _Duplex Socket (20A)=1 . | ELEC | Z2,3A | Z2,3A | 7th | 43851 | 43857 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0561 | Check second fix,continuity test,megger test and pannel installation for small power system in 7-th floor pannel EPP_UPS_IB_7 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=32 _single Socket (16A) Outlets=176 _Duplex Socket (16A)=16 _Duplex Socket (32A)=3 _Duplex Socket (20A)=3 . | ELEC | Z2,3A | Z2,3A | 7th | 43851 | 43857 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0562 | Check second fix,continuity test,megger test and pannel installation for small power system in 7-th floor pannel EPP_UPS_IC_7 at zone (3b,4) refer to electrical room (IC) according to the attached sketch. _No.of lines=36 _single Socket (16A) Outlets=140 _Duplex Socket (16A)=32 _Duplex Socket (32A)=2 _Duplex Socket (20A)=6 . | ELEC | Z3B,4 | Z3B,4 | 7th | 43851 | 43857 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0563 | Check second fix,continuity test,megger test and pannel installation for lighting system in 7-th floor pannel ELP_CB_IB_07 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _No. of lines=12 _Exit outlets =21 _C.B outlets=41 . | ELEC | Z2,3A | Z2,3A | 7th | 43851 | 43857 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0564 | Check second fix,continuity test,megger test and pannel installation for lighting system in 7-th floor pannel LP_IB_07 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _No. of lines=20 _Lighting outlets =175 . | ELEC | Z2,3A | Z2,3A | 7th | 43851 | 43857 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0565 | Check second fix,continuity test,megger test and pannel installation for small power system in 7-th floor pannel PP_IC_7 at zone (3b,4) refer to electrical room (IC) according to the attached sketch. _No.of lines=61 _single Socket (16A) Outlets=86 _Duplex Socket (16A)=95 _Dissconnect Switch(20A/220v)=53 _H.D=4 _Duplex Socket (32A)=2 _Duplex Socket (20A)=2 . | ELEC | Z3B,4 | Z3B,4 | 7th | 43851 | 43857 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0566 | Check second fix,continuity test,megger test and pannel installation for lighting system in 8-th floor pannel LP_IB_08 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _No. of lines=21 _Lighting outlets =185 . | ELEC | Z2,3A | Z2,3A | 8th | 43851 | 43858 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0567 | Check second fix,continuity test,megger test and pannel installation for lighting system in 8-th floor pannel ELP_CB_IB_08 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _No. of lines=10 _Exit outlets =10 _C.B outlets=23 . | ELEC | Z2,3A | Z2,3A | 8th | 43851 | 43862 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0568 | Check second fix,continuity test,megger test and pannel installation for small power system in 8-th floor pannel PP_IB_8_1 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=33 _single Socket (16A) Outlets=67 _Duplex Socket (16A)=15 _Dissconnect Switch(20A/220v)=30 _H.D=4 _Duplex Socket (32A)=1 _Duplex Socket (20A)=1 . | ELEC | Z2,3A | Z2,3A | 8th | 43851 | 43858 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0569 | Check second fix,continuity test,megger test and pannel installation for small power system in 6-th floor pannel PP_IB_8_2 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=51 _single Socket (16A) Outlets=50 _Duplex Socket (16A)=62 _Dissconnect Switch(20A/220v)=12 . | ELEC | Z2,3A | Z2,3A | 6th | 43851 | 43858 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0570 | Check second fix,continuity test,megger test and pannel installation for small power system in 8-th floor pannel EPP_UPS_IB_8 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=49 _single Socket (16A) Outlets=168 _Duplex Socket (16A)=7 _Duplex Socket (32A)=5 _Duplex Socket (20A)=2 . | ELEC | Z2,3A | Z2,3A | 8th | 43851 | 43858 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0571 | PLS Check the installation of floor boxies at first floor accordding to the attached sketch. _No.of (FB1)=260 _ No.of (FB2)=16 _No.of (FB4)=30 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43856 | 43872 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0572 | PLS Check the installation of floor boxies at the second floor accordding to the attached sketch. _No.of (FB1)=260 _ No.of (FB2)=33 _No.of (FB4)=48 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43856 | 43874 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0573 | PLS Check the installation of floor boxies at third floor accordding to the attached sketch. _No.of (FB1)= 97 _ No.of (FB2)=34 _No.of (FB4)=70 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43856 | 43872 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0574 | PLS Check the installation of floor boxies at fourth floor accordding to the attached sketch. _No.of (FB1)=115 _ No.of (FB2)=53 _No.of (FB4)=66 | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43856 | 43872 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0575 | PLS Check the installation of floor boxies at fifth floor accordding to the attached sketch. _No.of (FB1)=92 _ No.of (FB2)=31 _No.of (FB4)=46 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43856 | 43872 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0576 | PLS Check the installation of floor boxies at sixth floor accordding to the attached sketch. _No.of (FB1)=69 _ No.of (FB2)=17 _No.of (FB4)=19 . | ELEC | Z2,3,4 | Z2,3,4 | 6th | 43856 | 43872 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0577 | PLS Check the installation of floor boxies at 7-th floor accordding to the attached sketch. _No.of (FB1)=42 _ No.of (FB2)=37 _No.of (FB4)=10 . | ELEC | Z2,3,4 | Z2,3,4 | 7th | 43856 | 43872 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0578 | PLS Check the installation of floor boxies at 8-th floor accordding to the attached sketch. _No.of (FB1)=44 _ No.of (FB2)=4 _No.of (FB4)=6 . | ELEC | Z3 | Z3 | 8th | 43856 | 43872 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0579 | Check second fixtion,continuity test,megger test and pannel installation for lighting system in fourth floo at zone (Z1) LP_IA_04 refer to electrical room (IA) accordding to the attached sketch. _ lighting lines=11 _Lighting outlets =103 . | ELEC | Z1 | Z1 | 4th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0580 | Check second fixtion,continuity test,megger test and pannel installation for lighting system in fourth floor at zone (Z1) ELP_IA_04 refer to electrical room (IA) accordding to the attached sketch. _Emergency lighting lines=8 _power lines =6 _Emergency Lighting outlets=65 _Duplex socket(16A)=7 _single socket(16A)=3. | ELEC | Z1 | Z1 | 4th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0581 | Check second fixtion,continuity test,megger test and pannel installation for lighting system in fourth floor at zone (Z1) ELP_CB_IA_04 refer to electrical room (IA) accordding to the attached sketch. _ No.of lines=6 _Exit outlets=6 _C.B outlets =10 . | ELEC | Z1 | Z1 | 4th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0582 | Check second fix,continuity test,megger test and pannel installation for lighting system in fourth floor pannel LP_IB_04 at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _Lighting lines=25 _Lighting outlets =216 . | ELEC | Z2,3A | Z2,3A | 4th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0583 | Check second fix,continuity test,megger test and pannel installation for lighting system in fourth floor pannel ELP_IB_04 at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _No. of lighting lines=22 _No.of power lines =8 _No. of lighting outlets =155 _single socket(16A)=9 _Duplex socket(16A)=2 _3PH SPU(25A)=1 . | ELEC | Z2,3A | Z2,3A | 4th | 43858 | 43869 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0584 | Check second fix,megger test,continuity test and pannel installation for lighting system in fourth floor pannel ELP_CB_IB_04 at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _central battary lines=9 _central battary outlets =21 _exit outlets =8 . | ELEC | Z2,3A | Z2,3A | 4th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0585 | Check second fixtion,continuity test,megger test and pannel installation for lighting system in fourth floor pannel LP_IC_04 at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _Lighting lines=24 _Lighting outlets =257 . | ELEC | Z3B,4 | Z3B,4 | 4th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0586 | Check second fixtion,continuity test,megger test and pannel installation for lighting system in fourth floor pannel ELP_IC_04 at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _Lighting lines=22 _Lighting outlets =145 _Power lines =13 _Single socket(16A)=4 _Duplex socket(16A)=12 _3ph.SP.U(25A)=2. | ELEC | Z3B,4 | Z3B,4 | 4th | 43858 | 43869 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0587 | Check second fixtion,continuity test,megger test and pannel installation for lighting system in fourth floor pannel ELP_CB_IC_04 at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _central battary lines=10 _central battary outlets =24 _exit outlets =12. | ELEC | Z3B,4 | Z3B,4 | 4th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0588 | Check second fixtion,continuity test,megger test and pannel installation in fourth floor zone (Z5) LP_ID_04 refer to electrical room (ID) accordding to the attached sketch. _Lighting lines=13 . _ lighting outlets =109 | ELEC | Z5 | Z5 | 4th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0589 | Check second fixtion,continuity test,megger test and pannel installation in fourth floor at zone (Z5) ELP_ID_04 refer to electrical room (ID) accordding to the attached sketch. _Emergency lines=5 . _C.B lighting outlets =9 _Exit outlets =6. | ELEC | Z5 | Z5 | 4th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0590 | Check second fix,continuity test,megger test and pannel installation for lighting system fifth floor at zone (Z1) LP_IA_05 refer to electrical room (IA) accordding to the attached sketch. _normal Lighting lines= 12 _normal lighting outlets =111. | ELEC | Z1 | Z1 | 5th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0591 | Check second fix,megger test,continuity test and pannel installation for lighting system in fifth floor at zone (Z1) ELP_IA_05 refer to electrical room (IA) accordding to the attached sketch. _Emergency lighting lines=23 _emergency lighting outlets =75 _power lines =11 _Duplex socket(16A)=4 _single socket(16A)=7 _3ph.sp.u(25A)=2 . | ELEC | Z1 | Z1 | 5th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0592 | Check second fix,megger test,continuity test and pannel installation for lighting system in fifth floor pannel ELP_CB_IA_05 at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _central battary lines=8 _central battary outlets =17 _exit outlets =13. | ELEC | Z1 | Z1 | 5th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0593 | Check second fix,continuity,megger test and pannel installation for lighting system in fifth floor pannel LP_IB_05 at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _normal Lighting lines= 22 _normal lighting outlets =218 . | ELEC | Z2,3A | Z2,3A | 5th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0594 | Check second fix,megger test,continuity test and pannel installation for lighting system in fifth floor Pannel ELP_IB_05 at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _emergenc lighting lines =21 _emergencey lighting outlets=159 _emergency power lines =11 _single socket(16A)=6 _Duplex socket(16A)=9. | ELEC | Z2,3A | Z2,3A | 5th | 43858 | 43869 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0595 | Check second fix,continuity test,megger test and pannel installation for lighting system in fifth floor pannel ELP_CB_IB_05 at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _central battary lines=9 _central battary outlets =25 _exit outlets =11 . | ELEC | Z2,3A | Z2,3A | 5th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0596 | Check second fix,continuity test,megger test and pannel installation for lighting system in fifth floor pannel LP_IC_05 at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _normal Lighting lines= 21 _normal lighting outlets =246 . | ELEC | Z3B,4 | Z3B,4 | 5th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0597 | Check second fix,continuity test,megger test and pannel installation for lighting system in fifth floor pannel ELP_IC_05 at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _emergency lighting lines =18 _emergencey lighting outlets=126 _emergency power lines =14 _3ph.sp.u(25A)=2 _single socket(16A)=7 _Duplex socket(16A)=8. | ELEC | Z3B,4 | Z3B,4 | 5th | 43858 | 43869 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0598 | Check second fix,megger test,continuity test and pannel installation for lighting system in fifth floor pannel ELP_CB_IC_05 at axis (F_L) with axis (1-9) at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _central battary lines=8 _central battary outlets =24 _exit outlets =13. | ELEC | Z3B,4 | Z3B,4 | 5th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0599 | Check second fix,continuity test,megger test and pannel installation for lighting system in fifth floor at zone (Z5) LP_ID_05 refer to electrical room (ID) accordding to the attached sketch. _normal Lighting lines= 11 _normal lighting outlets =113 . | ELEC | Z5 | Z5 | 5th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0600 | Check second fix,continuity test,megger test and pannel installation for lighting system in fifth floor at zone (Z5) ELP_ID_05 refer to electrical room (ID) accordding to the attached sketch. _Emergency lighting lines=13 . _Emergency lighting outlets =78 _Power lines =11 _single socket(16A)=6 _Duplex socket(16A)=2. _3ph.sp.u(25A)=2 | ELEC | Z5 | Z5 | 5th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0601 | Check second fix,continuuity,megger test and pannel installation for lighting system in fifth floor at zone (Z5) ELP_ID_CB_05 refer to electrical room (ID) accordding to the attached sketch. _central battary lines=10 _central battary outlets =21 _exit outlets =14. | ELEC | Z5 | Z5 | 5th | 43858 | 43869 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0602 | Check first fixation for low voltage and low current man holes at site plane accordding to the attached sketch _LV man holes= 10 _LC man holes=28. | ELEC | L.S | L.S | EX | 43864 | 43869 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0603 | Check the first fixation and race way for site plane lighting accordding to the attached sketch . _no. of outlets=860 | ELEC | L.S | L.S | EX | 43864 | 43883 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0604 | Check second fix,continuity test,megger test for small power system in the fourth floor at zone (Z1) for pannel PP-IA-4 refer to electrical room (IA) accordding to the attached sketch. _No. of lines=42 . _Duplex socket(16A) =61 _single socket (16A)=66 _Disconnect switsh(20A)=32. | ELEC | Z1 | Z1 | 4th | 43864 | 43876 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0605 | Check second fix,continuity test,megger test for small power system in the fourth floor at zone (Z1) for pannel EPP-UPS-IA-4 refer to electrical room (IA) accordding to the attached sketch. _No. of lines=30 . _Duplex socket(16A) =26 _single socket (16A)=81 _Duplex socket(32A)=3 _Duplex socket(20A)=2. | ELEC | Z1 | Z1 | 4th | 43864 | 43876 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0606 | Check second fix,continuity test,megger test for small power system in the fourth floor at zone (Z3b,4) for PP-IB-4-1 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=43 . _Duplex socket(16A) =62 _single socket (16A)=14 _Disconnect switsh(20A)=30. | ELEC | Z3B,4 | Z3B,4 | 4th | 43864 | 43876 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0607 | Check second fix,continuity test,megger test for small power system in the fourth floor at zone (Z3a) for PP-IB-4-2 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=44 . _Duplex socket(16A) =45 _single socket (16A)=28 _Disconnect switsh(20A)=28 _H.D(20A)=4 _Duplex socket(32A)=1 _socket(20A)=1. | ELEC | Z3A | Z3A | 4th | 43864 | 43888 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0608 | Check second fix,continuity test,megger test for small power system in the fourth floor at zone (Z3a) for pannel EPP-UPS-IB-4 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=54 . _Duplex socket(16A) =22 _single socket (16A)=160 _Duplex socket(32A)=3 _ socket(20A)=2. | ELEC | Z3A | Z3A | 4th | 43864 | 43876 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0609 | Check second fix,continuity test,megger test for small power system in the fourth floor at zone (Z4) for PP-IC-4-1 refer to electrical room (IC) accordding to the attached sketch. _No. of lines=40 . _Duplex socket(16A) =75 _single socket (16A)=41 _Disconnect switsh(20A)=30. | ELEC | Z3B,4 | Z3B,4 | 4th | 43864 | 43876 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0610 | Check second fix,continuity test,megger test for small power system in the fourth floor at zone (Z4) for PP-IC-4-2 refer to electrical room (IC) accordding to the attached sketch. _No. of lines=30 . _Duplex socket(16A) =17 _single socket (16A)=41 _Disconnect switsh(20A)=28 _H.D(20A)=4 _Duplex socket(32A)=1 _socket(20A)=1. | ELEC | Z3B,4 | Z3B,4 | 4th | 43864 | 43888 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0611 | Check second fix,continuity test,megger test for small power system in the fourth floor at zone (Z4) for pannel EPP-UPS-IC-4 refer to electrical room (IC) accordding to the attached sketch. _No. of lines=41 . _Duplex socket(16A) =30 _single socket (16A)=150 _Duplex socket(32A)=3 _Duplex socket(20A)=3. | ELEC | Z3B,4 | Z3B,4 | 4th | 43864 | 43876 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0612 | Check second fix,continuity test,megger test for small power system in the fourth floor at zone (Z5) for PP-ID-4 refer to electrical room (ID) accordding to the attached sketch. _No. of lines=50 . _Duplex socket(16A) =92 _single socket (16A)=52 _Disconnect switsh(20A)=33. | ELEC | Z5 | Z5 | 4th | 43864 | 43876 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0613 | Check second fix,continuity test,megger test for small power system in the fourth floor at zone (Z5) for pannel EPP-UPS-ID-4 refer to electrical room (ID) accordding to the attached sketch. _No. of lines=37 . _Duplex socket(16A) =17 _single socket (16A)=142 _Duplex socket(32A)=3 _ socket(20A)=2. | ELEC | Z5 | Z5 | 4th | 43864 | 43876 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0614 | Check the second fix (Cable Pulling for low voltage cables) accordding to the attached table. (Check Cables Pulling for low voltage cables from main low voltage room I1 accordding to the attached table). (Check Cables Installation and Cables Megger Test for low voltage cables from main low voltage room I1 accordding to the attached table). | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 43870 | 43883 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0615 | Check the second fix (Cable Pulling for low voltage cables) accordding to the attached table. (Check Cables Pulling for low voltage cables from main low voltage room I2 accordding to the attached table).(Check Cables Installation and Cables Megger Test for low voltage cables from main low voltage room I2 accordding to the attached table). | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | ML | 43870 | 43883 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0616 | Check second fix,continuity test,megger test and pannel installation for lighting system in 9-th floor pannel LP_IB_09 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=28 _Lighting outlets =365 . | ELEC | Z3 | Z3 | 9th | 43873 | 43883 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0617 | Check second fix,continuity test,megger test and pannel installation for lighting system in 9-th floor pannel ELP_IB_9-1 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=35 _Lighting outlets =369 . | ELEC | Z3 | Z3 | 9th | 43873 | 43883 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0618 | Check second fix,continuity test,megger test and pannel installation for lighting system in 9-th floor pannel ELP_CB_IB_09 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=11 _Exit outlets =19 _C.B outlets=43 . | ELEC | Z3 | Z3 | 9th | 43873 | 43883 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0619 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the first floor (Z1) pannel EPP_UPS_IA_1_1 refer to electrical room (IA) accordding to the attached sketch. _number of lines=24 _Duplex socket(16A)=7 _single socket(16A)=105 . | ELEC | Z1 | Z1 | 1st | 43873 | 43884 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0620 | Check second fix,continuity test,megger test and pannel installation for small power system in the first floor at (Z1) pannel EPP_UPS_IA_1_2 refer to electrical room (IA) accordding to the attached sketch. _NO. of lines= 35 _Duplex socket(16A) =7 _single socket(16A)=151 _Duplex socket(32A)=3 _Duplex socket(20A)=2 . | ELEC | Z1 | Z1 | 1st | 43873 | 43883 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0621 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the first floor (Z1) pannel PP_IA_1_1 refer to electrical room (IA) accordding to the attached sketch. _number of lines=32 _Duplex socket(16A)=54 _single socket(16A)=42 _s.p.u(25)=11 . | ELEC | Z1 | Z1 | 1st | 43873 | 43883 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0622 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the first floor (Z1) pannel EPP_UPS_IA_1_2 refer to electrical room (IA) accordding to the attached sketch. _number of lines=42 _Duplex socket(16A)=86 _single socket(16A)=52 _s.p.u(25A)=20 . | ELEC | Z1 | Z1 | 1st | 43873 | 43883 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0623 | Check the installation,cable pulling and termination for Disconnect switch (Power for Hvac system) in the first floor accordding to the attached sketch. _total disconnect switch(220v-20A)= 133 _Disconnect switch(380v-40A)=4 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43877 | 43900 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0624 | Check the installation,cable pulling and termination for Disconnect switch (Power for Hvac system) in the fourth floor accordding to the attached sketch. _total disconnect switch(220v-20A)= 163 _Disconnect switch(380v-40A)=4 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43877 | 43900 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0625 | Check the installation,cable pulling and termination for Disconnect switch (Power for Hvac system) in the fifth floor accordding to the attached sketch. _total disconnect switch(220v-20A)= 153 _Disconnect switch(380v-40A)=4 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43877 | 43900 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0626 | Check the installation,cable pulling and termination for Disconnect switch (Power for Hvac system) in the sixth floor accordding to the attached sketch. _total disconnect switch(220v-20A)= 97 _Disconnect switch(380v-40A)=10 . | ELEC | Z2,3,4 | Z2,3,4 | 6th | 43877 | 43900 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0627 | Check the installation,cable pulling and termination for Disconnect switch (Power for Hvac system) in the 7-th floor accordding to the attached sketch._total disconnect switch(220v-20A)= 93 _Disconnect switch(380v-40A)=4 . | ELEC | Z2,3,4 | Z2,3,4 | 7th | 43877 | 43900 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0628 | Check the installation,cable pulling and termination for Disconnect switch (Power for Hvac system) in the 8-th floor accordding to the attached sketch._total disconnect switch(220v-20A)= 38 _Disconnect switch(380v-40A)=6 . | ELEC | Z3 | Z3 | 8th | 43877 | 43900 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0629 | Check second fix,continuity test,megger test and pannel installation for lighting system in first floor at axis (A_F) with axis (14-18) at zone (Z1) ELP_IA_01 refer to electrical room (IA) accordding to the attached sketch. _Lighting lines=17 _ lighting outlets =107 _Power lines=2 _single socket(16A)=3 . | ELEC | Z1 | Z1 | 1st | 43878 | 43884 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0630 | Check second fix,continuity test,megger test for small power system in the fifth floor at zone (Z1) for pannel PP-IA-5 refer to electrical room (IA) accordding to the attached sketch. _No. of lines=49 . _Duplex socket(16A) =74 _single socket (16A)=60 _Disconnect switsh(20A)=25. | ELEC | Z1 | Z1 | 5th | 43879 | 43895 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0631 | Check second fix,continuity test,megger test for small power system in the fifth floor at zone (Z1) for pannel EPP-UPS-IA-5 refer to electrical room (IA) accordding to the attached sketch. _No. of lines=38 . _Duplex socket(16A) =9 _single socket (16A)=124 _Duplex socket(32A)=3 _Duplex socket(20A)=3. | ELEC | Z1 | Z1 | 5th | 43879 | 43895 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0632 | Check second fix,continuity test,megger test for small power system in the fifth floor at zone (Z3a) for PP-IB-5-1 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=35 . _Duplex socket(16A) =59 _single socket (16A)=59 _Disconnect switsh(20A)=28 EWH = 1 . | ELEC | Z3A | Z3A | 5th | 43879 | 43895 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0633 | Check second fix,continuity test,megger test for small power system in the fifth floor at zone (Z3a) for PP-IB-5-2 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=29 . _Duplex socket(16A) =21 _single socket (16A)=46 _Disconnect switsh(20A)=17 _H.D(20A)=4 _Kettle(20A)=1 _Cooker(32A)=1 . | ELEC | Z3A | Z3A | 5th | 43879 | 43895 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0634 | Check second fix,continuity test,megger test for small power system in the fifth floor at zone (Z3a) for pannel EPP-UPS-IB-5 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=30 . _Duplex socket(16A) =35 _single socket (16A)=94 _IT RACK (32A)=3 _AV RACK (20A)=1 _ACP(20A) = 1 _ LCP(20A) = 1. | ELEC | Z3A | Z3A | 5th | 43879 | 43895 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0635 | Check second fix,continuity test,megger test for small power system in the fifth floor at zone (Z4) for PP-IC-5-1 refer to electrical room (IC) accordding to the attached sketch. _No. of lines=45. _Duplex socket(16A) =88 _single socket (16A)=50 _Disconnect switsh(20A)=27 _EWH(20A) = 1. | ELEC | Z3B,4 | Z3B,4 | 5th | 43879 | 43888 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0636 | Check second fix,continuity test,megger test for small power system in the fifth floor at zone (Z4) for PP-IC-5-2 refer to electrical room (IC) accordding to the attached sketch. _No. of lines=35 . _Duplex socket(16A) =22 _single socket (16A)=45 _Disconnect switsh(20A)=22 _H.D(20A)=4 . | ELEC | Z3B,4 | Z3B,4 | 5th | 43879 | 43888 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0637 | Check second fix,continuity test,megger test for small power system in the fifth floor at zone (Z4) for pannel EPP-UPS-IC-5 refer to electrical room (IC) accordding to the attached sketch. _No. of lines=44 . _Duplex socket(16A) =24 _single socket (16A)=178 _AV RACK(32A)=1 _IT RACK(32A)=3 _ACP(20A)=1 _LCP(20A) = 1 . | ELEC | Z3B,4 | Z3B,4 | 5th | 43879 | 43888 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0638 | Check second fix,continuity test,megger test for small power system in the fifth floor at zone (Z5) for PP-ID-5 refer to electrical room (ID) accordding to the attached sketch. _No. of lines=52 _Duplex socket(16A) =52 _single socket (16A)=53 _Disconnect switsh(20A)=25. | ELEC | Z5 | Z5 | 5th | 43879 | 43888 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0639 | Check second fix,continuity test,megger test for small power system in the fifth floor at zone (Z5) for pannel EPP-UPS-ID-5 refer to electrical room (ID) accordding to the attached sketch. _No. of lines=25 . _Duplex socket(16A) =8 _single socket (16A)=80 _Duplex socket(32A)=3 _ socket(20A)=3. | ELEC | Z5 | Z5 | 5th | 43879 | 43888 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0640 | PLS Check first fixation for electrical works For (Power, lighting, and light current Systems) at Ground floor Block Work accordding to the attached sketchies. _Lighting switshes and wall mounted otlets= 138 _small power outlets =474 -H.D outlets =9 _data outlets =432 _thermostst outlets =105 | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | GF | 43884 | 43895 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0641 | Please Check first fixtion for power cable trunk in ground floor accordding to the attached sketch. _ Power Cable Trunk(20*10) = 538 m . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | GF | 43884 | 43895 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0642 | Pls Check first fix Installation for Cable Trunks In ground floor according to the attached sketch. _2 Cable Trunks(N1&N2&N3) Size( 30*10cm)= (1025 m) _GSM Cable Trunk size(10*10cm)= (465 m). | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | GF | 43884 | 43895 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0643 | Check the third fix and lighting fixures installation for lighting system at first floor accordding to the attached sketches. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43894 | 43900 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0644 | Check the third fix and lighting fixures installation for lighting system at the second floor accordding to the attached sketches. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43894 | 43900 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0645 | Check the third fix and lighting fixures installation for lighting system at the third floor accordding to the attached sketches. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43894 | 43900 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0646 | Check second fixtion,continuity test,megger test and pannel installation in fourth floor at zone (Z5) ELP_ID_04 refer to electrical room (ID) accordding to the attached sketch. _Emergency lighting lines=9 . _Emergency lighting outlets =58 _Power lines =6 _single socket(16A)=4 _Duplex socket(16A)=4. | ELEC | Z5 | Z5 | 4th | 43895 | 43899 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0647 | Check second fix,continuity test,megger test and pannel installation for lighting system in 7-th floor pannel ELP_CB_IB_07 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _No. of lines=11 _Exit outlets =12 _C.B outlets=28 . | ELEC | Z2,3A | Z2,3A | 7th | 43895 | 43900 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0648 | Check second fix,continuity test,megger test and pannel installation for lighting system in 7-th floor pannel ELP_IB_07 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _No. of lines=30 _Lighting outlets =165 _Duplex socket(16A)=6 _Single socket(16A)=3 _3ph s.u=1 . | ELEC | Z2,3A | Z2,3A | 7th | 43895 | 43899 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0649 | Check second fix,continuity test,megger test and pannel installation for lighting system in 7-th floor pannel ELP_Ic_07 at zone (Z4) refer to electrical room (IC) accordding to the attached sketch. _No. of lines=51 _Lighting outlets =228 _Duplex socket(16A)=4 _Single socket(16A)=5 _3ph s.u=4 . | ELEC | Z2,3A | Z2,3A | 7th | 43895 | 43900 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0650 | Pls Check The Installation and termination of IT Racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at first floor at axis (A_E) with axis (14_18) ( Zone1) Refer to FTR (01-001) according to the attached sketch. | ELEC | Z1 | Z1 | 1st | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0651 | Pls Check The Installation and termination for it racks(N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at first floor at axis (F_L) with axis (10_18) ( Zone2,3a) Refer to FTR (01-010) according to the attached sketch. | ELEC | Z2,3A | Z2,3A | 1st | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0652 | Pls Check Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at first floor at axis (F_L) with axis (1_9) ( Zone3b,4) Refer to FTR (01-026) according to the attached sketch. | ELEC | Z3B,4 | Z3B,4 | 1st | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0653 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at first floor at axis (A_E) with axis (1_9) ( Zone5) Refer to FTR (01-041) according to the attached sketch. | ELEC | Z5 | Z5 | 1st | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0654 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at second floor at axis (A_E) with axis (14_18) ( Zone1) Refer to FTR (02-001) according to the attached sketch. | ELEC | Z1 | Z1 | 2nd | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0655 | Pls Check the Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at second floor at axis (F_L) with axis (10_18) ( Zone2,3a) Refer to FTR (02-010) according to the attached sketch. | ELEC | Z2,3A | Z2,3A | 2nd | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0656 | Pls Check The Installation and terminaion for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at second floor at axis (F_L) with axis (1_9) ( Zone3b,4) Refer to FTR (02-026) according to the attached sketch. | ELEC | Z3B,4 | Z3B,4 | 2nd | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0657 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at second floor at axis (A_E) with axis (1_9) ( Zone5) Refer to FTR (02-041) according to the attached sketch. | ELEC | Z5 | Z5 | 2nd | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0658 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at third floor at axis (A_E) with axis (14_18) ( Zone1) Refer to FTR (03-001) according to the attached sketch. | ELEC | Z1 | Z1 | 3rd | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0659 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at third floor at axis (F_L) with axis (10_18) ( Zone2,3a) Refer to FTR (03-010) according to the attached sketch. | ELEC | Z2,3A | Z2,3A | 3rd | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0660 | Pls Check The Installation and termination for it racks(N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at third floor at axis (F_L) with axis (1_9) ( Zone3b,4) Refer to FTR (03-026) according to the attached sketch. | ELEC | Z3B,4 | Z3B,4 | 3rd | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0661 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at third floor at axis (A_E) with axis (1_9) ( Zone5) Refer to FTR (03-041) according to the attached sketch. | ELEC | Z5 | Z5 | 3rd | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0662 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fourth floor at axis (A_E) with axis (14_18) ( Zone1) Refer to FTR (04-001) according to the attached sketch. | ELEC | Z1 | Z1 | 4th | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0663 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fourth floor at axis (F_L) with axis (10_18) ( Zone2,3a) Refer to FTR (04-010) according to the attached sketch. | ELEC | Z2,3A | Z2,3A | 4th | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0664 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fourth floor at axis (F_L) with axis (1_9) ( Zone3b,4) Refer to FTR (04-026) according to the attached sketch. | ELEC | Z3B,4 | Z3B,4 | 4th | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0665 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fourth floor at axis (A_E) with axis (1_9) ( Zone5) Refer to FTR (03-041) according to the attached sketch. | ELEC | Z5 | Z5 | 4th | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0666 | Pls Check The Installation and termination for (tap off units) at the first floor at cores (A,B,C,D) according to the attached sketch. _tap off (40A)=16 _tap off (63A)=4 _tap off (80A)=2 _tap off (100A)=2 _tap off (160A)=2 . | ELEC |  |  | 1st | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0667 | Pls Check The Installation and termination for (tap off units) at the second floor at cores (A,B,C,D) according to the attached sketch. _tap off (40A)=12 _tap off (63A)=4 _tap off (80A)=1 _tap off (100A)=1 . | ELEC |  |  | 2nd | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0668 | Pls Check The Installation and termination for (tap off units) at the third floor at cores (A,B,C,D) according to the attached sketch. _tap off (40A)=11 _tap off (63A)=5 _tap off (80A)=2 _tap off (100A)=3 . | ELEC |  |  | 3rd | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0669 | Pls Check The Installation and megger test for Bus way at core (A) from B1 up to roof floor according to the attached sketch. _ups bus way (700A) _bus way with feeding unit(700A) . | ELEC |  |  | ML | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0670 | Pls Check The Installation and megger test for Bus way at core (B) from B1 up to roof floor according to the attached sketch. _ups bus way (700A) _bus way with feeding unit(700A) _mcc bus way (1200A) _normal bus way(1600A) . | ELEC |  |  | ML | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0671 | Pls Check The Installation and megger test for Bus way at core (C) from B1 up to roof floor according to the attached sketch._ups bus way (800A) _bus way with feeding unit(700A) _mcc bus way (1200A) _normal bus way(1200A) . | ELEC |  |  | ML | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0672 | Pls Check The Installation and megger test for Bus way at core (D) from B1 up to roof floor according to the attached sketch. _ups bus way (800A) _bus way with feeding unit (700A) . | ELEC |  |  | ML | 43901 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0673 | Pls Check The Installation and termination for (tap off units) at the fourth floor at cores (A,B,C,D) according to the attached sketch. _tap off (40A)=12 _tap off (63A)=4 _tap off (80A)=2 _tap off (125A)=2 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43906 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0674 | Check The Installation and megger test for Bus way (2500A) at B1 from generators room to substations room according to the attached sketch. | ELEC |  |  | B1 | 43907 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0675 | Check The Installation for Bus way (3200A) at B1 from transformers room to substations room according to the attached sketch. | ELEC |  |  | B1 | 43907 | 43915 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0676 | Check the third fix and lighting fixures installation for lighting system at the fourth floor accordding to the attached sketches. | ELEC |  |  | 4th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0677 | Check the third fix and lighting fixures installation for lighting system at the fifth floor accordding to the attached sketches. | ELEC |  |  | 5th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0678 | Check the third fix and lighting fixures installation for lighting system at the sixth floor accordding to the attached sketches. | ELEC |  |  | 6th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0679 | Check the third fix and lighting fixures installation for lighting system at the 7-th floor accordding to the attached sketches. | ELEC |  |  | 7th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0680 | Check the third fix and lighting fixures installation for lighting system at the 8-th floor accordding to the attached sketches. | ELEC |  |  | 8th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0681 | Check the third fix and lighting fixures installation for lighting system at the ninth floor accordding to the attached sketches. | ELEC |  |  | 9th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0682 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at 9-th floor according to the attached sketch. _Number of points =218 _total lengths =13000 m . | ELEC |  |  | 9th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0683 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fifth floor at ( Zone1) Refer to FTR (05-001) according to the attached sketch. | ELEC | Z1 | Z1 | 5th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0684 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fifth floor at ( Zone2) Refer to FTR (05-010) according to the attached sketch. | ELEC | Z2 | Z2 | 5th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0685 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fifth floor at ( Zone4) Refer to FTR (05-026) according to the attached sketch. | ELEC | Z4 | Z4 | 5th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0686 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at fifth floor at ( Zone5) Refer to FTR (05-041) according to the attached sketch. | ELEC | Z5 | Z5 | 5th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0687 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at sixth floor at ( Zone2) Refer to FTR (06-010) according to the attached sketch. | ELEC | Z2 | Z2 | 6th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0688 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at sixth floor at ( Zone4) Refer to FTR (06-026) according to the attached sketch. | ELEC | Z4 | Z4 | 6th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0689 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at 7-th floor at ( Zone2) Refer to FTR (07-006) according to the attached sketch. | ELEC | Z2 | Z2 | 7th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0690 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at 7-th floor at ( Zone4) Refer to FTR (07-020) according to the attached sketch. | ELEC | Z4 | Z4 | 7th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0691 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at 8-th floor at ( Zone3) Refer to FTR (08-012) according to the attached sketch. | ELEC | Z3 | Z3 | 8th | 43927 | 43937 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0692 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at 9-th floor at ( Zone3) Refer to FTR (09-006) according to the attached sketch. | ELEC | Z3 | Z3 | 9th | 43927 | 43932 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0693 | Pls Check The Installation and termination for (tap off units) at the fifth floor at cores (A,B,C,D) according to the attached sketch. _tap off (40A)=13 _tap off (63A)=3 _tap off (80A)=2 . | ELEC |  |  | 5th | 43928 | 43936 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0694 | Pls Check The Installation and termination for (tap off units) at the sixth floor at cores (A,B,C,D) according to the attached sketch. _tap off (40A)=12 _tap off (63A)=2 _tap off (80A)=2 . | ELEC |  |  | 6th | 43928 | 43936 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0695 | Pls Check The Installation and termination for (tap off units) at the 7-th floor at cores (B,C) according to the attached sketches. _tap off (40A)=4 _tap off (63A)=2 _tap off (80A)=2 . | ELEC |  |  | 7th | 43928 | 43936 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0696 | Pls Check The Installation and termination for (tap off units) at the 8-th floor at cores (B,C) according to the attached sketch. _tap off (40A)=5 _tap off (63A)=2 _tap off (80A)=2 . | ELEC |  |  | 8th | 43928 | 43936 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0697 | Pls Check The Installation and termination for (tap off units) at the 9-th floor at core (B) according to the attached sketch. _tap off (40A)=4 _tap off (63A)=1 _tap off (100A)=1 . | ELEC |  |  | 9th | 43928 | 43936 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0698 | Pls Check The Installation and termination for (tap off units) at the first Basement floor at cores (A,B,C,D) according to the attached sketch. _tap off (40A)=9 _tap off (100A)=1 _feeding unit (320/700)=2 . | ELEC |  |  | B1 | 43928 | 43936 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0699 | Pls Check The Installation and termination for (tap off units) at the Ground floor at cores (A,B,C,D) according to the attached sketches. _tap off (40A)=20 _tap off (63A)=3 _tap off (100A)=2 . | ELEC |  |  | GF | 43928 | 43936 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0700 | Check the installation,cable pulling and termination for Dissconnect switch (Power for Hvac system) in the 9-th floor accordding to the attached sketch. _ disconnect switch(220v-20A)= 45 _Disconnect switch(380v-25A)=6 _ disconnect switch(220v-32A)=30 . | ELEC |  |  | 9th | 43928 | 43934 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0701 | Check second fix,continuity test,megger test and pannel installation for small power system in 9-th floor pannel PP_IB_9_1 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=43 _single Socket (16A) Outlets=59 _Duplex Socket (16A)=15 _Dissconnect Switch(20A/220v)=23 _Dissconnect Switch(32A/220v)=20 _H.D=4 _Duplex Socket (32A)=1 _Duplex Socket (20A)=1 . | ELEC | Z2,3A | Z2,3A | 9th | 43928 | 43932 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0702 | Check second fix,continuity test,megger test and pannel installation for small power system in 9-th floor pannel PP_IB_9_2 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=46 _single Socket (16A) Outlets=47 _Duplex Socket (16A)=29 _Disconnect Switch(20A/220v)=16 _Disconnect Switch(32A/220v)=10 . | ELEC | Z2,3A | Z2,3A | 9th | 43928 | 43932 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0703 | Check second fix,continuity test,megger test and pannel installation for small power system in 9-th floor pannel EPP_UPS_IB_9 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=40 _single Socket (16A) Outlets=59 _Duplex Socket (16A)=20 _Duplex Socket (32A)=3 _Duplex Socket (20A)=5 . | ELEC | Z2,3A | Z2,3A | 9th | 43928 | 43932 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0704 | Pls Check mockup Installation for IT Racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at second floor at axis (A_E) with axis (1_9) ( Zone5) Refer to FTR (02-041) according to the attached sketch. | ELEC | Z5 | Z5 | 2nd | 43928 | 43937 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0705 | Pls Check the release for electrical trades above false ceilling at the first floor according to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43932 | 43934 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0706 | Pls Check the release for electrical trades above false ceilling at the second floor according to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43932 | 43934 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0707 | Pls Check the release for electrical trades above false ceilling at the third floor according to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43932 | 43934 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0708 | Pls Check the release for electrical trades above false ceilling at the fourth floor according to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43932 | 43934 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0709 | Pls Check the release for electrical trades above false ceilling at the fifth floor according to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43932 | 43934 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0710 | Check second fix,continuity test,megger test and pannel installation for lighting system in the ground floor at axis (A_F) with axis (12-18) at zone (Z1) LP_IA_G refer to electrical room (IA) accordding to the attached sketch. _normal Lighting lines= 13 _normal lighting outlets=129 . | ELEC | Z1 | Z1 | GF | 43934 | 43937 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0711 | Check second fix,continuity test,megger test and pannel installation for lighting system at the ground floor at axis (A_F) with axis (14-18) at zone (Z1) ELP_IA_G refer to electrical room (IA) accordding to the attached sketch. _Lighting lines=14 _ lighting outlets =112 _Power lines=7 _single socket(16A)=7 _Bridge socket=1 _Duplex socket =4 . | ELEC | Z1 | Z1 | GF | 43934 | 43937 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0712 | Check second fix,continuity test,megger test and pannel installation for lighting system at the ground floor pannel ELP_CB_IA_G at axis (A_F) with axis (12-18) at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _central battary lines=20 _central battary outlets =94. | ELEC | Z1 | Z1 | GF | 43934 | 43937 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0713 | Check second fix,continuity test,megger test and pannel installation for lighting system in the ground floor at axis (A_F) with axis (1-6) at zone (Z5) for pannel LP_ID_G refer to electrical room (ID) accordding to the attached sketch. _normal Lighting lines= 11 _normal lighting outlets =101 . | ELEC | Z5 | Z5 | GF | 43934 | 43937 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0714 | Check second fixt,continuity test,megger test and pannel installation for lighting system in the ground floor at axis (A_F) with axis (1-6) at zone (Z5) ELP_ID_G refer to electrical room (ID) accordding to the attached sketch. _No. of lighting lines=14 _No. of power lines=5 _Emergency lighting outlets =135 _Single Socket Power outlets =8 _Duplex socket(20A\220)=4 . | ELEC | Z5 | Z5 | GF | 43934 | 43937 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0715 | Check second fix,continuity test,megger test and pannel installation for lighting system in the ground floor at axis (A_F) with axis (1-6) at zone (Z5) for pannel ELP_CB_ID_G refer to electrical room (ID) accordding to the attached sketch. _C.B Lighting lines= 20 _C.B lighting outlets =71 . | ELEC | Z5 | Z5 | GF | 43934 | 43937 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0716 | Pls Check the release for electrical trades above false ceilling at the ninth floor according to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 9th | 43934 | 43937 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0717 | Check second fix,continuity test,megger test and pannel installation for small power system in first floor pannel PP_IB_1_1 at zone (2,3b) refer to electrical room (IB) according to the attached sketch. _No.of lines=38 _single Socket (16A) Outlets=42 _Duplex Socket (16A)=109 _Dissconnect Switch(20A/220v)=12 . | ELEC | Z2,3B | Z2,3B | 1st | 43933 | 43948 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0718 | Check second fix,continuity test,megger test and pannel installation for small power system in first floor pannel PP_IB_1_2 at zone (2,3b) refer to electrical room (IB) according to the attached sketch. _No.of lines=52 _single Socket (16A) Outlets=56 _Duplex Socket (16A)=11 _Disconnect Switch(20A/220v)=25 _EWH(20A)=5 _EWH(16A)=2 _H.D=4 _single Socket (32A wp)=2 _kettle(20A)=1 _cooker (32A)=1 . | ELEC | Z2,3B | Z2,3B | 1st | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0719 | Check second fix,continuity test,megger test and pannel installation in the first floor pannel ELP_Ls_IB_01 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _no. of lines= 9 _MFSD=13 _MSD=1 _MD=4 . | ELEC | Z2,3A | Z2,3A | 1st | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0720 | Check second fix,continuity test,megger test and pannel installation in the first floor at axis (A_F) with axis (14-18) at zone (Z1) ELP_LS_IA_01 refer to electrical room (IA) accordding to the attached sketch. _No. lines=6 _MFSD =8 _MD =6 . | ELEC | Z1 | Z1 | 1st | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0721 | Check second fix,continuity test,megger test and pannel installation in the first floor pannel ELP_LS_IC_01 at axis (F_L) with axis (10-18) at zone (Z4) refer to electrical room (Ic) accordding to the attached sketch. _NO. of lines= 9 _MFSD =14 _MSD=1 _MD=6 . | ELEC | Z4 | Z4 | 1st | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0722 | Check second fix,continuity test,megger test and pannel installation in the first floor pannel ELP_LS_ID_01 at axis (F_L) with axis (10-18) at zone (Z5) refer to electrical room (ID) accordding to the attached sketch. _no.of lines= 6 _MFSD=9 _MD=6 . | ELEC | Z5 | Z5 | 1st | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0723 | Check second fix,continuity test,megger test and pannel installation in the fourth floor at axis (A_F) with axis (14-18) at zone (Z1) ELP_LS_IA_04 refer to electrical room (IA) accordding to the attached sketch. _No. lines=6 _MFSD =5 _MSD =2 _MD=1 . | ELEC | Z1 | Z1 | 4th | 43934 | 43946 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0724 | Check second fix,continuity test,megger test and pannel installation in the fourth floor pannel ELP_Ls_IB_04 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _no. of lines= 9 _MFSD=17 _MD=4 . | ELEC | Z2,3A | Z2,3A | 4th | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0725 | Check second fix,continuity test,megger test and pannel installation in the fourth floor pannel ELP_LS_IC_04 at axis (F_L) with axis (10-18) at zone (Z4) refer to electrical room (Ic) accordding to the attached sketch. _NO. of lines= 9 _MFSD =14 _MSD=1 _MD=6 . | ELEC | Z4 | Z4 | 4th | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0726 | Check second fix,continuity test,megger test and pannel installation in the fourth floor pannel ELP_LS_ID_04 at axis (F_L) with axis (10-18) at zone (Z5) refer to electrical room (ID) accordding to the attached sketch. _no.of lines= 6 _MFSD=5 _MSD=3 _MD=4 . | ELEC | Z5 | Z5 | 4th | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0727 | Pls Check The second fix for integrated security system Cables(access door and time attendance) at first floor according to the attached sketch. _DC=34 _CR=16 _DL=16 _DS=3 H=16 . | ELEC |  |  | 1st | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0728 | Pls Check The second fix for integrated security system Cables(access door and time attendance) at the second floor according to the attached sketch. _DC=34 _CR=16 _DL=16 _DS=2 H=16 . | ELEC |  |  | 2nd | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0729 | Pls Check The second fix for integrated security system Cables(access door and time attendance) at thethird floor according to the attached sketch. _DC=34 _CR=15 _DL=15 _DS=1 H=16 . | ELEC |  |  | 3rd | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0730 | Pls Check The second fix for integrated security system Cables(access door and time attendance) at the fourth floor according to the attached sketch. _DC=34 _CR=14 _DL=15 _DS=2 H=16 . | ELEC |  |  | 4th | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0731 | Pls Check The second fix for integrated security system Cables(access door and time attendance) at the fifth floor according to the attached sketch. _DC=34 _CR=15 _DL=15 _DS=2 H=16 . _DS=2 H=16 . | ELEC |  |  | 5th | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0732 | Pls Check The second fix for integrated security system Cables(access door and time attendance) at the fifth floor according to the attached sketch. _DC=34 _CR=15 _DL=15 _DS=2 H=16 . | ELEC |  |  | 5th | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0733 | Pls Check The second fix for integrated security system Cables(access door and time attendance) at the 8-th floor according to the attached sketch. _DC=20 _CR=16 _DL=16 _H=16 . | ELEC |  |  | 8th | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0734 | Pls Check The second fix for integrated security system Cables(access door and time attendance) at the 9-th floor according to the attached sketch. _DC=6 _CR=4 _DL=4 _DS=2 H=4 . | ELEC |  |  | 9th | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0735 | Pls Check The second fix for integrated security system Cables(access door and time attendance) at the ground floor according to the attached sketch. _DC=93 _CR=21 _DL=45 _DS=6 _ H=45 _PAB=11 _CR(wp)=18 _BR=6 . | ELEC |  |  | GF | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0736 | Pls Check The first fix for integrated security system Cables(access door and time attendance) at the ground floor according to the attached sketch. _DC=93 _CR=21 _DL=45 _DS=6 _ H=45 _PAB=11 _CR(wp)=18 _BR=6 . | ELEC |  |  | GF | 43934 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0737 | Check second fix,continuity test,megger test and pannel installation for lighting system in the ground floor at zone (Z3a) LP_IB_G refer to electrical room (IB) accordding to the attached sketch. _normal Lighting lines= 31 _normal lighting outlets =509 . | ELEC | Z3A | Z3A | GF | 43935 | 43937 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0738 | Check second fix,continuity test,megger test and pannel installation for lighting system in the ground floor at zone (Z3a) ELP_IB_G refer to electrical room (IB) accordding to the attached sketch. _Lighting lines=24 _ lighting outlets =196 _Power lines=15 _single socket(16A)=12 _Duplex socket(16A)=9 _lifter(16A)=3 _projector(3)=3 _FACP power=1 . | ELEC | Z3A | Z3A | GF | 43935 | 43946 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0739 | Check second fix,continuity test,megger test and pannel installation for lighting system in the ground floor pannel ELP_CB_IB_G at zone (Z3a) refer to electrical room (IB) accordding to the attached sketch. _central battary lines=22 _central battary outlets =60 _Exit=29 _(M)=2. | ELEC | Z3A | Z3A | GF | 43935 | 43937 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0740 | Check second fix,continuity test,megger test and pannel installation for lighting system in first floor at zone (Z4) LP_IC_G refer to electrical room (IC) accordding to the attached sketch. _normal Lighting lines= 231 _normal lighting outlets=578 . | ELEC | Z4 | Z4 | GF | 43935 | 43937 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0741 | Check second fix,continuity test,megger test and pannel installation for lighting system in the ground floor at zone (Z4) ELP_IC_G refer to electrical room (IC) accordding to the attached sketch. _Lighting lines=26 _ lighting outlets =250 _Power lines=13 _single socket(16A)=18 _Duplex socket(16A)=2 _AV rack(32A)=1 . | ELEC | Z4 | Z4 | GF | 43935 | 43946 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0742 | Check second fix,continuity test,megger test and pannel installation for lighting system in first floor pannel ELP_CB_IC_G at zone (Z4) refer to electrical room (IC) accordding to the attached sketch. _central battary lines=22 _central battary outlets =156. | ELEC | Z4 | Z4 | GF | 43935 | 43937 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0743 | Pleas Check The fluke test for structured cabling system Cables at the fifth floor ( Zone1) Refer to FTR (05-001) according to the attached sketches. | ELEC | Z1 | Z1 | 5th | 43936 | 43946 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0744 | Pls Check the release for electrical trades above false ceilling at the sixth floor according to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 6th | 43944 | 43948 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0745 | Pls Check the release for electrical trades above false ceilling at the 7-th floor according to the attached sketch. | ELEC | Z2,3,4 | Z2,3,4 | 7th | 43944 | 43948 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0746 | Pls Check the release for electrical trades above false ceilling at the 8-th floor according to the attached sketch. | ELEC | Z3 | Z3 | 8th | 43944 | 43948 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0747 | Pls Check the first fix(race way) for BMS system at the first floor according to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 1st | 43944 | 43948 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0748 | Pls Check the first fix(race way) for BMS system at the second floor according to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 2nd | 43944 | 43948 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0749 | Pls Check the first fix(race way) for BMS system at the third floor according to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 3rd | 43944 | 43948 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0750 | Pls Check the first fix(race way) for BMS system at the fourth floor according to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 4th | 43944 | 43948 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0751 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the ground floor (Z1) pannel PP_IA_G refer to electrical room (IA) accordding to the attached sketch. _number of lines=22 _Duplex socket(16A)=6 _single socket(16A)=43 _A.C.U=3 _EWH=3 _VAV=18 _Juicer=1 _Microwave=1 _Kettle=1 _Coffemachine=1 _floor box socket=1 . | ELEC | Z1 | Z1 | GF | 43950 | 43955 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0752 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the ground floor (Z1) pannel EPP_UPS_IA_G refer to electrical room (IA) accordding to the attached sketch. _number of lines=10 _Duplex socket(16A)=11 _single socket(16A)=2 _AVRack socket(32A)=3 _AVRack socket(20A)=1 _ACP socket(20A)=1 _F.Box socket=1 . | ELEC | Z1 | Z1 | GF | 43950 | 43955 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0753 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the ground floor (Z1) pannel PP_IB_G refer to electrical room (IB) accordding to the attached sketch. _number of lines=33 _Duplex socket(16A)=17 _single socket(16A)=48 _A.C.U=3 _EWH=4 _VAV=35 _Kettle(20A)=1 _Coocker(20A)=1 _floor box socket=2 _HD(20A)=4 . | ELEC | Z1 | Z1 | GF | 43950 | 43955 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0754 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the ground floor (Z1) pannel EPP_UPS_IB_G refer to electrical room (IB) accordding to the attached sketch. _number of lines=25 _Duplex socket(16A)=29 _single socket(16A)=4 _IT Rack socket(20A)=11 _IT Rack socket(32A)=3 _floor box socket=1 . | ELEC | Z1 | Z1 | GF | 43950 | 43955 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0755 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the ground floor (Z1) pannel PP_IC_G refer to electrical room (IC) accordding to the attached sketch. _number of lines=40 _Duplex socket(16A)=32 _single socket(16A)=62 _A.C.U=9 _EWH=5 _VAV=35 _Kettle=1 _HD=4 _Coocker=1 _floor box socket=6 . | ELEC | Z1 | Z1 | GF | 43950 | 43955 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0756 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the ground floor (Z1) pannel EPP_UBS_IC_G refer to electrical room (IC) accordding to the attached sketch. _number of lines=32 _Duplex socket(16A)=22 _single socket(16A)=8 _IT rack(32A)=6 _IT rack(20A)=8 . | ELEC | Z1 | Z1 | GF | 43950 | 43955 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0757 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the ground floor (Z1) pannel PP_ID_G refer to electrical room (ID) accordding to the attached sketch. _number of lines=20 _Duplex socket(16A)=22 _single socket(16A)=56 _A.C.U=3 _EWH=1 _VAV=18 _floor box(6) socket=1 . | ELEC | Z1 | Z1 | GF | 43950 | 43955 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0758 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the ground floor (Z1) pannel EPP_UBS_ID_G refer to electrical room (ID) accordding to the attached sketch. _number of lines=17 _Duplex socket(16A)=30 _single socket(16A)=2 _IT rack socket(32)=4 _IT rack socket(20)=3 . | ELEC | Z1 | Z1 | GF | 43950 | 43955 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0759 | Check the first fix (race way) for Dissconnect switch (Power for Hvac system) in the Ground floor accordding to the attached sketch. _disconnect switch(220v-20A)=110 _EO=26 _Disconnect switch(380v-40A)=5 _disconnect switch (ACU)=19 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | GF | 43950 | 43953 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0760 | Check the installation,cable pulling for Dissconnect switch (Power for Hvac system) in the Ground floor accordding to the attached sketch. _disconnect switch(220v-20A)=110 _EO=26 _Disconnect switch(380v-40A)=5 _disconnect switch (ACU)=19 . | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | GF | 43950 | 43955 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0761 | Check first fixtion for EMT race way for electrical work(lighting system) in the roof floor zone (3) refer to accordding to the attached sketch. _ lighting outlets=164 _exit outlets=10 _type M=22 _type f22=2 _type S=4 _type B=2 | ELEC | Z3 | Z3 | RF | 43953 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0762 | Pls Check the first fix for small power system at the roof floor according to the attached Clouded sketch. _number of points =50. | ELEC |  |  | RF | 43953 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0763 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at the ground floor at ( Zone1) Refer to FTR (GF-001) according to the attached sketch. _Number of points =78 _total length = 6400 m . | ELEC | Z1 | Z1 | GF | 43955 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0764 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at the first floor at ( Zone2,3a) Refer to FTR (GF-010) according to the attached sketch. _Number of points =217 _total length =17200 m . | ELEC | Z2,3A | Z2,3A | GF | 43955 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0765 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at the ground floor at (Zone3b,4) Refer to FTR (Gf-026) according to the attached sketch. _Number of points =307 _total length =24500 m . | ELEC | Z3B,4 | Z3B,4 | GF | 43955 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0766 | Pls Check The second fix Installation for Data,Telephone,Tv,cctv,Bms and Wifi Cables at the Ground floor at ( Zone5) Refer to FTR (GF-041) according to the attached sketch. _Number of points =111 _total length =8800 m . | ELEC | Z5 | Z5 | GF | 43955 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0767 | Pleas Check The fluke test for structured cabling system Cables at the fourth floor ( Zone1) Refer to FTR (04-001) according to the attached sketches. | ELEC | Z1 | Z1 | 4th | 43956 | 43969 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0768 | Pleas Check The fluke test for structured cabling system Cables at the fourth floor ( Zone2) Refer to FTR (04-010) according to the attached sketches. | ELEC | Z2 | Z2 | 4th | 43957 | 43969 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0769 | Pls Check the first fix(race way) for BMS system at the fifth floor according to the attached sketch. | ELEC | Z1,2,3,4,5 | Z1,2,3,4,5 | 5th | 43957 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0770 | Pls Check the first fix(race way) for BMS system at the sevinth floor according to the attached sketch. | ELEC | Z2,3,4 | Z2,3,4 | 7th | 43957 | 43962 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0771 | Pleas Check The fluke test for structured cabling system Cables at the fourth floor ( Zone4) Refer to FTR (04-026) according to the attached sketches. | ELEC | Z4 | Z4 | 4th | 43958 | 43969 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0772 | Pleas Check The fluke test for structured cabling system Cables at the fourth floor ( Zone5) Refer to FTR (04-041) according to the attached sketches. | ELEC | Z5 | Z5 | 4th | 43960 | 43970 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0773 | Check second fix,continuity test,megger test and pannel installation for lighting system in first Basement floor at zone (Z1) LP_IA_B1 refer to electrical room (IA) accordding to the attached sketch. _normal Lighting lines= 13 _normal lighting outlets =91 _power lines=22 _FCU(20A)=14 _single socket(16A)=46 _Duplex socket(16A)=1 _H.D=1 _EWH=1 . | ELEC | Z1 | Z1 | B1 | 43961 | 43970 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0774 | Check second fix,continuity test,megger test and pannel installation for lighting system at the first Basement floor at zone (Z1) ELP_IA_B1 refer to electrical room (IA) accordding to the attached sketch. _Lighting lines=17 _ lighting outlets =115 _Power lines=24 _single socket(16A)=3 _3ph(S.U) . | ELEC | Z1 | Z1 | B1 | 43961 | 43970 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0775 | Check second fix,continuity test,megger test and pannel installation for lighting system in the first Basement floor pannel ELP_CB_IA_B1 at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _central battary lines=13 _central battary outlets =50. | ELEC | Z1 | Z1 | B1 | 43961 | 43970 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0776 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the first Baement floor (Z1) pannel EPP_UPS_IA_B1 refer to electrical room (IA) accordding to the attached sketch. _number of lines=6 _Duplex socket(16A)=1 _LCP socket(20A)=2 _ACP socket(20A)=1 _AV rack socket(20A)=1 . | ELEC | Z1 | Z1 | B1 | 43961 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0777 | Check second fix,continuity test,megger test and pannel installation in the first Basement floor at zone (Z1) ELP_LS_IA_B1 refer to electrical room (IA) accordding to the attached sketch. _No. lines=6 _MFSD =14 . | ELEC | Z1 | Z1 | B1 | 43961 | 43970 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0778 | Pleas Check The fluke test for structured cabling system Cables at the fifth floor ( Zone2) Refer to FTR (05-010) according to the attached sketches. | ELEC | Z2 | Z2 | 5th | 43964 | 43983 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0779 | Check second fix,continuity test,megger test and pannel installation for lighting system in the second basement floor at zone (Z1) LP_IA_B2 refer to electrical room (IA) accordding to the attached sketch. _no.of lines= 25 . | ELEC | Z1 | Z1 | B2 | 43964 | 43970 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0780 | Check second fix,continuity test,megger test and pannel installation for lighting system in the second basement floor pannel ELP_CB_IA_B2 at axis (A_F) with axis (12-18) at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _central battary lines=13. | ELEC | Z1 | Z1 | B2 | 43964 | 43970 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0781 | Check second fix,continuity test,megger test and pannel installation for lighting system in the second basement floor at axis (A_F) with axis (14-18) at zone (Z1) ELP_IA_B2 refer to electrical room (IA) accordding to the attached sketch. _Lighting lines=17 _ no. of lines=15 . | ELEC | Z1 | Z1 | B2 | 43964 | 43970 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0782 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the second Baement floor (Z1) pannel EPP_UPS_IA_B2 refer to electrical room (IA) accordding to the attached sketch. _number of lines=6 _Duplex socket(16A)=1 _LCP socket(20A)=2 _ACP socket(20A)=1 _AV rack socket(20A)=1 . | ELEC | Z1 | Z1 | B2 | 43964 | 43969 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0783 | Pleas Check The fluke test for structure cabling system Cables at the third floor ( Zone1) Refer to FTR (03-001) according to the attached sketches. | ELEC | Z1 | Z1 | 3rd | 43965 | 43983 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0784 | Pleas Check The fluke test for structure cabling system Cables at the third floor ( Zone2) Refer to FTR (03-010) according to the attached sketches. | ELEC | Z2 | Z2 | 3rd | 43967 | 43983 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0785 | Check installation for MCC pannel boards and VFD modules at the first floor insid HVAC rooms accordding to the attached sketch. _MCC-1F-IC-01 _MCC-1F-IC-02 _MCC-1F-IC-03 _MCC-1F-IC-04 _VFD(18.5kw)=1 _VFD(22kw)=5. | ELEC |  |  | 1st | 43968 | 43990 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0786 | Check installation for MCC pannel boards and VFD modules at the second floor insid HVAC rooms accordding to the attached sketch. _MCC-2F-IC-01 _MCC-2F-IC-02 _VFD(18.5kw)=3 _VFD(22kw)=1 . | ELEC |  |  | 2nd | 43968 | 43983 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0787 | Check installation for MCC pannel boards and VFD modules at the third floor insid HVAC rooms accordding to the attached sketch. _MCC-3F-IC-01 _MCC-3F-IC-02 _VFD(18.5kw)=3 _VFD(22kw)=1 . | ELEC |  |  | 3rd | 43968 | 43983 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0788 | Check installation for MCC pannel boards and VFD modules at the fourth floor insid HVAC rooms accordding to the attached sketch. _MCC-4F-IC-01 _MCC-4F-IC _MCC-4F-IC-03 _MCC-4F-IC-04 _VFD(18.5kw)=5 _VFD(22kw)=1 . | ELEC |  |  | 4th | 43968 | 43983 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0789 | Check installation of MCC pannel boards and VFD modules at the fifth floor insid HVAC rooms accordding to the attached sketch. _MCC-5F-IC-01 _MCC-5F-IC-02 _VFD(18.5kw)=3 _VFD(22kw)=1. | ELEC |  |  | 5th | 43968 | 43983 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0790 | Check installation of MCC pannel boards and VFD modules at the sixth floor insid HVAC rooms accordding to the attached sketch. _MCC-6F-IC-01 _MCC-6F-IC-02 _VFD(18.5kw)=4 _VFD(4kw)=2. | ELEC |  |  | 6th | 43968 | 43983 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0791 | Check second fix,continuity test ,megger test and pannel installation for lighting system in first Basement floor pannel LP_IB_B1 at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _ Lighting lines= 16 _normal lighting outlets =110 _power lines=9 _single socket(16A)=24 _Duplex socket (16A)=1 _F.Box6 socket=2 _FCU=9 . | ELEC | Z2,3A | Z2,3A | B1 | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0792 | Check second fix,continuity test ,megger test and pannel installation for lighting system in first Basement floor Pannel ELP_IB_B1 at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _emergency lighting lines =13 _emergencey lighting outlets=59 _power lines=9 _3ph spu=2 _1ph spu=1 _FCU=1 _FACP=1 . | ELEC | Z2,3A | Z2,3A | B1 | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0793 | Check second fix,continuity test,megger test and pannel installation for lighting system in first floor pannel ELP_CB_IB_B1 at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _central battary lines=10 _central battary outlets =29 . | ELEC | Z2,3A | Z2,3A | B1 | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0794 | Check second fixt,continuity test,megger test and pannel installation for small power system in the first Basement floor pannel EPP_UPS_IB_B1 at zone (2,3a) refer to electrical room (IB) according to the attached sketch. _No.of lines=6 _Duplex Socket (16A)=2 _IT rack socket(32A)=2 _ACP socket(20A)=1 _LCP socket(20A)=1 | ELEC | Z2,3A | Z2,3A | B1 | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0795 | Check second fix,continuity test,megger test and pannel installation for lighting system in the first Basement floor pannel ELP_Ls_IB_B1 at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _no. of lines= 3 _MFSD=5 _MD=2 . | ELEC | Z2,3A | Z2,3A | B1 | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0796 | Check second fixt,continuity test,megger test and pannel installation for small power system in first Basement floor pannel EPP_UPS_IC_B1 at zone (3b,4) refer to electrical room (IC) according to the attached sketch. _No.of lines=10 _Duplex Socket (16A)=2 _It racksocket(32A)=4 _ACP socket(20A)=2 _LCP socket(20A)=2 . | ELEC | Z3B,4 | Z3B,4 | B1 | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0797 | Check second fix,continuity test,megger test and pannel installation in the first floor pannel ELP_LS_IC_B1 at zone (Z4) refer to electrical room (Ic) accordding to the attached sketch. _NO. of lines= 3 _MFSD =5 _MD=6 . | ELEC | Z4 | Z4 | B1 | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0798 | Check second fix,continuity test,megger test and pannel installation for lighting system in first Basement floor pannel LP_IC_B1 at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _normal Lighting lines= 12 _normal lighting outlets =91 Power lines=22 _Miv=8 _single socket(16A)=25 _Duplex socket(16A)=2 _F.Box6 socket=1 _FCU=1 . | ELEC | Z3B,4 | Z3B,4 | B1 | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0799 | Check second fix,continuity test,megger test and pannel installation for lighting system in first Basement floor pannel ELP_IC_B1 refer to electrical room (IC) accordding to the attached sketch. _emergency lighting lines =10 _emergencey lighting outlets=53 _power lines=13 _Single socket(16A) =5 _ 3ph spu.=3 _single phase spu=2 . | ELEC | Z3B,4 | Z3B,4 | B1 | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0800 | Check second fix,continuity test,megger test and pannel installation for lighting system in first Basement floor pannel ELP_CB_IC_B1 at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _central battary lines= 10 _central battary outlets =41 . | ELEC | Z3B,4 | Z3B,4 | B1 | 43969 | 43981 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0801 | Pleas Check The fluke test for structure cabling system Cables at the fifth floor ( Zone4) Refer to FTR (05-026) according to the attached sketches. | ELEC | Z4 | Z4 | 5th | 43969 | 43983 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0802 | Pleas Check The fluke test for structure cabling system Cables at the fifth floor ( Zone5) Refer to FTR (05-041) according to the attached sketches. | ELEC | Z5 | Z5 | 5th | 43969 | 43983 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0803 | Pleas Check The fluke test for structure cabling system Cables at the third floor ( Zone4) Refer to FTR (03-026) according to the attached sketches. | ELEC | Z4 | Z4 | 3rd | 43969 | 43983 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0804 | Pleas Check The fluke test for structure cabling system Cables at the third floor ( Zone5) Refer to FTR (03-041) according to the attached sketches. | ELEC | Z5 | Z5 | 3rd | 43969 | 43983 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0805 | Check the secondary earth fixation for Earthing System in fifth floor accordding to the attached sketch. _Cable Size 240 mm2=60 m _Cable Size 35 mm2=40 m . | ELEC |  |  | 5th | 43990 | 44003 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0806 | Check the secondary earth fixation for Earthing System in sixth floor accordding to the attached sketch. _Cable Size 35 mm2=40 m . | ELEC |  |  | 6th | 43990 | 44003 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0807 | Check the secondary earth fixation for Earthing System in sevinth floor accordding to the attached sketch. _Cable Size 240 mm2=60 m _Cable Size 35 mm2=40 m . | ELEC |  |  | 7th | 43990 | 44003 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0808 | Check second fix,continuity test,megger test and pannel installation for lighting system in first Basement floor at zone (Z5) for pannel LP_ID_B1 refer to electrical room (ID) accordding to the attached sketch. _normal Lighting lines= 13 _normal lighting outlets =112 _power lines=21 _FCU=19 _single socket(16A)=48 _Duplex socket(16A)=1 _HD=1 _EWH=1 _F.Box6 socket=1 . | ELEC | Z5 | Z5 | B1 | 43990 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0809 | Check second fix,continuity test,megger test and pannel installation for lighting system in first Basement floor at zone (Z5) for pannel ELP_CB_ID_B1 refer to electrical room (ID) accordding to the attached sketch. _C.B Lighting lines= 13 _C.B lighting outlets =50 . | ELEC | Z5 | Z5 | B1 | 43990 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0810 | Check second fixt,continuity test,megger test and pannel installation for lighting system in first Basement floor at zone (Z5) ELP_ID_B1 refer to electrical room (ID) accordding to the attached sketch. _No. of lighting lines=16 . _Emergency lighting outlets =114 _power lines=25 _Single Socket Power outlets =1 _3ph spu=8. | ELEC | Z5 | Z5 | B1 | 43990 | 44003 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0811 | Check second fix,continuity test,megger test and pannel installation in the first Basement floor pannel ELP_LS_ID_B1 at zone (Z5) refer to electrical room (ID) accordding to the attached sketch. _no.of lines= 9 _MFSD=14 . | ELEC | Z5 | Z5 | B1 | 43990 | 44003 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0812 | Check second fixt,continuity test,megger test and pannel installation for small power system in first Basement floor pannel EPP_UPS_ID_B1 at zone (5) refer to electrical room (ID) according to the attached sketch. _No.of lines=6 _Duplex Socket (16A) Outlets=1 _It rack socket(32A)=2 _LCP socket (20A)=2 _ACP socket(20A)=1 . | ELEC | Z5 | Z5 | B1 | 43990 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0813 | Pleas Check The fluke test for structure cabling system Cables at the second floor ( Zone5) Refer to FTR (02-041) according to the attached sketches. | ELEC | Z5 | Z5 | 2nd | 43990 | 43996 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0814 | Pleas Check The fluke test for structure cabling system Cables at the second floor ( Zone4) Refer to FTR (04-026) according to the attached sketches. | ELEC | Z4 | Z4 | 2nd | 43990 | 43996 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0815 | Pleas Check The fluke test for structured cabling system Cables at the second floor ( Zone1) Refer to FTR (02-001) according to the attached sketches. | ELEC | Z1 | Z1 | 2nd | 43990 | 43996 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0816 | Pleas Check The fluke test for structure cabling system Cables at the second floor ( Zone2) Refer to FTR (02-001) according to the attached sketches. | ELEC | Z2 | Z2 | 2nd | 43990 | 43996 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0817 | Pleas Check The fluke test for structured cabling system Cables at the first floor ( Zone1) Refer to FTR (01-001) according to the attached sketches. | ELEC | Z1 | Z1 | 1st | 43990 | 43996 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0818 | Pleas Check The fluke test for structured cabling system Cables at the first floor ( Zone5) Refer to FTR (01-041) according to the attached sketches. | ELEC | Z5 | Z5 | 1st | 43990 | 43996 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0819 | Check second fix,continuity test ,megger test and pannel installation for lighting system in the second basement floor pannel LP_IB_B2 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _normal Lighting lines= 25 . | ELEC | Z2,3A | Z2,3A | B2 | 43991 | 43997 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0820 | Check second fix,continuity test ,megger test and pannel installation for lighting system in the second basement floor Pannel ELP_IB_B2 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _emergency lines =19. | ELEC | Z2,3A | Z2,3A | B2 | 43991 | 43997 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0821 | Check second fix,continuity test,megger test and pannel installation for lighting system in the second basement floor pannel ELP_CB_IB_B2 at axis (F_L) with axis (10-18) at zone (Z3a,2) refer to electrical room (IB) accordding to the attached sketch. _central battary lines=9 _central battary outlets =31 . | ELEC | Z2,3A | Z2,3A | B2 | 43991 | 43996 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0822 | Check second fix,continuity test,megger test and pannel installation for lighting system in the second basement floor pannel LP_IC_B2 at axis (F_L) with axis (1-9) at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _normal Lighting lines= 17 . | ELEC | Z3B,4 | Z3B,4 | B2 | 43991 | 43997 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0823 | Check second fix,continuity test,megger test and pannel installation for lighting system in the seconed basement floor pannel ELP_IC_B2 at axis (F_L) with axis (1-9) at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _emergency lines =20 . | ELEC | Z3B,4 | Z3B,4 | B2 | 43991 | 43997 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0824 | Check second fix,continuity test,megger test and pannel installation for lighting system in the second basement floor pannel ELP_CB_IC_B2 at axis (F_L) with axis (1-9) at zone (Z3b,4) refer to electrical room (IC) accordding to the attached sketch. _central battary lines= 8 . | ELEC | Z3B,4 | Z3B,4 | B2 | 43991 | 43996 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0825 | Check second fix,continuity test,megger test and pannel installation for lighting system in the second basement floor at axis (A_F) with axis (1-6) at zone (Z5) for pannel LP_ID_B2 refer to electrical room (ID) accordding to the attached sketch. _normal Lighting lines= 24 . | ELEC | Z5 | Z5 | B2 | 43991 | 43997 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0826 | Check second fixt,continuity test,megger test and pannel installation for lighting system in the second basement floor at axis (A_F) with axis (1-6) at zone (Z5) ELP_ID_B2 refer to electrical room (ID) accordding to the attached sketch. _No. of lines=18 | ELEC | Z5 | Z5 | B2 | 43991 | 43997 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0827 | Check second fix,continuity test,megger test and pannel installation for lighting system in the second basement floor at axis (A_F) with axis (1-6) at zone (Z5) for pannel ELP_CB_ID_B2 refer to electrical room (ID) accordding to the attached sketch. _C.B Lighting lines= 14 . | ELEC | Z5 | Z5 | B2 | 43991 | 43996 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0828 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the second Baement floor (Z1) pannel EPP_UPS_IB_B2 refer to electrical room (IB) accordding to the attached sketch. _number of lines=6 _Duplex socket(16A)=1 _LCP socket(20A)=2 _ACP socket(20A)=1 _AV rack socket(20A)=1 . | ELEC | Z1 | Z1 | B2 | 43991 | 43996 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0829 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the second Baement floor (Z1) pannel EPP_UPS_IC_B2 refer to electrical room (IC) accordding to the attached sketch. _number of lines=11 . | ELEC | Z1 | Z1 | B2 | 43992 | 43996 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0830 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the second Baement floor (Z1) pannel EPP_UPS_ID_B2 refer to electrical room (ID) accordding to the attached sketch. _number of lines=5 . | ELEC | Z1 | Z1 | B2 | 43992 | 43996 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0831 | Check the third fix and lighting fixures installation for lighting system at the second basement floor accordding to the attached sketches. | ELEC |  |  | B2 | 43992 | 43997 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0832 | Check the third fix and lighting fixures installation for lighting system at the first basement floor accordding to the attached sketches. | ELEC |  |  | B1 | 43992 | 43997 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0833 | Pls Check The first and second fix for integrated security system Cables(access door and time attendance) at first basement floor according to the attached sketch. _DC=75 _CR=39 _DL=69 _BTE=39 _RTE=39 _PAB=6 _TAR=13 . | ELEC |  |  | B1 | 43992 | 43997 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0834 | Pls Check The first and second fix for integrated security system Cables(access door and time attendance) at the second basement floor according to the attached sketch. _DC=46 _CR=22 _DL=38 _BTE=22 _RTE=22 _PAB=6 _TAR=12 . | ELEC |  |  | B2 | 43992 | 43997 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0835 | Pls Check The second fix for integrated security system Cables(access door and time attendance) at the 7th floor according to the attached sketch. _DC=14 _CR=6 _DL=7 _ H=7 _DS=4 | ELEC |  |  | 7th | 43992 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0836 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the ground floor (Z1) pannel EPP_UPS_MTR1-1 accordding to the attached sketch. _number of lines (3ph)=6 .. | ELEC | Z1 | Z1 | GF | 43992 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0837 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the ground floor (Z1) pannel EPP_UPS_MTR1-2 accordding to the attached sketch. _number of lines (3ph)=6 . | ELEC | Z1 | Z1 | GF | 43992 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0838 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the ground floor (Z1) pannel EPP_UBS_MTR-I2-1 refer to electrical room (ID) accordding to the attached sketch. _number of lines(3ph)=14 | ELEC | Z1 | Z1 | GF | 43992 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0839 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the ground floor (Z1) pannel EPP_UBS_MTR-I2-2 refer to electrical room (ID) accordding to the attached sketch. _number of lines(3ph)=14 | ELEC | Z1 | Z1 | GF | 43992 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0840 | Check the first fix (race way) for Dissconnect switch (Power for Hvac system)at the first basement floor accordding to the attached sketch. _disconnect switches=90 _EO=42 . | ELEC |  |  | B1 | 43992 | 43997 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0841 | Check the first fix (race way) for Dissconnect switch (Power for Hvac system) at the second basement floor accordding to the attached sketch. _disconnect switches=65 _EO=5 . | ELEC |  |  | B2 | 43992 | 43997 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0842 | Check first fix for race way cable tray (Power routing) at 8-th floor accordding to the attached sketch. | ELEC |  |  | 8th | 43992 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0843 | Pls Check the first fix(race way) for BMS system at the sixth floor according to the attached sketch. | ELEC |  |  | 6th | 43992 | 43996 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0844 | Pls Check the first fix(race way) for BMS system at the 8th floor according to the attached sketch. | ELEC |  |  | 8th | 43992 | 43996 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0845 | Pls Check the first fix(race way) for BMS system at the ground floor according to the attached sketch. | ELEC |  |  | GF | 43992 | 43996 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0846 | Pls Check the release for electrical trades above false ceilling at the ground floor according to the attached sketch. | ELEC |  |  | GF | 43992 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0847 | Pls Check the release for electrical trades above ceilling at the first basement floor according to the attached sketch. | ELEC |  |  | B1 | 43992 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0848 | Pls Check the release for electrical trades above ceilling at the second basement floor according to the attached sketch. | ELEC |  |  | B2 | 43992 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0849 | Check the (LCP) pannels installation in the ground floor accordding to the attached sketch. | ELEC |  |  | GF | 43995 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0850 | Check the (LCP) pannels installation in the first floor accordding to the attached sketch. | ELEC |  |  | 1st | 43995 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0851 | Check the (LCP) pannels installation in the second floor accordding to the attached sketch. | ELEC |  |  | 2nd | 43995 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0852 | Check the (LCP) pannels installation in the third floor accordding to the attached sketch. | ELEC |  |  | 3rd | 43995 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0853 | Check the (LCP) pannels installation in the fourth floor accordding to the attached sketch. | ELEC |  |  | 4th | 43995 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0854 | Check the (LCP) pannels installation in the fifth floor accordding to the attached sketch. | ELEC |  |  | 5th | 43995 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0855 | Check the (LCP) pannels installation in the sixth floor accordding to the attached sketch. | ELEC |  |  | 6th | 43995 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0856 | Check the (LCP) pannels installation in the seventh floor accordding to the attached sketch. | ELEC |  |  | 7th | 43995 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0857 | Check the (LCP) pannels installation in the 8th floor accordding to the attached sketch. | ELEC |  |  | 8th | 43995 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0858 | Check the (LCP) pannels installation in the 9th floor accordding to the attached sketch. | ELEC |  |  | 9th | 43995 | 44003 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0859 | Check Cables and pannel megger test for pannel (CBP-I11) accordding to the attached sketches. (MEGGER CABLES TEST for pannel (CBP-I11) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0860 | Check Cables and pannel megger test for pannel (CBP-I12) accordding to the attached sketches. (Megger CablesTest For Pannel (CBP-I12) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0861 | Check Cables and pannel megger test for pannel (CBP-I13) accordding to the attached sketches. (Megger Cables Test For Pannel (CBP-I13) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0862 | Check Cables and pannel megger test for pannel (CBP-I21) accordding to the attached sketches. (Megger Cables Test For Pannel (CBP-I21) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0863 | Check Cables and pannel megger test for pannel (CBP-I22) accordding to the attached sketches. (Megger Cables Test For Pannel (CBP-I22) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0864 | Check Cables and pannel megger test for pannel (CBP-I22) accordding to the attached sketches. (Megger Cables Test For Pannel (CBP-I22) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0865 | Check Cables and pannel megger test for pannel (MDBI1) accordding to the attached sketches. (Megger CableTest For Pannel (MDBI1) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0866 | Check Cables and pannel megger test for pannel (MDB-I2) accordding to the attached sketches. (Megger CablesTest For Pannel (MDB-I2) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0867 | Check Cables and pannel megger test for pannel (EMDB-I11) accordding to the attached sketches. ( Megger Cables Test for pannel (EMDB-I11) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0868 | Check Cables and pannel megger test for pannel (EMDB-I12) accordding to the attached sketches. (Megger CablesTest for pannel (EMDB-I12) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0869 | Check Cables and pannel megger test for pannel (EMDB-I21) accordding to the attached sketches. (Megger Cables Test For Pannel (EMDB-I21) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0870 | Check Cables and pannel megger test for pannel (EMDB-I22) accordding to the attached sketches. (Megger CableTest For Pannel (EMDB-I22) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0871 | Check Cables and pannel megger test for pannel (EDBI1-B1) accordding to the attached sketches. (Megger Cables Test For Pannel (EDBI1-B1) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0872 | Check Cables and pannel megger test for pannel (EDB-LS-IA-B1) accordding to the attached sketches. (Megger Cable Test For Pannel (EDB-LS-IA-B1) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0873 | Check Cables and pannel megger test for pannel (DB-I1-B1) accordding to the attached sketches. (Megger CablesTest For Pannel (DB-I1-B1) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0874 | Check Cables and pannel megger test for pannel (EDB-LS-IB-B1) accordding to the attached sketches. (Megger Cables Test For Pannel (EDB-LS-IB-B1) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0875 | Check Cables and pannel megger test for pannel (DB-I2-B1) accordding to the attached sketches. (Megger Cables Test For Pannel (DB-I2-B1) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0876 | Check Cables and pannel megger test for pannel (EDB-LS-ID-B1) accordding to the attached sketches. (Megger Cables Test For Pannel (EDB-LS-ID-B1) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0877 | Check Cables and pannel megger test for pannel (EDB-I2-B1) accordding to the attached sketches. (Megger Cables Test For Pannel (EDB-I2-B1) accordding to the attached sketches). | ELEC |  |  | B1 | 43998 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0878 | Check second fix,megger test,continuity test and pannel inastallation for small power system in the ground floor pannel EPP-UPS-CONC-IC-G accordding to the attached sketch. _number of lines=9 . | ELEC |  |  | GF | 43998 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0879 | Check second fix,continuity test,megger test and pannel installation for lighting system in 9-th floor pannel ELP_IB_9-2 refer to electrical room (IB) accordding to the attached sketch. _No. of lines single phase=10 _No. of lines 3phase=7 . | ELEC | Z3 | Z3 | 9th | 43998 | 44005 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0880 | Mgger Cable Test for pannel (ELP-IB-9-1) From tapp off accordding to the attached sketches. cable size(4X10)+10E CU/XLPE/PVC | ELEC | Z3 | Z3 | 9th | 44000 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0881 | Megger Cable test for pannel (ELP-IB-9-2) from tapp off accordding to the attached sketches. cable size (4X16)+16E CU/XLPE/PVC | ELEC | Z3 | Z3 | 9th | 44000 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0882 | Megger Cable test for pannel (ELP-CB-IB-9) from EDB-CB-IB accordding to the attached sketches for size 2(3X10) CU/MICA/XLPE/SWA/LSHF) | ELEC | Z3 | Z3 | 9th | 44000 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0883 | Megger Cable test for pannel (EPP-UPS-IB-9) from tapp off accordding to the attached sketches. cable size (4X10)+10E CU/XLPE/PVC | ELEC | Z3 | Z3 | 9th | 44000 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0884 | Megger Cable test for pannel (LP-IB-9) from tap off accordding to the attached sketches. cable size (4X10)+10E CU/XLPE/PVC | ELEC | Z3 | Z3 | 9th | 44000 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0885 | Megger CableTest for pannel (PP-IB-9-1) from tap off accordding to the attached sketches. cable size (4X35)+16E CU/XLPE/PVC | ELEC | Z3 | Z3 | 9th | 44000 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0886 | Megger CableTest for pannel (PP-IB-9-2) from tap off accordding to the attached sketches. cable size (4X10)+10E CU/XLPE/PVC | ELEC | Z3 | Z3 | 9th | 44000 | 44005 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0887 | Pleas Check The fluke test for structure cabling system Cables at the sixth floor ( Zone4) Refer to FTR (06-026) according to the attached sketches. | ELEC | Z4 | Z4 | 6th | 44004 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0888 | Pleas Check The fluke test for structure cabling system Cables at the 8-th floor Refer to FTR (08-012) according to the attached sketches. | ELEC | Z3 | Z3 | 8th | 44004 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0889 | Pleas Check The fluke test for structure cabling system Cables at the seventh floor ( Zone4) Refer to FTR (07-026) according to the attached sketches. | ELEC | Z4 | Z4 | 7th | 44005 | 44010 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0890 | MEGGER CABLE TEST for pannel (ELP-IB-CB-08) from EDB-CB-IB accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF) | ELEC | Z3 | Z3 | 8th | 44013 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0891 | MEGGER CABLE TEST for pannel (ELP-IB-08) FROM TAP OFF accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC | ELEC | Z3 | Z3 | 8th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0892 | MEGGER CABLE TEST for pannel (EPP-UPS-IB-08) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC | ELEC | Z3 | Z3 | 8th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0893 | MEGGER CABLE TEST for pannel (LP-IB-08) From tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC | ELEC | Z3 | Z3 | 8th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0894 | MEGGER CABLE TEST for pannel (PP-IB-08-1) From tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC | ELEC | Z3 | Z3 | 8th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0895 | MEGGER CABLE TEST for pannel (PP-IB-08-2) From tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC | ELEC | Z3 | Z3 | 8th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0896 | Megger CableTest For Pannel (ELP-CB-IA-5) from EDB-CB-IA accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0897 | Megger CableTest For Pannel (ELP-CB-IB-5) from EDB-CB-IB accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0898 | Megger CableTest For Pannel (ELP-CB-IC-5) from EDB-CB-IC accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0899 | Megger CableTest For Pannel (ELP-CB-ID-5) from EDB-CB-ID accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0900 | Megger CableTest For Pannel (ELP-IA-5) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0901 | Megger CableTest For Pannel (ELP-IB-5) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0902 | Megger CableTest For Pannel (ELP-IC-5) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0903 | Megger CableTest For Pannel (ELP-ID-5) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0904 | Megger CableTest For Pannel (EPP-UPS-IA-5) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0905 | Megger CableTest For Pannel (EPP-UPS-IB-5) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0906 | Megger CableTest For Pannel (EPP-UPS-IC-5) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0907 | Megger CableTest For Pannel (EPP-UPS-ID-5) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0908 | Megger CableTest For Pannel (LP-IA-5) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0909 | Megger CableTest For Pannel (LP-IB-5) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0910 | Megger CableTest For Pannel (LP-IC-5) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0911 | Megger CableTest For Pannel (LP-ID-5) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0912 | Megger CableTest For Pannel (PP-IA-5) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0913 | Megger CableTest For Pannel (PP-IB-5-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0914 | Megger CableTest For Pannel (PP-IB-5-2) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0915 | Megger CableTest For Pannel (PP-IC-5-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0916 | Megger CableTest For Pannel (PP-IC-5-2) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0917 | Megger CableTest For Pannel (PP-ID-5) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 5th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0918 | Megger CableTest For Pannel (ELP-CB-IB-6) from tap off accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF) | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0919 | Megger CableTest For Pannel (ELP-CB-IC-6 )from tap off accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0920 | Megger CableTest For Pannel (ELP-IB-6) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0921 | Megger CableTest For Pannel (ELP-IC-6)from tap off accordding to the attached sketches. Cable size (4X10)+10E CU/XLPE/PVC | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0922 | Megger CableTest For Pannel (LP-IA-6) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0923 | Megger CableTest For Pannel (LP-IB-6)from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0924 | Megger CableTest For Pannel (LP-IC-6)from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0925 | Megger CableTest For Pannel (LP-ID-6)from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC . | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0926 | Megger CableTest For Pannel (PP-IA-6)from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0927 | Megger CableTest For Pannel (PP-IB-6-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0928 | Megger CableTest For Pannel (PP-IB-6-2) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0929 | Megger CableTest For Pannel (PP-IC-6-1)from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0930 | Megger CableTest For Pannel (PP-IC-6-2)from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0931 | Megger CableTest For Pannel (PP-ID-6)from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 6th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0932 | Megger Cable Test for pannel (ELP-CB-IB-07) from pannel EDB-CB-IB accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF) | ELEC |  |  | 7th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0933 | Megger Cable Test for pannel (ELP-CB-IC-07) from pannel EDB-CB-ICaccordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF) | ELEC |  |  | 7th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0934 | Megger Cable Test For Pannel (ELP-IB-7) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 7th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0935 | Megger Cable Test For Pannel (ELP-IC-7) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 7th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0936 | Megger Cable Test For Pannel (ELP-LS-IB-7) from pannel EDB-LS-IB-B1 accordding to the attached sketches. Cable Size (3X10) CU/MICA/XLPE/SWA/LSHF) | ELEC |  |  | 7th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0937 | Megger Cable Test For Pannel (ELP-LS-IC-7) from pannel EDB-LS-IC-B1 accordding to the attached sketches. Cable Size (3X10) CU/MICA/XLPE/SWA/LSHF) | ELEC |  |  | 7th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0938 | Megger Cable Test For Pannel (EPP-UPS-IB-7) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 7th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0939 | Megger Cable Test For Pannel (EPP-UPS-IC-7) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 7th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0940 | Megger Cable Test For Pannel (LP-IB-7) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 7th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0941 | Megger Cable Test For Pannel (LP-IC-7) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 7th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0942 | Megger Cable Test For Pannel (PP-IB-7) from tap off accordding to the attached sketches. Cable Size (4X35)+16E CU/XLPE/PVC. | ELEC |  |  | 7th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0943 | Megger Cable Test For Pannel (PP-IC-7) from tap off accordding to the attached sketches. Cable Size (4X35)+16E CU/XLPE/PVC. | ELEC |  |  | 7th | 44013 | 44019 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0944 | Megger CableTest For Pannel (ELP-CB-IA-03) from EDB-CB-IA accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0945 | Megger CableTest For Pannel (ELP-CB-IB-3) from EDB-CB-IB accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0946 | Megger CableTest For Pannel (ELP-CB-IC-3) from EDB-CB-IC accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0947 | Megger CableTest For Pannel (ELP-CB-ID-3) from EDB-CB-ID accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0948 | Megger Cable Test For Pannel (ELP-IA-3) from EDB-IA-2 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0949 | Megger Cable Test For Pannel (ELP-IB-3) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0950 | Megger Cable Test For Pannel (ELP-IC-3) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0951 | Megger Cable Test For Pannel (ELP-ID-3) from EDB-ID-2 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0952 | Megger Cable Test For Pannel (EPP-UPS-IA-3) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0953 | Megger Cable Test For Pannel (EPP-UPS-IB-3) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0954 | Megger Cable Test For Pannel (EPP-UPS-IC-3) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0955 | Megger Cable Test For Pannel (EPP-UPS-ID-3) from tap off accordding to the attached sketches. Cable Size (4X35)+16E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0956 | Megger Cable Test For Pannel (ELP-IA-3) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0957 | Megger Cable Test For Pannel (ELP-IB-3) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0958 | Megger CableTest For Pannel (ELP-CB-IA-4) from EDB-CB-IA accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF) | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0959 | Megger CableTest For Pannel (ELP-CB-IB-4) from EDB-CB-IB accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0960 | Megger CableTest For Pannel (ELP-CB-IC-4) from EDB-CB-IC accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0961 | Megger CableTest For Pannel (ELP-CB-ID-4) from EDB-CB-ID accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0962 | Megger CableTest For Pannel (ELP-IA-4) from EDB-IA-2 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0963 | Megger CableTest For Pannel (ELP-IB-4) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0964 | Megger CableTest For Pannel (ELP-IC-4) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0965 | Megger CableTest For Pannel (ELP-ID-4) from EDB-ID-2 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0966 | Megger CableTest For Pannel (ELP-LS-IA-4) from EDB-LS-IA-B1 accordding to the attached sketches. Cable Size (3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0967 | Megger CableTest For Pannel (ELP-LS-IB-4) from EDB-LS-IB-B1 accordding to the attached sketches. Cable Size (3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0968 | Megger CableTest For Pannel (ELP-LS-IC-4) from EDB-LS-IC-B1 accordding to the attached sketches. Cable Size (3X10) CU/MICA/XLPE/SWA/LSHF. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0969 | Megger CableTest For Pannel (ELP-LS-ID-4) from EDB-LS-ID-B1 accordding to the attached sketches. Cable Size (3X10) CU/MICA/XLPE/SWA/LSHF. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0970 | Megger CableTest For Pannel (EPP-UPS-IA-4) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0971 | Megger CableTest For Pannel (EPP-UPS-IB-4) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0972 | Megger CableTest For Pannel (EPP-UPS-IC-4) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0973 | Megger CableTest For Pannel (EPP-UPS-ID-4) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0974 | Megger CableTest For Pannel (LP-IA-4) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0975 | Megger CableTest For Pannel (LP-IB-4) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0976 | Megger CableTest For Pannel (LP-IC-4) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0977 | Megger CableTest For Pannel (LP-ID-4) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0978 | Megger CableTest For Pannel (PP-IA-4) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0979 | Megger CableTest For Pannel (PP-IB-4-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0980 | Megger CableTest For Pannel (PP-IB-4-2) from tap off accordding to the attached sketches. Cable Size 4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0981 | Megger CableTest For Pannel (PP-IC-4-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0982 | Megger CableTest For Pannel (PP-IC-4-2) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0983 | Megger CableTest For Pannel (PP-ID-4) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 4th | 44018 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0984 | Megger Cable Test For Pannel (ELP-IC-3) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44019 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0985 | Megger Cable Test For Pannel (ELP-ID-3) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | 3rd | 44019 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0986 | Megger Cable Test For Pannel (PP-IA-3) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44019 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0987 | Megger Cable Test For Pannel (PP-IB-3-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44019 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0988 | Megger Cable Test For Pannel (PP-IB-3-2) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44019 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0989 | Megger Cable Test For Pannel (PP-IC-3-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44019 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0990 | Megger Cable Test For Pannel (PP-IC-3-2) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44019 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0991 | Megger Cable Test For Pannel (PP-ID-3) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 3rd | 44019 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0992 | Pleas Check The fluke test for structured cabling system Cables at the seventh floor ( Zone2) Refer to FTR (07-010) according to the attached sketches. | ELEC |  |  | 7th | 44019 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0993 | Pleas Check The fluke test for structured cabling system Cables at the sixth floor ( Zone2) Refer to FTR (06-010) according to the attached sketches. | ELEC |  |  | 6th | 44019 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0994 | Megger CableTest For Pannel (ELP-IA-2) From EDB-IA-2 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0995 | Megger CableTest For Pannel (ELP-CB-IB-2) From EDB-CB-IB accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0996 | Megger CableTest For Pannel (ELP-CB-IC-2) From EDB-CB-IC accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0997 | Megger CableTest For Pannel (ELP-CB-ID-2) From EDB-CB-ID accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0998 | Megger CableTest For Pannel (ELP-IA-2) From tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-0999 | Megger CableTest For Pannel (ELP-IB-2) From tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1000 | Megger CableTest For Pannel (ELP-IC-2) From tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1001 | Megger CableTest For Pannel (ELP-ID-2) From tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1002 | Megger CableTest For Pannel (EPP-UPS-ID-2) From tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1003 | Megger CableTest For Pannel (EPP-UPS-IB-2) From tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1004 | Megger CableTest For Pannel (EPP-UPS-IC-2) From tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1005 | Megger CableTest For Pannel (EPP-UPS-ID-2) From tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1006 | Megger CableTest For Pannel (LP-IA-2) From tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1007 | Megger CableTest For Pannel (LP-IB-2) From tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1008 | Megger CableTest For Pannel (LP-IC-2) From tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1009 | Megger CableTest For Pannel (LP-ID-2) From tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1010 | Megger CableTest For Pannel (PP-IA-2) From tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1011 | Megger CableTest For Pannel (PP-IB-2-1) From tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1012 | Megger CableTest For Pannel (PP-IB-2-2) From tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1013 | Megger CableTest For Pannel (PP-IC-2-1) From tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1014 | Megger CableTest For Pannel (PP-IC-2-2) From tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1015 | Megger CableTest For Pannel (PP-ID-2) From tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1016 | Megger CableTest For Pannel (EDB-IA-2) From EMDB-I12 accordding to the attached sketches. Cable Size (4X25)+16E CU/XLPE/SWA/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1017 | Megger CableTest For Pannel (EDB-ID-2) From EMDB-I21 accordding to the attached sketches. Cable Size (4X25)+16E CU/XLPE/SWA/PVC. | ELEC |  |  | 2nd | 44020 | 44025 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1018 | Megger CableTest For Pannel (ELP-CB-IA-1) from EDB-CB-IA accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1019 | Megger CableTest For Pannel (ELP-CB-IB-1) from EDB-CB-IB accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1020 | Megger CableTest For Pannel (ELP-CB-IC-1) from EDB-CB-IC accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1021 | Megger CableTest For Pannel (ELP-CB-ID-1) from EDB-CB-ID accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1022 | Megger CableTest For Pannel (ELP-IA-1) from EDB-IA-2 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1023 | Megger CableTest For Pannel (ELP-IB-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1024 | Megger CableTest For Pannel (ELP-IC-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1025 | Megger CableTest For Pannel (ELP-ID-1) from EDB-ID-2 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1026 | Megger CableTest For Pannel (ELP-LS-IA-1) from EDB-LS-IA-B1 accordding to the attached sketches. Cable Size (3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1027 | Megger CableTest For Pannel (ELP-LS-IB-1) from EDB-LS-IB-B1 accordding to the attached sketches. Cable Size (3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1028 | Megger CableTest For Pannel (ELP-LS-IC-1) from EDB-LS-IC-B1 accordding to the attached sketches. Cable Size (3X10) CU/MICA/XLPE/SWA/LSHF. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1029 | Megger CableTest For Pannel (ELP-LS-ID-1) from EDB-LS-ID-B1 accordding to the attached sketches. Cable Size (3X10) CU/MICA/XLPE/SWA/LSHF. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1030 | Megger CableTest For Pannel (EPP-UPS-IA-1-1) from tap off accordding to the attached sketches. Cable Size (4X25)+16E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1031 | Megger CableTest For Pannel (EPP-UPS-IA-1-2) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1032 | Megger CableTest For Pannel (EPP-UPS-IB-1-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1033 | Megger CableTest For Pannel (EPP-UPS-IB-1-2) from tap off accordding to the attached sketches. Cable Size (4X35)+16E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1034 | Megger CableTest For Pannel (EPP-UPS-IC-1-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1035 | Megger CableTest For Pannel (EPP-UPS-IC-1-2) from tap off accordding to the attached sketches. Cable Size (4X35)+16E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1036 | Megger CableTest For Pannel (EPP-UPS-ID-1-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1037 | Megger CableTest For Pannel (EPP-UPS-ID-1-2) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1038 | Megger CableTest For Pannel (ELP-IA-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1039 | Megger CableTest For Pannel (ELP-IB-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1040 | Megger CableTest For Pannel (ELP-IC-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1041 | Megger CableTest For Pannel (ELP-ID-1) from EDB-ID-2 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1042 | Megger CableTest For Pannel (PP-IA-1-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1043 | Megger CableTest For Pannel (PP-IA-1-2) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1044 | Megger CableTest For Pannel (PP-IB-1-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1045 | Megger CableTest For Pannel (PP-IB-1-2) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1046 | Megger CableTest For Pannel (PP-IC-1-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1047 | Megger CableTest For Pannel (PP-IC-1-2) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1048 | Megger CableTest For Pannel (PP-ID-1-1) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1049 | Megger CableTest For Pannel (PP-ID-1-2) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | 1st | 44023 | 44026 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1050 | Megger CableTest For Pannel (EDB-CRAC-MTR-I1) from EMDB-I12 accordding to the attached sketches. Cable Size 2(4X25)+16E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1051 | Megger CableTest For Pannel (EDB-CRAC-MTR-I2) from EMDB-I21 accordding to the attached sketches. Cable Size (4X240)+120E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1052 | Megger CableTest For Pannel (EDB-UPS-MTR-I1) from UPS-G (40KVA) accordding to the attached sketches. Cable Size (4X25)+16E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1053 | Megger CableTest For Pannel (EDB-UPS-MTR-I2) from UPS-E(150KVA) accordding to the attached sketches. Cable Size (4X240)+120E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1054 | Megger CableTest For Pannel (EDB-UPS-MTR-I2) from UPS-F(150KVA) accordding to the attached sketches. Cable Size (4X240)+120E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1055 | Megger CableTest For Pannel (ELP-CB-IA-G) from EDB-CB-IA accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1056 | Megger CableTest For Pannel (ELP-CB-IB-G) from EDB-CB-IB accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1057 | Megger CableTest For Pannel (ELP-CB-IC-G) from EDB-CB-IC accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1058 | Megger CableTest For Pannel (ELP-CB-ID-G) from EDB-CB-ID accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1059 | Megger CableTest For Pannel (ELP-IA-G) from EDB-IA-2 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1060 | Megger CableTest For Pannel (ELP-IA-SERV) from EDB-IA-2 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1061 | Megger CableTest For Pannel (ELP-IB-G) from TAP OFF accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1062 | Megger CableTest For Pannel (ELP-IB-SERV) from TAP OFF accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1063 | Megger CableTest For Pannel (ELP- IC-G) from TAP OFF accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1064 | Megger CableTest For Pannel (ELP-IC-SERV) from TAP OFF accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1065 | Megger CableTest For Pannel (ELP-ID-G) from TAP OFF accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1066 | Megger CableTest For Pannel (ELP-ID-SERV) from EDB-ID-2 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1067 | Megger CableTest For Pannel (EPP-UPS-IA-G) from TAP OFF accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1068 | Megger CableTest For Pannel (EPP-UPS-IB-G) from TAP OFF accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1069 | Megger CableTest For Pannel (EPP-UPS-IC-G) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1070 | Megger CableTest For Pannel (EPP-UPS-ID-G) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1071 | Megger CableTest For Pannel (EPP-UPS-MTR-I1-1) from EDB-UPS-MTR-I1 accordding to the attached sketches. Cable Size (4X25)+16E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1072 | Megger CableTest For Pannel (EPP-UPS-MTR-I1-2) from EDB-UPS-MTR-I1 accordding to the attached sketches. Cable Size (4X25)+16E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1073 | Megger CableTest For Pannel (EPP-UPS-MTR-I2-1) from EDB-UPS-MTR-I2 accordding to the attached sketches. Cable Size (4X240)+120E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1074 | Megger CableTest For Pannel (EPP-UPS-MTR-I2-2) from EDB-UPS-MTR-I2 accordding to the attached sketches. Cable Size (4X240)+120E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1075 | Megger CableTest For Pannel (LP-IA-G) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1076 | Megger CableTest For Pannel (LP-IB-G) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1077 | Megger CableTest For Pannel (LP-IC-G) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1078 | Megger CableTest For Pannel (LP-ID-G) from accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1079 | Megger CableTest For Pannel (LP-LAND-IA-G) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1080 | Megger CableTest For Pannel (LP-LAND-IB-G) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1081 | Megger CableTest For Pannel (LP-LAND-IC-G) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1082 | Megger CableTest For Pannel (LP-LAND-ID-G) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1083 | Megger CableTest For Pannel (PP-IA-G) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1084 | Megger CableTest For Pannel (PP-IB-G) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1085 | Megger CableTest For Pannel (PP-IC-G) from tap off accordding to the attached sketches. Cable Size (4X16)+16E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1086 | Megger CableTest For Pannel (PP-ID-G) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1087 | Megger CableTest For Pannel (DISCONNECT SWITSH1) from EDB-CRAC-MTRI1 accordding to the attached sketches. Cable Size (4X6)+6E CU/XLPE/PVC . | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1088 | Megger CableTest For Pannel (DISCONNECT SWITSH2) from EDB-CRAC-MTRI1 accordding to the attached sketches. Cable Size (4X6)+6E CU/XLPE/PVC . | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1089 | Megger CableTest For Pannel (DISCONNECT SWITSH3) from EDB-CRAC-MTRI2 accordding to the attached sketches. Cable Size (4X6)+6E CU/XLPE/PVC . | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1090 | Megger CableTest For Pannel (DISCONNECT SWITSH4) from EDB-CRAC-MTRI2 accordding to the attached sketches. Cable Size (4X6)+6E CU/XLPE/PVC . | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1091 | Megger CableTest For Pannel (DISCONNECT SWITSH5) from EDB-CRAC-MTRI2 accordding to the attached sketches. Cable Size (4X6)+6E CU/XLPE/PVC . | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1092 | Megger CableTest For Pannel (UNIT 1) from EDB-CRAC-MTR-I1 accordding to the attached sketches. Cable Size (4X25)+16E CU/XLPE/SWA/PVC . | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1093 | Megger CableTest For Panne UNIT 2 from EDB-CRAC-MTR-I1 accordding to the attached sketches. Cable Size(4X25)+16E CU/XLPE/SWA/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1094 | Megger CableTest For Pannel OUT DOOR UNIT 1 from EDB-CRAC-MTR-I1 accordding to the attached sketches. Cable Size (4X6)+6E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1095 | Megger CableTest For Pannel OUT DOOR UNIT 2 from EDB-CRAC-MTR-I1 accordding to the attached sketches. Cable Size (4X6)+6E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1096 | Megger CableTest For Panne CRAC from EDB-UPS-MTR-I1 accordding to the attached sketches. Cable Size(4X25)+16E CU/MICA/XLPE/SWA/LSHF. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1097 | Megger CableTest For Panne CRAC from EDB-UPS-MTR-I1 accordding to the attached sketches. Cable Size(4X25)+16E CU/MICA/XLPE/SWA/LSHF. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1098 | Megger CableTest For Pannel (UNIT 1 ) from EDB-CRAC-MTRI2 accordding to the attached sketches. Cable Size (4X35)+16E CU/XLPE/LSHF . | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1099 | Megger CableTest For Pannel (UNIT 2) from EDB-CRAC-MTRI2 accordding to the attached sketches. Cable Size (4X35)+16E CU/XLPE/LSHF . | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1100 | Megger CableTest For Pannel UNIT (3) from EDB-CRAC-MTRI2 accordding to the attached sketches. Cable Size(4X35)+16E CU/XLPE/LSHF. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1101 | Megger CableTest For Pannel (UOT DOOR CRAC UNITS) from EDB-CRAC-MTRI2 accordding to the attached sketches. Cable Size 3(4X6)+6E CU/XLPE/LSHF . | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1102 | Megger CableTest For Pannel (UNIT 3) from EDB-CRAC-MTRI2 accordding to the attached sketches. Cable Size (4X35)+16E CU/XLPE/LSHF . | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1103 | Megger CableTest For Pannel (EPP-UPS-CON-IC-G) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | GF | 44026 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1104 | Megger Cable test for pannel (ELP-CB-IA-B2) from EDB-CB-IA accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1105 | Megger Cable test for pannel (ELP-CB-IB-B2) from EDB-CB-IB accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1106 | Megger Cable test for pannel (ELP-CB-IC-B2) from EDB-CB-IC accordding to the attached sketches. Cable Size 2((3X10) CU/MICA/XLPE/SWA/LSHF). | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1107 | Megger Cable test for pannel (ELP-CB-ID-B2) from EDB-CB-ID accordding to the attached sketches. Cable Size 2(3X10) CU/MICA/XLPE/SWA/LSHF. | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1108 | Megger Cable test for pannel (ELP-IA-B2) from EDB-I1-B1 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/LSHF. | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1109 | Megger Cable test for pannel (ELP-IB-B2) from EDB-I1-B1 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/LSHF. | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1110 | Megger Cable test for pannel (ELP-IC-B2) from EDB-I2-B1 accordding to the attached sketches. Cable Size (4X10+10E) CU/XLPE/LSHF. | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1111 | Megger Cable test for pannel (ELP-ID-B2) from EDB-I2-B1 accordding to the attached sketches. Cable Size (4X10+10E) CU/XLPE/LSHF. | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1112 | Megger Cable test for pannel (EPP-I1-B2) from EMDB-I12 accordding to the attached sketches. Cable Size (3X50+25)+25E CU/XLPE/LSHF. | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1113 | Megger Cable test for pannel (EPP-I2-B2) from EMDB-I21 accordding to the attached sketches. Cable Size (3X50+25)+25E CU/XLPE/LSHF. | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1114 | Megger Cable test for pannel (EPP-UPS-IA-B2) from TAP OFF accordding to the attached sketches. Cable Size(4X10)+10E CU/XLPE/PVC. | ELEC |  |  | B2 | 44027 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1115 | Megger Cable test for pannel (EPP-UPS-IB-B2) from TAP OFF accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | B2 | 44027 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1116 | Megger Cable test for pannel (EPP-UPS-IC-B2) from TAP OFF accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | B2 | 44027 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1117 | Megger Cable test for pannel (EPP-UPS-ID-B2) from TAP OFF accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC. | ELEC |  |  | B2 | 44027 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1118 | Megger Cable test for pannel (LP-IA-B2) from DB-I1-B1 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/LSHF. | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1119 | Megger Cable test for pannel (LP-IB-B2) from DB-I1-B1 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/LSHF. | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1120 | Megger Cable test for pannel (LP-IC-B2) from DB-I2-B1 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/LSHF. | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1121 | Megger Cable test for pannel (LP-ID-B2) from DB-I2-B1 accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/LSHF. | ELEC |  |  | B2 | 44027 | 44032 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1122 | Check the (Easy Check) pannels installation in the second basement floor accordding to the attached sketch. _EC1 _EC5 _EC12 _EC19. | ELEC |  |  | B2 | 44027 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1123 | Check the (Easy Check) pannels installation in the ground floor accordding to the attached sketch. _EC2 _EC6 _EC7 _EC23 _EC13 _EC14 _EC24 _EC20. | ELEC |  |  | GF | 44027 | 44053 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1124 | Check the (Easy Check) pannels installation in the FIRST floor accordding to the attached sketch. _EC3 _EC8 _EC15 _EC21. | ELEC |  |  | 1st | 44027 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1125 | Check the (Easy Check) pannels installation in the second floor accordding to the attached sketch. _EC9 _EC16. | ELEC |  |  | 2nd | 44027 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1126 | Check the (Easy Check) pannels installation in the fourth floor accordding to the attached sketch. _E4 _EC17 _EC22. | ELEC |  |  | 4th | 44027 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1127 | Check the (Easy Check) pannels installation in the fifth floor accordding to the attached sketch. _EC10. | ELEC |  |  | 5th | 44027 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1128 | Check the (Easy Check) pannel installation in the seventh floor accordding to the attached sketch. _EC8. | ELEC |  |  | 7th | 44027 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1129 | Check the (Easy Check) pannel installation in the 8-th floor accordding to the attached sketch. _EC11. | ELEC |  |  | 8th | 44027 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1130 | PLS Check Installation for Central Battary Pannels and modules inside low voltage rooms (z1,z5)accordding to the attached sketch. _Rate (15 KVA) =3 units _Rate(20KVA)=1 . | ELEC |  |  | B1 | 44027 | 44053 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1131 | Pleas Check Visual Inspection and pannels Installation for UPS Pannels inside UPS rooms at the first basement floor accordding to the attached sketch. _UPS (A,B)=300KVA _UPS(C,D)=300KVA _UPS(E,F)=150KVA _UPS(G,H)=40KVA . | ELEC |  |  | B1 | 44027 | 44053 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1132 | Megger Cable test for pannel (SM-DB-WF) from MDB-I2(SEC2) accordding to the attached sketches. Cable Size (3X70+35)+35E CU/XLPE/SWA/PVC . | ELEC |  |  | B1 | 44031 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1133 | Megger Cable test for pannel (ESMDB-WF) from EMDB-I22 accordding to the attached sketches. Cable Size(4X16)+16E CU/XLPE/SWA/PVC . | ELEC |  |  | B1 | 44031 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1134 | Megger Cable test for pannel (PP-KITCH-IB) from tap off accordding to the attached sketches. Cable Size (4X10)+10E CU/XLPE/PVC . | ELEC |  |  | GF | 44031 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1135 | Pleas Check The fluke test for structured cabling system Cables at the first basement floor ( Zone1) Refer to FTR (B1-040) according to the attached sketches. | ELEC | Z1 | Z1 | B1 | 44031 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1136 | Pleas Check The fluke test for structured cabling system Cables at the first basement floor ( Zone2) Refer to FTR (B1-054) according to the attached sketches. | ELEC | Z2 | Z2 | B1 | 44031 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1137 | Pleas Check The fluke test for structured cabling system Cables at the first basement floor ( Zone3) Refer to FTR (B1-062) according to the attached sketches. | ELEC | Z3 | Z3 | B1 | 44031 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1138 | Pleas Check The fluke test for structured cabling system Cables at the first basement floor ( Zone4) Refer to FTR (B1-068) according to the attached sketches. | ELEC | Z4 | Z4 | B1 | 44031 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1139 | Pleas Check The fluke test for structured cabling system Cables at the first basement floor ( Zone5) Refer to FTR (B1-039) according to the attached sketches. | ELEC | Z5 | Z5 | B1 | 44031 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1140 | Pleas Check The fluke test for structured cabling system Cables at the second basement floor ( Zone1) Refer to FTR (B2-035) according to the attached sketches. | ELEC | Z1 | Z1 | B2 | 44031 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1141 | Pleas Check The fluke test for structured cabling system Cables at the second basement floor ( Zone2) Refer to FTR (B2-049) according to the attached sketches. | ELEC | Z2 | Z2 | B2 | 44031 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1142 | Pleas Check The fluke test for structured cabling system Cables at the second basement floor ( Zone3) Refer to FTR (B2-057) according to the attached sketches. | ELEC | Z3 | Z3 | B2 | 44031 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1143 | Pleas Check The fluke test for structured cabling system Cables at the second basement floor ( Zone4) Refer to FTR (B2-063) according to the attached sketches. | ELEC | Z4 | Z4 | B2 | 44031 | 44034 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1144 | Pleas Check The fluke test for structured cabling system Cables at the second basement floor ( Zone5) Refer to FTR (B2-034) according to the attached sketches. | ELEC | Z5 | Z5 | B2 | 44031 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1145 | Check installation for MCC pannel boards and VFD modules at the ground floor insid HVAC rooms accordding to the attached sketch. _MCC-GR-IC-01 _MCC-GR-IC-02 _VFD(18.5kw)=1 _VFD(22kw)=3. | ELEC |  |  | GF | 44031 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1146 | Check installation for MCC pannel boards and VFD modules at the first basement floor insid mechanical rooms accordding to the attached sketch. _MCC-B1-IC-01 _EMCC-B1-IC-01 _EMCC-B1-IC-02 _EMCC-B1-IC-03 _EMCC-B1-IC-04 _EMCC-B1-IC-05 _EMCC-B1-IC-06 _VFD(18.5kw)=7 _VFD(22kw)=6 _VFD(37kw)=3 _VFD(15kw)=1 _VFD(55kw)=4 . | ELEC |  |  | B1 | 44031 | 44040 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1147 | Check installation for MCC pannel boards and VFD modules at the second basement floor insid mechanical rooms accordding to the attached sketch. _EMCC-B2-IC-01 _EMCC-B2-IC-02 _EMCC-B2-IC-03 _EMCC-B2-IC-04 _EMCC-B2-IC-05 _EMCC-B2-IC-06 _VFD(18.5kw)=1 _VFD(22kw)=1 _VFD(15kw)=6 _VFD(30kw)=1 _VFD(37kw)=4 _VFD(55kw)=1. | ELEC |  |  | B2 | 44031 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1148 | Check the third fix and lighting fixures installation for lighting system at the ground floor accordding to the attached sketches. | ELEC |  |  | GF | 44031 | 44053 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1149 | Ground Resistance Test For Switch Gear Room and RMU Room at ground floor accordding to the attached sketches. | ELEC |  |  | GF | 44037 | 44053 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1150 | Check the racks and cable tray installation for (MTR I1) at the ground floor accordding to the attached sketch. _NO. OF Rack=6. | ELEC |  |  | GF | 44052 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1151 | Check the racks and cable tray installation for (MTR I2) at the ground floor accordding to the attached sketch. _NO. OF Rack=18. | ELEC |  |  | GF | 44052 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1152 | Check the secondary earth (Cable pulling) for Earthing System in the first basement floor accordding to the attached sketch. | ELEC |  |  | B1 | 44055 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1153 | Check the secondary earth (Cable pulling) for Earthing System in the second basement floor accordding to the attached sketch. | ELEC |  |  | B2 | 44055 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1154 | Pleas Check The fluke test for structure cabling system Cables at the 9-th floor Refer to FTR (09-006) according to the attached sketches. | ELEC | Z3 | Z3 | 9th | 44055 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1155 | Pleas Check The fluke test for structured cabling system Cables at the first floor ( Zone4) Refer to FTR (01-026) according to the attached sketches. | ELEC | Z4 | Z4 | 1st | 44055 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1156 | Pls Check The Installation and termination of IT Racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at first basement floor at axis (A_E) with axis (14_18) ( Zone1) Refer to FTR (B1-040) according to the attached sketch. | ELEC | Z1 | Z1 | B1 | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1157 | Pls Check the Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at the first basement floor at axis (F_L) with axis (10_18) ( Zone2) Refer to FTR (B1-054) according to the attached sketch. | ELEC | Z2 | Z2 | B1 | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1158 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at first basement floor at ( Zone3) Refer to FTR (B1-062) according to the attached sketch. | ELEC | Z3 | Z3 | B1 | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1159 | Pls Check Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at first basement floor at axis (F_L) with axis (1_9) ( Zone4) Refer to FTR (B1-068) according to the attached sketch. | ELEC | Z4 | Z4 | B1 | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1160 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at first basement floor at axis (A_E) with axis (1_9) ( Zone5) Refer to FTR (B1-039) according to the attached sketch. | ELEC | Z5 | Z5 | B1 | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1161 | Pls Check The Installation and termination of IT Racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at second basement floor at axis (A_E) with axis (14_18) ( Zone1) Refer to FTR (B2-035) according to the attached sketch. | ELEC | Z1 | Z1 | B2 | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1162 | Pls Check the Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at the second basement floor at axis (F_L) with axis (10_18) ( Zone2) Refer to FTR (B2-049) according to the attached sketch. | ELEC | Z2 | Z2 | B2 | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1163 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at the second basement floor at ( Zone3) Refer to FTR (B2-057) according to the attached sketch. | ELEC | Z3 | Z3 | B2 | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1164 | Pls Check Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at the second basement floor at axis (F_L) with axis (1_9) ( Zone4) Refer to FTR (B2-063) according to the attached sketch. | ELEC | Z4 | Z4 | B2 | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1165 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at the second basement floor at axis (A_E) with axis (1_9) ( Zone5) Refer to FTR (B2-043) according to the attached sketch. | ELEC | Z5 | Z5 | B2 | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1166 | Pls Check The Installation and termination of IT Racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at Ground floor at axis (A_E) with axis (14_18) ( Zone1) Refer to FTR (Gf-060) according to the attached sketch. | ELEC | Z1 | Z1 | GF | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1167 | Pls Check the Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at the ground floor at axis (F_L) with axis (10_18) ( Zone2) Refer to FTR (GF-010) according to the attached sketch. | ELEC | Z2 | Z2 | GF | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1168 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at ground floor at ( Zone3) Refer to FTR (GF-02) according to the attached sketch. | ELEC | Z3 | Z3 | GF | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1169 | Pls Check Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at ground floor at axis (F_L) with axis (1_9) ( Zone4) Refer to FTR (GF-029) according to the attached sketch. | ELEC | Z4 | Z4 | GF | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1170 | Pls Check The Installation and termination for it racks (N1,N2,N3) for Data,Telephone,Tv,cctv,Bms and Wifi Cables at ground floor at axis (A_E) with axis (1_9) ( Zone5) Refer to FTR (GF-050) according to the attached sketch. | ELEC | Z5 | Z5 | GF | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1171 | Pls Check The Installation of IT Racks at first basement floor insid intrance room 1 at the first basement floor (Z1) according to the attached sketch. | ELEC | Z1 | Z1 | B1 | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1172 | Pls Check The Installation of IT Racks at first basement floor insid intrance room 2 at the first basement floor (Z5) according to the attached sketch. | ELEC | Z5 | Z5 | B1 | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1173 | Check the installation and megger test for MCC and VFD Cables accordding to the attached Table. | ELEC |  |  | ML | 44058 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1174 | Check installation for MCC pannel boards and VFD at the 8th floor accordding to the attached sketch. _MCC-8F-IC-01 _EMCC-8F-IC-01 _MCC-8F-IC-02 _EMCC-8F-IC-02 _VFD(5.5kw)=2 _VFD(22kw)=2 . | ELEC | Z3 | Z3 | 8th | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1175 | Check installation for MCC pannel boards and VFD at the Roof floor accordding to the attached sketch. _MCC-RF-IC-01 _EMCC-RF-IC-01 _MCC-RF-IC-02 _EMCC-RF-IC-02 _VFD(18.5kw)=9 _VFD(22kw)=1 _VFD(4kw)=1. | ELEC |  |  | RF | 44058 | 44070 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1176 | Check the third fix and wiring devices installation for small power system at the second basement floor accordding to the attached sketches. | ELEC |  |  | B2 | 44065 | 44096 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1177 | PLS Check Installation for two medium voltage RMU in (Z4) at ground floor accordding to the attached sketch. | ELEC | Z4 | Z4 | GF | 44066 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1178 | Check the first fix rase way for audio visual racks at the ground floor accordding to the attached sketch. _NO. OF Racks=7. | ELEC |  |  | GF | 44066 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1179 | Check the first fix rase way for audio visual racks at the first floor accordding to the attached sketch. _NO. OF Racks=2. | ELEC |  |  | 1st | 44066 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1180 | Check the first fix rase way for audio visual racks at the second floor accordding to the attached sketch. _NO. OF Racks=2. | ELEC |  |  | 2nd | 44066 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1181 | Check the first fix rase way for audio visual racks at the third floor accordding to the attached sketch. _NO. OF Racks=1. | ELEC |  |  | 3rd | 44066 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1182 | Check the first fix rase way for audio visual racks at the fourth floor accordding to the attached sketch. _NO. OF Racks=2. | ELEC |  |  | 4th | 44066 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1183 | Check the first fix rase way for audio visual racks at the fifth floor accordding to the attached sketch. _NO. OF Racks=2. | ELEC |  |  | 5th | 44066 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1184 | Check the first fix rase way for audio visual racks at the sixth floor accordding to the attached sketch. _NO. OF Racks=1. | ELEC |  |  | 6th | 44066 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1185 | Check the first fix rase way for audio visual racks at the Seventh floor accordding to the attached sketch. _NO. OF Racks=3. | ELEC |  |  | 7th | 44066 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1186 | Check the first fix rase way for audio visual rack at the ninth floor accordding to the attached sketch. _NO. OF Racks=1. | ELEC |  |  | 9th | 44066 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1187 | Check pannel megger test and pannel termination for pannel (LP-IB-09) accordding to the attached sketches. | ELEC |  |  | 9th | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1188 | Check pannel megger test and pannel termination for pannel (ELP-IB-09-1) accordding to the attached sketches. | ELEC |  |  | 9th | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1189 | Check pannel megger test and pannel termination for pannel (ELP-IB-CB-09) accordding to the attached sketches. | ELEC |  |  | 9th | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1190 | Check pannel megger test and pannel termination for pannel (ELP-IB-09-2) accordding to the attached sketches. | ELEC |  |  | 9th | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1191 | Check pannel megger test and pannel termination for pannel (PP-IB-09-1) accordding to the attached sketches. | ELEC |  |  | 9th | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1192 | Check pannel megger test and pannel termination for pannel (EPP-IB-UPS-09) accordding to the attached sketches. | ELEC |  |  | 9th | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1193 | Check pannel megger test and pannel termination for pannel (EPP-UPS-IB-09) accordding to the attached sketches. | ELEC |  |  | 9th | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1194 | Check second fix,continuity test,megger test and pannel installation for lighting system at the ground floor pannel LP_Land_IA_Gf at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _no. of lines=17. | ELEC | Z1 | Z1 | GF | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1195 | Check second fix,continuity test,megger test and pannel installation for lighting system at the ground floor pannel ELP_serv_IA_GF at zone (Z1) refer to electrical room (IA) accordding to the attached sketch. _no. of lines=27. | ELEC | Z1 | Z1 | GF | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1196 | Check second fix,continuity test,megger test and pannel installation for lighting system in the ground floor at zone (Z3a) ELP_Serv_IB_GF refer to electrical room (IB) accordding to the attached sketch. _normal Lighting lines= 53 . | ELEC | Z3A | Z3A | GF | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1197 | Check second fix,continuity test,megger test and pannel installation for lighting pannel ELP-IB-SERV-GF at the ground floor at zone (Z4) refer to electrical room (IC) accordding to the attached sketch. _no. of lines=76 . | ELEC | Z4 | Z4 | GF | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1198 | Check second fixt,continuity test,megger test and pannel installation for lighting system in the ground floor at zone (Z5) LP_Land_ID_GF refer to electrical room (ID) accordding to the attached sketch. _No.of lines= 18. | ELEC | Z5 | Z5 | GF | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1199 | Check second fixt,continuity test,megger test and pannel installation for lighting system in the ground floor at zone (Z5) ELP_Serv_ID_GF refer to electrical room (ID) accordding to the attached sketch. _No.of lines=27 . | ELEC | Z5 | Z5 | GF | 44067 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1200 | Check megger test and pannel termination for pannel (ELP-CB-IB-09) accordding to the attached sketch. | ELEC | Z3 | Z3 | 8th | 44070 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1201 | Check megger test and pannel termination for pannel (EPP-LIFT-IB-08) accordding to the attached sketch. | ELEC | Z3 | Z3 | 8th | 44070 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1202 | Check megger test and pannel termination for pannel (EPP-LIFT-IC-08) accordding to the attached sketch. | ELEC | Z3 | Z3 | 8th | 44070 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1203 | Check megger test and pannel termination for pannel (LP-IB-08) accordding to the attached sketch. | ELEC | Z3 | Z3 | 8th | 44070 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1204 | Check megger test and pannel termination pannel (LP-IC-08) accordding to the attached sketch. | ELEC | Z3 | Z3 | 8th | 44070 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1205 | Check megger test and pannel termination for pannel (PP-IB-8-1) accordding to the attached sketch. | ELEC | Z3 | Z3 | 8th | 44070 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1206 | Check megger test and pannel termination for pannel (PP-IB-8-2) accordding to the attached sketch. | ELEC | Z3 | Z3 | 8th | 44070 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1207 | Check megger test and pannel termination for pannel (PP-IB-8-3) accordding to the attached sketch. | ELEC | Z3 | Z3 | 8th | 44070 | 44074 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1208 | Check megger test and pannel termination for pannel (PP-IC-8) accordding to the attached sketch. | ELEC | Z3 | Z3 | 8th | 44070 | 44074 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1209 | Check megger test and pannel termination for pannel (ELP-CB-IB-07) accordding to the attached sketch. | ELEC |  |  | 7th | 44070 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1210 | Check megger test and pannel termination for pannel (ELP-IB-07) accordding to the attached sketch. | ELEC |  |  | 7th | 44070 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1211 | Check megger test and pannel termination for pannel (LP-IB-07) accordding to the attached sketch. | ELEC |  |  | 7th | 44070 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1212 | Check megger test and pannel termination for pannel (ELP-LS-IB-07) accordding to the attached sketch. | ELEC |  |  | 7th | 44070 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1213 | Check megger test and pannel termination for pannel (PP-IB-07) accordding to the attached sketch. | ELEC |  |  | 7th | 44070 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1214 | Check megger test and pannel termination for pannel (EPP-UPS-IB-07) accordding to the attached sketch. | ELEC |  |  | 7th | 44070 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1215 | Check megger test and pannel termination for pannel (ELP-CB-IC-07) accordding to the attached sketch. | ELEC |  |  | 7th | 44070 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1216 | Check megger test and pannel termination for pannel (ELP-IC-07) accordding to the attached sketch. | ELEC |  |  | 7th | 44070 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1217 | Check megger test and pannel termination for pannel (LP-IC-07) accordding to the attached sketch. | ELEC |  |  | 7th | 44070 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1218 | Check megger test and pannel termination for pannel (ELP-LS-IC-07) accordding to the attached sketch. | ELEC |  |  | 7th | 44070 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1219 | Check megger test and pannel termination for pannel (EPP-UPS-IC-07) accordding to the attached sketch. | ELEC |  |  | 7th | 44070 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1220 | Pleas Check The fluke test for structured cabling system Cables at the Ground floor ( Zone1) Refer to FTR (GF-060) according to the attached sketches. | ELEC | Z1 | Z1 | GF | 44072 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1221 | Pleas Check The fluke test for structured cabling system Cables at the Ground floor ( Zone2) Refer to FTR (GF-010) according to the attached sketches. | ELEC | Z2 | Z2 | GF | 44072 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1222 | Pleas Check The fluke test for structured cabling system Cables at the ground floor ( Zone3) Refer to FTR (GF-02) according to the attached sketches. | ELEC | Z3 | Z3 | GF | 44072 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1223 | Pleas Check The fluke test for structured cabling system Cables at the ground floor ( Zone4) Refer to FTR (GF-029) according to the attached sketches. | ELEC | Z4 | Z4 | GF | 44072 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1224 | Pleas Check The fluke test for structured cabling system Cables at the ground floor ( Zone5) Refer to FTR (GF-050) according to the attached sketches. | ELEC | Z5 | Z5 | GF | 44072 | 44077 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1225 | Pls Check The Visual Inspection and megger Test For Low Voltage Copper Plug In Bus way at core (I2) Run 11-LSB 2(CU) (800/1200A-50 KA)-3PH+FN+FE -(BD/I2-D/EDB-I2-UPS)(UPSBDI2-D) according to the attached sketch. | ELEC |  |  | B1 | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1226 | Pls Check The Visual Inspection and megger Test For Low Voltage Copper Plug In Bus way at core (I2) Run 12-LSB 2(CU) (400/800A-25 KA)-3PH+FN+FE -(BD/I2-C/EDB-I2-UPS)(UPSBDI2-C) according to the attached sketch. | ELEC |  |  | B1 | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1227 | Pls Check The Visual Inspection and megger Test For Low Voltage Copper Plug In Bus way at core (I2) Run 13-LSB 2(CU) (800/1200A-50 KA)-3PH+FN+HE -(BD/I2-C/MDB-I2-SEC2) according to the attached sketch. | ELEC |  |  | B1 | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1228 | Pls Check The Visual Inspection and megger Test For Low Voltage Copper Plug In Bus way at core (I2) Run 14-LSB 2(CU) (800/1200A-50 KA)-3PH+FN+HE -(BD/I2-C/MDB-I2-SEC2 according to the attached sketch. | ELEC |  |  | B1 | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1229 | Pls Check The Visual Inspection and megger Test For Low Voltage Copper Plug In Bus way at core (I2) Run 15-LSB 2(CU) (320/700A-25 KA)-3PH+FN+HE -(BD/I2-C/FEEDING UNIT)(EMDB I22) according to the attached sketch. | ELEC |  |  | B1 | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1230 | Pls Check The Visual Inspection and megger Test For Low Voltage Copper Plug In Bus way at core (I2) Run 16-LSB 2(CU) (320/700A-25 KA)-3PH+FN+HE -(BD/I2-D/FEEDING UNIT)(MDB I2-SEC1) according to the attached sketch. | ELEC |  |  | B1 | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1231 | Check megger test and pannel termination for pannel (LP-IA-06) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1232 | Check megger test and pannel termination for pannel (PP-IA-06) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1233 | Check megger test and pannel termination for pannel (LP-ID-06) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1234 | Check megger test and pannel termination for pannel (PP-ID-06) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1235 | Check megger test and pannel termination for pannel (EPP-LIFT-IA-06) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1236 | Check megger test and pannel termination for pannel (EPP-LIFT-ID-06) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1237 | Check megger test and pannel termination for pannel (ELP-CB-IB-06) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1238 | Check megger test and pannel termination for pannel (LP-IB-06) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1239 | Check megger test and pannel termination for pannel (PP-IB-6-1) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1240 | Check megger test and pannel termination for pannel (PP-IB-6-2) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1241 | Check megger test and pannel termination for pannel (EPP-UPS-IB-6-2) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1242 | Check megger test and pannel termination for pannel (ELP-CB-IC-6) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1243 | Check megger test and pannel termination for pannel (LP-IC-6) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1244 | Check megger test and pannel termination for pannel (PP-IC-6-1) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1245 | Check megger test and pannel termination for pannel (PP-IC-6-2) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1246 | Check megger test and pannel termination for pannel (EPP-UPS-IC-6) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1247 | Check megger test and pannel termination for pannel (MCC-6F-IC-01) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1248 | Check megger test and pannel termination for pannel (MCC-6F-IC-02) accordding to the attached sketch. | ELEC |  |  | 6th | 44073 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1249 | Check megger test and pannel termination for pannel (MCC-8F-IC-02) accordding to the attached sketch. | ELEC |  |  | 8th | 44073 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1250 | Check megger test and pannel termination for pannel (EMCC-8F-IC-01) accordding to the attached sketch. | ELEC |  |  | 8th | 44073 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1251 | Check megger test and pannel termination for pannel (EMCC-8F-IC-02) accordding to the attached sketch. | ELEC |  |  | 8th | 44073 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1252 | Check the second fix,megger test and pannel installation for Pannel LP_IA_06 at sixth floor ( refer to electrical room (IA) accordding to the attached sketch. _normal Lighting lines= 12. | ELEC |  |  | 6th | 44076 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1253 | Check the second fix,megger test and pannel installation for Pannel LP_ID_06 at sixth floor ( refer to electrical room (ID) accordding to the attached sketch. _normal Lighting lines= 12. | ELEC |  |  | 6th | 44076 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1254 | Check the second fix,megger test and pannel installation for Pannel LP_IC_08 at 8th floor ( refer to electrical room (IC) accordding to the attached sketch. _normal Lighting lines= 8. | ELEC |  |  | 8th | 44076 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1255 | Check the second fix,megger test and pannel installation for Pannel ELP_IC_08 at 8th floor ( refer to electrical room (IC) accordding to the attached sketch. _normal Lighting lines= 27. | ELEC |  |  | 8th | 44076 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1256 | Check second fix,continuity test,megger test for small power system in the sixth floor at zone (Z1) for pannel PP-IA-6 refer to electrical room (IA) accordding to the attached sketch. _No. of lines=18 . | ELEC |  |  | 6th | 44076 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1257 | Check second fix,continuity test,megger test for small power system in the sixth floor at zone (Z1) for pannel PP-ID-6 refer to electrical room (ID) accordding to the attached sketch. _No. of lines=18 . | ELEC |  |  | 6th | 44076 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1258 | Check second fix,continuity test,megger test for small power system in the 8th floor at zone (Z2) for pannel PP-IB-8 refer to electrical room (IB) accordding to the attached sketch. _No. of lines=16 . | ELEC |  |  | 8th | 44076 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1259 | Check second fix,continuity test,megger test for small power system in the 8th floor at zone (Z2) for pannel PP-IC-8 refer to electrical room (IC) accordding to the attached sketch. _No. of lines=17 . | ELEC |  |  | 8th | 44076 | 44081 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1260 | Check the second fix,megger test and pannel installation for Pannel EPP_I2_B2 at second basement floor ( refer to electrical room (ID) accordding to the attached sketch. _normal Lighting lines=9. | ELEC |  |  | B2 | 44076 | 44081 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1261 | Check the second fix,megger test and pannel installation for Pannel EPP_I1_B2 at second basement floor ( refer to electrical room (IA) accordding to the attached sketch. _normal Lighting lines=12. | ELEC |  |  | B2 | 44076 | 44081 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1262 | Check the second fix,megger test and pannel installation for Pannel EPP_PUMP_I2 at second basement accordding to the attached sketch. _normal Lighting lines=12. | ELEC |  |  | B2 | 44076 | 44128 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1263 | Check megger test and pannel termination for pannel (ELP-CB-IA-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44077 | 44096 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1264 | Check megger test and pannel termination for pannel (LP-IA-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44077 | 44096 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1265 | Check megger test and pannel termination for pannel (PP-IA-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44077 | 44096 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1266 | Check megger test and pannel termination for pannel (EPP-UPS-IA-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44077 | 44096 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1267 | Check megger test and pannel termination for pannel (ELP-CB-IB-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44077 | 44096 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1268 | Check megger test and pannel termination for pannel (LP-IB-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44077 | 44096 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1269 | Check megger test and pannel termination for pannel (PP-IB-05-01) accordding to the attached sketch. | ELEC |  |  | 5th | 44077 | 44096 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1270 | Check megger test and pannel termination for pannel (PP-IB-05-02) accordding to the attached sketch. | ELEC |  |  | 5th | 44077 | 44096 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1271 | Check megger test and pannel termination for pannel (EPP-UPS-IB-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44077 | 44096 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1272 | Check megger test and pannel termination for pannel (ELP-CB-IC-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44077 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1273 | Check megger test and pannel termination for pannel (LP-IC-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44077 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1274 | Check megger test and pannel termination for pannel (PP-IC-05-01) accordding to the attached sketch. | ELEC |  |  | 5th | 44077 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1275 | Check megger test and pannel termination for pannel (PP-IC-05-02) accordding to the attached sketch. | ELEC |  |  | 5th | 44077 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1276 | Check megger test and pannel termination for pannel (EPP-UPS-IC-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1277 | Check megger test and pannel termination for pannel (MCC-5F-IC-02) accordding to the attached sketch. | ELEC |  |  | 5th | 44079 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1278 | Check megger test and pannel termination for pannel (MCC-5F-IC-01) accordding to the attached sketch. | ELEC |  |  | 5th | 44079 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1279 | Check megger test and pannel termination for pannel (ELP-IA-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1280 | Check megger test and pannel termination for pannel (ELP-ID-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1281 | Check megger test and pannel termination for pannel (ELP-CB-ID-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1282 | Check megger test and pannel termination for pannel (LP-ID-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1283 | Check megger test and pannel termination for pannel (PP-ID-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1284 | Check megger test and pannel termination for pannel (EPP-UPS-ID-05) accordding to the attached sketch. | ELEC |  |  | 5th | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1285 | Pls Check The Visual Inspection and megger Test For Low Voltage Copper Plug In Bus way at core (I1) Run 11-LSB 2(CU) (200/700A-25 KA)-3PH+FN+FE -(BD/I1-A/EDB-I1-UPS)(UPSBDI1-A) according to the attached sketch. | ELEC |  |  | B1 | 44079 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1286 | Pls Check The Visual Inspection and megger Test For Low Voltage Copper Plug In Bus way at core (I1) Run 12-LSB 2(CU) (400/700A-25 KA)-3PH+FN+FE -(BD/I1-B1/FEEDING UNIT)(EMBDI2) according to the attached sketch. | ELEC |  |  | B1 | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1287 | Pls Check The Visual Inspection and megger Test For Low Voltage Copper Plug In Bus way at core (I1) Run 13-LSB 2(CU) (1000/1200A-50 KA)-3PH+FN+HE -(BD/I1-B/MDB-I1-SEC1) according to the attached sketch. | ELEC |  |  | B1 | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1288 | Pls Check The Visual Inspection and megger Test For Low Voltage Copper Plug In Bus way at core (I1) Run 14-LSB 2(CU) (1250/1600A-75 KA)-3PH+FN+HE -(BD/I1-B/MDB-I1-SEC2 according to the attached sketch. | ELEC |  |  | B1 | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1289 | Pls Check The Visual Inspection and megger Test For Low Voltage Copper Plug In Bus way at core (I1) Run 15-LSB 2(CU) (400/700A-25 KA)-3PH+FN+HE -(BD/I1-B/EDB-I1-UPS)(UBSDI1-B) according to the attached sketch. | ELEC |  |  | B1 | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1290 | Pls Check The Visual Inspection and megger Test For Low Voltage Copper Plug In Bus way at core (I1) Run 16-LSB 2(CU) (320/700A-25 KA)-3PH+FN+HE -(BD/I1-A/FEEDING UNIT)(MDB I1-SEC3) according to the attached sketch. | ELEC |  |  | B1 | 44079 | 44088 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1291 | Pls Check the first fix(race way) for BMS system at the ninth floor according to the attached sketch. | ELEC |  |  | 9th | 44091 | 44102 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1292 | Pleas Check The fluke test for structured cabling system Cables at the first floor ( Zone2) Refer to FTR (01-010) according to the attached sketches. | ELEC | Z2 | Z2 | 1st | 44096 | 44102 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1293 | Check megger test and pannel termination for pannel (MDBI1) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1294 | Check megger test and pannel termination for pannel (MDBI2) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1295 | Check megger test and pannel termination for pannel (EMDB-I11) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1296 | Check megger test and pannel termination for pannel (EMDB-I12) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1297 | Check megger test and pannel termination for pannel (EMDB-I21) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1298 | Check megger test and pannel termination for pannel (EMDB-I22) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1299 | Check megger test and pannel termination for pannel (G.P.BI1) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1300 | Check megger test and pannel termination for pannel (G.P.BI2) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1301 | Check megger test and pannel termination for pannel (CAPACITOR BANK (CBP-I11)) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1302 | Check megger test and pannel termination for pannel (CAPACITOR BANK (CBP-I12)) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1303 | Check megger test and pannel termination for pannel (CAPACITOR BANK (CBP-I13)) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1304 | Check megger test and pannel termination for pannel (CAPACITOR BANK (CBP-I21)) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1305 | Check megger test and pannel termination for pannel (CAPACITOR BANK (CBP-I22)) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1306 | Check megger test and pannel termination for pannel (CAPACITOR BANK (CBP-I23)) accordding to the attached sketch. | ELEC |  |  | B1 | 44097 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1307 | Pleas Check The fluke test for structured cabling system Cables at the sixth floor ( Zone2) Refer to FTR (06-010) according to the attached sketches. | ELEC |  |  | 6th | 44101 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1308 | Pleas Check The fluke test for structured cabling system Cables at the Seventh floor ( Zone2) Refer to FTR (07-010) according to the attached sketches. | ELEC |  |  | 7th | 44101 | 44108 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1309 | Pleas Check the installation of floor boxies at 9-th floor accordding to the attached sketch. _No.of (FB1)=26 _ No.of (FB2)=14 _No.of (FB4)=8 . | ELEC |  |  | 9th | 44101 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1310 | Pleas Check the installation of floor boxies at the ground floor accordding to the attached sketch. _No.of (FB2)=30 _ No.of (FB4)=10 _No.of (FB6)=6 _No.of (FB7)=3 _No.of (FB8)=7 _No.of (FB11)=24 . | ELEC |  |  | GF | 44101 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1311 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I1) Run1-LSBA(AL) (3200A-100 KA)-3PH+FN+FE -(BD/I1-MDB-I1SEC1)/TRI11 according to the attached sketch. | ELEC |  |  | B1 | 44108 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1312 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I2) Run2-LSBA1(AL) (3200A-100 KA)-3PH+FN+FE -(BD/I2-MDB-I2SEC2)/TRI23 according to the attached sketch. | ELEC |  |  | B1 | 44108 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1313 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I2) Run3-LSBA(AL) (3200A-100 KA)-3PH+FN+FE -(BD/I2-MDB-I2SEC3)/TRI22 according to the attached sketch. | ELEC |  |  | B1 | 44108 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1314 | Pls Check The Visual Inspection and megger Test For Low Voltage Aliuminum Plug In Bus way at core (I2) Run4-LSBA1(AL) (1600A-60 KA)-3PH+FN+FE -(BD/I2-ATS-ID/G.P.B-I2) according to the attached sketch. | ELEC |  |  | B1 | 44108 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1315 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I2) Run5-LSBA1(AL) (1600A-60 KA)-3PH+FN+FE -(BD/I2-ATS-ID/MDB-I2 SEC1) according to the attached sketch. | ELEC |  |  | B1 | 44108 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1316 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I2) Run6-LSBA1(AL) (1600A-60 KA)-3PH+FN+FE -(BD/I2-EMDB-I2/ATS-ID) according to the attached sketch. | ELEC |  |  | B1 | 44108 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1317 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I2) Run7-LSBA1(AL) (1600A-60 KA)-3PH+FN+FE -(BD/I2-ATS-IC-G.P.B-I2) according to the attached sketch. | ELEC |  |  | B1 | 44108 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1318 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I2) Run8-LSBA1(AL) (1600A-60 KA)-3PH+FN+FE -(BD/I2-ATS-IC-/MDB-I2 SEC3) according to the attached sketch. | ELEC |  |  | B1 | 44108 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1319 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I2) Run9-LSBA1(AL) (1600A-60 KA)-3PH+FN+FE -(BD/I2-EMDB-I22/ATS-IC) according to the attached sketch. | ELEC |  |  | B1 | 44108 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1320 | Check megger test and pannel termination for pannel (ELP-CB-IA-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1321 | Check megger test and pannel termination for pannel (ELP-IA-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1322 | Check megger test and pannel termination for pannel (LP-IA-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1323 | Check megger test and pannel termination for pannel (ELP-LS-IA-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1324 | Check megger test and pannel termination for pannel (PP-IA-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1325 | Check megger test and pannel termination for pannel (EPP-UPS-IA-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1326 | Check megger test and pannel termination for pannel (ELP-CB-IB-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1327 | Check megger test and pannel termination for pannel (ELP-IB-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1328 | Check megger test and pannel termination for pannel (LP-IB-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1329 | Check megger test and pannel termination for pannel (ELP-LS-IB-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1330 | Check megger test and pannel termination for pannel (PP-IB-04-01) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1331 | Check megger test and pannel termination for pannel (PP-IB-04-02) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1332 | Check megger test and pannel termination for pannel (EPUPS-IB-04-02) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1333 | Check megger test and pannel termination for pannel (ELP-CB-IC-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1334 | Check megger test and pannel termination for pannel (ELP-IC-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1335 | Check megger test and pannel termination for pannel (LP-IC-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1336 | Check megger test and pannel termination for pannel (ELP-LS-IC-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1337 | Check megger test and pannel termination for pannel (MCC-4F-IC-01) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1338 | Check megger test and pannel termination for pannel (MCC-4F-IC-02) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1339 | Check megger test and pannel termination for pannel (MCC-4F-IC-03) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1340 | Check megger test and pannel termination for pannel (MCC-4F-IC-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1341 | Check megger test and pannel termination for pannel (PP-IC-04-01) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1342 | Check megger test and pannel termination for pannel (PP-IC-04-02) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1343 | Check megger test and pannel termination for pannel (EPP-UPS-IC-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1344 | Check megger test and pannel termination for pannel (ELP-CB-ID-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1345 | Check megger test and pannel termination for pannel (ELP-ID-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1346 | Check megger test and pannel termination for pannel (LP-ID-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1347 | Check megger test and pannel termination for pannel (ELP-LS-ID-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1348 | Check megger test and pannel termination for pannel (PP-ID-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1349 | Check megger test and pannel termination for pannel (EPP-UPS-ID-04) accordding to the attached sketch. | ELEC |  |  | 4th | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1350 | Check megger test and pannel termination for pannel (PP-IA-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1351 | Check megger test and pannel termination for pannel (EPP-UPS-IA-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1352 | Check megger test and pannel termination for pannel (ELP-CB-IA-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1353 | Check megger test and pannel termination for pannel (LP-IA-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1354 | Check megger test and pannel termination for pannel (ELP-IA-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1355 | Check megger test and pannel termination for pannel (ELP-CB-IB-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1356 | Check megger test and pannel termination for pannel (ELP-IB-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1357 | Check megger test and pannel termination for pannel (LP-IB-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1358 | Check megger test and pannel termination for pannel (PP-IB-03-01) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1359 | Check megger test and pannel termination for pannel (PP-IB-03-02) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1360 | Check megger test and pannel termination for pannel (EPP-UPS-IB-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44118 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1361 | Check megger test and pannel termination for pannel (ELP-CB-IC-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1362 | Check megger test and pannel termination for pannel (ELP-IC-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1363 | Check megger test and pannel termination for pannel (LP-IC-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1364 | Check megger test and pannel termination for pannel (MCC-3F-IC-01) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1365 | Check megger test and pannel termination for pannel (MCC-3F-IC-02) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1366 | Check megger test and pannel termination for pannel (PP-IC-03-01) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1367 | Check megger test and pannel termination for pannel (PP-IC-03-02) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1368 | Check megger test and pannel termination for pannel (EPP-UPS-IC-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1369 | Check megger test and pannel termination for pannel (ELP-ID-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1370 | Check megger test and pannel termination for pannel (ELP-CB-ID-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1371 | Check megger test and pannel termination for pannel (LP-ID-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1372 | Check megger test and pannel termination for pannel (PP-ID-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1373 | Check megger test and pannel termination for pannel (EPP-UPS-ID-03) accordding to the attached sketch. | ELEC |  |  | 3rd | 44110 | 44119 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1374 | Check megger test and pannel termination for pannel (EDB-IA-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1375 | Check megger test and pannel termination for pannel (PP-IA-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1376 | Check megger test and pannel termination for pannel (EPP-UPS-IA-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1377 | Check megger test and pannel termination for pannel (ELP-IA-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1378 | Check megger test and pannel termination for pannel (ELP-CB-IA-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1379 | Check megger test and pannel termination for pannel (LP-IA-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1380 | Check megger test and pannel termination for pannel (ELP-CB-IB-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1381 | Check megger test and pannel termination for pannel (ELP-IB-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1382 | Check megger test and pannel termination for pannel (LP-IB-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1383 | Check megger test and pannel termination for pannel (PP-IB-2-1) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1384 | Check megger test and pannel termination for pannel (PP-IB-2-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1385 | Check megger test and pannel termination for pannel (EPP-UPS-IB-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1386 | Check megger test and pannel termination for pannel (ELP-CB-IC-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1387 | Check megger test and pannel termination for pannel (ELP-IC-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1388 | Check megger test and pannel termination for pannel (LP-IC-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1389 | Check megger test and pannel termination for pannel (MCC-2F-IC-01) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1390 | Check megger test and pannel termination for pannel (MCC-2F-IC-02) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1391 | Check megger test and pannel termination for pannel (PP-IC-2-1) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1392 | Check megger test and pannel termination for pannel (PP-IC-2-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1393 | Check megger test and pannel termination for pannel (EPP-UPS-IC-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1394 | Check megger test and pannel termination for pannel (EDB-ID-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1395 | Check megger test and pannel termination for pannel (ELP-ID-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1396 | Check megger test and pannel termination for pannel (ELP-CB-ID-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1397 | Check megger test and pannel termination for pannel (LP-ID-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1398 | Check megger test and pannel termination for pannel (PP-ID-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1399 | Check megger test and pannel termination for pannel (EPP-UPS-ID-2) accordding to the attached sketch. | ELEC |  |  | 2nd | 44117 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1400 | Check megger test and pannel termination for pannel (ELP-CB-IA-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1401 | Check megger test and pannel termination for pannel (EPP-UPS-IA-1-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1402 | Check megger test and pannel termination for pannel (EPP-UPS-IA-1-2) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1403 | Check megger test and pannel termination for pannel (ELP-LS-IA-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1404 | Check megger test and pannel termination for pannel (ELP-IA-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1405 | Check megger test and pannel termination for pannel (LP-IA-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1406 | Check megger test and pannel termination for pannel (PP-IA-1-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1407 | Check megger test and pannel termination for pannel (PP-IA-1-2) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1408 | Check megger test and pannel termination for pannel (ELP-CB-IB-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1409 | Check megger test and pannel termination for pannel (ELP-IB-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1410 | Check megger test and pannel termination for pannel (ELP-LS-IB-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1411 | Check megger test and pannel termination for pannel (EPP-UPS-IB-1-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1412 | Check megger test and pannel termination for pannel (EPP-UPS-IB-1-2) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1413 | Check megger test and pannel termination for pannel (LP-IB-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1414 | Check megger test and pannel termination for pannel (PP-IB-1-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1415 | Check megger test and pannel termination for pannel (PP-IB-1-2) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1416 | Check megger test and pannel termination for pannel (ELP-CB-IC-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1417 | Check megger test and pannel termination for pannel (ELP-IC-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1418 | Check megger test and pannel termination for pannel (ELP-LS-IC-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1419 | Check megger test and pannel termination for pannel (EPP-UPS-IC-1-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1420 | Check megger test and pannel termination for pannel (EPP-UPS-IC-1-2) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1421 | Check megger test and pannel termination for pannel (LP-IC-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1422 | Check megger test and pannel termination for pannel (MCC-1F-IC-01) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1423 | Check megger test and pannel termination for pannel (MCC-1F-IC-02) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1424 | Check megger test and pannel termination for pannel (MCC-1F-IC-03) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1425 | Check megger test and pannel termination for pannel (MCC-1F-IC-04) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44128 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1426 | Check megger test and pannel termination for pannel (PP-IC-1-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1427 | Check megger test and pannel termination for pannel (PP-IC-1-2) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1428 | Check megger test and pannel termination for pannel (ELP-LS-ID-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1429 | Check megger test and pannel termination for pannel (EPP-UPS-ID-1-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1430 | Check megger test and pannel termination for pannel (EPP-UPS-ID-1-2) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1431 | Check megger test and pannel termination for pannel (PP-ID-1-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1432 | Check megger test and pannel termination for pannel (PP-ID-1-2) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1433 | Check megger test and pannel termination for pannel (ELP-ID-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1434 | Check megger test and pannel termination for pannel (ELP-CB-ID-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44119 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1435 | Check megger test and pannel termination for pannel (LP-ID-1) accordding to the attached sketch. | ELEC |  |  | 1st | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1436 | Check megger test and pannel termination for pannel (EDB-CRAC_MTR_I1) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1437 | Check megger test and pannel termination for pannel (EDB-UPS_MTR_I1) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1438 | Check megger test and pannel termination for pannel (EPP-UPS_IA_G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1439 | Check megger test and pannel termination for pannel (EPP-UPS_MTR_I1-1) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1440 | Check megger test and pannel termination for pannel (EPP-UPS_MTR_I1-2) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1441 | Check megger test and pannel termination for pannel (LP-LAND-IA-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1442 | Check megger test and pannel termination for pannel (PP-IA-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1443 | Check megger test and pannel termination for pannel (ELP-CB-IA-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1444 | Check megger test and pannel termination for pannel (ELP-IA-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1445 | Check megger test and pannel termination for pannel (ELP-SERV-IA-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1446 | Check megger test and pannel termination for pannel (LP-IA-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1447 | Check megger test and pannel termination for pannel (EPP-UPS-IB-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1448 | Check megger test and pannel termination for pannel (LP-LAND-IB-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1449 | Check megger test and pannel termination for pannel (PP-IB-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1450 | Check megger test and pannel termination for pannel (ELP-CB-IB-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1451 | Check megger test and pannel termination for pannel (ELP-IB-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1452 | Check megger test and pannel termination for pannel (LP-IB-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1453 | Check megger test and pannel termination for pannel (ELP-SERV-IB-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1454 | Check megger test and pannel termination for pannel (EPP-UPS-CONC-IC-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1455 | Check megger test and pannel termination for pannel (EPP-UPS-IC-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1456 | Check megger test and pannel termination for pannel (LP-LAND-IC-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1457 | Check megger test and pannel termination for pannel (MCC-GF-IC-01) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1458 | Check megger test and pannel termination for pannel (MCC-GF-IC-02) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1459 | Check megger test and pannel termination for pannel (PP-IC-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1460 | Check megger test and pannel termination for pannel (ELP-CB-IC-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1461 | Check megger test and pannel termination for pannel (ELP-IC-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1462 | Check megger test and pannel termination for pannel (LP-IC-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1463 | Check megger test and pannel termination for pannel (ELP-SERV-IC-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1464 | Check megger test and pannel termination for pannel (EDB-CRAC-MTR-I2-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1465 | Check megger test and pannel termination for pannel (EDB-UPS-MTR-I2-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1466 | Check megger test and pannel termination for pannel (EPP-UPS-ID-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1467 | Check megger test and pannel termination for pannel (EPP-UPS-MTR-I2-1) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1468 | Check megger test and pannel termination for pannel (EPP-UPS-MTR-I2-2) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1469 | Check megger test and pannel termination for pannel (LP-LAND-ID-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1470 | Check megger test and pannel termination for pannel (PP-ID-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1471 | Check megger test and pannel termination for pannel (ELP-ID-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1472 | Check megger test and pannel termination for pannel (ELP-CB-ID-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1473 | Check megger test and pannel termination for pannel (LP-ID-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1474 | Check megger test and pannel termination for pannel (ELP-SERV-ID-G) accordding to the attached sketch. | ELEC |  |  | GF | 44125 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1475 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I1) Run1-LSBA(AL) (3200A-100 KA)-3PH+FN+FE -(BD/I1-MDB-I1SEC1)/TRI11 according to the attached sketch. | ELEC |  |  | B1 | 44131 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1476 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I1) Run2-LSBA(AL) (3200A-100 KA)-3PH+FN+FE -(BD/I1-MDB-I1SEC2)/TRI13 according to the attached sketch. | ELEC |  |  | B1 | 44131 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1477 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I1) Run3-LSBA(AL) (3200A-100 KA)-3PH+FN+FE -(BD/I1-MDB-I1SEC3)/TRI12 according to the attached sketch. | ELEC |  |  | B1 | 44131 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1478 | Pls Check The Visual Inspection and megger Test For Low Voltage Aliuminum Plug In Bus way at core (I1) Run4-LSBA1(AL) (1600A-60 KA)-3PH+FN+FE -(BD/I1-ATS-IB/G.P.B-I1) according to the attached sketch. | ELEC |  |  | B1 | 44131 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1479 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I1) Run5-LSBA1(AL) (1600A-60 KA)-3PH+FN+FE -(BD/I1-ATS-IB/MDB-I1 SEC1) according to the attached sketch. | ELEC |  |  | B1 | 44131 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1480 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I1) Run6-LSBA1(AL) (1600A-60 KA)-3PH+FN+FE -(BD/I1-EMDB-I1/ATS-IB) according to the attached sketch. | ELEC |  |  | B1 | 44131 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1481 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I1) Run7-LSBA1(AL) (1600A-60 KA)-3PH+FN+FE -(BD/I1-ATS-IA-G.P.B-I1) according to the attached sketch. | ELEC |  |  | B1 | 44131 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1482 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I1) Run8-LSBA1(AL) (1600A-60 KA)-3PH+FN+FE -(BD/I1-ATS-IA-/MDB-I1 SEC3) according to the attached sketch. | ELEC |  |  | B1 | 44131 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1483 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I1) Run9-LSBA1(AL) (1600A-60 KA)-3PH+FN+FE -(BD/I1-EMDB-I12/ATS-IA) according to the attached sketch. | ELEC |  |  | B1 | 44131 | 44140 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1484 | PLS Check Installing and connecting 22KV multi core cables (3x300)mm2 AL/XLPE/STA/PVC between the R.M.U and medium voltage switchgear accordding to the attached sketch. -total legnth=57 m. | ELEC |  |  | GF | 44131 | 44145 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1485 | PLS Check the Installation of duct bank pipes(4 inch) for lv and lc manholes at the site plane accordding to the attached sketches. -no. of lv manholes=14 _no.of lc manholes=36. | ELEC |  |  | EX | 44135 | 44161 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1486 | PLS Check the Installation of HDMI outlets at the first floor accordding to the attached sketches. | ELEC |  |  | 1st | 44135 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1487 | PLS Check the Installation of HDMI outlets at the second floor accordding to the attached sketches. | ELEC |  |  | 2nd | 44135 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1488 | PLS Check the Installation of HDMI outlets at the third floor accordding to the attached sketches. | ELEC |  |  | 3rd | 44135 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1489 | PLS Check the Installation of HDMI outlets at the fourth floor accordding to the attached sketches. | ELEC |  |  | 4th | 44135 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1490 | PLS Check the Installation of HDMI outlets at the 5th floor accordding to the attached sketches. | ELEC |  |  | 5th | 44135 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1491 | PLS Check the Installation of HDMI outlets at the 6th floor accordding to the attached sketches. | ELEC |  |  | 6th | 44135 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1492 | PLS Check the Installation of HDMI outlets at the 7th floor accordding to the attached sketches. | ELEC |  |  | 7th | 44135 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1493 | PLS Check the Installation of HDMI outlets at the 8th floor accordding to the attached sketches. | ELEC |  |  | 8th | 44135 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1494 | PLS Check the Installation of HDMI outlets at the 9th floor accordding to the attached sketches. | ELEC |  |  | 9th | 44135 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1495 | Check mockup (LPR camera) for integrated security system according to the attached sketch. | ELEC |  |  | EX | 44139 | 44171 | D
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1496 | Check mockup for access control pannel(ACP-1-4-04) (Enclosure and boards (LP1501+2 OF DDM+DRC-100)) at first floor zone 1 according to the attached sketch. | ELEC |  |  | 1st | 44139 | 44145 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1497 | Check the third fix and wiring devices installation at the first floor according to the attached sketches and QS sheet. | ELEC |  |  | 1st | 44142 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1498 | Check the third fix and wiring devices installation at the scond floor according to the attached sketches and QS sheet. | ELEC |  |  | 2nd | 44142 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1499 | Check megger test and pannel termination for pannel (EDB-CB-IA) accordding to the attached sketch. | ELEC |  |  | B1 | 44150 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1500 | Check megger test and pannel termination for pannel (EDB-LS-IA-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44150 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1501 | Check megger test and pannel termination for pannel (ELP-CB-IA-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44150 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1502 | Check megger test and pannel termination for pannel (EPP-UPS-IA-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44150 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1503 | Check megger test and pannel termination for pannel (ELP-IA-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44150 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1504 | Check megger test and pannel termination for pannel (ELP-LS-IA-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44150 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1505 | Check megger test and pannel termination for pannel (LP-IA-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44150 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1506 | Check megger test and pannel termination for pannel (ELP-CB-IB-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44150 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1507 | Check megger test and pannel termination for pannel (EDB-CB-IB) accordding to the attached sketch. | ELEC |  |  | B1 | 44150 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1508 | Check megger test and pannel termination for pannel (ELP-IB-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44150 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1509 | Check megger test and pannel termination for pannel (ELP-LS-IB-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44150 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1510 | Check megger test and pannel termination for pannel (EPP-UPS-IB-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44150 | 44161 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1511 | Check megger test and pannel termination for pannel (LP-IB-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44150 | 44161 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1512 | Check megger test and pannel termination for pannel (ELP-CB-IC-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1513 | Check megger test and pannel termination for pannel (EDB-CB-IC-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1514 | Check megger test and pannel termination for pannel (EDB-LS-IC-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1515 | Check megger test and pannel termination for pannel (ELP-IC-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1516 | Check megger test and pannel termination for pannel (ELP-LS-IC-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1517 | Check megger test and pannel termination for pannel (EPP-UPS-IC-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | D
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1518 | Check megger test and pannel termination for pannel (LP-IC-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1519 | Check megger test and pannel termination for pannel (EMCC-B1-IC-01) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1520 | Check megger test and pannel termination for pannel (EMCC-B1-IC-02) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1521 | Check megger test and pannel termination for pannel (EMCC-B1-IC-03) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1522 | Check megger test and pannel termination for pannel (EMCC-B1-IC-04) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1523 | Check megger test and pannel termination for pannel (EMCC-B1-IC-05) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1524 | Check megger test and pannel termination for pannel (MCC-B1-IC-01) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1525 | Check megger test and pannel termination for pannel (EDB-CB-IC-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1526 | Check megger test and pannel termination for pannel (EDB-LS-ID-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1527 | Check megger test and pannel termination for pannel (ELP-LS-ID-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1528 | Check megger test and pannel termination for pannel (EPP-UPS-ID-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1529 | Check megger test and pannel termination for pannel (ELP-ID-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1530 | Check megger test and pannel termination for pannel (ELP-CB-ID-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1531 | Check megger test and pannel termination for pannel (LP-ID-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1532 | Check megger test and pannel termination for pannel (EDB-LS-IB-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1533 | Check megger test and pannel termination for pannel (DB-I1-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1534 | Check megger test and pannel termination for pannel (DB-I2-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1535 | Check megger test and pannel termination for pannel (EDB-I1-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1536 | Check megger test and pannel termination for pannel (EDB-I1-UPS-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1537 | Check megger test and pannel termination for pannel (EDB-I2-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1538 | Check megger test and pannel termination for pannel (EDB-I2-UPS-B1) accordding to the attached sketch. | ELEC |  |  | B1 | 44151 | 44165 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1539 | Check the third fix and wiring devices installation at the third floor according to the attached sketches and QS sheet. | ELEC |  |  | 3rd | 44151 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1540 | Check the third fix and wiring devices installation at the fourth floor according to the attached sketches and QS sheet. | ELEC |  |  | 4th | 44151 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1541 | Check the third fix and wiring devices installation at the fifth floor according to the attached sketches and QS sheet. | ELEC |  |  | 5th | 44151 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1542 | PLS Check Installation and Termination for Split Unit Cables from ELP Pannels to FTR Rooms according to the attached Table. | ELEC |  |  | ML | 44151 | 44178 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1543 | Check the third fix and wiring devices installation at the seventh floor according to the attached sketches and QS sheet. | ELEC |  |  | 7th | 44166 | 44193 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1544 | Check the third fix and wiring devices installation for power system at the first basement floor according to the attached sketches and QS sheet. | ELEC |  |  | B1 | 44172 | 44207 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1545 | Pls Check The Quantity Survy for Bus Duct componant according to the attached QS sheet. | ELEC |  |  | ML | 44175 | 44207 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1546 | Check megger test and pannel termination for pannel (ELP-IB-08) according to the attached sketch. | ELEC |  |  | 8th | 44180 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1547 | Check megger test and pannel termination for pannel (MCC-8F-IC-01) accordding to the attached sketch. | ELEC |  |  | 8th | 44180 | 44207 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1548 | Check megger test and pannel termination for pannel (EPP-UPS-IB-08) according to the attached sketch. | ELEC |  |  | 8th | 44180 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1549 | Check megger test and pannel termination for pannel (PP-IC-07) according to the attached sketch. | ELEC |  |  | 7th | 44180 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1550 | Check megger test and pannel termination for pannel (ELP-IB-06) accordding to the attached sketch. | ELEC |  |  | 6th | 44180 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1551 | Check megger test and pannel termination for pannel (ELP-IC-06) accordding to the attached sketch. | ELEC |  |  | 6th | 44180 | 44201 | D
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1552 | Check megger test and pannel termination for pannel (EMCC-6F-IC-01) accordding to the attached sketch. | ELEC |  |  | 6th | 44180 | 44207 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1553 | Check megger test and pannel termination for pannel (EMCC-6F-IC-02) accordding to the attached sketch. | ELEC |  |  | 6th | 44180 | 44207 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1554 | Check megger test and pannel termination for pannel (ELP-IB-05) according to the attached sketch. | ELEC |  |  | 5th | 44180 | 44201 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1555 | Check megger test and pannel termination for pannel (ELP-IC-05) according to the attached sketch. | ELEC |  |  | 5th | 44180 | 44201 | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1556 | Check megger test and pannel termination for pannel (EPP-UPS-IA-B1) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1557 | Check megger test and pannel termination for pannel (ELP-CB-IA-B1) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1558 | Check megger test and pannel termination for pannel (ELP-IA-B1) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1559 | Check megger test and pannel termination for pannel (LP-IA-B1) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1560 | Check megger test and pannel termination for pannel (ELP-CB-IB-B2) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1561 | Check megger test and pannel termination for pannel (ELP-IB-B2) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1562 | Check megger test and pannel termination for pannel (EPP-UPS-IB-B2) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1563 | Check megger test and pannel termination for pannel (LP-IB-B2) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1564 | Check megger test and pannel termination for pannel (ELP-CB-IC-B2) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1565 | Check megger test and pannel termination for pannel (ELP-IC-B2) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1566 | Check megger test and pannel termination for pannel (EPP-UPS-IC-B2) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1567 | Check megger test and pannel termination for pannel (LP-IC-B2) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1568 | Check megger test and pannel termination for pannel (EMCC-B2-IC-01) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1569 | Check megger test and pannel termination for pannel (EMCC-B2-IC-02) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1570 | Check megger test and pannel termination for pannel (EMCC-B2-IC-03) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1571 | Check megger test and pannel termination for pannel (EMCC-B2-IC-04) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1572 | Check megger test and pannel termination for pannel (EMCC-B2-IC-05) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1573 | Check megger test and pannel termination for pannel (EMCC-B2-IC-06) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44193 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1574 | Check megger test and pannel termination for pannel (EPP-UPS-ID-B2) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1575 | Check megger test and pannel termination for pannel (ELP-ID-B2) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1576 | Check megger test and pannel termination for pannel (ELP-CB-ID-B2) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1577 | Check megger test and pannel termination for pannel (LP-ID-B2) according to the attached sketch. | ELEC |  |  | B2 | 44181 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1578 | Check megger test and pannel termination for pannel (ELP-IB-05) according to the attached sketch. | ELEC |  |  | 5th | 44185 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1579 | Check megger test and pannel termination for pannel (ELP-IC-05) according to the attached sketch. | ELEC |  |  | 5th | 44185 | 44201 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1580 | Check mockup for installation Test link for cable (240MM) at riser for (Earthing system) At FTR First floor Z(1) according to the attached . | ELEC | Z1 | Z1 | 1st | 44195 | 44207 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1581 | Check the third fix and wiring devices installation at the eighth floor accoording to the attached sketches and QS sheet. | ELEC |  |  | 8th | 44202 | 44223 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1582 | Check the third fix and wiring devices installation at the sixth floor acoording to the attached sketches and QS sheet. | ELEC |  |  | 6th | 44214 | 44223 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1583 | Check the third fix and wiring devices installation at the ninth floor according to the attached sketches and QS sheet. | ELEC |  |  | 9th | 44217 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1584 | CheckTesting and Commissioning for Pannel (ELP-CB-IB-09) according to the attached sketches. | ELEC |  |  | 9th | 44220 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1585 | CheckTesting and Commissioning for Pannel (ELP-IB-09-01) according to the attached sketches. | ELEC |  |  | 9th | 44220 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1586 | CheckTesting and Commissioning for Pannel (LP-IB-09) according to the attached sketches. | ELEC |  |  | 9th | 44220 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1587 | CheckTesting and Commissioning for Pannel (EPP-UPS-IB-09) according to the attached sketches. | ELEC |  |  | 9th | 44220 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1588 | Check the third fix and lighting fixures installation for land scape lighting type(LS2) according to the attached sketches . - NO.OF FIXTURE TYPE (LS2)=12 . | ELEC |  |  | EX | 44222 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1589 | CheckTesting and Commissioning for Pannel (ELP-CB-IB-08) according to the attached sketches. | ELEC |  |  | 8th | 44222 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1590 | CheckTesting and Commissioning for Pannel (ELP-IB-08) according to the attached sketches. | ELEC |  |  | 8th | 44222 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1591 | CheckTesting and Commissioning for Pannel (LP-IC-08) according to the attached sketches. | ELEC |  |  | 8th | 44222 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1592 | CheckTesting and Commissioning for Pannel (PP-IC-08) according to the attached sketches. | ELEC |  |  | 8th | 44222 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1593 | CheckTesting and Commissioning for Pannel (EPP-UPS-IB-08) according to the attached sketches. | ELEC |  |  | 8th | 44222 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1594 | CheckTesting and Commissioning for Pannel (EPP-LIFT-IC-08) according to the attached sketches. | ELEC |  |  | 8th | 44222 | 44364 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1595 | Check the third fix and lighting fixures installation for land scape lighting type(P1) according to the attached sketches . - NO.OF FIXTURE TYPE (P1)=12 . | ELEC |  |  | EX | 44222 | 44252 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1596 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I2) Run10-LSBA1(AL) (2500A-100 KA)-3PH+FN+FE-(BD/I2-G.P.B-I2/Generator Box) according to the attached sketch. | ELEC |  |  | B1 | 44227 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1597 | CheckTesting and Commissioning for Pannel (ELP-CB-IB-07) according to the attached sketches. | ELEC |  |  | 7th | 44228 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1598 | CheckTesting and Commissioning for Pannel (ELP_IB_07) according to the attached sketches. | ELEC |  |  | 7th | 44228 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1599 | CheckTesting and Commissioning for Pannel (LP_IB_07) according to the attached sketches. | ELEC |  |  | 7th | 44228 | 44238 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1600 | CheckTesting and Commissioning for Pannel (ELP_LS_IC_07) according to the attached sketches. | ELEC |  |  | 7th | 44228 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1601 | CheckTesting and Commissioning for Pannel (ELP_IC_07) according to the attached sketches. | ELEC |  |  | 7th | 44228 | 44238 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1602 | CheckTesting and Commissioning for Pannel (LP_IC_07) according to the attached sketches. | ELEC |  |  | 7th | 44228 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1603 | CheckTesting and Commissioning for Pannel (LP-ID-06) according to the attached sketches. | ELEC |  |  | 6th | 44230 | 44263 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1604 | CheckTesting and Commissioning for Pannel (LP-ID-05) according to the attached sketches. | ELEC |  |  | 5th | 44230 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1605 | CheckTesting and Commissioning for Pannel (EPP-UPS-ID-05) according to the attached sketches. | ELEC |  |  | 5th | 44230 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1606 | CheckTesting and Commissioning for Pannel (ELP-CB-ID-05) according to the attached sketches. | ELEC |  |  | 5th | 44230 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1607 | CheckTesting and Commissioning for Pannel (ELP-LS-ID-04) according to the attached sketches. | ELEC |  |  | 4th | 44230 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1608 | CheckTesting and Commissioning for Pannel (ELP-CB-ID-04) according to the attached sketches. | ELEC |  |  | 4th | 44230 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1609 | CheckTesting and Commissioning for Pannel (LP-ID-04) according to the attached sketches. | ELEC |  |  | 4th | 44230 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1610 | CheckTesting and Commissioning for Pannel (EPP-UPS-ID-04) according to the attached sketches. | ELEC |  |  | 4th | 44230 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1611 | CheckTesting and Commissioning for Pannel (LP-IC-04) according to the attached sketches. | ELEC |  |  | 4th | 44230 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1612 | CheckTesting and Commissioning for Pannel (ELP-CB-IC-04) according to the attached sketches. | ELEC |  |  | 4th | 44230 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1613 | CheckTesting and Commissioning for Pannel (ELP-LS-IC-04) according to the attached sketches. | ELEC |  |  | 4th | 44230 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1614 | CheckTesting and Commissioning for Pannel (LP-ID-03) according to the attached sketches. | ELEC |  |  | 3rd | 44230 | 44263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1615 | CheckTesting and Commissioning for Pannel (LP-ID-03) according to the attached sketches. | ELEC |  |  | 3rd | 44230 | 44263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1616 | CheckTesting and Commissioning for Pannel (LP-IC-02) according to the attached sketches. | ELEC |  |  | 2nd | 44233 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1617 | CheckTesting and Commissioning for Pannel (ELP-CB-IC-02) according to the attached sketches. | ELEC |  |  | 2nd | 44233 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1618 | CheckTesting and Commissioning for Pannel (EPP-UPS-ID-02) according to the attached sketches. | ELEC |  |  | 2nd | 44233 | 44243 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1619 | CheckTesting and Commissioning for Pannel (EDB-ID-02) according to the attached sketches. | ELEC |  |  | 2nd | 44233 | 44346 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1620 | CheckTesting and Commissioning for Pannel (EPP-UPS-IC-1-1) according to the attached sketches. | ELEC |  |  | 1st | 44233 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1621 | CheckTesting and Commissioning for Pannel (EPP-UPS-IC-1-2) according to the attached sketches. | ELEC |  |  | 1st | 44233 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1622 | CheckTesting and Commissioning for Pannel (ELP-LS-IC-1) according to the attached sketches. | ELEC |  |  | 1st | 44233 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1623 | CheckTesting and Commissioning for Pannel (ELP-CB-IC-01) according to the attached sketches. | ELEC |  |  | 1st | 44233 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1624 | CheckTesting and Commissioning for Pannel (PP-ID-1-1) according to the attached sketches. | ELEC |  |  | 1st | 44233 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1625 | CheckTesting and Commissioning for Pannel (PP-ID-1-2) according to the attached sketches. | ELEC |  |  | 1st | 44233 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1626 | CheckTesting and Commissioning for Pannel (EPP-UPS-ID-1-1) according to the attached sketches. | ELEC |  |  | 1st | 44233 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1627 | CheckTesting and Commissioning for Pannel (EPP-UPS-ID-1-2) according to the attached sketches. | ELEC |  |  | 1st | 44233 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1628 | CheckTesting and Commissioning for Pannel (ELP-LS-ID-1) according to the attached sketches. | ELEC |  |  | 1st | 44233 | 44238 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1629 | CheckTesting and Commissioning for Pannel (ELP-IA-05) according to the attached sketches. | ELEC |  |  | 5th | 44238 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1630 | CheckTesting and Commissioning for Pannel (ELP-CB-IA-05) according to the attached sketches. | ELEC |  |  | 5th | 44238 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1631 | CheckTesting and Commissioning for Pannel (EPP-UPS-IA-05) according to the attached sketches. | ELEC |  |  | 5th | 44238 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1632 | CheckTesting and Commissioning for Pannel (LP-IA-05) according to the attached sketches. | ELEC |  |  | 5th | 44238 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1633 | CheckTesting and Commissioning for Pannel (LP-IB-05) according to the attached sketches. | ELEC |  |  | 5th | 44238 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1634 | CheckTesting and Commissioning for Pannel (ELP-CB-IB-05) according to the attached sketches. | ELEC |  |  | 5th | 44238 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1635 | CheckTesting and Commissioning for Pannel (EPP-UPS-IB-05) according to the attached sketches. | ELEC |  |  | 5th | 44238 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1636 | CheckTesting and Commissioning for Pannel (PP-IB-5-1) according to the attached sketches. | ELEC |  |  | 5th | 44238 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1637 | CheckTesting and Commissioning for Pannel (PP-IB-5-1) according to the attached sketches. | ELEC |  |  | 5th | 44238 | 44251 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1638 | Check the third fix and lighting fixures installation for land scape lighting type(LS1) according to the attached sketches . - NO.OF FIXTURE TYPE (LS1)=117 . | ELEC |  |  | EX | 44243 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1639 | Check the third fix and lighting fixures installation for land scape lighting type(LS3) according to the attached sketches . - NO.OF FIXTURE TYPE (LS3)=115 . | ELEC |  |  | EX | 44243 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1640 | Check the third fix and lighting fixures installation for land scape lighting type(LS4) according to the attached sketches . - NO.OF FIXTURE TYPE (LS4)=74 . | ELEC |  |  | EX | 44243 | 44271 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1641 | Check the third fix and lighting fixures installation for land scape lighting type(LS5) according to the attached sketches . - NO.OF FIXTURE TYPE (LS5)= 37 . | ELEC |  |  | EX | 44243 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1642 | Check the third fix and lighting fixures installation for land scape lighting type(LS6) according to the attached sketches . - NO.OF FIXTURE TYPE (LS6)= 30 . | ELEC |  |  | EX | 44243 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1643 | CheckTesting and Commissioning for Pannel (ELP-IB-05) according to the attached sketches. | ELEC |  |  | 5th | 44248 | 44258 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1644 | CheckTesting and Commissioning for Pannel (PP-IA-05) according to the attached sketches. | ELEC |  |  | 5th | 44248 | 44258 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1645 | CheckTesting and Commissioning for Pannel (ELP-LS-IA-04) according to the attached sketches. | ELEC |  |  | 4th | 44248 | 44258 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1646 | CheckTesting and Commissioning for Pannel (ELP-IA-04) according to the attached sketches. | ELEC |  |  | 4th | 44248 | 44258 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1647 | CheckTesting and Commissioning for Pannel (ELP-CB-IA-04) according to the attached sketches. | ELEC |  |  | 4th | 44248 | 44258 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1648 | CheckTesting and Commissioning for Pannel (LP-IB-04) according to the attached sketches. | ELEC |  |  | 4th | 44248 | 44258 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1649 | CheckTesting and Commissioning for Pannel (ELP-LS-IB-04) according to the attached sketches. | ELEC |  |  | 4th | 44248 | 44258 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1650 | CheckTesting and Commissioning for Pannel (EPP-UPS-IB-04) according to the attached sketches. | ELEC |  |  | 4th | 44248 | 44258 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1651 | CheckTesting and Commissioning for Pannel (ELP-IB-04) according to the attached sketches. | ELEC |  |  | 4th | 44248 | 44258 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1652 | CheckTesting and Commissioning for Pannel (PP-IB-04-1) according to the attached sketches. | ELEC |  |  | 4th | 44248 | 44258 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1653 | CheckTesting and Commissioning for Pannel (ELP-CB-IB-04) according to the attached sketches. | ELEC |  |  | 4th | 44248 | 44258 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1654 | CheckTesting and Commissioning for Pannel (PP-ID-06) according to the attached sketches. | ELEC |  |  | 6th | 44248 | 44258 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1655 | CheckTesting and Commissioning for Pannel (ELP-CB-IA-03) according to the attached sketches. | ELEC |  |  | 3rd | 44252 | 44263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1656 | CheckTesting and Commissioning for Pannel (ELP-CB-IA-03) according to the attached sketches. | ELEC |  |  | 3rd | 44252 | 44263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1657 | CheckTesting and Commissioning for Pannel (LP-IA-03) according to the attached sketches. | ELEC |  |  | 3rd | 44252 | 44263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1658 | CheckTesting and Commissioning for Pannel (PP-IA-03) according to the attached sketches. | ELEC |  |  | 3rd | 44252 | 44263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1659 | CheckTesting and Commissioning for Pannel (EPP-UPS-IA-03) according to the attached sketches. | ELEC |  |  | 3rd | 44252 | 44263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1660 | CheckTesting and Commissioning for Pannel (ELP-CB-IB-03) according to the attached sketches. | ELEC |  |  | 3rd | 44252 | 44263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1661 | CheckTesting and Commissioning for Pannel (ELP-IB-03) according to the attached sketches. | ELEC |  |  | 3rd | 44252 | 44263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1662 | CheckTesting and Commissioning for Pannel (LP-IB-03) according to the attached sketches. | ELEC |  |  | 3rd | 44252 | 44263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1663 | CheckTesting and Commissioning for Pannel (PP-IB-03-1) according to the attached sketches. | ELEC |  |  | 3rd | 44252 | 44263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1664 | CheckTesting and Commissioning for Pannel (PP-IB-03-2) according to the attached sketches. | ELEC |  |  | 3rd | 44252 | 44263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1665 | CheckTesting and Commissioning for Pannel (EPP-UPS-IB-03) according to the attached sketches. | ELEC |  |  | 3rd | 44252 | 44263 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1666 | CheckTesting and Commissioning for Pannel (LP-IA-04) according to the attached sketches. | ELEC |  |  | 4th | 44252 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1667 | CheckTesting and Commissioning for Pannel (PP-IA-04) according to the attached sketches. | ELEC |  |  | 4th | 44252 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1668 | CheckTesting and Commissioning for Pannel (EPP-UPS-IA-04) according to the attached sketches. | ELEC |  |  | 4th | 44252 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1669 | CheckTesting and Commissioning for Pannel (PP-IB-04-2) according to the attached sketches. | ELEC |  |  | 4th | 44252 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1670 | CheckTesting and Commissioning for Pannel (ELP-CB-IA-02) according to the attached sketches. | ELEC |  |  | 2nd | 44257 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1671 | CheckTesting and Commissioning for Pannel (EDB-IA-02) according to the attached sketches. | ELEC |  |  | 2nd | 44257 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1672 | CheckTesting and Commissioning for Pannel (ELP-IA-02) according to the attached sketches. | ELEC |  |  | 2nd | 44257 | 44264 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1673 | CheckTesting and Commissioning for Pannel (LP-IA-02) according to the attached sketches. | ELEC |  |  | 2nd | 44257 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1674 | CheckTesting and Commissioning for Pannel (PP-IA-02) according to the attached sketches. | ELEC |  |  | 2nd | 44257 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1675 | CheckTesting and Commissioning for Pannel (EPP-UPS-IA-02) according to the attached sketches. | ELEC |  |  | 2nd | 44257 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1676 | CheckTesting and Commissioning for Pannel (ELP-CB-IB-02) according to the attached sketches. | ELEC |  |  | 2nd | 44257 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1677 | CheckTesting and Commissioning for Pannel (ELP-IB-02) according to the attached sketches. | ELEC |  |  | 2nd | 44257 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1678 | CheckTesting and Commissioning for Pannel (LP-IB-02) according to the attached sketches. | ELEC |  |  | 2nd | 44257 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1679 | CheckTesting and Commissioning for Pannel (PP-IB-02-1) according to the attached sketches. | ELEC |  |  | 2nd | 44257 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1680 | CheckTesting and Commissioning for Pannel (PP-IB-02-2) according to the attached sketches. | ELEC |  |  | 2nd | 44257 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1681 | CheckTesting and Commissioning for Pannel (EPP-UPS-IB-02) according to the attached sketches. | ELEC |  |  | 2nd | 44257 | 44264 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1682 | CheckTesting and Commissioning for Pannel (ELP-CB-IA-01) according to the attached sketches. | ELEC |  |  | 1st | 44262 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1683 | CheckTesting and Commissioning for Pannel (ELP-IA-01) according to the attached sketches. | ELEC |  |  | 1st | 44262 | 44268 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1684 | CheckTesting and Commissioning for Pannel (ELP-LS-IA-01) according to the attached sketches. | ELEC |  |  | 1st | 44262 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1685 | CheckTesting and Commissioning for Pannel (EPP-UPS-IA-01-1) according to the attached sketches. | ELEC |  |  | 1st | 44262 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1686 | CheckTesting and Commissioning for Pannel (EPP-UPS-IA-01-2) according to the attached sketches. | ELEC |  |  | 1st | 44262 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1687 | CheckTesting and Commissioning for Pannel (LP-IA-01) according to the attached sketches. | ELEC |  |  | 1st | 44262 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1688 | CheckTesting and Commissioning for Pannel (PP-IA-01-1) according to the attached sketches. | ELEC |  |  | 1st | 44262 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1689 | CheckTesting and Commissioning for Pannel (PP-IA-01-2) according to the attached sketches. | ELEC |  |  | 1st | 44262 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1690 | CheckTesting and Commissioning for Pannel (ELP-IB-01) according to the attached sketches. | ELEC |  |  | 1st | 44262 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1691 | CheckTesting and Commissioning for Pannel (ELP-LS-IB-01) according to the attached sketches. | ELEC |  |  | 1st | 44262 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1692 | CheckTesting and Commissioning for Pannel (EPP-UPS-IB-01-1) according to the attached sketches. | ELEC |  |  | 1st | 44263 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1693 | CheckTesting and Commissioning for Pannel (EPP-UPS-IB-01-2) according to the attached sketches. | ELEC |  |  | 1st | 44263 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1694 | CheckTesting and Commissioning for Pannel (LP-IB-01) according to the attached sketches. | ELEC |  |  | 1st | 44263 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1695 | CheckTesting and Commissioning for Pannel (PP-IB-01-1) according to the attached sketches. | ELEC |  |  | 1st | 44263 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1696 | CheckTesting and Commissioning for Pannel (PP-IB-01-2) according to the attached sketches. | ELEC |  |  | 1st | 44263 | 44268 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1697 | CheckTesting and Commissioning for Pannel (ELP-CB-IA-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1698 | CheckTesting and Commissioning for Pannel (EDB-CRACK-MTR-I1-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1699 | CheckTesting and Commissioning for Pannel (EDB-UPS-MTR-I1-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1700 | CheckTesting and Commissioning for Pannel (ELP-IA-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1701 | CheckTesting and Commissioning for Pannel (ELP-SERV-IA-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1702 | CheckTesting and Commissioning for Pannel (EPP-UPS-IA-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1703 | CheckTesting and Commissioning for Pannel (EPP-UPS-MTR-I1-1-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1704 | CheckTesting and Commissioning for Pannel (EPP-UPS-MTR-I1-2-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1705 | CheckTesting and Commissioning for Pannel (LP-IA-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1706 | CheckTesting and Commissioning for Pannel (PP-IA-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1707 | CheckTesting and Commissioning for Pannel (ELP-CB-IB-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1708 | CheckTesting and Commissioning for Pannel (ELP-IB-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1709 | CheckTesting and Commissioning for Pannel (EPP-UPS-IB-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1710 | CheckTesting and Commissioning for Pannel (LP-IB-GF) according to the attached sketches. | ELEC |  |  | GF | 44264 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1711 | CheckTesting and Commissioning for Pannel (PP-IB-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1712 | CheckTesting and Commissioning for Pannel (ELP-SERV-IB-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1713 | CheckTesting and Commissioning for Pannel (ELP-CB-IC-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1714 | CheckTesting and Commissioning for Pannel (ELP-IC-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1715 | CheckTesting and Commissioning for Pannel (EPP-UPS-CONC-IC-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1716 | CheckTesting and Commissioning for Pannel (LP-IC-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1717 | CheckTesting and Commissioning for Pannel (EPP-UPS-IC-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1718 | CheckTesting and Commissioning for Pannel (PP-IC-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1719 | CheckTesting and Commissioning for Pannel (ELP-SERV-IC-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1720 | CheckTesting and Commissioning for Pannel (ELP-CB-ID-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1721 | CheckTesting and Commissioning for Pannel (EDB-CRAC-MTR-I2-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1722 | CheckTesting and Commissioning for Pannel (EDB-UPS-MTR-I2-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1723 | CheckTesting and Commissioning for Pannel (ELP-ID-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1724 | CheckTesting and Commissioning for Pannel (EPP-UPS-ID-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1725 | CheckTesting and Commissioning for Pannel (EPP-UPS-MTR-I2-1-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1726 | CheckTesting and Commissioning for Pannel (EPP-UPS-MTR-I2-2-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1727 | CheckTesting and Commissioning for Pannel (LP-ID-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1728 | CheckTesting and Commissioning for Pannel (PP-ID-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1729 | CheckTesting and Commissioning for Pannel (ELP-SERV-ID-GF) according to the attached sketches. | ELEC |  |  | GF | 44265 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1730 | Check the third fix and lighting fixures installation for facad lighting fixtures at the second floor according to the attached sketches . - NO.OF FIXTURES TYPE (FA8)=176 - NO.OF FIXTURES TYPE (FA9)=26 . | ELEC |  |  | 2nd | 44268 | 44335 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1731 | CheckTesting and Commissioning for Pannel (ELP-IC-01) according to the attached sketches. | ELEC |  |  | 1st | 44269 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1732 | CheckTesting and Commissioning for Pannel (LP-IC-01) according to the attached sketches. | ELEC |  |  | 1st | 44269 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1733 | CheckTesting and Commissioning for Pannel (PP-IC-01-1) according to the attached sketches. | ELEC |  |  | 1st | 44269 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1734 | CheckTesting and Commissioning for Pannel (PP-IC-01-2) according to the attached sketches. | ELEC |  |  | 1st | 44269 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1735 | CheckTesting and Commissioning for Pannel (ELP-CB-ID-01) according to the attached sketches. | ELEC |  |  | 1st | 44269 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1736 | CheckTesting and Commissioning for Pannel (ELP-ID-01) according to the attached sketches. | ELEC |  |  | 1st | 44269 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1737 | CheckTesting and Commissioning for Pannel (LP-ID-01) according to the attached sketches. | ELEC |  |  | 1st | 44269 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1738 | CheckTesting and Commissioning for Pannel (ELP-IC-02) according to the attached sketches. | ELEC |  |  | 2nd | 44269 | 44279 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1739 | CheckTesting and Commissioning for Pannel (PP-IC-02-1) according to the attached sketches. | ELEC |  |  | 2nd | 44269 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1740 | CheckTesting and Commissioning for Pannel (PP-IC-02-2) according to the attached sketches. | ELEC |  |  | 2nd | 44269 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1741 | CheckTesting and Commissioning for Pannel (EPP-UPS-IC-02) according to the attached sketches. | ELEC |  |  | 2nd | 44269 | 44279 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1742 | CheckTesting and Commissioning for Easicheck Pannel (E.C03) at the first floor according to the attached sketches. | ELEC |  |  | 1st | 44270 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1743 | CheckTesting and Commissioning for Easicheck Pannel (E.C08) at the first floor according to the attached sketches. | ELEC |  |  | 1st | 44270 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1744 | CheckTesting and Commissioning for Pannel (ELP-CB-ID-02) according to the attached sketches. | ELEC |  |  | 2nd | 44273 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1745 | CheckTesting and Commissioning for Pannel (ELP-ID-02) according to the attached sketches. | ELEC |  |  | 2nd | 44273 | 44287 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1746 | CheckTesting and Commissioning for Pannel (LP-ID-02) according to the attached sketches. | ELEC |  |  | 2nd | 44273 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1747 | CheckTesting and Commissioning for Pannel (PP-ID-02) according to the attached sketches. | ELEC |  |  | 2nd | 44273 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1748 | CheckTesting and Commissioning for Pannel (ELP-CB-ID-03) according to the attached sketches. | ELEC |  |  | 3rd | 44273 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1749 | CheckTesting and Commissioning for Pannel (ELP-ID-03) according to the attached sketches. | ELEC |  |  | 3rd | 44273 | 44287 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1750 | CheckTesting and Commissioning for Pannel (PP-ID-03) according to the attached sketches. | ELEC |  |  | 3rd | 44273 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1751 | CheckTesting and Commissioning for Pannel (EPP-UPS-ID-03) according to the attached sketches. | ELEC |  |  | 3rd | 44273 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1752 | Check the third fix (lighting fixures installation) for facad lighting fixtures at the ground floor according to the attached sketches . - NO.OF FIXTURES TYPE (FA4)= 252 METER. | ELEC |  |  | 5th | 44277 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1753 | Check the third fix (lighting fixures installation) for facad lighting fixtures at the ground floor according to the attached sketches . - NO.OF FIXTURES TYPE (FA10)=62 - NO.OF FIXTURES TYPE (FA5)=132 - NO.OF FIXTURES TYPE (FA2)=0. | ELEC |  |  | GF | 44277 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1754 | CheckTesting and Commissioning for Pannel (ELP-CB-IC-03) according to the attached sketches. | ELEC |  |  | 3rd | 44277 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1755 | CheckTesting and Commissioning for Pannel (ELP-IC-03) according to the attached sketches. | ELEC |  |  | 3rd | 44277 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1756 | CheckTesting and Commissioning for Pannel (LP-IC-03) according to the attached sketches. | ELEC |  |  | 3rd | 44277 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1757 | CheckTesting and Commissioning for Pannel (PP-IC-03-1) according to the attached sketches. | ELEC |  |  | 3rd | 44277 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1758 | CheckTesting and Commissioning for Pannel (PP-IC-03-2) according to the attached sketches. | ELEC |  |  | 3rd | 44277 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1759 | CheckTesting and Commissioning for Pannel (ELP-IC-04) according to the attached sketches. | ELEC |  |  | 4th | 44278 | 44287 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1760 | CheckTesting and Commissioning for Pannel (PP-IC-04-1) according to the attached sketches. | ELEC |  |  | 4th | 44278 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1761 | CheckTesting and Commissioning for Pannel (PP-IC-04-2) according to the attached sketches. | ELEC |  |  | 4th | 44278 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1762 | CheckTesting and Commissioning for Pannel (EPP-UPS-IC-04) according to the attached sketches. | ELEC |  |  | 4th | 44278 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1763 | CheckTesting and Commissioning for Pannel (ELP-ID-04) according to the attached sketches. | ELEC |  |  | 4th | 44278 | 44287 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1764 | CheckTesting and Commissioning for Pannel (PP-ID-04) according to the attached sketches. | ELEC |  |  | 4th | 44278 | 44287 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1765 | CheckTesting and Commissioning for Easicheck Pannel (E.C04) at the fourth floor according to the attached sketches. | ELEC |  |  | 1st | 44283 | 44335 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1766 | CheckTesting and Commissioning for Easicheck Pannel (E.C09) at the second floor according to the attached sketches. | ELEC |  |  | 2nd | 44283 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1767 | CheckTesting and Commissioning for Pannel (ELP-ID-05) according to the attached sketches. | ELEC |  |  | 5th | 44285 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1768 | CheckTesting and Commissioning for Pannel (PP-ID-05) according to the attached sketches. | ELEC |  |  | 5th | 44285 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1769 | CheckTesting and Commissioning for Pannel (ELP-CB-IC-05) according to the attached sketches. | ELEC |  |  | 5th | 44285 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1770 | CheckTesting and Commissioning for Pannel (ELP-IC-05) according to the attached sketches. | ELEC |  |  | 5th | 44285 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1771 | CheckTesting and Commissioning for Pannel (LP-IC-05) according to the attached sketches. | ELEC |  |  | 5th | 44285 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1772 | CheckTesting and Commissioning for Pannel (PP-IC-05-1) according to the attached sketches. | ELEC |  |  | 5th | 44285 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1773 | CheckTesting and Commissioning for Pannel (PP-IC-05-2) according to the attached sketches. | ELEC |  |  | 5th | 44285 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1774 | CheckTesting and Commissioning for Pannel (EPP-UPS-IC-05) according to the attached sketches. | ELEC |  |  | 5th | 44285 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1775 | CheckTesting and Commissioning for Pannel (ELP-CB-IC-06) according to the attached sketches. | ELEC |  |  | 6th | 44290 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1776 | CheckTesting and Commissioning for Pannel (ELP-IC-06) according to the attached sketches. | ELEC |  |  | 6th | 44290 | 44324 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1777 | CheckTesting and Commissioning for Pannel (LP-IC-06) according to the attached sketches. | ELEC |  |  | 6th | 44290 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1778 | CheckTesting and Commissioning for Pannel (PP-IC-06-1) according to the attached sketches. | ELEC |  |  | 6th | 44290 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1779 | CheckTesting and Commissioning for Pannel (PP-IC-06-2) according to the attached sketches. | ELEC |  |  | 6th | 44290 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1780 | CheckTesting and Commissioning for Pannel (EPP-UPS-IC-06) according to the attached sketches. | ELEC |  |  | 6th | 44290 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1781 | CheckTesting and Commissioning for Pannel (ELP_LS_IB_07) according to the attached sketches. | ELEC |  |  | 7th | 44290 | 44306 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1782 | CheckTesting and Commissioning for Pannel (PP_IB_07) according to the attached sketches. | ELEC |  |  | 7th | 44290 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1783 | CheckTesting and Commissioning for Pannel (EPP_UPS_IB_07) according to the attached sketches. | ELEC |  |  | 7th | 44290 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1784 | CheckTesting and Commissioning for Pannel (ELP-CB-IC-07) according to the attached sketches. | ELEC |  |  | 7th | 44290 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1785 | CheckTesting and Commissioning for Pannel (PP-IC-07) according to the attached sketches. | ELEC |  |  | 7th | 44292 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1786 | CheckTesting and Commissioning for Pannel (EPP-UPS-IC-07) according to the attached sketches. | ELEC |  |  | 7th | 44292 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1787 | CheckTesting and Commissioning for Pannel (LP-IA-06) according to the attached sketches. | ELEC |  |  | 6th | 44292 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1788 | CheckTesting and Commissioning for Pannel (PP-IA-06) according to the attached sketches. | ELEC |  |  | 6th | 44292 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1789 | CheckTesting and Commissioning for Pannel (ELP-CB-IB-06) according to the attached sketches. | ELEC |  |  | 6th | 44292 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1790 | CheckTesting and Commissioning for Pannel (ELP-IB-06) according to the attached sketches. | ELEC |  |  | 6th | 44292 | 44306 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1791 | CheckTesting and Commissioning for Pannel (LP-IB-06) according to the attached sketches. | ELEC |  |  | 6th | 44292 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1792 | CheckTesting and Commissioning for Pannel (PP-IB-06-1) according to the attached sketches. | ELEC |  |  | 6th | 44292 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1793 | CheckTesting and Commissioning for Pannel (PP-IB-06-2) according to the attached sketches. | ELEC |  |  | 6th | 44292 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1794 | CheckTesting and Commissioning for Pannel (EPP-UPS-IB-06) according to the attached sketches. | ELEC |  |  | 6th | 44292 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1795 | CheckTesting and Commissioning for Easicheck Pannel (E.C10) at the FIFTH floor according to the attached sketches. | ELEC |  |  | 5th | 44292 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1796 | CheckTesting and Commissioning for Easicheck Pannel (E.C18) at the SEVENTH floor according to the attached sketches. | ELEC |  |  | 7th | 44292 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1797 | CheckTesting and Commissioning for Pannel (EPP-LIFT-IB-08) according to the attached sketches. | ELEC |  |  | 8th | 44294 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1798 | CheckTesting and Commissioning for Pannel (LP-IB-08) according to the attached sketches. | ELEC |  |  | 8th | 44294 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1799 | CheckTesting and Commissioning for Pannel (PP-IB-08-1) according to the attached sketches. | ELEC |  |  | 8th | 44294 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1800 | CheckTesting and Commissioning for Pannel (PP-IB-08-2) according to the attached sketches. | ELEC |  |  | 8th | 44294 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1801 | CheckTesting and Commissioning for Pannel (PP-IB-08-3) according to the attached sketches. | ELEC |  |  | 8th | 44294 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1802 | CheckTesting and Commissioning for Pannel (ELP-IB-09-02) according to the attached sketches. | ELEC |  |  | 9th | 44294 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1803 | CheckTesting and Commissioning for Pannel (PP-IB-09-01) according to the attached sketches. | ELEC |  |  | 9th | 44294 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1804 | CheckTesting and Commissioning for Pannel (PP-IB-09-02) according to the attached sketches. | ELEC |  |  | 9th | 44294 | 44306 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1805 | CheckThe Installation of GSM Race Way and outlets at the first floor according to the attached sketches. | ELEC |  |  | 1st | 44303 | 44324 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1806 | CheckThe Installation of GSM Race Way and outlets at the second floor according to the attached sketches. | ELEC |  |  | 2nd | 44303 | 44324 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1807 | CheckThe Installation of GSM Race Way and outlets at the third floor according to the attached sketches. | ELEC |  |  | 3rd | 44303 | 44324 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1808 | CheckTesting and Commissioning for Pannel (EPP-LIFT-IA-06) according to the attached sketches. | ELEC |  |  | 6th | 44312 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1809 | CheckTesting and Commissioning for Pannel (EPP-LIFT-ID-06) according to the attached sketches. | ELEC |  |  | 6th | 44312 | 44324 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1810 | CheckThe Installation of GSM Race Way and outlets at the fourth floor according to the attached sketches. | ELEC |  |  | 4th | 44312 | 44333 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1811 | CheckThe Installation of GSM Race Way and outlets at the fifth floor according to the attached sketches. | ELEC |  |  | 5th | 44312 | 44333 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1812 | CheckThe Installation of GSM Race Way and outlets at the sixth floor according to the attached sketches. | ELEC |  |  | 6th | 44312 | 44333 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1813 | Pleas Check The Fluke Test Of FIBER CABLES (N2 NETWORK) From Main Telecom Room (GF-163) TO FTR ROOMS According to the Attached Sketches. | ELEC |  |  | ML | 44313 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1814 | CheckTesting and Commissioning for Pannel (LP-IA-B2) according to the attached sketches. | ELEC |  |  | B2 | 44335 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1815 | CheckTesting and Commissioning for Pannel (ELP-IA-B2) according to the attached sketches. | ELEC |  |  | B2 | 44335 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1816 | CheckTesting and Commissioning for Pannel (ELP-CB-IA-B2) according to the attached sketches. | ELEC |  |  | B2 | 44335 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1817 | CheckTesting and Commissioning for Pannel (EPP-UPS-IA-B2) according to the attached sketches. | ELEC |  |  | B2 | 44335 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1818 | CheckTesting and Commissioning for Pannel (EPP-PUMP-I2-B2) according to the attached sketches. | ELEC |  |  | B2 | 44335 | 44359 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1819 | CheckTesting and Commissioning for Pannel (EPP-I1-B2) according to the attached sketches. | ELEC |  |  | B2 | 44335 | 44359 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1820 | CheckTesting and Commissioning for Pannel (ELP-CB-IB-B2) according to the attached sketches. | ELEC |  |  | B2 | 44336 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1821 | CheckTesting and Commissioning for Pannel (ELP-IB-B2) according to the attached sketches. | ELEC |  |  | B2 | 44336 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1822 | CheckTesting and Commissioning for Pannel (EPP-UPS-IB-B2) according to the attached sketches. | ELEC |  |  | B2 | 44336 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1823 | CheckTesting and Commissioning for Pannel (LP-IB-B2) according to the attached sketches. | ELEC |  |  | B2 | 44336 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1824 | CheckTesting and Commissioning for Pannel (ELP-CB-IC-B2) according to the attached sketches. | ELEC |  |  | B2 | 44336 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1825 | CheckTesting and Commissioning for Pannel (ELP-IC-B2) according to the attached sketches. | ELEC |  |  | B2 | 44336 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1826 | CheckTesting and Commissioning for Pannel (EPP-UPS-IC-B2) according to the attached sketches. | ELEC |  |  | B2 | 44336 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1827 | CheckTesting and Commissioning for Pannel (LP-IC-B2) according to the attached sketches. | ELEC |  |  | B2 | 44338 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1828 | CheckTesting and Commissioning for Pannel (LP-ID-B2) according to the attached sketches. | ELEC |  |  | B2 | 44338 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1829 | CheckTesting and Commissioning for Pannel (ELP-CB-ID-B2) according to the attached sketches. | ELEC |  |  | B2 | 44338 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1830 | CheckTesting and Commissioning for Pannel (ELP-ID-B2) according to the attached sketches. | ELEC |  |  | B2 | 44338 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1831 | CheckTesting and Commissioning for Pannel (EPP-UPS-ID-B2) according to the attached sketches. | ELEC |  |  | B2 | 44338 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1832 | CheckTesting and Commissioning for Pannel (EPP-I2-B2) according to the attached sketches. | ELEC |  |  | B2 | 44338 | 44359 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1833 | CheckTesting and Commissioning for Easicheck Pannel (E.C17) at the FOURTH floor according to the attached sketches. | ELEC |  |  | 4th | 44338 | 44359 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1834 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(01-001) at the first floor zone1 According to the Attached Sketches. | ELEC | Z1 | Z1 | 1st | 44343 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1835 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(01-010) at the first floor zone2 According to the Attached Sketches. | ELEC | Z2 | Z2 | 1st | 44343 | 44514 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1836 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(02-001) at the second floor zone1 According to the Attached Sketches. | ELEC | Z1 | Z1 | 2nd | 44343 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1837 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(02-010) at the second floor zone2 According to the Attached Sketches. | ELEC | Z2 | Z2 | 2nd | 44345 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1838 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(03-001) at the third floor zone1 According to the Attached Sketches. | ELEC | Z1 | Z1 | 3rd | 44345 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1839 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(03-010) at the third floor zone2 According to the Attached Sketches. | ELEC | Z2 | Z2 | 3rd | 44345 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1840 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (04-001) at zone 1 fourth floor according to the attached sketches. | ELEC | Z1 | Z1 | 4th | 44346 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1841 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (04-010) at zone 2 fourth floor according to the attached sketches. | ELEC | Z2 | Z2 | 4th | 44346 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1842 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (04-001) at zone 1 fifth floor according to the attached sketches. | ELEC | Z1 | Z1 | 5th | 44346 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1843 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (05-010) at zone 2 fifth floor according to the attached sketches. | ELEC | Z2 | Z2 | 5th | 44346 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1844 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (06-010) at zone 2 sixth floor according to the attached sketches. | ELEC | Z2 | Z2 | 6th | 44346 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1845 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (07-010) at zone 2 sevinth floor according to the attached sketches. | ELEC | Z2 | Z2 | 7th | 44346 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1846 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(GF-060) at the Ground floor zone1 According to the Attached Sketches. | ELEC | Z1 | Z1 | GF | 44348 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1847 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(GF-010) at the Ground floor zone2 According to the Attached Sketches. | ELEC | Z2 | Z2 | GF | 44348 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1848 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(B1-040) at the First Basement floor zone1 According to the Attached Sketches. | ELEC | Z1 | Z1 | B1 | 44348 | 44356 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1849 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(B1-054) at the First Basement floor zone2 According to the Attached Sketches. | ELEC | Z2 | Z2 | B1 | 44359 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1850 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(B2-035) at the Second Basement floor zone1 According to the Attached Sketches. | ELEC | Z1 | Z1 | B2 | 44359 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1851 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(B2-049) at the Second Basement floor zone2 According to the Attached Sketches. | ELEC | Z2 | Z2 | B2 | 44359 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1852 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(B2-057) at the Second Basement floor zone3b According to the Attached Sketches. | ELEC | Z3B | Z3B | B2 | 44359 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1853 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(B2-063) at the Second Basement floor zone4 According to the Attached Sketches. | ELEC | Z4 | Z4 | B2 | 44359 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1854 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(B2-034) at the Second Basement floor zone5 According to the Attached Sketches. | ELEC | Z5 | Z5 | B2 | 44359 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1855 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(B1-062) at the first Basement floor zone3b According to the Attached Sketches. | ELEC | Z3B | Z3B | B1 | 44359 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1856 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(B1-068) at the first Basement floor zone4 According to the Attached Sketches. | ELEC | Z4 | Z4 | B1 | 44359 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1857 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(B1-039) at the first Basement floor zone5 According to the Attached Sketches. | ELEC | Z5 | Z5 | B1 | 44359 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1858 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(GF-002) at the ground floor zone3b According to the Attached Sketches. | ELEC | Z3B | Z3B | GF | 44359 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1859 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(GF-029) at the ground floor zone4 According to the Attached Sketches. | ELEC | Z4 | Z4 | GF | 44359 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1860 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(GF-050) at the ground floor zone5 According to the Attached Sketches. | ELEC | Z5 | Z5 | GF | 44360 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1861 | CheckTesting and Commissioning for Easicheck Pannel (E.C15) at the FIRST floor according to the attached sketches. | ELEC |  |  | 1st | 44361 | 44467 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1862 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(01-026) at the first floor zone 4 According to the Attached Sketches | ELEC | Z4 | Z4 | 1st | 44361 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1863 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(01-041) at the first floor zone 5 According to the Attached Sketches. | ELEC | Z5 | Z5 | 1st | 44361 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1864 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(02-026) at the second floor zone4 According to the Attached Sketches. | ELEC | Z4 | Z4 | 2nd | 44362 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1865 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(02-041) at the second floor zone5 According to the Attached Sketches. | ELEC | Z5 | Z5 | 2nd | 44362 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1866 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(03-026) at the third floor zone4 According to the Attached Sketches | ELEC | Z4 | Z4 | 3rd | 44362 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1867 | Pleas Check The FIBER CABLES Fluke Test (N1-N2-N3) Networks From Main Telecom RoomsTo FTR Room(03-041) at the third floor zone5 According to the Attached Sketches. | ELEC | Z5 | Z5 | 3rd | 44362 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1868 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (04-026) at zone 4 fourth floor according to the attached sketches. | ELEC | Z4 | Z4 | 4th | 44364 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1869 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (04-041) at zone 5 fourth floor according to the attached sketches. | ELEC | Z5 | Z5 | 4th | 44364 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1870 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (05-026) at zone 4 fifth floor according to the attached sketches. | ELEC | Z4 | Z4 | 5th | 44364 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1871 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (05-041) at zone 5 fifth floor according to the attached sketches. | ELEC | Z5 | Z5 | 5th | 44364 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1872 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (06-026) at zone 4 sixth floor according to the attached sketches. | ELEC | Z4 | Z4 | 6th | 44364 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1873 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (07-026) at zone 4 _7th floor according to the attached sketches. | ELEC | Z4 | Z4 | 7th | 44364 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1874 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (08-012) at zone 3 _8th floor according to the attached sketches. | ELEC | Z3 | Z3 | 8th | 44368 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1875 | Pleas Check The FIBER CABLES FlukeTest (N1-N2-N3) Networks From Main Telecom RoomsTo FTR (09-006) at zone 3 _9th floor according to the attached sketches. | ELEC | Z3 | Z3 | 9th | 44368 | 44376 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1876 | Check the third fix (lighting fixures installation) for facad lighting fixtures at the seventh floor according to the attached sketches . - NO.OF FIXTURES TYPE (FA4)= 250 METER. | ELEC |  |  | 7th | 44374 | 44427 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1877 | Check Handing over of FTR Room (01-001) to the systems administration at the first floor zone1 According to the Attached Sketches. | ELEC | Z1 | Z1 | 1st | 44381 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1878 | Check Hand over of FTR Room (01-010) to the systems administration at the first floor zone2 According to the Attached Sketches. | ELEC | Z2 | Z2 | 1st | 44381 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1879 | Check Hand over of FTR Room (02-001) to the systems administration at the second floor zone1 According to the Attached Sketches. | ELEC | Z1 | Z1 | 2nd | 44381 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1880 | Check Hand over of FTR Room (02-010) to the systems administration at the second floor zone2 According to the Attached Sketches. | ELEC | Z2 | Z2 | 2nd | 44381 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1881 | Check Hand over of FTR Room (03-001) to the systems administration at the third floor zone1 According to the Attached Sketches. | ELEC | Z1 | Z1 | 3rd | 44381 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1882 | Check Hand over of FTR Room (03-010) to the systems administration at the third floor zone2 According to the Attached Sketches. | ELEC | Z2 | Z2 | 3rd | 44381 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1883 | Check Hand over of FTR (04-001) to the systems administration at zone 1 fourth floor according to the attached sketches. | ELEC | Z1 | Z1 | 4th | 44381 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1884 | Check Hand over of FTR (04-010) to the systems administration at zone 2 fourth floor according to the attached sketches. | ELEC | Z2 | Z2 | 4th | 44381 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1885 | Check Hand over of FTR (04-001) to the systems administration at zone 1 fifth floor according to the attached sketches. | ELEC | Z1 | Z1 | 5th | 44381 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1886 | Check Hand over of FTR (05-010) to the systems administration at zone 2 fifth floor according to the attached sketches. | ELEC | Z2 | Z2 | 5th | 44381 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1887 | CheckTesting and Commissioning for Easicheck Pannel (E.C16) at the SECOND floor according to the attached sketches. | ELEC |  |  | 2nd | 44384 | 44467 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1888 | Check Hand over of FTR (01-026) to the systems administration at zone 4 first floor according to the attached sketches. | ELEC |  |  | 1st | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1889 | Check Hand over of FTR (01-041) to the systems administration at zone 5 first floor according to the attached sketches. | ELEC |  |  | 1st | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1890 | Check Hand over of FTR (02-026) to the systems administration at zone 4 second floor according to the attached sketches. | ELEC |  |  | 2nd | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1891 | Check Hand over of FTR (02-041) to the systems administration at zone 5 second floor according to the attached sketches. | ELEC |  |  | 2nd | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1892 | Check Hand over of FTR (03-026) to the systems administration at zone 4 third floor according to the attached sketches. | ELEC |  |  | 3rd | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1893 | Check Hand over of FTR (03-041) to the systems administration at zone 5 third floor according to the attached sketches. | ELEC |  |  | 3rd | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1894 | Check Hand over of FTR (04-026) to the systems administration at zone 4 fourth floor according to the attached sketches. | ELEC |  |  | 4th | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1895 | Check Hand over of FTR (04-041) to the systems administration at zone 5 fourth floor according to the attached sketches. | ELEC |  |  | 4th | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1896 | Check Hand over of FTR (05-26) to the systems administration at zone 4 fifth floor according to the attached sketches. | ELEC |  |  | 5th | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1897 | Check Hand over of FTR (05-041) to the systems administration at zone 5 fifth floor according to the attached sketches. | ELEC |  |  | 5th | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1898 | Check Hand over of FTR (06-010) to the systems administration at zone 2 Sixth floor according to the attached sketches. | ELEC |  |  | 6th | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1899 | Check Hand over of FTR (06-026) to the systems administration at zone 4 Sixth floor according to the attached sketches. | ELEC |  |  | 6th | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1900 | Check Hand over of FTR (07-006) to the systems administration at zone 2 Seventh floor according to the attached sketches. | ELEC |  |  | 7th | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1901 | Check Hand over of FTR (07-020) to the systems administration at zone 4 Seventh floor according to the attached sketches. | ELEC |  |  | 7th | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1902 | Check Hand over of FTR (08-012) to the systems administration at zone 3 Eighth floor according to the attached sketches. | ELEC |  |  | 8th | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1903 | Check Hand over of FTR (B2-035) to the systems administration at zone 1 Bassesment 2 floor according to the attached sketches. | ELEC |  |  | B2 | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1904 | Check Hand over of FTR (B2-035) to the systems administration at zone 2 Bassesment 2 floor according to the attached sketches. | ELEC |  |  | B2 | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1905 | Check Hand over of FTR (B2-057) to the systems administration at zone 3 Bassesment 2 floor according to the attached sketches. | ELEC |  |  | B2 | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1906 | Check Hand over of FTR (B2-063) to the systems administration at zone 4 Bassesment 2 floor according to the attached sketches. | ELEC |  |  | B2 | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1907 | Check Hand over of FTR (B2-034) to the systems administration at zone 5 Bassesment 2 floor according to the attached sketches. | ELEC |  |  | B2 | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1908 | Check Hand over of FTR (GR-060) to the systems administration at zone 1 Ground floor according to the attached sketches. | ELEC |  |  | GF | 44410 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1909 | Check Hand over of FTR (GR-010) to the systems administration at zone 2 Ground floor according to the attached sketches. | ELEC |  |  | GF | 44422 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1910 | Check Hand over of FTR (GR-002) to the systems administration at zone 3 Ground floor according to the attached sketches. | ELEC |  |  | GF | 44422 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1911 | Check Hand over of FTR (GR-029) to the systems administration at zone 4 Ground floor according to the attached sketches. | ELEC |  |  | GF | 44422 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1912 | Check Hand over of FTR (GR-050) to the systems administration at zone 5 Ground floor according to the attached sketches. | ELEC |  |  | GF | 44422 |  | CANCELLED
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1913 | CheckThe Installation of GSM Race Way and outlets at the Ground floor according to the attached sketches. (3/4' Conduits = 180m) - (1' EMT Conduits = 430m) - ( No. of Points = 45). | ELEC |  |  | GF | 44436 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1914 | CheckThe Installation of GSM Race Way and outlets at the Seventh floor according to the attached sketches. (3/4' Conduits = 270m) - (1' EMT Conduits = 410m) - ( No. of Points = 34). | ELEC |  |  | 7th | 44436 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1915 | CheckThe Installation of GSM Race Way and outlets at the Eighth floor according to the attached sketches. (3/4' Conduits = 180m) - (1' EMT Conduits = 110m) - ( No. of Points = 12). | ELEC |  |  | 8th | 44436 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1916 | CheckThe Installation of GSM Race Way and outlets at the Ninth floor according to the attached sketches. (3/4' Conduits = 105m) - (1' EMT Conduits = 40m) - ( No. of Points = 17). | ELEC |  |  | 9th | 44436 | 44459 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1917 | CheckTesting & Commisioning of panels for core (A) as per attached Q.S sheet & attached sketches. | ELEC |  |  | B1 | 44447 | 44494 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1918 | CheckTesting & Commisioning of panels for core (B) as per attached Q.S sheet & attached sketches. | ELEC |  |  | B1 | 44447 | 44475 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1919 | CheckTesting & Commisioning of panels for core (C) as per attached Q.S sheet & attached sketches. | ELEC |  |  | B1 | 44447 | 44475 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1920 | CheckTesting & Commisioning of panels for core (D) as per attached Q.S sheet & attached sketches. | ELEC |  |  | B1 | 44447 | 44515 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1921 | CheckTesting & Commisioning of panels at MDB rooms as per attached Q.S sheet & attached sketches. | ELEC |  |  | B1 | 44447 | 44475 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1922 | CheckTesting & Commisioning of LCP panels at ELEC. Rooms (CORE A) as per attached Q.S sheet & attached sketches. | ELEC |  |  | Ml | 44454 | 44516 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1923 | CheckTesting & Commisioning of LCP panels at ELEC. Rooms (CORE B) as per attached Q.S sheet & attached sketches. | ELEC |  |  | Ml | 44454 | 44494 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1924 | CheckTesting & Commisioning of LCP panels at ELEC. Rooms (CORE C) as per attached Q.S sheet & attached sketches. | ELEC |  |  | Ml | 44454 | 44494 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1925 | CheckTesting & Commisioning of LCP panels at ELEC. Rooms (CORE D) as per attached Q.S sheet & attached sketches. | ELEC |  |  | Ml | 44454 | 44494 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1926 | Check FTR rooms at Z1 & Z2 as per attached check list and fluke test report for UTP cables | ELEC | Z1,2 | Z1,2 | GF | 44455 | 44475 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1927 | Check FTR rooms at Z3 & Z4 & Z5 as per attached check list and fluke test report for UTP cables | ELEC | Z3,4,5 | Z3,4,5 | GF | 44455 | 44475 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1928 | Check FTR rooms at Z1 & Z2 as per attached check list and fluke test report for UTP cables | ELEC | Z1,2 | Z1,2 | 1st | 44455 | 44488 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1929 | Check FTR rooms at Z4 & Z5 as per attached check list and fluke test report for UTP cables | ELEC | Z4,5 | Z4,5 | 1st | 44455 | 44488 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1930 | Check FTR rooms at Z1 & Z2 as per attached check list and fluke test report for UTP cables | ELEC | Z1,2 | Z1,2 | 2nd | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1931 | Check FTR rooms at Z4 & Z5 as per attached check list and fluke test report for UTP cables | ELEC | Z4,5 | Z4,5 | 2nd | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1932 | Check FTR rooms at Z1 & Z2 as per attached check list and fluke test report for UTP cables | ELEC | Z1,2 | Z1,2 | 3rd | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1933 | Check FTR rooms at Z4 & Z5 as per attached check list and fluke test report for UTP cables | ELEC | Z4,5 | Z4,5 | 3rd | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1934 | Check FTR rooms at Z1 & Z2 as per attached check list and fluke test report for UTP cables | ELEC | Z1,2 | Z1,2 | 4th | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1935 | Check FTR rooms at Z4 & Z5 as per attached check list and fluke test report for UTP cables | ELEC | Z4,5 | Z4,5 | 4th | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1936 | Check FTR rooms at Z4 & Z5 as per attached check list and fluke test report for UTP cables | ELEC | Z4,5 | Z4,5 | 5th | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1937 | Check FTR rooms at Z4 & Z5 as per attached check list and fluke test report for UTP cables | ELEC | Z4,5 | Z4,5 | 5th | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1938 | Check FTR rooms at Z2 & Z4 as per attached check list and fluke test report for UTP cables | ELEC | Z2,4 | Z2,4 | 6th | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1939 | Check FTR rooms at Z2 & Z4 as per attached check list and fluke test report for UTP cables | ELEC | Z2,4 | Z2,4 | 7th | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1940 | Check FTR rooms at Z3 as per attached check list and fluke test report for UTP cables | ELEC | Z3 | Z3 | 8th | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1941 | Check FTR rooms at Z3 as per attached check list and fluke test report for UTP cables | ELEC | Z3 | Z3 | 9th | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1942 | Check FTR rooms at Z1 & Z2 as per attached check list and fluke test report for UTP cables | ELEC | Z1,2 | Z1,2 | B2 | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1943 | Check FTR rooms at Z3 & Z4 & Z5 as per attached check list and fluke test report for UTP cables | ELEC | Z3,4,5 | Z3,4,5 | B2 | 44455 | 44483 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1944 | Check FTR rooms at Z1 & Z2 as per attached check list and fluke test report for UTP cables | ELEC | Z1,2 | Z1,2 | B1 | 44455 | 44475 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1945 | Check FTR rooms at Z3 & Z4 & Z5 as per attached check list and fluke test report for UTP cables | ELEC | Z3,4,5 | Z3,4,5 | B1 | 44455 | 44475 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1946 | Check installation and termination for Access control panels at FTR rooms at Z1 & Z2 as per attached | ELEC | Z1,2 | Z1,2 | 1st | 44455 | 44475 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1947 | Check installation and termination for Access control panels at FTR rooms at Z5 as per attached | ELEC | Z5 | Z5 | 1st | 44455 | 44494 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1948 | Check installation and termination for Access control panels at FTR rooms at Z1 & Z2 as per attached | ELEC | Z1,2 | Z1,2 | 2nd | 44455 | 44475 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1949 | Check installation and termination for Access control panels at FTR rooms at Z5 as per attached | ELEC | Z5 | Z5 | 2nd | 44455 | 44494 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1950 | Check installation and termination for Access control panels at FTR rooms at Z1 & Z2 as per attached | ELEC | Z1,2 | Z1,2 | 3rd | 44455 | 44475 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1951 | Check installation and termination for Access control panels at FTR rooms at Z5 as per attached | ELEC | Z5 | Z5 | 3rd | 44455 | 44494 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1952 | Check installation and termination for Access control panels at FTR rooms at Z1 & Z2 as per attached | ELEC | Z1,2 | Z1,2 | 4th | 44455 | 44475 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1953 | Check installation and termination for Access control panels at FTR rooms at Z5 as per attached | ELEC | Z5 | Z5 | 4th | 44455 | 44494 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1954 | Check installation and termination for Access control panels at FTR rooms at Z1 & Z2 as per attached | ELEC | Z1,2 | Z1,2 | 5th | 44455 | 44475 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1955 | Check installation and termination for Access control panels at FTR rooms at Z5 as per attached | ELEC | Z5 | Z5 | 5th | 44455 | 44494 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1956 | Check installation and termination for Access control panels at FTR rooms at Z2 as per attached | ELEC | Z2 | Z2 | 6th | 44455 | 44515 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1957 | CheckTesting and Commissioning for two ups 40 KVA (ups room B1-009*) according to the attached . | ELEC |  |  | B1 | 44472 | 44488 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1958 | CheckTesting and Commissioning for two ups 300 KVA (ups room B1-079) according to the attached . | ELEC |  |  | B1 | 44472 | 44488 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1959 | CheckTesting and Commissioning for two ups 300 KVA (ups room B1-072) according to the attached . | ELEC |  |  | B1 | 44472 | 44488 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1960 | CheckTesting and Commissioning for two ups 160 KVA (ups room B1-009) according to the attached . | ELEC |  |  | B1 | 44472 | 44488 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1961 | Check MTR rooms at Z (1) Network (2) as per attached check list according to the attached . | ELEC |  |  | GF | 44486 | 44516 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1962 | Check MTR rooms at Z (5) Network (1,3) as per attached check list according to the attached . | ELEC |  |  | GF | 44486 | 44514 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1963 | CheckTesting and Commissioning for Easicheck Pannel (E.C21) at the FIRST floor according to the attached sketches. | ELEC |  |  | 1st | 44496 | 44514 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1964 | CheckTesting and Commissioning for Easicheck Pannel (E.C22) at the FOURTH floor according to the attached sketches. | ELEC |  |  | 4th | 44496 | 44514 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1965 | Pls Check The Visual Inspection and megger Test For Low Voltage Aluminum Plug In Bus way at core (I1) Run10-LSBA1(AL) (2500A-100 KA)-3PH+FN+FE-(BD/I1-G.P.B-I1/Generator Box) according to the attached sketch. | ELEC |  |  | B1 | 44496 | 44516 | B
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1966 | Installation Of Shutter Door AS (Clouded area of the attachment) Zone 2, Zone 4 - Bassement 1 According to attached Sketch . | ELEC | Z2,4 | Z2,4 | B1 | 44502 | 44516 | C
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1967 | Check the third fix and lighting fixures installation for land scape lighting type(LS1) according to the attached sketches . - NO.OFFIXTURE TYPE (LS1)=23 . | ELEC |  |  | EX | 44524 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1968 | Check the third fix and lighting fixures installation for land scape lighting type(LS3) according to the attached sketches . - NO.OF FIXTURE TYPE (LS3)=63 . | ELEC |  |  | EX | 44524 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1969 | Check the third fix and lighting fixures installation for land scape lighting type(LS4) according to the attached sketches . - NO.OF FIXTURE TYPE (LS4)=14 . | ELEC |  |  | EX | 44524 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1970 | Check the third fix and lighting fixures installation for land scape lighting type(LS5) according to the attached sketches . - NO.OF FIXTURE TYPE (LS5)=36 . | ELEC |  |  | EX | 44524 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1971 | Check the third fix and lighting fixures installation for land scape lighting type(LS6) according to the attached sketches . - NO.OF FIXTURE TYPE (LS6)=20 . | ELEC |  |  | EX | 44524 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1972 | Check installation of lightning protection system at roof floor as per attached sketch. | ELEC |  |  | RF | 44524 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1973 | Check installation and termination for Access control panels at FTR rooms at Z4 as per attached Sketch . | ELEC | Z4 | Z4 | Ml | 44524 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1974 | Check Installation of First fix for Lighting System As per attached sketch . | ELEC |  |  | EX | 44542 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1975 | CheckTesting and Commissioning for Easicheck Pannel (EC.1) at the FIRST basement and Second Basement for Area Z(1) according to the attached sketches. | ELEC | Z1 | Z1 | B1&B2 | 44544 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1976 | CheckTesting and Commissioning for Easicheck Pannel (EC.19) at the FIRST basement and Second Basement for Area Z(5) according to the attached sketches. | ELEC | Z5 | Z5 | B1&B2 | 44544 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1977 | CheckTesting and Commissioning for Easicheck Pannel (EC.6) at the Ground Floor for Area Z(2) according to the attached sketches. | ELEC | Z2 | Z2 | GF | 44544 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1978 | CheckTesting and Commissioning for Easicheck Pannel (EC.7) at the Ground Floor for Area Z(2) according to the attached sketches. | ELEC | Z2 | Z2 | GF | 44544 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1979 | CheckTesting and Commissioning for Easicheck Pannel (EC.13) at the Ground Floor for Area Z(4) according to the attached sketches. | ELEC | Z4 | Z4 | GF | 44544 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1980 | CheckTesting and Commissioning for Easicheck Pannel (EC.14) at the Ground Floor for Area Z(4) according to the attached sketches. | ELEC | Z4 | Z4 | GF | 44544 |  | W
MINISTRY OF FOREIGN AFFAIRS PLOT 9A-10A | IR-ELE-1981 | Megger Cable test for PV Panels from MDB-I1 & MDB-I2 according to the attached sketches Cable Size (3x185+95)+1x95mm2 CU/XLPE/SWA/PVC | ELEC |  |  | B1 | 44579 |  | W
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0001 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41730 | 41731 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0002 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41730 | 41731 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0003 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41731 | 41732 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0004 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41732 | 41734 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0005 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41734 | 41735 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0006 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41735 | 41736 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0007 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41736 | 41737 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0008 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41742 | 41757 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0009 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41744 | 41745 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0010 | Surface Preparation for pile head at piles (H) no. (429-440-448-452-461-470-471- 472-473-483) | Surface Preparation | Piles |  |  | 41749 | 41752 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0011 | Casting Grout of Pile Head at piles H no. (429-440-448-452-461-470-471-472-473-483) | Grout | Piles |  |  | 41749 | 41752 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0012 | Casting grout of pile head at piles H no. (430-433-435-439-484) | Grout | Piles |  |  | 41751 | 41752 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0013 | Surface preparation of piles head at piles H no. (430-433-435-439-484) | Surface Preparation | Piles |  |  | 41751 | 41752 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0014 | Surface preparation and treatment for pile head at piles (493-498-503-508-511-512) | Surface Preparation | Piles |  |  | 41752 | 41755 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0015 | Casting grout for pile head at piles (493-498-503-508-511-512) | Grout | Piles |  |  | 41752 | 41755 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0016 | Casting grout for pile head at piles (528-524-525-485) | Grout | Piles |  |  | 41752 | 41755 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0017 | Surface preparation and treatment for pile head at piles (528-524-525-485) | Surface Preparation | Piles |  |  | 41752 | 41755 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0018 | Casting grout for pile H no. (428-436-443-454-502-523-527-537-536-490) | Grout | Piles |  |  | 41755 | 41756 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0019 | Casting grout for pile head at piles H no. (428-436-443-454-502-523-527-537-536-490) | Grout | Piles |  |  | 41755 | 41756 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0020 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41755 | 41756 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0021 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41755 | 41756 | N
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0022 | Surface preparation and treatment for pile head at piles H no( 437-441-442-460-478-494-544-545-557-564-547) | Surface Preparation | Piles |  |  | 41757 | 41758 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0023 | Casting grout by material sika grout 200 for pile head at piles H no (437-441-442-460-478-494-544-545-557-564-547) | Grout | Piles |  |  | 41757 | 41758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0024 | Casting grout by material sika grout 200 for pile head at piles H no (488-432-444-480-481-496-500-504-518-532) | Grout | Piles |  |  | 41757 | 41758 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0025 | Surface preparation and treatment for pile head at piles H no( 488-432-444-480-481-496-500-504-518-532) | Surface Preparation | Piles |  |  | 41757 | 41758 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0026 | Casting grout by material sika grout 200 for pile head at piles H no (546-561-563-548) | Grout | Piles |  |  | 41757 | 41758 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0027 | Surface preparation and treatment for pile head at piles H no( 546-561-563-548) | Surface Preparation | Piles |  |  | 41757 | 41758 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0028 | Casting grout by material sika grout 200 for pile head at piles H no. (574-573-577-488-438) | Grout | Piles |  |  | 41758 | 41759 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0029 | Surface prepartion and treatment for pile head at piles H no. (547-573-577-488-438) | Surface Preparation | Piles |  |  | 41758 | 41759 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0030 | Description of works to be inspected (attached highlighted copy of the relevant drawing | Form Work | P.C |  |  | 41759 | 41762 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0031 | Casting grout by material sika grout 200 for pile head at piles H no. (506-570-584-586-587-588-590-591-593) | Grout | Piles |  |  | 41759 | 41762 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0032 | Sutface prepartion and treatment for pile head at piles H no. (506-570-584-586-587-590-591-593) | Surface Preparation | Piles |  |  | 41759 | 41762 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0033 | Surface Preparation and treatment for pile head at piles H no. (434-479-482-486-487-492-499-507-510-513-514-516-520-521-522-529-530) | Surface Preparation | Piles |  |  | 41762 | 41763 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0034 | Casting grout by material sika grout 200 for pile head at piles H no.(534-479-482-486-487-492-499-507-510-513-514-516-520-521-522-529-530) | Grout | Piles |  |  | 41762 | 41763 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0035 | Casting grout by material sika grout 200 for pile head at piles H no. (509-519-526-538-539-540-541-542) | Grout | Piles |  |  | 41763 | 41764 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0036 | Surface preparation and treatment for pile head at piles H no. (509-519-526-538-539-540-541-542) | Surface Preparation | Piles |  |  | 41763 | 41764 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0037 | Surface Preparaton and treatment for pile head at piles H no. (559-558-556-555-551-550-549-543-533-534-535-491-431-449-447-446-445-451-450-459-497-495-489-501) | Surface Preparation | Piles |  |  | 41763 | 41764 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0038 | Casting grout by material sika grout 200 for pile head at piles H no. (559-558-556-555-551-550-549-543-533-534-535-491-431-449-447-446-445-451-450-459-497-495-489-501) | Grout | Piles |  |  | 41763 | 41764 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0039 | Surface preparation and treatment for pile head at piles H no. (8-9-10-14-17-15-16-21-23-52-53-54-55-50-402-383-384-393-399) Plus E19 | Surface Preparation | Piles |  |  | 41764 | 41765 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0040 | Casting grout by material sika grout 200 for pile head at piles E no. (8-9-10-14-17-15-16-21-23-52-53-54-55-50-402-383-384-393-399) Plus E19 | Grout | Piles |  |  | 41764 | 41765 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0041 | Surface preparation and treatment for pile head at piles E no. (51-19-1-3-4-30-38-69-76-78-79-81-82-86-87-89-85-90-40) | Surface Preparation | Piles |  |  | 41767 | 41769 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0042 | Casting grout by material sika grout 200 for pile head at piles E no. (51-19-1-3-4-30-38-69-76-78-79-81-82-86-87-89-85-90-40) | Grout | Piles |  |  | 41767 | 41769 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0043 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41769 | 41770 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0044 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41769 | 41770 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0045 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41769 | 41771 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0046 | Casting grout by material sika grout 200 for pile head at piles E no. (11-12-13-56-55-400-394-395-49-57-58-59-60-68-406-405-404-403) H (569-598-599-601-604-606) | Grout | Piles |  |  | 41769 | 41770 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0047 | Surface preparation and treatment for pile head at piles E no. (11-12-13-56-55-400-394-395-49-57-58-59-60-68-406-405-404-403) H (569-598-599-601-604-606) | Surface Preparation | Piles |  |  | 41769 | 41770 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0048 | Surface preparation and treatment for pile head at piles E no. (85-90-89-40-37-32-02) H (600-603-616-630-631-560-550-553-562-565-566-572-571-575-576-579-580-585-617) | Surface Preparation | Piles |  |  | 41769 | 41770 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0049 | Casting grout by material sika grout 200 for pile head at piles E (85-90-89-40-37-32-02) H (600-603-616-630-631-560-550-553-562-565-566-572-571-575-576-579-580-585-617) | Grout | Piles |  |  | 41769 | 41770 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0050 | Surface preparation and treatment for pile head at piles E no. (47-61-61) & H no. (644-613-515-517-583-594-602) | Surface Preparation | Piles |  |  | 41770 | 41771 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0051 | Casting grout by material sika grout 200 for pile head at piles E no. (47-61-61) & H no. (644-613-515-517-583-594-602) | Grout | Piles |  |  | 41770 | 41771 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0052 | Casting grout by material Sika grout 200 for piles No. E (29-39-7-24-46-64-65-66-63-20-45-391-392) | Grout | Piles |  |  | 41771 | 41772 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0053 | Surface preparation and treatment for pile head at piles E no. ( 29-39-7-24-46-64-65-66-63-20-45-391-392) | Surface Preparation | Piles |  |  | 41771 | 41772 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0054 | Casting grout by material Sika grout 200 for piles No. H (618-629-632-642-641-633) | Grout | Piles |  |  | 41771 | 41772 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0055 | Surface preparation and treatment for pile head at piles H no. (618-629-632-642-641-633) | Surface Preparation | Piles |  |  | 41771 | 41772 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0056 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41771 | 41772 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0057 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41771 | 41772 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0058 | Diaphragm Wall Surface Preparation for Water Proofing application (as Shown in Sketch) | Insulation | Diaphragm Wall |  |  | 41772 | 41773 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0059 | Surface Preparation and treatment for pile head at piles E no. (386-382-378-372-371-367-366-365-363-362-361-360-359-356-357-354) | Surface Preparation | Piles |  |  | 41772 | 41773 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0060 | Casting grout by material sika grout 200 for pile head at piles E no. (386-382-378-372-371-367-366-365-363-362-361-360-359-356-357-354) | Grout | Piles |  |  | 41772 | 41773 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0061 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41772 | 41773 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0062 | Surface Preparation and treatment for pile head at piles E no. (345-347-348-339-338-335-336-340-334-333-341-330-332-343-331-327-325-324 & 326) | Surface Preparation | Piles |  |  | 41773 | 41774 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0063 | Casting grout by material sika grout 200 for pile head at piles E no. (345-347-348-339-338-335-336-340-334-333-341-330-332-343-331-327-325-324 & 326) | Grout | Piles |  |  | 41773 | 41774 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0064 | Surface Preparation and treatment for pile head at piles E no. (358-370B-396-397-387-388-389-390-379) H (627-621-597-607-611 & 614) | Surface Preparation | Piles |  |  | 41773 | 41774 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0065 | Casting grout by material sika grout 200 for pile head at piles E no. (358-370B-396-397-387-388-389-390-379) H (627-621-597-607-611 & 614) | Grout | Piles |  |  | 41773 | 41774 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0066 | Casting grout by material sika grout 200 for pile head at piles E no. (334-333-311-312-310-309) | Grout | Piles |  |  | 41773 | 41774 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0067 | Surface Preparation and treatment for pile head at piles E no. (334-333-311-312-310-309) | Surface Preparation | Piles |  |  | 41773 | 41774 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0068 | Casting grout by material sika grout 200 for Pile Head At Piles E NO. (401.407.323.322.321.319.318.317.316.315.314.313.312.&H .262.264.263.285.286.287.288.358.357&335) | Grout | Piles |  |  | 41776 | 41776 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0069 | Surface Preparation and treatment for pile head at piles E no. (401.407.323.322.321.319.318.317.316.315.314.313.312.&H .262.264.263.285.286.287.288.358.357&335) | Surface Preparation | Piles |  |  | 41776 | 41776 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0070 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41776 | 41776 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0071 | Surface Preparation and treatment for pile head at piles H no. (29-54-55-78-214-212-211-210-186-183-182-157-153-128-381-104) | Surface Preparation | Piles |  |  | 41776 | 41777 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0072 | Casting grout by material sika grout 200 for Pile Head At Piles H NO. . (130-127-126-125-105-106-103-102-101-80-81-82-79-77-57-58-32-33-31) E (328-350-374-375-380-385-18-67-75) | Grout | Piles |  |  | 41777 | 41778 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0073 | Casting grout by material sika grout 200 for Pile Head At Piles H NO. . (29-54-55-78-214-212-211-210-186-183-182-157-153-128-381-104) | Grout | Piles |  |  | 41776 | 41777 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0074 | Surface Preparation and treatment for pile head at piles H no. (130-127-126-125-105-106-103-102-101-80-81-82-79-77-57-58-32-33-31) E (328-350-374-375-380-385-18-67-75) | Surface Preparation | Piles |  |  | 41777 | 41778 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0075 | Surface Preparation and treatment for pile head at piles H no. (213-239-153-184-187-215-240) & E (306-295-311) | Surface Preparation | Piles |  |  | 41777 | 41778 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0076 | Surface Preparation for pile head prior to apply epoxy at piles H no. (429-430-431-432-433-434) | Epoxy | Piles |  |  | 41777 | 41778 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0077 | Apply Epoxy at piles head for piles H no. (429-430-431-432-433-434) SIKA Dur 42 | Epoxy | Piles |  |  | 41777 | 41778 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0078 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41780 | 41781 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0079 | Surface preparation at diaphragm wall prior to apply GEOTEXTILE and mamberain sheet as attached scetch | Insulation | Diaphragm Wall |  |  | 41777 | 41779 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0080 | Casting grout by material sika grout 200 for pile head at piles H no. (213-239-153-184-187-215-240) E (306-295-311) | Grout | Piles |  |  | 41777 | 41778 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0081 | Surface preparation and treatment for Pile Head At Piles E NO. (355.364.373.377.398.48.62.70.31.80.83.84.88&22) | Surface Preparation | Piles |  |  | 41778 | 41779 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0082 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41780 | 41781 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0083 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41785
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0084 | Casting grout by material sika grout 200 for pile head at piles E no. (355.364.373.377.398.48.62.70.31.80.83.84.88&22) | Grout | Piles |  |  | 41778 | 41779 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0085 | Surface preparation and treatment for Pile Head At Piles H NO. (185.184.183.155.157.153.152.128.130.30.8.9.10.7.6.11.5.12.13.431.430.429.432.433.434.439.438&437) | Surface Preparation | Piles |  |  | 41778 | 41779 | N
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0086 | Casting grout by material sika grout 200 for Pile Head At Piles H N O Piles H NO. (185.184.183.155.157.153.152.128.130.30.8.9.10.7.6.11.5.12.13.431.430.429.432.433.434.439.438&437) | Grout | Piles |  |  | 41778 | 41779 | N
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0087 | Surface preparation and treatment for Pile Head At Piles H NO. (581-582-609-635-647-648-649-650-654) | Surface Preparation | Piles |  |  | 41778 | 41779 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0088 | Casting grout by material sika grout 200 for Pile Head At Piles H NO. (581-582-609-635-647-648-649-650-654) | Grout | Piles |  |  | 41778 | 41779
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0089 | Inspection of holes for dowels fixation for piles no. H (491 - 489) by Mungo Mit 600 RE | Dowels | Piles |  |  | 41778 | 41780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0090 | Surface preparation and treatment for Pile Head At Piles H NO. (505-552-554-612-615-636-639-664-678-667) | Surface Preparation | Piles |  |  | 41779 | 41780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0091 | Casting grout by material sika grout 200 for Pile Head At Piles H NO. (505-552-554-612-615-636-639-664-678-667) | Grout | Piles |  |  | 41779 | 41780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0092 | Surface preparation and treatment for Pile Head At Piles E NO. (94-95-96-97-98-99-100-101-102-74-71-72-73-352-353) | Surface Preparation | Piles |  |  | 41779 | 41780 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0093 | Casting grout by material sika grout 200 for Pile Head At Piles E NO. (94-95-96-97-98-99-100-101-102-74-71-72-73-352-353) | Grout | Piles |  |  | 41779 | 41780 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0094 | Surface Preparation for pile head prior to cast epoxy at piles H no. (437-438-439-440-441-443-446-447-448-449-451-452-453) | Epoxy | Piles |  |  | 41779 | 41780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0095 | Casting Epoxy by material Sikadur 42 for pile head at piles H no. (437-438-439-440-441-443-446-447-448-449-451-452-453) | Epoxy | Piles |  |  | 41779 | 41780 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0096 | Surface preparation and treatment for Pile Head At Piles E NO. (91-77-33-36-376-368-369-349-342-329-320-307-308-298-297-294-293-292-299) | Surface Preparation | Piles |  |  | 41781 | 41783 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0097 | Casting grout by material sika grout 200 for Pile Head At Piles E NO. (91-77-33-36-376-368-369-349-342-329-320-307-308-298-297-294-293-292-299) | Grout | Piles |  |  | 41781 | 41783 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0098 | Inspection of hotels for dowels fixation for piles no. E (85-86) | Dowels | Piles |  |  | 41780 | 41781 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0099 | Inspection of dowels for dowels fixation for piles no. E (85-86) | Dowels | Piles |  |  | 41780 | 41781 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0100 | Inspection of dowels fixation for piles no. H (679-625-624-623-622-610-643) | Dowels | Piles |  |  | 41780 | 41781 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0101 | Inspection of holes for dowels fixation for piles no. H (679-625-624-623-622-610-643) | Dowels | Piles |  |  | 41780 | 41781 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0102 | Surface preparation for pile head prior to cast epoxy at piles H no. (450-459-460-461-470-471-472-473-482-483) | Epoxy | Piles |  |  | 41780 | 41781 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0103 | Casting epoxy by material sika dur 42 for pile head at piles H no. (450-459-460-461-470-471-472-473-482-483) | Epoxy | Piles |  |  | 41780 | 41781 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0104 | Surface preparation and treatment for pile head at piles H no. (596-531-628-640-662-663-666-261-185-155-156-154-152-129-34-30-9-8-10-7) | Surface Preparation | Piles |  |  | 41780 | 41781 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0105 | Casting epoxy by material sika grout 200 for pile head at piles H no. (596-531-628-640-662-663-666-261-185-155-156-154-152-129-34-30-9-8-10-7) | Grout | Piles |  |  | 41780 | 41781 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0106 | Surface preparation for pile head prior to cast epoxy at piles H no. (428-436-444-454-478-479-480-481 - 445) | Epoxy | Piles |  |  | 41780 | 41783 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0107 | Casting epoxy by material sika dur 42 for pile head at piles H no. (428-436-444-454-478-479-480-481 - 445) | Epoxy | Piles |  |  | 41780 | 41783 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0108 | Inspection of dowel fixation for piles H (592-605-621) | Dowels | Piles |  |  | 41780 | 41783 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0109 | Inspection of holes for dowel fixation for piles H (592-605-621) | Dowels | Piles |  |  | 41780 | 41783 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0110 | Inspection of Holes for dowel fixation for piles E (17-12-55-50-52-396-399-87-82-81-37-39-66-65-63-47-20) | Dowels | Piles |  |  | 41781 | 41781 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0111 | Inspection of dowel fixation for piles E (17-12-55-50-52-396-399-87-82-81-37-39-66-65-63-47-20) | Dowels | Piles |  |  | 41781 | 41781 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0112 | Surface preparation and treatment for pile head at piles H no. (620-625-622-623-624-592-679-665-652-638-637-643) | Surface Preparation | Piles |  |  | 41781 | 41783 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0113 | Casting epoxy by material sika grout 200 for pile head at piles H no. (620-625-622-623-624-592-679-665-652-638-637-643) | Grout | Piles |  |  | 41781 | 41783 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0114 | Casting epoxy by material sika grout 200 for pile head at piles H no. (11-12-13-14-6-5) | Grout | Piles |  |  | 41781 | 41783 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0115 | Surface preparation and treatment for pile head at piles H no. (11-12-13-14-6-5) | Surface Preparation | Piles |  |  | 41781 | 41783 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0116 | Inspection of Holes Dowels Fixation for Piles no. (E78- E404) | Dowels | Piles |  |  | 41782
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0117 | Inspection of Dowels Fixation for Piles no. (E78- E404) | Dowels | Piles |  |  | 41783
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0118 | Apply Epoxy at piles head for piles H no. (484-485-486-487-488-489-490-492-493-494-495- 496-497-498-499-500-501-502-503-504) | Epoxy | Piles |  |  | 41783 | 41784 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0119 | Surface preparation prior to cast epoxy at piles head H no. (484-485-486-487-488-489-490-492-493-494-495- 496-497-498-499-500-501-502-503-504) | Epoxy | Piles |  |  | 41783 | 41784 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0120 | Casting grout by material sika grout 200 for Pile Head At Piles H NO. (1-2-4-645-589-568-567) | Grout | Piles |  |  | 41783 | 41784 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0121 | Casting grout by material sika grout 200 for Pile Head At Piles H NO. (238-237-236-76-52-28-25) | Grout | Piles |  |  | 41783 | 41784 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0122 | Surface preparation and treatment for pile head at piles H no. (1-2-4-645-589-568-567) | Surface Preparation | Piles |  |  | 41783 | 41784 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0123 | Surface preparation and treatment for pile head at piles H no. (238-237-236-76-52-28-25) | Surface Preparation | Piles |  |  | 41783 | 41784 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0124 | Inspection of Holes Dowels Fixation for Piles no. E (91-95-97-98-99-101-74-71-72-18-394-386-388-384-383-382-380- 378-379-375-369-365-366 | Dowels | Piles |  |  | 41784 | 41785 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0125 | Inspection of Dowels Fixation for Piles no. E (91-95-97-98-99-101-74-71-72-18-394-386-388-384-383-382-380-378-379-375-369-365-366) | Dowels | Piles |  |  | 41784 | 41785 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0126 | Surface preparation prior to cast epoxy at piles head H no. (506-507-508-509-510-511-512-513-514-515-516-517-51-519-520-521-522-523-524-525-526-527-528-529-530-533-534-535-536-537-538-539-540-541-542-543-544-545-546 | Epoxy | Piles |  |  | 41784 | 41785 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0127 | Casting epoxy by material sika dur 42 for pile head at piles H no. (506-507-508-509-510-511-512-513-514-515-516-517-51-519-520-521-522-523-524-525-526-527-528-529-530-533-534-535-536-537-538-539-540-541-542-543-544-545-546 | Epoxy | Piles |  |  | 41784 | 41785 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0128 | Surface preparation and treatment for pile head at piles H no. (15-16-59-634-653) | Surface Preparation | Piles |  |  | 41784 | 41785 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0129 | Casting grout by material sika grout 200 for Pile Head At Piles H NO. (15-16-59-634-653) | Grout | Piles |  |  | 41784 | 41785 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0130 | Surface preparation and treatment for pile head at piles H no. (651-655-605-610-3) | Surface Preparation | Piles |  |  | 41785 | 41786 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0131 | Casting grout by material sika grout 200 for Pile Head At Piles H NO. (651-655-605-610-3) | Grout | Piles |  |  | 41785 | 41786 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0132 | Inspection of Dowels Fixation for Piles no. E (363-360-358-350-347-346-345-313-316-318-336-340-334-333-349-342-343-321-319-320-306-307) & (H 505) | Dowels | Piles |  |  | 41785 | 41786 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0133 | Inspection of holes for Dowels Fixation for Piles no. E (363-360-358-350-347-346-345-313-316-318-336-340-334-333-349-342-343-321-319-320-306-307) & (H505) | Dowels | Piles |  |  | 41785 | 41786 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0134 | Surface preparation prior to cast epoxy at piles head H no. (531-547-548-549-552-553-554-555-556-559-560-561-562-563-564-565-572-573-574) | Epoxy | Piles |  |  | 41785 | 41786 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0135 | Casting epoxy by material sika dur 42 for pile head at piles H no. (531-547-548-549-552-553-554-555-556-559-560-561-562-563-564-565-572-573-574) | Epoxy | Piles |  |  | 41785 | 41786 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0136 | Casting grout by material sika grout 200 for Pile Head At Piles E no. (92-93-104-106-107-108-110) | Grout | Piles |  |  | 41786 | 41786 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0137 | Surface preparation and treatment for pile head at piles E no. (92-93-104-106-107-108-110) | Surface Preparation | Piles |  |  | 41786 | 41786 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0138 | Casting epoxy by material sika dur 42 for pile head at piles H no. (567-568-569-570-571-575-576-577-580-581-582-583-584-585-588-589-590-592-593-594-595) | Epoxy | Piles |  |  | 41786 | 41787 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0139 | Surface preparation for pile head prior to cast epoxy at piles H no. (567-568-569-570-571-575-576-577-580-581-582-583-584-585-588-589-590-592-593-594-595) | Epoxy | Piles |  |  | 41786 | 41787 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0140 | Surface preparation for pile head prior to cast epoxy at piles E no. (15-16-18-19-21-49-50-51-53-54-57-58-59-60-401-402-403-404-405-407) | Epoxy | Piles |  |  | 41786 | 41787 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0141 | Casting epoxy by material sika dur 42 for pile head at piles H no. (15-16-18-19-21-49-50-51-53-54-57-58-59-60-401-402-403-404-405-407) | Epoxy | Piles |  |  | 41786 | 41787 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0142 | Casting epoxy by material sika dur 42 for pile head at piles H no. (505-579-596-597-598-599-600-6014-602-603-604-607-608-609-611-613-614-615-616-617-618) | Epoxy | Piles |  |  | 41787 | 41788 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0143 | Casting epoxy by material sika dur 42 for pile head at piles E (55-52-24-46-47-64-67-71-72-73-74-39-40-395-396-397-399-406) | Epoxy | Piles |  |  | 41787 | 41788 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0144 | Surface preparation for pile head prior to cast epoxy at piles E no. (55-52-24-46-47-64-67-71-72-73-74-39-40-395-396-397-399-406) | Epoxy | Piles |  |  | 41787 | 41788 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0145 | Surface preparation for pile head prior to cast epoxy at piles H no. (505-579-596-597-598-599-600-6014-602-603-604-607-608-609-611-613-614-615-616-617-618) | Epoxy | Piles |  |  | 41787 | 41788 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0146 | Inspection of Dowels Fixation for Piles no. H (578) | Dowels | Piles |  |  | 41787 | 41788 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0147 | Inspection of holes for Dowels Fixation for Piles no. H (578) | Dowels | Piles |  |  | 41787 | 41788 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0148 | Inspection of holes for Dowels Fixation for Piles no. E (77-48-31) | Dowels | Piles |  |  | 41787 | 41790 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0149 | Inspection of Dowels Fixation for Piles no. E (77-48-31) | Dowels | Piles |  |  | 41787 | 41790 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0150 | Casting epoxy by material sika dur 42 for pile head at piles E (14-17-20-61-63-65-66-68-45-23-69-29-30-38-76-98-99-100-101-102-77-78-79-31) | Epoxy | Piles |  |  | 41788 | 41790 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0151 | Surface preparation for pile head prior to cast epoxy at piles E no. 14-17-20-61-63-65-66-68-45-23-69-29-30-38-76-98-99-100-101-102-77-78-79-31) | Epoxy | Piles |  |  | 41788 | 41790 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0152 | Surface preparation and treatment for pile head at piles H no. (26-27-35-83-100) E (111-370) | Surface Preparation | Piles |  |  | 41788 | 41788 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0153 | Casting grout by material sika grout 200 for Pile Head At Piles H NO. (26-27-35-83-100) E (111-370) | Grout | Piles |  |  | 41788 | 41788 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0154 | Inspection of holes for Dowels Fixation for Piles no. E (36-93-106-107-398) | Dowels | Piles |  |  | 41788 | 41788 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0155 | Inspection of Dowels Fixation for Piles no. E (36-93-106-107-398) | Dowels | Piles |  |  | 41788 | 41788 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0156 | Surface preparation and treatment for pile head at piles E no. ( 392-391-398-384-383-382-379-378-376-376-104-106-107-108-110) | Surface Preparation | Piles |  |  | 41790 | 41791 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0157 | Casting epoxy for pile head at piles no. E ( 392-391-398-384-383-382-379-378-376-376-104-106-107-108-110) | Epoxy | Piles |  |  | 41790 | 41791 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0158 | Casting epoxy for pile head at piles no. E (33-36-37-48-86-87-89-85-90-82-81-97-96-91-92-93-94-95) | Epoxy | Piles |  |  | 41790 | 41791 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0159 | Surface preparation prior casting epoxy for pile head at piles no. E ( (33-36-37-48-86-87-89-85-90-82-81-97-96-91-92-93-94-95) | Epoxy | Piles |  |  | 41790 | 41791 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0160 | Surface preparation prior geotextile for area attached sketch | Insulation |  |  |  | 41790 | 41795 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0161 | Surface preparation for pile head prior epoxy for piles head at piles E no. (387-388-389-371-370-369-368-362-361-360-356-351-354-347-346-345-340-342-341-343) | Epoxy | Piles |  |  | 41791 | 41792 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0162 | Casting epoxy by sikadur 42 for pile head at piles no. E 387-388-389-371-370-369-368-362-361-360-356-351-354-347-346-345-340-342-341-343) | Epoxy | Piles |  |  | 41791 | 41792 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0163 | Casting epoxy by sikadur 42 for pile head at piles no. E (339-336-338-333-330-331-326-325-324-322-323-319-315-317-327) | Epoxy | Piles |  |  | 41791 | 41792 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0164 | Surface preparation prior casting epoxy for piles head at piles E no. (339-336-338-333-330-331-326-325-324-322-323-319-315-317-327) | Epoxy | Piles |  |  | 41791 | 41792 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0165 | Inspection of repair by material sikacrete 114 at piles no. H (660-673-685-686-687-700) | Repair | Piles |  |  | 41791 | 41792 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0166 | Surface Preparation prior geotextile as per attached sketch | Insulation |  |  |  | 41792 | 41795 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0167 | Apply geotextile as per attached sketch | Insulation |  |  |  | 41792 | 41795 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0168 | Diaphragm Wall Surface Preparation for Water Proofing application (as Shown in Sketch) | Insulation | Diaphragm Wall |  |  | 41793 | 41795 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0169 | Diaphragm Wall Surface Preparation for Water Proofing application (as Shown in Sketch) | Insulation | Diaphragm Wall |  |  | 41793 | 41800 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0170 | Surface preparation prior casting epoxy for piles head at piles E no. (370B-344-320-316-314-313-312-311-307-308-297-298-295) | Epoxy | Piles |  |  | 41793 | 41794 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0171 | Casting epoxy by sikadur 42 for pile head at piles no. E 370B-344-320-316-314-313-312-311-307-308-297-298-295) | Epoxy | Piles |  |  | 41793 | 41794 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0172 | Diaphragm Wall Surface Preparation for Water Proofing application (as Shown in Sketch) | Insulation | Diaphragm Wall |  |  | 41794 | 41795 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0173 | Surface Preparation for prior Geotextile (as shown in Sketch) | Insulation |  |  |  | 41794 | 41795 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0174 | Surface preparation epoxy for piles head at piles E no. (7-8-9-10-11-62-70-83) | Epoxy | Piles |  |  | 41794 | 41795 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0175 | Casting Epoxy for pile head at piles no. E (7-8-9-10-11-62-70-83) | Epoxy | Piles |  |  | 41794 | 41795 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0176 | Diaphragm Wall Surface Preparation for Water Proofing application (as Shown in Sketch) | Insulation | Diaphragm Wall |  |  | 41800 | 41802 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0177 | Inspection of holes and dowels fixation for pile no. E (109) | Dowels | Piles |  |  | 41794 | 41795 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0178 | Inspection of repair by material sikacrete 114 at piles no. H (681) | Repair | Piles |  |  | 41795 | 41800 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0179 | Casting Grout by material Sika Grout 200 for pile head at piles no. E (337-109) | Grout | Piles |  |  | 41799 | 41800 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0180 | Surface Preparation and treatment for pile head at piles no. E (337 - 109) | Surface Preparation | Piles |  |  | 41799 | 41800 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0181 | Surface Preparation prior epoxy for pile head at piles no. H (6-7-8-10-28-29-30) | Epoxy | Piles |  |  | 41799 | 41800 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0182 | Casting Epoxy by Sikadur 42 for pile head at piles no. E (6-7-8-9-10-28-29-30) | Epoxy | Piles |  |  | 41799 | 41800 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0183 | Apply horizontal geotextile prior membrane sheet ( as shown in Sketch) Sec. 12 | Insulation |  |  |  | 41799 | 41800 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0184 | Surface Preparation for Water Proofing application (as shown in skectch) | Insulation |  |  |  | 41799 | 41802 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0185 | Apply Vertical Geotextile prior membrane sheet (as Shown in Sketch) | Insulation |  |  |  | 41799 | 41800 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0186 | Apply horizontal geotextile prior membrane sheet ( as shown in Sketch) Sec. 11 | Insulation |  |  |  | 41802 | 41804 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0187 | Surface Preparation prior geotextile & membrane sheet (as shown in sketch) Sec. 1 | Insulation |  |  |  | 41801 | 41804 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0188 | Inspection of holes and dowels fixation fpr pile no. H (33-52-57-59-51-60-79-78-77-81-100-104-105-125-127-129-128-154-156-184-183) | Dowels | Piles |  |  | 41807 | 41809 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0189 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41802 | 41804 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0190 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41802 | 41804 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0191 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41802 | 41804 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0192 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41802 | 41804 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0193 | Apply horizontal geotextile prior membrane sheet ( as shown in Sketch) Sec. 5 | Insulation |  |  |  | 41802 | 41804 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0194 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41802 | 41804 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0195 | Casting Grout by material sika grout 200 for pile head at piles no. H (455-456-457-458-462-463-464-465-467-469-477-474-475-476) | Grout | Piles |  |  | 41804 | 41806 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0196 | Surface Preparation and treatment for pile head at piles no. H 455-456-457-458-462-463-464-465-467-469-477-474-475-476) | Surface Preparation | Piles |  |  | 41804 | 41806 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0197 | Inspection of repair by material sikacrete 114 at piles no. H (466-468-674) | Repair | Piles |  |  | 41804 | 41806 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0198 | Casting Grout by material sika grout 200 for pit earth for L.P (1-2-3-12) | Grout |  |  |  | 41804 | 41806 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0199 | Casting grout by material sika grout 200 for pile head at piles no. H (682-683-684-690-691-692-695) | Grout | Piles |  |  | 41804 | 41806 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0200 | Surface Preparation and treatment for pile head at piles no. H (682-683-684-690-691-692-695) | Surface Preparation | Piles |  |  | 41804 | 41806 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0201 | Test for PVC membrane for horzontal joint at level 11 AT SEC (12) 7 (11) | Insulation |  |  |  | 41804 | 41806 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0202 | Surface Preparation and tretment for pile head at piles no. H (466-468-677-684-693-698-697-694-705-706-707-676) & E (6-44) | Surface Preparation | Piles |  |  | 41805 | 41807 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0203 | Casting grout by material sika grout 200 for pile head at piles no. (466-468-677-684-693-698-697-694-705-706-707-676) & E (6-44) | Grout | Piles |  |  | 41805 | 41807 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0204 | Inspection of holes and dowels fixation for pile no. H (455-457-458-462-465-468-469-464-698) & E (22-6-44) | Dowels | Piles |  |  | 41805 | 41807 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0205 | Inspection of repair by material sikacrete 114 at piles no. H (675) | Repair | Piles |  |  | 41805 | 41806 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0206 | Test for Joints PVC Membrane at Sec. (12) & (11) | Insulation |  |  |  | 41806 | 41807 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0207 | Surface preparation prior epoxy for piles head at piles E no. (404-49-57-60-19-21) | Epoxy | Piles |  |  | 41807 | 41809 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0208 | Apply horizontal & Vertical geotextile prior membrane sheet (as shown in sketch) sec. 5 | Insulation |  |  |  | 41806 | 41807 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0209 | Diaphragm Wall Surface Preparation for Water Proofing application (as Shown in Sketch) | Insulation | Diaphragm Wall |  |  | 41806 | 41807 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0210 | Apply horizontal & Vertical geotextile after membrane sheet second layer (as shown in sketch) sec. 11 & 12 | Insulation |  |  |  | 41806 | 41806 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0211 | Inspection of repair by material sikacrete 114 at piles no. H (696) | Repair | Piles |  |  | 41806 | 41806 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0212 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41806 | 41807 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0213 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41806 | 41807 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0214 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41806 | 41807 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0215 | Casting Epoxy by sikadur 42 for pile head at piles no. E (404-49-57-60-19-21) | Epoxy | Piles |  |  | 41807 | 41809 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0216 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41807 | 41807 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0217 | Test for Joints PVC Membrane at Sec. (1) & Sec. (13) | Insulation |  |  |  | 41806 | 41807 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0218 | Surface preparation prior epoxy for piles head at piles E no. (7-8-10-11-12-394-393) | Epoxy | Piles |  |  | 41808 | 41809 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0219 | Casting Epoxy by sikadur 42 for pile head at piles no. E (7-8-10-11-12-394-393) | Epoxy | Piles |  |  | 41808 | 41809 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0220 | Inspection of holes and dowels fixation for pile no. E (13-56-400) | Dowels | Piles |  |  | 41808 | 41809 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0221 | Inspection of holes and dowels fixation for pile no. H (3-11-12-13-31-26-27) | Dowels | Piles |  |  | 41808 | 41809 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0222 | Surface preparation prior geotectile & membrane sheet (as shown in sketch) at sec (3,7) | Surface Preparation |  |  |  | 41808 | 41811 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0223 | Surface preparation casting epoxy by sikadur for piles head at piles E no. (13-56-400-62) | Epoxy | Piles |  |  | 41808 | 41809 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0224 | Surface preparation casting epoxy by sikadur for piles head at piles E no. (3-4-5-11-12-13-26-27-31) | Epoxy | Piles |  |  | 41808 | 41809 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0225 | Steel reinforcement for raft bottom layers at section 12 | Steel Reinforcement | Raft |  |  | 41808 | 41811 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0226 | Inspection of fixation coupler for pile no. E (51-62-70) | Dowels | Piles |  |  | 41808 | 41813 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0227 | Inspection of holes and dowels fixation for pile no. H (4) | Dowels | Piles |  |  | 41808 | 41809 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0228 | Test for Joint PVC Membrane at Sec . 5 as attached sketch | Insulation |  |  |  | 41809 | 41811 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0229 | Applyhorizontal & Vertical geotextile after membrane sheet (Second layer) as shown in sketch sec. 5 | Insulation |  |  |  | 41809 | 41811 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0230 | Casting grout by material sika grout 200 for pile head at piles no. E(5-6-44-28) | Grout | Piles |  |  | 41809 | 41813 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0231 | Surface Preparation and tretment for pile head at piles no. E (5-6-44-28_ | Surface Preparation | Piles |  |  | 41809 | 41811 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0232 | Inspection of holes and dowels fixation for pile no. E (84-88-80) | Dowels | Piles |  |  | 41809 | 41811 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0233 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41809 | 41811 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0234 | Casting Grout by material sika grout 200 for pile head at piles no. H (675-696-698) | Grout | Piles |  |  | 41809 | 41811 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0235 | Surface Preparation and tretment for pile head at piles no. H (675-696-698) | Surface Preparation | Piles |  |  | 41809 | 41811 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0236 | Inspection of Fixation coupler for pile no. H (499,619,626) | Dowels | Piles |  |  | 41811 | 41813 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0237 | Casting epoxy by sikadur 42 for pile head at piles no. H (435-445-447-460-471-455-456-457-458-461-463-464-465-466-467-468-469-474-475-476-477-485-491-490-508) | Epoxy | Piles |  |  | 41811 | 41813 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0238 | Castinggrout by material sika grout 200 for pile head at piles no. H (646-656-657-658-660-661-669-668-670-671-672-673-674) | Grout | Piles |  |  | 41811 | 41813 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0239 | Surface preparation and treatment for pile head at piles. No H (646-656-657-658-660-661-669-668-670-671-672-673-674) | Surface Preparation | Piles |  |  | 41811 | 41813 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0240 | Surface preparation prior epoxy for pile head at piles no. H (435-445-447-460-471-455-456-457-458-461-463-464-465-466-467-468-469-474-475-476-477-485-491-490-508) | Epoxy | Piles |  |  | 41811 | 41813 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0241 | Inspection of repair by material sikacrete 114 at piles no. H (709) | Repair | Piles |  |  | 41811 | 41813 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0242 | Inspection of holes and dowels fixation for pile no. E (377-373-364-355-329-294-292) | Dowels | Piles |  |  | 41812 | 41813 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0243 | Check the level and location of R.C formwork as shown in attached sketch | Survey |  |  |  | 41812 | 41813 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0244 | Check the level and location of P.C form work as shown in attached sketch | Survey | P.C |  |  | 41812 | 41813 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0245 | Check the level and location of P.C form work as shown in attached sketch | Survey | P.C |  |  | 41812 | 41813 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0246 | Check the level and location of P.C form work as shown in attached sketch | Survey | P.C |  |  | 41812 | 41813 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0247 | Apply Vertical Geotextile prior membrane sheet (as Shown in Sketch) | Insulation |  |  |  | 41812 | 41813 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0248 | Steel reinforcement for raft top layers at section 12 walls & Columns dowels | Steel Reinforcement |  |  |  | 41812 | 41813 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0249 | Inspection of repair by material sikacrete 114 at piles no. E (381) | Repair | Piles |  |  | 41813 | 41813 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0250 | Casting Epoxy by sikadur 42 for pile head at piles no. H (532-542-543-544-553-554-555-556-564-566-567-568-571-575-577-578-582-585-586-587) | Epoxy | Piles |  |  | 41813 | 41814 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0251 | Surface preparation prior epoxy for piles head at piles H (532-542-543-544-553-554-555-556-564-566-567-568-571-575-577-578-582-585-586-587) | Epoxy | Piles |  |  | 41813 | 41814 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0252 | Inspection of holes and dowels fixation for pile no. E (352) | Dowels | Piles |  |  | 41813 | 41813 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0253 | Inspection for Injection Pipe at compartement (C121 - C122- C123) At Sec. 12 | Insulation |  |  |  | 41814 | 41814 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0254 | Apply vertical Geotextile prior membrane sheet (first layer) as shown in sketch | Insulation |  |  |  | 41814 | 41814 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0255 | Apply Horizontal Geotextile prior membrane sheet (first layer) as shown in sketch | Insulation |  |  |  | 41814 | 41816 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0256 | Form work (Shuttering) for raft foundation at sec. 12 | Form Work | Raft |  |  | 41814 | 41816 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0257 | Casting epoxy by sikadur 42 for pile head at piles no. H (528-537-554-565-566-567-568-595-596-597-607-608-610-611) | Paint | Piles |  |  | 41814 | 41816 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0258 | Surface preparation prior epoxy for pile head at piles no. H (528-537-554-565-566-567-568-595-596-597-607-608-610-611) | Epoxy | Piles |  |  | 41814 | 41816 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0259 | Inspection of holes and dowels fixation for pile no. H (663-669-687) | Dowels | Piles |  |  | 41814 | 41815 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0260 | Inspection of holes and dowels fixation for pile no. H (660-661-685-688-677-675) | Dowels | Piles |  |  | 41814 | 41814 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0261 | Surface Preparation prior geotextile - as shown in sketch | Insulation |  |  |  | 41815 | 41816 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0262 | Test for vertical joints PVC membrane at as attached sketch from ax C6 to C1 to A4 | Insulation |  |  |  | 41815 | 41822 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0263 | Apply Horizontal geotextile prior membrane sheet 9first layer) as shown in sketch C1 - C3 to A1 - A4 | Insulation |  |  |  | 41815 | 41816 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0264 | Apply vertical geotextile prior membrane sheet (First layer) as shown in sketch B7 to B13 | Insulation |  |  |  | 41815 | 41816 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0265 | Inspection of holes and dowels fixation for pile no. H (33-54-52-57-79-78-77-80-81-104-105-127-128) | Dowels | Piles |  |  | 41815 | 41816 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0266 | Inspection of holes and dowels fixation for pile no. H (672-334-311-310-309-287-288-286-285-138-185-187-240-261-212-37-51-60-124-358-357-335) | Dowels | Piles |  |  | 41815 | 41816 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0267 | Inspection of repair by material sikacrete 114 at piles no. H (107-708-710-619) | Repair | Piles |  |  | 41815 | 41816 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0268 | Apply vertical geotextile prior membrane sheet - first layer as shown in sketch from AXA 4 to A9 | Insulation |  |  |  | 41816 | 41816 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0269 | Test for horizontal joints PVC membrane as attached sketch from AX C4 to C9 | Insulation |  |  |  | 41816 | 41822 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0270 | Inspection of holes and dowels fixation for pile no. H (183-237) | Dowels | Piles |  |  | 41816 | 41818 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0271 | Test for vertical joints PVC membrane as attached sketch from AX A4 to A9 | Insulation |  |  |  | 41816 | 41822 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0272 | Test for vertical joints PVC membrane as attached sketch from AX B7 to B13 | Insulation |  |  |  | 41816 | 41822 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0273 | Surface preparation and treatment for Pile Head At Piles H no. (626-661-659-686-685-687-688-700-699-701-702-713-714-704-709-37-51-60-99-108-123) | Surface Preparation | Piles |  |  | 41816 | 41818 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0274 | Surface preparation and treatment for Pile Head At Piles E no. (25-26-27-28-34-35-41-42-43-381) | Surface Preparation | Piles |  |  | 41816 | 41818 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0275 | Casting grout by material sikagrout 200 for pile head at piles no. H (686-685-687-688-700-699-701-702-713-714-37-51-60-99-108-123) | Grout | Piles |  |  | 41816 | 41818 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0276 | Inspection of repair by material sikacrete 114 at piles no. H (708-710-619) | Repair | Piles |  |  | 41816 | 41818 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0277 | Inspection of fixation coupler for pile no. H (499-619-626-655-708-710) | Dowels | Piles |  |  | 41816 | 41818 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0278 | Casting grout by material sika grout 200 for pile head at piles no. E (25-26-28-34-35-41-42-43-381) | Grout | Piles |  |  | 41816 | 41818 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0279 | Apply Horizontal geotextile prior membrane sheet - second layer as shown in sketch from Axes C 4 to C11 | Insulation |  |  |  | 41818 | 41820 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0280 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41818 | 41820 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0281 | Inspection of holes and dowels fixation for pile no. H (59-100-125-129-154-156-236-16-184) | Dowels | Piles |  |  | 41818 | 41818 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0282 | Casting grout by material sika grout 200 for pile head at piles no. H (711-712) | Grout | Piles |  |  | 41818
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0283 | Inspection of fixation coupler for pile no. H 712 | Dowels | Piles |  |  | 41818
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0284 | Steel Reinforcement for Raft Bottom Layers at sec.5 | Steel Reinforcement | Raft |  |  | 41820
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0285 | Casting grout by material sika grout 200 for pile head at piles no. H (710-712) | Grout | Piles |  |  | 41819 | 41820 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0286 | Casting epoxy by sikadur 42 for pile head at piles no. H (532-531-549) | Epoxy | Piles |  |  | 41819 | 41820 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0287 | Surface Preparation and treatment for pile head at piles no. H (708-619) | Surface Preparation | Piles |  |  | 41820 | 41822 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0288 | Casting grout by material sika grout 200 for pile head at piles no. H (708-619) | Grout | Piles |  |  | 41820 | 41822 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0289 | Apply horizontal geotxtile prior membrane sheet - first layer as shown in sketch from AX A 3 to A9 | Insulation |  |  |  | 41820 | 41822 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0290 | Form Work shuttering for raft foundation at section 5 | Form Work | Raft |  |  | 41821 | 41825 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0291 | Steel reinforcement for raft top layers at section 5 | Steel Reinforcement | Raft |  |  | 41821 | 41825 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0292 | Test for horizontal joints PVC membrane as attached sketch from AX A3 to A9 | Insulation |  |  |  | 41821 | 41825 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0293 | Inspection for injection pipe at section for (C51,C52,C53,C54) | Insulation |  |  |  | 41821 | 41823 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0294 | Steel reinforcement columns &walls dowels & coupler | Steel Reinforcement |  |  |  | 41821 | 41825 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0295 | Inspection of repair by material sikacrete 114 at piles no. H (-85) | Repair | Piles |  |  | 41821 | 41825 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0296 | Surface prepartion prior geotextile as shown in sketch | Insulation |  |  |  | 41821 | 41822 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0297 | Surface Preparation and treatment for pile head at piles no. H (37-50-60-61-74-75-84-85-99-107-108-109-122-123-124) | Surface Preparation | Piles |  |  | 41822 | 41823 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0298 | Casting grout by material sika grout 200 for pile head at piles no. H(37-50-60-61-74-75-84-85-99-107-108-109-122-123-124) | Grout | Piles |  |  | 41822 | 41823 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0299 | Surface prepartion prior epoxy for pile head at piles no. E (1-2-3-4-5-6-44-70-25-26-30-41-42-28-43-38-76-75-91-79-78-80-77-32-83-88-84) | Epoxy | Piles |  |  | 41822 | 41823 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0300 | Casting epoxy by sikadur 42 for pile head at piles no. E 1-2-3-4-5-6-44-70-25-26-30-41-42-28-43-38-76-75-91-79-78-80-77-32-83-88-84) | Epoxy | Piles |  |  | 41822 | 41823 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0301 | Inspection of repair by material sikacrete 114 at piles no. 703 | Repair | Piles |  |  | 41822 | 41823 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0302 | Test for horizontal joints PVC membrane as attached sketch from AX C4 to C9/B3 | Insulation |  |  |  | 41822 | 41825 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0303 | Inspection of fixation coupler for pile no. H 703 | Dowels | Piles |  |  | 41822 | 41823 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0304 | Apply horizontal geotxtile prior membrane sheet - second layer as shown in sketch from AX A 4 to A9 | Insulation |  |  |  | 41822 | 41827 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0305 | Surface Preparation prior geotextile as shown in scketch | Insulation |  |  |  | 41825 | 41825 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0306 | Surface Preparation and treatment for pile head at piles no. H (51-36-703) | Surface Preparation | Piles |  |  | 41823 | 41825 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0307 | Casting grout by material sika grout 200 for pile head at piles no. H (51) | Grout | Piles |  |  | 41823 | 41825 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0308 | Inspection of fixation coupler for pile no. H 711 | Dowels | Piles |  |  | 41823 | 41825 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0309 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41823 | 41825 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0310 | Apply horizontal geotxtile prior membrane sheet - first layer as shown in sketch from AX A 4 to A4/C3 | Insulation |  |  |  | 41826 | 41827 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0311 | Apply horizontal geotxtile prior membrane sheet - first layer as shown in sketch from AX C4 to C8/A2 to A4 | Insulation |  |  |  | 41826 | 41827 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0312 | Surface prepartion prior epoxy for pile head at piles no. E (98-99-102) | Epoxy | Piles |  |  | 41826 | 41827 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0313 | Casting epoxy by sikadur 42 for pile head at piles no. E (98-99-102) | Epoxy | Piles |  |  | 41826 | 41827 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0314 | Surface Preparation and treatment for pile head at piles no. H (107-108-109-122-123-124-56) | Surface Preparation | Piles |  |  | 41826 | 41827 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0315 | Casting grout by material sika grout 200 for pile head at piles no. H (107-108-109-122-123-124-56) | Grout | Piles |  |  | 41826 | 41827 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0316 | Surface Preparation prior geotextile as shown in scketch from AX B5 to B14/A12 | Insulation |  |  |  | 41826 | 41827 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0317 | Test for horeziontal joints PVC membrane as attached sketch from AX C6 To C5 | Insulation |  |  |  | 41827 | 41828 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0318 | Surface preparation prior epoxy for pile head at piles no. H (523-536-550-551-557-566-571-575) | Epoxy | Piles |  |  | 41827 | 41828 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0319 | Casting epoxy by sikadur 42 for pile head at piles no. H (523-536-550-566) | Epoxy | Piles |  |  | 41827 | 41828 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0320 | Apply horizontal geotxtile prior membrane sheet - second layer as shown in sketch from AX C5 to C8 | Insulation |  |  |  | 41827 | 41828 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0321 | Surface preparation prior epoxy for pile head at piles no. H (585-586-587-578-590-591-592-602-600-599) | Epoxy | Piles |  |  | 41828 | 41829 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0322 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41827 | 41828 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0323 | Casting epoxy by sikadur 42 for pile head at piles no. H (585-586-587-578-590-591-592-602-600-599) | Epoxy | Piles |  |  | 41828 | 41829 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0324 | Test for horeziontal joints PVC membrane as attached sketch from AX C6 To C4 at Sec. (3,7) | Insulation |  |  |  | 41828 | 41829 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0325 | Apply horizontal geotxtile after PVC second layer AX C6 to C4 at Sec. (3.7) | Insulation |  |  |  | 41828 | 41829 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0326 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41828 | 41829 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0327 | Apply horizontal geotxtile after PVC first layer AX B13 to B7 at Sec. (5.6) as attached sketch | Insulation |  |  |  | 41829 | 41829 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0328 | Treatment & injection for wet pile head at piles no. H (530-557-551-558) | Insulation | Piles |  |  | 41829 | 41832 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0329 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41829 | 41832 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0330 | Apply horizontal geotxtile after PVC second layer AX C1 to C4 at Sec. (1) as attached sketch | Insulation |  |  |  | 41830 | 41832 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0331 | Test for horeziontal joints PVC membrane as attached sketch from AX C1 To C4 at Sec. (1) | Insulation |  |  |  | 41830 | 41832 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0332 | Casting epoxy by sikadur 42 for pile head at piles no. H (1-2-14-15-16-24-25-33-34-35-37) | Epoxy | Piles |  |  | 41830 | 41834 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0333 | Surface preparation prior epoxy for pile head at piles no. H (1-2-14-15-16-24-25-33-34-35-37) | Epoxy | Piles |  |  | 41830 | 41832 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0334 | Steel Reinforcement for raft bottom layers at section 7 | Steel Reinforcement | Raft |  |  | 41830 | 41832 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0335 | Bottom Mesh Raft R.C raft Sec. 11 as shown in sketch | Steel Reinforcement | Raft |  |  | 41832 | 41834 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0336 | Apply PVC membrane for the area floor (B6-B14) | Insulation |  |  |  | 41832 | 41834 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0337 | Treatment & injection for wet pile head at piles no. H (1) | Insulation | Piles |  |  | 41833 | 41836 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0338 | Apply horizontal geotxtile after PVC membrane for area B6-B14 to A12 Horizontal | Insulation |  |  |  | 41832 | 41834 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0339 | Check the level and location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41832 | 41834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0340 | Bottom Reinforcement additional for sec. 7 for raft | Steel Reinforcement | Raft |  |  | 41832 | 41834 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0341 | Surface prepartion prior epoxy for pile head at piles no. H (663-664-665-666-667-678-679-680-681-692-693-694-695-706-707-708-709) & E (34-35) | Epoxy | Piles |  |  | 41834 | 41835 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0342 | Casting epoxy by sikadur 42 for pile head at piles no. H (663-664-665-666-667-678-679-680-681-692-693-694-695-706-707-708-709) & E (34-35) | Epoxy | Piles |  |  | 41834 | 41835 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0343 | Steel Reinforcement for raft top layers & Walls, columns dowels at section 7 | Steel Reinforcement |  |  |  | 41834 | 41835 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0344 | Installation for injection pipes at section 5 for (C71,C72,C73,C74) | Insulation |  |  |  | 41834 | 41835 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0345 | Form Work shuttring for raft foundation at section 7 | Form Work | Raft |  |  | 41834 | 41835 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0346 | Installation for injection hose at construction joint between at section 5 for (5,7) | Insulation |  |  |  | 41834 | 41835 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0347 | Steel Reinforcement for two columns type C1 on axes A11,,12/B3 | Steel Reinforcement |  |  |  | 41835 | 41837 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0348 | Casting grout by material sika grout 200 for pile head at piles no. E (300-301-302-303-304-305-370A) | Grout | Piles |  |  | 41835 | 41836 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0349 | Surface preparation and treatment for Pile Head At Piles E no. (300-301-302-303-304-305-370A) | Surface Preparation | Piles |  |  | 41835 | 41836 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0350 | Check the level and location of PC form work as shown in attached sketch | Survey | P.C |  |  | 41835 | 41836 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0351 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41835 | 41836 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0352 | Steel reinforcement for raft bottom layers at section 1 | Steel Reinforcement | Raft |  |  | 41835 | 41837 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0353 | Formwork for two columns type C1/1 on axes A11,12 / B3 | Form Work |  |  |  | 41835 | 41837 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0354 | Apply Vertical geotxtile before PVC First Layer AX B13 to B21 at sec. (4.14) | Insulation |  |  |  | 41836 | 41837 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0355 | Surface prepartion prior geotextile & membrane sheet as shown in sketch sec. 2 | Insulation |  |  |  | 41836 | 41837 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0356 | Surface prepartion prior epoxy for pile head at piles no. H (659-660-662-668-669-670-671-672-673-674-675-676-677-682-683-684-685-686-687-688-689-690-691-696-697-698-699-700-701-702-703-704-705-710-711-712-713-714 | Epoxy | Piles |  |  | 41836 | 41837 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0357 | Casting epoxy by sikadur 42 for pile head at piles no. H (659-660-662-668-669-670-671-672-673-674-675-676-677-682-683-684-685-686-687-688-689-690-691-696-697-698-699-700-701-702-703-704-705-710-711-712-713-714 | Epoxy | Piles |  |  | 41836 | 41837 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0358 | Steel reinforcement for raft top layers & walls, columns dowels at section 1 A5 To A8 | Steel Reinforcement |  |  |  | 41836 | 41840 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0359 | Surface prepartion and treatment for pile head at piles no. E (386-387-388) | Surface Preparation | Piles |  |  | 41836 | 41837 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0360 | Casting grout by material sika grout 200 for pile head at piles no. E (386-387-388) | Grout | Piles |  |  | 41836 | 41837 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0361 | Form Work Shuttering for raft foundation at section 1 as attached sketch | Form Work | Raft |  |  | 41837 | 41840 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0362 | Installation for injection pipes at section 1 for (C14,C15,C73,C16) | Insulation |  |  |  | 41837 | 41840 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0363 | Installation for injection hose between section 1,12 | Insulation |  |  |  | 41837 | 41840 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0364 | Apply horizontal geotxtile after PVC first layer AX C2 to C4 as attached sketch | Insulation |  |  |  | 41837 | 41840 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0365 | Casting epoxy by sikadur 42 for pile head at piles no. E (355-357-358-359-363-364-366-369-361-372-373-377-374-375-380-381-385) | Epoxy | Piles |  |  | 41839 | 41840 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0366 | Surface preparation prior epoxy for pile head at piles no. E (355-357-358-359-363-364-366-369-361-372-373-377-374-375-380-381-385) | Epoxy | Piles |  |  | 41839 | 41840 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0367 | Inspection of holes and dowels fixation for pile no. E (304-305-386-388-390) | Dowels | Piles |  |  | 41839 | 41841 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0368 | Steel reinforcement for raft bottom layers at section 11 for area as attached sketch B4 to B9 | Steel Reinforcement | Raft |  |  | 41839 | 41842 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0369 | Steel reinforcement for raft top layers & walls, columns dowels at section 11 for area as attached sketch B4 to B9 | Steel Reinforcement |  |  |  | 41839 | 41844 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0370 | Form Work Shuttering for raft foundation at section 11 as attached sketch | Form Work | Raft |  |  | 41840 | 41844 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0371 | Installation for injection hose between section 11,12 | Insulation |  |  |  | 41840 | 41840 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0372 | Test for horizontal goints PVC membrane l as attached sketch from AX C2 To C5 at sec. 1 | Insulation |  |  |  | 41840 | 41842 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0373 | Installation for injection pipe at section 11 for C111, C112,C113 | Insulation |  |  |  | 41840 | 41840 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0374 | Apply horizontal geotxtile prior PVC first layer as attached sketch | Insulation |  |  |  | 41840 | 41842 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0375 | Apply horizontal geotxtile prior PVC first layer as attached sketch sump Pit | Insulation |  |  |  | 41840 | 41842 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0376 | Apply horizontal geotxtile prior PVC second layer as attached sketch | Insulation |  |  |  | 41840 | 41846 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0377 | Test for horizontal goints PVC membrane as attached sketch from AX B15 To B20 | Insulation |  |  |  | 41840 | 41842 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0378 | Steel reinforcement for raft bottom layers at section 1,3 for area as attached sketch | Steel Reinforcement | Raft |  |  | 41840 | 41842 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0379 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41840 | 41843 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0380 | Steel reinforcement for SHW No. 3 at second basement | Steel Reinforcement |  |  |  | 41841 | 41842 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0381 | Inspection of fixation coupler for pile No. H(684-696) | Dowels | Piles |  |  | 41841 | 41842 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0382 | Inspection of holes and dowels fixation for pile No. H (61-74-85-73-86-97-108-123) | Dowels | Piles |  |  | 41841 | 41842 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0383 | Surface preparation prior epoxy for pile head at piles No. H(623-616-615-613-612-603-604-605-606) | Epoxy | Piles |  |  | 41841 | 41842 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0384 | Casting epoxy by sikadur 42 for pile head at piles No. H(623-616-615-613-612-603-604-605-606) | Epoxy | Piles |  |  | 41841 | 41846 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0385 | surface prepation prior epoxy for pile head at piles No. H(617-618-619-620-21-622-624-625-626-627-628-629-630-631-632-633-634-635-636-637-638-639-640-641-642-643-644-645-646-647-648-649-650-651-652-653-654-655-656-657-658) | Epoxy | Piles |  |  | 41841 | 41844 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0386 | Casting epoxy by sikadur 42 for pile head at piles No. H(617-618-619-620-21-622-624-625-626-627-628-629-630-631-632-633-634-635-636-637-638-639-640-641-642-643-644-645-646-647-648-649-650-651-652-653-654-655-656-657-658) | Epoxy | Piles |  |  | 41841 | 41844 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0387 | Injection and treatment for wet pile head at piles No. H(1-606) | Insulation | Piles |  |  | 41841 | 41846 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0388 | Steel reinforcement for- 4 columns type C1 at second basement on axes A8,7,6,5/ B3,2 as attached sketch | Steel Reinforcement | Column |  |  | 41842 | 41842 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0389 | Apply vertical geotextile prior PVC (first layer) as attached sketch | Insulation |  |  |  | 41841 | 41842 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0390 | Apply vertical geotextile prior PVC (first layer) as attached sketch | Insulation |  |  |  | 41841 | 41842 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0391 | Diaphragm Wall Surface Preparation for Water Proofing application (as Shown in Sketch) | Insulation | Diaphragm Wall |  |  | 41842 | 41844 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0392 | Test for horizontal joints PVC membrane as attached sketch. | Insulation |  |  |  | 41842 | 41846 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0393 | Apply horizontal geotextile after PVC (second layer) as attached sketch. | Insulation |  |  |  | 41843 | 41846 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0394 | Form work (shuttering) for four columns on axes A5,6,7,8/ B3,2 | Form Work | Column |  |  | 41843 | 41847 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0395 | Surface preparation prior geotextile & membrane sheet (as shown in sketch) | Insulation |  |  |  | 41843 | 41846 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0396 | Surface prepration prior epoxy for pile head at piles No. H(51-52-53-54-55-56-57-58-59-60-79-78-77-76-80-81-82-83-84-99-100-101-102-103-104-105-106-107-108-123-124-125-126-127) & E(390-387-386) | Epoxy | Piles |  |  | 41843 | 41846 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0397 | Casting epoxy by sikadur 42 for pile head at piles No. H(51-52-53-54-55-56-57-58-59-60-79-78-77-76-80-81-82-83-84-99-100-101-102-103-104-105-106-107-108-123-124-125-126-127) & E(390-387-386) | Epoxy | Piles |  |  | 41843 | 41846 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0398 | Apply horizontal geotextile prior PVC (first layer) as attached sketch. | Insulation |  |  |  | 41843 | 41846 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0399 | Steel reinforcement for raft top layers at scetion 1 & walls, column dowels for area as attached sketch | Steel Reinforcement |  |  |  | 41844 | 41846 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0400 | Form work (Shuttering) for raft foundation at section 1 as area sketch | Form Work | Raft |  |  | 41844 | 41847 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0401 | Installation for injection pipe at section 1 for C11, C12, C13 | Insulation |  |  |  | 41844 | 41846 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0402 | Installation for injection (hose) at section 1 for construction joint | Insulation |  |  |  | 41844 | 41846 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0403 | Steel reinforcement for raft botoom layers at Section 3 for Area as attached sketch | Steel Reinforcement | Raft |  |  | 41844 | 41847 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0404 | Form work (shuttering) for shear wall No. 3 on Axes C6 | Form Work |  |  |  | 41844 | 41847 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0405 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41846 | 41847 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0406 | Inspection of fixation coupler for pile No. H(56) | Dowels | Piles |  |  | 41844 | 41846 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0407 | Inspection of repair by material sikacrete 114 at piles No. H(75) | Repair | Piles |  |  | 41844 | 41846 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0408 | Test for Vertical joints PVC membrane as attached sketch | Insulation |  |  |  | 41844 | 41847 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0409 | Apply vertical geotextile after PVC (second layer) as attached sketch | Insulation |  |  |  | 41844 | 41846 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0410 | Surface preparation prior epoxy for pile head at piles No. H(128-129-130) | Epoxy | Piles |  |  | 41844 | 41846 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0411 | Casting epoxy by sikadur 42 for pile head at piles No. H(128-12-130) | Epoxy | Piles |  |  | 41844 | 41846 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0412 | Test for horizontal joints PVC membrane as attached sketch | Insulation |  |  |  | 41844 | 41847 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0413 | Inspection of holes and dowels fixation for pile No. H (36-98) & E(381) | Dowels | Piles |  |  | 41846 | 41853 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0414 | Apply horizontal geotextile prior PVC (first layer) as attached sketch. | Insulation |  |  |  | 41846 | 41847 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0415 | Surface prepration prior geotextile as shown in sketch | Insulation |  |  |  | 41846 | 41847 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0416 | Apply horizontal geotextile after PVC (second layer) as attached sketch. | Insulation |  |  |  | 41847 | 41854 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0417 | Surface preparation and treatment for pile head at piles No. H (36-75) | Surface Preparation | Piles |  |  | 41853 | 41854 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0418 | Casting grout by material sika grout 200 for pile head No. H (36-75) | Grout | Piles |  |  | 41853 | 41854 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0419 | Surface preparation prior epoxy for pile head at piles No. E (349-352-353-348-335-334-337) | Epoxy | Piles |  |  | 41853 | 41854 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0420 | Casting epoxy by sikadur 42 for piles No. E (349-352-353-348-335-334-337) | Epoxy | Piles |  |  | 41853 | 41854 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0421 | Removable for 3 struts as attached sketch | Strut | Strut |  |  | 41853 | 41856 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0422 | Form work shuttering for column on axes B3/A8 | Form Work | Column |  |  | 41854 | 41854 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0423 | Steel reinforcement for 2 columns type C4 on axes A6,7,8/B2 | Steel Reinforcement | Column |  |  | 41854 | 41854 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0424 | Removable lower strut for 5 struts as attached sketch | Strut | Strut |  |  | 41854 | 41856 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0425 | Surface preparation prior epoxy for pile head at piles No. E(350-332-329-328-321-318-306-305-304-303-302-301-300-299-294-293-292-288-297) | Epoxy | Piles |  |  | 41854 | 41856 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0426 | Casting epoxy by sikadur 42 for pile head at piles No. E(350-332-329-328-321-318-306-305-304-303-302-301-300-299-294-293-292-288-297) | Epoxy | Piles |  |  | 41854 | 41856 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0427 | Test of horizontal joints PVC membrane as attached sketch | Insulation |  |  |  | 41854 | 41856 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0428 | Apply horizontal geotextile prior PVC (first layer) as attached sketch. | Insulation |  |  |  | 41854 | 41856 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0429 | Surface prepration prior geotextile as shown in sketch | Insulation |  |  |  | 41854 | 41856 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0430 | Form work (shuttering) for 2 columns type C4 between axes A6,7,8/B2 | Form Work | Column |  |  | 41855 | 41857 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0431 | Apply horizontal geotextile after PVC second layer highlighted as attached sketch | Insulation |  |  |  | 41855 | 41856 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0432 | Apply horizontal geotextie prior PVC first layer as attached sketch | Insulation |  |  |  | 41855 | 41856 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0433 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41855 | 41856 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0434 | Surface preparation prior epoxy for pile head at piles No. H(36-75-50-61-74-85-109-122-152-153-154-155-156-157-182-183-184) & E (390-370A-324) | Epoxy | Piles |  |  | 41855 | 41857 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0435 | Casting epoxy by sikadur 42 for pile head at piles No. H(36-75-50-61-74-85-109-122-152-153-154-155-156-157-182-183-184) & E(390-370A-324) | Epoxy | Piles |  |  | 41855 | 41858 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0436 | Installation for injection (Hose) between section (3,7) for construction joint | Insulation |  |  |  | 41856 | 41857 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0437 | Steel reinforcement for raft top layers at section 3 & walls & columns dowels | Steel Reinforcement | SHW |  |  | 41856 | 41857 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0438 | Form work (shuttering) for raft foundation at section 3 as area sketch | Form Work | Raft |  |  | 41856 | 41857 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0439 | Installation of injection (pip) at Section 3 for C31-C32-C33-C34-C35 | Insulation |  |  |  | 41856 | 41857 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0440 | Test for horizontal joints PVC membrane as area attached sketch | Insulation |  |  |  | 41856 | 41857 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0441 | Apply horizontal geotextile after PVC second layer as attached sketch | Insulation |  |  |  | 41856 | 41857 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0442 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41856 | 41857 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0443 | Removable lower strut for 6 struts as attached sketch | Strut | Strut |  |  | 41856 | 41861 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0444 | Diaphragm Wall Surface Preparation for Water Proofing application (as Shown in Sketch) | Insulation | Diaphragm Wall |  |  | 41856 | 41857 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0445 | Removable lower anchor for 3 anchors as attached sketch | Anchor | Anchor |  |  | 41857 | 41861 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0446 | Inspection fabrications and storage area | Fabrication |  |  |  | 41857 | 41857 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0447 | Diaphragm wall geotextile first layer for water proofing application as shown in sketch from level -9 to level -4.5 | Insulation | Diaphragm Wall |  |  | 41857 | 41860 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0448 | Surface prepration prior geotextile as shown in sketch | Insulation |  |  |  | 41857 | 41860 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0449 | Diaphragm wall surface preparation for Water Proofing application (as Shown in Sketch) from level 9 to level 4.5 | Insulation | Diaphragm Wall |  |  | 41857 | 41860 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0450 | Test for horizontal joints PVC membrane as area shown in attached sketch | Insulation |  |  |  | 41858 | 41860 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0451 | Apply horizontal geotextile after PVC second layer as attached sketch | Insulation |  |  |  | 41858 | 41862 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0452 | Diaphragm wall surface prepration for water proofing application as shown in attached sketch from level -9 to level -4.5 | Insulation | Diaphragm Wall |  |  | 41860 | 41861 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0453 | Diaphragm wall geotextile first layer for water proofing application as shown in sketch from level -9 to level -4.5 | Insulation | Diaphragm Wall |  |  | 41860 | 41861 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0454 | Diaphragm wall test PVC as shown in sketch from level -9 up to level -4.5 | Insulation | Diaphragm Wall |  |  | 41860 | 41862 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0455 | Relies lower anchor for 3 anchor as attached sketch 22-80-78 | Anchor | Anchor |  |  | 41860 | 41864 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0456 | Surface prepration and treatment and casting grout for pile head at piles No. E (105) | Grout | Piles |  |  | 41868 | 41869 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0457 | Casting epoxy by sikadur 42 for pile head at piles No. H(185-186-211-212-213-214-237-238) | Epoxy | Piles |  |  | 41860 | 41870 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0458 | Surface prepration prior epoxy for pile head at piles No. H(185-186-211-212-213-214-237-238) | Epoxy | Piles |  |  | 41860 | 41864 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0459 | Steel reinforcement for raft botom layers at section 6 for area in attached sketch | Steel Reinforcement | Raft |  |  | 41861 | 41863 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0460 | Apply horizontal geotextile prior PVC (first layer) as attached sketch. | Insulation |  |  |  | 41862 | 41862 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0461 | Diaphragm wall geotextile second layer as shown in attached sketch from level -9 to level -4.5 on axes B13 ot B18 | Insulation | Diaphragm Wall |  |  | 41862 | 41864 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0462 | Diaphragm wall surface prepration as shown in attached sketch from level -9 to level -4.5 axes (A1/B19-18), (A1/C7-C9) | Surface Preparation | Diaphragm Wall |  |  | 41862 | 41864 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0463 | Apply horizontal geotextile after PVC second layer as attached sketch along axes A10-11/B9-B18 | Insulation |  |  |  | 41861 | 41869 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0464 | Test for horizontal joints PVC membrane as area attached sketch along Axes A10-11/B9-B18 | Insulation |  |  |  | 41862 | 41864 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0465 | Steel reinforcement for 3 columns type C1 at second basement along Axes A3/B16,18,19 | Steel Reinforcement | Column |  |  | 41862 | 41863 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0466 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41862 | 41863 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0467 | Remove lower for 3 anchor as attached sketch | Anchor | Anchor |  |  | 41858 | 41861 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0468 | Removable of lower strut for 2 strut as attached sketch | Strut | Strut |  |  | 41857 | 41861 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0469 | Diaphragm wall test PVC as shown in sketch from level -9 up to level -4.5 along axes A1/C7, C9&C18, 19 | Insulation | Diaphragm Wall |  |  | 41864 | 41864 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0470 | Diaphragm wall geotextile first layer as shown in sketch from level -9 to level -4.5 along axes A1/C7, C9& C18, 19 | Insulation | Diaphragm Wall |  |  | 41864 | 41864 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0471 | Relies lower anchor for 3 anchor as attached sketch 72-74-76 | Anchor | Anchor |  |  | 41863 | 41865 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0472 | Release lower anchor for 8 anchors as attached sketch No. of anchors (79- 77- 75- 73- 71- 70- 69- 68) | Anchor | Anchor |  |  | 41864 | 41867 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0473 | Surface prepration prior epoxy for head at piles No. (239- 262- 263- 286- 287- 310- 311- 334) | Epoxy | Piles |  |  | 41864 | 41867 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0474 | Casting epoxy for pile head at piles No. H(239-262- 263- 286- 287- 310- 311- 334)&E (324) | Epoxy | Piles |  |  | 41864 | 41867 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0475 | Casting SIKA grout 200 for galvanized steel pipe at strust support | Steel Reinforcement |  |  |  | 41864 | 41869 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0476 | Release lower anchor for 1 anchor as attached sketch No. of anchors 67 | Anchor | Anchor |  |  | 41865 | 41867 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0477 | Form work shuttering for 3 columns type C1 along axes A3/B16-18-19 | Form Work | Column |  |  | 41865 | 41867 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0478 | Diaphragm wall geotextile second layer as shown in attached sketch from level -9 to level -4.5 up along axes A1/C7, C9&C18, C19 | Insulation | Diaphragm Wall |  |  | 41867 | 41869 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0479 | Surface prepration prior epoxy for piles No. H(187, 210, 215, 236, 240, 261, 264, 285, 288, 304, 312, 333, 335) | Epoxy | Piles |  |  | 41867 | 41868 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0480 | Casting epoxy by sikadur 42 for pile head at piles No. H(187, 210, 215, 236, 240, 261, 264, 285, 288, 304, 312, 333, 335) | Epoxy | Piles |  |  | 41867 | 41869 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0481 | Steel reinforcement for shear wall 5* along axes C2/A2, A3 | Steel Reinforcement | SHW |  |  | 41867 | 41868 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0482 | Steel reinforcement for shear wall 6 along axes C4/A2, A3 | Steel Reinforcement | SHW |  |  | 41867 | 41868 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0483 | Steel reinforcement for shear wall 7 along axes C3/A2, A3 | Steel Reinforcement | SHW |  |  | 41867 | 41868 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0484 | Steel reinforcement for retainig wall between axes A1/ B13 to B18 | Steel Reinforcement | Retaining Wall |  |  | 41867 | 41870 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0485 | Release lower anchor for anchor as attached sketch No. of anchors (66-65-64-63-62-61-60-59-58) | Anchor | Anchor |  |  | 41867 | 41869 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0486 | Release lower anchor for 4 anchor as attached sketch No. of anchors (57-56-55-54) | Anchor | Anchor |  |  | 41868 | 41871 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0487 | Surface prepration prior geotextile and membrane sheet as shown in attached sketch section 7 | Insulation |  |  |  | 41868 | 41870 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0488 | Apply horizontal geotextile prior PVC first layer as attached sketch Sec. 7 | Insulation |  |  |  | 41868 | 41869 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0489 | Test for horizontal joints PVC membrane as attached sketch Sec. 7 | Insulation |  |  |  | 41868 | 41869 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0490 | Apply horizontal geotextile after PVC second ayer as attached sketch Sec. 7 | Insulation |  |  |  | 41868 | 41869 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0491 | Surface prepration prior epoxy for pile head at piles No. E(100, 101) | Epoxy | Piles |  |  | 41868 | 41869 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0492 | Casting epoxy by sikadur 42 for pile head at piles No. E(101, 100) | Epoxy | Piles |  |  | 41868 | 41869 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0493 | Steel reinforcement for shear wall 1 along axes C10/A2,3 | Steel Reinforcement | SHW |  |  | 41868 | 41869 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0494 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41870 | 41872 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0495 | Form work for shear wall No. 6 along axes C4/ A2, A3 as shown in attached sketch | Form Work | SHW |  |  | 41870 | 41875 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0496 | Form work for shear wall No. 7 along aes (C3/A2, A3) as shown in attached sketch | Form Work | SHW |  |  | 41870 | 41872 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0497 | Form work for shear wall No. 1 along axes (C10/A2, A3) | Form Work | SHW |  |  | 41870 | 41872 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0498 | Apply vertical geotextile after PVC (second layer) along axes (A1/B18, 19)& (A1/C7, C9) as attached sketch | Insulation | SHW |  |  | 41870 | 41872 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0499 | Steel Reinforcement for Retainig wall between axes B13 to B18 As Shown In Attached Sketch | Steel Reinforcement | Retaining Wall |  |  | 41871 | 41872 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0500 | Applying 2 cm Epoxy For Strut T-Beam Between Shear Wall 2* and 3* As Shown In Attached Sketch | Epoxy | SHW |  |  | 41871 | 41872 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0501 | Release Lower Anchor for 8 Anchor As Attached Sketch No. of Anchors (53-52-51-50-49-48-46-45) | Anchor | Anchor |  |  | 41869 | 41872 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0502 | Installation of Steel Reinforcement for Beam B6 Shear Wall 6 (Axe C4 Between A2, A3) As Shown In Attached Sketch | Steel Reinforcement | SHW |  |  | 41872 | 41875 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0503 | Check the Level and Location of P.C Formwork as shown in attached sketch | Survey | P.C |  |  | 41872 | 41876 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0504 | Release Lower Anchor for 6 Anchor as attached sketch No of Anchors (53*-47-44-43-42-41) | Anchor | Anchor |  |  | 41872 | 41876 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0505 | Installation of Steel Reinforcement Column C5 Axe (B18,A2) As Shown In Attached Sketch | Steel Reinforcement | Column |  |  | 41871 | 41872 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0506 | Installation of Steel Reinforcement for Shear Wall 5* Axe (C5, Between A2, A3) As Shown In Attached Sketch | Steel Reinforcement | SHW |  |  | 41871 | 41876 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0507 | Steel Reinforcement for Raft Bottom Layer at Section 14 Zone 5C as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41872 | 41874 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0508 | Installation of Injection Pipe at Section 6 As Shown In Attached Sketch | Insulation |  |  |  | 41871 | 41872 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0509 | Reinjection Pipe (FUCO) at Section 6 As Shown In Attached Sketch | Insulation |  |  |  | 41872 | 41872 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0510 | Rebar Work for Raft Foundation at Section 7 Zone 5B Top Layer and Dowels As Shown In Attached Sketch | Dowels | Raft |  |  | 41872 | 41875 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0511 | Rebar Work for Raft Foundation at Section 6 Additional and Dowel As Shown In Attached Sketch | Dowels | Raft |  |  | 41872 | 41872 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0512 | Steel Reinforcement for Raft Bottom Layer at Section 16 Zone 5C as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41872 | 41874 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0513 | Steel Reinforcement for Raft Bottom Layer at Section 7 Zone 5B as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41872 | 41874 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0514 | Rebar Work for Raft Foundation at Section 6 Top Layer As Shown In Attached Sketch | Steel Reinforcement | Raft |  |  | 41872 | 41872 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0515 | Form Work for Raft Foundation at Section 6 | Form Work | Raft |  |  | 41872 | 41872 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0516 | Apply for water proofing details for strut supports as per attached sketch | Insulation |  |  |  | 41872 | 41876 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0517 | Installation for Injection Pipe for Wall Compartment at C14 From Level -11 Up To Level -7.20 | Insulation | SHW |  |  | 41872 | 41876 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0518 | Release lower anchor for 7 anchor as attached sketch No of anchors (40-39-38-37-36-35-34) | Anchor | Anchor |  |  | 41872 | 41876 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0519 | Steel Reinforcement for retaining wall between axes B18 to B19/A1 as shown in attached sketch | Steel Reinforcement | Retaining Wall |  |  | 41874 | 41877 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0520 | Form work for columns C5 along axes B18/A2 as shown in attached sketch | Form Work | Column |  |  | 41874 | 41877 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0521 | Form work for raft Foundation at Section 7 as shown in attached sketch | Form Work | Raft |  |  | 41874 | 41877 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0522 | Installation for injection pipe and injection hose at section 7 as shown in attached sketch | Insulation |  |  |  | 41874 | 41877 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0523 | Relese lower anchor for 4 anchors as attached sketch No. of anchors (33-32-31-30) | Anchor | Anchor |  |  | 41875 | 41878 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0524 | Steel reinforcement raft foundation bottom layer at section 15 as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41875 | 41877 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0525 | Apply 1st layer geotextile axes B18,19/A11,12 at section 22 | Insulation |  |  |  | 41875 | 41878 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0526 | Apply 2nd layer geotextile axes B18,19/A11, 12 at section 22 | Insulation |  |  |  | 41875 | 41878 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0527 | Test for horizontal joints PVC membrane at section 22 along axes B18,19/A11,12 | Insulation |  |  |  | 41875 | 41878 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0528 | Steel reinforcement for shear wall No. 8 axes C2/A2,A3 | Steel Reinforcement | SHW |  |  | 41875 | 41877 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0529 | Form work for shear wall No. 5* along axes C5/A2,A3 as attached | Form Work | SHW |  |  | 41875 | 41877 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0530 | Steel reinforcement for column C1 along axes B19/A2 as shown in attached sketch | Steel Reinforcement | Column |  |  | 41875 | 41877 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0531 | Form work for retaining wall along axes B13 to B18/A1 as shown in attached sketch | Form Work | Retaining Wall |  |  | 41875 | 41877 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0532 | Installation of re-injection hose along axes B13 to B18/A1 as shown in attached sketch | Insulation |  |  |  | 41875 | 41877 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0533 | Form work for shear wall No. 8 along axes C2/A2,A3 as attached sketch | Form Work | SHW |  |  | 41877 | 41878 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0534 | Diaphragm wall surface preparation along axes C7 to C5/A1 at level -9 up to -4.5 as attached sketch | Surface Preparation | Diaphragm Wall |  |  | 41877 | 41881 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0535 | Diaphragm wall geotextile 1st layer surface preparation along axes C7 to C5/A1 at level -9 up to -4.5 as attached sketch | Insulation | Diaphragm Wall |  |  | 41877 | 41882 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0536 | Diaphragm wall test PVC along axes C7 to C5/A1 at level -9 up to -4.5 as attached sketch | Insulation | Diaphragm Wall |  |  | 41877 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0537 | Steel reinforcement work for column C6 along axes B6/A13 and column C7 along axes B8/A12 as attached sketch | Steel Reinforcement | Column |  |  | 41877 | 41878 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0538 | Form work for axes C6 along axes B6/A13 and axes C7 along axes B8/A12 as attached sketch | Form Work |  |  |  | 41877 | 41878 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0539 | Release lower anchor for 8 anchor as attached sketch No. of anchors (31-30-29-28-27-26-25-24) | Anchor | Anchor |  |  | 41877 | 41883 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0540 | Steel reinforcement for core No. 8 along axes B1/A2, A3 as attached sketch | Steel Reinforcement | Core |  |  | 41878 | 41883 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0541 | Steel reinforcement raft foundation top layer, wall and column dowels at section 15 as shown in attached sketch | Steel Reinforcement | SHW |  |  | 41877 | 41877 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0542 | Form work (Shuttering) for raft foundation at section 15 as shown in attached sketch | Form Work | Raft |  |  | 41877 | 41877 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0543 | Installation for injection pipe at section 15 as shown in attached sketch | Insulation |  |  |  | 41877 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0544 | Steel reinforcement for raft foundation bottom layer at section 14 at zone 2 as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41877 | 41877 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0545 | Steel reinforcement for retaining wall between axes B13 to C8/A1 as shown in attached sketch | Steel Reinforcement | Retaining Wall |  |  | 41877 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0546 | Steel reinforcement for core 7 along axes C7/A1,A3 as shown in attached sketch | Steel Reinforcement | Core |  |  | 41877 | 41878 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0547 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41877 | 41878 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0548 | Form work for core No. 7 along axes C7/A1,A2 as attached sketch | Form Work | Core |  |  | 41878 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0549 | Steel Reinforcement for Top Layer Raft Foundation at Section 14 as attached | Steel Reinforcement | Raft |  |  | 41879 | 41879 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0550 | Installation for Re-Injectable Hose and Injection Pipe for Section 14 as attached sketch | Insulation |  |  |  | 41879 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0551 | Check the Level and Location of P.C Form Work as shown in attached sketch | Survey | P.C |  |  | 41879 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0552 | Form Work (Shuttering) for Section 14 as attached sketch | Form Work |  |  |  | 41879 | 41881 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0553 | Form Work for Retaining Wall from Axe B18 to B19/ A1 as attached sketch | Form Work | Retaining Wall |  |  | 41879 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0554 | Installation for Re-Injectable Hose and Injection Pipe for Retaining Wall from Axe B18 to B19/ A1 as attached sketch | Insulation | Retaining Wall |  |  | 41879 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0555 | Installation for Re-Injectable Hose and Injection Pipe for Retaining Wall from Axe B13 to C8/ A1 as attached sketch | Insulation | Retaining Wall |  |  | 41879 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0556 | Form Work for Retaining Wall from Axe B13 to C8/ A1 as attached sketch | Form Work | Retaining Wall |  |  | 41879 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0557 | Steel Reinforcement for 3 Columns Type C1 Along Axes B3/A4,A5,A6 as attached sketch | Steel Reinforcement | Column |  |  | 41879 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0558 | Form Work for 3 Columns Type C1 Along Axes B3/A4,A5,A6 as attached sketch | Form Work | Column |  |  | 41879 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0559 | Steel Reinforcement for 2 Columns Type C1 Axes A4/B2 and B6/A12 and 1 Column Type C3 Axes B4/A13 as attached sketch | Steel Reinforcement | Column |  |  | 41879 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0560 | Form Work for 2 Columns Type C1 Axes A4/B2 and B6/A12 and 1 Column Type C3 Axes B4/A13 as attached sketch | Form Work | Column |  |  | 41881 | 41884 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0561 | Diaphragm Wall Surface Preparation from Axes C4 to C2/A1 at Level -9 Up To Level -4.5 as attached sketch | Surface Preparation | Diaphragm Wall |  |  | 41879 | 41881 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0562 | Diaphragm Wall Geotextile 1st Layer from Axes C4 to C2/A1 at Level -9 Up To Level -4.5 as attached sketch | Insulation | Diaphragm Wall |  |  | 41879 | 41884 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0563 | Diaphragm Wall Geotextile 2nd Layer from Axes C4 to C7/A1 at Level -9 Up To Level -4.5 as attached sketch | Insulation | Diaphragm Wall |  |  | 41879 | 41882 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0564 | Diaphragm Wall Geotextile 1st Layer from Axes C6 to C4 as attached sketch | Insulation | Diaphragm Wall |  |  | 41881 | 41882 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0565 | Steel Reinforcement for Shear Wall No. 5 as attached sketch | Steel Reinforcement | SHW |  |  | 41881 | 41884 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0566 | Steel Reinforcement for Core No. 6 as attached sketch | Steel Reinforcement | Core |  |  | 41881 | 41883 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0567 | Diaphragm Wall Surface Preparation from Axes C3 to C1/A1 at Level -9 Up To Level -4.5 as attached sketch | Surface Preparation | Diaphragm Wall |  |  | 41881 | 41884 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0568 | Steel Reinforcement Top Layer Raft Foundation and Dowels at Section 16 as attached sketch | Steel Reinforcement | Raft |  |  | 41881 | 41882 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0569 | Form Work for Core No. 8 as shown in attached sketch | Form Work | Core |  |  | 41885 | 41885 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0570 | Release Lower Anchor for 9 Anchors as attached sketch No. of anchors (23-22-21-20-19-18-17-15-13) | Anchor | Anchor |  |  | 41881 | 41884 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0571 | Installation for Injection Pipe and Injection Hose at sSection 16 as shown in attached sketch | Insulation |  |  |  | 41881 | 41882 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0572 | Form Work for Raft at Section 16 Zone 5C as shown in attached sketch | Form Work | Raft |  |  | 41882 | 41882 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0573 | Steel Reinforcement for 2 Columns Type C7 Along Axes A12/B10,B12 and 2 Columns Type C1 Along Axes A14/B13, B14 as attached sketch | Steel Reinforcement | Column |  |  | 41882 | 41882 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0574 | Steel Reinforcement for Retaining Wall Along Axes C8 to C4/A1 as attached sketch | Steel Reinforcement | Retaining Wall |  |  | 41882 | 41883 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0575 | Check the Level and Location of P.C Form Work as shown in attached sketch | Survey | P.C |  |  | 41883 | 41883 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0576 | Form Work for Core No. 6 as shown in attached sketch | Form Work | Core |  |  | 41884 | 41884 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0577 | Form Work for Retaining Wall Along Axes C8 to C4/A1 as shown in attached sketch | Form Work | Retaining Wall |  |  | 41884 | 41884 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0578 | Installation of Injection Pipe and Re-Injectable Hose for Retaining Wall Along Axes from C8 to C4/A1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41883 | 41889 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0579 | Steel Reinforcement for 2 Columns Type C6 Axes B9/A12 and B13/A12 and 1 Column Type C1 Axes B16/A14 as shown in attached sketch | Steel Reinforcement | Column |  |  | 41883 | 41884 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0580 | Form Work for 2 Columns Type C7 Along Axes A12/B10, B12 and 2 Columns Type C1 Along Axes A14/B13, B14 as attached sketch | Form Work | Column |  |  | 41884 | 41884 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0581 | Damage Area of Geotextile and PVC of Retaining Wall at Section 1,2 as shown in Attached Sketch | Insulation | Retaining Wall |  |  | 41884 | 41884 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0582 | Release of Lower Anchor for 28 Anchor as attached sketch No of anchors (12-10-8-6-5-1-156-155-154-153-152-151-150-149-148-147-146-145-144-143-142-141-140-139-138-137-136-135) | Anchor | Anchor |  |  | 41883 | 41890 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0583 | Inspection of Holes for Pile No. H(134) | Dowels | Piles |  |  | 41883 | 41888 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0584 | Inspection for Repair for Pile Cover No. H(163-135) | Repair | Piles |  |  | 41883 | 41884 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0585 | Steel Reinforcement for 1 Column Type C1 Along Axes B18/A14 as shown in attached sketch | Steel Reinforcement | Column |  |  | 41884 | 41884 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0586 | Drilling and Fixation of Dowels for Piles H(120-121-162-163-161-181-209-192-205-159) as shown in attached sketch | Dowels | Piles |  |  | 41884 | 41888 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0587 | Steel Reinforcement for Shear Wall 2* as shown in attached sketch | Steel Reinforcement | SHW |  |  | 41884 | 41884 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0588 | Form Work for Shear Wall 2* as shown in attached sketch | Form Work | SHW |  |  | 41885 | 41888 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0589 | Steel Reinforcement for Shear Wall 5 as shown in attached sketch | Steel Reinforcement | SHW |  |  | 41884 | 41884 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0590 | Inspection for Repair for Pile No. H(134-135) | Repair | Piles |  |  | 41884 | 41888 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0591 | Inspection for Holes for Pile No. H(147) | Dowels | Piles |  |  | 41884 | 41888 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0592 | Check the Level and Location of P.C form Work as shown in attached sketch | Survey | P.C |  |  | 41884 | 41888 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0593 | Diaphragm Wall Test PVC from C4 to C2/A1 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41884 | 41884 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0594 | Diaphragm Wall Surface Preparation from Axes C1 to C2/A1 and from A1 to A5/C1 as attached sketch | Surface Preparation | Diaphragm Wall |  |  | 41884 | 41884 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0595 | Diaphragm Wall Geotextile 1st Layer from Axes C1 to C2/A1 and from A5/C1 as attachede sketch | Insulation | Diaphragm Wall |  |  | 41884 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0596 | Inspection for Repair for Pile No. H(147) | Repair | Piles |  |  | 41884 | 41888 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0597 | Removing of Lower Anchor Head from No. 156 to No. 135 about Sec 3-3 of DW and Check of Water Proffing Protection by ASJV | Survey | Anchor |  |  | 41884 | 41884 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0598 | Repair Work of PVC Damaged Area at Section 1, 2 as shown in attached sketch | Insulation |  |  |  | 41885 | 41885 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0599 | Repair Work of Geotextile Damaged Area at Section 1, 2 as shown in attached sketch | Insulation |  |  |  | 41885 | 41885 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0600 | Form Work for 2 Columns Type C1 Axes B18,16/A14 and 2 Columns Type C6 Axes B13,9/A12 as attached sketch | Form Work | Column |  |  | 41885 | 41888 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0601 | Inspection for Holes of Pile No. H(190-191-206-207) | Dowels | Piles |  |  | 41885 | 41888 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0602 | Removing of Lower Struts of South-East | Strut | Strut |  |  | 41885 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0603 | Form Work for Slab Basement 2 at Area Axes B17, 18, 19, 20/A1, 2, 3 | Form Work | Slab |  |  | 41885 | 41888 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0604 | Repair of Pile No. H(151-180) | Repair | Piles |  |  | 41885 | 41888 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0605 | Steel Reinforcement for Column C1 on Axes A14/B19 & C6 on Axes A12/B9 at 2nd Basement | Steel Reinforcement | Column |  |  | 41886 | 41888 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0606 | Form Work for Column C1 on Axes A14/B18 at 2nd Basement | Form Work | Column |  |  | 41889 | 41892 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0607 | Diaphragm Wall Geotextile 2nd Layer from Level -9 to Level -4.5 Along Axes C2 to C4/A1 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41886 | 41889 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0608 | Diaphragm Wall Test PVC from Level -9 up to Level -4.5 Along Axes C2 to C1/A1 | Insulation | Diaphragm Wall |  |  | 41886 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0609 | Form Work for Shear Wall 5 at 2nd Basement Along Axes C5 | Form Work | SHW |  |  | 41889 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0610 | Form Work for Slab at 2nd Basement Along Axes B17,16,15,14,13/A1,2,3 | Form Work | Slab |  |  | 41886 | 41888 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0611 | Steel Reinforcement for Shear Wall 3* at 2nd Basement Along Axes C8 | Steel Reinforcement | SHW |  |  | 41886 | 41890 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0612 | Inspection of Holes and Dowels Fixation for Pile No. H(110, 147, 134, 189, 190, 191, 206, 207, 133, 218, 220, 221) | Dowels | Piles |  |  | 41886 | 41888 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0613 | Diaphragm Wall Surface Preparation from Level -9 Up To Level -4.5 from Axes A5 To A9/C1 | Surface Preparation | Diaphragm Wall |  |  | 41886 | 41889 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0614 | Release for Lower Anchor Head for No. 1-2-3-4 About East Side | Anchor | Anchor |  |  | 41886 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0615 | Diaphragm Wall Geotextile 2nd Layer from Level -9 to Level -4.5 Along Axes B1/C3 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41888 | 41895 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0616 | Diaphragm Wall Geotextile 1st Layer from Level -9 to Level -4.5 Along Axes A1/A6 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41888 | 41889 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0617 | Surface Preparation and Treatment and Casting Grout for Pile Head at Piles No. H(134-147-148-149-150-161-159-176-177-193-204-208) | Grout | Piles |  |  | 41888 | 41890 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0618 | Check the Level and Location of P.C Form Work as shown in attached sketch | Survey | P.C |  |  | 41888 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0619 | Inspection for Holes about Pile No. 218 | Dowels | Piles |  |  | 41888 | 41890 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0620 | Dowels Fixation about Pile No. 206-207-190-191-218 | Dowels | Piles |  |  | 41888 | 41890 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0621 | Release for Lower Anchor Head for South East Side about Walling Beam (165-163-161-159-157) | Anchor | SHW |  |  | 41888 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0622 | Release for Lower Anchor Head for South East side about Walling Beam (166-164-162-160-158) | Anchor | SHW |  |  | 41888 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0623 | Steel Reinforcement for Column CC5 Along Axes C9/A3 & CC6 Along Axes C11/A3 | Steel Reinforcement | Column |  |  | 41888 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0624 | Installation and Anchors Tighten of Anchor Bolts for Steel Composite Column CC5 Along Axes C9/A3 & CC6 Along Axes C11/A3 | Steel Reinforcement | Column |  |  | 41888 | 41889 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0625 | Grouting Under Base Plate of Steel Composite Column CC5 Along Axes C9/A3 & CC6 Along Axes C11/A3 | Steel Reinforcement | Column |  |  | 41888 | 41889 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0626 | Form Work for Composite Column CC5 Along Axes C9/A3 & CC6 Along Axes C11/A3 | Form Work | Column |  |  | 41888 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0627 | Diaphragm Wall Test PVC from Level -9 up to Level -4.5 Along Axes A1 to A5 | Insulation | Diaphragm Wall |  |  | 41888 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0628 | Fabrication of Steel Structure Composite Column CC5 Along Axes C9/A3 and CC6 Along Axes C11/A3 | Fabrication | Column |  |  | 41889 | 41890 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0629 | Steel Reinforcement for Retaining Wall Along Axes C4 to C3/A1 | Steel Reinforcement | Retaining Wall |  |  | 41889 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0630 | Form Work for Column C1 on Axes A14/B19 and C6 on Axes A12/B9 at 2nd Basement | Form Work | Column |  |  | 41889 | 41890 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0631 | Form Work for Retaining Wall Along Axes C4 to C3/A1 at 2nd Basement | Form Work | Retaining Wall |  |  | 41890 | 41891 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0632 | Form Work for Shear Wall 3* Along Axes C8, A2, A3 at 2nd Basement | Form Work | SHW |  |  | 41890 | 41891 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0633 | Steel Reinforcement Bottom Layer for Slab of 2nd Basement on Axes B19, 18, 17, 16, 15/A1, 2, 3 as attached sketch | Steel Reinforcement | Slab |  |  | 41889 | 41891 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0634 | Installation of Injection Pipe and Re-Injectable Hose for Retaining Wall Along Axes from C4 to C3/A1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41889 | 41891 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0635 | Dowels Fixation about Pile No. H(206-207) | Dowels | Piles |  |  | 41889 | 41890 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0636 | Repair of Pile No. H(208-159-135) | Repair | Piles |  |  | 41889 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0637 | Steel Reinforcement for column C1 Along Axes B13/A14 and C6 Along Axes B13/A12 | Steel Reinforcement | Column |  |  | 41889 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0638 | Diaphragm Wall Surface Preparation from Level -9 Up To Level -4.5 from Axes B9 to B12 | Surface Preparation | Diaphragm Wall |  |  | 41889 | 41891 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0639 | Diaphragm Wall Geotextile 1st Layer from Level -9 to Level -4.5 Along Axes B9 to B12 | Insulation | Diaphragm Wall |  |  | 41889 | 41891 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0640 | Diaphragm Wall Test PVC from Level -9 up to Level -4.5 Along Axes A1 to A7/C1 | Insulation | Diaphragm Wall |  |  | 41889 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0641 | Surface Preparation and Treatment for Pile Head At Piles No. H(110-120-121-158-163-162-221-220-192-205) | Surface Preparation | Piles |  |  | 41889 | 41890 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0642 | Diaphragm Wall Surface Preparation from Level -9 Up To Level -4.5 from Axes B9 to B12 | Surface Preparation | Diaphragm Wall |  |  | 41889 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0643 | Check the Level and Location of P.C Form Work as shown in attached sketch | Survey | P.C |  |  | 41889 | 41891 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0644 | Fabrication of Steel Structure Composite Column CC6 2 Along Axes C11/A3 | Fabrication | Column |  |  | 41891 | 41892 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0645 | Surface Preparation and Treatment for Pile Head at piles No. H (178 ,179 ,181 ,189 ,188 ,208 ,209 ,216 ,217 ,159 ,234 ,242) as shown inattached sketch | Surface Preparation | Piles |  |  | 41890 | 41890 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0646 | Remove for Lower Strut as per attached sketch | Strut | Strut |  |  | 41891 | 41891 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0647 | Form Work for Slab Basement 2 at Area Axes B9,10,11,12,13/A12,13 | Form Work | Slab |  |  | 41891 | 41892 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0648 | Diaphragm Wall Geotextile 1st Layer from Level -9 to Level -4.5 Along Axes C1/C2 and A1/A7 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41891 | 41895 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0649 | Drilling and Fixation of Dowels for Piles H (235-232-233-231-230-243-244) as shown in attached sketch | Dowels | Piles |  |  | 41891 | 41892 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0650 | Steel Reinforcement Top Layer for Slab of 2nd Basement on Axes from B19 to B13/A1, 2, 3 as attached sketch | Steel Reinforcement | Slab |  |  | 41891 | 41892 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0651 | Steel Rainforcement for column type (c3) Along Axes B3/A13& 3columns type (c4) Along AxesB2/A9.10 . A13/Between B2,3 | Steel Reinforcement | Column |  |  | 41891 | 41892 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0652 | form work for column type (c3) Along Axes B3/A13& 3columns type (c4) Along AxesB2/A9.10 . A13/Between B2,4 | Form Work | Column |  |  | 41891 | 41892 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0653 | Steel Reinforcement for Bottom Layers for Slab of Second Basement on Axes B15,14,13/A1,2,3 to Construction Joint as attached sketch | Steel Reinforcement | Slab |  |  | 41891 | 41892 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0654 | Diaphragm Wall Test PVC from Level -9 up to Level -4.5 Along Axes B9 to B12/A12 as attached sketch | Insulation | Diaphragm Wall |  |  | 41891 | 41895 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0655 | Inspection of Dowels Fixation About Pile No. H (232-233) | Dowels | Piles |  |  | 41892 | 41895 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0656 | Inspection of Holes Dowels Fixation About Pile No. H (332-233) | Dowels | Piles |  |  | 41892 | 41895 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0657 | Check the Level and Location of P.C Form Work as shown in attached sketch | Survey | P.C |  |  | 41892 | 41892 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0658 | Surface Preparation and Treatment for Pile Head at piles No. H (135-133-132-131-151-180-241-245-246-230-231-190-191-206-219-232) as attached sketch | Surface Preparation | Piles |  |  | 41892 | 41895 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0659 | Drilling and Fixation of Dowels for Piles H (254-258-257-256-255-270-269-268-266-265-283-282-280) as attached sketch | Dowels | Piles |  |  | 41892 | 41892 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0660 | Form Work for 2nd Basement Roof Along Axes C8 to (between C6 and C5) and A1 to A4 as attached sketch | Form Work |  |  |  | 41893 | 41892 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0661 | Form Work for 2nd Basement Roof Along Axes C5 to (between C3 and C2) and A1 to A4 as attached sketch | Form Work |  |  |  | 41893 | 41892 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0662 | Diaphragm Wall Geotextile 2nd Layer from Level -9 to Level -4.5 Along Axes A1 to A3/C1 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41892 | 41895 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0663 | Steel Reinforcement for Retaining Wall Along Axes C3 to (between C1 and C2)/A1 as shown in attached sketch | Steel Reinforcement | Retaining Wall |  |  | 41892 | 41895 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0664 | Installation of Injection Pipe and Re-Injectable Hose for Retaining Wall Along Axes from C3 to (between C3 and C2)/A1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41892 | 41896 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0665 | Form Work for Retaining Wall Along Axes from C3 to (between C3 and C2)/A1 as shown in attached sketch | Form Work | Retaining Wall |  |  | 41893 | 41895 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0666 | Diaphragm Wall Geotextile 2nd Layer from Level -9 up to Level -4.5 Along Axes B9 to B13/A14,15 | Insulation | Diaphragm Wall |  |  | 41892 | 41898 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0667 | Steel Reinforcement for Reatining Wall Along Axes A5 to A7 | Steel Reinforcement | SHW |  |  | 41892 | 41895 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0668 | Form Work for Retaining Wall Along Axes A5 to A7 | Form Work | Retaining Wall |  |  | 41895 | 41896 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0669 | Installation of Injection Pipe and Re-Injectable Hose for Retaining Wall Along Axes A5 to A7/C1 | Insulation | Retaining Wall |  |  | 41892 | 41895 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0670 | Fabrication for Steel Structure of Composite Columns (CC5 & CC6) 2 | Fabrication | Column |  |  | 41892 | 41892 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0671 | Steel Reinforcement for Retaining Wall Along Axes C9 to C7/A1 at 2nd Basement | Steel Reinforcement | Retaining Wall |  |  | 41893 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0672 | Form Work for Retaining Wall Along Axes C9 to C7/A1 at 2nd Basement | Form Work | Retaining Wall |  |  | 41900 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0673 | Form Work for Retaining Wall Along Axes C4 to C6/A1 at 2nd Basement | Form Work | Retaining Wall |  |  | 41900 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0674 | Installation for Injection Pipe and Re Injectable Hose of Retaining Wall Along Axes C7 to C9/A1 at attached sketch | Insulation | Retaining Wall |  |  | 41900 | 41903 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0675 | Installation for Injection Pipe and Re-Injectable Hose of Retaining Wall Along Axes C4 to C6/A1 at 2nd Basement | Insulation | Retaining Wall |  |  | 41900 | 41903 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0676 | Surface Preparation for P.C Prior Geotextile at Section 17 | Insulation | P.C |  |  | 41893 | 41896 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0677 | Apply Geotextile Prior PVC Membrane Sheet 1st Layer at Section 17 | Insulation |  |  |  | 41893 | 41898 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0678 | Steel Reinforcement for Retaining Wall Along Axes A3 to A5/C1 at 2nd Basement | Steel Reinforcement | Retaining Wall |  |  | 41893 | 41895 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0679 | Form Work for Retaining Wall Along Axes A3 to A5/C1 at 2nd Basement | Form Work | Retaining Wall |  |  | 41895 | 41896 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0680 | Installation Injection Pipe and Re-Injectable Hose for Retaining Wall Along Axes A3 to A5/C1 at 2nd Basement | Insulation | Retaining Wall |  |  | 41893 | 41896 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0681 | Steel Reinforcement for Retaining Wall Along Axes C4 to C6/A1 at 2nd Basement | Steel Reinforcement | Retaining Wall |  |  | 41893 | 41905 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0682 | Repair By Material Sikacrete 114 at Pile No. H(243-244) | Repair | Piles |  |  | 41895 | 41898 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0683 | Steel Reinforcement for Retaining Wall Along Axes C2 to C1/A1 and A1 to A3/C1 | Steel Reinforcement | Retaining Wall |  |  | 41895 | 41898 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0684 | Form Work for Retaining Wall Along Axes C2 to C1/A1 and A1 to A3/C1 | Form Work | Retaining Wall |  |  | 41895 | 41899 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0685 | Installation of Injection Pipe and Re-Injectable Hose for Retaining Wall Along Axes C2 to C1/A1 and A1 to A3/C1 | Insulation | Retaining Wall |  |  | 41895 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0686 | Steel Reinforcement for Column Type C1 at Second Basement on Axes A4/B1 as attached sketch | Steel Reinforcement | Column |  |  | 41896 | 41898 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0687 | Steel Reinforcement for Retaining Wall 2nd Basement Slong Axes B9 to B13/A15 as attached sketch | Steel Reinforcement | Retaining Wall |  |  | 41895 | 41898 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0688 | Steel Reinforcement for Ramp Beams B6 from Level B2 to B1 Between Axes (A3-B7:B12) | Steel Reinforcement | Beam |  |  | 41896 | 41899 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0689 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0690 | Steel Reinforcement for Slab B2 Between Axes A3-C5:C8 Section 4B | Steel Reinforcement | Slab |  |  | 41896 | 41899 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0691 | Test PVC Membrane Sheet at Section 17 as per attached sketch | Insulation |  |  |  | 41896 | 41898 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0692 | APPLY Geotextile 2nd Layer After PVC Membrane Sheet at Section 17 as per attached sketch | Insulation |  |  |  | 41896 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0693 | Inspection of Holes and Dowels Fixation for Piles No. H(293-308-306) | Dowels | Piles |  |  | 41896 | 41898 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0694 | Surface Preparation and Treatment and Casting Grout for Piles No. (206-207-219-218-230-231-232-233-235-246-241-255-256-257-259-260-265-266-267-268-269-293-308-306) | Grout | Piles |  |  | 41896 | 41899 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0695 | Form Work for Column Type C1 Along Axes A4/B1 as attached sketch | Form Work | Column |  |  | 41896 | 41898 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0696 | Check the Level and Location of P.C Form Work as shown in attached sketch | Survey | P.C |  |  | 41897 | 41898 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0697 | Repair About Pile No. H(282) | Repair | Piles |  |  | 41897 | 41899 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0698 | Steel Reinforcement for Core 8 at 1st Basement | Steel Reinforcement | Core |  |  | 41895 | 41896 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0699 | Form Work for Core No. 8 at Basement 1 as attached sketch | Form Work | Core |  |  | 41897 | 41900 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0700 | Holes and Dowels Fixation for Pile No. H(317-245-304-290-294) | Dowels | Piles |  |  | 41897 | 41898 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0701 | Steel Top Reinforcement for 2nd Basement Slab Section 4B as attached sketch | Steel Reinforcement | Slab |  |  | 41897 | 41900 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0702 | Steel Bottom Reinforcement for 2nd Basement Slab at Section 3A as attached sketch | Steel Reinforcement | Slab |  |  | 41897 | 41900 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0703 | Surface Preparation and Treatment and Castig Grout for Pile Head at Piles No. H(243-244-270-284-283-281-280-279-294-263-292-291-290) | Grout | Piles |  |  | 41897 | 41899 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0704 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41898 | 41899 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0705 | Check Level and Location of P.C form Work as shown in attached sketch | Survey | P.C |  |  | 41898 | 41899 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0706 | Form Work for Stair No. 14 Along Axes from A2 to A3/B1 as attached sketch | Form Work | Stair |  |  | 41898 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0707 | Surface Preparation for Water Proofing at R.C Raft Construction Joints at Section 18 as attached sketch | Insulation | Raft |  |  | 41898 | 41899 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0708 | Apply Geotextile 1st Layer for Water Proofing at R.C Raft Construction Joints at Section 18 as attached sketch | Insulation | Raft |  |  | 41898 | 41902 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0709 | Dowels Fixation for Piles No. H(305-307-315-318) as attached sketch | Dowels | Piles |  |  | 41898 | 41899 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0710 | Surface Preparation and Casting Epoxy for Piles Head No. H (120-121-131-132-133-134-139-150-151-149-148-147-158-159-160-161-162-163-176-177-178-179-180-181) | Epoxy | Piles |  |  | 41898 | 41903 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0711 | Check the Level and Location of P.C Form Work as shown in attached sketch | Survey | P.C |  |  | 41898 | 41900 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0712 | Surface Preparation and Treatment and Casting Grout for Pile Head at Piles No. H(258-282-289-303-304-305-306-307-308-313-314-315-316-317-318-327-328-329-330-331-332) | Grout | Piles |  |  | 41899 | 41900 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0713 | Inspection of Holes and Dowels Fixation for Pile No. H(111-112-119-135) | Dowels | Piles |  |  | 41899 | 41900 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0714 | Surface Preparation Prior Geotextile& Membrane Sheet at Section 19 as shown in attached sketch | Insulation |  |  |  | 41899 | 41902 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0715 | Steel Reinforcement for Raft Top Layers at Water Tank& Wall Dowels | Steel Reinforcement | SHW |  |  | 41899 | 41904 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0716 | Form Work for Ramp Beam at Section 4B | Form Work | Beam |  |  | 41899 | 41903 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0717 | Inspection Holes and Dowels Fixation for Stair No. 14 | Dowels | Stair |  |  | 41899 | 41903 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0718 | Surface Preparation and Casting Epoxy for Pile Head at Piles No. H(187-210-215-236-240-261-264-285-288-309-312-333) | Epoxy | Piles |  |  | 41899 | 41903 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0719 | Check the Level and Location of P.C Form Work as shown in attached sketch | Survey | P.C |  |  | 41900 | 41902 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0720 | Form Work Dismantle for Slab Basement 2 Section 4A as shown in attached sketch | Removing Form Work | Slab |  |  | 41900 | 41903 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0721 | Bottom Reinforcement for B2 Roof Slab -7.20 From C6 to C4/A1 to A2 and From C9 to C7/A1 to A4 as shown in attached sketch | Steel Reinforcement | Slab |  |  | 41900 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0722 | Top Reinforcement for B2 Roof Slab -7.20 From C6 to C4/A1 to A2 and From C9 to C7/A1 to A4 as shown in attached sketch | Steel Reinforcement | Slab |  |  | 41900 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0723 | Steel Reinforcement Top Layer for B2 Roof Slab -7.20 Section 3A as shown in attached sketch | Steel Reinforcement | Slab |  |  | 41900 | 41903 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0724 | Installation of Injection Pipe and Re-Injectable Hose for B2 Roof Slab (-7.20) Section 4B as attached sketch | Insulation | Slab |  |  | 41900 | 41903 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0725 | Installation of Injection Pipe and Re-Injectable Hose for B2 Roof Slab (-7.20) Section 3A as attached sketch | Insulation | Slab |  |  | 41900 | 41903 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0726 | Installation of Injection Pipe and Re-Injectable Hose for B2 Roof Slab (-7.20) Along Axes C6 to C4/A1 to A2 and From C9 to C7/A1 to A4 as attached sketch | Insulation | Slab |  |  | 41900 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0727 | Form Work for Water Tank Raft Along Axes A3-A6/B2 as attached sketch | Form Work | Raft |  |  | 41900 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0728 | Water Stop for Insolation for Water Tank Along Axes A3 to A6/B2 as attached sketch | Insulation |  |  |  | 41900 | 41904 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0729 | Form Work for Retaining Wall 2nd Basement Axes B9 to B13/A15 as attached sketch | Form Work | Retaining Wall |  |  | 41900 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0730 | Steel Reinforcement for Stair No. 14 Axes B15 to B17/A2 as attached sketch | Steel Reinforcement | Stair |  |  | 41900 | 41903 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0731 | Steel Reinforcement Bottom Layer for Water Tank Axes A3 to A4/B2 as attached sketch | Steel Reinforcement |  |  |  | 41900 | 41904 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0732 | Apply Horizontal Geotextile Prior PVC 1st Layer at Section 19 as attached sketch | Insulation |  |  |  | 41900 | 41909 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0733 | Apply Horizontal Geotextile Prior PVC 1st Layer at Section 18 as attached sketch | Insulation |  |  |  | 41900 | 41904 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0734 | Test PVC Membrane Sheet at R.C Raft Section 18 as shown in attached sketch | Insulation | Raft |  |  | 41902 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0735 | Surface Preparation and Treatment and Casting Grout for Pile Head at Piles No. H(110-112-119-136-146-97-86-73-62-49-96-87-72-63-48-95-88-71-64-47) as shown in attached sketch | Grout | Piles |  |  | 41902 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0736 | Dowels Fixation for Piles No. H(111-87-88-71-49) as attached sketch | Dowels | Piles |  |  | 41902 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0737 | Surface Preparation and Casting Epoxy for Pile Head at Piles No. H(187-210-261-240-215-236-264-285-288-309-312-333) as attached sketch | Epoxy | Piles |  |  | 41902 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0738 | Check the Level and Location of P.C formwork as shown in attached sketch | Survey | P.C |  |  | 41903 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0739 | Steel Reinforcement for Shear Wall 3 on Axes C6 at Basement 1 | Steel Reinforcement | SHW |  |  | 41903 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0740 | Steel Reinforcement for Shear Wall 6 o Axes C4 at Basement 1 | Steel Reinforcement | SHW |  |  | 41903 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0741 | Steel Reinforcement for Sear Wall 7 on Axes C3 at Basement 1 | Steel Reinforcement | SHW |  |  | 41903 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0742 | Form Work for Shear Walls 3,6,7 at Basement 1 | Form Work | SHW |  |  | 41904 | 41906 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0743 | Dowels Fixation for Piles No. H(41-22-18-42-19-20-44-70) as attached sketch | Dowels | Piles |  |  | 41903 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0744 | Surface Preparation and Treatment and Casting Grout for Pile Head at Piles No. H(38-39-40-89-70-65-46-41-23-22-17) as shown in attached sketch | Grout | Piles |  |  | 41903 | 41904 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0745 | Installation for Injection Pipe and Re Injectable Hose for Construction Joint Between Axes C9 to C7 of B2 Roof (-7.20) at attached sketch | Insulation |  |  |  | 41903 | 41904 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0746 | Installation for Injection Pipe and Re-Injectable Hose for Construction Joints Between Axes C9 to C7 of 2nd Basement Roof (-7.20) as attached sketch | Insulation |  |  |  | 41903 | 41909 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0747 | Form Work for Slab Basement 2 at Section 14 on Axes B9 to B13/A14,15 | Form Work | Slab |  |  | 41904 | 41906 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0748 | Steel Reinforcement for Shear Wall 5* at Basement 1 | Steel Reinforcement | SHW |  |  | 41904 | 41906 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0749 | Surface Preparation and Casting Grout for Pile Head at Piles No. H(17-18-19-20-21-22-23-42-43-44-45-66-67-68-69-90-91-93-94-113) | Grout | Piles |  |  | 41904 | 41906 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0750 | Surface Preparation and Casting Epoxy for Pile Head at Piles No. H(119-136-146-190-191-192-193-204-205-206-207-218-219-220-221-230-231-233-243-244-245-246-255-256-257-258-260) | Epoxy | Piles |  |  | 41904 | 41906 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0751 | Surface Preparation Prior Geotextile at Section 8 as area attached sketch | Insulation |  |  |  | 41904 | 41909 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0752 | Test PVC Membrane Sheet at Section 08 as per attached sketch | Insulation |  |  |  | 41904 | 41909 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0753 | Inspection of Holes and Dowels Fixation for Pile No. (68-113) | Dowels | Piles |  |  | 41904 | 41906 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0754 | Inspection of Holes and Dowels Fixation for Pile No. E(103-112-113-114-115-118-120-121-122-124-126-127-130-131-132) | Dowels | Piles |  |  | 41905 | 41906 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0755 | Check Level and Location of Screed as shown in attached sketch | Survey | Screed |  |  | 41906 | 41910 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0756 | Steel Reinforcement Bottom Layer Slab Basement 2 of Section (5D-A) Axes B9,10,13/A12,13,14 as attached sketch | Steel Reinforcement | Slab |  |  | 41905 | 41907 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0757 | Form Work for Shear Wall 5* at Basement 1 on Axes C5 | Form Work | SHW |  |  | 41907 | 41909 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0758 | Form Work for Slab Basement 2 of Section 3B | Form Work | Slab |  |  | 41905 | 41907 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0759 | Bottom Steel Reinforcement for Water Tank as attached sketch sketch | Steel Reinforcement |  |  |  | 41898 | 41899 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0760 | Form Work for Stair 12 as shown in attached sketch | Form Work | Stair |  |  | 41905 | 41909 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0761 | Drilling and Fixation of Dowels for Stair 12 as shown in attached sketch | Dowels | Stair |  |  | 41905 | 41910 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0762 | Steel Reinforcement Bottom Layer for Raft of Section 17 | Steel Reinforcement | Raft |  |  | 41905 | 41909 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0763 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0764 | Surface Preparation and Casting Epoxy for Pile Head at Piles No. H(266-267-268-269-270-279-280-281-282-283-284-290-291-292-293-294-303-304-305-306-307-308-318-289) as attached sketch | Epoxy | Piles |  |  | 41905 | 41909 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0765 | Apply Geotextile Prior PVC Membrane Sheet 1st Layer at Section 8 as shown in attached sketch | Insulation |  |  |  | 41906 | 41909 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0766 | Check the Level and Location of P.C Form Work as shown in attached sketch | Survey | P.C |  |  | 41906 | 41906 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0767 | Steel Reinforcement for Slab Basement 2 Top Layer at Section (5D-A) as attached sketch | Steel Reinforcement | Slab |  |  | 41906 | 41909 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0768 | Installation for Re-Injectable Hose and Injection Pipe for Slab Basement 2 at Section (5D-A) as shown in attached sketch | Insulation | Slab |  |  | 41906 | 41909 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0769 | Steel Reinforcement Bottom Layer for Raft of Section 18 as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41906 | 41909 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0770 | Steel Reinforcement for Walls of Water Tank as shown in attached sketch | Steel Reinforcement | SHW |  |  | 41906 | 41909 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0771 | Steel Reinforcement for Stair No. 12 as shown in attached sketch | Steel Reinforcement | Stair |  |  | 41906 | 41909 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0772 | Test PVC Membrane Sheet at Section 8 as shown in attached sketch | Insulation |  |  |  | 41906 | 41909 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0773 | Apply Geotextile 2nd Layer at Section 8 as per attached sketch | Insulation |  |  |  | 41906 | 41909 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0774 | Surface Preparation and Casting Grout for Pile Head at Piles No. E(103-112-113-114-115-116-117-118-119-120-121-122-123-124-125-126-127-128-129-130-131-132-133) as per attached sketch | Grout | Piles |  |  | 41906 | 41909 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0775 | Inspection of Holes and Dowels Fixation for Pile No. E(123) as per attached sketch | Dowels | Piles |  |  | 41906 | 41906 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0776 | Surface Preparation Prior Geotextile at Section 10 as area attached sketch | Insulation |  |  |  | 41906 | 41912 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0777 | Apply Geotextile 1st Layer at Section 10 as per attached sketch | Insulation |  |  |  | 41906 | 41912 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0778 | Apply Geotextile 1st Layer at Section 19 as per attached sketch | Insulation |  |  |  | 41906 | 41909 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0779 | Apply 1st Layer for Geotextile From B3 to C7/A1 Level -4.5 to -2.5 as per attached sketch | Insulation |  |  |  | 41907 | 41909 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0780 | Test PVC Membrane Sheet From B3 to C7/A1 Level -4.5 to -2.5 as per attached sketch | Insulation |  |  |  | 41907 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0781 | Apply 2nd Layer for Geotextile From B3 to C7/A1 Level -4.5 to -2.5 as per attached sketch | Insulation |  |  |  | 41907 | 41912 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0782 | Surface Preparation From B3 to B7/A15 Level -4.5 to -2.5 as per attached sketch | Surface Preparation |  |  |  | 41907 | 41909 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0783 | Steel Reinforcement for Shear Wall 5 Axes A2 to A3/C5 as shown attached sketch | Steel Reinforcement | SHW |  |  | 41907 | 41910 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0784 | Form Work for Shear Wall 5 Axes A2 to A3/C5 as shown attached sketch | Form Work | SHW |  |  | 41907 | 41909 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0785 | Drilling and Fixation for Pull out Bars for Core 8 B2 Roof (-7.20) at Section 3 as shown in attached sketch | Dowels | Core |  |  | 41907 | 41910 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0786 | Surface Preparation and Casting Grout for Pile Head at Piles No. H(97-98) as per attached sketch | Grout | Piles |  |  | 41907 | 41909 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0787 | Surface Preparation and Casting Grout for Pile Head at Piles No. H(86-73-62-49) as per attached sketch | Grout | Piles |  |  | 41907 | 41909 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0788 | Test PVC Membrane Sheet for Section 19 as shown in attached sketch | Insulation |  |  |  | 41907 | 41912 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0789 | Apply 2nd Layer for Geotextile at Section 19 as shown in attached sketch | Insulation |  |  |  | 41907 | 41912 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0790 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41909 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0791 | Installation for Re-Injectable Hose and Injection Pipe for Section 17 as shown in attached sketch | Insulation |  |  |  | 41909 | 41912 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0792 | Surface Preparation and Casting Epoxy for Pile Head at Piles No. H( 47-48-49-62-63-64-71-72-73-86-87-88) as shown in attached sketch | Epoxy | Piles |  |  | 41909 | 41910 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0793 | Steel Reinforcement Top Layer for Raft of Section 17 as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41909 | 41910 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0794 | Form Work for Raft of Section 17 as shown in attached sketch | Form Work | Raft |  |  | 41909 | 41910 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0795 | Form Work for Walls of Water Tank as shown in attached sketch | Form Work | SHW |  |  | 41909 | 41911 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0796 | Surface Preparation for Water Proofing for R.C Raft Section (9&10) as shown in attached sketch | Insulation | Raft |  |  | 41909 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0797 | Surface Preparation and Casting Grout for Pile Head at Piles No. H(114-115-117-92)& E(129-138-147-135-136-137-144) as shown in attached sketch | Grout | Piles |  |  | 41909 | 41910 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0798 | Dowels Fixation for Piles No. H(114-117-118)& E(135-136-137-144 as shown in attached sketch | Dowels | Piles |  |  | 41909 | 41910 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0799 | Apply 1st Layer for Geotextile From B3 to B7/A15 Level -4.5 to -2.5 as per attached sketch as shown in attached sketch | Insulation |  |  |  | 41909 | 41912 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0800 | Removal of Upper Strut at North Wall about No. H(89-92-100) | Strut | SHW |  |  | 41909 | 41912 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0801 | Steel Reinforcement bottom Layer for B2 Roof (-7.20) Section 3B as shown in attached sketch | Steel Reinforcement |  |  |  | 41909 | 41913 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0802 | Inspection of Hunger of Pile No. H(44-45-46-47-64-65-66-67-68-69-70-71-88-89-90-91-114-115-117-118-194-193-216-268-269)& E(104-105-106-107-108-109-110-111-112-113-114-115) | Pile Hunger | Piles |  |  | 41909 | 41910 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0803 | Surface Preparation and Casting Epoxy for Pile Head at Piles No. H(188-189-208-209-216-217-234-235-241-242-259-265) as shown in attached sketch | Epoxy | Piles |  |  | 41910 | 41920 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0804 | Surface Preparation and Casting Epoxy for Pile Head at Piles No. H(38-39-40) as shown in attached sketch | Epoxy | Piles |  |  | 41910 | 41912 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0805 | Surface Preparation for Water Proofing at Section 9 as shown in attached sketch | Insulation |  |  |  | 41910 | 41912 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0806 | Surface Preparation for Water Proofing for Retaining Wall Axes from B7 to B9/A15 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41910 | 41912 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0807 | Apply 2nd Layer for Geotextile at Section (9&10) as shown in attached sketch | Insulation |  |  |  | 41910 | 41923 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0808 | Test PVC Membrane Sheet for Section (9&10) as shown in attached sketch | Insulation |  |  |  | 41910 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0809 | Apply 1st Layer for Geotextile at Retaining Wall Axes from B3 to B7/A15 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41910 | 41912 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0810 | Test PVC Membrane Sheet for Retaining Wall Axes from B3 to B7/A15) as shown in attached sketch | Insulation | Retaining Wall |  |  | 41910 | 41912 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0811 | Apply 2nd Layer for Geotextile at Retaining Wall Axes from B3 to B7/A15 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41910 | 41912 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0812 | Release of Lower Anchor Head about East Side for No. 1-2-3-4 | Anchor | Anchor |  |  | 41910 | 41920 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0813 | Apply 1st Layer for Geotextile at Retaining Wall Axes from B7 to B9/A15 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41911 | 41912 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0814 | Apply 1st Layer for Geotextile at Section 9 as shown in attached sketch | Insulation |  |  |  | 41911 | 41912 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0815 | Surface Preparation and Casting Epoxy for Pile Head at Piles No. H(19-18-17-23-22-21-20-43-42-41) as shown in attached sketch | Epoxy | Piles |  |  | 41911 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0816 | Steel Reinforcement Top Layer for Raft of Section 18 as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41911 | 41920 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0817 | Form Work for Retaining Wall from Axes B9 to B4/A1 at Basement 1 | Form Work | Retaining Wall |  |  | 41913 | 41913 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0818 | Installation for Re-Injectabe Hose and Injection Pipe at Retaining wall from Axes B9 to B4/A1 at Basement 1 | Insulation | Retaining Wall |  |  | 41912 | 41914 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0819 | Steel Reinforcement For 2 Columns Type C1 Axes B18,B19/A3 as shown in attached sketch | Steel Reinforcement | Column |  |  | 41911 | 41912 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0820 | Form Work For 2 Columns Type C1 Axes B18,B19/A3 as shown in attached sketch | Form Work | Column |  |  | 41920 | 41923 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0821 | Form Work for Column Type C5 Axes B18/A2 as shown in Attached sketch | Form Work | Column |  |  | 41920 | 41923 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0822 | Steel Reinforcement for Column Type C5 Axes B18/A2 | Steel Reinforcement | Column |  |  | 41911 | 41912 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0823 | Steel Reinforcement for Column Type C7 Along Axes B10,12/A12 | Steel Reinforcement | Column |  |  | 41911 | 41912 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0824 | Form Work for Column Type C7 Along Axes B10,12/A12 | Form Work | Column |  |  | 41913 | 41913 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0825 | Form Work for Shear Wall 2 Axes C10/A2 | Form Work | SHW |  |  | 41913 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0826 | Steel Reinforcement for Shear Wall 2 Axes C10/A2 | Steel Reinforcement | SHW |  |  | 41911 | 41912 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0827 | Installation of Injection Pipe and Re-Injectable Hose bottom Layer for B2 Roof (-7.20) Section 3B as shown in attached sketch | Insulation |  |  |  | 41912 | 41913 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0828 | Apply 2nd Layer for Geotextile at Retaining Wall Axes from B7 to B9/A15 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41911 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0829 | Test PVC Membrane Sheet for Retaining Wall Axes from (B7 to B9/A15) as shown in attached sketch | Insulation | Retaining Wall |  |  | 41911 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0830 | Steel Reinforcement Top Layer for B2 Roof (-7.20) Section 3B as shown in attached sketch | Steel Reinforcement |  |  |  | 41911 | 41913 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0831 | Form Work for Raft of Section 18 as shown in attached sketch | Form Work | Raft |  |  | 41913 | 41920 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0832 | Installation for Re-Injectabe Hose and Injection Pipe at Raft of Section 18 as shown in attached sketch | Insulation | Raft |  |  | 41912 | 41913 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0833 | Surface Preparation and Casting Epoxy for Pile Head at Piles No. H(44-45-46-65-66-67-68-69-70-89-90-91-92-93-94) as shown in attached sketch | Epoxy | Piles |  |  | 41912 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0834 | Check the Level and Location of P.C Form Work as shown in attached sketch | Survey | P.C |  |  | 41912 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0835 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41912 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0836 | Form Work Dismantling for B2 Roof (-7.20) as shown in attached sketch | Removing Form Work | Slab |  |  | 41912 | 41920 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0837 | Steel Reinforcement at Retaining Wall Axes from B7 to B9/A15 as shown in attached sketch | Steel Reinforcement | Retaining Wall |  |  | 41912 | 41914 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0838 | Bottom Steel Reinforcement for Raft of Section 8 as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41913 | 41914 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0839 | Steel Reinforcement for Retaining Wall From Axes B4 to B9/A1 as shown in attached sketch | Steel Reinforcement | Retaining Wall |  |  | 41913 | 41913 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0840 | Surface Preparation of Diaphragm Wall for Water Proofing at Axes A15 between B3 and B1 at Axes C1 between A8 and A15 Up To Level -4.50 as shown in attached sketch. | Surface Preparation | Diaphragm Wall |  |  | 41913 | 41923 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0841 | Surface Preparation and Treatment and Casting Grout for Pile Head at Piles No. E(139-140-141-142-143-134-145-146-148-149-150-151)& H(118-137) as shown in attached sketch | Grout | Piles |  |  | 41913 | 41920 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0842 | Dowels Fixation for Piles No. E(142-149-148-145-146-134) as shown in attached sketch | Dowels | Piles |  |  | 41913 | 41913 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0843 | Form Work for Shear Wall No. 8 at B1 as shown in attached sketch | Form Work | SHW |  |  | 41920 | 41921 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0844 | Steel Reinforcement for Shear Wall No. 8 at B1 as shown in attached sketch | Steel Reinforcement | SHW |  |  | 41913 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0845 | Steel Reinforcement for Retaining wall of Basement 2 along Axes B3 to B9 /A15 | Steel Reinforcement | Retaining Wall |  |  | 41913 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0846 | Surface Preparation of Diaphragm Wall for Water Proofing at Axes From B9 to B14/A15 From Level -7.50 Up To Level -2.50 as shown in attached sketch. | Surface Preparation | Diaphragm Wall |  |  | 41920 | 41921 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0847 | Apply 2nd Layer for Geotextile for Rest of Section (9&10) as shown in attached sketch | Insulation |  |  |  | 41913 | 41923 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0848 | Test PVC Membrane Sheet for Rest of Section (9&10) as shown in attached sketch | Insulation |  |  |  | 41913 | 41923 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0849 | Surface Preparation for Diaphragm Wall for Water Proofing from C1 to C3/A1 up to Level -2.50 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41920 | 41921 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0850 | Check location and level of screed as shown in attached sketch | Survey | Screed |  |  | 41912 | 41914 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0851 | Surface Preparation for Water Proofing of R.C Raft Section 23 as shown in attached sketch | Insulation | Raft |  |  | 41920 | 41920 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0852 | Diaphragm Wall Geotextile 1st Layer from Level -7.20 to Level -2.50 Along Axes C4 to C2/A1 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41921 | 41925 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0853 | Form Work for Retaining Wall from B3 to B5/A15 from Level -11 to 7.20 as shown in attached sketch | Form Work | Retaining Wall |  |  | 41926 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0854 | Diaphragm Wall Geotextile 1st Layer from Level -7.20 up to Level -2.5 Along Axes C3 to C1/A1 | Insulation | Diaphragm Wall |  |  | 41920 | 41921 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0855 | Release of Upper Strut About East-Side | Strut | Strut |  |  | 41921 | 41923 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0856 | Inspection of Hunger for Piles No. H(45-46-47-64-65-66-67-68-69-70-71-88-89-90-91-93-94-95-114-115-117-116)& E(104-105-106-107-108-109-110-111-112-113-114-116-103) | Pile Hunger | Piles |  |  | 41921 | 41923 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0857 | Geotextile 1st Layer for Water Proofing of Retaining Wall From Axes A7 to A15/C1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41921 | 41926 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0858 | Pouring Epoxy for Piles at Section 09 No E(103-112-113-114-115-116-117-118-119-120-121-122-123-124-125-126-127-128-129-130-131-132-133-135-136-105-111-109) as shown in attached sketch | Epoxy | Piles |  |  | 41921 | 41923 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0859 | Geotextile 2nd Layer for Water Proofing of Retaining Wall From Level -7.20 to 2.50 From Axes A1 to A3/C1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41921 | 41925 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0860 | Test PVC for Water Proofing of Retaining Wall From Level -7.20 to 2.50 from Axes C1 to C2/A1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41921 | 41926 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0861 | Pouring Epoxy for Piles at Section 10 NoH(118-117-113-114-115) as shown in attached sketch | Epoxy | Piles |  |  | 41921 | 41923 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0862 | Form Work Dismantle for Axes C3 to C9/A1 to A3 as shown in attached sketch | Removing Form Work | Slab |  |  | 41921 | 41924 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0863 | Diaphragm Wall Geotextile 1st Layer from Level -7.20 to Level -2.50 Along Axes C1 to C2/A1 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41921 | 41925 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0864 | Diaphragm Wall Geotextile 1st Layer from Level -7.20 to Level -2.50 Along Axes A1 to A3/C1 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41921 | 41926 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0865 | Diaphragm Wall Geotextile 2nd Layer from Level -7.20 to Level -2.50 Along Axes C1 to C2/A1 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41921 | 41926 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0866 | Test PVC Membrane Sheet from Level -7.20 to Level -2.50 Along Axes C4 to C2/A1 as shown in attached sketch | Insulation |  |  |  | 41921 | 41925 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0867 | Test PVC Membrane Sheet from Level -7.20 to Level -2.50 Along Axes A1 to A3/C1 as shown in attached sketch | Insulation |  |  |  | 41921 | 41925 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0868 | Form Work for Raft Section 8 as shown in attached sketch | Form Work | Raft |  |  | 41894 | 41895 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0869 | Steel Reinforcement Top Layer and Dowels for Raft Section 8 as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41923 | 41924 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0870 | Installation for Re-Injectable Hose and Injection Pipe for Raft Section 8 as shown in attached sketch | Insulation | Raft |  |  | 41923 | 41925 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0871 | Check level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41923 | 41923 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0872 | Holes and Dowels Fixation at Raft Section 9 as shown in attached sketch | Dowels | Raft |  |  | 41923 | 41926 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0873 | Release of Upper Strut About North-Side | Strut | Strut |  |  | 41923 | 41924 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0874 | PVC test for Retaining Wall for Water Proofing from level -9.00 to -5.00 at Axes from A7 to A15/C1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41923 | 41926 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0875 | Geotextile 2nd Layer for Retaining Wall for Water Proofing from level -9.00 to -5.00 at Axes from A7 to A15/C1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41923 | 41927 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0876 | Geotextile 1st Layer for Retaining Wall Water Proofing from level -9.00 to -5.00 at Axes from B2 to B5/A15 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41923 | 41925 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0877 | Geotextile 1st Layer for Retaining Wall Water Proofing from level -9.00 to -5.00 at Axes from A7 toA15/C1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41923 | 41925 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0878 | Surface Preparation for R.C Raft Water Proofing at Section 20 as shown in attached sketch | Insulation | Raft |  |  | 41923 | 41924 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0879 | Steel Reinforcement for Raft Water Proofing Axes from C4 to B1/A1 from level -7.20 to -3.80 as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41923 | 41924 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0880 | Installation for Injection Pipe and Re-Injectable Hose at Retaining Wall of Basement 1 from Axes C4 to B1/A1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41924 | 41924 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0881 | Form Work for Retaining Wall at Basement 1 From Axes C4 to B1/A1 as shown in attached sketch | Form Work | Retaining Wall |  |  | 41926 | 41927 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0882 | Steel Reinforcement Bottom Layer for Raft Foundation at Section 9 as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41924 | 41925 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0883 | Steel Reinforcement for Retaining Wall Axes from C4 to B1/A1 from level -7.20 to -3.80 as shown in attached sketch | Steel Reinforcement | Retaining Wall |  |  | 41924 | 41925 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0884 | Steel Reinforcement Bottom Layer for Raft Section 19 as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41925 | 41927 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0885 | Steel Reinforcement Bottom Layer for Raft Section 10 as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41925 | 41927 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0886 | Geotextile 1st Layer for Diaphragm Wall Water Proofing from level -9.00 to -4.50 at Axes from B1 to B3/A15 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41924 | 41925 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0887 | PVC Test for Diaphragm Wall Water Proofing from level -9.00 to -4.50 at Axes from B1 to B3/A15 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41925 | 41926 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0888 | Geotextile 2nd Layer for Diaphragm Wall Water Proofing from level -9.00 to -4.50 at Axes from B1 to B3/A15 as shown in attached sketch | Insulation | Diaphragm Wall |  |  | 41924 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0889 | Release of Upper Strut About North-Side as shown in attached sketch | Strut | Strut |  |  | 41924 | 41927 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0890 | Form Work for B2 Roof Slab -7.20 for Section 5B-1 as shown in attached sketch | Form Work | Slab |  |  | 41924 | 41925 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0891 | Dowels Fixation for Piles No. H(328-326-339-338) as shown in attached sketch | Dowels | Piles |  |  | 41925 | 41928 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0892 | Pouring Epoxy for Piles No. H(303-304-305-306-307-308-313-314-315-316-317-318) as shown in attached sketch | Epoxy | Piles |  |  | 41926 | 41927 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0893 | Steel Reinforcement for Column C1 Axes B16/A3 from level -7.20 up to -3.80 as shown in attached sketch | Steel Reinforcement | Column |  |  | 41925 | 41927 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0894 | Form Work for Column C1 Axes B16/A3 from level -7.20 up to -3.80 as shown in attached sketch | Form Work | Column |  |  | 41926 | 41927 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0895 | Form Work for Shear Wall 2 Axes C10/A3 from level -7.20 up to -3.80 as shown in attached sketch | Form Work | SHW |  |  | 41926 | 41927 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0896 | Steel Reinforcement for Shear Wall 2 Axes C10/A3 from level -7.20 up to -3.80 as shown in attached sketch | Steel Reinforcement | SHW |  |  | 41926 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0897 | Steel Reinforcement for Retaining Wall Axes B9 to B10/A15 from level -11 up to -3.80 as shown in attached sketch | Steel Reinforcement | Retaining Wall |  |  | 41925 | 41927 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0898 | Form Work for Retaining Wall Axes B9 to B10/A15 from level -11 up to -3.80 as shown in attached sketch | Form Work | Retaining Wall |  |  | 41926 | 41927 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0899 | Surface Preparation of Diaphragm Wall for Retaining Wall Water Proofing up to level -2.50 at Axes C9 to B17/A1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41926 | 41927 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0900 | Geotextile 1st Layer for R.C Raft Water Proofing up to level -2.50 at Section 23 as shown in attached sketch | Insulation | Raft |  |  | 41926 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0901 | Pouring Epoxy for Piles No E(134-137-138-139-140-141-142-143-144-145-146-147-148149-150) as shown in attached sketch as shown in attached sketch | Epoxy | Piles |  |  | 41926 | 41927 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0902 | PVC Test for Section 23 as shown in attached sketch | Insulation |  |  |  | 41926 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0903 | Geotextile 2nd Layer for Section 23 as shown in attached sketch | Insulation |  |  |  | 41926 | 41928 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0904 | Steel Reinforcement Bottom Layer for Remaining of Raft Foundation at Section 9 as shown in attached sketch | Steel Reinforcement | Raft |  |  | 41926 | 41927 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0905 | Steel Reinforcement for Retaining Wall Axes B1 to C1/A1& A1 to A3/C1 as shown in attached sketch | Steel Reinforcement | Retaining Wall |  |  | 41926 | 41927 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0906 | Form Work for Retaining Wall Axes B1 to C1/A1& A1 to A3/C1 as shown in attached sketch | Form Work | Retaining Wall |  |  | 41928 | 41930 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0907 | Installation of Re-Injectable Hose and Injection Pipe for Retaining Wall Axes B1 to C1/A1& A1 to A3/C1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41926 | 41926 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0908 | Steel Reinforcement Bottom Layer for B2 Roof Slab -7.20 Section 5B-1 as shown in attached sketch | Steel Reinforcement | Slab |  |  | 41926 | 41928 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0909 | Drilling and Fixation for Core 8 Starter Bar for B2 Roof Slab -7.20 as shown in attached sketch | Dowels | Core |  |  | 41926 | 41927 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0910 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0911 | Steel Reinforcement for Raft Top Layer and Dowels of Section 9 | Steel Reinforcement | Raft |  |  | 41927 | 41930 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0912 | Steel Reinforcement for Raft Top Layer and Dowels of Section 19 | Steel Reinforcement | Raft |  |  | 41927 | 41931 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0913 | Steel Reinforcement for Raft Top Layer and Dowels of Section 10 | Steel Reinforcement | Raft |  |  | 41927 | 41930 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0914 | Installation for Injection Pipe and Re-Injectable Hose of Raft Section 10 | Insulation | Raft |  |  | 41927 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0915 | Installation for Injection Pipe and Re-Injectable Hose of Raft Section 19 | Insulation | Raft |  |  | 41927 | 41931 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0916 | Installation for Injection Pipe and Re-Injectable Hose of Raft Section 9 | Insulation | Raft |  |  | 41927 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0917 | Inspection of Holes and Dowels Fixation at B2 Roof | Dowels |  |  |  | 41927 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0918 | Geotextile 1st Layer of Retaining Wall Water Proofing up to Level -2.5 Section 14 Axes B9 to B13/A15 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41928 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0919 | PVC Test of Retaining Wall Water Proofing up to Level -2.5 Section 14 Axes B9 to B13/A15 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41928 | 41931 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0920 | Geotextile 2nd Layer of Retaining Wall Water Proofing up to Level -2.5 Section 14 Axes B9 to B13/A15 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41928 | 41931 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0921 | Geotextile 1st Layer of Retaining Wall Water Proofing up to Level -2.5 Section 14 Axes C9 to B17/A1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41928 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0922 | PVC Test of Retaining Wall Water Proofing up to Level -2.5 Section 14 Axes C9 to B17/A1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41928 | 41931 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0923 | Geotextile 2nd Layer of Retaining Wall Water Proofing up to Level -2.5 Section 14 Axes C9 to B17/A1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41928 | 41932 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0924 | Form Work for Retaining Wall From -11 to -7.20 Axes A7 to A10/C1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41928 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0925 | Steel Reinforcement for Retaining Wall From -11 to -7.20 Axes A7 to A10/C1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41928 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0926 | Geotextile 1st Layer for Retaining Wall Water Proofing up to Level -2.50 at Axe C7 to C9/A1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41928 | 41930 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0927 | PVC Test for Retaining Wall Water Proofing up to Level -2.50 at Axe C7 to C9/A1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41928 | 41931 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0928 | Geotextile 2nd Layer for Retaining Wall Water Proofing up to Level -2.50 at Axe C7 to C9/A1 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41928 | 41932 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0929 | Check Level and Location of P.C form Work Axes B17-B14/A12-A4 as shown in attached sketch | Survey | P.C |  |  | 41928 | 41930 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0930 | Check the level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41928 | 41931 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0931 | Steel Reinforcement for Retaining Wall Axes A10 to A13/C1 From Level -11 to 7.20 as shown in attached sketch | Steel Reinforcement | Retaining Wall |  |  | 41928 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0932 | Form Work for Retaining Wall Axes A10 to A13/C1 From Level -11 to 7.20 as shown in attached sketch | Form Work | Retaining Wall |  |  | 41928 | 41933 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0933 | Installation of Re-Injectable Hose and Injection Pipe for Retaining Wall Axes A10 to A13/C1 From Level -11 to 7.20 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41928 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0934 | Installation of Re-Injectable Hose and Injection Pipe for Retaining Wall Axes A10 to A7/C1 From Level -11 to 7.20 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41928 | 41928 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0935 | Fixation of Column CC5 Axes C9/A3 From Level -4.8 to +1.7 as shown in attached sketch | Column Fixation | Column |  |  | 41928 | 41930 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0936 | Fixation of Column CC6 Axes C11/A3 From Level -6 to -1 as shown in attached sketch | Column Fixation | Column |  |  | 41928 | 41930 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0937 | Form Work for B2 Roof -7.2 Section 5C-1 as shown in attached sketch | Form Work |  |  |  | 41928 | 41930 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0938 | Form Work for B1 Roof -3.8 Axes C6 to C3/A1 to A3 as shown in attached sketch | Form Work |  |  |  | 41928 | 41931 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0939 | Form Work for Raft Section 9 as shown in attached sketch | Form Work | Raft |  |  | 41928 | 41930 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0940 | Form Work for Raft Section 10 as shown in attached sketch | Form Work | Raft |  |  | 41928 | 41930 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0941 | Form Work for Raft Section 19 as shown in attached sketch | Form Work | Raft |  |  | 41928 | 41932 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0942 | Inspection for installation of diagonal struts at north side | Strut | Strut |  |  | 41934 | 41951 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0943 | Form Work Removal for B2 Roof -7.2 Section 5C-1 as shown in attached sketch | Removing Form Work | Slab |  |  | 41930 | 41932 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0944 | Form Work for B2 Roof Slab -7.2 Axes B9 to B4/A12-A15 as shown in attached sketch | Form Work | Slab |  |  | 41930 | 41932 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0945 | Steel Reinforcement Top Layer for B2 Roof Slab -7.2 Axes B2 to B4/A3-A6 as shown in attached sketch | Steel Reinforcement | Slab |  |  | 41930 | 41932 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0946 | Installation of Re-Injectable Hose and Injection Pipe for B2 Roof Slab -7.2 Axes B9 to B4/A12-A15 as shown in attached sketch | Insulation | Slab |  |  | 41930
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0947 | Surface Preparation and Treatment and Casting Grout for Pile Head at Piles No. H(336-337-338-339-340-341-351-352-353-354-355-356-359-360-361-362-363-364-375-376) as shown in attached sketch | Grout | Piles |  |  | 41930 | 41932 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0948 | Dowels Fixation for Piles No. H(337-339-340-353-354-355-360-361-362-364-375-376) as shown in attached sketch | Dowels | Piles |  |  | 41930 | 41932 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0949 | Steel Reinforcement for Shear Wall 2* Level -7.2 to -3.8 as shown in attached sketch | Steel Reinforcement | SHW |  |  | 41930 | 41931 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0950 | Form Work for Shear Wall 2* Level -7.2 to -3.8 as shown in attached sketch | Form Work | SHW |  |  | 41930 | 41931 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0951 | Installation of Re-Injectable Hose and Injection Pipe Level -7.2 to -3.8 for Shear Wall 2* as shown in attached sketch | Insulation | SHW |  |  | 41930 | 41932 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0952 | Steel Reinforcement for Retaining Wall Axes A13 to A15/C1 & B2 to B4/A15 From -11 to -7.2 as shown in attached sketch | Steel Reinforcement | Retaining Wall |  |  | 41930 | 41931 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0953 | Form Work for Retaining Wall Axes A13 to A15/C1 & B2 to B4/A15 From -11 to -7.2 as shown in attached sketch | Form Work | Retaining Wall |  |  | 41930 | 41932 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0954 | Installation of Re-Injectable Hose and Injection Pipe for Retaining Wall Axes A13 to A15/C1 & B2 to B4/A15 From -11 to -7.2 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41930 | 41931 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0955 | Release of Upper Strut North Side | Strut | Strut |  |  | 41932 | 41934 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0956 | Installation of Re-Injectable Hose and Injection Pipe for B2 Roof Slab -7.20 Section 5B-1 as shown in attached sketch | Insulation | Slab |  |  | 41931 | 41940 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0957 | Form Work for B1 Roof Slab -3.8 at Section 3B Axes C3 to C1/A1 to A4 | Form Work | Slab |  |  | 41931 | 41932 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0958 | Surface Preparation and Treatment and Casting Grout for Pile Head at Piles No. H(377-378-379-380-382-383-404) | Grout | Piles |  |  | 41931 | 41932 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0959 | Dowels Fixation for Piles No. H(337-378-379-380) | Dowels | Piles |  |  | 41931 | 41932 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0960 | Steel Reinforcement for Core 7 Level -3.80 to -7.20 | Steel Reinforcement | Core |  |  | 41931 | 41932 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0961 | Steel Reinforcement for Core 5 Level -11 to -7.2 | Steel Reinforcement | Core |  |  | 41932 | 41934 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0962 | Form Work Dismantle for B2 Roof Slab Section 3B | Removing Form Work | Slab |  |  | 41931 | 41932 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0963 | Form Work for Core 7 Level -11 to -7.20 | Form Work | Core |  |  | 41932 | 41934 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0964 | Steel Reinforcement Bottom Layer for B2 Roof Slab -7.2 Axes B9 to B4/A12-A15 as shown in attached sketch | Steel Reinforcement | Slab |  |  | 41932 | 41934 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0965 | Steel Reinforcement for Retaining Wall Axes C6 to C9/A1 Level -7.2 to -3.8 | Steel Reinforcement | Retaining Wall |  |  | 41932 | 41934 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0966 | Geotextile 2nd Layer of Retaining Wall Water Proofing up to Level -2.5 Section 14 Axes B9 to B14/A15 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41932 | 41942 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0967 | PVC Test of Retaining Wall Water Proofing up to Level -2.5 Section 14 Axes B9 to B14/A15 as shown in attached sketch | Insulation | Retaining Wall |  |  | 41932 | 41942 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0968 | Steel Reinforcement for 3 Columns Type C1 Axes (B4/A5,A4) & (B6/A4) Level -11 to -7.2 | Steel Reinforcement | Column |  |  | 41932 | 41934 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0969 | Form Work for 4 Columns Type C1 Axes (B4/A5,A4,A6) & (B6/A4) Level -11 to -7.2 | Form Work | Column |  |  | 41932 | 41934 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0970 | Installation of Injection Pipe and Re-Injectable Hose for Retaining Wall Axes C6 to C9/A1 Level -7.2 to -3.8 | Insulation | Retaining Wall |  |  | 41932 | 41940 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0971 | Form Work for Retaining Wall Axes C6 to C9/A1 Level -7.2 to -3.8 | Form Work | Retaining Wall |  |  | 41932 | 41934 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0972 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0973 | Steel Reinforcement for Retaining Wall for Axes C9 to C11/A1 from Level -7.2 to -3.8 | Steel Reinforcement | Retaining Wall |  |  | 41934 | 41935 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0974 | Form Work for Retaining Wall for Axes C9 to C11/A1 from Level -7.2 to -3.8 | Form Work | Retaining Wall |  |  | 41934 | 41935 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0975 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0976 | Form Work for Column C1 at Axes B4/A6 from Level -11 to -7.2 | Form Work | Column |  |  | 41934 | 41935 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0977 | Steel Reinforcement for Core 6 from Level -11 to -7.2 | Steel Reinforcement | Core |  |  | 41942 | 41944 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0978 | Form Work for B2 Roof Slab Level -7.2 Axis A7 to A12/C1 to B3 | Form Work | Slab |  |  | 41934 | 41935 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0979 | Steel Reinforcement Bottom Layer at B1 Roof Slab Level -3.8 Axis C1 to B6/A1 to A3 | Steel Reinforcement | Slab |  |  | 41934 | 41935 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0980 | Surface Preparation For R.C Raft Water Proofing Section 20 & 26 | Insulation | Raft |  |  | 41934 | 41940 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0981 | Geotextile 1st Layer For R.C Raft Water Proofing Section 20 & 26 | Insulation | Raft |  |  | 41934 | 41940 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0982 | PVC Test For R.C Raft Water Proofing Section 20 & 26 | Insulation | Raft |  |  | 41934 | 41940 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0983 | Geotextile 2nd Layer For R.C Raft Water Proofing Section 20 & 26 | Insulation | Raft |  |  | 41934 | 41940 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0984 | Surface Preparation for Retaining Wall Water Proofing up to level -2.5 Axis A3 to A7/C1 | Insulation | Retaining Wall |  |  | 41934 | 41942 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0985 | Surface Preparation for Retaining Wall Water Proofing up to level -2.5 Axis B17 to (between B19&B20)/A1 | Insulation | Retaining Wall |  |  | 41934 | 41940 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0986 | Geotextile 1st Layer for Retaining Wall Water Proofing up to level -2.5 Axis B17 to (between B19&B20)/A1 | Insulation | Retaining Wall |  |  | 41934 | 41940 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0987 | PVC Test for Retaining Wall Water Proofing up to level -2.5 Axis B17 to (between B19&B20)/A1 | Insulation | Retaining Wall |  |  | 41934 | 41940 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0988 | Geotextile 2nd Layer for Retaining Wall Water Proofing up to level -2.5 Axis B17 to (between B19&B20)/A1 | Insulation | Retaining Wall |  |  | 41934 | 41940 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0989 | Installation of Injection Pipe and Re-Injectable Hose for Retaining Wall for Axes C9 to C11/A1 from Level -7.2 to -3.8 | Insulation | Retaining Wall |  |  | 41934 | 41940 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0990 | Installation of 2 Composite Column CC7 at Axis A4/A10,A11 from Level -11 to -3 | Column | Column |  |  | 41934 | 41938 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0991 | Steel Reinforcement for Retaining Wall from Axis C11 to B18/A1 from Level -7.2 to -3.8 | Steel Reinforcement | Retaining Wall |  |  | 41934 | 41935 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0992 | Form Work for Retaining Wall from Axis C11 to B18/A1 from Level -7.2 to -3.8 | Form Work | Retaining Wall |  |  | 41934 | 41935 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0993 | Installation of Injection Pipe and Re-Injectable Hose for Retaining Wall from Axis C11 to B18/A1 from Level -7.2 to -3.8 | Insulation | Retaining Wall |  |  | 41934 | 41940 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0994 | Steel Reinforcement for 7 Columns Type C1 Axis (A4/B1,2,3) (A5/B2,3) (A6/B2,3) Level -7.2 to -3.8 | Steel Reinforcement | Column |  |  | 41934 | 41935 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0995 | Form Work for Core 5 at Second Basement | Form Work | Core |  |  | 41934 | 41938 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0996 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0997 | Repair Pile No. H(376) | pile | Piles |  |  | 41934 | 41935 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0998 | Steel Reinforcement Core 6 at B1 | Steel Reinforcement | Core |  |  | 41934 | 41938 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-0999 | Steel Reinforcement for Column C1 Axis (B6/A5) for level -11 to 7.20 | Steel Reinforcement | Column |  |  | 41935 | 41935 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1000 | Form Work for Column C1 Axis (B6/A5) for level -11 to 7.20 | Form Work | Column |  |  | 41935 | 41935 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1001 | Top Reinforcement for B2 Roof Slab -7.20 From B9 to B4/A12 to A15 | Steel Reinforcement | Slab |  |  | 41935 | 41938 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1002 | Form Work for B2 Roof Slab -7.20 from Axis A11 to A15/B4 to C1 | Form Work | Slab |  |  | 41935 | 41935 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1003 | Installation of Injection Pipe and Re-Injectable Hose for B2 Roof Slab -7.20 Axis B9 to B14/A12 to A15 | Insulation | Slab |  |  | 41935 | 41938 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1004 | Steel Reinforcement for Shear Wall 3*Axis C8/A2,A3 from level -7.20 to -3.80 | Steel Reinforcement | SHW |  |  | 41935 | 41935 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1005 | Form Work for Shear Wall 3*Axis C8/A2,A3 from level -7.20 to -3.80 | Form Work | SHW |  |  | 41935 | 41938 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1006 | Form Work for 7 Columns Type C1 Axis (A4/B1,2,3) (A5/B2,3) (A6/B2,3) Level -7.2 to -3.8 | Form Work | Column |  |  | 41935 | 41938 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1007 | Steel Reinforcement for Core 3 at level -11 to -7.20 | Steel Reinforcement | Core |  |  | 41935 | 41938 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1008 | Steel Reinforcement Bottom Layer for B2 Roof Slab -7.2 Axis A7 to A11/C1 to B3 | Steel Reinforcement | Slab |  |  | 41935 | 41938 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1009 | Check Level and Location of P.C form Work as shown in attached sketch | Survey | P.C |  |  | 41938 | 41941 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1010 | Steel Reinforcement for bottom layer B2 roof slab (-7.20) part of section #5A from axis B5 to C1/A11 to A15 | Steel Reinforcement | Slab |  |  | 41938 | 41940 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1011 | Form Work for B1 Roof Slab (-3.80) part of section # 3A from axis C5 to C6/ A1 to A3 | Form Work | Slab |  |  | 41938 | 41940 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1012 | Steel Reinforcement for Retaining Wall Basement 1 from Axis B17 to B19/A1 | Steel Reinforcement | Retaining Wall |  |  | 41938 | 41940 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1013 | Form Work for Retaining Wall at Basement 1 from Axis B17 to B19/A1 | Form Work | Retaining Wall |  |  | 41938 | 41939 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1014 | Installation for Re-Injectable Hose and Injection Pipe of Retaining Wall Basement 1 from Axis B17 to B19/A1 | Insulation | Retaining Wall |  |  | 41938 | 41939 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1015 | Check Level and Location of P.C form Work as shown in attached sketch | Survey | P.C |  |  | 41938 | 41941 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1016 | Check the location and level of screed as shown in attached sketch | Survey | Screed |  |  | 41938 | 41941 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1017 | Inspection of holes and dowels fixation for pile No. H(383-385-386-387-388-373-367-366-365-343-342) | Dowels | Piles |  |  | 41938 | 41939 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1018 | Steel Reinforcement for 2 columns type C6 on xis (B6/A13), (B9/A12)& type C1 on axis (B8/A12) | Steel Reinforcement | Column |  |  | 41938 | 41940 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1019 | Form Work for Core 6 of Basement 1 from Level -7.20 to -3.80 | Form Work | Core |  |  | 41939 | 41942 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1020 | Steel Reinforcement Work for Core 4 at Level -11 to -7.20 | Steel Reinforcement | Core |  |  | 41939 | 41940 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1021 | Geotextile 1st Layer up to Level -2.50 from A3 to A6/C1 | Insulation |  |  |  | 41939 | 41945 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1022 | Surface Preparation and Treatment and Casting Grout for Pile Head at Piles No. H(374-373-372-365-366-367-348-342-343-391-390-389-388-387-385-384-349-350-386) | Grout | Piles |  |  | 41939 | 41941 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1023 | Installation of Re-Injectable Hose for Roof Slab Basement 1 at Section 3A | Insulation | Slab |  |  | 41939 | 41942 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1024 | Steel Reinforcement Top Layer for Roof Slab Basement 1 at Section 3A | Steel Reinforcement | Slab |  |  | 41939 | 41941 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1025 | Form Work for Roof Slab Basement 1 at Section 4B from Axis C7 to C8 | Form Work | Slab |  |  | 41939 | 41940 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1026 | Form Work for Roof Slab Basement 2 at Section 5B-2 from Axis A3 to A5/B3 to B6 | Form Work | Slab |  |  | 41939 | 41940 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1027 | Form Work Dismantle for Slab Basement 2 Section 5B-1 as shown in attached sketch | Removing Form Work | Slab |  |  | 41940 | 41945 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1028 | Surface Preparation and Casting Epoxy for Pile Head at Piles No. H(313-314-315-316-317-328-329-330-331-332-336-337-338-339-340-352-353-354-355-356-359-360-361-362-377-378-379-380) | Epoxy | Piles |  |  | 41940 | 41942 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1029 | Form Work for Columns Type C6(B6/A13), C1(B6/A12), C6(B9/A12), C7(B8/A12), C7(B8/A12) level -7.2 to -3.8 | Form Work | Column |  |  | 41940 | 41940 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1030 | Steel Reinforcement Top Layer for B2 Roof Slab -7.20 at Section 5A-2 | Steel Reinforcement | Slab |  |  | 41940 | 41942 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1031 | Installation of Injection Pipe and Re-Injectable Hose for B2 Roof Slab -7.20 at Section 5A-2 | Insulation | Slab |  |  | 41940 | 41942 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1032 | Dowels Fixation for Piles No. H(301-319-320-324-344) | Dowels | Piles |  |  | 41941 | 41941 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1033 | Steel Reinforcement Bottom Layer for B2 Roof Slab -7.20 for Section 5B-2 | Steel Reinforcement | Slab |  |  | 41941 | 41944 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1034 | Surface Preparation and Treatment and Casting Grout for Pile Head at Piles No. H(300-301-302-319-320-321-324-325-326-344) | Grout | Piles |  |  | 41941 | 41944 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1035 | Installation for Shear Connectors for Column CC5 from Level -4 up to +1.70 | Shear Connectors | Column |  |  | 41941 | 41942 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1036 | Casting Grout Under Base Plate for Composite Columns 3(CC7) Axis B4/A9,10,11 and 2(CC1) Axis B9/A10 | Composite Columns | Column |  |  | 41941 | 41944 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1037 | Installation for Shear Connectors for Column CC6 from Level -6 up to -1 | Shear Connectors | Column |  |  | 41941 | 41942 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1038 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1039 | Surface Preparation and Casting Epoxy for Pile Head at Piles No. H(335-357-358-381) | Epoxy | Piles |  |  | 41942 | 41944 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1040 | Form Work for Core 3 from Level -11.00 to -7.20 | Form Work | Core |  |  | 41942 | 41942 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1041 | Steel Reinforcement for CC5/C9 and CC6/C11 from Level -7.20 to -3.80 | Steel Reinforcement |  |  |  | 41942 | 41944 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1042 | Form Work for CC5/C9 and CC6/C11 from Level -7.20 to -3.80 | Form Work |  |  |  | 41942 | 41944 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1043 | Dowels Fixation for Piles No. H(297-296-295-276-278) | Dowels | Piles |  |  | 41942 | 41945 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1044 | Surface Preparation and Treatment and Casting Grout for Pile Head at Piles No. H(276-277-278-279-296-295) | Grout | Piles |  |  | 41942 | 41945 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1045 | Surface Preparation for Water Proofing Section 26 and Part of Section 24 | Insulation |  |  |  | 41942 | 41945 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1046 | Form Work for Core 4 from Level -11 to -7.20 | Form Work | Core |  |  | 41944 | 41946 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1047 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1048 | Installation for Shear Connectors CC7-1 Axis B4/A8,9,10,11 | Shear Connectors | Column |  |  | 41944 | 41945 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1049 | Casting Grout for 1 Column CC7 Axis A8/B4 and 2 Columns CC1 Axis B9/A10 at Second Basement | Grout | Column |  |  | 41944 | 41945 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1050 | Steel Reinforcement Bottom Layer for B1 Roof Slab -3.80 at Section 3B | Steel Reinforcement | Slab |  |  | 41944 | 41946 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1051 | Installation of Injection Pipe and Re-Injectable Hose for B1 Roof Slab -3.80 at Section 3B | Insulation | Slab |  |  | 41944 | 41948 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1052 | Form Work Dismantling for B2 Roof (-7.20) Section 5A-1 | Removing Form Work | Slab | -7.20 | B2 | 41945 | 41947 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1053 | Surface Preparation of Diaphragm Wall for Water Proofing up to Level -2.5 at Axis from A6 to A10/C1 | Insulation | Diaphragm Wall |  |  | 41944 | 41948 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1054 | Geotextile 1st Layer for R.C Raft Water Proofing Section 26 | Insulation | Raft |  |  | 41944 | 41952 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1055 | Dowels Fixation for Piles No. H(273) | Dowels | Piles |  |  | 41944 | 41947 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1056 | Surface Preparation and Treatment and Casting Grout for Pile Head at Piles No. H(271-272-273) | Grout | Piles |  |  | 41944 | 41947 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1057 | Surface Preparation and Casting Epoxy for Pile Head at Piles No. H(276-277-295-297-300-318-319-320-321-324-325-326-327-341-342-343-344-348-349-350-351-364-365-366-367-372-373-374-375-376-382-383-384-385-386-387-388-389-390-391-404) | Epoxy | Piles |  |  | 41944 | 41955 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1058 | PVC Test for Retaining Wall Water Proofing up to Level -2.50 at Axis C1/A3,A6 | Insulation | Retaining Wall |  |  | 41944 | 41945 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1059 | Geotextile 2nd Layer for Retaining Wall Water Proofing up to Level -2.50 at Axis C1/A3,A6 | Insulation | Retaining Wall |  |  | 41944 | 41948 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1060 | PVC test for Retaining Wall Water Proofing up to Level -2.50 at Axis A15/B9 to B13 | Insulation | Retaining Wall |  |  | 41944 | 41945 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1061 | Geotextile 2nd Layer for Retaining Wall Water Proofing up to Level -2.50 at Axis A15/B9 to B13 | Insulation | Retaining Wall |  |  | 41944 | 41952 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1062 | Form Work for 4 Columns CC7 Axis B4/A11,10,9,8 from Level -11 to -7.20 | Form Work | Column |  |  | 41945 | 41946 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1063 | Steel Reinforcement Work for 4 Columns CC7 Axis B4/A11,10,9,8 from Level -11 to -7.20 | Steel Reinforcement | Column |  |  | 41945 | 41946 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1064 | Form Work for 2 Columns C* Axis from A9 to A10/B3 to B4 from Level -11 to -7.20 | Form Work | Column |  |  | 41945 | 41946 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1065 | Steel Reinforcement Work for 2 Columns C* Axis from A9 to A10/B3 to B4 from Level -11 to -7.20 | Steel Reinforcement | Column |  |  | 41945 | 41946 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1066 | Form Work for 3 Columns C1 Axis B3/A11,10,8 from Level -7.20 to -3.80 | Form Work | Column |  |  | 41945 | 41946 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1067 | Steel Reinforcement Work for 3 Columns C1 Axis B3/A11,10,8 from Level -7.20 to -3.80 | Steel Reinforcement | Column |  |  | 41945 | 41946 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1068 | Form Work for Shear Wall 7 at Hotel from Level -3.80 to -1.1 | Form Work | SHW |  |  | 41945 | 41947 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1069 | Steel Reinforcement Work for Shear Wall 7 at Hotel from Level -3.80 to +1.1 | Steel Reinforcement | SHW |  |  | 41945 | 41945 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1070 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1071 | Steel Reinforcement Top Layer for B2 Roof Slab -7.20 at Section 5B-2 | Steel Reinforcement | Slab |  |  | 41945 | 41946 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1072 | Form Work for B1 Roof Slab -3.8 from Axis C8 to C10/A1 to A3 | Form Work | Slab |  |  | 41945 | 41945 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1073 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1074 | Inspection of Repair for Piles No. H(278-296-302) | pile | Piles |  |  | 41945 | 41948 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1075 | Top Layer Steel Reinforcement Work for Slab 3B Axis A1 to A3/C1 to C3 at B1 | Steel Reinforcement | Slab |  |  | 41946 | 41947 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1076 | Form Work for Slab Section 4A at Axis C10 to B19/A1 to A3 at B2 | Form Work | Slab |  |  | 41946 | 41947 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1077 | Installation of Injection Pipe and Re-Injectable Hose at Retainng Wall Construction Joint for Slab 3B on Axis A1 to A3/C1 to C3 at B1 | Insulation | Retaining Wall |  |  | 41946 | 41948 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1078 | Bottom Layer Steel Reinforcement Work for Slab 4B (C5 to C9)/(A1 to A3) | Steel Reinforcement | Slab |  |  | 41946 | 41948 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1079 | Steel Reinforcement for Shear Wall 5* Axis C8/A2-A3 at B.O.H | Steel Reinforcement | SHW |  |  | 41946 | 41948 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1080 | Form Work for Slab Section 1 Axis from A8 to A12/B3 to B6 | Form Work | Slab |  |  | 41947 | 41948 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1081 | Form Work for Shear Wall 6 Axis C4/A2 to A3 at B.O.H | Form Work | SHW |  |  | 41946 | 41948 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1082 | Steel Reinforcement for Shear wall 6 Axis C4/A2 to A3 at B.O.H | Steel Reinforcement | SHW |  |  | 41946 | 41947 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1083 | Form Work for Column C1 Axis B2/A7 at B1 | Form Work | Column |  |  | 41946 | 41947 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1084 | Steel Reinforcement for Column C1 Axis B2/A7 at B1 | Steel Reinforcement | Column |  |  | 41946 | 41947 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1085 | Steel Reinforcement for Ramp Beam Section 4B Axis B8 to B11/ A3 Level -7.20 to -3.80 | Steel Reinforcement | Beam |  |  | 41946 | 41947 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1086 | Steel Reinforcement for Column C6 Axis B9/A12 at B1 | Steel Reinforcement | Column |  |  | 41946 | 41948 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1087 | Form Work for Column C6 Axis B9/A12 at B1 | Steel Reinforcement | Column |  |  | 41946 | 41951 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1088 | Check level and location of P.C form work | Survey | P.C |  |  | 41946 | 41947 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1089 | Check level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41948 | 41951 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1090 | Check the Level and Location of P.C Form Work as shown in attached sketch | Survey | P.C |  |  | 41949 | 41949 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1091 | Bottom layer steel reinforcement work for slab C1 at B2 roof slab Level -7.20 axis A12 to A8/B3 to B6 | Steel Reinforcement | Slab |  |  | 41948 | 41952 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1092 | Removal of form work slab 3A at B1 roof slab level -3.80 | Removing Form Work | Slab |  |  | 41948 | 41952 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1093 | Steel reinforcement for beam of slab at B1 roof slab Level -3.80 axis C7 to C10/A3 | Steel Reinforcement | Slab |  |  | 41948 | 41951 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1094 | Top layer Steel reinforcement work for slab 4B at B1 roof slab Level -3.80 | Steel Reinforcement | Slab |  |  | 41948 | 41951 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1095 | steel reinforcement for 4 columns axis B4/A4-A5 & B6/A4-A5 at B1 Level -7.20 to -3.80 | Steel Reinforcement | Column |  |  | 41948 | 41951 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1096 | form work for 4 columns axis B4/A4-A5 & B6/A4-A5 at B1 Level -7.20 to -3.80 | Form Work | Column |  |  | 41948 | 41953 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1097 | form work for shear wall 5* axis C5/A2 to A3 at B.O.H level -3.80 to +1.10 | Form Work | SHW |  |  | 41948 | 41951 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1098 | steel reinforcement for retaining wall axis A3 to A5/C1 at B1 level -7.20 to -3.80 | Steel Reinforcement | Retaining Wall |  |  | 41948 | 41951 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1099 | form work for retaining wall axis A3 to A5/C1 level -7.20 to -3.80 | Form Work | Retaining Wall |  |  | 41948 | 41951 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1100 | Istallation of injection pipe and re-injectable hose for retaining wall A3 to A5/C1 | Insulation | Retaining Wall |  |  | 41948 | 41952 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1101 | steel reinforcement for core 8 axis B1/A1,2,3 | Steel Reinforcement | Core |  |  | 41948 | 41951 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1102 | installation and casting grout for composite columns CC3 at B2 level -11 axis B9/A11 | Grout | Column |  |  | 41949 | 41951 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1103 | steel reinforcement for sum pit 2 composite columns CC7E at B2 level -11 on axis A6/B5,6 | Steel Reinforcement | Column |  |  | 41948 | 41951 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1104 | top layer steel reinforcement work for slab section 1 at B2 roof slab level -7.20 axis A12 to A8/B3 to B6 | Steel Reinforcement | Slab |  |  | 41949 | 41951 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1105 | Installation of injection pipe and re-injectable hose at retaining wall construction joint for slab section 4B at B1 roof slab level -3.80 axis B8 to B12/A1 to A3 | Insulation | Retaining Wall |  |  | 41949 | 41951 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1106 | steel reinforcement for retaining wall axis C5 to C3/A1 | Steel Reinforcement | Retaining Wall | -2.50 to 1.10 | BOH | 41955 | 41961 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1107 | Installation for shear connector for compstite column CC3 at B2 axis B9/A11 | Shear Connectors | Column |  |  | 41949 | 41951 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1108 | Installation and casting grout for 2 composite columns CC7E at B2 level -11 axis A6/B5,6 | Grout | Column |  |  | 41949 | 41951 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1109 | Installation for shear connector for 2 composite columns CC7E level -11.00 axis A6/B5,6 | Shear Connectors | Column |  |  | 41949 | 41951 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1110 | installation for shear connector for 4 composite columns CC1 at B2 level -11 axis B13/A11,9,10 | Shear Connectors | Column |  |  | 41949 | 41951 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1111 | Installation and casting grout for 2 composite columns CC1 at B2 level -11 axis B13/A11 | Grout | Column |  |  | 41949 | 41951 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1112 | steel reinforcement for shear wall 8 at B.O.H level -3.80 to +1.10 | Steel Reinforcement | SHW |  |  | 41949 | 41952 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1113 | installation of geotextile 1st layer to proceed with PVC membrane installation for diphrgm wall level -2.50 axis A6 to A7/C1 | Insulation | SHW |  |  | 41949 | 41951 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1114 | installation and test of PVC membrane to proceed with geotextile 2nd layer for diaphragm wall level -2.50 axis A6 to A7/C1 | Insulation | Diaphragm Wall |  |  | 41949 | 41952 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1115 | installation and test of geotextile membrane to proceed with geotextile 2nd layer for diaphragm wall level -2.50 axis A6 to A7/C1 | Insulation | Diaphragm Wall |  |  | 41949 | 41952 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1116 | surface preparation for P.C to proceed with geotextile 1st layer at part of section 24 level -13.50 to -12.50 axis B12,13/A6 to A8 | Insulation | P.C |  |  | 41949 | 41956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1117 | piles cutting level, surface preparation to proceed with casting grout section 24 level -13.50 H(144-202-203-222-223-224-227-228-229) | pile | Piles |  |  | 41949 | 41952 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1118 | Drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation H(229-228-227-223-222-202) | Dowels | Piles |  |  | 41949 | 41951 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1119 | piles surface preparation to proceed with epoxy application section 24 piles H(271-272-273-276-277) | Epoxy | Piles |  |  | 41949 | 41954 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1120 | Piles surface preparation to proceed with epoxy application section 2 piles H(300-301-302-297-287-296-295-276-277-273-272-271) | Epoxy | Piles |  |  | 41949 | 41952 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1121 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation H(253-254-297-175-145-137-136-139) | Dowels | Piles |  |  | 41949 | 41951 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1122 | Surface preparation for RC raft water proofing axis B4 to B9/A8 to A5 Level -13.5 | Insulation | Raft |  |  | 41949 | 41953 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1123 | form work for slab removal section 5A-2 at B2 level -7.20 axis A7 to A15/C1 to B4 | Removing Form Work | Slab |  |  | 41951 | 41952 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1124 | installation of injection pipe and re-injectable hose for retaining wall A to A5/C1 | Insulation | Retaining Wall |  |  | 41948
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1125 | bottom layer steel reinforcement work for slab 4A at B1 level -3.80 axis B12 to B19/A1 to A4 | Steel Reinforcement | Slab | -3.80 | B1 | 41951 | 41960 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1126 | Steel reinforcement work for core 7 at B.O.H axis C7/A2-A3 Level -3.80 to +1.10 | Steel Reinforcement | Core |  |  | 41951 | 41953 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1127 | Form work for core 8 at B.O.H Level -3.80 to +1.10 Axis B1/A1-A2-A3 | Form Work | Core |  |  | 41951 | 41952 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1128 | bottom layers steel reinforcement work for raft section 26 level -11.00 axis B14,15/A6,7,8,9 | Steel Reinforcement | Raft |  |  | 41951 | 41952 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1129 | bottom layer steel reinforcement work for raft section 20 level -11.00 axis A10,11/B14,15 | Steel Reinforcement | Raft |  |  | 41951 | 41952 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1130 | steel reinforcement for retaining wall at b1 level -7.20 to -3.80 axis B9 to B13/A15 | Steel Reinforcement | Retaining Wall |  |  | 41951 | 41953 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1131 | Inspection of injection pipe and re-injectable hose for retaining wall at B1 level -7.20 to -3.80 axis B9 to B13/A15 | Insulation | Retaining Wall |  |  | 41951 | 41953 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1132 | steel reinforcement for 2 columns CC7E at B2 level -11 to -7.20 axis B5/A6 & B6/A6 | Steel Reinforcement | Column |  |  | 41951 | 41952 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1133 | form work for 2 columns CC7E at B2 level -11 to -7.20 axis B5/A6 & B6/A6 | Form Work | Column |  |  | 41951 | 41953 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1134 | form work for shear wall 8 at B.O.H level -3.80 to +1.10 axis C2/A2 to A3 | Form Work | SHW |  |  | 41951 | 41953 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1135 | form work for core 7 level -3.80 to +1.10 axis A2 to A3/B10 to B12 | Form Work | Core |  |  | 41952 | 41956 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1136 | installation of horizontal geotextile 2nd layer to proceed with protection screed pouring at section 13,14&19 level -13.50 to -12.50 axis B8 to B14/A14 to A9 | Insulation | Screed |  |  | 41952 | 41960 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1137 | installation and test of PVC membrane and water bars to proceed with geotextile 2nd layer at section 13,24&19 level -13.50 axis B8 to B14/A14 | Insulation |  |  |  | 41952 | 41956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1138 | installation of horizontal geotextile 1st layer under raft to proceed with PVC membrane installation section 13,24&19 level -13.50 axis B8 to B14/A6 to A9 | Insulation | Raft |  |  | 41952 | 41953 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1139 | steel reinforcement for pits CC3&CC1 level -11 axis B9/A10-A11 | Steel Reinforcement |  |  |  | 41952 | 41953 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1140 | Piles surface preparation to proceed with epoxy application for piles No. H(144-145-137-138-139-116-252-253-254-247-248-249-227-228-229-222-223-224-202-203-194-175-164) | Epoxy | Piles |  |  | 41953 | 41958 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1141 | form work for B2 roof slab section 1C level -7.20 axis A5 to A9/B3 to B9 | Form Work | Slab |  |  | 41953 | 41954 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1142 | installation of injection pipe and re-injectable hose at retaining wall construction joint for slab section 4A at B1 roof slab level -3.80 axis B12 to B19/A1 to A4 | Insulation | Retaining Wall |  |  | 41953 | 41956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1143 | top layer steel reinforcement work, dowels and final inspection for B1 roof slab 4A level -3.80 axis B12 to B19/A1 to A4 | Steel Reinforcement | Slab | -3.80 | B1 | 41953 | 41960 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1144 | form work for B1 roof slab 5B-1 level -3.80 axis A3 to A7/C1 to B3 | Form Work | Slab |  |  | 41953 | 41954 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1145 | Check level and location of screed as shown in attached sketch | Survey | Screed |  |  | 41954 | 41956 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1146 | check level and location of P.C form work | Survey | P.C |  |  | 41954 | 41955 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1147 | steel reinforcement for composite columns CC3& CC1 | Steel Reinforcement | Column |  |  | 41953 | 41954 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1148 | form work for retaining walls at B1 level -7.20 to -3.80 axis B9 to B13/A15 | Form Work | Retaining Wall |  | B1 | 41953 | 41954 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1149 | steel reinforcement for pits CC1 at axis B13/A11 level -11 | Steel Reinforcement |  |  |  | 41953 | 41954 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1150 | steel reinforcement for shear wall 3 B.O.H level -3.80 to +1.10 | Steel Reinforcement | SHW |  | BOH | 41954 | 41956 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1151 | Release for upper anchor about south east | Anchor | Anchor |  |  | 41954 | 41956 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1152 | Release for upper struts about south east | Strut | Strut | -7.20 |  | 41954 | 41956 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1153 | top layer steel reinforcement work, dowels and final inspection for section 1C at B2 roof slab level -7.20 axis B3 to B6.A5 to A9 | Steel Reinforcement | Slab |  | B2 | 41954 | 41956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1154 | bottom layer steel reinforcement work for slab section 1C at B2 roof slab level -7.20 axis B3 to B6/A5 to A9 | Steel Reinforcement | Slab |  | B2 | 41954 | 41956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1155 | form work for slab section 5B-2 at B1 roof slab level -3.80 axis A3 to A5/B3 to B6 | Form Work | Slab |  | B1 | 41954 | 41956 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1156 | inspection for hunger cutting for piles No. H(193-194-223-224-228-226-247-249-230-251-252-253-274-273-271-275-276-278-279-280-297-292-299-322) | pile | Piles |  |  | 41954 | 41958 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1157 | top layer steel reinforcement work, dowels, embedded items and final inspection for raft 20&26 level -11 axis A6 to A12/B19 to B16 | Steel Reinforcement | Raft |  |  | 41954 | 41956 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1158 | form work for raft 20&26 level -11 axis A6 to A12/B14 to B16 | Form Work | Raft |  |  | 41954 | 41956 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1159 | installationof injection pipe and re-injectable hose at raft construction joints section 20&26 level -11 axis A6 to A12/B14 to B16 | Insulation | Raft |  |  | 41954 | 41956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1160 | installation of injection pipe and re-injectable hose for retaining wall at B1 level -7.20 to -3.80 axis A5 to A7/C1 | Insulation | Retaining Wall |  | B1 | 41954 | 41956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1161 | steel reinforcement for retaining wall at B1 level -7.20 to -3.80 axis A5 to A7/C1 | Steel Reinforcement | Retaining Wall |  | B1 | 41954 | 41958 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1162 | form work for retaining wall at B1 level -7.20 to -3.80 axis A5 to A7/C1 | Form Work | Retaining Wall |  | B1 | 41954 | 41956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1163 | form work for columns CC1& CC3 at B2 level -11 to -7.20 axis B9/A10-A11 | Form Work | Column |  | B2 | 41954 | 41956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1164 | form work for shear wall 3 at BOH level -3.80 to +1.10 | Form Work | SHW |  | BOH | 41954 | 41956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1165 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation for Piles No. H(201-195-196-173-174-165-167-143-140-142-168) | Dowels | Piles |  |  | 41954 | 41956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1166 | piles cutting level, surface preparation to proceed with casting grout at section 24 piles No. H(201-195-173-174-165-166-167-168-169-140-141-142-143-196) | Grout | Piles |  |  | 41954 | 41956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1167 | steel reinforcement for retaining wall axis C5 to C3/A1 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 41955 | 41956 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1168 | form work for slab part of section 5B-1&5B-2 at B1 level -3.80 | Form Work | Slab | -3.80 | B1 | 41954 | 41956 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1169 | piles cutting level, surface preparation to proceed with casting grout E(151-152-153-154-155-156-157) | Grout | Piles | -12.50 | Raft | 41955 | 41959 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1170 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation piles No. E(156-155) | Dowels | Piles |  |  | 41955 | 41958 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1171 | surface preparation for P.C to proceed with geotextile 1st layer at part of section 23 level -13.50 to -12.50 axis B9 to B11/A9 to A5 | Insulation | P.C | -13.50 to -12.50 |  | 41955 | 41959 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1172 | form work for shear wall 5 at BOH level -3.80 to +1.10 axis C5/A3 to A2 | Form Work | SHW |  | BOH | 41955 | 41958 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1173 | Steel reinforcement for shear wall 5 at BOH level -3.80 to +1.10 axis C5/A2 to A3 | Steel Reinforcement | SHW |  | BOH | 41955 | 41958 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1174 | form work removal for section 3B at B1 level -3.80 axis C1 to C3/A1 to A3 | Removing Form Work | Slab |  | B1 | 41955 | 41958 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1175 | form work removal section 5B-2 at B2 level -7.20 axis B3 to B6/A3 to A5 | Removing Form Work | Slab |  | B2 | 41955 | 41956 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1176 | installation and test of PVC membrane and water bars to proceed with geotextile 2nd layer at section 24 | Insulation |  | -13.50 to -12.50 | Under Raft | 41956 | 41960 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1177 | Installation of horizontal geotextile 2nd layer to proceed with protection screed pouring at section 24 level -13.50 to -12.50 axis A5 to A6/b9 to B10 | Insulation | Screed | -13.50 to -12.50 | Under Raft | 41956 | 41960 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1178 | installation of horizontal geotextile 1st layer under raft to proceed with PVC membrane installation section 24 level -13.50 to -12.50 axis A5 to A6/b9 to B10 | Insulation | Raft | -13.50 to -12.50 | Under Raft | 41956 | 41960 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1179 | piles cutting level, surface preparation to proceed with casting grout section 2 Piles No. H(170-171-172)& E(158-159-160-163) | Grout | Piles |  |  | 41956 | 41958 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1180 | Drilling depth, diameter for missing/shot reinforcement of piles to proceed with dowels fixation Piles No. H(170-171)& E(158) | Dowels | Piles |  |  | 41956 | 41958 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1181 | Piles surface preparation to proceed with epoxy application for Piles No. H(201-195-173-174-165-166-167-168-169-140-141-142-143-196) | Epoxy | Piles | -13.5 to -12.5 | Under Raft | 41956 | 41960 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1182 | casting grout under base plate 2 columns CC9 at B2 axis B6/A11& B8/A11 | Grout | Column |  | B2 | 41956 | 41958 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1183 | casting grout under base plate column CC1 at B2 axis B13/A10 | Grout | Column |  | B2 | 41956 | 41958 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1184 | form work for column CC1 at B2 axis B13/A11 | Form Work | Column | -7.20 | B2 | 41956 | 41958 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1185 | steel reinforcement for column CC1 at B2 axis B13/A11 | Steel Reinforcement | Column |  | B2 | 41956 | 41958 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1186 | form work for retaining wall at BOH axis C3 to C5/A1 | Form Work | Retaining Wall | -3.80 to 1.10 | BOH | 41956 | 41956 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1187 | inspection for shear connectors column CC7/1 at B1 axis B4/A11-A10-A9 | Shear Connectors | Column |  | B1 | 41956 | 41958 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1188 | inspection for shear connectors column CC1/1 at B2 axis B13/A10 | Shear Connectors | Column |  | B2 | 41956 | 41963 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1189 | form work for 4 columns CC7 Axis B4/A11,10,9,8 from Level -7.20 to -3.80 | Form Work | Column | -7.20 to -3.80 | B1 | 41958 | 41960 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1190 | steel reingorcement work for 4 columns CC7 Axis B4/A11,10,9,8 from Level -7.20 to -3.80 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41958 | 41959 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1191 | steel reinforcement for pits for CC9 at raft level -11 axis A11/B8, B6 | Steel Reinforcement | Raft | -11.00 | Raft | 41958 | 41959 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1192 | bottom steel reinforcement work for slab 5B-2 at B1 level -3.80 axis B3 to B6/A3 to A5 | Steel Reinforcement | Slab | -3.80 | B1 | 41958 | 41959 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1193 | steel reinforcement for column C4 at B1 level -7.20 to -3.80 axis B1, B2/A8, A7 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41958 | 41960 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1194 | form work for column C4 at B1 level -7.20 to -3.80 axis B1, B2/A8, A7 | Form Work | Column | -7.20 to -3.80 | B1 | 41958 | 41960 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1195 | fixation for shear connector for two columns CC9 at B2 level -11 to -7.20 axis A11/B6-B8 | Shear Connectors | Column | -11.00 to -7.20 | B2 | 41958 | 41959 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1196 | Piles Surface Preparation to proceed with Epoxy Application H(170-171-172)& E(151-152-153-154-155-156-157-158-159-163) | Epoxy | Piles | -13.50 to -12.50 | Under Raft | 41958 | 41962 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1197 | installation and test of PVC membrane and water bars to proceed with geotextile 2nd layer at part of section 23 at -13.5 to -12.5 | Insulation |  |  |  | 41958 | 41961 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1198 | installation of horizontal geotextile 1st layer under raft to proceed with PVC membrane installation for part of section 23 level -13.50 to -12.50 axis B9,B10/A4,A5 | Insulation | Raft | -13.50 to -12.50 | Under Raft | 41958 | 41959 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1199 | installation of horizontal geotextile 2nd layer to proceed with protection screed pouring for part of section 23 level -13.50 to -12.50 axis B9,B10/A4,A5 | Insulation | Screed |  |  | 41958 | 41961 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1200 | surface peparation for P.C to proceed with geotextile 1st layer for part of section 23 level -13.50 to -12.50 axis B10/A4, A5 | Insulation | P.C | -13.50 to -12.50 | Under Raft | 41958 | 41959 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1201 | form work for 2 columns CC9 at B2 level -11 to -7.5 axis A11/B6-B8 | Form Work | Column | -11.00 to -7.20 | B2 | 41959 | 41961 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1202 | Steel reinforcement work for 2 columns CC9 at B2 level -11 to -7.5 axis A11/B6-B8 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41959 | 41961 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1203 | steel reinforcement work for 2 columns CC3, CC1 at B2 level -11 to -7.20 axis B9/A11-A10 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41959 | 41960 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1204 | form work for 2 columns CC3, CC1 at B2 level -11 to -7.20 axis B9/A11-A10 | Form Work | Column | -11.00 to -7.20 | B2 | 41959 | 41963 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1205 | steel reinforcement for 1 column C1 at B1 level -7.20 to -3.80 axis B4/A6 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41959 | 41960 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1206 | form work for 1 column C1 at B1 level -7.20 to -3.80 axis B4/A6 | Form Work | Column | -7.20 to -3.80 | B1 | 41959 | 41960 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1207 | Steel reinforcement for shear wall 2* at BOH level -3.80 to +1.10 axis C8/A2-A3 | Steel Reinforcement | SHW | -3.80 to 1.10 | BOH | 41959 | 41960 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1208 | form work for shear wall 2* at BOH level -3.80 to +1.10 axis C8/A2-A3 | Form Work | SHW | -3.80 to 1.10 | BOH | 41959 | 41960 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1209 | form work for stair case No. 3 at B2 level -11 to -7.20 at Core 5 AXIS B6 to B7/A8 to A9 | Form Work | Stair | -11.00 to -7.20 | B2 | 41959 | 41961 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1210 | form work for stair case No. 5 at B2 level -11 to -7.20 at Core 5 axis B6 to B7/A8 to A9 | Form Work | Stair | -11.00 to -7.20 | B2 | 41959 | 41961 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1211 | form work removal for section 4B axis C6 to C9/A1 to A3 | Removing Form Work | Slab | -3.80 | B1 | 41960 | 41963 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1212 | form work removal for section 5A-3 | Removing Form Work | Slab | -7.20 | B2 | 41960 | 41963 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1213 | steel reinforcement work fore core 6 axis A1,2/B15 to 17 | Steel Reinforcement | Core | -7.20 to -3.80 | BOH | 41960 | 41962 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1214 | top layer steel reinforcement work, dowels and final inspection for slab 5B-2 axis A3 to A5/B3 to B6 | Steel Reinforcement | Slab | -3.80 | B1 | 41960 | 41961 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1215 | form work stair case 6 axis B15 to B17/A2 | Form Work | Stair | -11.00 to -7.20 | B2 | 41961 | 41963 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1216 | steel reinforcement 4 columns C4 axis between B3&B2/A13 and B2/ (B10 to B11), (B9 to B10), (B8to B7) | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41960 | 41961 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1217 | form work 4 columns C4 axis between B3&B2/A13 and B2/ (B10 to B11), (B9 to B10), (B8to B7) | Form Work | Column | -7.20 to -3.80 | B1 | 41960 | 41961 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1218 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation No. H(197) at section 23 | Dowels | Piles | -13.5 to -12.5 | Raft | 41960 | 41961 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1219 | piles cutting level, surface preparation to proceed with casting grout No. H(197-198-199-200) | Grout | Piles | -13.5 to -12.5 | Raft | 41960 | 41961 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1220 | steel reinforcement work for column CC1 axis B13/A11 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41960 | 41962 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1221 | form work for column CC1 axis B13/A11 | Form Work | Column | -11.00 to -7.20 | B2 | 41960 | 41962 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1222 | concrete repair of 3 columns CC&& 1 column C1 axis (B4/A6-A10-A11)& (B10/A12) | Repair | Column | -11.00 to -7.20 | B2 | 41961 | 41968 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1223 | steel reinforcement for column C1 axis B14/A12 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41961 | 41962 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1224 | form work for column C1 axis B14/A12 | Form Work | Column | -11.00 to -7.20 | B2 | 41961 | 41962 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1225 | steel reinforcement work for core 8 axis A1 to A3/B1 to B2 | Steel Reinforcement | Core | -20 to 3.60 | Ground Floor | 41961 | 41962 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1226 | steel reinforcement for retaining wall axis C5 to C6/A1 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 41961 | 41962 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1227 | steel reinforcement for retaining wall axis C3 to B1/A1 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 41961 | 41962 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1228 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1229 | steel reinforcement 2 columns C* axis between B3-B4/between A10-A9 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41961 | 41962 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1230 | form work 2 columns C* axis between B3-B4/between A10-A9 | Form Work | Column | -7.20 to -3.80 | B1 | 41961 | 41962 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1231 | steel reinforcement 2 columns C3 axis A13/B3-B4 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41961 | 41963 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1232 | form work 2 columns C3 axis A13/B3-B4 | Form Work | Column | -7.20 to -3.80 | B1 | 41961 | 41963 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1233 | installation and test of PVC membrane and water bars to proceed with geotextile 2nd layer axis B10 to B11/A5 to A4 | Insulation |  | -13.50 to -12.50 | Under Raft | 41961 | 41962 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1234 | installation of horizontal geotextile 2nd layer to proceed with protection screed pouring axis B10 to B11/A5 to A4 | Insulation | Screed | -13.50 to -12.50 | Under Raft | 41961 | 41962 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1235 | Piles surface preparation to proceed with epoxy application No. H(200-199-198-197) | Epoxy | Piles | -13.50 to -12.50 | Under Raft | 41961 | 41963 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1236 | fixation of shear connector composite column CC1 and CC9 axis B10/A11& B13/A10 | Shear Connectors | Column | -11.00 to -7.20 | B2 | 41961 | 41963 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1237 | Casting grout for composite column CC1 and CC9 axis B10/A11& B13/A10 | Grout | Column | -11.00 to -7.20 | B2 | 41961 | 41962 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1238 | form work for slab section 1A | Form Work | Slab | -7.20 | B2 | 41962 | 41963 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1239 | form work for retaining wall axis C5 to C6/A1 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 41962 | 41963 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1240 | installation torque of Composite Column CC7E/2 axis B5/A6 | Composite Columns | Column | -3.80 to ±0.5 | BOH | 41963 | 41963 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1241 | installation torque of Composite column CC7E/2 axis B6/A6 | Composite Columns | Column | -3.80 to ±0.5 | BOH | 41963 | 41963 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1242 | Installation for shear connectors for column CC7E/2 axis B5/A6 | Shear Connectors | Column | -3.80 to ±0.5 | BOH | 41962 | 41963 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1243 | Installation for shear connectors for column CC7E/2 axis B6/A6 | Shear Connectors | Column | -3.80 to ±0.5 | BOH | 41962 | 41963 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1244 | steel reinforcement work for pit at CC9 axis B10/A11 | Steel Reinforcement |  | -3.80 to ±0.5 | BOH | 41962 | 41963 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1245 | steel reinforcement for column CC1 axis B13/A10 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41962 | 41963 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1246 | form work for column CC1 axis B13/A10 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41962 | 41963 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1247 | steel reinforcement for pit at column CC1 axis B13/A10 | Steel Reinforcement | Column | -3.80 to -2.50 | BOH | 41962 | 41963 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1248 | form work for retaining wall axis C3 o B1/A1 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 41962 | 41966 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1249 | Form work for core 6 axis B15 to B17/A1 to A2 | Form Work | Core | -3.80 to 1.10 | BOH | 41963 | 41966 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1250 | check level and location of P.C form work axis B9-B12/A7-A3 | Survey | P.C | -13.73 |  | 41965 | 41968 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1251 | Form Work for column CC9 axis B10/A11 | Form Work | Column | -11.00 to -7.20 | B2 | 41963 | 41966 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1252 | steel reinforcement for 3 columns axis B3/A5,A4 & B4/A4 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41963 | 41966 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1253 | form work for 3 columns C1 axis B6/A4, B4/A5, B4/A4 | Form Work | Column | -7.20 to -3.80 | B1 | 41963 | 41966 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1254 | steel reinforcement for 1 column CC9 axis B10/A11 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41963 | 41966 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1255 | casting grout for column CC7E axis B8/A6 | Grout | Column | -11.00 to -7.20 | B2 | 41963 | 41966 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1256 | steel reinforcement for stair case No. 12 axis A1-A2/B1-B2 | Steel Reinforcement | Stair | -11.00 to -7.20 | B2 | 41963 | 41966 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1257 | form work for column CC7E axis B5 - B6/A6 | Form Work | Column | -7.20 to -3.80 | B1 | 41963 | 41966 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1258 | steel reinfrcement for column CC7E axis B5, B6/A6 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41963 | 41966 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1259 | form work for core 8 axis B1/A1-A2-A3 | Form Work | Core | -0.20 to 3.20 | Ground Floor | 41965 | 41966 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1260 | bottom layer steel reinforcement work for slab section 1A axis B5 to B9/A8 to A12 | Steel Reinforcement | Slab | -7.20 | B2 | 41965 | 41968 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1261 | bottom layer steel reinforcement work for raft section 13 axis A1 to A4/B1 to B2 | Steel Reinforcement | Raft | -11.00 | Raft | 41965 | 41966 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1262 | drilling depth, diameter for missing/ short reinforcement of piles to proceed with dowels fixation piles E9161-162-164) | Dowels | Piles | -13.50 to -12.50 | Under Raft | 41965 | 41966 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1263 | piles cutting level, surface preparation to proceed with casting grout E(160-161-162-164) | Grout | Piles | -13.50 to -12.50 | Under Raft | 41965 | 41966 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1264 | form work for retaining wall axis C3 to B1/A1 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 41965 | 41968 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1265 | steel Reinforcement for retaining wall axis C6 to B12/A1 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 41965 | 41966 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1266 | piles surface preparation to proceed with epoxy application E(160-161-162-164) | Epoxy | Piles |  |  | 41966 | 41968 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1267 | form work for slab part of section 5A-1, 5A-2, 5A-3 and 1C axis A6 to A13/B2 to B4 | Form Work | Slab | -3.80 | B1 | 41966 | 41969 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1268 | form work for retaining wall axis C6 to C9/A1 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 41966 | 41968 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1269 | casting grout under base plate for 1 column CC7 axis B8/A6 | Grout | Column | -11.00 to -7.20 | B2 | 41966 | 41967 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1270 | steel reinforcement for shear wall 2 axis C10/A2 | Steel Reinforcement | SHW | -3.80 to 1.10 | BOH | 41966 | 41969 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1271 | steel reinforcement for 1 column C1 axis B16/A3 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41966 | 41968 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1272 | surface preparation for diaphragm wall water proofing axis A7 to A14/C1 | Insulation | Diaphragm Wall | -5.00 to -2.50 | Under Raft | 41966 | 41968 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1273 | installation of geotextile 1st layer to proceed with PVC membrane installation at section 23 | Insulation |  |  |  | 41966 | 41968 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1274 | top layer steel reinforcement work, dowels and final inspection for slab section 1A axis B5 to B9/A8 to A12 | Steel Reinforcement | Slab | -7.20 | B2 | 41967 | 41969 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1275 | installation of geotextile 2nd layer to proceed with retaining wall reinforcement axis A7 to A13/C1 | Insulation | Retaining Wall | -4.5 to -2.5 |  | 41967 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1276 | installation of geotextile 1st layer to proceed with PVC membrane installation for retaining wall axes A7 to A13/C1 | Insulation | Retaining Wall | -4.5 to -2.5 |  | 41967 | 41968 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1277 | installation and test of pvc membrane to proceed with geotextile 2nd layer for diaphragm wall level -4.50 to -2.50 axis A7 to A13/C1 | Insulation | Diaphragm Wall | -4.5 to -2.5 |  | 41967 | 41969 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1278 | release of lower anchor head No. (127-128-129-130-131-132-133-134) | Anchor | Anchor | -8.00 | Above Raft | 41968 | 41973 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1279 | form work for 2 columns C1 axis B16/A3 & B18/A3 | Form Work | Column | -3.80 to 1.10 | BOH | 41968 | 41968 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1280 | installation torque composite column CC9 axis B12/A11 | Composite Columns | Column | -12.00 to -4.80 | B2 | 41967 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1281 | Steel reinforcement for column C5 axis B18/A2 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41967 | 41969 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1282 | Steel reinforcement for column C1 axis B18/A3 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41968 | 41968 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1283 | fixation of shear connector for composite column CC9 axis B12/A11 | Shear Connectors | Column | -7.20 to ±0.50 | B2 | 41967 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1284 | Form work removal section 1C axis A5 to A8/B3 to B6 | Removing Form Work | Slab | -7.20 | B2 | 41967 | 41968 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1285 | form work removal section 4A axis B13 to B19/ A1 to A3 | Removing Form Work | Slab | -3.80 | B1 | 41967 | 41968 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1286 | Check the Level and Location of P.C Form Work as shown in attached sketch | Survey | P.C | -7.20 | B2 | 41968 | 41969 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1287 | form work for raft section 13 axis B7 to B10/A4 to A7 | Form Work | Raft | -11.00 | Raft | 41968 | 41969 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1288 | top layer steel reinforcement work, dowels, embedded items and final inspection for raft 13 axis B7 to B10/A4 to A7 | Steel Reinforcement | Raft | -11.00 | Raft | 41968 | 41969 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1289 | installation of injection pipe and re-injectable hose at raft construction joints section 13 axis A9 to A7/B7 to B10 | Insulation | Raft | -11.00 | Raft | 41968 | 41968 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1290 | piles cutting level, surface preparation to proceed with casting grout for piles No. H(225-226-250)& E(165-166-167-168-172) | Grout | Piles | -13.50 to -12.50 | Under Raft | 41968 | 41969 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1291 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation section 30 piles No. H(225-226-250)& E(168-172) | Dowels | Piles |  |  | 41968 | 41969 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1292 | surface preparation for P.C to proceed with geotextile 1st layer at part of section 23, 30 and 24 | Insulation | P.C | -13.50 to -12.50 | Under Raft | 41968 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1293 | steel reinforcement for column CC1 axis B13/A10 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41968 | 41969 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1294 | Form work for column CC1 west side axis B13/A10 | Form Work | Column | -11.00 to -7.20 | B2 | 41968 | 41969 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1295 | form work for retaining wall axis C6 to C9/A1 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 41968 | 41970 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1296 | installation for 2composite columns CC7 axis B4/A8-A9 | Composite Columns | Column | -3.00 to -6.00 | BOH & GR | 41968 | 41973 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1297 | fixation of shear connectors for composite column CC5 axis C9/A3 | Shear Connectors | Column | 1.10 | BOH | 41968 | 41972 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1298 | Steel reinforcement for column CC5 axis C9/A3 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41968 | 41970 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1299 | fixation of shear connectors for 2 composite columns CC7 axis B4/A8-A9 | Shear Connectors | Column | -3.00 to -6.00 | BOH & GR | 41968 | 41970 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1300 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation H(403-405-406-419)& E(309) | Dowels | Piles | -13.5 to -12.5 | Raft | 41969 | 41970 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1301 | piles cutting level, surface preparation to proceed with casting grout H(401-402-403-405-406-407-419-420)& E(309-310) | Grout | Piles | -13.5 to -12.5 | Raft | 41969 | 41970 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1302 | form work for column C5 axis B18/A2 | Form Work | Column | -3.80 to 1.10 | BOH | 41969 | 41970 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1303 | from work for column CC5 axis C9/A3 | Form Work | Column | -3.80 to 1.10 | BOH | 41969 | 41972 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1304 | installation of geotextile 1st layer to proceed with PVC membrane installation at retaining wall axis A15/B9 to B3 | Insulation | Retaining Wall | -7.20 to -2.50 |  | 41970 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1305 | surface preparation for external diaphragm walls to proceed with geotextile 1st layer axis A15/B9: B3 | Insulation | Diaphragm Wall | -4.5 to -2.5 |  | 41970 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1306 | steel reinforcement for shear wall 2 axis C10/A3 | Steel Reinforcement | SHW | -3.80 to 1.10 | BOH | 41969 | 41970 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1307 | Steel reinforcement for column C1 axis B19/A3 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41969 | 41970 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1308 | from work for shear wall 2 axis C10/A3 | Form Work | SHW | -3.80 to 1.10 | BOH | 41969 | 41970 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1309 | form work for column C1 axis B19/A3 | Form Work | Column | -3.80 to 1.10 | BOH | 41969 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1310 | installation of horizontal geotextile 2nd layer to proceed with protection screed pouring section 23, 24, 30 | Insulation | Screed | -13.5 to -12.5 |  | 41969 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1311 | installation of horizontal geotextile 1st layer under raft to proceed with PVC membrane installation section 23,30,24 | Insulation | Raft | -13.5 to -12.5 |  | 41969 | 41975 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1312 | installation and test of PVC membrane and water bars to proceed with geotextile 2nd layer | Insulation |  | -13.5 to -12.5 |  | 41969 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1313 | steel reinforcement work for stair case 5 | Steel Reinforcement | Stair | -11.00 to -7.20 | B2 | 41970 | 41973 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1314 | steel reinforcement work for stair case 3 | Steel Reinforcement | Stair | -11.00 to -7.20 | B2 | 41970 | 41973 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1315 | installation and test of PVC membrane to proceed with geotextile 2nd layer at retaining wall axis A15/B9 to B3 | Insulation | Retaining Wall | -7.20 to -2.50 |  | 41970 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1316 | installation of geotextile 2nd layer to proceed with retaining wall axis A15/B9 to B3 | Insulation | Retaining Wall | -7.20 to -2.50 |  | 41970 | 41981 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1317 | steel reinforcement for ramp beam axis A7 to A10/B2 | Steel Reinforcement | Beam | -7.20 to -3.80 | B1 | 41972 | 41975 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1318 | installation of injection pipe and re-injectable hose for retaining wall axis A1 to A3/C1 to B1 | Insulation | Retaining Wall | -3.80 to 1.10 | BOH | 41970 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1319 | form work for retaining wall axis A1 to A3/C1 to B1 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 41970 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1320 | steel reinforcement for retaining wall axis A1 to A3/C1 to B1 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 41970 | 41973 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1321 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation | Dowels | Piles |  |  | 41972 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1322 | steel reinforcement for column C1 axis B19/A1 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41970 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1323 | piles cutting level, surface preparation and form work to proceed with casting grout piles No. E(174-175-176-177-178-186-187-190-185-184-180)& H(251-274-275) | Grout | Piles |  |  | 41972 | 41973 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1324 | bottom layer steel reinforcement work for slab axis A5 to A8/B3 to B6 | Steel Reinforcement | Slab | -3.80 | B1 | 41972 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1325 | bottom layer steel reinforcement work for slab section 5B-1 axis A3 to A6/C1 to B3 | Steel Reinforcement | Slab | -3.80 | B1 | 41972 | 41973 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1326 | repair work of retaining wall axis A1 to A4/C1 | Repair | Retaining Wall | -2.50 to 1.10 | BOH | 42000 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1327 | start repair for shear wall 7 axis A2 to A3/C3 | Repair | SHW | -3.80 | B1 | 41983 | 41987 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1328 | Installation of Horizontal Geotextile 1st layer under Raft to proceed with PVC membrane installation at section 30 axis B11 to B14/A3 to A6 | Insulation | Raft | -13.50 to -12.50 | Raft | 42000 | 42003 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1329 | surface preparation for external diaphragm walls to proceed with geotextile 1st layer axis A14 to A15/B2 to B3 | Insulation | Diaphragm Wall | -2.50 |  | 41973 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1330 | installation of horizontal geotextile 1st layer under raft to proceed with PVC membrane installation | Insulation | Raft | -2.50 |  | 41972 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1331 | installation and test of PVC membrane and water bars to proceed with geotextile 2nd layer axis A14 to A15/B2 to B3 | Insulation |  | -2.50 |  | 41972 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1332 | installation of horizontal geotextile 2nd layer to proceed with protection screed pouring | Insulation | Screed | -2.50 |  | 41972 | 41981 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1333 | check level and location of P.C form work axis A3-A7/B10-B13 | Survey | P.C |  |  | 41972 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1334 | steel reinforcement for pit composite columns CC9 axis B12/A11 | Steel Reinforcement | Column | -11.00 | Raft | 41972 | 41974 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1335 | steel reinforcement for pit composite column CC7 axis B8/A6 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41975 | 41975 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1336 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1337 | form work for slab 3A axis C3 to C5/A1 to A3 | Form Work | Slab | 1.10 | BOH | 41973 | 41975 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1338 | bottom layer steel reinforcement work for slab 5A-1 axis A7 to A11/C1 | Steel Reinforcement | Slab | -3.80 | B1 | 41975 | 41975 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1339 | surface preparation for R.C raft water profing at section 30&24 axis B11 to B13/A4 to A9 | Insulation | Raft |  |  | 41973 | 41973 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1340 | surface preparation for R.C raft water profing section 30, 21& 22 axis B16 to B21/A12 to A9 | Insulation | Raft |  |  | 41973 | 41973 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1341 | fixation of shear connector for 2 columns CC9 axis B6-B8/A11 | Shear Connectors | Column | -3.80 to ±0.5 | BOH | 41973 | 41975 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1342 | form work for retaining wall axis C5 to C6/A1 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 41973 | 41974 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1343 | form work for retaining wall axis C9 to B15/A1 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 41975 | 41975 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1344 | steel reinforcement for retaining wall axis C9 to B15/A1 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 41973 | 41975 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1345 | installation for composite 2 composite columns CC9/2 axis B6-B8/A11 | Composite Columns | Column | -3.80 | B1 | 41973 | 41975 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1346 | check level and location of P.C form work axis B3-B14/A7-A4 | Survey | P.C |  |  | 41975 | 41975 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1347 | steel reinforcement for stair case 6 axis B10 to B11/A8 to A9 | Steel Reinforcement | Stair | -11.00 to -7.20 | B2 | 41974 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1348 | steel reinforcement work for core 2 axis B14 to B18/A7 to A10 | Steel Reinforcement | Core | -11.00 to -7.20 | B2 | 41974 | 41976 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1349 | Drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation piles No. H(299-250) | Dowels | Piles |  |  | 41974 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1350 | form work for stair case 1 axis A9 to A10/B3 to B4 | Form Work | Stair | -11.00 to -7.20 | B2 | 41974 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1351 | piles cutting level, surface preparation to proceed with casting grout piles No. H(298-250)& E(188-189) | Insulation | Piles |  |  | 41974 | 41977 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1352 | form work removal for slab section 5B-2 axis B3 to B6/A3 to A5 | Removing Form Work | Slab | -3.80 | B1 | 41975 | 41977 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1353 | installation of injection pipe and re-injectable hose at retaining wall construction joint for slab section 5B-1 axis C1 to B3/A3 to A6 | Insulation | Retaining Wall | -3.80 | B1 | 41974 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1354 | top layer steel reinforcement work, dowels and final inspection for slab section 5B-1 axis C1 to B3/A3 to A6 | Steel Reinforcement | Slab | -3.80 | B1 | 41974 | 41976 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1355 | top layer steel reinforcement work, dowels and final inspection for slab section 1C axis B3 to B6/A5 to A9 | Steel Reinforcement | Slab | -3.80 | B1 | 41974 | 41977 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1356 | form work for slab section 2-1A axis B9 to B13/A8 to A11 | Form Work | Slab | -7.20 | B2 | 41975 | 41977 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1357 | form work for retaining wall axis B1 to C1/A1 and A1 to A3/C1 | Form Work | Retaining Wall | -2.50 to 0.6 | BOH | 41974 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1358 | steel reinforcement for 2 columns CC9 axis B6 to B8/A11 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41975 | 41975 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1359 | installation of injection pipe and re-injectable hose for retaining wall axis A7 to A10/C1 | Insulation | Retaining Wall | -7.20 to -3.80 | B1 | 41974 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1360 | steel reinforcement for retaining wall axis A7 to A10/C1 | Steel Reinforcement | Retaining Wall | -7.20 to -3.80 | B1 | 41974 | 41977 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1361 | form work for columns CC9 axis B6-B8/A11 | Form Work | Column | -7.20 to -3.80 | B1 | 41975 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1362 | steel reinforcement for columns CC7&CC9 axis B8/A6& B12/A11 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41975 | 41975 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1363 | form work for columns CC7 and CC9 axis B8/A6& B12/A11 | Form Work | Column | -11.00 to -7.20 | B2 | 41975 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1364 | top layer steel reinforcement work, dowels and final inspection for slab 5A-1 | Steel Reinforcement | Slab | -3.80 | B1 | 41975 | 41980 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1365 | final inspection steel reinforcement work for ramp beam axis A11 to A13/B2 to B3 | Steel Reinforcement | Beam | -3.80 to 1.10 | B1 | 41975 | 41977 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1366 | steel reinforcement for retaining wall axis B15 to B19/A1 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 41975 | 41977 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1367 | bottom layer steel reinforcement for section 31 axis A5 to A7/B13 to B16 | Steel Reinforcement |  |  | Raft | 42000 | 42002 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1368 | steel reinforcement for retaining wall axis B1 to C1/A1 and A1 to A3/C1 | Steel Reinforcement | Retaining Wall | -2.50 to 1.10 | BOH | 41975 | 41976 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1369 | torque for column CC7 axis B4/A11 to A8 | Composite Columns | Column | -3.00 to 6.00 | Ground Floor | 41975 | 41980 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1370 | form work for column C1 axis B8/A4 | Form Work | Column | -11.00 to -7.20 | B2 | 41975 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1371 | form work for column C1 axis B8/A5 | Form Work | Column | -11.00 to -7.20 | B2 | 41975 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1372 | steel reinforcement for column C1 axis B8/A5 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41975 | 41976 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1373 | steel reinforcement for column C1 axis B8/A4 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41975 | 41976 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1374 | casting grout for column CC1 axis B9/A8 | Grout | Column | -12 |  | 41975 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1375 | installation for column CC1 (torque) axis B9/A8 | Composite Columns | Column | -6.00 to zero |  | 41989 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1376 | steel reinforcement for retaining walls axis B9 to B6/A15 | Steel Reinforcement | Retaining Wall | -7.20 to -3.80 | B1 | 41976 | 41980 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1377 | installation for columns CC1/2 axis B9/A10 | Composite Columns | Column | -12 |  | 41976 | 41980 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1378 | installation and casting grout for 2 composite columns CC7/1 axsi B9/A6 | Grout | Column | -12.00 |  | 41976 | 41980 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1379 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation piles No.(191) | Dowels | Piles | -13.50 to -12.50 |  | 41976 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1380 | piles cutting level, surface preparation and form work to proceed with casting grout piles No. E(168-191-192) | Grout | Piles | -13.50 to -12.50 |  | 41976 | 41977 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1381 | piles surface preparation to proceed with epoxy application piles No. E(160-161-162-164-165-166-167-174-175-176-190)& H(225-226-250-251-274-275) | Surface Preparation | Piles |  |  | 41976 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1382 | steel reinforcement work for core 5 axis B6 to B9/A8 to A10 | Steel Reinforcement | Core | -7.20 to -3.80 | B1 | 41976 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1383 | check level and location of P.C form work axis B13 to B14/A4 to A7 | Survey | P.C |  |  | 41976 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1384 | steel reinforcement work for pit composite column CC1 axis B9/A8 | Steel Reinforcement | Column |  | Raft | 41976 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1385 | form work for part of section 3A axis C5 to C6/A1 to A3 | Form Work |  | 1.10 | BOH | 41976 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1386 | form work for core 2 axis A8,9,10/B14,15 | Form Work | Core | -11.00 to -7.20 | B2 | 41977 | 41977 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1387 | check level and location of P.C form work axis B19-B21/A9-A12 | Survey | P.C |  |  | 41977 | 41977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1388 | form work for retaining wall axis B15 to B19A1 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 41982 | 41983 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1389 | Form work for retaining wall axis C9 to B15/A1 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 41977 | 41980 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1390 | Torque for 2 columns CC3 axis B9/A11 | Composite Columns | Column | -6.00 to Zero | B1/BOH | 41977 | 41980 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1391 | installation of injection pipe and re-injectable hose for retaining wall axis B9 to B6/A15 | Insulation | Retaining Wall | -7.20 to -3.80 | B1 | 41977 | 41981 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1392 | bottom layer steel reinforcement work for slab section 3A axis C3 to C6/A1 to A3 | Steel Reinforcement | Slab | 1.10 | BOH | 41980 | 41981 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1393 | steel reinforcement for beam B9 of slab B1 section 5A-2& 5A-3 axis B3 to B6/A11 to A13 | Steel Reinforcement | Slab | -3.80 | B1 | 41979 | 41983 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1394 | check level and location of screed axis B8-B7/A5-A4 | Survey | Screed |  |  | 41979 | 41980 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1395 | form work removal section 1A axis B6 to B9/A9 to A11 | Removing Form Work | Slab | -7.20 | B2 | 41979 | 41980 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1396 | steel reinforcement for stair case 1 axis A10/B3 | Steel Reinforcement | Stair | -11.00 to -7.20 | B2 | 41979 | 41980 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1397 | piles cutting level, surface preparation and form work to proceed with casting grout piles No. E(291-289-288-287-286)& H(421) | Grout | Piles | -13.50 to -12.50 |  | 41979 | 41981 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1398 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation | Dowels | Piles | -13.50 to -12.50 |  | 41979 | 41980 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1399 | piles surface preparation to proceed with epoxy application piles No. H(298-299)& E(191-192) | Epoxy | Piles | -13.50 to 12.50 |  | 41979 | 41981 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1400 | form work for slab section 2-1A (Remainng) axis B12 to B13/A8 to A11 | Form Work | Slab | -7.20 | B2 | 41980 | 41981 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1401 | check location and level of P.C form work axis B19-B21/A9-A12 | Survey | P.C |  |  | 41980 | 41981 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1402 | form work for 1 column C3 axis B8/A4 | Form Work | Column | -11.00 to -7.20 | B2 | 41980 | 41981 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1403 | steel reinfrcement for column C3 axis B8/A4 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41980 | 41981 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1404 | form work for column CC1 axis B9/A8 | Form Work | Column | -11.00 to -7.20 | B2 | 41980 | 41981 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1405 | steel reinforcement for column CC1 axis B9/A8 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41980 | 41981 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1406 | steel reinforcement for pit for column CC7 axis B9/A6 | Steel Reinforcement | Column | -11.00 | Raft | 41980 | 41981 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1407 | installation of injection pipe and re-injectable hose for retaining wall axis A3 to A6/C1 | Insulation | Retaining Wall | -3.80 to 1.10 | BOH | 41980 | 41989 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1408 | steel reinforcement for column CC7 axis B4/A8 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41980 | 41982 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1409 | fixation of shear connector for column CC7 axis B4/A8 | Shear Connectors | Column | 1.10 to ± 0.5 | Ground Floor | 41980 | 41982 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1410 | steel reinforcement for column C1 axis B4/A6 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41980 | 41982 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1411 | steel reinforcement for retaining wall axis A3 to A6/C1 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 41982 | 41983 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1412 | inspection of holes and dowels fixation for slab impeded shear wall 5* | Dowels | Slab | -70.00 | BOH | 41980 | 41983 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1413 | Bottom layer steel reinforcement work for slab section 2-1A | Steel Reinforcement | Slab | -7.20 | B2 | 41980 | 41987 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1414 | installation of injection pipe and re-injectable hose for retaining wall axis B9 to B6/A15 | Insulation | Retaining Wall | -3.80 to 1.10 | BOH | 41980 | 41989 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1415 | steel reinforcement for core 8 axis B1/A1,2,3 | Steel Reinforcement | Core | 3.60 to 7.20 | First Floor | 41981 | 41982 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1416 | bottom layer steel reinforcement work for raft section 24 axis B11 to B13/A6 to A8 | Steel Reinforcement | Raft | -11.00 | Raft | 41982 | 41983 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1417 | piles cutting level, surface preparation and form work to proceed with casting grout piles No. H(399-400-408-409-417-418-422-423)& E(285-290) | Insulation | Piles | -13.50 to -12.50 | Raft | 41981 | 41982 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1418 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation H(409-400-418-422-423) | Dowels | Piles | -13.50 | Raft | 41981 | 41982 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1419 | piles surface preparation to proceed with epoxy application piles No. E(189) | Epoxy | Piles | -13.50 to -12.50 | Raft | 41981 | 41982 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1420 | surface preparation for P.C to proceed with geotextile 1st layer section 22 axis B19 to B21/A10 to A12 | Insulation | P.C | -13.50 to -12.50 | Raft | 41982 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1421 | installation for composite columns (Torque) column CC6 axis C11/A3 | Composite Columns | Column | -1.00 to 4.00 | Ground Floor | 41981 | 41982 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1422 | installation for 2 composite columns (torque) CC7E axis A6/B5-B6 | Composite Columns | Column | zero to 6.00 | Ground Floor | 41981 | 41984 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1423 | steel reinforcement for shear wall 3* axis C8/A2 | Steel Reinforcement | SHW | -3.80 to 1.10 | BOH | 41981 | 41984 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1424 | form work for retaining wall axis B6 to B9/A15 | Form Work | Retaining Wall | -7.20 to -3.80 | B1 | 41981 | 41982 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1425 | fixation of shear connector composite column CC6 axis C11/A3 | Shear Connectors | Column |  | Ground Floor | 41982 | 41982 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1426 | piles cutting level, surface preparation and form work to proceed with casting grout piles No. H(397-398-410-411-415-416-424) | Grout | Piles | -13.50 to -12.50 | Raft | 41982 | 41984 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1427 | form work removal for slab 5B-1 axis A3 to A5/C1 to B3 | Removing Form Work | Slab | -3.80 | B1 | 41984 | 41987 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1428 | fixation of sher connector composite column CC7E axis B6/A6 | Shear Connectors | Column |  | BOH | 41982 | 41984 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1429 | steel reinforcement for ramp beam axis B3 to B6/A13 | Steel Reinforcement | Beam | -7.20 to -3.80 | B1 | 41982 | 41987 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1430 | steel reinforcement for elevator pit at shear wall 5* axis C5/A2 | Steel Reinforcement | SHW | -0.70 | BOH | 41982 | 41984 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1431 | steel reinforcement for column CC6 axis B15/A3 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41982 | 41984 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1432 | form work for column CC6 axis B15/A3 | Form Work | Column | -3.80 to 1.10 | BOH | 41982 | 41984 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1433 | check level and location of P.C form work axis B19 to B21/A9 to A12 | Survey | P.C |  |  | 41982 | 41983 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1434 | drilling depth diameter for missing/short reinforcement of piles to proceed with dowels fixation piles No. H(397-416-424 | Dowels | Piles | -13.50 to -12.50 | Raft | 41982 | 41984 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1435 | check level and location of screed axis B13 to B14/A6 to A7 | Survey | Screed |  |  | 41982 | 41984 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1436 | bottom steel reinforcement work for slab section 5A-2& 5A-3 | Steel Reinforcement | Slab | -3.80 | B1 | 41983 | 41987 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1437 | form work for slab section 1B& 5B-3 | Form Work | Slab | -7.20 | B2 | 41983 | 41987 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1438 | top layer steel reinforcement work, dowels and final inspection for slab section 3A axis B3 to B8/A1 to A3 | Steel Reinforcement | Slab | 1.10 | BOH | 41983 | 41984 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1439 | form work for core 5 axis A8 to A10/B6 to B8 | Form Work | Core | -7.20 to -3.80 | B1 | 41983 | 41987 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1440 | form work for core 8 axis A2 to A3/B1 | Form Work | Core | 3.60 to 7.20 | First Floor | 41983 | 41984 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1441 | fixation of shear connector 2 composite columns CC1 axis B9/A10 | Shear Connectors | Column |  |  | 41983 | 41984 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1442 | fixation of shear connector 2 composite columns CC3 axis B9/A11 | Shear Connectors | Column | -6.00 to zero |  | 41983 | 41984 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1443 | installation for 2 composite columns (torque) CC9 axis B10/A11& B12/A11 | Composite Columns | Column |  |  | 41983 | 41987 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1444 | fixation of shear connector composite column CC9 axis B10/A11& B12/A11 | Shear Connectors | Column |  |  | 41983 | 41987 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1445 | form work for column C1 axis B4/A6 | Form Work | Column | -3.80 to 1.10 | BOH | 41984 | 41987 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1446 | check location of screed axis B13 to B14/A6 to A7 | survey | Screed |  |  | 41982 | 41983 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1447 | steel reinforcement work for column CC7 axis B9/A6 east side | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41984 | 41987 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1448 | form work for composite column CC7 axis B9/A6 east side | Form Work | Column | -11.00 to -7.20 | B2 | 41984 | 41987 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1449 | form work for composite column C4 axis A6/between B2 and B1 | Form Work | Column |  |  | 41984 | 41987 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1450 | steel reinforcement for composite column C4 axis A6/between B2 and B1 | Steel Reinforcement | Column |  |  | 41984 | 41987 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1451 | form work for composite column CC7 axis B4/A8 | Form Work | Column | -3.80 to 1.10 | BOH | 41984 | 41987 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1452 | from work for shear wall 3* axis C8/A2 to A3 | Form Work | SHW | -3.80 to 1.10 | BOH | 41984 | 41988 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1453 | installation of 2 composite columns CC1 (Torque) axis B13/A11 | Composite Columns | Column | -6.00 to zero |  | 41984 | 41984 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1454 | installation of 2 composite columns CC1 (Torque) axis B13/A10 | Composite Columns | Column | -6.00 to zero |  | 41984 | 41987 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1455 | fixation of shear connectors for 2 composite columns CC1 axis B13/A11 | Shear Connectors | Column | -6.00 to zero |  | 41984 | 41987 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1456 | fixation of shear connectors for 2 composite columns CC1 axis B13/A10 | Shear Connectors | Column | -6.00 to zero |  | 41984 | 41987 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1457 | check the level and location of P.C form work for axis B14-B16/A5-A6 | Survey | P.C |  |  | 41984 | 41987 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1458 | form work for raft section 24 axis A6 to A8/B11 to B13 | Form Work | Raft | -11.00 | Raft | 41984 | 41987 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1459 | installation of injection pipe and re-injectable hose at raft construction joints section 24 | Insulation | Raft | -11.00 | Raft | 41984 | 41986 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1460 | top steel reinforcement work, dowels, embeded items and final inspection for raft axis A6 to A8/B11 to B12 | Steel Reinforcement | Raft | -11.00 | Raft | 41984 | 41987 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1461 | steel reinforcement for 4 columns C1 axis A4-7-8-10/B1-2-3 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41984 | 41984 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1462 | steel reinforcement for 3 columns C4 axis B1-2-3/A7-A11 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41984 | 41984 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1463 | top layer steel reinforcement work, dowels and final inspection for slab section 2-1A axis B9 to B13/A8 to A11 | Steel Reinforcement | Slab | -7.20 | B2 | 41987 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1464 | bottom steel reinforcement work for slab section 1B axis A8 to A5/B6 to B9 | Steel Reinforcement | Slab | -7.20 | B2 | 41987 | 41987 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1465 | form work for slab section 4B axis B8 to C9/A1 to A3 | Form Work | Slab | 1.10 | BOH | 41987 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1466 | drilling depth, diameter for missing?short reinforcement of piles to proceed with dowels fixation E(204-206)& H(345-347-346) | Dowels | Piles |  |  | 41987 | 41988 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1467 | piles cutting level, surface preparation and form work to proceed with casting grout H(322-323-345-347-346)& E(205-204-206-207-201) | Grout | Piles |  |  | 41987 | 41988 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1468 | installation of injection pipe and re-injectable hose for retaining wall axis A3 to A6/C1 | Insulation | Retaining Wall | -3.80 to -2.50 | BOH | 41987 | 41989 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1469 | form work for retaining wall axis A7 to A10/C1 | Form Work | Retaining Wall | -7.20 to -3.80 | B1 | 41987 | 41990 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1470 | form work for 4 columns C4 axis A6 to A11/B1 to B3 | Form Work | Column | -3.80 to 1.10 | BOH | 41987 | 41988 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1471 | form work for 5 columns C1 axis B1-2-3-4/A4-6-7-8-10 | Form Work | Column | -3.80 to 1.10 | BOH | 41987 | 41988 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1472 | steel reinforcement for retaining wall axis B9 to B10/A15 | Steel Reinforcement | Retaining Wall | -7.20 to -3.80 | B1 | 41987 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1473 | form work for retaining wall axis B9 to B10/A15 | Form Work | Retaining Wall | -7.20 to -3.80 | B1 | 41987 | 41991 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1474 | form work removal at section 1C axis B3 to B7/A9 to A5 | Removing Form Work | Slab | -3.80 | B1 | 41987 | 41990 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1475 | form work for slab 5B-3 axis A4 to A5/B6 to B9 | Form Work | Slab | -7.20 | B2 | 41988 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1476 | form work for slab 5A-4 axis B5 to B9/A12 to A15 | Form Work | Slab | -3.80 | B1 | 41988 | 41991 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1477 | top layer steel reinforcement work, dowels, embeded items and final inspection forslab 5A-2& 5A-3 axis A9 to A15/C1 to B5 | Steel Reinforcement | Slab | -3.80 | B1 | 41988 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1478 | top layer steel reinforcement work, dowels and final inspection for slab 1B | Steel Reinforcement | Slab | -7.20 | B2 | 41988 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1479 | form work for 2 columns CC7 axis A6/B5-6 | Form Work | Column | -3.80 to 1.10 | BOH | 41988 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1480 | steel reinforcement for 2 columns CC7 axis A6/B5-6 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41988 | 41989 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1481 | form work for retaining wall axis A3 to A6/C1 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 41988 | 41990 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1482 | release for lower anchor head for No. (127-128-129-130-131-132-133-134) | Anchor | Anchor |  |  | 41989 | 41991 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1483 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation H(425) | Dowels | Piles | -13.50 to -12.50 | Raft | 41989 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1484 | installation of horizontal geotextile 1st layer under raft to proceed with PVC membrane installation section 30& 22 axis A8 to A12/B18 to B21 | Insulation | Raft | -13.50 to -12.50 | Raft | 41989 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1485 | piles cutting level, surface preparation and form work to proceed with casting grout | Grout | Piles | -13.50 to -12.50 | Raft | 41989 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1486 | steel reinforcement for core 7 for elevator pit axis A2 to A3/B10 to B11 | Steel Reinforcement | Core | 1.15 | BOH | 41989 | 41994 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1487 | start repair in core wall 5 axis B6 to B8/A8 to A10 | Repair | Core |  |  | 41989 | 41990 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1488 | installation for composite column (torque) CC7E axis B8/A6 | Composite Columns | Column | -6.00 to zero |  | 41989 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1489 | installation for composite column (Torque) CC1 axis B13/A10 | Composite Columns | Column | -6.00 to zero |  | 41989 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1490 | steel reinforcement for column CC7 west side axis B9/A6 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 41989 | 41990 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1491 | form work for column CC7 west side A6/B9 | Form Work | Column | -11.00 to -7.20 | B2 | 41989 | 41991 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1492 | form work for retaining wall axos B4 to B7/A15 | Form Work | Retaining Wall | -7.20 to -3.80 | B1 | 41989 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1493 | installation of injection pipe and re-injectable hose for retaining wall axis B4 to B7/A15 | Insulation | Retaining Wall | -7.20 to -3.80 | B1 | 41989 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1494 | steel reinforcement for retaining wall axis B4 to B7/A15 | Steel Reinforcement | Retaining Wall | -7.20 to -3.80 | B1 | 41989 | 41991 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1495 | bottom layer steel reinforcement work for raft section 23 axis A4 to A7/B9 to B11 | Steel Reinforcement | Raft | -11.00 | Raft | 41989 | 41990 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1496 | installation and test of PVC membrane and water bars to proceed with geotextile 2nd layer for section 22 axis A10 to A13/B19 to B21 | Insulation |  | -12.5 to -13.5 | Raft | 41990 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1497 | piles cutting level, surface preparation and form work to proceed with casting grout iles No. E(169-170-171-179-180-181-182-183-184) | Grout | Piles | -12.5 to -13.5 | Raft | 41990 | 41991 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1498 | piles surface preparation to proceed with epoxy application piles No. H(390-389-388-387-386-385-384-383-382-397-398-399-400-401-402-403-404-405-406-407-408-409-410-411-415-416-417-418-419-420-421-422-423-424-425)& E(309-310-296-291-290-289-288-287) | Epoxy | Piles | -12.5 to -13.5 | Raft | 41990 | 41991 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1499 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation piles No. E(169-180-181-183-184) | Dowels | Piles | -13.5 to -12.5 | Raft | 41990 | 41991 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1500 | form work for 2 columns CC9 axis B10-12/A11 | Form Work | Column | -7.20 to -3.80 | B1 | 41990 | 41991 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1501 | form work for column CC7 axis B8/A6 | Form Work | Column | -7.20 to -3.80 | B1 | 41990 | 41994 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1502 | steel reinforcement for column CC7 axis B8/A6 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41990 | 41991 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1503 | steel reinforcement for 2 columns CC9 axis B10-12/A11 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41990 | 41990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1504 | fixation of shear connector 2 columns CC7 axis B8/A6 | Shear Connectors | Column | -3.80 to ±0.5 | BOH | 41990 | 41991 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1505 | fixation of shear connector 2 columns CC1 axis B9/A10 | Shear Connectors | Column | -3.80 to ±0.5 | BOH | 41990 | 41991 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1506 | fixation of shear connector 2 columns CC3 axis B9/A11 | Shear Connectors | Column | -3.80 to ±0.5 | BOH | 41990 | 41991 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1507 | form work removal for slab section 5A-1 axis A7 to A10/B2 to B3 | Removing Form Work | Slab | -3.80 | B1 | 41991 | 41995 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1508 | form work for slab section 3B axis A1 to A3/C1 to C3 | Form Work | Slab | 1.10 | BOH | 41991 | 41995 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1509 | form work for salb 4A axis B12 to B19/A1 to A3 | Form Work |  | 1.10 | BOH | 41991 | 41995 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1510 | bottom layer steel reinforcement work for slab 5B-3 axis A4 to A6/B6 to B9 | Steel Reinforcement | Slab | -7.20 | B2 | 41991 | 41994 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1511 | bottom layer steel reinforcement work for slab section 4B axis A1 to A3/B8 to C9 | Steel Reinforcement | Slab | 1.10 | BOH | 41991 | 41994 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1512 | form work stair case 12 | Form Work | Stair | -7.20 to -3.80 | B1 | 41991 | 41994 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1513 | form work for column CC3 east side axis B9/A11 | Form Work | Column | -7.20 to -3.80 | B1 | 41991 | 41994 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1514 | form work for column CC1 east side axis B9/A10 | Form Work | Column | -7.20 to -3.80 | B1 | 41991 | 41994 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1515 | steel reinforcement for column CC3 east side axis B9/A11 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41991 | 41993 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1516 | steel reinforcement for column CC1 east side axis B9/A10 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41991 | 41993 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1517 | fixation of shear connectors for column CC7 axis B4/A11 | Shear Connectors | Column | 1.10 to ± 0.5 | Ground Floor | 41991 | 41994 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1518 | installation and test of PVC membrane and water bars to proceed with geotextile 2nd layer | Insulation |  | -13.5 to -12.5 | Raft | 41991 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1519 | installation of horizontal geotextile 2nd layer to proceed with protection screed pouring section 21 axis A8 to A12/A16 to A18 | Insulation | Screed | -13.50 to -12.50 | Raft | 41993 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1520 | installation and test of PVC membrane and water bars to proceed with geotextile 2nd layer at section 21 axis A8 to A12/B16 to B18 | Insulation |  | -13.50 to -12.50 | Raft | 41993 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1521 | steel reinforcement work for core wall 3 axis A7 to A11/B10 to B13 | Steel Reinforcement | Core | -7.20 to -3.80 | B1 | 41993 | 41994 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1522 | drilling and fixation of dowels for stair case 12 axis A1 to A2/B1 to B2 | Dowels | Stair | -7.20 to -3.80 | B1 | 41993 | 41995 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1523 | steel reinforcement for 1 column CC3 west sdie axis B9/A11 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41993 | 41995 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1524 | steel reinforcement for 2 columns CC1 axis B9/A10 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41993 | 41994 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1525 | steel reinforcement for 3 columns CC7 axis B4/A9-A10-A11 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41993 | 41994 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1526 | form work for 3 columns CC7 axis B4/A9-A10-A11 | Form Work | Column | -7.20 to -3.80 | B1 | 41993 | 41994 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1527 | form work for 2 columns CC1 axis B9/A8-A10 | Form Work | Column | -7.20 to -3.80 | B1 | 41993 | 41994 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1528 | form work for 1 column CC3 west side axis B9/A11 | Form Work | Column | -7.20 to -3.80 | B1 | 41993 | 41994 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1529 | steel reinforcement for retaining wall axis A10 to A13/C1 | Steel Reinforcement | Retaining Wall | -7.20 to -3.80 | B1 | 41993 | 41994 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1530 | form work for retaining wall axis A10 to A13/C1 | Form Work | Retaining Wall | -7.20 to -3.80 | B1 | 41993 | 41994 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1531 | casting grout for 3 columns CC7& 2 columns CC1* axis B13/A8-A6& B12/A6 | Grout | Column | -11.00 | Raft | 41993 | 41995 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1532 | form work for slab (Removal) section 3A axis C3 to C6/A1 to A3 | Removing Form Work | Slab | 1.10 | BOH | 41997 | 42000 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1533 | check the level and location of screed axis B17 to B21/A10 to A15 | Survey | Screed |  |  | 41993 | 41994 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1534 | top steel reinforcement work, dowels, embeded items and final inspection for raft section 23 axis B9 to B11/A6 to A4 | Steel Reinforcement | Raft | -11.00 | Raft | 41994 | 41997 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1535 | form work for raft section 23 axis B9 to B11/A4 to A6 | Form Work | Raft | -11.00 | Raft | 41994 | 41997 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1536 | installation of injection pipe and re-injectable hose at B9 to B11/A4 to A6 | Insulation |  | -11.00 | Raft | 41994 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1537 | surface preparation for P.C proceed with geotextile 1st layer section 30& 31 axis A4 to A7/B11 to B16 | Insulation | P.C | -13.50 to -12.50 | Raft | 41994 | 41995 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1538 | installation of injection pipe and re-injectable hose for retaining wall axis A13 to A15/C1 to B4 | Insulation | Retaining Wall | -7.20 to -3.80 | B1 | 41994 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1539 | form work for retaining wall axis A13 to A15/C1 to B4 | Form Work | Retaining Wall | -7.20 to -3.80 | B1 | 41994 | 41996 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1540 | steel reinforcement for retaining wall axis A13 to A15/C1 to B4 | Steel Reinforcement | Retaining Wall | -7.20 to -3.80 | B1 | 41994 | 41995 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1541 | steel reinforcement for pit composite column at axis B12/A6 | Steel Reinforcement | Column | -11.00 | Raft | 41994 | 41996 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1542 | bottom layer steel reinforcement work for slab section 5A-4 axis B6 to B9/A12 to A15 | Steel Reinforcement | Slab | -3.80 | B1 | 41995 | 41996 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1543 | installation of geotextile 2nd layer to proceed with retaining walls reinforcement axs B5 to B9/A15 | Insulation | Retaining Wall | -7.20 to -2.50 |  | 41970 | 41981 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1544 | top layer steel reinforcement work, dowels and final inspection for slab 5B-3 axis A4 to A6/B6 to B9 | Steel Reinforcement | Slab | -7.20 | B2 | 41995 | 41996 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1545 | form work for core 3 axis A10 to A8/B10 to B12 | Form Work | Core | -7.20 to -3.80 | B1 | 41997 | 41998 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1546 | installation of horizontal geotextile 1st layer under raft to proceed with PVC membrane installation at section 31 axis B14 to B16/A5 to A7 | Insulation | Raft | -13.50 to -12.50 | Raft | 41995 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1547 | installation and test of PVC membrane and water bars to proceed with geotextile 2nd layer at section 31 axis B14 to B16/A5 to A7 | Insulation |  | -13.50 to -12.50 | Raft | 41995 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1548 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation piles No. H(368)& E(193) | Dowels | Piles | -12.50 to -13.50 | Raft | 41995 | 41996 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1549 | piles cutting level, surface preparation and form work to proceed with casting grout piles No. E(193-194-195)& H(368-369) | Grout | Piles | -13.50 to -12.50 | Raft | 41995 | 41996 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1550 | piles surface preparation to proceed with epoxy application H(322-323-345-347-346)& E(201-205-206-204) | Epoxy | Piles | -13.50 to -12.50 | Raft | 41995 | 41996 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1551 | steel reinforcement for pit composite column CC7 axis B13/A6 | Steel Reinforcement | Column | -11.00 | Raft | 41995 | 41996 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1552 | bottom layer steel reinforcement work for raft 22, 30, 28 and 27 axis A6 to A12/B16 to B21 | Steel Reinforcement | Raft | -11.00 | Raft | 41997 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1553 | release of lower strut about south-west | Strut | Strut |  |  | 42008 | 42011 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1554 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1555 | form work for slab 5C-1 axis B9 to B1/A12 to A15 | Form Work | Slab | -3.80 | B1 | 41996 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1556 | form work for slab part of section 1A | Form Work | Slab | -3.80 | B1 | 41996 | 41998 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1557 | steel reinforcement work for core 4 | Steel Reinforcement | Core | -7.20 to -3.80 | B1 | 41996 | 42000 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1558 | form work for stair case 3 axis B6 to B7/A8 to A9 | Form Work | Stair | -7.20 to -3.80 | B1 | 41996 | 41997 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1559 | installation of geotextile 1st layer to proceed with PVC membrane installation for section 15 axis B12 to B17/A15 | Insulation |  | -11.00 to -7.20 | B2 | 42004 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1560 | form work for slab 1B axis B7 to B9/A6 to A8 | Form Work | Slab | -3.80 | B1 | 41997 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1561 | steel reinforcement work for 2 columns C3 and 1 column C1 axis A13/B4-B& A11/B3 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41996 | 41997 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1562 | steel reinforcement work for pit of composite column B13/A8 | Steel Reinforcement | Column | -11.00 | Raft | 41996 | 41997 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1563 | top layer steel reinforcement work, dowels and final inspection for slab part of section 4B axis B8 to C7/A1 to A3 | Steel Reinforcement | Slab | 1.10 | BOH | 41997 | 42002 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1564 | check the level and location of screed axis B16 to B14/A5 to A6 | Survey | Screed |  |  | 41996 | 41996 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1565 | bottom layer steel reinforcement work for slab 3B axis A1 to A3/C1 to C3 | Steel Reinforcement | Slab | 1.10 | BOH | 41997 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1566 | form work for 1 column C4 axis (between B3-B2/A13) | Form Work | Column | -3.80 to 1.10 | BOH | 41997 | 41998 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1567 | steel reinforcement for 1 column C4 axis (between B3-B2/A13) | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41997 | 41998 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1568 | casting grout under base plate axis B8/A6 | Grout |  | -11.00 to -7.20 | B2 | 41996 | 41996 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1569 | form work for 2 columns C1 axis B8/A4-A5 | Form Work | Column | -7.20 to -3.80 | B1 | 41997 | 41998 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1570 | Steel reinforcement for 2 columns C1 axis B8/A4-A5 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41997 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1571 | steel reinforcement for stair case 3 axis A8 to A9/B6 to B8 | Steel Reinforcement | Stair | -7.20 to -3.80 | B1 | 41998 | 42001 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1572 | form work for stair case 5 axis A8 to A9/B6 to B8 | Form Work | Stair | -7.20 to -3.80 | B1 | 41998 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1573 | top layer steel reinforcement work for slab 3B axis A1 to A3/C1 to C3 | Steel Reinforcement | Slab | 1.10 | BOH | 41998 | 42001 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1574 | steel reinforcement for retaining wall axis A6 to A10/C1 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 41998 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1575 | form work for retaining wall axis A6 to A10/C1 | Form Work | Retaining Wall | -3.80 to 1.10 | BOH | 41998 | 42001 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1576 | steel reinforcement for 1 column C3 axis B4/A13 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 41998 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1577 | form work for 1 column C3 axis B4/A13 | Form Work | Column | -3.80 to 1.10 | BOH | 41998 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1578 | form work removal slab section 5A-2& 5A-3 axis B2 to B5/A7 to A13 | Removing Form Work | Slab | -3.80 | B1 | 41998 | 42000 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1579 | form work for column C1 axis B8/A4 | Form Work | Column | -7.20 to -3.80 | B1 | 42000 | 42000 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1580 | steel reinforcement for stair case 12 axis A1-A2/B1-B2 | Steel Reinforcement | Stair | -7.20 to -3.80 | B1 | 42000 | 42004 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1581 | fixation of shear connectors of composite column CC7 axis B4/A9-A10 | Shear Connectors | Column | 1.10 to ± 0.5 | Ground Floor | 42001 | 42002 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1582 | steel reinforcement for 3 columns CC7 axis B4/A9-A10-A11 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42001 | 42002 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1583 | form work for 3 columns CC7 axis B4/A9-A10-A11 | Form Work | Column | -3.80 to 1.10 | BOH | 42001 | 42004 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1584 | form work for 1 column CC1 axis B9/A10 west side | Form Work | Column | -7.20 to -3.80 | B1 | 42001 | 42003 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1585 | steel reinforcement for 1 column CC1 axis B9/A10 west side | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42001 | 42002 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1586 | steel reinforcement for 1 column C3 axis B8/A4 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42001 | 42002 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1587 | form work for 1 column C3 axis B8/A4 | Form Work | Column | -7.20 to -3.80 | B1 | 42001 | 42004 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1588 | form work for raft section 22 and 30 axisA8 to A13/B18 to B21 | Form Work | Raft | -11.00 | Raft | 42001 | 42002 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1589 | installation of injection pipe and re-injectable hose at raft section 22 and 30 axisA8 to A13/B18 to B21 | Insulation | Raft | -11.00 | Raft | 42001 | 42002 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1590 | top layer steel reinforcement work, dowels, embeded items and final inspection for raft section 22 and 30 axisA8 to A13/B18 to B21 | Steel Reinforcement | Raft | -11.00 | Raft | 42001 | 42002 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1591 | form work for ramp from level -7.20 to level -3.80 axis A13 to A15/B1 to B6 | Form Work | Ramp | -7.20 to -3.80 | B1 | 42001 | 42002 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1592 | form work for slab of core 2 axis B14 to B16/A8 to A14 | Form Work | Slab | -7.20 | B2 | 42001 | 42004 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1593 | installation of geotextile 2nd layer to proceed with retaining wall reinforcement at section 30 axis B11 to B14/A3 to A8 | Insulation | Retaining Wall | -11.00 | Raft | 42002 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1594 | installation and test of PVC membrane to proceed with geotextile 2nd layer axis B11 to B14/A3 to A8 | Insulation |  | -11.00 | Raft | 42002 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1595 | piles surface preparation to proceed with epoxy application piles No. E(193-192-188-187-186-178-177-185-180-181-182-183-184-179-168-169-170-171-172-173-194-195) | Epoxy | Piles | -13.50 to -12.50 | Raft | 42002 | 42003 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1596 | steel reinforcement for stair 5 axis A8 to A9/B8 | Steel Reinforcement | Stair | -7.20 to -3.80 | B1 | 42002 | 42005 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1597 | bottom layer steel reinforcement work for slab 1B axis A6 to A7/B7 to B8 | Steel Reinforcement | Slab | -3.80 | B1 | 42002 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1598 | form work for retaining wall axis A6 to A10/C1 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 42002 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1599 | form work for 3 columns Axis B10/A4-A5& B9/A5 "east side" | Form Work | Column | -11.00 to -7.20 | B2 | 42002 | 42004 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1600 | steel reinforcement for 4 columns Axis B9/A4 "west side"& B10/A4-A5& B9/A5 "east side" | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42002 | 42004 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1601 | top layer steel reinforcement work, dowels and final inspection for slab 1B axis B6 to B9/A6 to A8 | Steel Reinforcement | Slab | -3.80 | B1 | 42003 | 42005 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1602 | surface preparation and repair work for ramp 2 beam axis A13/B3 to B6 | Repair | Beam | -7.20 to -3.80 | B1 | 42003 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1603 | final inspection steel reinforcement work for ramp beam axis B11 to B16 | Steel Reinforcement | Beam | -3.80 to 1.10 | BOH | 42003 | 42020 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1604 | top layer steel reinforcement work, dowels, embedded items and final inspection for raft section 31 axis B13 to B16/A5 to A7 | Steel Reinforcement | Raft | -11.00 | Raft | 42003 | 42005 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1605 | installation of injection pipe and re-injectable hose at raft construction joints section 21 axis A8 to A12/B16 to B18 | Insulation | Raft | -11.00 | Raft | 42003 | 42012 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1606 | top layer steel reinforcement work, dowels, embeded items and final inspection for raft section 21 axis A8 to A12/B16 to B18 | Steel Reinforcement | Raft | -11.00 | Raft | 42003 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1607 | form work for raft 21 axis A8 to A12/B16 to B18 | Form Work | Raft | -11.00 | Raft | 42003 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1608 | steel reinforcement for stair 6 axis B10 to B11/A8 to A9 | Steel Reinforcement | Stair | -7.20 to -3.80 | B1 | 42003 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1609 | surface preparation for external diaphragm walls to proceed with geotextile 1st layer axis B12 to B17/A15 | Insulation | Diaphragm Wall | -11.00 to -7.20 | B2 | 42004 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1610 | form work for 2 columns CC7 axis A6/B12-B13 "east side" | Form Work | Column | -11.00 to -7.20 | B2 | 42004 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1611 | form work for stair case 6 | Form Work | Stair | -7.20 to -3.80 | B1 | 42003 | 42004 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1612 | fixation of shear connectors for 2 composite columns CC7 axis A6/B12-B13 "east side" | Shear Connectors | Column | -7.20 to ±0.50 | B1 | 42003 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1613 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation pile No. E(196) | Dowels | Piles | -13.50 to -12.50 | Raft | 42004 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1614 | form work for core 3 slab axis B10 to B12/A8 to A10 | Form Work | Slab | -3.80 | B1 | 42004 | 42005 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1615 | form work for slab 5B-3 axis A4 to A5/B6 to B9 | Form Work | Slab | -3.80 | B1 | 42004 | 42005 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1616 | installation and test of PVC membrane to proceed with geotextile 2nd layer axis B13 to B16/A15 | Insulation |  | -11.00 to -4.50 | B2 | 42004 | 42012 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1617 | installation of geotextile 2nd layer to proceed with retaining walls reinforcement axis B13 to B16/A15 | Insulation | Retaining Wall | -11.00 to -4.50 | B2 | 42004 | 42012 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1618 | piles cutting level, surface preparation and form work to proceed with casting grout for pile No. E(196) | Insulation | Piles | -13.5 to -12.5 | Raft | 42004 | 42004 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1619 | form work for column C1 axis A11/B3 | Form Work | Column | -3.80 to 1.10 | BOH | 41996 | 42362 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1620 | form work for 2 columns C1 and 1 column CC1* axis B19/A10-A12& B13/A8 east side | Form Work | Column | -11.00 to -7.20 | B2 | 42005 | 42008 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1621 | steel reinforcement for 2 columns C1 and 1 column CC1* axis B19/A10-A12& B13/A8 east side | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42005 | 42005 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1622 | fixation of shear connectors for composite column CC1* axis B13/A8 east side | Shear Connectors | Column | -11.00 to -7.20 | B2 | 42005 | 42005 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1623 | form work for stair case 1 axis A9 to A10/B3 to B4 | Form Work | Stair | -7.20 to -3.80 | B1 | 42008 | 42009 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1624 | top layer steel reinforcement work for ramp 2 axis A13 to A15/B2 to B6 | Steel Reinforcement | Ramp | -7.20 to -3.80 | B1 | 42005 | 42008 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1625 | steel reinforcement for column CC7 axis B13/A6 west side | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42008 | 42012 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1626 | casting grout for composite column CC9 axis B14/A11 | Grout | Column | -11.00 | Raft | 42008 | 42009 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1627 | steel reinforcement for retaining wall axis A10 to A14/C1 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 42005 | 42005 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1628 | form work for stair case 6 axis B10 to B11/A8 to A9 | Form Work | Stair | -7.20 to -3.80 | B1 | 42005 | 42005 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1629 | piles surface preparation to proceed with epoxy application for piles No. E(196) | Epoxy | Piles | -13.50 to -12.50 | Raft | 42005 | 42005 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1630 | form work for 3 columns C1 axis B9/A4 east side | Form Work | Column | -11.00 to -7.20 | B2 | 42005 | 42005 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1631 | form work for raft axis B13 to B15/A5 to A7 | Form Work | Raft | -11.00 | Raft | 42005 | 42008 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1632 | bottom layer steel reinforcement work for raft section 30 axis B11 to B14/A4 to A5 | Steel Reinforcement | Raft | -11.00 | Raft | 42008 | 42010 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1633 | form work for column CC7 axis B13/A6 west side | Form Work | Column | -11.00 to -7.20 | B2 | 42008 | 42009 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1634 | steel reinforcement for 2 columns C1 axis B9/A4 east side& B9/A5 west side | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42008 | 42012 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1635 | form work for 2 columns C1 axis B9/A4 east side& B9/A5 west side | Form Work | Column | -11.00 to -7.20 | B2 | 42008 | 42009 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1636 | form work for retaining wall axis A10 to A14/C1 | Form Work | Retaining Wall | -3.80 to 1.10 | BOH | 42009 | 42012 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1637 | steel reinforcement for pit CC9 axis B14/A11 | Steel Reinforcement |  | -11.00 | Raft | 42009 | 42010 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1638 | steel reinforcement for 2 column C* between axis B3-B4/A9-A10 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42009 | 42010 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1639 | form work for 2 columns C* between axis B3-B4/A9-A10 | Form Work | Column | -3.80 to 1.10 | BOH | 42009 | 42010 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1640 | steel reinforcement work for core wall 1 axis A9 to A10/B16 to B18 | Steel Reinforcement | Core | -11.00 to -7.20 | B2 | 42009 | 42011 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1641 | top layer steel reinforcement work, dowels and final inspection for slab 1A axis B5 to B8/A8 to A11 | Steel Reinforcement | Slab | -3.80 | B1 | 42009 | 42010 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1642 | bottom layer steel reinforcement work for 1A axis B5 to B8/A8 to A11 | Steel Reinforcement |  | -3.80 | B1 | 42009 | 42010 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1643 | bottom layer steel reinforcement work for slab 5B-3 axis B7 to B9/A3 to A6 | Steel Reinforcement | Slab | -3.80 | B1 | 42009 | 42012 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1644 | STEEL REINFORCEMENT FOR STAIR CASE 1 AXIS A10/B3 | Steel Reinforcement | Stair | -3.80 | B1 | 42009 | 42014 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1645 | steel reinforcement for 1 column CC1* axis B13/A8 west side | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42010 | 42010 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1646 | form work for 1 column CC1* axis B13/A8 west side | Form Work | Column | -11.00 to -7.20 | B2 | 42010 | 42012 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1647 | top layer steel reinforcement work, dowels and final inspection for slab section 5B-3 axis A4 to A6/B6 to B9 | Steel Reinforcement | Slab | -3.80 | B1 | 42010 | 42014 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1648 | top layer steel reinforcement work, dowels, embeded items and final inspection for raft section 30 axis B11 to B14/A6 to A4 | Steel Reinforcement | Raft | -11.00 | Raft | 42010 | 42014 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1649 | installation of injection pipe and re-injectable hose at raft construction joints section 30 axis B11 to B14/A6 to A4 | Insulation | Raft | -11.00 | Raft | 42010 | 42014 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1650 | steel reinforcement work for retaining wall axis B13 to B16/A15 | Steel Reinforcement | Retaining Wall | -11.00 to -7.20 | B2 | 42010 | 42014 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1651 | form work for retaining wall axis B13 to B16/A15 | Form Work | Retaining Wall | -11.00 to -7.20 | B2 | 42010 | 42014 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1652 | repair work for surface preparation of 2 columns C1 | Repair | Column | -3.80 to 1.10 | BOH | 42010 | 42014 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1653 | form work for stair case 12 axis B1/A2 | Form Work | Stair | -3.80 to 0.45 | BOH | 42011 | 42014 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1654 | form work removal for section 3B axis C1 to C3/A1 to A3 | Removing Form Work | Slab | 1.10 | BOH | 42011 | 42014 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1655 | inspection of holes and dowels fixation at core 7 axis C7/A3 | Dowels | Core | -3.80 to 1.10 | BOH | 42011 | 42014 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1656 | inspection of fixation of composite column (Torque) CC9 axis B8/A11 | Composite Columns | Column | -0.30 | BOH | 42012 | 42014 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1657 | inspection of fixation of composite column (Torque) CC9 axis B6/A11 | Shear Connectors | Column | -0.30 | BOH | 42012 | 42014 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1658 | inspection of fixation for composite column (Torque) CC7 axis B8/A6 | Composite Columns | Column | Zero | BOH | 42012 | 42014 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1659 | fixation of shear connector for composite column CC9 axis B6/A11 | Shear Connectors | Column | 1.10 | BOH | 42012 | 42014 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1660 | fixation of shear connector composite column CC9 axis B8/A11 | Shear Connectors | Column | 1.10 | BOH | 42012 | 42014 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1661 | fixation of shear connectors for composite column CC7 axis B8/A6 | Shear Connectors | Column | 1.10 | BOH | 42012 | 42014 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1662 | fixation of shear connector for comosite column CC1 axis B9/A10 | Shear Connectors | Column | 1.10 | BOH | 42012 | 42015 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1663 | fixation of shear connector of composite column CC3 axis B9/A11 | Shear Connectors | Column | 1.10 | BOH | 42014 | 42015 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1664 | steel reinforcement for column C1 axis A4/B12 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42014 | 42015 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1665 | steel reinforcement for column C1 axis A4/B13 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42014 | 42015 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1666 | steel reinforcement for column C1 axis A5/B13 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42014 | 42015 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1667 | steel reinforcement for column C7 axis A5/B12-B13 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42014 | 42016 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1668 | form work for column C1 axis A4/B12 | Form Work | Column | -11.00 to -7.20 | B2 | 42014 | 42015 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1669 | form work for column C1 axis A4/B13 east side | Form Work | Column | -11.00 to -7.20 | B2 | 42014 | 42015 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1670 | form work for column C1 axis A5/B13 east side | Form Work | Column | -11.00 to -7.20 | B2 | 42014 | 42015 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1671 | form work for column C7 axis A5/between B12-B13 | Form Work | Column | -11.00 to -7.20 | B2 | 42014 | 42017 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1672 | form work for column CC7 axis A6/B8 | Form Work | Column | -3.80 to 1.10 | BOH | 42014 | 42017 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1673 | form work for column CC9 axis A11/B6 | Form Work | Column | -3.80 to 1.10 | BOH | 42014 | 42017 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1674 | form work for column CC9 axis A11/B8 | Form Work | Column | -3.80 to 1.10 | BOH | 42014 | 42017 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1675 | installation of injection pipe and re-injectable hose for retaining wall B13 to B16/A15 | Insulation | Retaining Wall | -11.00 to -7.20 | B2 | 42014 | 42022 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1676 | steel reinforcement for column CC7 axis A6/B8 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42014 | 42015 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1677 | steel reinforcement for column CC9 axis A11/B8 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42014 | 42017 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1678 | steel reinforcement for column CC9 axis A11/B6 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42014 | 42015 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1679 | inspection of fixation for 4 composite columns CC3& CC1(Torque) axis B9/A11, B9/A10 | Composite Columns | Column | Zero | BOH | 42011 | 42014 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1680 | check level and location of screed axis B10 to B13/A4 to A5 | Survey | Screed |  |  | 42005 | 42005 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1681 | steel reinforcement for 2 columns CC7 axis A6/B12-B13 east side | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42003 | 42004 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1682 | bottom steel reinforcement for ramp axis A13 to A15/B2 to B6 | Steel Reinforcement | Ramp | -7.20 to -3.80 | B1 | 42003 | 42005 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1683 | form work raft section 30 axis B12 to B13/A4 to A5 | Form Work | Raft | -11.00 | Raft | 42015 | 42016 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1684 | form work for stair 14 axis A2 to A3/B16 to B17 | Form Work | Stair | -7.20 to -3.80 | B1 | 42015 | 42018 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1685 | form work for core 1 axis A8 to A10/B16 to B18 | Form Work | Core | -11.00 to -7.20 | B2 | 42015 | 42017 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1686 | casting grout for composite column CC4 axis A9/between B18-B19 | Grout | Column | -11.00 to -7.20 | B2 | 42015 | 42017 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1687 | steel reinforcement for panoramic elevator between axis B9-B10/between axis A5-A6 | Steel Reinforcement | Panoramic Elevator | -11.00 to -7.20 | B2 | 42015 | 42024 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1688 | form work for ramp curved beams B2 to B3/A13& A13 to A15/C1 to B3 | Form Work | Beam | -7.20 | B2 | 42015 | 42018 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1689 | bottom layer steel reinforcement work for slab section 2-1A | Steel Reinforcement | Slab | -3.80 | B1 | 42015 | 42018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1690 | form work for 1 column C axis B3/A9 | Form Work | Column | -3.80 to 1.10 | BOH | 42017 | 42018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1691 | steel reinforcement for 1 column C** axis B3/A9 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42017 | 42017 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1692 | form work for retaining wall axis A10 to A14/C1 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 42016 | 42017 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1693 | form work for shear wall 6 axis C4/A2 to A3 | Form Work | SHW | 1.10 to 5.45 | Ground Floor | 42016 | 42018 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1694 | steel reinforcement for shear wall 6 axis C4/A2 to A3 | Steel Reinforcement | SHW | 1.10 to 5.45 | Ground Floor | 42016 | 42018 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1695 | steel reinforcement for retaining wall axis B1 to B5/A1 | Steel Reinforcement | Retaining Wall | 1.10 to 5.45 | Ground Floor | 42016 | 42018 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1696 | steel reinforcement for shear wall 7 axis C3/A2 to A3 | Steel Reinforcement | SHW | 1.10 to 5.45 | Ground Floor | 42016 | 42018 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1697 | form work for shear wall 7 axis C3/A2 to A3 | Form Work | SHW | 1.10 to 5.45 | Ground Floor | 42016 | 42018 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1698 | form work for 2 columns C1 axis B13/A4-A5 "west side" | Form Work | Column | -11.00 to -7.20 | B2 | 42016 | 42018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1699 | steel reinforcement for 2 columns C1 axis B13/A4-A5 "west side" | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42016 | 42018 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1700 | form work for part of slab section 2-2A, 2-1A& 2-1A axis B13 to B14/A7 to A10 | Form Work | Slab | -7.20 | B2 | 42016 | 42018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1701 | casting grout for composite column CC7 axis A6/B14 | Grout | Column | -11.00 | Raft | 42016 | 42018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1702 | steel reinforcement for beams and slab elevator pit core 7 axis A2 to A3/C7 | Steel Reinforcement | Slab | 1.15 | BOH | 42016 | 42018 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1703 | steel reinforcement for shear wall 5* axis B7 to B8/A2 to A3 | Steel Reinforcement | SHW | 1.10 to 5.40 | Ground Floor | 42017 | 42018 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1704 | steel reinforcement for shear wall 8 axis C2/A1 to A3 | Steel Reinforcement | SHW | 1.10 to 5.40 | Ground Floor | 42018 | 42021 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1705 | steel reinforcement for retaining wall axis B3 to B7/A15 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 42017 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1706 | form work for column C1 axis A5/B8 | Form Work | Column | -3.80 to 1.10 | BOH | 42018 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1707 | steel reinforcement for column pit CC4 axis A10/B19-B18 | Steel Reinforcement | Column | -11.00 | Raft | 42017 | 42018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1708 | steel reinforcement for column pit CC7 axis A6/B14 | Steel Reinforcement | Column | -11.00 | Raft | 42017 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1709 | form work for shear wall 1 axis B5 to B9/A1 | Form Work | SHW | 1.10 to 5.40 | Ground Floor | 42022 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1710 | top layer steel reinforcement work, dowels and final inspection for slab part of section 4B axis C7 to C9/A1 to A3 | Steel Reinforcement | Slab | 1.10 | BOH | 42017 | 42018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1711 | installation of injection pipe and re-injectable hose for retaining wall B3 to B7/A15 | Insulation | Retaining Wall | -3.80 to 1.10 | BOH | 42017 | 42022 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1712 | form work for elevator pit beam at shear wall 5* axis A2/C5 | Form Work | SHW | -0.70 | BOH | 42018 | 42018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1713 | form work for elevator pit beam at core 7 axis A2 to A3/C7 | Form Work | Core | 1.15 | BOH | 42018 | 42019 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1714 | form work for column C1 axis A5/B6 | Form Work | Column | -3.80 to 1.10 | BOH | 42018 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1715 | Piles Cutting Level, Surface Preparation and form work to proceed with Casting Grout. E(197-198-199-200-202-203) | Grout | Piles | -11.00 | Raft | 42018 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1716 | Drilling depth, diameter for missing / short reinforcement of Piles to proceed with Dowels Fixation. E(199) | Dowels | Piles | -11.00 | Raft | 42018 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1717 | form work removal slab 1B axis B6 to B9/A6 to A8 | Removing Form Work | Slab | -3.80 | B1 | 42018 | 42018 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1718 | steel reinforcement for column C1 axis A5/B8 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42018 | 42018 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1719 | steel reinforcement for column C1 axis A5/B6 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42018 | 42018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1720 | form work for stair case 7 at core 3 | Form Work | Stair | -11.00 to -7.20 | B2 | 42018 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1721 | form work for stair 8 at core 3 | Form Work | Stair | -11.00 to -7.20 | B2 | 42018 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1722 | surface preparation and repair work for R.C beam | Repair | Beam | -3.80 to 0.45 | stair 12 | 42018 | 42022 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1723 | top layer steel reinforcement work, dowels and final inspection for part of slab 2-1A axis A8 to A10/B9 | Steel Reinforcement | Slab | -3.80 | B1 | 42018 | 42021 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1724 | steel reinforcement for pit composite columns CC4 axis A9/B18-B19 between | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42018 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1725 | form work for column CC4 axis A10/between B18-B19 | Form Work | Column | -11.00 to -7.20 | B2 | 42018 | 42021 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1726 | steel reinforcement for column CC4 axis A10/between B18-B19 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42018 | 42021 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1727 | casting grout for composite column CC7 axis A6/B10 | Grout | Column | -11.00 | Raft | 42018 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1728 | casting grout for composite column CC4 axis A11-A10/B16 | Grout | Column | -11.00 | Raft | 42018 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1729 | steel reinforcement for shear wall 1 axis B5 to B9/A1 | Steel Reinforcement | SHW | 1.10 to 5.40 | Ground Floor | 42018 | 42021 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1730 | steel reinforcement for shear wall 3 axis C6/A2 to A3 | Steel Reinforcement | SHW | 1.10 to 5.40 | Ground Floor | 42018 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1731 | steel reinforcement for stair case 14 axis A2/B16 | Steel Reinforcement | Stair | -7.20 to ±3.80 |  | 42018 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1732 | check level and location of P.C as shown in attached sketch | Survey | P.C |  |  | 42018 | 42019 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1733 | form work for shear wall 1 axis A1/B5 to B1 | Form Work | SHW | 1.10 to 5.45 | Ground Floor | 42018 | 42021 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1734 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1735 | form work for shear wall 3 axis C6/A2 to A3 | Form Work | SHW | 1.10 to 5.40 | Ground Floor | 42019 | 42022 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1736 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1737 | steel reinforcement for pit composite column CC4 axis B16/A10-A11 | Steel Reinforcement | Column | -11.00 | Raft | 42019 | 42021 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1738 | steel reinforcement for shear wall 1 axis B9 to B12/A1 | Steel Reinforcement | SHW | 1.10 to 5.45 | Ground Floor | 42019 | 42021 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1739 | steel reinforcement for retaining wall axis A13 to A15/C1& B3 to B2/A15 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 42019 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1740 | form work for retaining wall axis B6 to B3/A15 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 42021
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1741 | fixation of shear connector composite column CC7 axis A6/B14 | Shear Connectors | Column | -7.20 to ±0.50 | BOH | 42021 | 42021 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1742 | fixation of shear connector for composite column CC4 axis A10/B18-B19 | Shear Connectors | Column | -7.20 | B2 | 42019 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1743 | fixation of shear connector for composite column CC4 axis A9/B18-B19 | Shear Connectors | Column | -7.20 | B2 | 42019 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1744 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1745 | casting grout for composite column CC4 axis A12/B18 | Grout | Column | -11.00 | Raft | 42019 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1746 | casting grout for composite column CC7 axis A12/B16 | Grout | Column | -11.00 | Raft | 42019 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1747 | form work for retaining wall axis B3 to B7/A15 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 42019 | 42021 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1748 | form work for retaining wall axis B3 to B7/A15 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 42019 | 42022 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1749 | form work for stair case 1 axis A10/B3 to B4 | Form Work | Stair | -3.80 to 0.45 | BOH | 42021 | 42024 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1750 | steel reinforcement work for core wall 7 axis A2 to A3/C7 | Steel Reinforcement | Core | 1.10 to 4.50 | Ground Floor | 42021 | 42022 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1751 | form work for slab 5C-2 axis A11 to B15/B13 to B16 | Form Work | Slab | -7.20 | B2 | 42021 | 42022 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1752 | bottom layer steel reinforcement work for slab of core 2 axis A7 to A10/B14 to B16 | Steel Reinforcement | Slab | -7.20 | B2 | 42021 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1753 | steel reinforcement for column CC9 axis A11/B14 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42021 | 42022 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1754 | fixation of shear connector composite column CC9 axis A11/B14 | Shear Connectors | Column | -7.20 | B2 | 42021 | 42022 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1755 | steel reinforcement for pit composite column CC7 axis A12/B16 | Steel Reinforcement | Column | -11.00 | Raft | 42021 | 42022 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1756 | form work for column CC9 axis A11/B14 | Form Work | Column | -11.00 to -7.20 | B2 | 42021 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1757 | form work for column CC7 axis A6/B14 | Form Work | Column | -11.00 to -7.20 | B2 | 42021 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1758 | steel reinforcement for column CC7 axis A6/B14 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42021 | 42024 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1759 | drilling and fixation for dowels of beam B10 for new ramp at level -3.80 on axis B8/A15 | Dowels | Beam | -3.80 | B1 | 42021 | 42022 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1760 | bottom layer steel reinforcement for slab 5C-2 axis B13 to B16/A11 to A15 | Steel Reinforcement | Slab | -7.20 | B2 | 42022 | 42024 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1761 | steel reicnforcement for new ramp beams B10 aixs A12 to A15/B9 | Steel Reinforcement | Beam | -3.80 | B1 | 42022 | 42026 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1762 | steel reinforcement for core 5 axis B6 to B8/A8 to A10 | Steel Reinforcement | Core | -3.80 to 1.10 | BOH | 42022 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1763 | steel reinforcement for core 1 axis B16 to B17/A9 | Steel Reinforcement | Core | -7.20 to -3.80 | B1 | 42022 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1764 | steel reinforcement for core wall 8 axis A2-A3/B1 | Steel Reinforcement | Core | 5.40 to 7.95 |  | 42022 | 42026 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1765 | surface preparation for external diaphragm wall to proceed with geotextile 1st layer axis B18 to B20/A15 | Insulation | Diaphragm Wall | -11.00 to -4.50 |  | 42022 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1766 | installation of geotextile 1st layer to proceed with PVC memrane installation axis B18 to B20/A15 | Insulation |  | -11.00 to -4.50 |  | 42022 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1767 | fixation of shear connector for column CC4 axis A10-A11/B16 | Shear Connectors | Column | -7.20 | B2 | 42022 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1768 | fixation of shear connector for 2 columns CC1 axis A10/B9 east and west side | Shear Connectors | Column | 1.10 | BOH | 42022 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1769 | fixation of shear connector for 2 columns CC3 axis A11/B9 east and west side | Shear Connectors | Column | 1.10 | BOH | 42022 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1770 | fixation of shear connector composite column CC7 axis A6/B13 west side | Shear Connectors | Column | -3.80 | B1 | 42022 | 42024 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1771 | inspection of fixation for composite column (Torque) CC7 axis A6/B13 west side | Composite Columns | Column | zero |  | 42022 | 42024 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1772 | inspection of fiaxtion of composite column (Torque) CC1 axis A10/B9 west side | Composite Columns | Column | zero |  | 42022 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1773 | inspection of fixation for composite column (Torque) CC3 axis B11/B9 west side | Composite Columns | Column | zero |  | 42022 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1774 | form work for column CC4 axis A9/B18 to B19 | Form Work | Column | -3.80 to 1.10 | BOH | 42022 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1775 | surface preparation and repair work for R.C column C1 axis A4/B1 | Repair | Column | -3.80 to 1.10 | BOH | 42022 | 42026 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1776 | steel reinforcement for composite column pit CC4 axis A11 to A12/B18 | Steel Reinforcement | Column | -11.00 | Raft | 42022 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1777 | steel reinforcement for column CC4 axis A9/B18 to B19 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42022 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1778 | installation of geotextile 1st layer to proceed with PVC membrane installation axis B15 to B18/A15 | Insulation |  | -11.00 to -4.50 | wall | 42023 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1779 | installation and test of PVC membrane to proceed with geotextile 2nd layer axis B15 to B20/A15 | Insulation |  | -11.00 to -4.50 | wall | 42023 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1780 | installation of geotextile 2nd layer to proceed with retaining wall B15 to B20/A15 | Insulation | Retaining Wall | -11.00 to -4.50 | wall | 42023 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1781 | steel reinforcement for shear wall 3* axis C8/A1 to A3 | Steel Reinforcement | SHW | 1.10 to 4.45 | Ground Floor | 42023 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1782 | fixation of shear connector composite column CC7 axis A12/B16 | Shear Connectors | Column | -7.20 | B2 | 42023 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1783 | form work for core wall 7 axis A2 to A3/C7 | Form Work | Core | 1.10 to 4.50 | Ground Floor | 42023 | 42024 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1784 | steel reinforcement for new ramp beam B10 axis B8/A12 to A15 | Steel Reinforcement | Beam | -3.80 | B1 | 42023 | 42026 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1785 | steel reinforcement for new ramp beam B10 axis B10,12/A12 to A15 | Steel Reinforcement | Beam | -3.80 | B1 | 42023 | 42026 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1786 | steel reinforcement for column CC4 axis B16/A10-A11 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42024 | 42026 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1787 | fixation of shear connector composite column CC4 axis B16/A10 | Shear Connectors | Column | -7.20 | B2 | 42023 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1788 | steel reinforcement for column CC4 axis D2 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42023 | 42026 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1789 | form work for column CC4 axis D2 | Form Work | Column | -11.00 to -7.20 | B2 | 42023 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1790 | steel reinforcement for column CC7 axis B16/A12 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42024 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1791 | installation of injection pipe and re-injetable hose for retaining wall axis B3 to C1/A15& A14 to A15/C1 | Insulation | Retaining Wall | -3.80 to -2.50 | BOH | 42023 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1792 | form work for retaining wall axis B3 to C1/A15& A14 to A15/C1 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 42023 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1793 | steel reinforcement for column CC4 axis D4/A11-A12 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42024 | 42026 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1794 | bottom layer steel reinforcement work for slab 5C-1 axis A11 to B15/B8 to B13 | Steel Reinforcement | Slab | -3.80 | B1 | 42024 | 42028 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1795 | form work for core wall 1 axis B17/A9 | Form Work | Core | -7.20 to -3.80 | B1 | 42024 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1796 | form work for retaining wall axis B3 to C1/A15& A14 to A15/C1 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 42024 | 42026 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1797 | form work for column CC4 axis D4/A11-A12 | Form Work | Column | -11.00 to -7.20 | B2 | 42024 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1798 | form work for column CC7 axis B16/A12 | Form Work | Column | -11.00 to -7.20 | B2 | 42024 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1799 | form work for column CC4 axis B16/A10-A11 | Form Work | Column | -11.00 to -7.20 | B2 | 42024 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1800 | fixation of shear connectors for column CC9 axis B12/A11 | Shear Connectors | Column | -0.30 |  | 42024 | 42026 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1801 | fixation of shear connectors for column CC9 axis B10/A11 | Shear Connectors | Column | -0.30 |  | 42024 | 42026 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1802 | steel reinforcement for shear wall 5 axis C5/A1 to A3 | Steel Reinforcement | SHW | 1.10 to 5.40 | Ground Floor | 42024 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1803 | torque for column CC1* axis B13/A8 west side | Composite Columns | Column | -6.00 |  | 42024 | 42024 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1804 | steel reinforcement for column pit CC7 axis A6/B10 | Steel Reinforcement | Column |  |  | 42024 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1805 | inspection of holes and dowels fixation of core 4 axis A8/B9 | Dowels | Core | -11.00 to -7.20 | B2 | 42025 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1806 | top layer steel reinforcement work, dowels and final inspection for slab section 5C-2 axis A11 to A15/B13 to B16 | Steel Reinforcement | Slab | -7.20 | B2 | 42025 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1807 | installation of injection pipe and re-injectable hose at retaining wall construction joint for slab section5C-2 axis A11 to A15/B13 to B16 | Insulation | Retaining Wall | -7.20 | B2 | 42025 | 42054 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1808 | steel reinforcement for column C1 axis A4/B3 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42025 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1809 | steel reinforcement for column C1 axis A4/B2 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42025 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1810 | steel reinforcement for column C1 axis A6/B2 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42025 | 42026 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1811 | steel reinforcement for column C1 axis A5/B2 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42025 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1812 | form work for column C1 axis A6/B2 | Form Work | Column | -3.80 to 1.10 | BOH | 42025 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1813 | form work for column C1 axis A5/B2 | Form Work | Column | -3.80 to 1.10 | BOH | 42025 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1814 | form work for column C1 axis A4/B3 | Form Work | Column | -3.80 to 1.10 | BOH | 42025 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1815 | form work for column C1 axis A4/B2 | Form Work | Column | -3.80 to 1.10 | BOH | 42025 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1816 | surface preparation for external diaphragm wall to proceed with geotextile 1st layer axis B19 to B21/A15 and A12 to A15/B21 | Insulation | Diaphragm Wall | -11.00 to -4.50 | wall | 42025 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1817 | installation of geotextile 1st layer to proceed with PVC membrane installation axis B19 to B21/A15 and A12 to A15/B21 | Insulation |  | -11.00 to -4.50 | wall | 42025 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1818 | installation of geotextile 2nd layer to proceed with retaining wall reinforcement axis B19 to B21/A15 and A12 to A15/B21 | Insulation | Retaining Wall | -11.00 to -4.50 | wall | 42025 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1819 | installation and test of PVC memrane to proceed with geotextile 2nd layer axis B19 to B21/A15 and A12 to A15/B21 | Insulation |  | -11.00 to -4.50 | wall | 42025 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1820 | installation for composite columns (Torque) 2 columns CC7 axis A6/B13 west and A6/B14 | Composite Columns | Column | -6.00 |  | 42025 | 42026 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1821 | form work for 2 columns C4 axis A7,8/B2,3 | Form Work | Column | -3.80 to 1.10 | BOH | 42025 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1822 | form work for shear wall 8 axis C2 | Form Work | SHW | 1.10 to 5.40 | Ground Floor | 42025 | 42026 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1823 | installation for 1 composite column (Torque) CC5 axis A3/B13 | Composite Columns | Column | 1.7 | BOH | 42025 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1824 | installation for 1 composite column (Torque) CC1* axis B13/A8 east side | Composite Columns | Column | -6.00 |  | 42025 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1825 | form work for core 8 axis A2 to A3/B1 | Form Work | Core | 6.75 to 9.25 |  | 42026 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1826 | fixation of shear connector for 2 columns CC1* east and west sides axis A8/B13 | Shear Connectors | Column | -3.80 to -0.5 |  | 42026 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1827 | fixation of fixation of shear connector for 2 columns CC1 east and west side A10/B13 | Shear Connectors | Column | -3.80 to -0.5 |  | 42026 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1828 | fixation of shear connector for 2 columns CC1* east and west sides axis A11/B13 | Shear Connectors | Column | -3.80 to -0.5 |  | 42026 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1829 | fixation of shear connectors for column CC7 axis A6/B12 | Shear Connectors | Column | -3.80 to -0.5 |  | 42026 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1830 | fixation of shear connectors for column CC7 west side axis A6/B13 | Shear Connectors | Column | -3.80 to -0.5 |  | 42026 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1831 | form work for core 5 axis A8 to A10/B6 to B8 | Form Work | Core | -3.80 to 1.10 | BOH | 42026 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1832 | steel reinforcement for core 2 axis B14 to B15/A8 to A10 | Steel Reinforcement | Core | -7.20 to -3.80 | B1 | 42026 | 42028 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1833 | steel reinforcement for 2 columns C1 axis B3/A5-A6 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42026 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1834 | form work for 2 columns C1 axis B3/A5-A6 | Form Work | Column | -3.80 to 1.10 | BOH | 42026 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1835 | top layer steel reinforcement work, dowels and final inspection for slab section 5A-4 axis A11 to A15/B5 to B9 | Steel Reinforcement | Slab | -3.80 | B1 | 42026 | 42028 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1836 | installation of injection pipe and re0injectable hose for roof slab 5A-4 axis A11 to A15/B5 to B9 | Insulation | Slab | -3.80 | B1 | 42026 | 42054 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1837 | installation of injection pipe and re-injectable hse for roof slab section 5C-1 axis A11 to A15/B9 to B13 | Insulation | Slab | -3.80 | B1 | 42026 | 42054 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1838 | top layer steel reinforcement work, dowels and final inspection for slab 5C-1 axis A11 to A15/B1 to B9 | Steel Reinforcement | Slab | -3.80 | B1 | 42026 | 42028 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1839 | form work for slab 4A axis A1 to A3/B15 to B19 | Form Work | Slab | 1.10 | BOH | 42026 | 42031 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1840 | fixation of shear connector at column CC5 axis C9 | Shear Connectors | Column | 5.40 | First Floor | 42026 | 42030 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1841 | fixation of shear connector at column CC6 axis C11 | Shear Connectors | Column | 5.40 | First Floor | 42026 | 42030 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1842 | installation for composite column (Torque) CC6 axis C11 | Composite Columns | Column | 4.00 | Ground Floor | 42026 | 42026 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1843 | bottom layer steel reinforcement for slab 2-2A axis B13 to B16/A6 to A11 | Steel Reinforcement | Slab | -7.20 | B2 | 42028 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1844 | form work for column C4 axis A6/B2-B1 | Form Work | Column | -3.80 to 1.10 | BOH | 42028 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1845 | steel reinforcement for column C1 axis A12/B14 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42028 | 42032 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1846 | steel reinforcement for column C1 axis A14/B14 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42028 | 42032 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1847 | steel reinforcement for column C1 axis A14/B13 east side | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42028 | 42032 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1848 | steel reinforcement for column C6 axis A12/B13 east | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42028 | 42032 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1849 | form work for shear wall 5 axis C5/A1 to A3 | Form Work | SHW | 1.10 to 5.40 | Ground Floor | 42029 | 42031 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1850 | form work for column C1 axis A12/B6 | Form Work | Column | -3.80 to 1.10 | BOH | 42029 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1851 | form work for column C7 axis A12/B8 | Form Work | Column | -3.80 to 1.10 | BOH | 42029 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1852 | form wrok for column C6 axis A12/B9 east side | Form Work | Column | -3.80 to 1.10 | BOH | 42029 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1853 | form work for column C7 axis A12/B10 | Form Work | Column | -3.80 to 1.10 | BOH | 42029 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1854 | form work for column C7 axis A12/B12 | Form Work | Column | -3.80 to 1.10 | BOH | 42029 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1855 | steel reinforcement for C1 axis A12/B6 | Steel Reinforcement |  | -3.80 to 1.10 | BOH | 42029 | 42030 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1856 | steel reinforcement for column C7 axis A12/B8 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42029 | 42030 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1857 | steel reinforcement for column C6 axis A12/B9 east side | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42029 | 42030 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1858 | steel reinforcement for column C7 axis A12/B10 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42029 | 42030 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1859 | steel reinforcement for column C7 axis A12/B12 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42029 | 42030 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1860 | form work for column C6 axis A12/B13 east side | Form Work | Column | -7.20 to -3.80 | B1 | 42029 | 42031 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1861 | form work for column C1 axis A12/B14 | Form Work | Column | -7.20 to -3.80 | B1 | 42029 | 42030 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1862 | form work for column C1 axis A14/B14 | Form Work | Column | -7.20 to -3.80 | B1 | 42029 | 42031 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1863 | form work for column C1 axis A14/B13 east side | Form Work | Column | -7.20 to -3.80 | B1 | 42029 | 42030 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1864 | steel reinforcement for retaining wall axis B15 to B19/A15 | Steel Reinforcement | Retaining Wall | -11.00 to -7.20 | B2 | 42029 | 42030 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1865 | bottom layer steel reinforcement for slab section 4A | Steel Reinforcement | Slab | 1.10 | BOH | 42029 | 42033 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1866 | top layer steel reinforcement work, dowels and final inspection for slab section 2-2A axis A6 to A12/B13 to B16 | Steel Reinforcement | Slab | -7.20 | B2 | 42029 | 42031 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1867 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1868 | steel reinforcement work for core wall 3 axis A5 to A10/B10 to B12 | Steel Reinforcement | Core | -3.80 to 1.10 | BOH | 42029 | 42033 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1869 | steel reinforcement work for core wall 4 axis B8 to B9/A7 to A9 | Steel Reinforcement | Core | -11.00 to -7.20 | B2 | 42030 | 42031 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1870 | steel reinforcement for stair case 12 axis A2/B1 | Steel Reinforcement | Stair | -3.80 to 0.45 | BOH | 42029 | 42035 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1871 | inspection for fixation of shear connectors for 2 composite columns CC9 axis B10-B12/A12 | Shear Connectors | Column | 1.10 | BOH | 42030 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1872 | inspection for fixation of 2 composite columns (torque) for CC9 axis B10-B12/A12 | Composite Columns | Column | 1.10 | BOH | 42030 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1873 | form work for retaining wall axis B15 to B19/A15 | Form Work | Retaining Wall | -11.00 to -7.20 | B2 | 42030 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1874 | form work for shear wall 3* axis C8/A2 to A3 | Form Work | SHW | 1.10 to 5.40 | Ground Floor | 42030 | 42031 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1875 | form work for panoramic elevator axis A5 to A6/B10 to B11 | Form Work | Panoramic Elevator | -11.00 to -7.20 | B2 | 42030 | 42033 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1876 | check the level and location of P.C form work | Survey | P.C |  |  | 42032 | 42032 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1877 | form work for slab 5-A1 axis C1 to B3/A8 to A12 | Form Work | Slab | 1.05 | BOH | 42032 | 42033 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1878 | inspection of fixation of composite column (Torque) CC7 axis A6/B13 east side | Composite Columns | Column | -7.20 to -3.80 | B1 | 42031 | 42033 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1879 | steel reinforcement for column CC3 axis A11/B9 west side | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42031 | 42032 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1880 | steel reinforcement for column CC1 axis A10/B9 west | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42031 | 42032 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1881 | steel reinforcement for column CC7 axis A6/B10 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42031 | 42035 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1882 | steel reinforcement for shear wall 6 axis C4 | Steel Reinforcement | SHW | 5.40 to 12.10 | First Floor | 42031 | 42037 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1883 | steel reinforcement for retaining wall axis A15/B19 to B21 | Steel Reinforcement | Retaining Wall | -11.00 to -7.20 | B2 | 42031 | 42031 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1884 | form work for retaining wall axis A15/B19 to B21 | Form Work | Retaining Wall | -11.00 to -7.20 | B2 | 42031 | 42033 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1885 | inspection of fixation for composite column (torque) CC9 axis A11/B14 | Composite Columns | Column | -7.20 to -3.80 | B1 | 42031 | 42033 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1886 | form work for panoramic elevator axis A5 to A6/B9 | Form Work | Panoramic Elevator | -11.00 to -7.20 | B2 | 42031 | 42033 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1887 | steel reinforcement for stair 1 axis A9/B4 | Steel Reinforcement | Stair | -3.80 to 0.45 | BOH | 42031 | 42037 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1888 | form work for core 2 axis B15/A9 | Form Work | Core | -7.20 to -3.80 | B1 | 42032 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1889 | steel reinforcement for core 7 axis C7/A2-A3 | Steel Reinforcement | Core | 4.50 to 7.90 |  | 42032 | 42035 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1890 | repair for ramp beam axis B3 to B6/A13 | Repair | Beam | -7.20 to -3.80 | B1 | 42032 | 42054 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1891 | form work for column CC3 axis A11/B9 west side | Form Work | Column | -3.80 to 1.10 | BOH | 42033 | 42033 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1892 | form work for column CC9 axis A11/B10 | Form Work | Column | -3.80 to 1.10 | BOH | 42032 | 42033 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1893 | surface preparation and repair work for R.C retaining wall axis C1/ A6 to A8 | Repair | Retaining Wall | -7.20 to -3.80 | B1 | 42032 | 42037 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1894 | form work for column C6 axis A13/B6 | Form Work | Column | -3.80 to 1.10 | BOH | 42032 | 42033 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1895 | drilling depth, diameter for missing / short reinforcement of Piles to proceed with Dowels Fixation. E(281-283-284) | Dowels | Piles | -13.50 to -12.50 | Raft | 42032 | 42033 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1896 | piles cutting level, surface preparation to proceed with casting grout E(281-282-283-284) | Grout | Piles | -13.50 to -12.50 | Raft | 42032 | 42033 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1897 | form work for column CC9 axis A11/B12 | Form Work | Column | -3.80 to 1.10 | BOH | 42032 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1898 | steel reinforcement for column CC9 axis A11/B10 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42032 | 42032 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1899 | steel reinforcement for column CC9 axis A11/B12 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42032 | 42032 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1900 | steel reinforcement for column C6 axis A13/B6 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42032 | 42033 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1901 | steel reinforcement for 2 columns C1 axis B20/A12-A14 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42035 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1902 | form work for 2 columns C1 axis B20/A12-A14 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42035 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1903 | piles surface preparation to proceed with epoxy application piles No. E(281-282-283-284-285-286) | Epoxy | Piles | -13.50 to -12.50 | Raft | 42033 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1904 | form work for column CC1 axis A10/B13 west side | Form Work | Column | -7.20 to -3.80 | B1 | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1905 | steel reinforcement for column CC1 west A10/B13 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1906 | form work for column CC7 axis A6/B14 | Form Work | Column | -7.20 to -3.80 | B1 | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1907 | steel reinforcement for column CC7 axis A6/B14 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1908 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1909 | form work for slab 5A-3 axis A9 to A11/B3 to B5 | Form Work | Slab | 1.05 | BOH | 42033 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1910 | form work for slab 5A-2 axis C1 to B5/A11 to A15 | Form Work | Slab | 1.05 | BOH | 42033 | 42040 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1911 | surface preparation for external diaphragm walls to proceed with geotextile 1st layer axis A7 to A10/B21 | Insulation | Diaphragm Wall | -11.00 to -4.50 | wall | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1912 | installation of geotextile 1st layer for external diaphragm walls to proceed with PVC membrane axis A7 to A10/B21 | Insulation | Diaphragm Wall | -11.00 to -4.50 | wall | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1913 | form work removal for section 5C-2 axis A11 to A15/B13 to B16 | Removing Form Work | Slab | -7.20 | B2 | 42033 | 42035 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1914 | installation and test of PVC memrane for external diaphragm walls axis A7 to A10/B21 | Insulation | Diaphragm Wall | -11.00 to -4.50 | wall | 42033 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1915 | installation of geotextile 2nd layer for external diaphragm wall axis A7 to A10/B21 | Insulation | Diaphragm Wall | -11.00 to -4.50 | wall | 42033 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1916 | installation and test of horizontal PVC membrane under raft part of section 28 axis A7 to A10/B19 to B21 | Insulation | Raft | -13.50 to -12.50 | Raft | 42033 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1917 | installation of horizontal geotextile 2nd layer under raft PVC membrane installation part of section 28 axis A7 to A10/B19 to B21 | Insulation | Raft | -13.50 to -12.50 | Raft | 42033 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1918 | installation of horizontal geotextile 1st layer under raft to proceed with PVC memrane installation for part of section 28 axis A7 to A10/B19 to B21 | Insulation | Raft | -13.50 to -12.50 | Raft | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1919 | form work for retainng wall axis A12 to A15/B21 | Form Work | Retaining Wall | -11.00 to -7.20 | B2 | 42033 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1920 | steel reinforcement for retaining wall axis A12 to A15/B21 | Steel Reinforcement | Retaining Wall | -11.00 to -7.20 | B2 | 42033 | 42035 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1921 | steel reinforcement for column C6 axis A12/B13 west | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1922 | steel reinforcement for column C1 axis A14/B13 west side | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1923 | form work for column C1 A14/B13 west | Form Work | Column | -7.20 to -3.80 | B1 | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1924 | steel reinforcement work for panoramic elevator axis A6/B10 | Steel Reinforcement | Panoramic Elevator | -11.00 to -7.20 | B2 | 42033 | 42035 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1925 | steel reinforcement for column CC7 axis A6/B13 west | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42033 | 42035 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1926 | form work for column CC7 axis A6/B13 west | Form Work | Column | -7.20 to -3.80 | B1 | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1927 | form work for column C6 axis A12/B13 west | Form Work | Column | -7.20 to -3.80 | B1 | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1928 | form work for column CC1 axis A11/B13 west | Form Work | Column | -7.20 to -3.80 | B1 | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1929 | steel reinforcement for column CC1 axis A11/B13 west | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42033 | 42035 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1930 | form work for column CC1 axis A10/B9 west | Form Work | Column | -3.80 to 1.10 | BOH | 42033 | 42033 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1931 | form work for core 7 axis A2 to A3/C7 | Form Work | Core | 4.50 to 7.90 | First Floor | 42035 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1932 | form work for core 4 axis A8/B9 | Form Work | Core | -11.00 to -7.20 | B2 | 42035 | 42042 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1933 | form work for core 3 axis A10 to A8/B10 to B12 | Form Work | Core | -3.80 to 1.10 | BOH | 42035 | 42038 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1934 | steel reinforcement for shear wall 1 axis B1 to B5/A1 | Steel Reinforcement | SHW | 5.40 to 10.30 | First Floor | 42035 | 42037 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1935 | steel reinforcement for column CC1* axis A8/B13 east side | Steel Reinforcement | Column | -7.20 to -3.80 | B2 | 42035 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1936 | steel reinforcement for column C6 axis A12/B9 west side | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42035 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1937 | form work for shear wall 1 axis B1 to B5/A1 | Form Work | SHW | 5.40 to 10.30 | First Floor | 42035 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1938 | check level and location of screed axis B19 to B21/A8 to A10 | Survey | Screed |  |  | 42035 | 42042 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1939 | form work for column CC1* axis A8/B13 east side | Form Work | Column | -7.20 to -3.80 | B2 | 42035 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1940 | bottom layer steel reinforcement work for slab 5A-1 axis C1 to B3/A9 to A12 | Steel Reinforcement | Slab | 1.05 | BOH | 42036 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1941 | bottom layer steel reinforcement work for slab 4A axis B17 to B19/A1 to A3 | Steel Reinforcement | Slab | 0.6 | BOH | 42036 | 42037 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1942 | form work for slab 5C-3 axis B15 to B19/A11 to A15 | Form Work | Slab | -7.20 | B2 | 42036 | 42037 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1943 | form work for ramp axis B7 to B12/A3 to A4 | Form Work | Ramp | -10.5 to -7.20 | B2 | 42036 | 42038 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1944 | drilling and fixation for ramp beam dowels axis A4/B6 | Dowels | Beam | -11.00 | B2 | 42036 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1945 | form work for shear wall 7 axis C3/A2 to A3 | Form Work | SHW | 5.40 to 8.00 |  | 42036 | 42038 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1946 | form work for 1 column CC7 axis A6/B10 | Form Work | Column | -11.00 to -7.20 | B2 | 42036 | 42038 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1947 | form work for panoramic elevator axis A6/B10 | Form Work | Panoramic Elevator | -11.00 to -7.20 | B2 | 42036 | 42038 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1948 | fixation of shear connector composite column CC9 axis A11/B14 | Shear Connectors | Column | -3.80 | B1 | 42036 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1949 | form work for panoramic elevator axis B9 to B10/A5 | Form Work | Panoramic Elevator | -11.00 to -7.20 | B2 | 42036 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1950 | steel reinforcement for 1 column C1 axis A8/B3 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42036 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1951 | form work for 1 column C1 axis A8/B3 | Form Work | Column | -3.80 to 1.10 | BOH | 42036 | 42037 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1952 | form work for 1 column C6 axis A12/B9 west | Form Work | Column | -3.80 to 1.10 | BOH | 42036 | 42037 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1953 | bottom steel reinforcement for slab 5C-3 axis B16 to B19/A11 to A15 | Steel Reinforcement | Slab | -7.20 | B2 | 42037 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1954 | steel reinforcement for shear wall 2* axis C8/A2 to A3 | Steel Reinforcement | SHW | 1.10 to 5.40 | Ground Floor | 42037 | 42037 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1955 | steel reinforcement for column C1 axis A7/B2 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42037 | 42038 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1956 | form work for column C1 axis A7/B2 | Form Work | Column | -3.80 to 1.10 | BOH | 42037 | 42038 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1957 | steel reinforcement cor column CC9 axis A11/B14 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42038 | 42039 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1958 | form work for column CC9 axis A11/B14 | Form Work | Column | -7.20 to -3.80 | BOH | 42037 | 42038 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1959 | form work for column CC1 axis A11/B13 east | Form Work | Column | -3.80 to 1.10 | BOH | 42037 | 42039 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1960 | steel reinforcement for column CC1 axis A11/B13 east | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42037 | 42038 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1961 | form work for column CC1 axis A10/B13 east | Form Work | Column | -7.20 to -3.80 | B1 | 42037 | 42038 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1962 | steel reinforcement for column CC1 axis A10/B13 west | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42037 | 42038 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1963 | bottom steel reinforcement for raft of part of section 22, 28 axis B19 to B21/A8 to A10 | Steel Reinforcement | Raft | -11.00 | Raft | 42037 | 42038 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1964 | top layer steel reinforcement for slab 5A-1 axis C1 to B3/A9 to A12 | Steel Reinforcement | Slab | 1.05 | BOH | 42038 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1965 | form work for raft of part of section 22, 28 axis B19 to B21/A8 to A10 (section 28') | Form Work | Raft | -11.00 | Raft | 42038 | 42039 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1966 | top steel reinforcement for raft of part of section 22, 28 axis B19 to B21/A8 to A10 | Steel Reinforcement | Raft | -11.00 | Raft | 42038 | 42039 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1967 | inspection for re-injectable hose and injection pie for raft section 22, 28 | Insulation | Raft | -11.00 | Raft | 42038 | 42049 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1968 | steel reinforcement for column CC3 axis A11/B9 west side | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42038 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1969 | form work for column CC3 axis A11/B9 west side | Form Work | Column | -3.80 to 1.10 | BOH | 42038 | 42042 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1970 | steel reinforcement for column CC1 axis A10/B9 east side | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42038 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1971 | form work for column CC1 axis A10/B9 east side | Form Work | Column | -3.80 to 1.10 | BOH | 42038 | 42042 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1972 | form work for column CC1* axis A8/B13 west side | Form Work | Column | -7.20 to -3.80 | B1 | 42038 | 42042 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1973 | steel reinforcement for column CC1* axis A8/B13 west side | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42038 | 42039 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1974 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1975 | form work for shear wall 2* axis C8/A2 to A3 | Form Work | SHW | 1.10 to 5.40 | Ground Floor | 42038 | 42039 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1976 | steel reinforcement for column CC7 axis A6/B13 east | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42039 | 42040 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1977 | CHECK LOCATION AND LEVEL OF P.C AS SHOWN IN ATTACHED SKETCH A4 to A5/B17 to B15 | Survey | P.C |  |  | 42039 | 42042 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1978 | form work for column CC7 axis A6/B13 east | Form Work | Column | -7.20 to -3.80 | B1 | 42039 | 42042 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1979 | steel reinforcement for core 7 axis C7/A2-A3 | Steel Reinforcement | Core | 7.90 to 11.30 | First Floor | 42039 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1980 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation piles No. E(213-214-215-216-217-218-219) | Dowels | Piles | -13.50 to -12.50 | Raft | 42039 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1981 | piles cutting level, surface preparation to proceed with casting grout piles No. H(208-209-211-212-213-214-215-216-217-218-219) | Grout | Piles | -13.50 to -12.50 | Raft | 42039 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1982 | top steel reinforcement for slab 5C-3 axis B16 to B19/A11 to A15 | Steel Reinforcement | Slab | -3.80 | B1 | 42039 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1983 | steel reinforcement for ramp beam axis B8 to B12/A4 | Steel Reinforcement | Beam | -11.00 to -7.20 | B2 | 42039 | 42042 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1984 | installation of injection pipe and re-injectable hose for slab 5C-3 axis B16 to B19/A11 to A15 | Insulation | Slab | -3.80 | B1 | 42040 | 42042 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1985 | form work for column C* (planted column) axis A13/B12 | Form Work | Column | -3.80 to 1.10 | BOH | 42040 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1986 | steel reinforcement for column C* (planted column) axis A13/B12 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42040 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1987 | top layer steel reinforcement work, dowels and final inspection for slab 4A axis C9 to B16/A1 to A3 | Steel Reinforcement | Slab | 1.10 | BOH | 42040 | 42042 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1988 | top layer steel reinforcement work, dowels and final inspection for slab 4A axis B19 to B16/A1 to A3 | Steel Reinforcement | Slab | 0.6 | BOH | 42040 | 42042 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1989 | steel reinforcement work for core 5 axis B6 to B8/A8 to A10 | Steel Reinforcement | Core | -0.4 to 3.00 | Ground Floor | 42040 | 42045 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1990 | form work for column C* (planted column) axis A13/B10 | Form Work | Column | -3.80 to 1.10 | BOH | 42040 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1991 | steel reinforcement for column C* (planted column) axis A13/B10 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42040 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1992 | form work for column C* (planted column) axis A13/B9 | Form Work | Column | -3.80 to 1.10 | BOH | 42040 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1993 | steel reinforcement for column C* (planted column) axis A13/B9 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42040 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1994 | steel reinforcement for retaining wall axis A15/ B6 to B9 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 42040 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1995 | form work for shear wall 6 axis C4/A2 to A3 | Form Work | SHW | 8.00 to 12.10 | First Floor | 42042 | 42044 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1996 | form work for core 7 axis A2 to A3/C7 | Form Work | Core | 7.90 to 11.30 | First Floor | 42040 | 42044 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1997 | surface preparation and repair for 2 columns CC7 and 1 column C6 and 1 column C6 "east") axis A12-A13/B6-B12 | Repair | Column | -3.80 to 1.10 | BOH | 42040 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1998 | bottom layer steel reinforcement work, dowels and final inspection for slab 2-2B axis B15 to B19/A8 to A11 | Steel Reinforcement | Slab | -7.20 | B2 | 42040 | 42042 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-1999 | steel reinforcement for shear wall 6 axis C4/A2 to A3 | Steel Reinforcement | SHW | 8.00 to 12.10 | First Floor | 42040 | 42045 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2000 | steel reinforcement for 1 column C1 axis B9/between A14-A15 east side | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42042 | 42044 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2001 | steel reinforcement for shear wall 7 axis C3/A1 to A3 | Steel Reinforcement | SHW | 8.00 to 12.10 | First Floor | 42042 | 42045 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2002 | form work for slab section 5D-1 axis B9 to B14/A4 to A6 | Form Work | Slab | -7.20 | B2 | 42042 | 42044 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2003 | form work for slab section 2-1B axis B9 to B13/A6 to A8 | Form Work | Slab | -7.20 | B2 | 42042 | 42044 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2004 | piles cutting level, surface preparation to proceed with casting grout for piles No. H(370-371-396-395-394-393-392-410-412-414)& E(220) | Grout | Piles | -13.50 to -12.50 | Raft | 42042 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2005 | drilling depth, diameter for mssing/short reinforcement of piles to proceed with dowels fixation for piles No. H(329-394-396-410-412-414)& E(220) | Dowels | Piles | -13.50 to -12.50 | Raft | 42042 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2006 | surface preparation and repair of slab 5A-4& 5C-1 axis B8 to B7/A4 to A3 | Repair | Slab | -3.80 | B1 | 42042 | 42054 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2007 | form work for retaining wall axis B6 to B9/A15 | Form Work | Retaining Wall | -3.80 to 1.10 | BOH | 42042 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2008 | form work for stair case 12 axis B1/A2 | Form Work | Stair | -0.45 to 1.10 | BOH | 42042 | 42044 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2009 | check the level and location of P.C form work axis B19 to B16/A9 to A6 | Survey | P.C |  |  | 42042 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2010 | steel reinforcement for shear wall 1 axis A1/B5 to B9 | Steel Reinforcement | SHW | 5.40 to 8.00 | First Floor | 42042 | 42044 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2011 | form work for shear wall 1 axis A1/B9 to B10 | Form Work | SHW | 1.10 to 5.40 | Ground Floor | 42042 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2012 | bottom steel reinforcement for ramp axis B7 to B13/A3 to A4 | Steel Reinforcement | Ramp | -11.00 to -7.20 | B2 | 42042 | 42044 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2013 | surface preparation and repair for core 3 axis B10 to B12/A8 to A10 | Repair | Core | -3.80 to 1.10 | BOH | 42043 | 42056 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2014 | surface preparation for P.C to proceed with geotextile 1st layer axis B19 to B18/A4 to A5 | Insulation | P.C | -13.50 to -12.50 | Raft | 42043 | 42049 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2015 | bottom layer steel reinforcement work for slab 5A-2 axis C1 to B5/A11 to A15 | Steel Reinforcement | Slab | 1.05 | BOH | 42043 | 42045 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2016 | bottom layer steel reinforcement work for slab section 5A-3 axis A9 to A11/B3 to B5 | Steel Reinforcement | Slab | 1.10 | BOH | 42043 | 42045 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2017 | steel reinforcement for L shape ramp beam axis B3 to B6/A13 to A14 | Steel Reinforcement | Beam | -3.80 to 1.05 | BOH | 42043 | 42050 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2018 | fixation of shear connector for composite column CC7 axis A12/B16 | Shear Connectors | Column | -3.80 | B1 | 42043 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2019 | inspection of fixation for composite column CC4 (Torque) axis A12/B18 | Composite Columns | Column | -7.20 to -3.80 | B1 | 42043 | 42045 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2020 | inspection of fixation of composite column (Torque) CC7 axis A12/B16 | Composite Columns | Column | -7.20 to -3.80 | B1 | 42043 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2021 | inspection of fixation for composite column CC4 (Torque) axis B16/A10-A11 | Composite Columns | Column | -7.20 to -3.80 | B1 | 42043 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2022 | steel reinforcement for column C1 axis A14/B16 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42043 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2023 | form work for column C1 axis A14/B16 | Form Work | Column | -7.20 to -3.80 | B1 | 42043 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2024 | steel reinforcement for column C1 axis A14/B18 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42043 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2025 | form work for composite column C1 axis A14/B18 | Form Work | Column | -7.20 to -3.80 | B1 | 42043 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2026 | form work for column C1 axis A10/B20 | Form Work | Column | -11.00 to -7.20 | B2 | 42043 | 42045 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2027 | steel reinforcement for column C1 axis A10/B20 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42043 | 42045 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2028 | fixation of shear connector composite column CC4 axis A10-A11/B16 | Shear Connectors | Column | -3.80 | B1 | 42043 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2029 | fixation of shear connector composite column CC4 axis A12/B18 | Shear Connectors | Column | -3.80 | B1 | 42043 | 42045 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2030 | form work for shear wall 1 axis A1 to A2/B9 to B5 | Form Work | SHW | 5.40 to 8.00 | First Floor | 42043 | 42045 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2031 | check the level and location of P.C form work axis B18 to B19/A8 to A5 | Survey | P.C |  |  | 42043 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2032 | steel reinforcement for retaining wall axis A15/B9 to B12 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 42043 | 42044 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2033 | form work for retaining wall axis A14 to A15/B6 to B9 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 42043 | 42044 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2034 | inspection for holes and dowels fixation for beams of panoramic elevators axis A5 to A6/B9 to B10 | Dowels | Beam | -7.20 | B2 | 42043 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2035 | steel reinforcement for column C1 axis B10/A15 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42043 | 42044 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2036 | steel reinforcement for column C1 axis A15//B12 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42043 | 42044 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2037 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation E(210) | Dowels | Piles | -13.50 to -12.50 | Raft | 42044 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2038 | piles cutting level, surface preparation and form work to proceed with casting grout piles No. E(210) | Grout | Piles | -13.50 to -12.50 | Raft | 42044 | 42044 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2039 | piles surface preparation to proceed with epoxy application H(370-371-391-392-393-394-395-396-410-412-414) | epoxy | Piles | -13.50 to -12.50 | Raft | 42044 | 42051 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2040 | piles surface preparation to proceed with epoxy application for piles No. E(197-198-199-200-202-203-207-208-209-210-211-212-213-214-215-216-217-218-219) | epoxy | Piles | -13.50 to -12.50 | Raft | 42044 | 42045 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2041 | steel reinforcement for panoramic beams axis B9 to B10/A5 to A6 | Steel Reinforcement | Beam | -7.20 | B2 | 42044 | 42054 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2042 | form work for stair 1 axis A9/B4 | Form Work | Stair | -0.45 to 1.10 | BOH | 42044 | 42046 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2043 | form work for retaining wall axis A15/B9 to B10 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 42045 | 42050 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2044 | form work for column CC4 axis A10 to A11/B16 | Form Work | Column | -7.20 to -3.80 | B1 | 42044 | 42045 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2045 | steel reinforcement for column CC4 axis A10 to A11/B16 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42044 | 42045 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2046 | installation of horizontal geotextile 2nd layer to proceed with protection screed pouring axis A6 to A8/B16 to B19 | Insulation | Screed | -13.50 to -12.50 | Raft | 42044 | 42054 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2047 | installation and test of horizontal PVC membrane under raft section 27 axis A6 to A8/B19 to B16 | Insulation | Raft | -13.50 to -12.50 | Raft | 42044 | 42052 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2048 | installation of horizontal geotextile 1st layer raft section 27 axis A6 to A8/B19 to B16 | Insulation | Raft | -13.50 to -12.50 | Raft | 42044 | 42052 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2049 | installation of horizontal geotextile 1st layer section 25 axis A4 to A5/B14 to B18 | Insulation |  | -13.50 to -12.50 | Raft | 42044 | 42049 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2050 | installation of horizontal geotextile 2nd layer to proceed with protection screed pouring section 25 axis A4 to A5/B14 to B18 | Insulation | Screed | -13.50 to -12.50 | Raft | 42044 | 42049 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2051 | installation and test of horizontal PVC membrane under raft section 25 | Insulation | Raft | -13.50 to -12.50 | Raft | 42044 | 42049 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2052 | surface preparation prior vertical geotextile for external diaphragm wall axis A7 to A12/B21 | Insulation | Diaphragm Wall | -11.00 to -04.50 | B2, B1 | 42044 | 42049 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2053 | installation of vertical geotextile 1st layer to proceed with PVC membrane installation axis A7 to A12/B21 | Insulation | Retaining Wall | -11.00 to -04.50 | B2, B1 | 42044 | 42049 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2054 | installation of vertical geotextile 2nd layer to proceed with retaining wall reinforcement axis A7 to A12/B21 | Insulation | Retaining Wall | -11.00 to -04.50 | B2, B1 | 42044 | 42049 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2055 | form work for retaining wall axis B9 to B10/A15 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 42044 | 42045 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2056 | form work for column CC7 axis B16/A12 | Form Work | Column | -7.20 to -3.80 | B1 | 42044 | 42045 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2057 | steel reinforcement for column CC7 axis B16/A12 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42044 | 42045 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2058 | steel reinforcement for column C1 axis A15/B9 west | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42044 | 42045 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2059 | form work for column C1 axis A15/B9 west | Form Work | Column | -3.80 to 1.10 | BOH | 42044 | 42045 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2060 | bottom layer steel reinforcement for slab section 2-1B axis B9 to B13/A6 to A8 | Steel Reinforcement | Slab | -7.20 | B2 | 42045 | 42052 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2061 | bottom layer steel reinforcement for slab 5D-1 axis B9 to B13/A4 to A6 | Steel Reinforcement | Slab | -7.20 | B2 | 42045 | 42052 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2062 | top layer steel reinforcement for ramp axis A3 to A4/B7 to B12 | Steel Reinforcement | Ramp | -11.00 to -7.20 | B2 | 42045 | 42051 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2063 | drilling and fixation for ramp top reinforcement due to design change axis A3 to A4/B7 to B12 |  | Ramp | -11.00 to -7.20 | B2 | 42045 | 42050 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2064 | steel reinforcement for ramp beam axis B5 to B8/A3 | Steel Reinforcement | Beam | -11.00 to -7.20 | B2 | 42045 | 42051 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2065 | steel reinforcement for column CC4 axis A12/B18 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42045 | 42050 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2066 | installation of composite column (Torque) axis A10/B18-B19 | Composite Columns | Column | -7.20 to -3.80 | B1 | 42045 | 42045 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2067 | form work for column CC4 axis A12/B18 | Form Work | Column | -7.20 to -3.80 | B1 | 42045 | 42051 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2068 | Installation and Test of PVC membrane to Proceed with Geotextile 2nd layer A7 to A12/B21 | Insulation |  | -11.00 to -4.50 | B2, B1 | 42044 | 42049 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2069 | steel reinforcement for core 4 axis A7 to A9/B8 to B9 | Steel Reinforcement | Core | -7.20 to -3.80 | B1 | 42050 | 42051 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2070 | form work for shear wall 7 axis C3/A2 to A3 | Form Work | SHW | 9.00 to 11.30 | First Floor | 42049 | 42051 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2071 | check the level and location of screed axis B17 to B14/A4 to A5 | Survey | Screed |  |  | 42050 | 42050 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2072 | check the level and location of P.C form work axis B18 to B19/A4 to A6 | Survey | P.C |  |  | 42050 | 42050 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2073 | top layer steel reinforcement work, dowels and final inspection for slab 5A-2 | Steel Reinforcement | Slab | 1.05 | BOH | 42050 | 42053 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2074 | top layer steel reinforcement work, dowels and final inspection for slab 5A-3 axis A8 to A12/B3 to B5 | Steel Reinforcement | Slab | 1.10 | BOH | 42050 | 42053 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2075 | piles cutting level, surface preparation to proceed with casting grout piles No. E(221-222-225-226-227-228-231) | Grout | Piles | -13.50 to -12.50 | Raft | 42050 | 42051 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2076 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation piles No. E(221-222-225-228) | Dowels | Piles | -13.50 to -12.50 | Raft | 42050 | 42051 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2077 | bottom layer steel reinforcement work for raft 25' | Steel Reinforcement | Raft | -11.00 | B2 | 42050 | 42051 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2078 | form work for retaining wall axis A9 to A13/B21 | Form Work | Retaining Wall | -11.00 to -7.20 | B2 | 42050 | 42051 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2079 | steel reinforcement for retaining wall axis A9 to A13/B21 | Steel Reinforcement | Retaining Wall | -11.00 to -7.20 | B2 | 42050 | 42051 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2080 | inspection of holes and dowels fixation fir stair 12 | Dowels | Stair | 1.10 | BOH | 42050 | 42050 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2081 | form work for core 4 axis A8/B9 | Form Work | Core | -7.20 to -3.80 | B1 | 42051 | 42051 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2082 | form work for core 5 axis A8 to A10/B6 to B8 | Form Work | Core | -0.4 to 3.00 | Ground Floor | 42051 | 42052 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2083 | top layer steel reinforcement work, fowels, embedded items and final inspection for raft section 25' | Steel Reinforcement | Raft | -11.00 | Raft | 42052 | 42053 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2084 | steel reinforcement for stair 1 axis A9/B4 | Steel Reinforcement | Stair | -0.45 to 1.10 | BOH | 42044 | 42045 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2085 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation piles No. E(223-234-237) | Dowels | Piles | -13.50 to -12.50 | Raft | 42053 | 42054 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2086 | piles surface preparation to proceed with epoxy application piles No. E(223-234-237-238) | epoxy | Piles | -13.50 to -12.50 | Raft | 42053 | 42057 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2087 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2088 | piles cutting level, surface preparation to proceed with casting grout E(223-234-237-238) | Grout | Piles | -13.50 to -12.50 | Raft | 42053 | 42054 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2089 | top layer steel reinforcement work, dowels and final inspection for slab 2-1B axis A6 to A8/B9 to B13 | Steel Reinforcement | Slab | -7.20 | B2 | 42053 | 42054 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2090 | form work for raft 25' axis A3 to A6/B13 to B17 | Form Work | Raft | -11.00 | Raft | 42053 | 42053 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2091 | steel reinforcement for column CC5 axis A2 to A3/C9 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42053 | 42054 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2092 | steel reinforcement for shear wall 1 axis A1 to A2/C9 to C11 | Steel Reinforcement | SHW | 1.10 to 5.40 | Ground Floor | 42053 | 42054 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2093 | steel reinforcement for shear wall 2 axis C10/A1 to A3 | Steel Reinforcement | SHW | 1.10 to 5.40 | Ground Floor | 42053 | 42054 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2094 | steel reinforcement for core 2 axis B14 to B15/A8 to A10 | Steel Reinforcement | Core | -3.80 to -0.40 | BOH | 42053 | 42054 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2095 | top layer steel reinforcement work, dowels and final inspection for slab 5D-1 | Steel Reinforcement | Slab | -7.20 | B2 | 42053 | 42054 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2096 | check the level and location of plain concrete axis B18 to B19/A4 to A6 | Survey | P.C |  |  | 42053 | 42054 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2097 | check the level and location of screed axis B19 to B15/A5 to A6 | Survey | Screed |  |  | 42053 | 42054 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2098 | form work for shear wall 2 axis C10/A1 to A3 | Form Work | SHW | 1.10 to 5.40 | Ground Floor | 42053 | 42054 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2099 | form work for shear wall 1 axis C9 to C11/A1 | Form Work | SHW | 1.10 to 5.40 | Ground Floor | 42053 | 42058 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2100 | bottom layer steel reinforcement for slab axis B7/A3 to A4 | Steel Reinforcement | Slab | -7.20 | B2 | 42054 | 42057 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2101 | top layer steel reinforcement for slab axis B7/A3 to A4 | Steel Reinforcement | Slab | -7.20 | B2 | 42054 | 42057 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2102 | steel reinforcement for 1 column CC1 axis B9/A8 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42054 | 42056 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2103 | form work for column CC5 axis A2 to A3/C9 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42054 | 42056 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2104 | steel reinforcement work for core 5 axis B6 to B8/A8 to A10 | Steel Reinforcement | Core | 3.00 to 6.40 | Ground Floor | 42054 | 42072 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2105 | form work for 1 column CC1 axis B9/A8 | Form Work | Column | -7.20 to -3.80 | B1 | 42054 | 42057 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2106 | form work for slab 5C-4 axis B21 to B19/A10 to A15 | Form Work | Slab | -7.20 | B2 | 42054 | 42054 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2107 | form work for slab at hotel tower axis B1 to B9/A1 to A3 | Form Work | Slab | 5.40 | First Floor | 42056 | 42058 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2108 | piles cutting level, surface preparation to proceed with casting grout H(427) E(253-254-255-256-257-258) | Grout | Piles | -13.5 to -12.5 | Raft | 42056 | 42058 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2109 | steel reinforcement for column C1 axis A5/B9 west side | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42057 | 42058 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2110 | bottom layer steel reinforcement work for slab 5C-4 axis B19 to B21/A10 to A15 | Steel Reinforcement | Slab | -7.20 | B2 | 42056 | 42058 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2111 | steel reinforcement for 4 columns C1 axis A4/B9, B10, B12, B13 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42056 | 42057 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2112 | form work for 4 columns C1 axis A4/B9, B10, B12, B13 | Form Work | Column | -7.20 to -3.80 | B1 | 42056 | 42057 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2113 | drilling depth, diameter for missing/ short reinforcement of piles to proceed with dowels fixation piles H(427-426)& H(253-254-255-256-257-258) | Dowels | Piles | -13.5 to -12.5 | Raft | 42056 | 42058 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2114 | check the level and location of P.C form work axis B21 to B19/A3 to A1 | Survey | P.C |  |  | 42057 | 42058 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2115 | form work for column C1 axis A5/B9 west | Form Work | Column | -7.20 to -3.80 | B1 | 41995 | 42058 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2116 | steel reinforcement for column C1 axis A5/B10 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 41995 | 42058 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2117 | form work for column C1 axis A5/B10 | Form Work | Column | -7.20 to -3.80 | B1 | 42057 | 42058 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2118 | steel reinforcement for column C7 axis A5/B12-B13 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42057 | 42058 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2119 | form work for column C7 axis A5/B12-B13 | Form Work | Column | -7.20 to -3.80 | B1 | 42057 | 42058 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2120 | piles surfacepreparation to proceed with epoxy application pile No. E(222) | Epoxy | Piles | -13.50 to -12.50 | Raft | 42057 | 42058 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2121 | steel reinforcement for column CC7 axis A6/B12 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42057 | 42058 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2122 | form work for column CC7 axis A6/B12 | Form Work | Column | -7.20 to -3.80 | B1 | 42057 | 42058 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2123 | steel reinforcement for column C1 axis A5/B13 east side | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42057 | 42058 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2124 | form work for column C1 axis A5/B13 east side | Form Work | Column | -7.20 to -3.80 | B1 | 42057 | 42058 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2125 | steel reinforcement for panoramic elevator between axis B9-B10/between axis A5 | Steel Reinforcement | Panoramic Elevator | -7.20 to -3.80 | B1 | 42057 | 42058 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2126 | steel reinforcement for panoramic elevator axis A5 to A6/B9 | Steel Reinforcement | Panoramic Elevator | -7.20 to -3.80 | B1 | 42057 | 42058 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2127 | form work for panoramic elevator axis A5/B9 to B10 | Form Work | Panoramic Elevator | -7.20 to -3.80 | B1 | 42057 | 42060 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2128 | steel reinforcement for panoramic elevator axis A5 to A6/B10 to B11 | Steel Reinforcement | Panoramic Elevator | -7.20 to -3.80 | B1 | 42057 | 42059 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2129 | form work for column C1 axis A4/B9 | Form Work | Column | -7.20 to -3.80 | B1 | 42057 | 42058 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2130 | steel reinforcement for column C1 axis A4/B9 west side | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42057 | 42058 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2131 | form work for beam 5D-1 axis B12 to B10 | Form Work | Beam | -7.20 | B2 | 42057 | 42059 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2132 | form work for column C1 axis A4/B14 | Form Work | Column | -7.20 to -3.80 | B1 | 42058 | 42059 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2133 | form work for panoramic elevator axis A5 to A6/B10 to B11 | Form Work | Panoramic Elevator | -7.20 to -3.80 | B1 | 42058 | 42060 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2134 | steel reinforcement for column C1 axis A5/B14 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42058 | 42059 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2135 | form work for column C1 axis A5/B14 | Form Work | Column | -11.00 to -7.20 | B2 | 42058 | 42059 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2136 | form work for core 2 axis B14 to B15/A8 to A10 | Form Work | Core | -3.80 to -0.40 | BOH | 42058 | 42060 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2137 | steel reinforcement for core 3 axis B10 to B12/A8 to A10 | Steel Reinforcement | Core | -0.4 to +3.00 | Ground Floor | 42058 | 42063 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2138 | steel reinforcement for shear wall 1 from axis B15 to B19 /A1 | Steel Reinforcement | SHW | 1.10 to 5.40 | Ground Floor | 42058 | 42064 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2139 | bottom layer steel reinforcement for Raft section 27 axis B16to B19 / A5 to A8 | Steel Reinforcement | Raft | -11.00 | raft | 42058 | 42060 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2140 | inspection of holes and dowels fixation for core 8 | dowels | Core | 5.40 | slab | 42058 | 42059 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2141 | installation of composite column (Torque) axis cc7 axis A6/B9 west | Composite Columns | Column | -7.20 to -3.80 | B1 | 42058 | 42059 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2142 | installation of composite column (Torque) axis cc7 axis A6/B10 | Composite Columns | Column | -7.20 to -3.80 | B1 | 42058 | 42059 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2143 | fixation of shear connector composite column axis cc7 axis A6/B9 west | Shear Connectors | Column | -7.20 to -3.80 | B1 | 42058 | 42061 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2144 | fixation of shear connector composite column axis cc7 axis A6/B10 | Shear Connectors | Column | -7.20 to -3.80 | B1 | 42058 | 42059 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2145 | Check level and location of screed as shown in attached sketch B19-B17/A4-A6 | Survey | Screed | -12.50 | under raft | 42059 | 42060 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2146 | Check level and location of P.C as shown in attached sketch B21-B17/A5-A1 | Survey | P.C | -12.51 | under raft | 42059 | 42060 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2147 | drilling depth, diameter for missing/ short reinforcement of piles to proceed with dowels fixation piles E 229-224-233-235-236-246-247-248-249-250-251-252-259-260 | Dowels | Piles | -13.5 to -12.5 | under Raft | 42059 | 42063 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2148 | piles cutting level, surface preparation to proceed with casting grout E-229-230-232-224-233-241-242-245-235-236-246-247-248-249-250-251-252-259-260 | Grout | Piles |  |  | 42059 | 42063 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2149 | installation for re injectable hose for slab 5C-4 axis B19 to B21/A10 to A15 | Insulation | Slab | -7.20 | B2 | 42059 | 42064 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2150 | top layer steel reinforcement work for slab 5C-4 axis B19 to B21/A10 to A15 | Steel Reinforcement | Slab | -7.20 | B2 | 42059 | 42072 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2151 | steel reinforcement for panoramic elevator A6/B10 | Steel Reinforcement | Panoramic Elevator | -7.20 to -3.80 | B1 | 42059 | 42061 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2152 | steel reinforcement for 4 columns C1 axis A4,A5/B9,east side A4, A5, B13 west side | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42059 | 42060 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2153 | form work for 4 columns C1 axis A4,A5/B9,east side A4, A5, B13 west side | Form Work | Column | -7.20 to -3.80 | B1 | 42059 | 42060 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2154 | installation of geotextile 2nd layer for external diaphragm wall axis B13 to B18 /A15 | Insulation | Diaphragm Wall | -4.50 to Finish | Ground Floor | 42059 | 42064 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2155 | installation of geotextile 1st layer for external diaphragm wall axis B13 to B18 /A15 | Insulation | Diaphragm Wall | -4.50 to Finish | Ground Floor | 42059 | 42064 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2156 | installation and test PVC for external diaphragm wall axis B13 to B18 /A15 | Insulation | Diaphragm Wall | -4.50 to Finish | Ground Floor | 42059 | 42064 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2157 | surface preparation for external diaphragm wall axis B13 to B18 /A15 | Insulation | Diaphragm Wall | -4.50 to Finish | Ground Floor | 42059 | 42064 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2158 | form work slab as attached B6,B8/A3,A4 | Form Work | Slab | -3.80 | B1 | 42059 | 42060 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2159 | form work removal for ramp A3,A4 / B7 B12 | Removing Form Work | Ramp | -11.00 to -7.20 | B2 | 42059 | 42061 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2160 | bottom steel reinforcement for slab as attached | Steel Reinforcement | Slab | -3.80 | B1 | 42060 | 42061 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2161 | form work for column cc7 west A6/B9 | Form Work | Column | -7.20 to -3.80 | B1 | 42060 | 42063 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2162 | steel reinforcement for column CC7 west A6/B9 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42060 | 42061 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2163 | top layer steel reinforcement work for raft section 27 axis A6 to A7 /B17 toB18 | Steel Reinforcement | Raft | -11.00 | raft | 42060 | 42063 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2164 | installation of injection pipe and re-injectable hose for raft section 27 axis A6 to A7 /B17 toB18 | Insulation | Raft | -11.00 | raft | 42060 | 42064 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2165 | form work for raft | Form Work | Raft | -11.00 | raft | 42060 | 42063 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2166 | form work for stair case 9 A7,A8/B14-B16 | Form Work | Stair | -11.00 to -7.20 | B2 | 42060 | 42064 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2167 | inspection of holes and dowels fixation of slab | dowels | Slab | 5.40 | First Floor | 42060 | 42063 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2168 | form work for retaining wall B12 to B16/A15 | Form Work | Retaining Wall | -7.20 to -3.80 | B1 | 42060 | 42063 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2169 | steel reinforcement for retaining wall B12 to B16/A15 | Steel Reinforcement | Retaining Wall | -7.20 to -3.80 | B1 | 42060 | 42061 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2170 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2171 | fixation of shear connector composite columns CC7 B4/A9,A10,A11 | Shear Connectors | Column | 5.40 | First Floor | 42060 | 42063 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2172 | form work for panoramic elevator A5,A6/B9 | Form Work | Panoramic Elevator | -7.20 to -3.80 | B1 | 42060 | 42061 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2173 | form work for panoramic elevator A6/B10 | Form Work | Panoramic Elevator | -7.20 to -3.80 | B1 | 42060 | 42063 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2174 | top steel reinforcement for slab as ataached | Steel Reinforcement | Slab | -3.80 | B1 | 42060 | 42063 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2175 | ispection of holes and dowels fixation for core 5 slab axis B8/A8 to A9 | Dowels | Slab | -3.80 | B1 | 42060 | 42061 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2176 | steel reinforcement for column C1 axis A4/B14 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42058 | 42059 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2177 | fixation of shear connector composite column CC7 axis B9/A6 east side | Shear Connectors | Column | -7.20 to -3.80 | B1 | 42063 | 42063 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2178 | steel reinforcement for column C1 axis A1/B19 | Steel Reinforcement | Column | 0.65 to 5.40 | Ground Floor | 42063 | 42063 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2179 | form work for column C1 axis A1/B19 | Form Work | Column | 0.65 to 5.40 | Ground Floor | 42063 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2180 | form work for shear wall 1 axis A1/B17 to B19 | Form Work | SHW | 0.65 to 5.40 | Ground Floor | 42063 | 42064 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2181 | bottom layer steel reinforcement for part of slab 1A axis B8 to B9/A8 to A10 | Steel Reinforcement | Slab | -3.80 | B1 | 42063 | 42068 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2182 | top layer steel reinforcement for part of slab 1A axis B8 to B9/A8 to A10 | Steel Reinforcement | Slab | -3.80 | B1 | 42063 | 42068 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2183 | form work removal 5A-2& 5A-3 axis B1 to A5/A9 to A5 | Removing Form Work | Slab | 1.05 | BOH | 42063 | 42063 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2184 | form work removal 5D-1& 2-1B axis B9 to B13/A9 to A8 | Removing Form Work | Slab | -7.20 | B2 | 42063 | 42063 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2185 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2186 | piles surface preparation to proceed with epoxy application axis E(221-224-225-226-227-228-229-230-231-232-235-236-241-242-245-246-247-248-249-250-251-252) | Epoxy | Piles | -13.50 to -12.50 | raft | 42064 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2187 | installation of horizontal geotextile 1st layer to proceed with PVC axis B18 to B19/A4 to A6 | Insulation |  | -13.50 to -12.50 | raft | 42063 | 42070 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2188 | surface preparation for P.C to proceed with geotextile 1st layer B18 to B19/A4 to A6 | Insulation | P.C | -13.50 to -12.50 | raft | 42063 | 42070 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2189 | installation and test of PVC membrane and water bars to proceed with geotextile 2nd layer axis B18 to B19/A4 to A6 | Insulation |  | -13.50 to -12.50 | raft | 42063 | 42070 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2190 | installation of horizontal geotextile 2nd layer to proceed with prtection screed pouring axis B18 to B19/A4 to A6 | Insulation | Screed | -13.50 to -12.50 | raft | 42063 | 42070 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2191 | form work for slab section 2-2A axis A7 to A12/B13 to B16 | Form Work | Slab | -3.80 | B1 | 42064 | 42066 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2192 | form work for slab section 5C-2 axis A12 to A15/B13 bto B16 | Form Work | Slab | -3.80 | B1 | 42064 | 42066 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2193 | form work for core 3 axis A8 to A10/B10 to B12 | Form Work | Core | -0.4 to 2.9 | Ground Floor | 42064 | 42066 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2194 | steel reinforcement for column CC6 axis B15/C11 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42064 | 42066 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2195 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2196 | check the level and location of P.C form work axis B21 to B19/A4 to A8 | Survey | P.C |  |  | 42064 | 42064 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2197 | steel reinforcement work for column CC7 axis B9/A6 east side | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42064 | 42064 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2198 | form work for shear wall 1 axis A1/B15 to B17 | Form Work | SHW | 1.10 to 5.40 | Ground Floor | 42064 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2199 | fixation of shear connector composite column CC4 axis D3/B19& A10/B18 | Shear Connectors | Column | -7.20 to -3.80 | B1 | 42064 | 42064 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2200 | form work for column CC6 axis A3/C11 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42064 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2201 | piles cutting level, surface preparation to proceed with casting grout piles No. E(238-239-243-244-261-262-264-265-266-267-268-269-270-271-272-273-274-275-276-277-278-279-280) | Grout | Piles | -13.50 to -12.50 | raft | 42064 | 42071 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2202 | drilling depth, diameter for missing/short reinforcement of piles to proceed with dowels fixation piles No. E(243-244-262-263-264-265-266-267-268-269-270-272-273-276-277-239-279) | dowels | Piles | -13.50 to -12.50 | raft | 42064 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2203 | steel reinforcement for column CC4 axis D3/B18 to B19 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42064 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2204 | steel reinforcement for 3 columns C1 axis B19/A10-A12-A14 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42064 | 42066 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2205 | steel reinforcement for column C1 axis B20/A10 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42064 | 42066 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2206 | steel reinforcement for 3 columns CC7 axis B4/A9-A10-A11 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42064 | 42066 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2207 | form wok for roof slab section 5D-1 axis B9 to B13/A4 to A6 | Form Work | Slab | -3.80 | B1 | 42064 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2208 | form work for column CC7 axis B9/A6 east side | Form Work | Column | -7.20 to -3.80 | B1 | 42065 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2209 | bottom steel reinforcement for roof slab 5D-1 axis B9 to B13/A4 to A6 | Steel Reinforcement | Slab | -3.80 | B1 | 42065 | 42068 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2210 | form work for roof slab 2-1B axis B9 to B13/A6 to A7 | Form Work | Slab | -3.80 | B1 | 42065 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2211 | steel reinforcement for 2 beams axis B14/A12-A14& B16/A12-A14 | Steel Reinforcement | Beam | -3.80 | B1 | 42065 | 42068 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2212 | bottom steel reinforcement for slab section 2-2A axis B13 to B16/A7 to A11 | Steel Reinforcement | Slab | -3.80 | B1 | 42065 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2213 | bottom steel reinforcement for slab section 5C-2 axis B13 to B16/A11 to A15 | Steel Reinforcement | Slab | -3.80 | B1 | 42065 | 42070 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2214 | check the level and location of screed axis B16 to B19/A5 to A4 | Survey | Screed |  |  | 42066 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2215 | form work for 4 columns C1 axis B19/A14-A12-A10& B20/A10 | Form Work | Column | -7.20 to -3.80 | B1 | 42065 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2216 | installation of geotextile 1st layer under PVC for part of section 28-29 axis A3 to A7/B19 to B21 | Insulation |  | -13.50 to -12.50 | raft | 42065 | 42074 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2217 | form work for columns column CC4 axis D3/B18 to B19 | Form Work | Column | -7.20 to -3.80 | B1 | 42065 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2218 | surface preparation for P.C to proceed with geotextile 1st layer axis A3 to A7/B19 to B21 | Insulation | P.C | -13.50 to -12.50 | raft | 42065 | 42074 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2219 | installation of horizontal geotextile 2nd layer to proceed with protection screed pouring axis A3 to A7/B19 to B21 | Insulation | Screed | -13.50 to -12.50 | raft | 42065 | 42074 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2220 | installation and test of horizontal PVC membrane under raft part of section 28-29 axis A3 to A7/B19 to B21 | Insulation | Raft | -13.50 to -12.50 | raft | 42065 | 42074 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2221 | piles surface preparation to proceed with epoxy application for piles No. E(238-239-243-244-265-267-272-273-278-279) | Epoxy | Piles | -13.50 to -12.50 | raft | 42065 | 42070 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2222 | form work for 3 columns CC7 axis B4/A9-A10-A11 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42066 | 42066 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2223 | top steel reinforcement for slab section 2-2A axis B13 to B16/A7 to A11 | Steel Reinforcement | Slab | -3.80 | B1 | 42066 | 42067 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2224 | inspection for holes and dowels fixation for slab around the panoramic elevator axis A5 to A6/B9 to B10 | dowels | Slab | -3.80 | B1 | 42066 | 42070 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2225 | form work for core 5 axis A8 to A10/B6 to B8 | Form Work | Core | 2.9 to 6.2 | Ground Floor | 42066 | 42068 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2226 | bottom layer steel reinforcement for first pour strip of slab axis A1/B1 to C5 | Steel Reinforcement | Slab | 5.40 | First Floor | 42066 | 42067 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2227 | form work for shear wall 1 axis A1/B1 to C5 | Form Work | SHW | 8.80 to 12.20 | First Floor | 42066 | 42070 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2228 | steel reinforcement for shear wall 1 axis A1/B1 to C5 | Steel Reinforcement | SHW | 8.80 to 12.20 | First Floor | 42066 | 42068 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2229 | bottom steel reinforcement for slab 2-1B axis B9 to B13/A6 to A7 | Steel Reinforcement | Slab | -3.80 | B1 | 42066 | 42068 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2230 | surface preparation and repair for core 2 axis B14 to B16/A7 to A10 | Repair | Core | -3.80 to -0.40 | BOH | 42077 | 42096 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2231 | inspection of holes and dowels fixation due to design change at driver stair case columns axis A14 to A15/B19 to B20 | Dowels | Column | -11.00 to -7.20 | B2 | 42067 | 42070 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2232 | bottom steel reinforcement for part of raft section 25-29 axis B16 to B19/A4 to A5 | Steel Reinforcement | Raft | -11.00 | raft | 42067 | 42072 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2233 | steel reinforcement for beam at ramp 4 axis B8 to B14/A4 | Steel Reinforcement | Beam | -7.20 to -3.80 | B1 | 42067 | 42070 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2234 | top steel reinforcement for roof slab 5D-1 axis B9 to B13/A4 to A6 | Steel Reinforcement | Slab | -3.80 | B1 | 42067 | 42068 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2235 | top steel reinforcement for slab 2-1B axis B9 to B13/A6 to A7 | Steel Reinforcement | Slab | -3.80 | B1 | 42067 | 42068 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2236 | check the level and location of screed axis A4 to A7/B21 to B19 | Survey | Screed |  |  | 42068 | 42070 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2237 | steel reinforcement for shear wall 1 axis C4 to C7/A1 | Steel Reinforcement | SHW | 8.80 to 12.20 | First Floor | 42068 | 42070 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2238 | form work for shear wall 1 axis C4 to C7/A1 | Form Work | SHW | 8.80 to 12.20 | First Floor | 42068 | 42070 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2239 | form work for 4 columns C8 axis B19 to B20/A14 to A15 | Form Work | Column | -11.00 to -7.20 | B2 | 42070 | 42070 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2240 | steel reinforcement for 4 columns C8 axis B19 to B20/A14 to A15 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42070 | 42070 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2241 | piles surface preparation to proceed with epoxy application piles No. E(261-262-263-264-266-268-269-270-271-274-275-276-277-280) | Epoxy | Piles | -13.50 to -12.50 | raft | 42070 | 42071 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2242 | form work removal section 4A axis B14 to B16/A1 to A3 | Removing Form Work | Slab | -7.20 | B2 | 42070 | 42074 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2243 | form work removal 5C-4 axis B19 to B21/A15 to A11 | Removing Form Work | Slab | 1.10 | BOH | 42070 | 42074 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2244 | form work for slab 5A-4 axis A10 to A15/B5 to B9 | Form Work | Slab | 1.10 | BOH | 42070 | 42078 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2245 | steel reinforcement work for core 2 axis B14 to B16/A8 to A10 | Steel Reinforcement | Core | -0.4 to 2.9 | Ground Floor | 42071 | 42073 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2246 | installation of composite columns (torque) for 2 columns CC4-1 axis D2/b18-B19& D1/B18-B19 | Composite Columns | Column | -12 | B2 | 42072 | 42074 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2247 | fixation of shear connector for 2 composite columns (Torque) axis D2/b18-B19& D1/B18-B19 | Composite Columns | Column | -12 | B2 | 42072 | 42074 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2248 | installation of composite column (Torque) axis A9/B19 | Composite Columns | Column | -12 to -6 | B2 | 42072 | 42073 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2249 | fixation of shear connector for composite column CC4-2 axis A9/B19 | Shear Connectors | Column | -12 to -6 | B2 | 42072 | 42073 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2250 | installation of composite column (Torque) axis CC1-2 axis A10/B13 | Composite Columns | Column | -6.00 to Zero | B1/BOH | 42072 | 42072 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2251 | fixation of shear connector for composite column axis CC1-2 axis A10/B13 | Shear Connectors | Column | -6.00 to Zero | B1/BOH | 42072 | 42072 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2252 | form work for shear wall 7 axis C3/A2 to A3 | Form Work | SHW | 11.30 to 14.60 | Second Floor | 42071 | 42073 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2253 | form work for shear wall 6 axis C4/A2 to A3 | Form Work | SHW | 11.30 to 14.60 | Second Floor | 42071 | 42072 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2254 | steel reinforcement for shear wall 7 axis C3/A2 to A3 | Steel Reinforcement | SHW | 11.30 to 14.60 | Second Floor | 42071 | 42072 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2255 | steel reinforcement for shear wall 6 axis C4/A2 to A3 | Steel Reinforcement | SHW | 11.30 to 14.60 | Second Floor | 42071 | 42071 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2256 | piles surface preparation to proceed with epoxy application piles No. E(260-259) | Epoxy | Piles | -13.50 to -12.50 | raft | 42071 | 42073 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2257 | steel reinforcement for 2 panoramic elevators columns axis A5/B9-B10& B9/A5 to A6 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42071 | 42071 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2258 | steel reinforcement for 4 columns C1 axis A4/B9 "west", B10, B12, B13 "east" | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42071 | 42072 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2259 | form work for 4 columns C1 axis A4/B9 "west", B10, B12, B13 "east" | Form Work | Column | -3.80 to 1.10 | BOH | 42071 | 42072 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2260 | form work for 3 columns C1 axis A5/B10-B13 "esat"- B9 "west" | Form Work | Column | -3.80 to 1.10 | BOH | 42072 | 42073 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2261 | form work for 1 column C1 axis A4/B8 west | Form Work | Column | -3.80 to 1.10 | BOH | 42072 | 42073 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2262 | steel reinforcement for 3 columns C1 axis A5/B10-B13 "east"-B9 "west" | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42072 | 42072 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2263 | steel reinforcement work for 1 column C1 axis A4/B8 west | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42072 | 42073 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2264 | installation of composite column (Torque) CC7E-2 axis A6/B14 | Composite Columns | Column | -6.00 to Zero | B1/BOH | 42072 | 42074 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2265 | fixation of shear connector for comosite column CC7E-2 axis A6/B14 | Shear Connectors | Column | -6.00 to Zero | B1/BOH | 42072 | 42072 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2266 | top layer steel reinforcement work, dowels and final inspection for slab 5C-2 axis A10 to A15/B13 to B16 | Steel Reinforcement | Slab | -3.80 | B1 | 42072 | 42073 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2267 | installation of injection pipe and reinjectable hose at retaining wall construction joint for slab 5C-2 axis A10 to A15/B13 to B16 | Insulation | Retaining Wall | -3.80 | B1 | 42072 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2268 | steel reinforcement for 2 beams B1 of driver stair case axis B19 to B20/A13 to A15 | Steel Reinforcement | Stair | -7.20 | B2 | 42072 | 42072 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2269 | form work for 2 beams B1 of driver stair case axis B19 to B20/A13 to A15 | Form Work | Stair | -7.20 | B2 | 42072 | 42072 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2270 | steel reinforcement for panoramic elevator axis B10-B11/A5-A6 | Steel Reinforcement | Panoramic Elevator | -3.80 to 1.10 | BOH | 42072 | 42074 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2271 | form work for panoramic elevator axis B10-B11/A5-A6 | Form Work | Panoramic Elevator | -3.80 to 1.10 | BOH | 42072 | 42074 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2272 | steel reinforcement for column C7 axis A5/B12-B13 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42072 | 42073 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2273 | form work for column C7 axis A5/B12-B13 | Form Work | Column | -3.80 to 1.10 | BOH | 42072 | 42073 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2274 | form work for 2 panoramic elevators axis B9/A5& B9/A5-A6 | Form Work | Panoramic Elevator | -3.80 to 1.10 | BOH | 42072 | 42074 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2275 | installation of composite column (Torque) CC7 axis A6/B14 | Composite Columns | Column | -3.80 to 1.10 | BOH | 42072 | 42072 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2276 | casting grout for 2 composite columns CC4 axis D1-D2 | Grout | Column | -12.00 | B2 | 42072 | 42073 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2277 | CHECK THE LEVEL AND LOCATION OF SCREED AXIS A4 TO A8/B21 TO B19 | Survey | Screed |  |  | 42073 | 42074 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2278 | installation of 3 composite columns (torque) CC7 axis A6/B9-B10-B12 | Composite Columns | Column | zero to 6.00 | BOH | 42073 | 42075 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2279 | form work for column CC1 axis A10/B13 west side | Form Work | Column | -3.80 to 1.10 | BOH | 42073 | 42078 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2280 | steel reinforcement for 1 column CC1 axis A10/B13 west side | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42073 | 42074 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2281 | steel reinforcement for 1 column CC7 aqxis B14/A6 | Form Work | Column | -3.80 to 1.10 | BOH | 42073 | 42074 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2282 | form work for column CC7 axis B14/A6 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42073 | 42075 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2283 | steel reinforcement for 1 column CC4 axis A9/B18-B19 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42073 | 42074 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2284 | form work for 1 column CC4 axis A9/B18-B19 | Form Work | Column | -7.20 to -3.80 | B1 | 42073 | 42075 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2285 | fixation of shear connector for composite column CC7 axis A6/B9 west sdie | Shear Connectors | Column | 1.10 | BOH | 42073 | 42075 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2286 | fixation for shear connector for composite column CC7 axis B10/A6 | Shear Connectors | Column | 1.10 | BOH | 42073 | 42075 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2287 | fixation for shear connector for compsoite column CC7 axis A6/B12 | Shear Connectors | Column | 1.10 | BOH | 42073 | 42075 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2288 | steel reifnforcement for shear wall 1 axis C7 to B19/A1 | Steel Reinforcement | SHW | 5.40 to 8.00 | First Floor | 42073 | 42075 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2289 | STEEL REINFORCEMENT FOR 2 PITS COMPOSITE COLUMNS CC4 AXIS D1-D2 | Steel Reinforcement | Column | -11.00 | raft | 42074 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2290 | STEEL REINFORCEMENT FOR COLUMN C1 AXIS B9/A4 EAST | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42074 | 42075 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2291 | FORM WORK FOR COLUMN C1 AXIS B9/A4 EAST | Form Work | Column | -3.80 to 1.10 | BOH | 42074 | 42078 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2292 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2293 | form work for shear wall 1 axis C7 to B19/A1 | Form Work | SHW | 4.50 to 8.00 | First Floor | 42075 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2294 | form work for part of raft section 25& 29 axis A3 to A8/B17 to B20 | Form Work | Raft | -11.00 | raft | 42075 | 42075 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2295 | Form work for columns CC7 axis B12/A6 | Form Work | Column | -3.80 to 1.10 | BOH | 42077 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2296 | form work for 3 columns C1 axis B14/A12,A14 | Form Work | Column | -3.80 to 1.10 | BOH | 42075 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2297 | installation of steel column (Torque) CC1 axis B13/A11 east | Composite Columns | Column | zero to 6.00 | BOH | 42075 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2298 | form work for column C3 axis B8/A4 | Form Work | Column | -3.80 to 1.10 | BOH | 42075 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2299 | shear connector for column CC1 axis B13/A11 east | Shear Connectors | Column | -3.80 to 1.10 | BOH | 42075 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2300 | steel reinforcement for 3 columns B14/A12, A14& B13/A14 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42075 | 42078 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2301 | form work for column C1 axis B9/A5 west | Form Work | Column | -3.80 to 1.10 | BOH | 42075 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2302 | form work for column C1 axis B13/A5 west | Form Work | Column | -3.80 to 1.10 | BOH | 42075 | 42078 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2303 | steel reinforcement for column C1 axis B13/A5 west | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42075 | 42076 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2304 | steel reinforcement for column C1 axis B13/A4 west | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42075 | 42075 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2305 | steel reinforcement for column C1 axis B9/A5 west | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42075 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2306 | steel reinforcement for column C3 axis B8/A4 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42075 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2307 | steel reinforcement for retaining wall axis B12 to B16/A15 | Steel Reinforcement | Retaining Wall | -3.80 to -2.50 | BOH | 42075 | 42078 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2308 | form work for retaining wall axis B12 to B16/A15 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 42075 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2309 | steel reinforcement for column C6 axis B13/A12 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42075 | 42078 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2310 | form work for column C6 axis B13/A12 | Form Work | Column | -3.80 to 1.10 | BOH | 42075 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2311 | installation of injection pipe and re-injectable hose at raft construction joints for part of 25& 29 axis A3 to A8/B17 to B20 | Insulation | Raft | -11.00 | raft | 42075 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2312 | installation of injection pipe and re-injectable hose for retaining wall axis B18 to B12/A15 | Insulation | Retaining Wall | -3.80 to 1.10 | BOH | 42075 | 42099 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2313 | top layer steel reinforcement work, dowels, embedded items and final inspection for raft 25& 29 axis A3 to A8/B17 to B20 | Steel Reinforcement | Raft | -11.00 | raft | 42075 | 42075 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2314 | Form work for columns CC7 axis B13/A6 east | Form Work | Column | -3.80 to 1.10 | BOH | 42078 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2315 | Form work for columns CC7 axis B9/A6 EAST | Form Work | Column | -3.80 to 1.10 | BOH | 42077 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2316 | Steel Reinforcement for columns CC7 B10/A6 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42077 | 42078 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2317 | Steel Reinforcement for columns CC7 B12/A6 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42077 | 42078 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2318 | Steel Reinforcement for columns CC7 B13/A6 EAST | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42077 | 42078 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2319 | Steel Reinforcement for columns CC7 B9/A6 EAST | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42077 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2320 | Fixation of shear connectors for composite column CC1 axis B9/A8 | Shear Connectors | Column | -3.80 to 1.10 | BOH | 42078 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2321 | installation of steel composite column (Torque) for column CC1 axis B9/A8 | Composite Columns | Column | -3.80 to 1.10 | BOH | 42078 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2322 | Fixation of shear connectors for composite column CC1 axis B13/A10 east | Shear Connectors | Column | -3.80 to 1.10 | BOH | 42078 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2323 | form work for core 2 axis B14 to B15/A8 to A10 | Form Work | Core | -0.4 to 2.9 |  | 42078 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2324 | bottom layer steel reinforcement for slab 5A-4 axis B5 to B9/A11 to A15 | Steel Reinforcement | Slab | 1.10 | BOH | 42078 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2325 | steel reinforcement for core 8 axis B1/A1,2,3 | Steel Reinforcement | Core | 9.40 to 13.00 |  | 42078 | 42080 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2326 | steel reinforcement for core 7 axis C7/A2-A3 | Steel Reinforcement | Core | 11.00 to 14.40 |  | 42078 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2327 | form work for column CC4 axis D1/B18-B19 | Form Work | Column | -11.00 to -7.20 | B2 | 42078 | 42080 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2328 | steel reinforcement for column CC4 axis D1/B18-B19 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42078 | 42081 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2329 | steel reinforcement for 2 columns C1 axis A5/B18-B19 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42078 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2330 | steel reinforcement for 3 columns C1 axis A4/B16-B18-B19 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42078 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2331 | form work for retaining wall axis B12 to B16/A15 | Form Work | Retaining Wall | -2.50 to 1.10 | BOH | 42078 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2332 | form work for core 8 axis A2 to A3/B1 | Form Work | Core | 9.40 to 13.00 | BOH | 42079 | 42081 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2333 | form work for core 7 axis A2 to A3/C7 | Form Work | Core | 11.00 to 14.40 |  | 42079 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2334 | form work for column C6 axis A12/B13 east | Form Work | Column | -3.80 to 1.10 | BOH | 42079 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2335 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2336 | form work of column CC7 axis A6/B13 west | Form Work | Column | -3.80 to 1.10 | BOH | 42079 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2337 | steel reinforcement for column C6 axis A12/B13 east | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42079 | 42081 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2338 | steel reinforcement for column CC7 axis A6/B13 west | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42079 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2339 | fixation of shear connector of column CC9 axis A11/B14 | Shear Connectors | Column | -3.80 to 1.10 | BOH | 42079 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2340 | fixation of shear connector of column CC1* A8/B13 east | Shear Connectors | Column | -3.80 to 1.10 | BOH | 42079 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2341 | fixation of shear connector of column CC7 axis A6/B13 west | Shear Connectors | Column | -3.80 to 1.10 | BOH | 42079 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2342 | fixation of composite column (Torque) CC9 axis A11/B14 | Composite Columns | Column | -3.80 to 1.10 | BOH | 42079 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2343 | fixation of composite column (Torque) CC1* axis A8/B13 east | Composite Columns | Column | -3.80 to 1.10 | BOH | 42079 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2344 | fixation of column CC7 (Torque) axis A6/B13 west | Composite Columns | Column | -3.80 to 1.10 | BOH | 42079 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2345 | form work for column CC1 axis A11/B13 east | Form Work | Column | -3.80 to 1.10 | BOH | 42079 | 42081 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2346 | steel reinforcement for column CC1 axis A11/B13 east | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42079 | 42081 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2347 | form work for 2 columns C1 axis A5/B18-B19 | Form Work | Column | -11.00 to -7.20 | B2 | 42080 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2348 | form work for 3 columns C1 axis A4/B16-B18-B19 | Form Work | Column | -11.00 to -7.20 | B2 | 42080 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2349 | casting grout under base plate for 1 composite column CC7 axis B16/A6 | Grout | Column | -13.50 to -12.50 | raft | 42080 | 42081 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2350 | installation and test of PVC under part of raft secton 29 axis A1 to A4/B19 to B21 | Insulation | Raft | -13.50 to -12.50 | raft | 42080 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2351 | surface preparation prior geotextile 1st layer under part of aft section 29 axis A1 to A4/B19 to B21 | Insulation |  | -13.50 to -12.50 | raft | 42080 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2352 | piles surface preparation to proceed with epoxy application piles No. E(253-254-255-256-257-258)& H(426-427) | Epoxy | Piles | -13.50 to -12.50 | raft | 42080 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2353 | installation of geotextile 2nd layer under raft after PVC for part of section 29 axis A1 to A4/B19 to B21 | Insulation | Raft | -13.50 to -12.50 | raft | 42080 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2354 | installation of geotextile 1st layer under raft perior PVC for part of raft 29 axis A1 to A4/B19 to B21 | Insulation | Raft | -13.50 to -12.50 | raft | 42080 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2355 | form work for composite column C1 axis A5/B13 | Form Work | Column | -3.80 to 1.10 | BOH | 42080 | 42081 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2356 | steel reinforcement for 1 column C1 axis A5/B13 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42080 | 42081 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2357 | steel reinforcement for column CC1 axis A10/B13 east | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42080 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2358 | form work for column CC1 axis A10/B13 east | Form Work | Column | -3.80 to 1.10 | BOH | 42080 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2359 | form work for column CC7 axis A9/B6 west | Form Work | Column | -3.80 to 1.10 | BOH | 42080 | 42081 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2360 | steel reinforcement for column CC7 axis A9/B6 west | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42080 | 42081 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2361 | form work for stair 5 axis A8 to A9/B8 | Form Work | Stair | -3.80 to 0.45 | BOH | 42080 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2362 | form work for stair 3 axis A8 to A9/B8 to B6 | Form Work | Stair | -3.80 to 0.45 | BOH | 42080 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2363 | form work for stair 6 axis A8 to A9/B10 to B11 | Form Work | Stair | -3.80 to 0.45 | BOH | 42080 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2364 | top layer steel reinforcement for slab 5A-4 axis B5 to B9/A11 to A15 | Steel Reinforcement | Slab | 1.05 | BOH | 42080 | 42081 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2365 | Bottom Steel Reinfrocement For Part of Section 1A axis A8 to A11/B5 to B9 | Steel Reinforcement | Slab | 1.10 | BOH | 42080 | 42082 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2366 | bottom laye steel reinforcement for raft section 29 axis A4-A8 /B19-B21 | Steel Reinforcement | Raft | -11.00 | raft | 42080 | 42081 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2367 | steel reinforcement for shear wall 8 axis C2/A1 to A3 | Steel Reinforcement | SHW | 5.40 to 8.80 | First Floor | 42080 | 42081 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2368 | form work for 2 columns C1 axis A6/B18-B19 | Form Work | Column | -11.00 to -7.20 | B2 | 42080 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2369 | steel reinforcement for 2 columns C1 axis A6/B18-B19 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42080 | 42081 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2370 | form work for part slab 5B-2 axis A2 to A5/B4 to B7 | Form Work | Slab | 1.10 | BOH | 42080 | 42081 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2371 | steel reinforcement for panoramic elevator A6/B10 | Steel Reinforcement | Panoramic Elevator | -3.80 to 1.10 | BOH | 42080 | 42081 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2372 | form work for panoramic elevator axis A6/B10 | Form Work | Panoramic Elevator | -3.80 to 1.10 | BOH | 42080 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2373 | form work for column CC1 axis A8/9 | Form Work | Column | -3.80 to 1.10 | BOH | 42080 | 42087 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2374 | steel reinforcement for column CC1 axis A8/B9 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42080 | 42085 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2375 | fixation of shear connector for column CC7 axis A6/B9 west | Shear Connectors | Column | -3.80 to 1.10 | BOH | 42081 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2376 | top layer steel reinforcement work, dowels and final inspection for slab 5B-2 for crane opening part | Steel Reinforcement | Slab | -7.20 | B2 | 42081 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2377 | steel reinforcement for core 3 axis B10 to B12/A8 to A10 | Steel Reinforcement | Core | 2.90 to 6.20 | Ground Floor | 42078 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2378 | form work for shear wall 8 axis C2/A2 to A3 | Form Work | SHW | 5.40 to 8.80 | First Floor | 42082 | 42087 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2379 | form work for stair case 14 axis A2/B15 to B17 | Form Work | Stair | -2.10 to -0.45 | BOH | 42082 | 42085 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2380 | drilling and fixation of slab dowels at core 5 axis B6 to B8/A8 to A10 | dowels | Slab | 1.10 | BOH | 42078 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2381 | top layer steel reinforcement work, dowels and final inspection for part of slab 1A axis B5 to B8/A7 to A11 | Steel Reinforcement | Slab | 1.05 | BOH | 42081 | 42082 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2382 | installation of composite column (Torque) for CC7 axis A6/B9 west | Composite Columns | Column | -3.80 to 1.10 | BOH | 42082 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2383 | steel reinforcement for shear wall 1 axis A1/B1 to C7 | Steel Reinforcement | SHW | 11.30 to 14.70 | Second Floor | 42082 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2384 | steel reinforcement for core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | Core | 6.20 to 9.50 | First Floor | 42082 | 42082 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2385 | steel reinforcement for column CC4 axis D2 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42082 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2386 | form work for column CC4 axis D2 | Form Work | Column | -3.80 to 1.10 | BOH | 42082 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2387 | steel reinforcement for column CC9 axis A11/B14 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42082 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2388 | form work for column CC9 axis A11/B14 | Form Work | Column | -3.80 to 1.10 | BOH | 42082 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2389 | steel reinforcement for pit of column CC7 axis A6/B16 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42082 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2390 | check the level and location of screed axis B19 to B21/A1 to A4 | Survey | Screed |  |  | 42078 | 42079 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2391 | post tension work for slab (tension-strands-anchors and profiles) | Post Tension | Slab | 5.40 | First Floor | 42078 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2392 | steel reinforcement for 2 columns C1 axis B20/A3-A4 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42088 | 42089 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2393 | form work for slab 5B-2 axis B3 to B6/A3 to A5 | Form Work | Slab | 1.10 | BOH | 42082 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2394 | form work for slab 5D-1 axis A3 to A6/B9 to B13 | Form Work | Slab | 1.10 | BOH | 42082 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2395 | form work for slab 1B axis B7 to B9/A6 to A8 | Form Work | Slab | 1.10 | BOH | 42082 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2396 | steel reinforcement for column C5 axis B18/A2-A3 | Steel Reinforcement | Column | 0.60 to 4.00 | BOH | 42081 | 42085 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2397 | form work for column C5 axis B18/A2 to A3 | Form Work | Column | 0.60 to 4.00 | BOH | 42082 | 42087 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2398 | form work for shear wall 1 axis A1/B1 to C7 | Form Work | SHW | 11.30 to 14.70 | Second Floor | 42082 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2399 | form work for raft part of section 29 axis A3 to a4/B19 to B21 | Form Work | Raft | -11.00 | raft | 42082 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2400 | top layer steel reinforcement for part of section 29 axis A3 to A4/B19 to B21 | Steel Reinforcement |  | -11.00 | raft | 42082 | 42085 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2401 | installation of injection pipe and re-injectable hose at raft construction joints for part of 29 axis A3 to A4/B19 to B21 | Insulation | Raft | -11.00 | raft | 42082 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2402 | inspection of holes and dowels fixation for stair 3, 5, 6 axis B6/A8& B8/A10& B10/A7 | Dowels | Stair | -3.80 to 1.10 | BOH | 42082 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2403 | bottom layer steel reinforcement for slab 2-1B axis B11 to B13/A5 to A8 | Steel Reinforcement | Slab | 1.10 | BOH | 42168 | 42170 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2404 | top layer steel reinforcement for slab 2-1B axis B11 to B13/A5 to A8 | Steel Reinforcement | Slab | 1.10 | BOH | 42168 | 42170 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2405 | form work for column C1 axis A5/B16 | Form Work | Column | -11.00 to -7.20 | B12 | 42082 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2406 | steel reinforcement for column C1 axis A5/B16 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42082 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2407 | top layer steel reinforcement work, dowels and final inspection for first pour slab axis A1/B1 to C5 | Steel Reinforcement | Slab | 5.40 | First Floor | 42078 | 42088 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2408 | form work removal for slab 5D-1& 2-1B axis A4,A7/B9 to B13 | Removing Form Work | Slab | -3.80 | B1 | 42078 | 42080 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2409 | steel reinforcement for stair case 8 axis B12/A8 to A9 | Steel Reinforcement | Stair | -11.00 to -7.20 | B2 | 42078 | 42081 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2410 | steel reinforcement for stair 7 axis A10/B10 to B11 | Steel Reinforcement | Stair | -11.00 to -7.20 | B2 | 42078 | 42080 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2411 | form work for column C1 axis B13/A14 west | Form Work | Column | -3.80 to 1.10 | BOH | 42082 | 42082 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2412 | form work for core 3 axis B10 to B12/A8 to A10 | Form Work | Core | 2.90 to 6.20 | Ground Floor | 42085 | 42089 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2413 | form work for column C1 axis B13/A14 east | Form Work | Column | -3.80 to 1.10 | BOH | 42085 | 42087 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2414 | steel reinforcement for column C1 axis B13/A14 east | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42085 | 42087 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2415 | fixation of shear connectors for column CC7 axis A6/B16 | Shear Connectors | Column | -11.00 to -7.20 | B2 | 42085 | 42088 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2416 | fixation of shear connectors for column CC1 axis B13/A11 west | Shear Connectors | Column | -3.80 to 1.10 | BOH | 42085 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2417 | installation of composite column (torque) CC1 axis B13/A11 west | Composite Columns | Column | -3.80 to 1.10 | BOH | 42085 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2418 | fixation of shear connector for column CC1* axis B13/A8 west | Shear Connectors | Column | -3.80 to 1.10 | BOH | 42085 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2419 | installation of composite column (torque) CC1* axis B13/A8 west | Composite Columns | Column | -3.80 to 1.10 | BOH | 42085 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2420 | form work for column CC7 axis A6/B16 | Form Work | Column | -11.00 to -7.20 | B2 | 42085 | 42087 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2421 | steel reinfrocement for column CC7 axis A6/B16 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42085 | 42088 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2422 | installation of composite column (torque) for CC7 axis A6/B16 | Composite Columns | Column | -11.00 to -7.20 | B2 | 42085 | 42085 | D
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2423 | bottom layer steel reinforcement for raft section 29 axis A3 to A1/B19 to B21 | Steel Reinforcement | Raft | -11.00 | raft | 42085 | 42085 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2424 | supports, dowels holes, casting concrete, 1st and 2nd layer of geotextile and PVC isolation for raft axis A2 to A3/B16 to B19 | Insulation | Raft | -11.00 | raft | 42085 | 42105 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2425 | stressing of srands. Hotel building slab (5.40) first stage of slab "post tension" | Stressing | Slab | 5.40 | First Floor | 42086 | 42088 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2426 | installation of injection pipe and re-injectable hose at raft construction joints for raft section 29 axis A1 to A4/B19 to B21 | Insulation | Raft | -11.00 | raft | 42085 | 42099 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2427 | top layer steel reinforcement work, dowels, embedded items and final inspection for raft part of section 29 axis A1 to A4/B19 to B21 | Steel Reinforcement | Raft | -11.00 | raft | 42085 | 42088 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2428 | steel reinforcement for column CC1* axis B13/A8 west | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42085 | 42087 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2429 | form work for column CC1* axis B13/A8 west | Form Work | Column | -3.80 to 1.10 | BOH | 42085 | 42087 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2430 | form work for column CC1 axis B13/A11 west | Form Work | Column | -3.80 to 1.10 | BOH | 42085 | 42087 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2431 | steel reinforcement for column CC1 axis B13/A11 west | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42085 | 42087 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2432 | steel reinforcement for 2 columns C1 axis B20/A3-A4 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42088 | 42089 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2433 | steel reinforcement for stair 5 axis A8 to A9/B8 | Steel Reinforcement | Stair | -3.80 to 0.45 | BOH | 42085 | 42089 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2434 | steel reinforcement for stair 6 axis B10 to B11/A8 to A9 | Steel Reinforcement | Stair | -3.80 to 0.45 | BOH | 42085 | 42091 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2435 | bottom layer steel reinforcement for slab of 2 planters axis B4 to B7/A3 to A5 | Steel Reinforcement | Slab | 0.65 & 0.55 | BOH | 42085 | 42085 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2436 | form work for slab section 1C & 2-1B axis A3 to A7/B6 to B13 | Form Work | Slab | 1.10 | BOH | 42085 | 42088 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2437 | form work for 2 columns C1 axis B20/A3-A4 | Form Work | Column | -11.00 to -7.20 | B2 | 42088 | 42089 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2438 | steel reinforcement for 3 columns C1 axis B20/A5-A6-A8 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42086 | 42089 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2439 | form work for 3 columns C1 axis B20/A5-A6-A8 | Form Work | Column | -11.00 to -7.20 | B2 | 42086 | 42089 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2440 | inspection for holes and dowels of panoramic elevator axis A5-A6/B9-B10 | dowels | Panoramic Elevator | 1.10 | BOH | 42086 | 42088 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2441 | form work for stair 8 axis B12 to B13/A8 to A9 | Form Work | Stair | -3.80 to 1.10 | BOH | 42086 | 42089 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2442 | form work for stair 7 axis B10-B11/A10-A11 | Form Work | Stair | -3.80 to 1.10 | BOH | 42086 | 42088 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2443 | steel reinforcement for column C1 axis A8/B19 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42086 | 42088 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2444 | form work for column C1 axis A8/B19 | Form Work | Column | -11.00 to -7.20 | B2 | 42086 | 42088 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2445 | steel reinforcement for column CC1* axis A8/B13 east side | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42087 | 42091 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2446 | form work for column CC1* axis A8/B13 east side | Form Work | Column | -3.80 to 1.10 | BOH | 42087 | 42092 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2447 | form work for slab 2-2B axis A5 to A9/B15 to B19 | Form Work | Slab | -7.20 | B2 | 42087 | 42091 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2448 | steel reinforcement for shear wall 1 axis A1/C7 to B19 | Steel Reinforcement | SHW | 7.50 to 10.80 | First Floor | 42088 | 42092 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2449 | top layer steel reinforcement work dowels and final inspection for firt pour strip axis A1/B1 to C5 | Steel Reinforcement | Slab | 5.40 | First Floor | 42078 | 42079 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2450 | steel reinforcement for stair 7 axis A10/B10 to B11 | Steel Reinforcement | Stair | -7.20 to -3.80 | B1 | 42089 | 42093 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2451 | drilling and fixation of slab dowels at stair 8 axis B12 to B13/A8 to A9 | Dowels | Slab | -7.20 to -3.80 | B1 | 42089 | 42091 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2452 | form work for stair 11 axis B16 to B17/A8 to A10 | Form Work | Stair | -11.00 to -7.20 | B2 | 42089 | 42091 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2453 | surface preparation and repair work for core 5 axis B6 to B8/A8 to A10 | Repair | Core | -7.20 | B2 | 42089 | 42172 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2454 | steel reinforcement for core 8 axis B1/A1,2,3 | Steel Reinforcement | Core | 7.50 to 10.80 | First Floor | 42089 | 42092 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2455 | steel reinforcement for stair 8 axis A7 to A9/B12 to B13 | Steel Reinforcement | Stair | -7.20 to -3.80 | B1 | 42091 | 42093 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2456 | form work removal for section 1A axis A9 to A12/B5 to B9 | Removing Form Work | Slab | 1.10 | BOH | 42091 | 42096 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2457 | form work removal section 5A-4 axis A11 to A15/B5 to B9 | Form Work | Slab | 1.10 | BOH | 42091 | 42095 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2458 | form work for shear wall 1 axis C7 to B19/A1 | Form Work | SHW | 7.80 to 11.20 | First Floor | 42091 | 42093 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2459 | form work for core 8 axis B1/A2 to A3 | Form Work | Core | 12.80 to 16.20 | Second Floor | 42091 | 42094 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2460 | inspection of holes and dowels fixation for stair 11 axis A8 to A10/B16 to B18 | Dowels | Stair | -11.00 to -7.20 | B2 | 42091 | 42099 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2461 | form work for stair case 9 axis A8 to A9/B19 to B16 | Form Work | Stair | -11.00 to -7.20 | B2 | 42091 | 42093 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2462 | form work for ramp curved beams B2 to B3/A13& A13 to A15/C1 to B3 | Form Work | Beam | -7.20 | B2 | 42092 | 42093 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2463 | form work removal for first pour strip axis B1 to B6/A1 to A4 | Removing Form Work | Slab | 5.40 | First Floor | 42092 | 42092 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2464 | steel reinfrocement for shear wall 1 axis A1/B19 to B20 | Steel Reinforcement | SHW | -0.45 to 3.00 | BOH | 42092 | 42093 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2465 | form work for slab 5D-2 axis A2 to A6/B13 to B18 | Form Work | Slab | -7.20 | B2 | 42092 | 42095 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2466 | form work for core 5 axis A8 to A10/B6 to B8 | Form Work | Core | 6.10 to 9.50 | First Floor | 42092 | 42100 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2467 | steel reinfrocement for stair 11 axis A8 to A10/B16 to B18 | Steel Reinforcement | Stair | -11.00 to -7.20 | B2 | 42092 | 42096 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2468 | bottom layer steel reinforcement for 2-2B axis A7 to A9/B15 to B20 | Steel Reinforcement | Slab | -7.20 | B2 | 42093 | 42094 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2469 | bottom layer steel reinforcement work for slab 5D-2 axis B14 to B18/A3 to A6 | Steel Reinforcement | Slab | -7.20 | B2 | 42093 | 42095 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2470 | form work for stair case 6 axis B10 to B11/A8 to A9 | Form Work | Stair | -0.45 to 1.10 | BOH | 42093 | 42096 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2471 | form work for stair case 5 axis A7 to A9/B8 to B9 | Form Work | Stair | -0.45 to 1.10 | BOH | 42093 | 42096 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2472 | surface preparation for external diahragm wall axis A1 to A9/B21 | Insulation | Diaphragm Wall | -11.00 to -2.50 | wall | 42093 | 42099 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2473 | installation of geotextile 1st layer to proceed with PVC membrane installation axis A1 to A9/B21 | Insulation |  | -11.00 to -2.50 | wall | 42093 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2474 | installation and test of PVC membrane to proceed with geotextile 2nd layer axis A1 to A9/B21 | Insulation |  | -11.00 to -2.50 | wall | 42093 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2475 | installation of geotextile 2nd layer to proceed with retaining wall reinforcement axis A1 to A9/B21 | Insulation | Retaining Wall | -11.00 to -2.50 | wall | 42093 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2476 | repair for water tank walls and ceiling C1 to B2/A3 to A6 | Repair |  | -11.00 to -7.20 | wall | 42093 | 42094 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2477 | form work for retaining wall axis A5 to A9/B21 | Form Work | Retaining Wall | -11.00 to -7.20 | B2 | 42094 | 42096 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2478 | steel reinforcement for retaining wall axis A5 to A9/B21 | Steel Reinforcement | Retaining Wall | -11.00 to -7.20 | B2 | 42094 | 42095 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2479 | installation of injection pipe and re-injectable hose for retaining wall axis A5 to A9/B21 | Insulation | Retaining Wall | -11.00 to -7.20 | B2 | 42094 | 42099 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2480 | form work for shear wall 1 axis A1/B19 to B20 | Form Work | SHW | -0.45 to 3.00 | BOH | 42094 | 42095 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2481 | top layer steel reinforcement work, dowels and final inspection for slab 2-2B axis A7 to A9/B15 to B20 | Steel Reinforcement | Slab | -7.20 | B2 | 42094 | 42096 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2482 | top layer steel reinforcement work, dowels and final inspection for slab 5D-2 axis A3 to A6/B13 to B18 | Steel Reinforcement | Slab | -7.20 | B2 | 42094 | 42096 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2483 | steel reinforcement for panoramic elevator beams axis A5 to A6/B9 to B10 | Steel Reinforcement | Beam | 1.10 | BOH | 42087 | 42093 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2484 | re-stressing for 17 strands according to DTF No. 872 axis C5 to B1/A1 | Stressing | Slab | 5.40 | First Floor | 42095 | 42098 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2485 | surface preparation and repair for slabs construction joints section 5B-3, 5D-1 and 2-1B | Repair | Slab | -3.80 | B1 | 42095 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2486 | surface preparation and repair for slabs construction joints section 5A-3, 5A-1 and 5A-2 | Repair | Slab | 1.10 | BOH | 42095 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2487 | surface preparation for external diaphragm wall axis B19 to B21/A1 | Insulation | Diaphragm Wall | -11.00 to -2.50 | wall | 42095 | 42099 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2488 | inspection of geotextile 1st layer to proceed with PVC membrane installation axis B19 to B21/A1 | Insulation |  | -11.00 to -2.50 | wall | 42095 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2489 | installaion and test of PVC memrane to proceed with geotextile 2nd layer | Insulation |  | -11.00 to -2.50 | wall | 42095 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2490 | installation of geotextile 2nd layer to proceed with retaining wall reinforcement axis B19 to B21/A15 and A12 to A15/B21 | Insulation | Retaining Wall | -11.00 to -2.50 | wall | 42095 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2491 | installation of composite columns (torque) for column CC5 axis A2 to A3/C9 | composite Columns | Column | 10.30 to 15.20 | Second Floor | 42172 | 42175 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2492 | form work for stair case7 | Form Work | Stair | -3.80 to 0.45 | STAIR | 42096 | 42099 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2493 | form work for stair case 8 | form work | Stair | -3.80 to 0.45 | stair | 42096 | 42099 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2494 | form work for ramp curved beams a12-a13/b2-b3&b5-b7 | Form Work | Beam | -3.80 | beam | 42096 | 42098 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2495 | STEEL REINFORCEMENT FOR COLUMN C1 A5/B14 | Steel Reinforcement | Column | -7.20 TO -3.80 | B1 | 42098 | 42099 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2496 | STEEL REINFORCEMENT FOR COLUMN C1 A5/B16 | Steel Reinforcement | Column | -7.20 TO -3.80 | B1 | 42098 | 42099 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2497 | STEEL REINFORCEMENT FOR COLUMN C1 A4/B16 | Steel Reinforcement | Column | -7.20 TO -3.80 | B1 | 42098 | 42099 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2498 | FORM WORK FOR COLUMN C1 A5/B16 | Form Work | Column | -7.20 TO -3.80 | B1 | 42098 | 42099 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2499 | FORM WORK FOR COLUMN C1 A4/B16 | Form Work | Column | -7.20 TO -3.80 | B1 | 42098 | 42099 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2500 | FORM WORK FOR COLUMN C1 A5/B14 | Form Work | Column | -7.20 TO -3.80 | B1 | 42098 | 42099 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2501 | STEEL REINFORCEMENT FOR COLUMN C1 A4/B14 | Steel Reinforcement | Column | -7.20 TO -3.80 | B1 | 42098 | 42099 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2502 | FORM WORK FOR COLUMN C1 A4/B14 | Form Work | Column | -7.20 TO -3.80 | B1 | 42098 | 42099 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2503 | FIXATION FOR COMPOSITE COLUMN TORQUE FOR COLUMN CC4 D2/A7,A8 | Composite Columns | Column | -7.20 | B2 | 42099 | 42100 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2504 | FIXATION FOR COMPOSITE COLUMN TORQUE FOR COLUMN CC4 D1/A6,A7 | Composite Columns | Column | -7.20 | B2 | 42099 | 42100 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2505 | FIXATION FOR SHEAR CONNECOR FOR COMPOSITE COLUMN CC4 D1/A6,A7 | Composite Columns | Column | -7.20 | B2 | 42099 | 42100 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2506 | FIXATION FOR SHEAR CONNECOR FOR COMPOSITE COLUMN CC4 D2/A7,A8 | Composite Columns | Column | -7.20 | B2 | 42099 | 42100 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2507 | STEEL REINFORCEMENT FOR 3 COLMNS C1 A8/B19-A6/B19-A6/B18 | Steel Reinforcement | Column | -7.20 | B2 | 42099 | 42100 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2508 | FORM WORK FOR 3 COLMNS C1 A8/B19-A6/B19-A6/B18 | Form Work | Column | -7.20 | B2 | 42099 | 42100 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2509 | STEEL REINFORCEMENT FOR COMPOSITE COLUMN CC4 D1/A6,A7 | Steel Reinforcement | Column | -7.20 | B2 | 42099 | 42101 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2510 | STEEL REINFORCEMENT FOR COLUMN CC4 D2/A7,A8 | Steel Reinforcement | Column | -7.20 | B2 | 42099 | 42101 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2511 | FORM WORK FOR COLUMN CC4 D2/A7,A8 | Form Work | Column | -7.20 | B2 | 42099 | 42102 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2512 | FORM WORK FOR COMPOSITE COLUMN CC4 D1/A6,A7 | Form Work | Column | -7.20 | B2 | 42099 | 42102 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2513 | DOWELS DRILLING AND FIXATION FOR STAIR 8 | Dowels | Stair | -3.80 | B1 | 42099 | 42116 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2514 | DOWELS DRILLING AND FIXATION FOR STAIR 7 | Dowels | Stair | -3.80 | B1 | 42099 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2515 | STEEL REINFORCEMENT FOR COLUMN C1 A4/B18 | Steel Reinforcement | Column | -7.20 TO -3.80 | B1 | 42099 | 42100 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2516 | FORM WORK FOR COLUMN C1 A4/B18 | Form Work | Column | -7.20 TO -3.80 | B1 | 42099 | 42100 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2517 | STEEL REINFORCEMENT FOR COLUMN C1 | Steel Reinforcement | Column | -7.20 TO -3.80 | B1 | 42099 | 42100 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2518 | FORM WORK FOR COLUMN C1 | Form Work | Column | -7.20 TO -3.80 | B1 | 42099 | 42100 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2519 | STEEL REINFORCEMENT FOR SHEAR WALL 1 | Steel Reinforcement | SHW | 3.00 to 6.40 | Ground Floor | 42099 | 42102 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2520 | form work for slab sec 5D-4A | Form Work | Slab | -7.20 | B2 | 42099 | 42100 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2521 | BOTTOM LAYER STEEL REINFORCEMENT FOR SLAB 5D-4A | Steel Reinforcement | Slab | -7.20 | B2 | 42100 | 42101 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2522 | FORM WORK FOR SLAB 5D-3 | Form Work | Slab | -7.20 | B2 | 42100 | 42101 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2523 | BOTTOM LAYER STEEL REINFORCEMENT FOR SLAB 5D-3 | Steel Reinforcement | Slab | -7.20 | B2 | 42100 | 42101 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2524 | TOP LAYER STEEL REINFORCEMENT FOR SLAB 5D-3 | Steel Reinforcement | Slab | -7.20 | B2 | 42100 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2525 | INSTALATION FOR RE INJECTION PIPE AND RE INJECTABLE HOSE FOR SLAB 5D-3 | Insulation | Slab | -7.20 | B2 | 42100 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2526 | steel reinforcement for stair case 8 axis B12/A8 to A9 | Steel Reinforcement | Stair | 1.10 | BOH | 42100 | 42113 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2527 | steel reinforcement for stair case 9 axis 7-A8/ B15-B16 | Steel Reinforcement | Stair | -11.00 to -7.20 | B2 | 42100 | 42103 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2528 | TOP LAYER STEEL REINFORCEMENT FOR SLAB 5D-4A | Steel Reinforcement | Slab | -7.20 | B2 | 42100 | 42103 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2529 | SURFACE PREPARATION AND REPAIR FOR SLABS CONSTRUCTION JOINTS ( 1A )-(2-2A)-(2-1A) | Repair | Slab | -3.80 | B1 | 42100 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2530 | STEEL REINFORCEMENT FOR STAIR CASE 12 | Steel Reinforcement | Stair | -0.45 TO 1.10 | BOH | 42101 | 42105 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2531 | STEEL REINFORCEMENT FOR CORE WALL 6 | Steel Reinforcement | Core | 1.10 TO 5.40 | Ground Floor | 42101 | 42103 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2532 | FORM WORK FOR CORE WALL 6 | Form Work | Core | 1.10 TO 5.40 | Ground Floor | 42101 | 42105 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2533 | FORM WORK FOR SHEAR WALL 1AXIS A1/B19-20 | Form Work | SHW | 3.00 to 6.40 | Ground Floor | 42101 | 42103 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2534 | DOWELS DRILLING FIXATION INSPECTION FOR COUPLING BEAM CORE 6 | Dowels | Core | 1.10 To 5.40 | Ground Floor | 42101 | 42103 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2535 | FIXATION FOR SHEAR CONNECOR FOR COMPOSITE COLUMN CC7 A6/B16 | Composite Columns | Column | -7.20 TO -3.80 | B1 | 42101 | 42102 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2536 | FIXATION FOR COMPOSITE COLUMN TORQUE FOR COLUMN CC7 A6/B16 | Composite Columns | Column | -7.20 TO -3.80 | B1 | 42101 | 42102 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2537 | form work for slab 5C-1 axis B9 to B1/A12 to A15 | Form Work | Slab | 1.05 | BOH | 42103 | 42103 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2538 | steel reinforcement for column CC7 axis A6/B16 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42102 | 42103 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2539 | form work for column CC7 axis A6/B16 | Form Work | Column | -7.20 to -3.80 | B1 | 42102 | 42105 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2540 | form work for retaining wall axis A1/B19 to B21& A1 to A4/B20 to B21 | Form Work | Retaining Wall | -11.00 to -7.20 | B2 | 42102 | 42110 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2541 | steel reinforcement for retaining wall axis A1/B19 to B21& A1 to A4/B20 to B21 | Steel Reinforcement | Retaining Wall | -11.00 to -7.20 | B2 | 42102 | 42108 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2542 | installation of injection pipe and re-injectable hose for retaining wall axis B19 to B21/A1& A1 to A4/B20 to B21 | Insulation | Retaining Wall | -11.00 to -7.20 | B2 | 42102 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2543 | surface preparation and repair for construction joints | Repair |  | 1.10 | BOH | 42102 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2544 | surface preparation and repair for construction joints | Repair |  | -3.80 | B1 | 42102 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2545 | steel reinforcement for shear wall 1 axis A1/C7 to C8 | Steel Reinforcement | SHW | 10.80 to 14.10 | Second Floor | 42103 | 42103 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2546 | form work for shear wall 1 axis A1/C7 to C8 | Form Work | SHW | 10.80 to 14.10 | Second Floor | 42103 | 42103 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2547 | surface preparation for core 3 outer walls | Repair | Core | -7.20 | B2 | 42103 | 42106 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2548 | form work for stair 11 axis B16 to B17/A8 to A10 | Form Work | Stair | -7.20 TO -3.80 | B1 | 42103 | 42103 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2549 | installation of geotextile 2nd layer to proceed with retaining wall reinforcement axis B20 to B21/A15 to A13/B21 | Insulation | Retaining Wall | -4.50 to Finish | Ground Floor | 42112 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2550 | form work for retaining wall axis A5 to A3/B21 | Form Work | Retaining Wall | -11.00 to -7.20 | B2 | 42103 | 42106 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2551 | steel reinforcement for retaining wall axis A5 to A3/B21 | Steel Reinforcement | Retaining Wall | -11.00 to -7.20 | B2 | 42103 | 42105 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2552 | installation of injection pipe and re-injectable hose for retaining wall axis A5 to A3/B21 | Insulation | Retaining Wall | -11.00 to -7.20 | B2 | 42103 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2553 | form work removal for slab 5D-2 axis B14 to B18/A3 to A6 | Removing Form Work | Slab | -7.20 | B2 | 42105 | 42106 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2554 | form work for 2 columns C1 axis A4-A5/B19 | Form Work | Column | -7.20 TO -3.80 | B1 | 42105 | 42106 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2555 | steel reinforcement for 2 columns C1 axis A4-A5/B19 | Form Work | Column | -7.20 TO -3.80 | B1 | 42105 | 42106 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2556 | form work for shear wall 1 axis A1/B1 to C7 | Form Work | SHW | 14.10 to 17.50 | 3rd | 42105 | 42106 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2557 | steel reinforcement for shear wall 1 axis A1/B1 to C7 | Steel Reinforcement | SHW | 14.10 to 17.50 | 3rd | 42105 | 42105 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2558 | steel reinforcement for 2 columns C1 axis A6-A8/B20 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42106 | 42108 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2559 | form work for 2 columns C1 axis A6-A8/B20 | Form Work | Column | -7.20 to -3.80 | B1 | 42106 | 42109 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2560 | steel reinforcement for stair case 11 axis A18 to A19/B16 to B18 | Steel Reinforcement | Stair | -7.20 to -3.80 | B1 | 42106 | 42109 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2561 | form work for column C1 axis A4/B19 | Form Work | Column | -7.20 to -3.80 | B1 | 42106 | 42109 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2562 | steel reinforcement for column C1 axis A4/B19 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42106 | 42108 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2563 | steel reinforcement for shear wall 6 axis C4/A3 to A2 | Steel Reinforcement | SHW | 13.90 to 17.30 | Typical Floor | 42108 | 42109 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2564 | form work for shear wall 6 axis C4/A3 to A2 | Form Work | SHW | 13.90 to 17.30 | Typical Floor | 42108 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2565 | form work for shear wall 7 axis C3/A2 to A3 | Form Work | SHW | 13.80 to 17.20 | Typical Floor | 42108 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2566 | steel reinforcement for shear wall 7 axis C3/A2 to A3 | Steel Reinforcement | SHW | 13.80 to 17.20 | Typical Floor | 42108 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2567 | form work for slab 5D-2 axis A2 to A6/B13 to B18 | Form Work | Slab | -3.80 | B1 | 42108 | 42110 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2568 | steel reinfrocement for shear wall 1 axis A1/C7 to C8 | Steel Reinforcement | SHW | 14.10 to 17.50 | Typical Floor | 42108 | 42113 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2569 | form work for shear wall 1 axis A1/C7 to C8 | Form Work | SHW | 14.10 to 17.50 | Typical Floor | 42108 | 42113 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2570 | final inspection for surface preparation dowels fixation, steel reinforcement, casting grout at pipe of struts, welding of pipe cap, geotextile 1st and 2nd& PVC prior to casting concrete as attached sketch | Insulation |  | -11.00 | Raft | 42108 | 42109 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2571 | demolition of wall and beam as per DSF# 471 for core 2 axis A7 to A10/B14 to B16 | Demolition | Core | -7.20 TO -3.80 | B2 | 42110 | 42133 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2572 | surface preparation for external diphragm wall axis B20 to B21/A15 to A14/B21 | Insulation | SHW | -4.50 to Finish | Ground Floor | 42112 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2573 | installation of geotextile 2nd layer to proceed with retaining wall reinforcement walls axis B16 to B20/A15 | Insulation | Retaining Wall | -4.50 to Finish | Ground Floor | 42109 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2574 | installation of geotextile 1st layer to proceed with PVC mebrane installation | Insulation |  | -4.50 to Finish | Ground Floor | 42109 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2575 | surface preparation for external diaphram walls axis B16 to B20/A15 | Insulation | Diaphragm Wall | -4.50 to Finish | Ground Floor | 42109 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2576 | insulatallation and test of PVC mebrane to proceed with geotextile 2nd layer for walls axis B16 to B21/A15 | Insulation | SHW | -4.50 to Finish | Ground Floor | 42109 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2577 | intallation of geotextile 2nd layer to proceed with retaiing wall reinforcement axis A9 to A14/B21 | Insulation | SHW | -4.50 to Finish | Ground Floor | 42109 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2578 | installation of geotextile 1st layer to proceed with PVC membrane installation axis A9 to A14/B21 | Insulation |  | -4.50 to Finish | Ground Floor | 42109 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2579 | installation and test of PVC membrane to proceed with geotextile 2nd layer axis A9 to A14/B21 | Insulation |  | -4.50 to Finish | Ground Floor | 42109 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2580 | surface preparation for external diaphragm wall axis A9 to A14/B21 | Insulation | Diaphragm Wall | -4.50 to Finish | Ground Floor | 42109 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2581 | form work removal for slab 5D-3 axis A6 to A10/B19 to B21 | Removing Form Work | Slab | -7.20 | B2 | 42110 | 42113 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2582 | form work removal slab 5D-4 axis B18 to B19/A3 to A6 | Removing Form Work | Slab | -7.20 | B2 | 42110 | 42113 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2583 | form work for post tension slab second pour strip axis C4 to C5/B19/A1 to A3 | Form Work | Slab | 5.40 | First Floor | 42113 | 42113 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2584 | bottom layer steel reinforcement work, dowels and final inspection for slab 5D-2 | Steel Reinforcement | Slab | -3.80 | B1 | 42110 | 42114 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2585 | form work for slab 2-2B axis A6 to A12/B15 to B19 | Form Work | Slab | -3.80 | B1 | 42110 | 42113 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2586 | installation and test of PVC embrane to proceed with geotextile 2nd layer axis B20 to B21/A15 to A14/B21 | Insulation |  | -4.50 to Finish | Ground Floor | 42112 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2587 | form work for stair case 9 axis A7 to A8/B14 to B16 | Form Work | Stair | -7.20 to -3.80 | B2 | 42112 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2588 | installation of injection pipe and re-injectable hose for retaining wall axis B17 to B19/A15 | Insulation | Retaining Wall | -7.20 to -3.80 | B1 | 42113 | 42137 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2589 | form work for retaining wall axis B17 to B19/A15 | Form Work | Retaining Wall | -7.20 to -3.80 | B1 | 42113 | 42115 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2590 | steel reinforcement for retaining wall axis B17 to B19/A15 | Steel Reinforcement | Retaining Wall | -7.20 to -3.80 | B1 | 42113 | 42114 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2591 | form work for slab 5D-4B axis B19 to B21/A1 to A6 | Form Work | Slab | -7.20 | B2 | 42113 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2592 | bottom layer steel reinforcement work for slab 2-2B axis A6 to A12/B15 to B19 | Steel Reinforcement | Slab | -3.80 | B1 | 42113 | 42114 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2593 | installation of geotextile 1st layer to proceed with PVC membrane installation B20 to B21/A15 to A14/B21 | Insulation |  | -4.50 to Finish | Ground Floor | 42112 | 42115 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2594 | top layer steel reinforcement work, dowels and final inspection for slab 5D-2 axis A3 to A6/B13 to B18 | Steel Reinforcement | Slab | -3.80 | B1 | 42114 | 42114 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2595 | form work for core 4 axis A7 to A9/B8 to B9 | Form Work | Core | -3.80 to 1.10 | BOH | 42114 | 42120 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2596 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2597 | steel reinforcement for 2 columns C1 axis A12-A14/B20 | Steel Reinforcement | Column | -7.20 to -3.80 | B2 | 42115 | 42115 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2598 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2599 | top layer steel reinforcement work, dowels and final inspection for slab 2-2B axis A6 to A10/B16 to B19 | Steel Reinforcement | Slab | -3.80 | B1 | 42115 | 42117 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2600 | steel reinforcement for 5 second pour strip beams B1-CB3-B3-CB2-EB axis B7-B8/A2, A2-A3/C6, A2-A3/B11, A2-A3/C10, A2-A3/B15-B19 | Steel Reinforcement | Slab | 5.40 | First Floor | 42115 | 42124 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2601 | demolishing of raft for variation at core 2 axis B15,B16/A9 | Demolition | Core | -11.00 | Raft | 42115 | 42133 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2602 | steel reinforcement for retaining wall axis B19 to B21/A15 | Steel Reinforcement | Retaining Wall | -7.20 to -3.80 | B1 | 42115 | 42117 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2603 | dowels drilling and fixation inspection beams (B3-EB) and core 6 at second pour strip axis A2-A3/C6, A2-A3/B15 -B19 | Dowels | Core | 5.40 | First Floor | 42115 | 42116 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2604 | steel reinforcement for stair case 7 axis B12 to B13/A7 to A9 | Steel Reinforcement | Stair | -3.80 to 0.45 | BOH | 42116 | 42122 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2605 | steel reinforcement for stair case 8 axis B10 to B11/A9 to A11 | Steel Reinforcement | Stair | -3.80 to 0.45 | BOH | 42116 | 42120 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2606 | steel reinforcement for stair 9 axis B14 to B16/A7 to A8 | Steel Reinforcement | Stair | -7.20 to -3.80 | B1 | 42116 | 42122 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2607 | steel reinforcement for 6 columns C1 axis A4/B14-B16-B18& A5/B14-B16-B18 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42116 | 42120 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2608 | form work for 6 columns C1 axis A4/B14-B16-B18& A5/B14-B16-B18 | Form Work | Column | -3.80 to 1.10 | BOH | 42116 | 42120 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2609 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2610 | bottom layer steel reinforcement work for slab 5D-4B axis B19 to B21/A1 to A5 | Steel Reinforcement | Slab | -7.20 | B2 | 42116 | 42117 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2611 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2612 | form work for retaining wall A14/A15 to A15/B21 | Form Work | Retaining Wall | -7.20 to -3.80 | B1 | 42117 | 42120 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2613 | steel reinforcement for retaining wall axis A12 to A14/A15 to B21 | Steel Reinforcement | Retaining Wall | -7.20 TO -3.80 | B1 | 42117 | 42117 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2614 | top layer steel reinforcement work, dowels and final inspection for slab 5D-4B axis A1-A6/B19-B21 | Steel Reinforcement | Slab | -7.20 | B2 | 42117 | 42120 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2615 | steel reinforcement for 2 columns C1 axis B19/A8-A10 | Steel Reinforcement | Column | -3.80 to -0.15 | BOH | 42117 | 42120 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2616 | form work for 2 columns C1 axis A6/B18-B19 | Form Work | Column | -3.80 to -0.25 | BOH | 42117 | 42120 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2617 | form work for 2 columns C1 axis B19/A8-A10 | Form Work | Column | -3.80 to -0.15 | BOH | 42117 | 42120 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2618 | steel reinforcement for 2 columns C1 axis A6/B18-B19 | Steel Reinforcement | Column | -3.80 to -0.25 | BOH | 42117 | 42120 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2619 | surface preparation for external diaphragm walls to proceed with geotextile 1st layer axis A6 to between A3-A4/B21 | Insulation | Diaphragm Wall | -2.50 to 0.25 | BOH | 42120 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2620 | installation of geotextile 1st layer to proceed with PVC membrane installation axis A6 to between A3-A4/B21 | Insulation |  | -2.50 to 0.25 | BOH | 42120 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2621 | installation and test of PVC membrane to proceed with geotextile 2nd layer axis A6 to between A3-A4/B21 | Insulation |  | -2.50 to 0.25 | BOH | 42120 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2622 | installation of geotextile 2nd layer to proceed with retaining wall reinforcement axis A6 to between A3-A4/B21 | Insulation | Retaining Wall | -2.50 to 0.25 | BOH | 42120 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2623 | steel reinforcement for 3 column C1 axis B20/A3-A4-A5 | Steel Reinforcement | Column | -7.20 to -3.80 | B1 | 42120 | 42120 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2624 | form work for 3 columns C1 axis B20/A3-A4-A5 | Form Work | Column | -7.20 to -3.80 | B1 | 42120 | 42121 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2625 | form work for retaining wall axis A7 to A12/B21 | Form Work | Retaining Wall | -7.20 to -3.80 | B1 | 42120 | 42122 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2626 | steel reinforcement for retaining wall axis A7 to A12/B21 | Steel Reinforcement | Retaining Wall | -7.20 to -3.80 | B1 | 42120 | 42120 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2627 | steel reinforcement for core 1 axis A8/B16-B17 | Steel Reinforcement | Core | -3.80 to 1.10 | BOH | 42120 | 42122 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2628 | surface preparation and repair for 3 columns CC7 axis B4/A9-A10-A11 | Repair | Column | 1.10 to 5.40 | Ground Floor | 42122 | 42122 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2629 | steel reinforcement for core 5 axis B6 to B8/A8 to A10 | Steel Reinforcement | Core | 9.50 to 12.80 | Second Floor | 42121 | 42123 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2630 | dowels drilling and fixation inspection for slab at second pour strip axis B17 to B19/A1 | Dowels | Slab | 5.40 | BOH | 42122 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2631 | ducts grouting for post tension slab for first pour strip C3 to C4/A1 to A3/B1 | Grout | Slab | 5.40 | First Floor | 42121 | 42126 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2632 | form work removal for slab 5D-2 axis B14 to B18/A3 to A6 | Removing Form Work | Slab | -3.80 | B1 | 42122 | 42124 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2633 | form work for 4 columns driver stair case axis A14 to A15/B19 | Form Work | Column | -7.20 to -3.80 | B1 | 42121 | 42063 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2634 | form work removal for slab 2-2B axis A6 to A12/B15 to B19 | Removing Form Work | Slab | -3.80 | B1 | 42123 | 42123 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2635 | installation of composite column (torque) for CC6 axis A2 to A3/C11 | composite Columns | Column | 10.30 to 15.20 | Second Floor | 42172 | 42175 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2636 | steel reinfrocement for shear wall 1 axis B19 to B20/A1 | Steel Reinforcement | SHW | 10.30 to 15.20 | Second Floor | 42171 | 42172 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2637 | demolition for elevator pit at core 2 axis B15 to B16/A8 to A9 | Demolition | Core | -11.00 to -12.70 | Raft | 42122 | 42133 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2638 | post tension work for slab (tension-strands-anchors and profiles) C3-C4/B19/A1-A3 | Post Tension | Slab | 5.40 | First Floor | 42122 | 42128 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2639 | top and bottom layers of steel reinforcement work, dowels and final inspection for post tension slab for second pour strip axis C3-C4/B19/A1-A3 | Steel Reinforcement | Slab | 5.40 | First Floor | 42122 | 42124 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2640 | installation of geotextile 2nd layer to proceed with retaining wall reinforcement axis A6 to between A3-A4/B21 to between B20&B19/A1 | Insulation | Retaining Wall | -3.30 to -2.50 | BOH | 42122 | 42137 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2641 | installation and test of PVC membrane to proceed with geotextile 2nd layer axis A6 to between A3-A4/B21 to between B20&B19/A1 | Insulation |  | -3.30 to -2.50 | BOH | 42122 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2642 | installation of geotextile 1st layer to proceed with PVC membrane installation axis A6 to between A3-A4/B21 to between B20&B19/A1 | Insulation |  | -3.30 to -2.50 | BOH | 42122 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2643 | surface preparation for external diaphragm walls to proceed with geotextile 1st layer axis A6 to between A3-A4/B21 to between B20&B19/A1 | Insulation | Diaphragm Wall | -3.30 to -2.50 | BOH | 42122 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2644 | surface preparation and repair for beam in core 3 axis A7 to A8/B13 to B14 | Repair | Core | -3.80 | B1 | 42122 | 42130 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2645 | torque and shear connector for 1 column CC4 axis A9/B18 to B19 | Composite Columns | Column | -3.80 to 1.10 | BOH | 42122 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2646 | torque and shear connector for 1 column CC4 axis D1 | Composite Columns | Column | -3.80 to 1.10 | BOH | 42122 | 42126 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2647 | torque and shear connector for 1 column CC4 axis D2 | Composite Columns | Column | -3.80 to 1.10 | BOH | 42122 | 42126 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2648 | torque and shear connector for 1 column CC4 axis D3 | Composite Columns | Column | -3.80 to 1.10 | BOH | 42122 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2649 | torque and shear connector for 1 column CC4 axis B16/A6 | Composite Columns | Column | -3.80 to 1.10 | BOH | 42122 | 42126 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2650 | form work for core 1 axis A8/B16-B17 | Form Work | Core | -3.80 to 1.10 | BOH | 42122 | 42124 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2651 | form work for 2 columns C1 axis A4/B14-B16 | Form Work | Column | -3.80 to 1.10 | BOH | 42122 | 42124 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2652 | steel reinforcement work for 2 columns C1 axis A4/B14-B16 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42122 | 42124 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2653 | steel reinforcement for retaining wall axis A9 to A6/B21 | Steel Reinforcement | Retaining Wall | -7.20 to -3.80 | B1 | 42122 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2654 | form work for retaining wall axis A9 to A6/B21 | Form Work | Retaining Wall | -7.20 to -3.80 | B1 | 42122 | 42124 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2655 | installation of injection pipe and re-injectable hose for retaining wall axis A9 to A6/B21 | Insulation | Retaining Wall | -7.20 to -3.80 | B1 | 42122 | 42123 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2656 | inspection of holes and dowels fixation around core 7 | Dowels | Core | 5.40 | First Floor | 42122 | 42124 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2657 | form work for 2 columns driver stair case axis A14 to A15/B19 | Form Work | Column | -7.20 to -3.80 | B1 | 42122 | 42124 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2658 | fixation of shear connector for 1 column CC7 axis A12/B16 | Shear Connectors | Column | -3.80 to 1.10 | BOH | 42123 | 42133 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2659 | fixation of shear connector for composite column CC4 axis B16/A10-A11 | Shear Connectors | Column | -3.80 to 1.10 | BOH | 42123 | 42126 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2660 | installation of composite column (Torque) for CC4 axis B16/A10-A11 | Composite Columns | Column | -3.80 to 1.10 | BOH | 42123 | 42126 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2661 | installation of composite column (torque) CC7 axis A12/B16 | Composite Columns | Column | -3.80 to 1.10 | BOH | 42123 | 42133 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2662 | form work for column C1 axis A4/B14 | Form Work | Column | -3.80 to 1.10 | BOH | 42126 | 42126 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2663 | bottom layer steel reinforcement work for slab 1B axis B5 to B9/A9 to A6 | Steel Reinforcement | Slab | 1.10 | BOH | 42124 | 42127 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2664 | form work for slab 5D-4A | Form Work | Slab | -3.80 | B1 | 42124 | 42126 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2665 | form work for retaining wall axis A4 to A6/B21 | Form Work | Retaining Wall | -7.20 to -3.80 | B1 | 42124 | 42127 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2666 | installation of injection pipe and re-injectable hose for retaining wall axis A4 to A6/B21 | Insulation | Retaining Wall | -7.20 to -3.80 | B1 | 42124 | 42137 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2667 | steel reinforcement for retaining wall axis A4 to A6/B21 | Steel Reinforcement | Retaining Wall | -7.20 to -3.80 | B1 | 42124 | 42126 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2668 | form work for slab 5C-3 and 5C-4 axis A9 to A15/B15 to B21 | Form Work | Slab | -3.80 | B1 | 42126 | 42128 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2669 | installation of composite column (Torque) and fixation of shear connector for CC5 axis A2-A3/B18 | Composite Columns | Column | 6.40 to 9.40 | First Floor | 42126 | 42128 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2670 | installation of composite column (Torque) and fixation of shear connector for CC6 axis A2-A3/C11 | Composite Columns | Column | 6.40 to 9.40 | First Floor | 42126 | 42128 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2671 | steel reinforcement for shear wall 2 axis A1 to A3/C10 | Steel Reinforcement | SHW | 5.40 to 8.80 | First Floor | 42126 | 42128 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2672 | steel reinforcement for shear wall 3 axis A1 to A3/C6 | Steel Reinforcement | SHW | 5.40 to 8.80 | First Floor | 42126 | 42128 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2673 | surface preparation prior to repair for core wall 2 | Repair | Core | -0.4 to 2.9 | BOH | 42127 | 42172 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2674 | form work removal for slab 5D-4B axis B19 to B21/A1 to A6 | Removing Form Work | Slab | -7.20 | B2 | 42127 | 42128 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2675 | stressing of strands for post tension slab at second pour strip axis C4 to C5/B19/A1 to A3 | Stressing | Slab | 5.40 | First Floor | 42127 | 42130 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2676 | steel reinforcement for 4 columns CC4 axis D1-D2-D3& A9/B19 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42127 | 42128 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2677 | form work for 4 columns CC4 axis D1-D2-D3& A9/B19 | Form Work | Column | -3.80 to 1.10 | BOH | 42127 | 42130 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2678 | form work for core 5 axis B6 to B8/A8 to A10 | Form Work | Core | 9.50 to 12.80 | Second Floor | 42127 | 42130 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2679 | steel reinforcement fr beam axis A11 to A14/B18 | Steel Reinforcement | Beam | -3.80 | B1 | 42127 | 42130 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2680 | form work for shear wall 2 axis C10/A1 to A3 | Form Work | SHW | 5.40 to 8.80 | First Floor | 42127 | 42130 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2681 | form work for shear wall 3 axis A1 to A3/C6 | Form Work | SHW | 5.40 to 8.80 | First Floor | 42127 | 42130 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2682 | steel reinforcement for column C5 axis A1 to A3/B18 | Steel Reinforcement | Column | 5.40 to 8.80 | First Floor | 42127 | 42128 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2683 | coring for strands ducts in walls for shear wall 6-7 | Core | SHW | 10.30 | Second Floor | 42127 | 42133 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2684 | bottom layer steel reinforcement work for slab 5D-4A axis B18 to B19/A3 to A5 | Steel Reinforcement | Slab | -3.80 | B1 | 42127 | 42129 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2685 | installation of injection pipe and re-injectable hose for retaining wall axis A4 to A1/B19 to B21 | Insulation | Retaining Wall | -7.20 to -3.80 | B1 | 42127 | 42137 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2686 | steel reinforcement for retaining wall axis A1 to A4/B19 | Steel Reinforcement | Retaining Wall | -7.20 to -3.80 | B1 | 42127 | 42130 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2687 | form work for column CC4 axis A10-A11/B16 | Form Work | Column | -3.80 to 1.10 | BOH | 42128 | 42133 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2688 | steel reinforcement for column CC4 axis A10-A11/B16 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42128 | 42131 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2689 | bottom layer steel reinforcement work for slab 5C-3 axis B16 to B19/A12 to A15 | Steel Reinforcement | Slab | -3.80 | B1 | 42128 | 42130 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2690 | bottom layer steel reinforcement work for slab 5C-4 axis B19 to B21/A12 to A15 | Steel Reinforcement | Slab | -3.80 | B1 | 42128 | 42131 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2691 | form work for column CC7 axis A6/B16 | Form Work | Column | -3.80 to 1.10 | BOH | 42128 | 42130 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2692 | steel reinforcement for column CC7 axis A6/B16 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42128 | 42130 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2693 | form work for retaining wall axis A1 to A4/B19 | Form Work | Retaining Wall | -7.20 to -3.80 | B1 | 42128 | 42130 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2694 | top layer steel reinforcement work, dowels and final inspection for slab 5D-4A axis A1-A6/B19-B21 | Steel Reinforcement | Slab | -3.80 | B1 | 42128 | 42130 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2695 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2696 | form work for core 6 axis A1 to A2/B15 to B17 | Form Work | Core | 5.40 to 8.80 | First Floor | 42128 | 42133 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2697 | steel reinforcement work for core 6 axis A1 to A2/B15 to B17 | Steel Reinforcement | Core | 5.40 to 8.80 | First Floor | 42128 | 42131 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2698 | drilling and fixation of dowels of the side bars and the additional steel bars above the opening of core 6 axis A1 to A2/B15 to B17 | Dowels | Core | 5.40 to 8.80 | First Floor | 42128 | 42131 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2699 | form work for column CC6 axis C11 | Form Work | Column | 5.40 to 8.80 | First Floor | 42128 | 42131 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2700 | Steel reinforcement for column CC6 axis C11 | Steel Reinforcement | Column | 5.40 to 8.80 | First Floor | 42128 | 42130 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2701 | form work for column CC5 axis C9 | Form Work | Column | 5.40 to 8.80 | First Floor | 42128 | 42130 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2702 | steel reinforcement work for column CC5 axis C9 | Steel Reinforcement | Column | 5.40 to 8.80 | First Floor | 42128 | 42130 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2703 | installation of composite column (Torque) for 2 columns CC9 axis A11/B6-B8 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42129 | 42133 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2704 | demolishing for wall at core 5 axis B7/A8 to A10 | Demolition | Core | -3.80 to -0.40 | BOH | 42129 | 42130 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2705 | fixation of shear connectors for 2 columns CC9 axis A11/B6-B8 | Shear Connectors | Column | -3.80 to 1.10 | BOH | 42129 | 42133 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2706 | top layer steel reinforcement work, dowels and final inspection for slab 1B asxis A6 to A8/B5 to B9 | Steel Reinforcement | Slab | 1.10 | BOH | 42129 | 42131 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2707 | concrete repair for tansversal direction cables No. 17, 38 at second pour strip | Repair | Slab | 5.40 | First Floor | 42129 | 42135 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2708 | top layer steel reinforcement work and final inspection for slab 5C-4 axis A9 to A15/B19 to B21 | Steel Reinforcement | Slab | -3.80 | B1 | 42130 | 42133 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2709 | top layer steel reinforcement work and final inspection for slab 5C-3 axis A10 to A15/B19 to B16 | Steel Reinforcement | Slab | -3.80 | B1 | 42130 | 42131 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2710 | surface preparation and repair for ramp beam axis B9 to B10/A4 | Repair | Beam | -11.00 to -7.20 | B2 | 42131 | 42148 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2711 | steel reinforcement for shear wall 5* axis A2 to A3/C5 | Steel Reinforcement | SHW | 5.40 to 8.70 | First Floor | 42131 | 42133 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2712 | re-stressing for strands No. 17& 38 in transversal direction for second pour strip | Stressing | Slab | 5.40 | First Floor | 42131 | 42133 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2713 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2714 | form work for column C5 axis B18/A1 | Form Work | Column | 5.40 to 10.30 | First Floor | 42133 | 42133 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2715 | form work for shear wall 5* axis C5/A2 to A3 | Form Work | SHW | 5.40 to 8.70 | First Floor | 42133 | 42135 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2716 | form work for slab 5D-4B axis B19 to B21/A1 to A6 | Form Work | Slab | -3.80 | B1 | 42133 | 42135 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2717 | form work for stair 8 axis B12 to B13/A8 to A9 | Form Work | Stair | -0.45 to 1.10 | BOH | 42133 | 42135 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2718 | form work for stair 7 axis B10-B11/A10-A11 | Form Work | Stair | -0.45 to 1.10 | BOH | 42133 | 42135 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2719 | form work for stair 11 axis B16 to B17/A8 to A10 | Form Work | Stair | -3.80 to -0.45 | BOH | 42133 | 42135 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2720 | steel reinforcement for core 2 new wall due to design change at foundation level axis A8 to A9/B15 to B16 | Steel Reinforcement | Core | -12.70 to -11.00 | Raft | 42133 | 42138 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2721 | steel reinforcement work for shear wall 2* axis C8/A2 to A3 | Steel Reinforcement | SHW | 5.40 to 8.80 | First Floor | 42133 | 42135 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2722 | inspection of holes and dowels fixation for stair 11 axis A8 to A10/B16 to B18 | Dowels | Stair | -3.80 to -0.45 | BOH | 42134 | 42137 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2723 | surface preparation for ramp beam axis A4/B8-B9 | Repair | Beam | -7.20 | B2 | 42134 | 42143 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2724 | steel reinforcement for first pour strip beams B1/C3-C4 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42135 | 42137 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2725 | demolishing for beam at core 5 due to design change axis B7 to B8/A9 to A10 | Demolition | Core | -7.20 to -3.80 | B1, BOH | 42134 | 42147 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2726 | demolishing for wall at core 5 axis B7/A9 | Demolition | Core | -7.20 to -3.80 | B1, BOH | 42134 | 42145 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2727 | steel reinforcement for stair 7 axis A10/B10 to B11 | Steel Reinforcement | Stair | -0.45 to 1.10 | BOH | 42134 | 42138 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2728 | steel reinforcement for stair 8 axis A9/B12 | Steel Reinforcement | Stair | -0.45 to 1.10 | BOH | 42134 | 42138 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2729 | steel reinfrocement for stair 11 axis A8 to A10/B16 to B18 | Steel Reinforcement | Stair | -3.80 to -0.45 | BOH | 42134 | 42138 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2730 | bottom layer steel reinforcement work for slab 5D-4B axis B19 to B21/A1 to A5 | Steel Reinforcement | Slab | -3.80 | B1 | 42134 | 42137 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2731 | form work for shear wall 2* axis C8/A2-A3 | Form Work | SHW | 5.40 to 8.80 | First Floor | 42135 | 42135 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2732 | dowels drilling and fixation inspection for core 3 opening reduction axis A9 to A10/B12 | Dowels | Core | 1.10 to 5.40 | Ground Floor | 42136 | 42138 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2733 | dowels drilling and fixation inspection for core 2 new wall due to design change at foundation level axis A7 to A9/B15 to B16 | Dowels | Core | -11.00 | Raft | 42136 | 42138 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2734 | form work for core 2 new wall due to design change at foundation level axis A7 to A9/B15 to B16 | Form Work | Core | -12.70 to -11.00 | Raft | 42136 | 42138 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2735 | form work for shear wall 1 axis A1/B18 to B19 | Form Work | SHW | 7.10 to 10.10 | First Floor | 42138 | 42140 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2736 | dowels drilling and fixation inspection for stair 7 axis A10/B10 to B11 | Dowels | Stair | 1.10 | BOH | 42136 | 42140 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2737 | dowels drilling and fixation inspection for stair 8 axis A9/B12 | Dowels | Stair | 1.10 | BOH | 42136 | 42140 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2738 | steel reinforcement for core 2 new wall due to design change at foundation level A8 to A9/B15 to B16 | Steel Reinforcement | Core | -11.00 to -7.20 | B2 | 42136 | 42138 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2739 | top layer steell reinforcement work, dowels and final inspection for slab 5D-4B axis B19 to B21/A1 to A6 | Steel Reinforcement | Slab | -3.80 | B1 | 42136 | 42138 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2740 | steel reinforcement for 3 columns C1 axis B20/A10-A12-A14 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42136 | 42138 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2741 | form work for 3 columns C1 axis B20/A10-A12-A14 | Form Work | Column | -3.80 to 1.10 | BOH | 42136 | 42138 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2742 | form work for shear wall 5* axis C5/A1-A3 | Form Work | SHW | 5.40 to 8.80 | First Floor | 42136 | 42138 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2743 | Steel reinforcement work for shear wall 5* axis C5/A1-A3 | Steel Reinforcement | SHW | 5.40 to 8.80 | First Floor | 42136 | 42138 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2744 | installation of injection pipe and re-injectable hose at slab 5D-4B axis B19 to B21/A1 to A6 | Insulation | Slab | -3.80 | B1 | 42136 | 42148 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2745 | steel reinforcement for opening at core 3 due to modification axis B12/A9-A10 | Steel Reinforcement | Core | 2.90 to 6.20 | Ground Floor | 42137 | 42138 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2746 | steel reinforcement for opening at core 3 due to modification axis B12/A9-A10 | Steel Reinforcement | Core | 2.90 to 6.20 | Ground Floor | 42137 | 42138 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2747 | steel reinforcement for opening at core 3 due to modification axis B12/A9-A10 | Steel Reinforcement | Core | 1.10 to 2.90 | Ground Floor | 42137 | 42138 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2748 | form work for opening at core 3 due to modification axis B12/A9-A10 | Form Work | Core | 2.90 to 6.20 | Ground Floor | 42137 | 42138 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2749 | steel reinforcement for shear wall 3* axis A1 to A3/C8 | Steel Reinforcement | SHW | 5.40 to 8.80 | First Floor | 42137 | 42138 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2750 | form work for shear wall 3* axis C8/A2 to A3 | Form Work | SHW | 5.40 to 8.80 | First Floor | 42137 | 42138 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2751 | steel reinforcement for shear wall 1 axis C1/B18-B19/A1 | Steel Reinforcement | SHW | 7.50 to 10.90 | First Floor | 42137 | 42140 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2752 | form work removal slab 5D-4A axis B18 to B19/A3 to A6 | Removing Form Work | Slab | -3.80 | B1 | 42138 | 42138 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2753 | steel reiforcement for 4 columns C1 axis A14/B19-B18-B16& A12/B19 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42138 | 42141 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2754 | form work for 4 columns C1 axis A14/B19-B18-B16& A12/B19 | Form Work | Column | -3.80 to 1.10 | BOH | 42138 | 42141 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2755 | steel reinforcement for shear wall 1 axis C8/B1/A1 | Steel Reinforcement | SHW | 17.50 to 20.90 | Typical Floor | 42138 | 42141 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2756 | surface preparation for slab construction joints for slabs 5B-1, 5B-2& 5B-3 | Repair | Slab | -3.80 | B1 | 42138 | 42140 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2757 | form work for core 2 new wall due to design change at foundation level axis A8 to A9/B15 to B16 | Form Work | Core | -11.00 to -7.20 | B2 | 42140 | 42141 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2758 | form work for slab 5D-3 axis A6 to A10/B19 to B21 | Form Work | Slab | -3.80 | B1 | 42140 | 42141 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2759 | steel reinforcement for slab and beam at core 2 due to modfication at axis B15/A8-A9 | Steel Reinforcement | Slab | -7.20 | B2 | 42140 | 42141 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2760 | form work for shear wall 1 axis B1 to C7/A1 | Form Work | SHW | 17.50 to 20.90 | Typical Floor | 42140 | 42144 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2761 | form work for retaining wall axis A15 to A10/B21 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 42141 | 42144 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2762 | steel reinforcement for retaining wall axis A15 to A10/B21 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 42141 | 42141 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2763 | installation of injection pipe and re-injectable hose for retaining wall axis A15 to A10/B21 | Insulation | Retaining Wall | -3.80 to 1.10 | BOH | 42141 | 42166 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2764 | bottom layer steel reinforcement work for slab 5C-1 axis A11 to B15/B8 to B13 | Steel Reinforcement | Slab | 1.10 | BOH | 42141 | 42144 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2765 | form work removal for post station slab level 5.40 at hotel for second pour strip axis C5 to B18/A1 to A3 | Removing Form Work | Slab | 5.40 | First Floor | 42142 | 42143 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2766 | steel reinforcement for for new wall at core 2 due to modification axis A8 to A9/B16 to B15 | Steel Reinforcement | Core | -7.20 to -3.80 | B1 | 42143 | 42145 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2767 | form work for for new wall at core 2 due to modification axis A8 to A9/B16 to B15 | Form Work | Core | -7.20 to -3.80 | B1 | 42143 | 42147 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2768 | demolition for wall and beam at core 5 due to modification axis A9/B6 | Demolition | Core | -11.00 to -0.45 | B1,B2,BOH | 42143 | 42156 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2769 | holes and dowels fixation for new wall at core 2 due to modification axis A8 to A9/B16 to B15 | Dowels | Core | -7.20 to -3.80 | B1 | 42142 | 42144 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2770 | back propping supports for the second pour strip slab axis C5-B18/A1-A3 | Back Propping | Slab | 5.40 | First Floor | 42142 | 42143 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2771 | bottom layer steel reinforcement work for slab 5D-3 axis A6 to A10/B19 to B21 | Steel Reinforcement | Slab | -3.80 | B1 | 42142 | 42143 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2772 | holes and dowels fixation for slab at core 2 due to modification axis A8 to A9/B16 to B15 | Dowels | Slab | -3.80 | B1 | 42143 | 42145 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2773 | form work for new slab at core 2 due to modification at axis A8 to A9/B16 to B15 | Form Work | Slab | -3.80 | B1 | 42143 | 42145 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2774 | surface preparation and repair for slab construction joints for sections 5A-3& 5D-4 | Repair | Slab | -7.20 | B2 | 42143 | 42144 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2775 | demolition for elevator bit at core 5 due to modification at axis A9/B6 to B8 | Demolition | Core | -11.00 to -12.70 | B1,B2,BOH | 42143 | 42156 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2776 | demolition for wall at core 3 due to mdification axis A9/B11 | Demolition | Core | -0.45 to -3.80 | B1 | 42143 | 42170 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2777 | form work for retaining wall axis A10 to A15/B21 | Form Work | Retaining Wall | -2.50 to -1.10 | BOH | 42143 | 42147 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2778 | installation of injection pipe and re-injectable hose at retaining wall construction joints for slab 5D-3 axis A6 to A10/B19 to B21 | Insulation | Retaining Wall | -3.80 | B1 | 42143 | 42148 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2779 | top layer steel reinforcement work, dowels and final inspection for slab 5D-3 axis A6 to A10/B19 to B21 | Steel Reinforcement | Slab | -3.80 | B1 | 42143 | 42144 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2780 | steel reinforcement for retaining wall axis B21/A6 to A1 | Steel Reinforcement | Retaining Wall | -3.80 to Zero | B1 | 42143 | 42144 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2781 | steel reinfrocement for retaining wall axis B17 to B21/A15 | Steel Reinforcement | Retaining Wall | -3.80 to -2.50 | BOH | 42143 | 42144 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2782 | bottom layer steel reinforcement work for slab 5B-2 axis B4 to B9/A3 to A6 | Steel Reinforcement | Slab | 1.10 | BOH | 42145 | 42150 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2783 | form work removal for slab 5D-4B axis B19 to B21/A1 to A6 | Removing Form Work | Slab | -3.80 | B1 | 42145 | 42147 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2784 | steel reinforcement fopr new slab at core 2 due to modification axis A8 to A10/B16 to B14 | Steel Reinforcement | Slab | -3.80 | B1 | 42144 | 42145 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2785 | form work for retaining walls axis B17 to B21/A15 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 42144 | 42147 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2786 | installation of injection pipe and reinjectable hose at retaining wall axis B17 to B21/A15 | Insulation | Retaining Wall | -3.80 to -2.50 | BOH | 42144 | 42166 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2787 | steel reinforcement for column CC9 axis A11/B8 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42145 | 42147 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2788 | installation of composite column (Torque) for column CC9 axis A11/B6 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42145 | 42147 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2789 | steel reinforcement for new ramp beam at slab 5C-1 axis A13/B9 to B13 | Steel Reinforcement | Beam | -3.80 to 1.10 | BOH | 42145 | 42150 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2790 | form work for slab 2-1A axis B9 to B11/A8 to A11 | Form Work | Slab | 1.10 | BOH | 42147 | 42152 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2791 | fixation of shear connector for composite column CC9 axis B6/A11 | Shear Connectors | Column | 5.40 | Ground Floor | 42145 | 42147 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2792 | installation of injection pipe and re-injectable hose for retaining wall axis A6 to A4/B21 | Insulation | Retaining Wall | -3.80 to -2.50 | BOH | 42147 | 42148 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2793 | form work for retaining wall axis A6 to A4/B21 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 42147 | 42148 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2794 | steel reinforcement for retaining wall axis A6 to A10/B21 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 42147 | 42150 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2795 | inspection for holes and dowels fixation for shear wall 6 axis C3 | Dowels | SHW | 10.30 | Second Floor | 42147 | 42148 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2796 | steel reinforcement for shear wall 2 axis A2 to A3/C10 | Steel Reinforcement | SHW | 10.30 to 15.20 | Second Floor | 42171 | 42172 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2797 | steel reinforcement for core 2 new wall due to design change axis A9/B15 to B16 | Steel Reinforcement | Core | -3.80 to -0.4 | BOH | 42147 | 42148 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2798 | form work for core 2 new wall due to design change axis A9/B15 to B16 | Form Work | Core | -3.80 to -0.4 | BOH | 42147 | 42148 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2799 | drilling and fixation for side bars dowels in core 2 new wall axis A9/B15 to B16 | Dowels | Core | -3.80 to -0.4 | BOH | 42147 | 42148 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2800 | bottom layer steel reinforcement work for slab 1C | Steel Reinforcement | Slab | 1.10 | BOH | 42148 | 42150 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2801 | top layer steel reinforcement work, dowels and final inspection for slab of section 5B-2 axis B7 to B9/A4 to A6 | Steel Reinforcement | Slab | 1.10 | BOH | 42148 | 42150 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2802 | holes and dowels fixation for new beam at core 2 due to modification axis A8-A9/B16 to B15 | Dowels | Core | 1.10 | BOH | 42148 | 42151 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2803 | form work for core wall 7 axis A2 to A3/C7 | Form Work | Core | 14.30 to 16.60 | 3rd | 42148 | 42150 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2804 | form work for post tension slab at second pour strip axis C4-C5/B19/A1-A3 | Form Work | Slab | 10.30 | Second Floor | 42148 | 42150 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2805 | top and bottom layers of steel reinforcement work, dowels and final inspection for post tension slab and beams for first pour strip axis C4-C5/B1/A1-A3 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42148 | 42150 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2806 | post tension works for slab (Tendons-strands-anchors and profiles for first pour strip axis C4-C5/B1/A1-A3 | Cables | Slab | 10.30 | Second Floor | 42148 | 42150 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2807 | installation of injection pipe and re-injectable hose for retaining wall axis A10 to A6/B21 | Insulation | Retaining Wall | -3.80 to -2.50 | BOH | 42149 | 42166 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2808 | form work for retaining wall axis A6 to A10/B21 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 42149 | 42151 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2809 | dowels drilling and fixation for new beam B9 at core 7 | Dowels | Core | 10.30 | Second Floor | 42149 | 42158 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2810 | steel reinforcement work for core 8 axis A1 to A3/B1 to B2 | Steel Reinforcement | Core | 16.50 to 20.10 | 3rd | 42149 | 42151 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2811 | steel reinforcement for new wall at core 2 due to modification axis A8 to A9/B16 to B15 | Steel Reinforcement | Core | -0.4 to 2.9 | BOH | 42149 | 42150 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2812 | form work for new wall at core 2 due to modification axis A8 to A9/B16 to B15 | Form Work | Core | -0.4 to 2.9 | BOH | 42149 | 42151 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2813 | top layer steel reinforcement work, dowels and final inspection for slab 5B-2 axis B4 to B8/A3 to A6 | Steel Reinforcement | Slab | 1.10 | BOH | 42149 | 42156 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2814 | steel reinforcement for core 7 axis C7/A2-A3 | Steel Reinforcement | Core | 14.30 to 16.60 | 3rd | 42149 | 42150 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2815 | form work for column CC9 axis A11/B8 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42149 | 42152 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2816 | form work for stair 12 axis B1/A2 to A3 | Form Work | Stair | 1.10 to 5.40 | Ground Floor | 42150 | 42151 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2817 | top layer steel reinforcement work, dowels and final inspection for slab 5C-1 axis A11 to A15/B1 to B9 | Steel Reinforcement | Slab | 1.10 | BOH | 42150 | 42151 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2818 | surface preparation and repair for slab construction joints for sections 5A-3& 5D-4 | Repair | Slab | -7.20& -3.80 | B1, B2 | 42150 | 42159 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2819 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2820 | form work for core 8 | Form Work | Core | 16.50 to 19.90 | 3rd | 42151 | 42154 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2821 | steel reinforcement for shear wall 8 axis C2/A2 to A3 | Steel Reinforcement | SHW | 10.30 to 13.60 | Second Floor | 42151 | 42155 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2822 | steel reiforcement for shear wall 1 and column C1 axis C8 to B19/A1 | Steel Reinforcement | SHW | 10.90 to 14.90 | Second Floor | 42151 | 42155 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2823 | steel reinforcement for retaining wall axis B19 to B21/A15 | Steel Reinforcement | Retaining Wall | -3.80 to 1.10 | BOH | 42151 | 42155 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2824 | form work removal for slab 5D-3 axis A6 to A10/B19 to B21 | Removing Form Work | Slab | -3.80 | B1 | 42151 | 42152 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2825 | top layer steel reinforcement work, dowels and final inspection for slab 1C axis A5 to A8/B9 to B11 | Steel Reinforcement | Slab | 1.10 | BOH | 42151 | 42154 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2826 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2827 | drilling and fixation for reduced door opening at core 2 due to design change axis A9/B14 | Dowels | Core | 1.10 to 3.40 | Ground Floor | 42152 | 42157 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2828 | steel reinforcement for 1 column CC9 axis B6/A11 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42151 | 42154 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2829 | form work for 1 column CC9 axis B6/A11 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42151 | 42154 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2830 | steel reinforcement for core 2 axis A8 to A10/B14 to B16 | Steel Reinforcement | Core | 2.9 to 6.2 | Ground Floor | 42152 | 42157 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2831 | stressing of strands for first pour strip for post tension slab axis C4-C5/B1/A1-A3 | Stressing | Slab | 10.30 | Second Floor | 42158 | 42159 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2832 | fixation of shear connectors for column CC7 axis B5/A6 | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42155 | 42159 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2833 | installation of column CC7 (torque) axis B5/A6 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42155 | 42159 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2834 | form work for ramp axis A7 to A15/B1-B6 | Form Work | Ramp | -7.20 to 1.10 | B2 : BOH | 42155 | 42158 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2835 | bottom layer steel reinforcement work for slab 2-1A axis B9 to B11/A8 to A11 | Steel Reinforcement | Slab | 1.10 | BOH | 42155 | 42158 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2836 | holes and dowels fixation for new ramp beam due to modification axis A10 to A13/B2 to B3 | Dowels | Beam | -3.80 | B1 | 42155 | 42156 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2837 | steel reinforcement for stair 5 axis A8 to A9/B8 | Steel Reinforcement | Stair | -0.45 to 1.10 | BOH | 42155 | 42159 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2838 | steel reinforcement for stair 6 axis A8/B10-B11 | Steel Reinforcement | Stair | -0.45 to 1.10 | BOH | 42155 | 42159 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2839 | holes and dowels fixation for new wall at core 5 due to modification axis A9/A5 | Dowels | Core | -12.70 | Raft | 42155 | 42156 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2840 | form work for retaining wall axis A4 to A1/B19 to B21 | Form Work | Retaining Wall | -3.80 to -2.50 | BOH | 42155 | 42157 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2841 | installation of injection pipe and re-injectable hose for retaining wall axis A4 to A1/B19 to B21 | Insulation | Retaining Wall | -3.80 to -2.50 | BOH | 42155 | 42166 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2842 | form work for shear wall 1 axis B1 to C7/A1 | Form Work | SHW | 17.50 to 20.90 | Typical Floor | 42156 | 42157 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2843 | dowels drilling and fixation for core 6-7 | Dowels | Core | 10.30 | Second Floor | 42157 | 42159 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2844 | form work for shear wall 8 axis C1/A2 to A3 | Form Work | SHW | 10.30 to 13.60 | Second Floor | 42156 | 42157 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2845 | Bottom Layer Steel Reinforcement Work for Slab 5D-1 axis A4 to A5/B9 to B13 | Steel Reinforcement | Slab | 1.10 | BOH | 42156 | 42157 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2846 | drilling and fixation for core 5 side bars axis B7/A8 | Dowels | Core | -7.20 to -11.00 | B2 | 42156 | 42162 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2847 | drilling and fixation for ramp dowels axis A8 to A15/C1 to B6 | Dowels | Ramp | -7.20 to -11.00 | B2 | 42156 | 42161 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2848 | form work for core 5 new wall due to design change axis B7/A9 | Form Work | Core | -12.70 to -11.00 | Raft | 42157 | 42157 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2849 | form work removal axis B9 to B13/A12 to A15 | Removing Form Work | Slab | 1.10 | BOH | 42159 | 42159 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2850 | steel reinforcement work for core 5 new wall due to design change axis B7/A9 | Steel Reinforcement | Core | -12.70 to -11.00 | Raft | 42157 | 42157 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2851 | dowels drilling and fixation for embedded beam axis A1/B17 to B19 | Dowels | Beam | 10.30 | Second Floor | 42157 | 42159 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2852 | steel reinforcement for panoramic elevator column axis B9/between A5-A6 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42157 | 42158 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2853 | top Layer Steel Reinforcement Work for Slab 5D-1 axis A4 to A5/B9 to B13 | Steel Reinforcement | Slab | 1.10 | BOH | 42157 | 42159 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2854 | steel reinforcement work for core 5 new wall due to design change axis B7/A9 | Steel Reinforcement | Core | -11.00 to -7.20 | B2 | 42157 | 42159 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2855 | form work for core 5 new wall due to design change axis B7/A9 | Form Work | Core | -11.00 to -7.20 | B2 | 42157 | 42162 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2856 | top layer steel reinforcement work for slab 2-1A axis B9 to B11/A8 to A11 | Steel Reinforcement | Slab | 1.10 | BOH | 42157 | 42159 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2857 | steel reinforcement for second pour strip 5 beams (B1-CB3-B3-CB2-EB) axis B7-B8/A2, A2-A3/C6, A2-A3/B11, A2-A3/C10& A2-A3/B15-B19 | Steel Reinforcement | Slab | 10.30 | Ground Floor | 42157 | 42159 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2858 | holes and dowels fixation for new beam at core 5 due to modification axis A10 to B9/B7 to B8 | Dowels | Core | -7.20 | B2 | 42158 | 42159 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2859 | installation of composite column (Torque) CC7 axis A6/B6 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42158 | 42159 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2860 | fixation of shear connectors for composite column CC7 axis A6/B6 | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42158 | 42159 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2861 | surface preparation and repair for slab construction joints for sections 5A-4& 4A | Repair | Slab | -3.80 & 1.10 | B1& BOH | 42158 | 42180 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2862 | steel reinforcement for new slab and beam at core 5 due to modification axis A10 to A9/B6 to B8 | Steel Reinforcement | Slab | -7.20 | B2 | 42159 | 42162 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2863 | steel reinforcement for panoramic elevator column axis between B9-B10/A5 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42158 | 42159 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2864 | installation of 2 composite column CC7 (Torque) axis A6/B9-B10 west | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42159 | 42162 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2865 | fixation of shear connectors for 2 composite columns CC7 axis A6/B9-B10 west | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42159 | 42162 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2866 | steel reinforcement for 2 columns CC7 axis A6/B5-B6 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42159 | 42161 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2867 | form work for 2 columns CC7 axis A6/B5-B6 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42159 | 42162 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2868 | form work for 2 panoramic elevator columns axis A5/B9-B10 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42159 | 42163 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2869 | steel reinforcement work, dowels and final inspection for bridge beams axis A2-A3/C7-C8 | Steel Reinforcement | Beam | 10.30 | Second Floor | 42159 | 42161 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2870 | restressing of strands for 8 post tension strands in longitudinal direction for first pour strip axis C4-C5/B1/A1-A3 | Stressing | Slab | 10.30 | Second Floor | 42159 | 42161 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2871 | form work for shear wall 1 axis B19 to B21/A1 | Form Work | SHW | -2.50 to 1.10 | BOH | 42161 | 42162 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2872 | steel reinforcement for column CC7 east axis A6/B9 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42161 | 42163 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2873 | form work for column CC7 east axis A6/B9 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42161 | 42165 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2874 | bottom steel reinforcmenet for ramp axis A6 to A15/C1 to B6 | Steel Reinforcement | Ramp | -7.20 to 1.10 | B1& BOH | 42161 | 42161 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2875 | grouting for post tension slab for first pour strip axis C3 to C4 | Grout | Slab | 10.30 | Second Floor | 42161 | 42165 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2876 | form work removal for slab 1C axis | Removing Form Work | Slab | 1.10 | BOH | 42161 | 42162 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2877 | fixation of shear connectors for composite column CC7 axis A6/B8 | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42161 | 42162 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2878 | installation of composite column (torque) CC7 axis A6/B8 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42161 | 42162 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2879 | form work for part of slab 5B-1 axis B4 to B5/A6 to A8 | Form Work | Slab | 1.10 | BOH | 42162 | 42165 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2880 | steel reinforcement for column CC7 axis B8/A6 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42162 | 42165 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2881 | installation of composite column (torque) for CC7 axis B9/A6 west | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42162 | 42163 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2882 | fixation of shear connectors for composite column CC7 axis B9/A6 west | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42162 | 42163 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2883 | installation of composite column (Torque) for CC9 axis B10/A11 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42162 | 42165 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2884 | fixation of shear connectors for composite column CC9 axis B10/A11 | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42162 | 42165 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2885 | form work for slab of paoramic elevator axis A5 to A6/B9 to B10 | Form Work | Slab | -7.20 | B2 | 42162 | 42165 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2886 | form work for column CC7 axis B8/A6 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42162 | 42165 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2887 | installation of composite column (torque) CC3 axis B9/A11 east | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42163 | 42165 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2888 | fixation of shear connectors for column CC3 axis B9/A11 east | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42163 | 42165 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2889 | surface preparation and repair of slab 5C-3 axis A11 to A15/B16 to B21 | Repair | Slab | -7.20 | B2 | 42163 | 42180 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2890 | steel fabrication for composite columns for items as attached | Fabrication | Column | - | - | 42164 | 42170 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2891 | holes and dowels fixation for new beam at core 5 due to modification axis A10 to B9/B7 to B8 | Dowels | Core | -3.80 | B1 | 42163 | 42165 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2892 | demolition of wall and elevator bit at core 3 due to modification axis A11/B9 | Demolition | Core | -3.80 to -11.00 & -11.00 to -12.70 | B2-B1 | 42163 | 42176 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2893 | steel reinforcement for column CC9 axis A11/B10 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42163 | 42166 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2894 | form work for column CC9 axis A11/B10 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42163 | 42166 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2895 | form work for part of slab 2-1A& 2-2A axis B12 to B14/A11 to A8 | Form Work | Slab | 1.10 | BOH | 42163 | 42165 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2896 | steel reinforement for shear wall 1 axis B19 to B20/A1 | Steel Reinforcement | SHW | 1.10 to 7.10 | Ground Floor | 42163 | 42165 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2897 | form work for shear wall 1 axis B19 to B20/A1 | Form Work | SHW | 1.10 to 7.10 | Ground Floor | 42164 | 42165 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2898 | bottom layer steel reinforcement for part of slab 5B-1 axis B4/A5 to A8 | Steel Reinforcement | Slab | 1.05 | BOH | 42163 | 42165 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2899 | form work removal for slab 5B-2 axis B4 to B9/A3 to A6 | Removing Form Work | Slab | 1.10 | BOH | 42163 | 42165 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2900 | form work for core 2 axis A8 to A10/B10 to B14 | Form Work | Core | 2.9 to 6.2 | Ground Floor | 42165 | 42168 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2901 | steel reinforcement for core 4 axis B8 to B9/A7 to A10 | Steel Reinforcement | Core | 1.10 to 5.40 | Ground Floor | 42164 | 42165 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2902 | form work for core 4 axis B9 to B8/A7 to A10 | Form Work | Core | 1.10 to 5.40 | Ground Floor | 42164 | 42166 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2903 | top layer steel reinforcement work, dowels and final inspection for part of slab 5B-1 axis B4/A5 to A8 | Steel Reinforcement | Slab | 1.05 | BOH | 42164 | 42165 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2904 | steel reinforcement for 1 column panoramic elevator between B10-B11/A5 to A6 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42164 | 42165 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2905 | post tension works for slab (Tendons-strands-anchors and profiles for second pour strip axis C5-B19/A1-A3 | Cables | Slab | 10.30 | Second Floor | 42164 | 42165 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2906 | top and bottom layers of steel reinforcement work, dowels and final inspection for second pour strip axis C5 to B19/A1 to A3 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42164 | 42165 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2907 | steel reinforcement for stair 12 axis B1/A2 to A3 | Steel Reinforcement | Stair | 1.10 to 5.40 | Ground Floor | 42165 | 42165 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2908 | steel reinforcement for 5 columns C1 axis B20/A3-A4-A5& B19/A4-A5 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42165 | 42165 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2909 | steel reinforcement for column CC3 axis A11/B9 east side | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42164 | 42170 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2910 | form work for column CC3 axis A11/B9 east side | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42164 | 42170 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2911 | form work for column CC7 axis B9/A6 west side | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42164 | 42166 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2912 | steel reinforcement for column CC7 axis B9/A6 west side | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42164 | 42166 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2913 | top layer steel reinforcement for ramp axis A7 to A15/B7 to B1 | Steel Reinforcement | Ramp | -7.20 to 1.10 | B2 : BOH | 42164 | 42168 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2914 | steel rienforement for new wall and beam at core 5 due to modification at axis A10 to A9/B7 to B8 | Steel Reinforcement | Core | -7.20 to -3.80 | B2 | 42164 | 42168 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2915 | form work for 1 panoramic elevator column between axis A5-A6/B10-B11 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42165 | 42168 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2916 | form work for remaining of panoramic elevator columns due to modification at axis A5-A6/B9-B10-B11 | Form Work | Column | -11.00 to -7.20 | B2 | 42165 | 42168 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2917 | form work removal for first pour strip axis B1 to C5/A1 to A3 | Removing Form Work | Slab | 10.30 | Second Floor | 42165 | 42168 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2918 | steel reinforcement for 1 column panoramic elevator between B10/A6 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42166 | 42168 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2919 | form work for new wall and beam at core 5 due to modification at axis A9/B7 | Form Work | Core | -7.20 to -3.80 | B1 | 42166 | 42170 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2920 | drilling and fixation for core 3 new wall and beam due to design change axis A9/B11 | Dowels | Core | -12.70 | Raft | 42166 | 42170 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2921 | fixation of shear connectors for composite column CC7 axis A7-A8/B4 | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42168 | 42170 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2922 | installation of composite column (torque) CC7 axis A7-A8/B4 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42168 | 42170 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2923 | form work for 1 column panoramic elevator between B10/A6 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42168 | 42170 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2924 | top and bottom layers of steel reinforcement work, dowels and final inspection for rest of post tension slab at second pour strip axis B19 to B20/A1 to A3 | Steel Reinforcement | Slab | 5.40 | First Floor | 42169 | 42170 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2925 | steel reinforcement for shear wall 5 axis A2 to A3/C5 | Steel Reinforcement | SHW | 10.30 to 15.20 | Second Floor | 42169 | 42172 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2926 | steel reinforcement for shear wall 3 axis A2 to A3/C6 | Steel Reinforcement | SHW | 10.30 to 15.20 | Second Floor | 42169 | 42170 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2927 | steel einforcement for shear wall 2* axis A2 to A3/C8 | Steel Reinforcement | SHW | 10.30 to 15.20 | Second Floor | 42169 | 42170 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2928 | form work for shear wall 1 axis C8 to B19/A1 | Form Work | SHW | 11.30 to 14.40 | Second Floor | 42169 | 42170 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2929 | surface preparation and repair of retaining wall as attached | Repair | Retaining Wall | -11.00 to -7.20 | B2 | 42169 | 42183 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2930 | steel reinforcement for elevator pit of core 3 due to modification axis A10-A9/B10-B11 | Steel Reinforcement | Core | -12.70 to -11.00 | Raft | 42169 | 42172 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2931 | form work for elevator pit of core 3 due to modification axis A10-A9/B10-B11 | Form Work | Core | -12.70 to -11.00 | Raft | 42169 | 42172 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2932 | form work for ramp beams axis A13 to A14/B4 to B7 | Form Work | Beam | 1.10 | BOH | 42171 | 42175 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2933 | bottom layer steel reinforcement for part of slab 2-1A& 2-2A axis B12 to B14/A8 to A11 | Steel Reinforcement | Slab | 1.10 | BOH | 42169 | 42170 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2934 | fixation of shear connectors for 2 columns CC1 axis B9/A8& B9/A10 west side | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42169 | 42170 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2935 | installation of 2 composite column (torque) CC1 axis B9/A8& B9/A10 west side | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42169 | 42170 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2936 | steel reinforcement for 1 column CC7 axis B4/A8 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42169 | 42170 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2937 | form work for 1 column CC7 axis B4/A8 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42169 | 42170 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2938 | form work for retaining wall axis B17 to B20/A15 | Form Work | Retaining Wall | -2.50 to 1.20 | BOH | 42169 | 42172 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2939 | form work for shear wall 5 axis C5/A1 to A3 | Form Work | SHW | 10.30 to 15.20 | Second Floor | 42171 | 42172 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2940 | form work removal for slab 2-1A axis B9 to B11/A8 to A12 | Removing Form Work | Slab | 1.10 | BOH | 42169 | 42170 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2941 | form work removal for slab 5D-1 axis B9 to B13/A4 to A5 | Removing Form Work | Slab | 1.10 | BOH | 42169 | 42170 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2942 | form work for shear wall 3 axis C6/A2 to A3 | Form Work | SHW | 10.30 to 15.20 | Second Floor | 42171 | 42172 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2943 | form work for shear wall 2* axis C8/A2 to A3 | Form Work | SHW | 10.30 to 15.20 | Second Floor | 42171 | 42172 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2944 | stressing of strands for post tension slab at second pour strip | Stressing | Slab | 10.30 | Second Floor | 42171 | 42175 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2945 | bottom layer steel reinfrocement work for slab panoramic elevator axis B9 to B10/A5 to A6 | Steel Reinforcement | Slab | -7.20 | B2 | 42171 | 42175 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2946 | installaation of composite column (torque) CC7 and CC4 axis D4& B16/A12 | Composite Columns | Column | -3.80 to 1.10 | BOH | 42171 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2947 | fiaxtion of shear connectors for composite columns CC7 and CC4 axis D4& B16/A12 | Shear Connectors | Column | -3.80 to 1.10 | BOH | 42171 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2948 | form work for column CC7 axis B16/A12 | Form Work | Column | -3.80 to 1.10 | BOH | 42171 | 42175 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2949 | steel reinforcement for column CC7 axis B16/A12 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42171 | 42175 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2950 | steel reinforcement for column CC4 axis D4 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42171 | 42175 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2951 | form work for column CC4 axis D4 | Form Work | Column | -3.80 to 1.10 | BOH | 42171 | 42175 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2952 | form work for 5 columns C1 axis B20/A3-A4-A5& B19/A4-A5 | Form Work | Column | -3.80 to 1.10 | BOH | 42171 | 42172 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2953 | form work for shear wall 2 axis A2 to A3/C10 | Form Work | SHW | 10.30 to 15.20 | Second Floor | 42171 | 42172 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2954 | steel reinforcement for core 7 axis C7/A2-A3 | Steel Reinforcement | Core | 16.60 to 19.90 | 3rd | 42171 | 42175 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2955 | form work for retaining wall axis A15 to A10/B21 | Form Work | Retaining Wall | -2.50 to -1.00 | BOH | 42171 | 42175 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2956 | form work for retaining wall axis A7 to A4/B21 | Form Work | Retaining Wall | -2.50 to -1.00 | BOH | 42171 | 42175 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2957 | steel reinforcement for new wall at core 5 due to modification axis A10 to A9/B7 to B8 | Steel Reinforcement | Core | -3.80 to 1.10 | BOH | 42171 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2958 | form work for slab of core 5 axis B6 to B8/A8 to A10 | Form Work | Slab | 1.10 | BOH | 42171 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2959 | steel reinforcement for 1 column CC1 axis B9/A10 east side | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42171 | 42172 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2960 | form work for 1 column CC1 axis B9/A10 east side | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42171 | 42175 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2961 | top layer steel reinforcement work, dowels and final inspection for part of slab of sections 2-1A& 2-2A axis B12 to B14/A8 to A11 | Steel Reinforcement | Slab | 1.10 | BOH | 42171 | 42175 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2962 | form work for shear wall 1 axis B19 to B20/A1 | Form Work | SHW | 10.30 to 15.20 | Second Floor | 42171 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2963 | surface preparation for slab construction joints for slabs as attached sketch | Repair | Slab | 3.80 | Ground Floor | 42171 | 42175 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2964 | fixation of shear connectors of composite column CC7 axis A2-A3/C9 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42172 | 42175 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2965 | fixation of shear connectors of composite column CC6 axis A2-A3/C11 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42172 | 42175 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2966 | stressing of strands for post tension slab by increasing force 5% for cables 25-29-49 in transversal | Stressing | Slab | 5.40 | First Floor | 42172 | 42178 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2967 | form work for core 7 axis A2 to A3/C7 | Form Work | Core | 17.30 to 20.60 | Typical Floor | 42172 | 42175 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2968 | steel reinforcement for shear wall 6 axis C4/A2 to A3 | Steel Reinforcement | SHW | 17.30 to 20.60 | Typical Floor | 42172 | 42183 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2969 | steel reinforcement for shear wall 7 axis C3/A2 to A3 | Steel Reinforcement | SHW | 17.30 to 20.60 | Typical Floor | 42172 | 42191 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2970 | form work for retaining wall axis A10 to A7/B21 | Form Work | Retaining Wall | -2.50 to -1.00 | BOH | 42172 | 42175 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2971 | form work removal for salab 5B-1 axis B4 to B5/A5 to A8 | Removing Form Work | Slab | 1.10 | BOH | 42172 | 42175 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2972 | top layer steel reinforcement work, dowels and final inspection for slab of panoramic elevator axis B9 to B10/A5 to A6 | Steel Reinforcement | Slab | -7.20 | B2 | 42172 | 42175 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2973 | installation of composite column (torque) for CC3& CC1 west side axis B9/A10-A11 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42172 | 42175 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2974 | form work for new wall at core 5 due to modification axis A10-A9/B7-B8 | Form Work | Core | -3.80 to 1.10 | BOH | 42172 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2975 | fixation of shear connectors for composite columns CC3& CC1 axis B9/A10-A11 west side | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42172 | 42175 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2976 | steel reinfrocement for shear wall 1 axis B19 to B20/A1 | Steel Reinforcement | SHW | 10.30 to 15.20 | Second Floor | 42173 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2977 | drilling and fixation for core 5 de to design change axis A10 to B9/B7 to B8 | Dowels | Core | 1.10 | BOH | 42173 | 42183 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2978 | ducts grouting for post tension slab for second pour strip axis C3-C4/A1-A3/B20 | Grout | Slab | 5.40 | First Floor | 42175 | 42178 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2979 | steel reinforcement for shear wall 3* axis A2-A3/C8 | Steel Reinforcement | SHW | 10.30 to 15.20 | Second Floor | 42175 | 42176 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2980 | form work for shear wall 3* axis A2-A3/C8 | Form Work | SHW | 10.30 to 15.20 | Second Floor | 42175 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2981 | surface preparation and repair for core 3 outer walls | Repair | Core | -1.10 to 3.80 | BOH | 42175 | 42183 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2982 | form work for shear wall 1 axis B19-B20/A2-A3 | Form Work | SHW | 5.40 to 10.30 | First Floor | 42173 | 42175 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2983 | holes and dowels fixation for new beam at core 5 due to modification axis A10-A9/B7-B8 | Dowels | Core | -1.10 | BOH | 42175 | 42179 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2984 | holes and dowels fixation for new wall and beam at core 3 due to modification axis A10-A9/B10-B11 | Dowels | Core | -11.00 to -7.20 | B2 | 42175 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2985 | surface prearation and repair for core 5 axis B6/A8 to A10& A10/B6 to B8 | Repair | Core | 11.00 to 7.10 | Ground Floor | 42175 | 42179 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2986 | steel reinforcement for shear wall 5* axis C5/A2-A3 | Steel Reinforcement | SHW | 10.30 to 13.60 | Second Floor | 42176 | 42177 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2987 | form work for shear wall 5* axis C5/A2-A3 | Form Work | SHW | 10.30 to 13.60 | Second Floor | 42176 | 42180 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2988 | form work for column CC5 axis C9/A3 | Form Work | Column | 10.30 to 14.80 | Second Floor | 42176 | 42178 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2989 | form work for column CC6 axis C11/A2-A3 | Form Work | Column | 10.30 to 14.80 | Second Floor | 42176 | 42178 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2990 | fixation of shear connectors for composite columns CC7& CC9 axis B12/A6-A11 | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42176 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2991 | installation of composite column (torque) CC7& CC9 axis B21/A6& B12/A11 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42176 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2992 | steel reinforcement for column CC3 axis B9/A11 east side | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42176 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2993 | form work for column CC3 axis B9/A11 east side | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42176 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2994 | steel reinforcement for column CC1 axis A8/B9 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42176 | 42177 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2995 | form work for column CC1 axis A8/B9 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42176 | 42178 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2996 | form work for retaining wall axis B19 to B21/A15 | Form Work | Retaining Wall | -2.50 to -1.2 | BOH | 42176 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2997 | form work for retaining wall axis A1 to A4/B21& B19 to B21/A1 | Form Work | Retaining Wall | -2.50 to -1.2 | BOH | 42176 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2998 | steel reinforcment for column CC6 axis A3/C11 | Steel Reinforcement | Column | 10.30 to 14.80 | Second Floor | 42176 | 42178 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-2999 | steel reinforcement for column CC5 axis A3/C9 | Steel Reinforcement | Column | 10.30 to 14.80 | Second Floor | 42176 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3000 | surface preparation and repair for construction joints for slab 5D-4B axis B19 to B21/A6 | Repair | Slab | -3.80 | B1 | 42177 | 42180 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3001 | steel reinforcement for new wall at core 3 due to modification axis A10 to A9/B11 to B12 | Steel Reinforcement | Core | -11.00 to -7.20 | B2 | 42177 | 42179 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3002 | form work for column CC7 axis A6/B12 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42177 | 42178 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3003 | steel reinforcement for column CC7 axis A6/B12 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42177 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3004 | form work for column CC1 axis B9/A10 west side | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42177 | 42178 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3005 | steel reinfrocement for column CC1 axis B9/A10 west side | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42177 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3006 | form work for column CC9 axis B12/A11 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42177 | 42180 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3007 | steel reinforcement for column CC9 axis B12/A11 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42177 | 42180 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3008 | form work for 2 columns C1 axis B20/A8-A6 | Form Work | Column | -3.80 to 1.10 | BOH | 42177 | 42178 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3009 | steel reinforcement for 2 columns C1 axis B20/A8-A6 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42177 | 42177 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3010 | repair of core 5 axis A7 to A8/B8 to B9 | Repair | Core | 1.10 to 6.10 | Ground Floor | 42178 | 42184 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3011 | repair of core 3 axis B10 to B12/A7 to A8 | Repair | Core | 1.10 to 3.10 | Ground Floor | 42178 | 42184 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3012 | steel reinforcement for new wall at core 5 due to modification axis A8 to A9/B7 to B8 | Steel Reinforcement | Core | -11.00 to -7.20 | B2 | 42178 | 42180 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3013 | form work for new wall at core 5 due to modification axis A8 to A9/B7 to B8 | Form Work | Core | -11.00 to -7.20 | B2 | 42178 | 42180 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3014 | form work removal for second pour strip axis C5 to B19/B20 and A1 to A4 | Removing Form Work | Slab | 10.30 | Second Floor | 42178 | 42186 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3015 | ducts grouting for post tension second pour strip slab axis C5 to B19/B20& A1 to A4 | Grout | Slab | 10.30 | Second Floor | 42179 | 42186 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3016 | form work for new walls at core 3 due to modification axis A8 to A9/B11 to B12 | Form Work | Core | -11.00 to -7.20 | B2 | 42178 | 42180 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3017 | steel reinforcement for new walls at core 3 due to modification axis A8 to A9/B11 to B12 | Steel Reinforcement | Core | -11.00 to -7.20 | B2 | 42178 | 42182 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3018 | steel reinforcement work for core 6 axis B15 to B17/A1 to A2 | Steel Reinforcement | Core | 8.80 TO 15.20 | Second Floor | 42178 | 42180 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3019 | Form work for core 6 axis B15 to B17/A1 to A2 | Form Work | Core | 8.80 TO 15.20 | Second Floor | 42178 | 42182 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3020 | steel reinforcmeen tfor rest of slab axis B19 to B20/A1 to A3 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42178 | 42180 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3021 | form work for stair case 3 axis B6 to B7/A8 to A9 | Form Work | Stair | -0.45 to 1.10 | BOH | 42179 | 42180 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3022 | form work for first pour strip axis A1 to A3/C4 to C5 | Form Work | Slab | 5.40 | First Floor | 42179 | 42180 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3023 | steel reinforcement for first pour strip axis A1 to A3/C4 to C5 | Form Work | Slab | 5.40 | First Floor | 42179 | 42180 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3024 | form work removal for slab 2-1B axis A3 to A7/B6 to B13 | Removing Form Work | Slab | 1.10 | BOH | 42179 | 42180 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3025 | surface preparation and repair for slab for part of 5B-2 | Repair | Slab | -3.80 | B1 | 42180 | 42184 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3026 | steel reinforcement work, dowels and final inspection for slab to closing opening for tower crane 1 axis A2-A3/C3 to C4 | Steel Reinforcement | Slab | -3.80 | B1 | 42180 | 42182 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3027 | form work for slab to closing opening for tower crane 1 axis A2 to A3/C3 to C4 | Form Work | Slab | -3.80 | B1 | 42180 | 42182 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3028 | steel reinforcement for shear wall 1 axis C8 to C11/A1 | Steel Reinforcement | SHW | 14.50 to 17.80 | 3rd | 42180 | 42182 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3029 | form work for core 3 due to modification axis A8 to A9/B11 to B12 | Form Work | Core | -7.20 to -3.80 | B1 | 42180 | 42189 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3030 | form work for shear wall 7 axis A1 to A3/C3 | Form Work | SHW | 18.00 to 21.30 | Typical Floor | 42182 | 42190 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3031 | steel reinforcement for shear wall 1 axis B19 to B20/A1 | Steel Reinforcement | SHW | 10.30 to 13.60 | Second Floor | 42180 | 42182 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3032 | form work for shear wall 6 axis A1 to A3/C4 | Form Work | SHW | 18.00 to 21.30 | Typical Floor | 42182 | 42190 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3033 | form work form first pour strip for post tension slab axis C4 to C5/A1 to A3 | Form Work | Slab | 15.20 | 3rd | 42182 | 42189 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3034 | form work for shear wall 1 axis A1 to A3/B19 to B20 | Form Work | SHW | 10.30 to 13.60 | Second Floor | 42182 | 42182 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3035 | surface preparation and repair for slab construction joints for slabs 5B-1, 5B-2& 5A-1 | Repair | Slab | -3.80 | B1 | 42182 | 42182 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3036 | form work for new walls and beam at core 5 axis A8 to A10/B6 to B7 | Form Work | Core | -7.20 to -3.80 | B1 | 42182 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3037 | steel reinforcement for new walls and beam at core 5 axis A8 to A10/B6 to B7 | Steel Reinforcement | Core | -7.20 to -3.80 | B1 | 42182 | 42183 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3038 | fixation of shear connectors for 2 composite columns CC1 axis A10-A11/B13 east side | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42182 | 42183 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3039 | installation (Torque) for 2 composite columns CC1 axis A10-A11/B13 east side | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42182 | 42183 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3040 | restressing of strands for 4 post tension strands by increasing force 5% for cables 22, 34 in Y direction and cables 26, 40 in X direction | Stressing | Slab | 10.30 | Second Floor | 42183 | 42184 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3041 | steel reinforcement for new slab and beam at core 5 due to modification axis A8 to A10/B6 to B8 | Steel Reinforcement | Core | 1.10 | BOH | 42183 | 42192 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3042 | dowels drilling and fixation for beam at core 3 due to modification axis A9/B10-B11 | Dowels | Core | -3.80 | B1 | 42183 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3043 | steel reinforcement for new wall and beam at core 3 due to modification axis A8 to A10/B11 to B12 | Steel Reinforcement | Core | -7.20 to -3.80 | B1 | 42183 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3044 | fixation of shear connector for columns CC1* east side axis A8/B13 | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42183 | 42184 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3045 | fixation of column CC1* (Torque) axis A8/B13 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42183 | 42184 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3046 | form work for shear wall 1 axis A1/B19 to C11 | Form Work | SHW | 13.60 to 16.90 | Second Floor | 42184 | 42189 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3047 | form work for shear wall 1 axis A1/C8 to C11 | Form Work | SHW | 13.60 to 16.90 | Second Floor | 42184 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3048 | surface preparation for slab and slab's construction joints for sections 1B& 5B-2 | Repair | Slab | 1.10 | BOH | 42184 | 42190 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3049 | steel reinforcement for shear wall 1 axis B17 to B19/A1 | Steel Reinforcement | SHW | 13.60 to 16.90 | Second Floor | 42184 | 42186 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3050 | steel reinforcement for 2 columns CC1 axis B13/A10-A11 east side | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42184 | 42186 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3051 | form work for 2 columns CC1 axis B13/A10-A11 east side | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42184 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3052 | steel reinforcement for new wall and beam at core 3 due to modification axis A8 to A10/B11 to B12 | Steel Reinforcement | Core | -7.20 to -3.80 | B1 | 42184 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3053 | form work for new wall and beam at core 3 due to modification axis A8 to A10/B10 to B12 | Form Work | Core | -7.20 to -3.80 | B1 | 42184 | 42189 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3054 | form work for panoramic elevator slab axis A5 to A6/B9 to B10 | Form Work | Slab | -3.80 | B1 | 42184 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3055 | form work for shear wall 1 axis B15 to B17/A1 | Form Work | SHW | 13.60 to 16.90 | Second Floor | 42185 | 42190 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3056 | steel reinforcement for shear wall 1 axis B15 to B17/A1 | Steel Reinforcement | SHW | 13.60 to 16.90 | Second Floor | 42185 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3057 | form work for new wall and beam at core 5 due to modification at axis A9/B7 | Form Work | Core | -3.80 to 1.10 | BOH | 42185 | 42191 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3058 | steel reinforcement for new wall and beam at core 5 due to modification axis A8 to A10/B6 to B7 | Steel Reinforcement | Core | -3.80 to 1.10 | BOH | 42185 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3059 | installation of 2 columns (torque) CC1 axis A10-A11/B13 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42185 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3060 | fixation of shear connector for 2 columns CC1 west axis A10 to A11/B13 | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42185 | 42189 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3061 | fixation of shear connector for column CC1* axis A8/B13 west side | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42185 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3062 | installation of column CC1* (torque) axis A8/B13 west side | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42185 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3063 | form work for column CC1* axis B13/A8 east side | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42185 | 42189 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3064 | steel reinforcement for columns CC1* axis B13/A8 east side | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42185 | 42186 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3065 | repair of column C1 axis A14/B19 to close NCR No. 079 | Repair | Column | -11.00 to -7.20 | B2 | 42186 | 42191 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3066 | installation of strirrups after surface preparation for column C1 axis A14/B19 to close NCR No. 079 | Repair | Column | -11.00 to -7.20 | B2 | 42186 | 42189 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3067 | form work for column CC1 axis B13/A10 west side | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42186 | 42189 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3068 | surface preparation for column C1 axis A14/B19 to close NCR No. 079 | Repair | Column | -11.00 to -7.20 | B2 | 42186 | 42189 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3069 | steel reinforcement work for column CC1 axis B13/A10 west side | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42186 | 42189 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3070 | form work for core 2 axis A7 to A10/B14 to B16 | Form Work | Core | 6.20 to 9.50 | First Floor | 42186 | 42196 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3071 | steel reinforcement work for core 2 axis A7 to A10/B14 to B16 | Steel Reinforcement | Core | 6.20 to 9.50 | First Floor | 42186 | 42189 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3072 | bottom layer steel reinforcement work, dowels and final inspection for slab of panoramic elevator | Steel Reinforcement | Slab | -3.80 | B1 | 42186 | 42189 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3073 | steel reinforcement work, dowels and final inspection for post tension slab beams at first pour strip axis C4 to C5/A1 to A3 | Steel Reinforcement | Beam | 15.20 | 3rd | 42187 | 42196 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3074 | steel reinforcement work for core 8 axis A1 to A3/B1 to B2 | Steel Reinforcement | Core | 19.50 to 22.90 | Typical Floor | 42187 | 42189 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3075 | form work for core 8 axis A2 to A3/B1 | Form Work | Core | 19.50 to 22.90 | Typical Floor | 42187 | 42196 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3076 | form work for new walls and beam at core 3 due to modification axis A8 to A10/B10 to B12 | Form Work | Core | -3.80 to 1.10 | BOH | 42187 | 42198 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3077 | steel reinforcement work for new walls and beam at core 3 due to design change axis A8 to A10/B10 to B12 | Steel Reinforcement | Core | -3.80 to 1.10 | BOH | 42187 | 42198 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3078 | form work removal for slab at pour strip | Removing Form Work | Slab | 5.40 | Second Floor | 42189 | 42189 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3079 | steel reinforcement for stair 3 axis B6 to B7/A8 | Steel Reinforcement | Stair | -0.45 to 1.10 | BOH | 42189 | 42192 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3080 | steel reinforcement for walls at core 3 axis A10 to A9/B7 to B8 | Steel Reinforcement | Core | 2.90 to 5.40 | Ground Floor | 42189 | 42191 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3081 | holes and dowels fixation for wall at core 3 due to modification axis A10 to A9/B7 to B8 | Dowels | Core | -3.80 to -0.45 | BOH | 42189 | 42189 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3082 | instalation of 3 composite columns (Torque) axis B4/A9-A10-A11 | Composite Columns | Column | 5.40 to 10.30 | First Floor | 42190 | 42191 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3083 | top steel reinforcement for panoramic elevator slab A5 to A6/B9 to B10 | Steel Reinforcement | Slab | -3.80 | B2 | 42189 | 42190 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3084 | form work fir column CC1 axis A11/B13 west side | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42189 | 42190 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3085 | steel reinforcement for column CC1 axis A11/B13 west | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42189 | 42189 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3086 | surface preparation for slab construction joints 3A, 5A-3 and 5B-2 | Repair | Slab | 1.10 | BOH | 42190 | 42196 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3087 | form work for slab axis B14 to B21/A4 to A11 | Form Work | Slab | 1.10 | BOH | 42190 | 42191 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3088 | repair of slab and slab construction joints 5B-2& 1B to close NCR No. 80 | Repair | Slab | 1.10 | BOH | 42190 | 42196 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3089 | form work for first pour strip axis B4 to B9/A6 to A11 | Form Work | Slab | 5.40 | Ground Floor | 42194 | 42199 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3090 | steel reinforcement for column CC1* axis B13/A8 west side | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42191 | 42191 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3091 | form work for column CC1* axis B13/A8 west side | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42191 | 42192 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3092 | steel reinforcement for new wall at core 5 due to modification axis A8 to A9/B7 to B8 | Steel Reinforcement | Core | 1.10 to 5.40 | Ground Floor | 42191 | 42192 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3093 | form work for new wall at core 5 due to modification axis A8 to A9/B7 to B8 | Form Work | Core | 1.10 to 5.40 | Ground Floor | 42191 | 42196 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3094 | steel reinforcement for shear wall 1 axis B1 to C8/A1 | Steel Reinforcement | SHW | 21.50 to 24.80 | Typical Floor | 42191 | 42193 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3095 | form work for shear wall 1 axis B1 to C8/A1 | Form Work | SHW | 21.50 to 24.80 | Typical Floor | 42191 | 42205 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3096 | steel reinforcement for column C5 axis A2/B18 | Steel Reinforcement | Column | 10.30 to 14.50 | Second Floor | 42192 | 42193 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3097 | form work for column C5 axis A2/B18 | Form Work | Column | 10.30 to 14.50 | Second Floor | 42192 | 42196 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3098 | surface preparation of slab construction joints 5A-4& 1A | Repair | Slab | 1.10 | BOH | 42192 | 42193 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3099 | steel reinforcement work for new wall and beam at core 5 due to modification axis A8 to A10/B6 to B7 | Steel Reinforcement | Core | 1.10 to 5.40 | Ground Floor | 42192 | 42196 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3100 | form work for new wall and beam at core 5 due to modification axis A89 to A10/B6 to B7 | Form Work | Core | 1.10 to 5.40 | Ground Floor | 42192 | 42198 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3101 | form work for slab at core 3 axis A8 to A10/B10 to B12 | Form Work | Slab | 1.10 | BOH | 42192 | 42197 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3102 | form work for core 3 (stair 8 walls) axis A10 to A9/B12 to B13 | Form Work | Core | 2.90 to 5.40 | Ground Floor | 42193 | 42196 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3103 | holes and dowels fixation for beam at core 3 due to modification axis A10 to A9/B10 to B11 | Dowels | Core | 1.10 | BOH | 42193 | 42196 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3104 | form work for slab 5D-5 axis A3 to A4/B8 to B13 | Form Work | Slab | 1.10 | BOH | 42193 | 42196 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3105 | bottom layer steel reinforcement work for slab 5D-5 axis A3 to A4/B8 to B13 | Steel Reinforcement | Slab | 1.10 | BOH | 42193 | 42196 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3106 | top layer steel reinforcement work, dowels and final inspection for slab 5D-5 axis A3 to A4/B8 to B13 | Steel Reinforcement | Slab | 1.10 | BOH | 42193 | 42196 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3107 | steel reinforcement for core 3 slab axis A10 to A8/B10 to B12 | Steel Reinforcement | Slab | 1.10 | BOH | 42194 | 42197 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3108 | steel reinforcement for shear wall 1 axis B15 to C8/A1 | Steel Reinforcement | SHW | 17.90 to 21.20 | Typical Floor | 42194 | 42201 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3109 | form work for shear wall 1 axis B15 to C8/A1 | Form Work | SHW | 17.90 to 21.20 | Typical Floor | 42194 | 42211 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3110 | repair of slabs construction joints 5B-2, 5B-3, 1C, and 1B | Repair | Slab | -3.80 | B1 | 42194 | 42196 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3111 | repair of slab construction joints 5B-2, 1B, and 3A | Repair | Slab | 1.10 | BOH | 42194 | 42196 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3112 | steel reinforcement for walls at core 5 due to modification axis A10 to A9/B7 to B6 | Steel Reinforcement | Core | 4.70 to 8.00 | First Floor | 42196 | 42198 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3113 | form work for walls at core 5 due to modification axis A10 to A9/B7 to B6 | Form Work | Core | 4.70 to 8.00 | First Floor | 42196 | 42198 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3114 | top and bottom layers of steel reinforcement work, dowels and final inspection for post tension slab axis C4 to C5/A1 to A3 | Steel Reinforcement | Slab | 15.20 | 3rd | 42196 | 42199 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3115 | post tension works for slab (Tendons-strands-anchors and profiles) for first pour strip axis C4 to C5/A1 to A3 | Cables | Slab | 15.20 | 3rd | 42196 | 42199 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3116 | form work for panoramic elevator slab axis A5 to A6/B9 to B10 | Form Work | Slab | 1.10 | BOH | 42196 | 42197 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3117 | holes and dowels fixation for panoramic elevator slab A5 to A6/B9 to B10 | Dowels | Slab | 1.10 | BOH | 42196 | 42197 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3118 | surface preparation of slab 5A-4 to 1A, 5A-2, 5B-2 | Repair | Slab | -3.80 | B1 | 42196 | 42197 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3119 | repair of slab construction joints 5A-1, 3B, and 3A | Repair | Slab | -3.80 | B1 | 42196 | 42226 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3120 | surface preparation for core 4, 5 outer walls | Repair | Core | -3.80 to 1.10 | BOH | 42196 | 42197 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3121 | steel reinforcement bottom layer for panoramic elevator slab axis A5 to A6/B9 to B10 | Steel Reinforcement | Slab | 1.10 | BOH | 42197 | 42198 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3122 | steel reinforcement top layer for panoramic elevator slab axis A5 to A6/B9 to B10 | Steel Reinforcement | Slab | 1.10 | BOH | 42197 | 42198 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3123 | steel reinforcement for new wall at core 3 due to modification axis A10 to A9/B11 to B12 | Steel Reinforcement | Core | 1.10 to 4.70 | Ground Floor | 42198 | 42201 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3124 | form work for new wall core 3 modification axis A9 to A11/B11 to B12 | Form Work | Core | 1.10 to 4.70 | Ground Floor | 42198 | 42201 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3125 | surface preparation and repair for construction joints of slab axis A9 to A11/B10 to B6 | Repair | Slab | 1.10 | BOH | 42198 | 42198 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3126 | repair work for external side of core 5 axis A8 to A11/B8 to B6 | Repair | Core | -3.80 to 1.10 | BOH | 42199 | 42201 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3127 | steel reinforcement for walls core 5 modification axis A9/B7 to B6 | Steel Reinforcement | Core | 4.70 to 8.10 | First Floor | 42200 | 42201 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3128 | form work for core 5 modification axis A9/B7 to B6 | Form Work | Core | 4.70 to 8.10 | First Floor | 42200 | 42201 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3129 | stressing of strands for first pour strip for post tension slab axis C4-C5/B1/A1-A3 | Stressing | Slab | 15.20 | 3rd | 42205 | 42207 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3130 | form work for stair case 5 axis B8 to B9/A7 to A9 | Form Work | Stair | 1.10 to 5.40 | Ground Floor | 42205 | 42207 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3131 | form work for stair case 9 axis B14 to B16/A7 to A9 | Form Work | Stair | -3.80 to -0.45 | Ground Floor | 42205 | 42207 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3132 | steel reinforcement for core 3 modification axis A9/B11 to B12 | Steel Reinforcement | Core | 4.70 to 6.20 | Ground Floor | 42207 | 42210 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3133 | form work for core 3 modification axis A9/B11 to B12 | Form Work | Core | 4.70 to 6.20 | Ground Floor | 42207 | 42210 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3134 | form work for core 2 slab axis A9/B15 to B16 | Form Work | Slab | 1.10 | BOH | 42206 | 42226 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3135 | steel reinforcement for shear wall 1 axis B15 to B19/A1 | Steel Reinforcement | SHW | 16.90 to 20.20 | 3rd | 42206 | 42207 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3136 | form work for shear wall 1 axis B15 to B19/A1 | Form Work | SHW | 16.90 to 20.20 | 3rd | 42206 | 42211 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3137 | steel reinforcement for shear wall 8 axis C2/A2 to A3 | Steel Reinforcement | SHW | 15.20 to 18.50 | 3rd | 42206 | 42210 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3138 | form work for shear wall 8 axis C2/A2 to A3 | Form Work | SHW | 15.20 to 18.50 | 3rd | 42207 | 42210 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3139 | form work removal for slab 5D-5 axis B8 to B13/A3 to A4 | Removing Form Work | Slab | 1.10 | BOH | 42207 | 42207 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3140 | form work removal for first stage axis B1 to B5/A1 to A3 | Removing Form Work | Slab | 15.20 | 3rd | 42207 | 42218 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3141 | bottom steel reinforcement for first pour strip of RD tower axis A8 to A11/B4 to B9 | Steel Reinforcement | Slab | 5.40 | First Floor | 42207 | 42207 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3142 | dowels drilling and fixation for beam at stair 12 axis A2/B1 | Dowels | Beam | 5.40 | First Floor | 42210 | 42215 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3143 | form work for shear wall 7 axis C3/A2 to A3 | Form Work | SHW | 21.20 to 24.50 | Typical Floor | 42210 | 42220 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3144 | steel reinforcement for shear wall 7 axis C3/A2 to A3 | Steel Reinforcement | SHW | 21.20 to 24.50 | Typical Floor | 42210 | 42220 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3145 | surface preparation of slab's construction joints for slabs 2-1B, 1C, 5A-1 | Repair | Slab | 1.10 | BOH | 42210 | 42211 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3146 | holes and dowels fixation for stair 5 axis A8 to A9/B8 | Dowels | Stair | 1.10 to 5.40 | Ground Floor | 42211 | 42215 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3147 | holes and dowels fixation for stair 9 axis A7 to A8/B15 | Dowels | Stair | -3.80 to 0.45 | Ground Floor | 42211 | 42215 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3148 | bottom steel reinforcement for slab 2-1B& 5C-1 axis A6 to A8/B11 to B13 | Steel Reinforcement | Slab | 1.10 | BOH | 42211 | 42212 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3149 | top steel reinforcement for slab 2-1B& 5C-1 axis A6 to A8/B11 to B13 | Steel Reinforcement | Slab | 1.10 | BOH | 42211 | 42218 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3150 | steel reinforcement for new wall of core 5 due to modification axis A9/B6-B7 | Steel Reinforcement | Core | 8.00 to 12.70 | First Floor | 42212 | 42212 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3151 | form work for new wall of core 5 due to modification axis A9/B6 to B7 | Form Work | Core | 8.00 to 12.70 | First Floor | 42212 | 42214 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3152 | steel reinforcement for new wall of core 5 due to modification axis A9/B6-B7 | Steel Reinforcement | Core | 8.00 to 12.70 | First Floor | 42212 | 42214 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3153 | form work for new wall of core 5 due to modification axis A9/B6 to B7 | Form Work | Core | 8.00 to 11.40 | First Floor | 42212 | 42214 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3154 | steel reinforcement work for core walls 7 axis C7/A2-A3 | Steel Reinforcement | Core | 21.00 to 24.30 | Typical Floor | 42212 | 42214 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3155 | form work for core 7 axis A2 to A3/C7 | Form Work | Core | 21.00 to 24.30 | Typical Floor | 42212 | 42215 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3156 | form work for stair 4 axis A10/B7 to B8 | Form Work | Stair | -11.00 to -7.20 | B2 | 42213 | 42214 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3157 | form work for new ramp 5 axis A13 to A12/B19 to B14 | Form Work | Ramp | -3.80 to 1.10 | BOH | 42213 | 42227 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3158 | steel reinforcement for stair 12 axis B1/A1 to A2 | Steel Reinforcement | Stair | 1.10 to 5.40 | Ground Floor | 42213 | 42214 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3159 | steel reinforcement for core 3 axis B10 to B12/A8 to A10 | Steel Reinforcement | Core | 6.20 to 9.50 | First Floor | 42213 | 42215 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3160 | steel reinforcement for core 8 axis B1/A2 to A3 | Steel Reinforcement | Core | 23.20 to 26.50 | Typical Floor | 42213 | 42215 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3161 | form work for core 8 axis B1/A2 to A3 | Form Work | Core | 23.20 to 26.50 | Typical Floor | 42213 | 42221 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3162 | inspection for holes and dowels fixation for stair 4 axis B6 to B7/A10 | Dowels | Stair | -11.00 to -7.20 | B2 | 42214 | 42221 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3163 | form work for stair case 11 axis B16 to B17/A9 | Form Work | Stair | -0.45 to 1.10 | BOH | 42215 | 42215 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3164 | surface preparation prior to repair for soffit panoramic elevator slab to close NCR #87 axis A5 to A6/B9 to B10 | Repair Elev | Slab | -3.80 | B1 | 42217 | 42218 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3165 | steel reinforcement for core 2 axis B14 to B15/A8 to A10 | Steel Reinforcement | Core | 9.50 to 12.80 | Second Floor | 42215 | 42220 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3166 | re-stressing for tension No. 1, 3, 4, 10, 13 for post tension stage 1 | Stressing | Slab | 15.20 | 3rd | 42215 | 42215 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3167 | form work for core 3 axis B10 to B12/A8 to A10 | Form Work | Core | 6.20 to 9.50 | First Floor | 42217 | 42220 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3168 | form work for new wall core 5 due to modification axis A9/B6-B7 | Form Work | Core | 11.40 to 12.70 | Typical Floor | 42217 | 42224 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3169 | steel reinforcement for stair 14 axis B15 to B16/A2 | Steel Reinforcement | Stair | -3.80 to -0.45 | BOH | 42218 | 42221 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3170 | ducts grouting for post tension slab at first pour strip axis C4 to C5/A1 to A3 | Grout | Slab | 15.20 | 3rd | 42218 | 42222 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3171 | form work for stair 12 axis B1/A2 to A3 | Form Work | Stair | 5.40 to 10.30 | First Floor | 42219 | 42222 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3172 | top layer steel reinforcement work, (tendons-strands-anchors and profiles) final inspection for post tension slab first pour strip at residential tower axis B4 to B9/A6 to A12 | Steel Reinforcement | Slab | 5.40 | Ground Floor | 42218 | 42224 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3173 | form work for walls core 5 (Crane Opening) axis A9/B6 to B7 | Form Work | Core | 10.30 to 12.70 | Second Floor | 42221 | 42225 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3174 | steel reinforcement for stair 9 axis A7 to A8/B14 to B15 | Steel Reinforcement | Stair | -3.80 to -0.45 | BOH | 42219 | 42221 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3175 | steel reinforcement for shear wall 6 axis C4/A2 to A3 | Steel Reinforcement | SHW | 20.40 to 23.70 | Typical Floor | 42219 | 42222 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3176 | form work for part of slab 2-2C and 5D-2 axis A5 to A7/B14 to B17 | Form Work | Slab | 1.10 | BOH | 42220 | 42222 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3177 | form work for first pour strip for post tension at axis C4 to C5/A1 to A3 | Form Work | Slab | 18.50 | Typical Floor | 42220 | 42221 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3178 | surface preparation of slab's construction joints for slabs 2-1B, 1C, 5D-1 | Repair | Slab | 1.10 | BOH | 42220 | 42221 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3179 | form work for part of slab 5C-3 and 2-2B axis B17 to B19/A11 to A14 | Form Work | Slab | 1.10 | BOH | 42220 | 42222 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3180 | steel reinforcement for core 5 new wall (Crane Opening) axis A9/B6 to B7 | Steel Reinforcement | Core | 10.30 to 12.70 | Typical Floor | 42220 | 42221 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3181 | top steel reinforcement for ramp 5 axis B14 to B19/A12 to A13 | Steel Reinforcement | Ramp | -3.80 to 1.10 | BOH | 42221 | 42227 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3182 | bottom steel reinforcement for ramp 5 and inverted beams axis A12 to A13/B14 to B19 | Steel Reinforcement | Beam | -3.80 to 1.10 | BOH | 42221 | 42227 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3183 | form work for core 2 axis B14 to B15/A8 to A10 | Form Work | Core | 9.50 to 12.80 | Second Floor | 42221 | 42222 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3184 | surface preparation and repair for beam of panoramic elevator slab axis B9 to B10/A5 to A6 | Repair Elev | Beam | -3.80 | B1 | 42222 | 42226 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3185 | dowels drilling and fixation inspection for new design change at C5 axis A1/B18 | Dowels | Column | 15.20 to 18.50 | 3rd | 42227 | 42231 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3186 | dowels drilling and fixation inspection for staircase 14 axis A1/B15 to B17 | Dowels | Stair | 1.10 | BOH | 42227 | 42231 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3187 | dowels driling and fixation inspection for stair case 12 axis A2 to A3/B1 | Dowels | Stair | 7.77, 8.125& 10.30 | First Floor | 42227 | 42231 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3188 | steel reinforcement for 2 columns CC7 axis A10-A11/B4 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42227 | 42228 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3189 | steel reinforcement for shear wall 1 axis C8 to B17/A1 | Steel Reinforcement | SHW | 21.10 to24.50 | Typical Floor | 42222 | 42222 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3190 | form work for slab of second pour strip axis B8 to B13/A6 to A12 | Form Work | Slab | 5.40 | First Floor | 42225 | 42226 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3191 | steel reinforcement for beams of post tension slab axis B1 to C5/A1 to A3 | Steel Reinforcement | Beam | 18.50 | Typical Floor | 42225 | 42228 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3192 | surface preparation for internal sides of core 5 | Repair | Core | -11.00 to -7.20 | B2 | 42225 | 42226 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3193 | bottom layer steel reinforcement work, dowels for slab of first pour strip axis A1 to A3/B1 to C5 | Steel Reinforcement | Slab | 18.50 | First Floor | 42225 | 42232 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3194 | form work for stair 6 axis A8 to A9/B10 to B11 | Form Work | Stair | 1.10 to 5.40 | Ground Floor | 42225 | 42232 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3195 | drilling and fixation for panoramic elevator beams axis A5 to A6/B9 to B10 | Dowels | Beam | 5.40 | First Floor | 42225 | 42226 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3196 | form work for shear wall 6 axis C4/A2 to A3 | Form Work | SHW | 20.40 to 23.70 | Typical Floor | 42225 | 42226 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3197 | fixation of shear connector for 3 composite columns CC7 axis B8-B6-B5/A6 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42226 | 42229 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3198 | fixation of shear connector for 4 columns CC7 axis A8-A9-A10/B4 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42226 | 42229 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3199 | form work for stair 14 axis A2 to A3/B16 to B17 | Form Work | Stair | -0.45 to 3.35 | BOH | 42226 | 42226 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3200 | fixation of shear connectors for 2 columns CC9 axis A11/B6-B8 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42227 | 42229 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3201 | installation for 2 columns CC9 (Torque) axis A11/B6-B8 | Composite Columns | Column | 5.40 to 10.30 | First Floor | 42227 | 42228 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3202 | bottom layer steel reinforcement work for part of slab 5C-8 axis B19 to B21/A13 to A6 | Steel Reinforcement | Slab | 1.10 | BOH | 42227 | 42231 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3203 | steel reinforcement work for core 5 axis B6 to B8/A8 to A10 | Steel Reinforcement | Core | 12.80 to 16.10 | Second Floor | 42228 | 42234 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3204 | form work for beams of ramp 5 axis A12 to A13/B14 to B19 | Form Work | Beam | -3.80 to 1.10 | BOH | 42228 | 42229 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3205 | steel reinforcement for 2 columns CC7 axis B4/A8-A9 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42228 | 42229 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3206 | form work for 2 columns CC7 axis B4/A10-A11 | Form Work | Column | 5.40 to 10.30 | First Floor | 42228 | 42229 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3207 | stressing of strands for first pour strip axis B4 to B9/A6 to A12 | Stressing | Slab | 5.40 | First Floor | 42228 | 42232 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3208 | installation for composite column CC7 (Torque) axis B13/A6 east side | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42228 | 42229 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3209 | post tension works for slab (Tendons-Strands-Anchors and profiles) at first pour strip axis A1 to A3/B1 to C5 | Cables | Slab | 18.50 | First Floor | 42229 | 42232 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3210 | top layer steel reinforcement work, dowels for slab and final inspection for post tension slab at first pour strip axis A1 to A3/B1 to C5 | Steel Reinforcement | Slab | 18.50 | First Floor | 42229 | 42232 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3211 | fixation of shear connector for 1 column CC7 axis A6/B13 west side | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42229 | 42231 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3212 | steel reinforcement for 2 columns CC7 axis A6/B5-B6 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42229 | 42231 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3213 | form work for 2 columns CC7 axis A6/B5-B6 | Form Work | Column | 5.40 to 10.30 | First Floor | 42229 | 42232 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3214 | form work for 2 columns CC7 axis B4/A8-A9 | Form Work | Column | 5.40 to 10.30 | First Floor | 42229 | 42229 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3215 | steel reinforcement work for core 7 axis C7/A2 to A3 | Steel Reinforcement | Core | 24.30 to 27.60 | Typical Floor | 42229 | 42232 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3216 | installation of composite column (Torque) for 1 column CC7 axis A6/B13 west | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42229 | 42231 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3217 | steel reinforcement for beam at slab section 5C-8 axis B19/A10 to A6 | Steel Reinforcement | Beam | 1.10 | BOH | 42229 | 42234 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3218 | surface preparation and repair for retaining wall axis A5 to A6/B21 | Repair | Retaining Wall | -7.20 | B2 | 42231 | 42239 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3219 | form work for 1 column CC7 axis A6/B8 | Form Work | Column | 5.40 to 10.30 | First Floor | 42231 | 42234 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3220 | steel reinforcment for column CC7 axis A6/B8 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42231 | 42232 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3221 | steel reinforcement for 2 columns CC9 axis A11/B6-B8 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42231 | 42234 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3222 | form work for columns CC9 axis A11/B6-B8 | Form Work | Column | 5.40 to 10.30 | First Floor | 42231 | 42234 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3223 | restressing of strands for 7 post tension strands by increasing force 5% for cables (95-94-93-78-71-70-96) in Y direction axis A6 to A12/B4 to B9 | Stressing | Slab | 5.40 | Second Floor | 42231 | 42234 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3224 | form work for ramp 6 axis B10 to B13/A14 to A15 | Form Work | Ramp | -3.80 to 1.10 | BOH | 42232 | 42235 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3225 | repair work for internal side of core 5 | Repair | Core | -3.80 to 1.10 | BOH | 42232 | 42234 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3226 | surface preparation for internal sides of core 5 | Repair | Core | -7.20 to -3.80 | B2 | 42232 | 42239 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3227 | form work for core 7 axis A2 to A3/C7 | Form Work | Core | 24.20 to 27.50 | Typical Floor | 42233 | 42234 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3228 | steel reinforcement for stair case 14 axis A2/B16 | Steel Reinforcement | Stair | 0.45 to 3.35 | BOH | 42234 | 42235 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3229 | steel reinforcement for shear wall 7 axis C3/A2 to A3 | Steel Reinforcement | SHW | 24.80 to 28.10 | Typical Floor | 42233 | 42239 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3230 | surface preparation and repair for ramp 6 beams to close NCR # 88 | Repair | Beam | 1.10 to -3.80 | BOH | 42233 | 42243 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3231 | surface preparation for core 2 internal walls | Repair | Core | -7.20 to -3.80 | B2 to B1 | 42233 | 42239 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3232 | repair for core 5 internal walls | Repair | Core | -11.00 to -7.20 | B2 | 42233 | 42234 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3233 | bottom layer steel reinforcement work for second pour strip axis B9 to B12/A6 to A12 | Steel Reinforcement | Slab | 5.40 | Ground Floor | 42234 | 42236 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3234 | top layer steel reinforcement work for part of slab 5C-8 axis B19 to B21/A13 to A6 | Steel Reinforcement | Slab | 1.10 | BOH | 42233 | 42236 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3235 | top layer steel reinforcement work, (tendons-strands-anchors and profiles) final inspection for post tension slab axis B9 to B12/A6 to A12 | Steel Reinforcement | Slab | 5.40 | Ground Floor | 42234 | 42236 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3236 | steel reinforcement for shear wall 6 axis C4/A1 to A3 | Steel Reinforcement | SHW | 24.40 to 27.70 | Typical Floor | 42234 | 42241 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3237 | steel reinforcement work for stair case 12 axis C1 to C2/A1 to A3 | Steel Reinforcement | Stair | 5.40 to 10.30 | First Floor | 42234 | 42239 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3238 | steel reinforcement for shear wall 8 axis C2/A1 to A3 | Steel Reinforcement | SHW | 18.50 to 20.60 | Typical Floor | 42234 | 42236 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3239 | form work for core 5 axis B6 to B8/A8 to A10 | Form Work | Core | 12.80 to 16.10 | Second Floor | 42235 | 42236 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3240 | steel reinforcement for core 3 axis B10 to B12/A8 to A10 | Steel Reinforcement | Core | 9.50 to 12.80 | Second Floor | 42235 | 42239 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3241 | stressing for strands in transveral& longitudinal direction at first pour strip | Stressing | Slab | 18.50 | Typical Floor | 42235 | 42239 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3242 | ducts grouting for post tension slab axis A6 to A12/B4 to B9 | Grout | Slab | 5.40 | First Floor | 42235 | 42236 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3243 | steel reinforcement for shear wall 1 axis C1 to C4/A1 | Steel Reinforcement | SHW | 24.80 to 28.10 | Typical Floor | 42236 | 42240 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3244 | steel reinforcement work for stair case 5 axis A8 to A9/B8 to B9 | Steel Reinforcement | Stair | 1.10 to 5.40 | Ground Floor | 42238 | 42241 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3245 | repair for core 2 internal walls | Repair | Core | -7.20 to -3.80 | B2-B1 | 42238 | 42248 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3246 | fixation of shear connector for 2 composite columns CC3 axis A11/B9 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42238 | 42239 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3247 | fixation of shear connector for 3 composite columns CC1 axis A8-A10/B9 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42238 | 42239 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3248 | fixation of shear connector for 4 composite columns CC7 axis A6/B9-B10-B12 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42238 | 42241 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3249 | fixation of shear connector for 2 composite columns CC1 and CC9 axis A11/B10-B11 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42238 | 42241 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3250 | installation of 2 composite columns (Torque) CC1 and CC9 axis A11/B10-B11 | Composite Columns | Column | 5.40 to 10.30 | First Floor | 42238 | 42241 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3251 | form work for shear wall 8 axis C2/A2 to A3 | Form Work | SHW | 18.50 to 20.60 | Typical Floor | 42238 | 42239 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3252 | bottom layer steel reinforcement work for ramp 6 axis B10 to B13/A14 to A15 | Form Work | Ramp | -3.80 to 1.10 | BOH | 42238 | 42240 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3253 | stressing for strands in transversal and longitudinal directions for reidential tower at second pour strip | Stressing | Slab | 5.40 | First Floor | 42239 | 42245 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3254 | form work for shear wall 1 axis A1/C4 to C1 | Form Work | SHW | 24.50 to 27.80 | Typical Floor | 42239 | 42241 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3255 | form work for shear wall 7 axis A2 to A3/C3 | Form Work | SHW | 24.80 to 28.10 | Typical Floor | 42239 | 42243 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3256 | steel reinforcement for core 4 axis A8/B9 | Steel Reinforcement | Core | 5.40 to 10.30 | First Floor | 42239 | 42239 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3257 | steel reinforcement for column CC1 and CC3 axis B9/A10-A11 west side | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42239 | 42241 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3258 | top layer steel reinforcement for ramp 6 axis B10 to B13/A14 to A15 | Steel Reinforcement | Ramp | -3.80 to 1.10 | BOH | 42239 | 42240 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3259 | steel reinforcement for slab section 2-2A axis B13 to B14/A7 to A12 | Steel Reinforcement | Slab | 1.10 | BOH | 42240 | 42244 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3260 | form work for column CC1 and CC3 axis B9/A10-A11 west side | Form Work | Column | 5.40 to 10.30 | First Floor | 42240 | 42241 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3261 | restressing of strands for 6 post tension strands by increasing force 5% for cables (7-9-10-11-12-13) | Stressing | Slab | 18.50 | Typical Floor | 42242 | 42243 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3262 | dowels drilling and fixation for stair 14 axis A2 to A3/B16 to B17 | Dowels | Stair | 3.35 to 8.125 | Ground Floor | 42242 | 42247 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3263 | form work removal for first pour strip axis C4 TO C5/A1 TO A3 | Removing Form Work | Slab | 18.50 | Typical Floor | 42242 | 42243 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3264 | installation of 2 columns CC7 (torque) axis A6/B5-B6 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42242 | 42246 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3265 | steel reinforcement for column CC1 axis A10/B9 east side | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42242 | 42243 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3266 | form work for column CC1 axis A10/B9 east side | Form Work | Column | 5.40 to 10.30 | First Floor | 42242 | 42247 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3267 | form work for column CC7 axis A6/B9 east side | Form Work | Column | 5.40 to 10.30 | First Floor | 42242 | 42243 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3268 | steel reinforcement for column CC7 axis A6/B9 east side | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42242 | 42243 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3269 | form work for column CC3 axis A11/B9 east side | Form Work | Column | 5.40 to 10.30 | First Floor | 42242 | 42247 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3270 | steel reinforcement for column CC3 axis A11/B9 east side | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42242 | 42243 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3271 | form work for core 3 axis A7 to A11/B10 to B12 | Form Work | Core | 9.50 to 12.80 | Second Floor | 42242 | 42243 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3272 | form work for slab of core 2 axis B14 to B16/A8 to A14 | Form Work | Slab | 1.10 | BOH | 42242 | 42247 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3273 | form work of slab at levels -0.30, 0.60 and 0.45 at axis A6 to A4/B16 to B20 | Form Work | Slab | -0.30, 0.60, 0.45 | Lower Ground Floor | 42243 | 42245 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3274 | steel reinforcement for column CC7 axis A6/B9 west side | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42240 | 42241 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3275 | steel reinforcement for column CC7 axis A6/B13 west side | Steel Reinforcement | Column | 1.10 to 5.40 | First Floor | 42240 | 42242 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3276 | steel reinforcement work, dowels and final inspection for cantilever slab axis A15/B2 to B6 | Steel Reinforcement | Slab | 1.10 | BOH | 42240 | 42242 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3277 | form work for column CC7 axis A6/B9 west side | Form Work | Column | 5.40 to 10.30 | First Floor | 42240 | 42241 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3278 | top layer steel reinforcement work for slab 5C-5 axis B16 to B19/A12 to A10 | Steel Reinforcement | Slab | 1.10 | BOH | 42242 | 42245 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3279 | steel reinforcement work for stair wall 9 axis A7 to A8/B14 to B16 | Steel Reinforcement | SHW | 2.90 to 5.40 | Ground Floor | 42241 | 42243 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3280 | installation of column CC7 (torque) axis B8/A6 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42241 | 42243 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3281 | form work for 2 columns CC9 axis A6/B10-B12 | Form Work | Column | 5.40 to 10.30 | First Floor | 42241 | 42247 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3282 | steel reinforcement for 2 columns CC9 axis A6/B10-B12 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42241 | 42245 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3283 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3284 | steel reinforcement for column CC7 axis A6/B12 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42241 | 42243 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3285 | form work for column CC7 axis A6/B13 west | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42241 | 42243 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3286 | dowels drilling and fixation inspection for stair case 6 axis A8/B10 to B11 | Dowels | Stair | 1.10 to 5.40 | Ground Floor | 42241 | 42242 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3287 | form work for core 4 axis A8/B9 | Form Work | Core | 5.40 to 10.30 | First Floor | 42241 | 42243 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3288 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3289 | bottom layer steel reinforcement work for slab 5C-5 B16 to B19/A12 to A10 | Steel Reinforcement | Slab | 1.10 | BOH | 42241 | 42245 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3290 | steel reinforcement for cantilever at column CC4 axis D4 | Steel Reinforcement | Column | 1.10 | BOH | 42241 | 42245 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3291 | steel reinforcement for cantilever at column CC7 axis B16/A12 | Steel Reinforcement | Column | 1.10 | BOH | 42241 | 42245 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3292 | form work for shear wall 6 axis C4/A2 to A3 | Form Work | SHW | 24.60 to 27.90 | Typical Floor | 42241 | 42243 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3293 | form work for stair case 14 axis A2/B15 to B17 | Form Work | Stair | 3.35 to 8.125 | Ground Floor | 42241 | 42243 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3294 | bottom layer steel reinforcement work for slab 2-2B axis A8 to A12/B15 to B18 | Steel Reinforcement | Slab | 1.10 | BOH | 42242 | 42247 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3295 | plugging of dewatering wells No. 9- 12- 13 | Dewatering | Dewatering | -11.00 | B1 | 42242 | 42242 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3296 | form work for column CC7 axis A6/B13 east side | Form Work | Column | 1.10 to 5.40 | BOH | 42243 | 42250 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3297 | steel reinforcement for column CC7 axis A6/B13 east side | Steel Reinforcement | Column | 1.10 to 5.40 | BOH | 42243 | 42248 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3298 | ducts grouting for post tension slab at first pour strip | Grout | Slab | 18.50 | Typical Floor | 42243 | 42247 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3299 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3300 | installation of horizontal geotextile 1st layer under raft to proceed with PVC membrane installation between axis A3-A4 to between axis A7-A8/B21 | Insulation | Raft | -1.0 to 1.5 | Ground Floor | 42245 | 42246 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3301 | installation and test ovc membrane and water bars to proceed wite geotextile 2nd layer (retaining wall) axis between A3-A4 to between A7-A8/B21 | Insulation | Retaining Wall | -1.0 to 1.5 | Ground Floor | 42245 | 42246 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3302 | installation of horizontal geotextile 2nd layer between axis A3-A4 to between axis A7-A8/B21 | Insulation | Slab | -1.0 to 1.5 | Ground Floor | 42245 | 42246 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3303 | surface preparation and repair for slab cracked concrete axis B12-B13/A11-A12 | Repair | Slab | 5.40 | First Floor | 42245 | 42246 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3304 | steel reinforcement for stair case 11 axis A8 to A10/B16 to B18 | Steel Reinforcement | Stair | -0.45 to 1.10 | Ground Floor | 42245 | 42246 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3305 | form work for stair case 7 axis A10/B10-B11 | Form Work | Stair | 1.10 to 5.40 | Ground Floor | 42245 | 42247 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3306 | fixation of 4 columns CC7 (Torque) axis A8-A9-A10-A11/B4 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42245 | 42247 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3307 | steel reinforcement for column CC1 axis A8/B9 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42245 | 42244 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3308 | form work for column CC1 axis A8/B9 | Form Work | Column | 5.40 to 10.30 | First Floor | 42245 | 42247 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3309 | dowels drilling and fixation inspection inside core 2 sxis A7 to A10/B14 to B16 | Dowels | Core | 1.10 | BOH | 42245 | 42248 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3310 | form work for stair case 9 axis A7 to A8/B14 to B16 | Form Work | Stair | -0.45 to 1.10 | Ground Floor | 42247 | 42248 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3311 | installation of composite column (Torque) CC4 axis B16/A10-A11 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42250 | 42250 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3312 | form work for post tension slab at first pour strip axis A6 to A12/B4 to B8 | Form Work | Slab | 10.30 | Second Floor | 42246 | 42248 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3313 | installation for 2 composite columns (Torque) axis A11/B6-B8 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42246 | 42248 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3314 | steel reinforcement for stair case 14 axis A2/B16 | Steel Reinforcement | Stair | 3.35 to 5.125 | Ground Floor | 42246 | 42254 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3315 | form work for stair case 12 axis B1/A2 | Form Work | Stair | 10.30 to 15.20 | Second Floor | 42246 | 42250 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3316 | surface preparation and repair for core 3 internal and external | Repair | Core | -3.8 to 1.10 | BOH | 42246 | 42256 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3317 | top layer steel reinforcement work, dowels and final inspection for slab (2-2B) axis B15 to B18/A7 to A11 | Steel Reinforcement | Slab | 1.10 | BOH | 42247 | 42250 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3318 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3319 | form work for ramp beam at ramp 6 axis B10 to B13/A13 | Form Work | Beam | -3.8 to 1.10 | BOH | 42247 | 42248 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3320 | stressing of strands for 6 post tension strands for cables 40, 41, 43& 44 in Y direction and cable 28 in X direction | Stressing | Slab | 5.40 | First Floor | 42248 | 42248 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3321 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3322 | installation of 2 cdolumns CC9 axis A11/B6-B8 (Torque) | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42248 | 42255 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3323 | steel reinforcement for core 2 slab axis A8 to A10/B14 to B16 | Steel Reinforcement | Slab | 1.10 | BOH | 42248 | 42250 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3324 | inspection for holes and dowels fixation for core 5 beams due to design change axis A8 to A10/B6 to B8 | Dowels | Core | 5.40 | First Floor | 42248 | 42250 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3325 | form work for core 5 slab axis A8 to A10/B6 to B8 | Form Work | Slab | 5.40 | First Floor | 42248 | 42250 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3326 | inspection for holes and dowels fixation axis B15 to B16/A7 to A8 | Dowels | Stair | 1.10 | BOH | 42249 | 42250 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3327 | steel reinforcement work for core 5 wall axis B6 to B8/A8 to A10 | Steel Reinforcement | Core | 16.10 to 19.40 | 3rd | 42249 | 42256 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3328 | stressing of strands for 2 post tension strands by increasing force 5% for cables 96/95 in X direction for second pour strip | Stressing | Slab | 5.40 | First Floor | 42249 | 42250 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3329 | steel reinforcement ad final inspection for pour strip between 1st and second strip axis A6 to A12/B8 to B9 | Steel Reinforcement | Slab | 5.40 | First Floor | 42249 | 42250 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3330 | fixation of shear connector for columns CC9, CC7, CC4 axis A11-A12/B14-B16-B18 | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42249 | 42250 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3331 | fixation of 3 columns CC9, CC7, CC4 (Torque) axis A11-A12/B14-B16-B18 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42249 | 42250 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3332 | form work removal for slab section 2-2A axis B13 to B14/A8 to A11 | Removing Form Work | Slab | 1.10 | BOH | 42249 | 42250 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3333 | top layer steel reinforcement work, dowels and final inspection for slab 5D-5 axis A3 to A4/B8 to B13 | Steel Reinforcement | Slab | 1.10 | BOH | 42250 | 42252 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3334 | bottom steel reinforcement for slab 5D-5 axis B18 to B19/A6 to A10 | Steel Reinforcement | Slab | 1.10 | BOH | 42250 | 42252 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3335 | steel reinfrocement for column CC7 axis B16/A12 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42252 | 42253 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3336 | steel reinforcement for column CC4 axis D4 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42252 | 42253 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3337 | form work for column CC7 axis B16/A12 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42252 | 42256 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3338 | form work for 1 column CC4 axis B16/A10-A11 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42252 | 42256 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3339 | form work for column CC4 axis D4 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42252 | 42256 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3340 | steel reinforcement for 1 column CC4 axis B16/A10-A11 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42252 | 42254 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3341 | steel reinforcement for stair case 9 axis 7-A8/ B15-B16 | Steel Reinforcement | Stair | -0.45 to 1.10 | BOH | 42252 | 42256 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3342 | steel reinforcement for core 1 axis B16 to B17/A9 | Steel Reinforcement | Core | 1.10 to 5.40 | Ground Floor | 42252 | 42256 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3343 | form work for ramp beam axis A12/B14 to B19 | Form Work | Beam | 1.10 | BOH | 42252 | 42254 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3344 | fixation of shear connectors for column CC4 axis B16/A10-A11 | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42250 | 42250 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3345 | surface preparation and repair for core 3 internal walls | Repair | Core | -7.20 to -3.80 | B1 | 42253 | 42256 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3346 | dowels drilling and fixation for stair case 12 axis A2/B1 | Dowels | Stair | 12.76 to 13.10 | Second Floor | 42253 | 42254 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3347 | steel reinforcement for panoramic beams axis A5 to A6/B10 to B9 | Steel Reinforcement | Beam | 5.40 | First Floor | 42253 | 42256 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3348 | inspection for holes and dowels fixation for slab axis B5 to B8/A6 to A10 | Dowels | Slab | 10.30 | Second Floor | 42253 | 42255 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3349 | steel reinforcement for stair case 6 axis B10 to B11/A8 to A9 | Steel Reinforcement | Stair | 1.10 to 5.40 | Ground Floor | 42253 | 42254 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3350 | bottom steel reinforcement for part of slab 2-2D axis A6 to A7/B14 to B16 | Steel Reinforcement | Slab | 1.10 | BOH | 42253 | 42256 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3351 | steel reinforcement for column CC9 axis B14/A11 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42253 | 42254 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3352 | form work for column CC9 axis B14/A11 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42253 | 42254 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3353 | form work removal for ramp 6 axis B10 to B13/A13 | Removing Form Work | Ramp | -3.80 to 1.10 | BOH | 42253 | 42254 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3354 | installation of 4 columns (Torque) CC4 axis D1-D2-D3/A19 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42254 | 42255 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3355 | fixation of shear connectors for 4 columns CC4 axis D1-D2-D3/A19 | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42254 | 42255 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3356 | form work for core 1 axis A8/B16-B17 | Form Work | Core | 1.10 to 5.40 | Ground Floor | 42254 | 42256 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3357 | form work for stair case 3 axis B6 to B7/A8 to A9 | Form Work | Stair | 1.10 to 5.40 | Ground Floor | 42254 | 42259 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3358 | steel reinforcement for core 5 slab axis A8 to A10/B6 to B8 | Steel Reinforcement | Slab | 5.40 | Ground Floor | 42254 | 42261 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3359 | dowels drilling and fixation for stair case 12 beam and core 8 beam axis A2/B1 | Dowels | Core | 21.80 | Typical Floor | 42254 | 42259 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3360 | top layer steel reinforcement work, dowels and final inspection for slabs 2-2D& 2-2C axis B16 to B13/ A6 to A7 | Steel Reinforcement | Slab | 1.10 | BOH | 42255 | 42256 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3361 | form work for slab 5C-2 axis B13 to B14/A12 to A15 | Form Work | Slab | 1.10 | BOH | 42255 | 42259 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3362 | surface preparation and repair for columns C1& C5 | Repair | Column | 1.10 | BOH | 42255 | 42267 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3363 | surface preparation and repair of core 7& 8 internal walls | Repair | Core | 1.10 | BOH | 42255 | 42282 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3364 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3365 | surface preparation and repair of slab's construction joints | Repair | Slab | 1.10 | BOH | 42255 | 42267 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3366 | steel reinforcement for stair case 12 axis A2/B1 | Steel Reinforcement | Stair | 10.30 to 15.20 | Second Floor | 42255 | 42259 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3367 | grouting pouring for opening in slab | Grout | Slab | 1.10 10.30 | 1.10 10.30 | 42255 | 42256 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3368 | form work for core 5 axis A18 to A10/B6 to B8 | Form Work | Core | 16.10 to 19.40 | 3rd | 42256 | 42259 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3369 | form work for stair case 5 axis B6/A8 to A9 | Form Work | Stair | 5.40 to 10.30 | First Floor | 42256 | 42268 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3370 | steel reinforcement for cantilever axis A15/B11 to B13 | Steel Reinforcement | Cantilever | 1.10 | BOH | 42256 | 42260 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3371 | form work for cantilever axis A15/B11 to B13 | Form Work | Cantilever | 1.10 | BOH | 42256 | 42260 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3372 | surface preparation and repair for core wall 2 external axis A8 to A10/B14 to B16 | Repair | Core | 1.10 to 5.40 | Ground Floor | 42256 | 42256 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3373 | surface preparation and repair for core wall 2 internal axis A8 to A10/B14 to B16 | Repair | Core | -11.00 to -7.20 | B2 | 42256 | 42256 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3374 | steel reinforcement for panoramic slab axis A5 to A6/B9 to B10 | Steel Reinforcement | Slab | 5.40 | First Floor | 42256 | 42256 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3375 | surface preparation and repair for core 3 internal walls | Repair | Core | -11.00 to -7.20 | B2 | 42252 | 42254 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3376 | form work for ramp beam axis A12/B14 to B19 | Repair | Beam | 1.10 | BOH | 42252 | 42253 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3377 | dowels drilling and fixation for stair case 7 axis A10/B11 | Dowels | Stair | 1.10 to 5.40 | Ground Floor | 42248 | 42261 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3378 | surface preparation and repair of soffit slab axis A1 to A3/C6-C9-C11 | Repair | Slab | 1.10 | BOH | 42261 | 42267 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3379 | form work for 2 columns CC4 axis D3& A9/B19 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42256 | 42260 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3380 | steel reinforcement for 2 columns CC4 axis D3& A9/B19 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42256 | 42259 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3381 | steel reinforcement for 2 columns CC4 axis D2& D1 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42257 | 42259 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3382 | form work for 2 columns CC4 axis D2& D1 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42257 | 42261 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3383 | dowels drilling and fixation for stair case 5 axis A8/B8 to B9 | Dowels | Stair | 5.40 to 10.30 | First Floor | 42259 | 42261 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3384 | dowels drilling and fixation for stair case 3 axis A8/B6-B7 | Dowels | Stair | 1.10 to 5.40 | Ground Floor | 42259 | 42260 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3385 | form work removal for slabs 5D-5, 2-2B& 5C-8 axis A10 to A12/B16 to B19 | Removing Form Work | Slab | 1.10 | BOH | 42260 | 42260 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3386 | form work for wall of core 2 axis A7 to A8/B14 to B15 | Form Work | Core | 2.90 to 5.40 | Ground Floor | 42259 | 42261 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3387 | fixation of shear connectors for 2 columns CC7 axis B14-B16/A6 | Shear Connectors | Column | 1.10 to 5.40 | Ground Floor | 42259 | 42261 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3388 | installation of 2 columns CC7 (torque) axis A6/B14 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42259 | 42261 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3389 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3390 | bottom layer steel reinforcement for RD tower slab first stage | Steel Reinforcement | Slab | 10.30 | Second Floor | 42259 | 42262 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3391 | installation of composite column (Torque) for column CC1 axis A8/B9 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42260 | 42261 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3392 | steel reinforcement for column CC7 axis A6/B14 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42260 | 42262 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3393 | form work for column CC7 axis A6/B14 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42260 | 42262 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3394 | ducts grouting for post tension slab at second pour strip axis A6 to A12/B8 to B12 | Grout | Slab | 5.40 | First Floor | 42260 | 42261 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3395 | surface preparation for core 1 internal axis B17/A9 | Repair | Core | -7.20 to -3.80 | B1 | 42261 | 42267 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3396 | installation of composite column (Torque) CC7 axis A6/B16 | Composite Columns | Column | 1.10 to 5.40 | Ground Floor | 42261 | 42262 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3397 | steel reinforcement for column CC7 axis A6/B16 | Steel Reinforcement | Column | 1.10 to 5.40 | Ground Floor | 42261 | 42263 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3398 | form work for column CC7 axis A6/B16 | Form Work | Column | 1.10 to 5.40 | Ground Floor | 42261 | 42264 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3399 | steel reinforcement for 2 panoramic columns axis B9/A5-A6 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42261 | 42263 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3400 | steel reinforcement for core 3 axis A8 to A10/B10 to B12 | Steel Reinforcement | Core | 12.80 to 16.10 | Second Floor | 42261 | 42266 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3401 | demolition of the upper concrete of column CC9 and cleaning and re-adjustment the steel reinforcement for column's neck to close NCR 89 | Repair | Column | 5.40 to 10.30 | First Floor | 42261 | 42262 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3402 | form work for stair 14 axis A2 to A3/B16 to B17 | Form Work | Stair | 8.125 to 13.025 | Typical Floor | 42262 | 42264 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3403 | top layer steel reinforcement work, dowels and final inspection for slab 5C-2 axis A10 to A15/B13 to B16 | Steel Reinforcement | Slab | 1.10 | BOH | 42262 | 42267 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3404 | top layer steel reinforcement work, Tendons-strands-anchors and profiles) final inspection for post tension slab at first stage axis A6 to A12/B4 to B9 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42262 | 42263 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3405 | bottom layer steel reinforcement for slab 5C-2 axis B13 to B16/A11 to A15 | Steel Reinforcement | Slab | 1.10 | BOH | 42262 | 42267 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3406 | form work for 2 panormic columns axis A5-A6/B9-B10 | Form Work | Column | 5.40 to 10.30 | Second Floor | 42262 | 42264 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3407 | steel reinforcement for 2 panoramic columns and 1 column CC7 axis A5-A6/B10-B11 | Steel Reinforcement | Column | 5.40 to 10.30 | Second Floor | 42262 | 42264 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3408 | top layer steel reinforcement work, dowels and final inspection for slab of core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | Slab | 5.40 | Ground Floor | 42263 | 42267 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3409 | form work for stair case 6 axis B10 to B11/A8 to A9 | Form Work | Stair | 5.40 to 10.30 | First Floor | 42263 | 42267 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3410 | form work for slab 5C-3 axis B14 to B19/A13 to A15 | Form Work | Slab | 1.10 | BOH | 42263 | 42267 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3411 | steel reinfrocement fir column C* axis A13/B14 | Steel Reinforcement | Column | -3.80 to 1.10 | Second Floor | 42263 | 42266 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3412 | form work for slab 5C-4 axis B17 to B19/A12 to A14 | Form Work | Slab | 1.10 | BOH | 42263 | 42267 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3413 | dowels drilling and fixation for stair 14 axis A2 to A3/B16 to B17 | Dowels | Stair | 8.125 to 13.025 | First Floor | 42263 | 42264 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3414 | steel reinforcement for stair case 3 axis A8 to A9/B6 to B8 | Steel Reinforcement | Stair | 1.10 to 5.40 | Ground Floor | 42264 | 42266 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3415 | form work for 2 columns C* axis B14-B16/A13 | Form Work | Column | -3.80 to 1.10 | BOH | 42264 | 42266 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3416 | steel reinforcement for ramp beam B5 axis A12 to A13/B14 to B19 | Steel Reinforcement | Beam | 1.10 | BOH | 42266 | 42268 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3417 | form work for panoramic columns and column CC7 axis B10-B11/A5-A6 | Form Work | Column | 5.40 to 10.30 | First Floor | 42264 | 42267 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3418 | steel reinforcement for column C* axis A3/B16 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42266 | 42266 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3419 | surface preparation for interior and exterior walls of core 8 axis B1/A1 to A2 | Surface Preparation | Core | -3.80 to 1.10 | BOH | 42266 | 42267 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3420 | repair for interior and exterior walls of core 8 axis B1/A1 to A2 | Repair | Core | -3.80 to 1.10 | BOH | 42266 | 42269 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3421 | steel reinforcement for core 5 axis B6 to B8/A8 to A10 | Steel Reinforcement | Core | 19.40 to 20.10 | Typical Floor | 42266 | 42269 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3422 | form work for core 3 axis A8 to A10/B10 to B12 | Form Work | Core | 12.80 to 16.10 | Second Floor | 42267 | 42268 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3423 | steel reinforcement for stair case 14 axis A2/B16 | Steel Reinforcement | Stair | 8.125 to 13.025 | First Floor | 42267 | 42269 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3424 | form work for stair case 12 axis A2/B1 | Form Work | Stair | 15.80 to 18.50 | 3rd | 42267 | 42268 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3425 | form work for ramp beam B9 to B14/A14 to A13 | Form Work | Beam | -3.80 to 1.10 | BOH | 42268 | 42268 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3426 | form work for third pouring strip post tension | Form Work | Slab | 5.40 | First Floor | 42268 | 42268 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3427 | form work removal slab 5C-2 axis A12 to A15/B13 to B14 | Removing Form Work | Slab | 1.10 | BOH | 42275 | 42276 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3428 | steel reinforcement for third pour strip beam axis A6 to A12/B14 | Steel Reinforcement | Beam | 5.40 | 5.40 | 42278 | 42280 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3429 | inspection for holes and dowels fixation of core 7 axis C7/A2 to A3 | Dowels | Core | 15.20 | 3rd | 42276 | 42277 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3430 | steel reinforcement for core 2 axis A8 to A10/B14 to B16 | Steel Reinforcement | Core | 12.80 to 16.10 | Second Floor | 42276 | 42285 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3431 | bottom layer steel reinforcement for slab 5C-4 axis B17 to B19/A15 to A12 | Steel Reinforcement | Slab | 1.10 | BOH | 42276 | 42303 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3432 | steel reinforcement for tower crane 1 opening axis A2 to A3/B4 | Steel Reinforcement | Tower Crane | 1.10 | BOH | 42278 | 42280 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3433 | drilling and dowels fixation panoramic elevaor beams axis A5 to A6/B9 to B10 | Dowels | Beam | 10.30 | Second Floor | 42280 | 42281 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3434 | form work form core 5 slab axis A8 to A10/B6 to B8 | Form Work | Slab | 10.30 | Second Floor | 42280 | 42282 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3435 | drilling and dowels fixation for core 5 slab axis A8 to A10/B6 to B8 | Dowels | Slab | 10.30 | Second Floor | 42280 | 42290 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3436 | surface preparation and repair for core 6 | Repair | Core | -7.20 to -3.80 | B2 | 42280 | 42325 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3437 | surface preparation and repair for core 6 | Repair | Core | -3.80 to 1.10 | B2 | 42280 | 42325 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3438 | steel reinforcement for concrete beam axis A6/B13 to B14 | Steel Reinforcement | Beam | 5.40 | Ground Floor | 42280 | 42287 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3439 | steel reinforcement for 2 columns CC7 axis A6/B5-B8 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42280 | 42282 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3440 | fixation of shear connectors for 2 columns CC7 axis A6/B5-B8 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42280 | 42281 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3441 | bottom layer steel reinforcement for slab of RD tower thid stage axis A6 to A12/B13 to B19 | Steel Reinforcement | Slab | 5.40 | First Floor | 42281 | 42287 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3442 | form work for stair case 3 axis B6 to B7/A8 to A9 | Form Work | Stair | 5.40 to 10.30 | Second Floor | 42281 | 42282 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3443 | form work for stair case 11 axis B16 to B17/A9 | Form Work | Stair | 1.10 to 5.40 | Ground Floor | 42281 | 42282 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3444 | form work for core 5 axis B6 to B8/A8 to A10 | Form Work | Core | 19.40 to 20.10 | Typical Floor | 42281 | 42282 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3445 | form work for slab 5D-2& 5D-3 axis B13 to B17/A4 to A6 | Form Work | Slab | 1.10 | BOH | 42281 | 42284 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3446 | form work for stair case 14 axis A2/B15 to B17 | Form Work | Stair | 13.025 to 15.20 | Second Floor | 42281 | 42282 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3447 | steel reinforcement for post tenson slab beams and drops at hotel at second pour strip | Steel Reinforcement | Beam | 15.20 | 3rd | 42281 | 42291 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3448 | form work for post tension slab for second pour strip axis between C3-C4 to B21/A1 to A3 | Form Work | Slab | 15.20 | 3rd | 42281 | 42282 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3449 | stressing for strands in first stage axis A6 to A12/B4 to B9 | Stressing | Slab | 10.30 | Second Floor | 42281 | 42290 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3450 | steel reinforcement for stair case 5 axis B8 to B9/A8 to A9 | Steel Reinforcement | Stair | 5.40 to 10.30 | First Floor | 42282 | 42285 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3451 | steel reinforcement for stair case 11 axis A8 to A10/B16 to B18 | Steel Reinforcement | Stair | 1.10 to 5.40 | Ground Floor | 42282 | 42288 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3452 | form work for 2 columns CC7 axis A6/B5-B8 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42282 | 42282 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3453 | form work for 3 columns CC7 axis B4/A8-A9-A10 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42282 | 42287 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3454 | steel reinforcement work for 3 columns CC7 axis B4/A8-A9-A10 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42282 | 42285 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3455 | fixation of shear connectors for 3 columns CC7 axis B4/A8-A9-A10 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42282 | 42285 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3456 | installation of composite column (Torque) for 2 columns CC7 axis B6/A6& B4/A11 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42282 | 42285 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3457 | installation of composite column (Torque) for 2 columns CC9 axis A11/B6-B8 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42282 | 42285 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3458 | bottom layer steel reinforcement for slabs 5D-2& 5D-3 axis B17 to B13/A4 to A6 | Steel Reinforcement | Slab | 1.10 | BOH | 42284 | 42290 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3459 | steel reinforcement for stair case 14 axis B15 to B17/A1 | Steel Reinforcement | Stair | 13.00 to 15.20 | 3rd | 42284 | 42289 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3460 | drilling and fixation of dowels for stair case 14 axis B15 to B17/A1 | Dowels | Stair | 15.20 | Typical Floor | 42284 | 42285 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3461 | form work for shear wall 1 axis B1 to B6/A1 | Form Work | SHW | 27.40 to 30.70 | Typical Floor | 42284 | 42290 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3462 | steel reinforcement work for shear wall 1 axis B1 to B6/A1 | Steel Reinforcement | SHW | 27.40 to 30.70 | Typical Floor | 42284 | 42290 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3463 | repair for slab axis A5 to A9/B12 to B14 | Repair | Slab | 1.10 | BOH | 42284 | 42325 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3464 | form work for 2 columns CC9 axis A11/B6-B8 | Form Work | Column | 10.30 to 15.20 | 3rd | 42284 | 42285 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3465 | steel reinforcement for 2 columns CC9 axis A11/B6-B8 | Steel Reinforcement | Column | 10.30 to 15.20 | 3rd | 42284 | 42285 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3466 | steel reinforement for panoramic elevator beams axis A5 to A6/B9 to B10 | Steel Reinforcement | Beam | 10.30 | Second Floor | 42284 | 42285 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3467 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3468 | steel reinforcement for 2 columns CC7 axis B6/A6& A11/B4 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42284 | 42288 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3469 | fixation of shear connectors for 2 columns CC7 axis A6/B6 & A11/B4 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42284 | 42285 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3470 | form work for 2 columns CC7 axis A6/B6& A11/B4 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42284 | 42290 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3471 | top layer steel reinforcement for third stage post tension slab axis B12 to B19/A6 to A12 | Steel Reinforcement | Slab | 5.40 | Ground Floor | 42285 | 42287 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3472 | (Tendons-strands-anchors and profiles) final inspection for third stage post tension slab axis B12 to B19/A6 to A12 | Cables | Slab | 5.40 | Ground Floor | 42285 | 42288 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3473 | form work for second pour strip slab axis B9 to B13/A6 to A12 | Form Work | Slab | 10.30 | Second Floor | 42285 | 42285 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3474 | steel reinforcement for stair case 6 axis B10 to B11/A8 to A9 | Steel Reinforcement | Stair | 5.40 to 10.30 | First Floor | 42285 | 42298 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3475 | final inspection for post tension slab (Tendons-strands-anchors and profiles) for second pour strip axis C3 to C4/B19 | Cables | Slab | 15.20 | 3rd | 42285 | 42289 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3476 | top and bottom layers of steel reinforcement work, dowels and final inspection for post tension slab axis C3 to B19/A1 to A3 | Steel Reinforcement | Slab | 15.20 | 3rd | 42285 | 42289 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3477 | form work for part of slab 5D-4& 5D-5 axis B17 to B19/A4 to A7 | Form Work | Slab | 1.10 | BOH | 42287 | 42296 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3478 | top layer steel reinforcement for slab 5D-2& 5D-3 axis B13 to B17/A4 to A7 | Steel Reinforcement | Slab | 1.10 | BOH | 42287 | 42290 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3479 | fixation of shear connectors for 5 columns CC4 axis D4/A12, D3/A10, D2/A8, D1/A7, A9/B19 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42289 | 42289 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3480 | fixation for shear connectors for 1 column CC7 axis A6/B16 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42289 | 42291 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3481 | steel reinfrocement for shear wall 1 axis B15 to B19/A1 | Steel Reinforcement | SHW | 21.20 to 25.50 | Typical Floor | 42290 | 42291 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3482 | form work for shear wall 1 axis B15 to B19/A1 | Form Work | SHW | 21.20 to 25.50 | Typical Floor | 42290 | 42295 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3483 | form work for shear wall 1 axis B15 to C8/A1 | Form Work | SHW | 21.20 to 25.50 | Typical Floor | 42290 | 42291 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3484 | steel reinforcement for column CC7 axis A6/B16 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42290 | 42296 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3485 | steel reinforcement for column CC4 axis A9/B18 to B19 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42290 | 42291 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3486 | steel reinforcement for column CC4 axis D4 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42290 | 42294 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3487 | steel reinfrocement for column CC4 axis D3 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42290 | 42291 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3488 | steel reinforcement for column CC4 axis D2 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42290 | 42294 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3489 | steel reinforcement for column CC4 axis D1/B18-B19 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42290 | 42294 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3490 | stressing cables No. 61, 60 in X direction first strip axis B8 to B7/A6 to A12 | Stressing | Slab | 10.30 | Second Floor | 42290 | 42291 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3491 | form work for core 2 axis A8 to A10/B16 to B14 | Form Work | Core | 12.80 to 16.10 | Second Floor | 42290 | 42291 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3492 | form work for shear wall 1 axis C4 to C8/A1 | Form Work | SHW | 24.00 to 27.30 | Typical Floor | 42290 | 42291 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3493 | bottom layer steel reinforcement slab of core 5 axis A7 to A11/B6 to B8 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42291 | 42294 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3494 | bottom layer steel reinforcement for panoramic elevator slab axis A5 to A6/B9 to B11 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42291 | 42299 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3495 | grouting for first pour strip slab axis A6 to A12/B4 to B9 | Grout | Slab | 10.30 | Second Floor | 42291 | 42298 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3496 | form work removal for first pour strip slab axis A6 to A12/B10 to B12 | Removing Form Work | Slab | 10.30 | Second Floor | 42291 | 42298 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3497 | drilling and fixation for dowels for slab of core 3 axis B10 to B12/A7 to A11 | Dowels | Slab | 10.30 | Second Floor | 42291 | 42294 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3498 | bottom layer steel reinforcement for second pour strip axis B9 to B13/A6 to A12 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42297 | 42299 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3499 | steel reinforcement for stair case 3 axis A8 to A9/B6 to B8 | Steel Reinforcement | Stair | 5.40 to 10.30 | First Floor | 42291 | 42298 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3500 | steel reinforcement for core 3 axis B10 to B12/A8 to A10 | Steel Reinforcement | Core | 16.20 to 20.10 | 3rd | 42291 | 42296 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3501 | steel reinforcement for shear wall 3 axis C6/A2 to A3 | Steel Reinforcement | SHW | 15.20 to 17.70 | 3rd | 42291 | 42291 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3502 | form work for shear wall 3 axis C6/A2 to A3 | Form Work | SHW | 15.20 to 17.70 | 3rd | 42291 | 42296 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3503 | form work for 2 columns CC7 axis A6/B14-B13 west side | Form Work | Column | 5.40 to 10.30 | First Floor | 42297 | 42298 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3504 | steel reinforcement for stair case 12 axis B1/A2 | Steel Reinforcement | Stair | 15.20 to 18.50 | 3rd | 42291 | 42301 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3505 | fixation for shear connectors for 4 columns CC7 axis A6/B14-B13& A12/B16 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42291 | 42291 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3506 | fixation for shear connectors for 2 columns CC1* axis B13/A8 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42291 | 42291 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3507 | fixation for shear connectors for 4 columns CC1 axis B13/A10-A11 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42291 | 42291 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3508 | fixation for shear connectors for 1 column CC9 axis B14/A11 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42291 | 42291 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3509 | fixation for shear connectors for 1 column CC4 axis A11/B14 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42291 | 42291 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3510 | form work for 3 columns CC4 axis B18 to B19/A7 to A10 (D3-D2-A9/B18-B19) | Form Work | Column | 5.40 to 10.30 | First Floor | 42291 | 42295 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3511 | form work for 2 columns CC4 axis D1- D2 | Form Work | Column | 5.40 to 10.30 | First Floor | 42294 | 42295 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3512 | form work for 1 column CC7 axis A12/B16 | Form Work | Column | 5.40 to 10.30 | First Floor | 42294 | 42296 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3513 | fixation of shear connectors for 1 column CC4 axis B16/A10-A11 | Shear Connectors | Column | 5.40 to 10.30 | First Floor | 42295 | 42296 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3514 | installation of composite column CC9 (Torque) axis B14/A11 | Composite Columns | Column | 5.40 to 10.30 | First Floor | 42295 | 42296 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3515 | form work for shear wall 5/5* axis C5/A2 to A3 | Form Work | SHW | 15.20 to 18.30 | 3rd | 42295 | 42298 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3516 | steel reinforcement for shear wall 5/5* axis C5/A2 to A3 | Steel Reinforcement | SHW | 15.20 to 18.30 | 3rd | 42295 | 42296 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3517 | steel reinforcement for shear wall 2*/3* axis C8/A2 to A3 | Steel Reinforcement | SHW | 15.20 to 18.30 | 3rd | 42295 | 42298 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3518 | form work for shear wall 2*/3* axis C8/A2 to A3 | Form Work | SHW | 15.20 to 18.30 | 3rd | 42295 | 42299 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3519 | stressing for strands for third stage pour strip R.D tower axis B13 to B18/A6 to A12 | Stressing | Slab | 5.40 | First Floor | 42295 | 42299 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3520 | stressing for strands for second stage pour strip at hotel axis C5 to B19/A1 to A3 | Stressing | Slab | 15.20 | 3rd | 42295 | 42298 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3521 | steel reinforcement work for 1 column CC7 axis A12/B16 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42294 | 42294 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3522 | top layer steel reinforcement for slab of core 5 axis A7 to A11/B6 to B8 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42295 | 42298 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3523 | steel reinforcement for column CC4 axis B16/A10-A11 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42295 | 42296 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3524 | form work for column CC4 axis B16/A10-A11 | Form Work | Column | 5.40 to 10.30 | First Floor | 42295 | 42296 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3525 | form work for column CC7 axis B16/A6 | Form Work | Column | 5.40 to 10.30 | First Floor | 42295 | 42296 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3526 | steel reinforcement for column CC9 axis B14/A11 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42295 | 42298 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3527 | steel reinforcement for column CC7 axis B14/A6 | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42295 | 42296 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3528 | bottom layer steel reinforcement for slab 5D-5 axis B17 to B19/A4 to A7 (5D-7) | Steel Reinforcement | Slab | 1.10 | BOH | 42295 | 42296 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3529 | fixation of shear connectors for column CC5 axis C9 | Shear Connectors | Column | 15.20 to 18.50 | 3rd | 42295 | 42296 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3530 | Steel reinforcement for column CC5 axis C9/A3 | Steel Reinforcement | Column | 15.20 to 18.50 | 3rd | 42295 | 42298 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3531 | fixation of shear connectors for column CC6 axis C11 | Shear Connectors | Column | 15.20 to 18.50 | 3rd | 42295 | 42304 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3532 | installation of composite column (Torque) CC6 axis C11 | Composite Columns | Column | 15.20 to 18.50 | 3rd | 42295 | 42304 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3533 | steel reinfrocement for shear wall 2 axis C10/A2 to A3 | Steel Reinforcement | SHW | 15.20 to 18.50 | 3rd | 42295 | 42296 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3534 | form work for shear wall 2 axis C10/A1 to A3 | Form Work | SHW | 15.20 to 18.50 | 3rd | 42295 | 42298 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3535 | steel reinforcement for column CC6 axis C11 | Steel Reinforcement | Column | 15.20 to 18.50 | 3rd | 42295 | 42305 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3536 | steel reinforcement for 1 column CC7 axis A6/B13 west side | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42297 | 42298 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3537 | form work for shear wall 1 and column C1 axis B19 to B20/A1 | Form Work | Column | 15.20 to 18.50 | 3rd | 42295 | 42306 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3538 | steel reinforcement for shear wall 1 and column C1 axis B19 to B20/A1 | Steel Reinforcement | Column | 15.20 to 18.50 | 3rd | 42295 | 42298 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3539 | form work for 1 column CC9 axis B14/A11 | Form Work | Column | 5.40 to 10.30 | First Floor | 42297 | 42298 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3540 | steel reinforcement for core 1 axis B16 to B17/A9 | Steel Reinforcement | Core | 5.40 to 10.30 | First Floor | 42297 | 42299 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3541 | bottom layer steel reinforcement for core 3 slab axis B10 to B12/A8 to A10 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42297 | 42299 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3542 | top layer steel reinforcement for slab of 5D-7 axis B17 to B19/A4 to A7 | Steel Reinforcement | Slab | 1.10 | BOH | 42297 | 42298 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3543 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3544 | bottom layer steel reinforcement for core 2 slab axis B14 to B16/A8 to A10 | Steel Reinforcement | Slab | 5.40 | First Floor | 42297 | 42305 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3545 | form work for core 2 slab axis B14 to B16/A8 to A10 | Form Work | Slab | 5.40 | First Floor | 42297 | 42303 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3546 | repair for post tension cable in 3rd pouring strip slab axis B12 to B13/A8 to A9 | Repair | Slab | 5.40 | First Floor | 42297 | 42298 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3547 | steel reinforcement work for 2 columns CC1 axis B13/A10-A11 west side | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42297 | 42299 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3548 | form work for 2 columns CC1 axis B13/A10-A11 west side | Form Work | Column | 5.40 to 10.30 | First Floor | 42297 | 42299 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3549 | steel reinforcement for 1 column CC1* axis A8/B13 west side | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42297 | 42298 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3550 | Form work for 1 column CC1* axis A8/B13 west side | Form Work | Column | 5.40 to 10.30 | First Floor | 42297 | 42306 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3551 | form work removing for slab 5D-2& 5D-3 axis B13 to B17/A4 to A7 | Removing Form Work | Slab | 5.40 | First Floor | 42297 | 42298 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3552 | form work for column CC5 axis C9/A3 | Form Work | Column | 15.20 to 18.50 | 3rd | 42298 | 42299 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3553 | steel reinforcement for core 8 axis B1/A2 to A3 | Steel Reinforcement | Core | 26.50 to 29.80 | Typical Floor | 42298 | 42303 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3554 | steel reinforcement for core 6 axis B15 to B17/A1 to A2 | Steel Reinforcement | Core | 15.20 to 18.50 | 3rd | 42298 | 42312 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3555 | Form work for core 6 axis B15 to B17/A1 to A2 | Form Work | Core | 15.20 to 18.50 | 3rd | 42298 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3556 | preparation of 2 columns CC7& 1 column CC9 after demolation of concrete axis B4/A9-A10 and B6/A11 | Repair | Column | 10.30 to 15.20 | Second Floor | 42298 | 42299 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3557 | form work for column CC7 axis A10/B4 (Re-work) | Form Work | Column | 10.30 to 15.20 | Second Floor | 42298 | 42301 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3558 | steel reinforcement for column CC7 axis A9/B4 (Re-work) | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42298 | 42299 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3559 | final inspection for post tension slab (Tendons-strands-anchors and profiles) for second pour strip axis B9 to B13/A6 to A12 | Cables | Slab | 10.30 | Second Floor | 42298 | 42301 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3560 | top layer steel reinforcement for post tension slab at second pour strip axis B9 to B13/A6 to A12 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42298 | 42299 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3561 | form work for slab 5D-6 axis A4 to A7/B21 to B19 | Form Work | Slab | 1.10 | BOH | 42299 | 42301 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3562 | top layer steel reinforcement for core 3 slab axis A10 to A8/B10 to B12 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42298 | 42299 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3563 | steel reinforcement for shear wall 2 axis C10/A2 North Side | Steel Reinforcement | SHW | 15.20 to 18.50 | 3rd | 42298 | 42299 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3564 | form work for shear wall 2 axis C10/A2 North Side | Form Work | SHW | 15.20 to 18.50 | 3rd | 42298 | 42299 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3565 | form work for column CC7 axis A9/B4 (Re-work) | Form Work | Column | 10.30 to 15.20 | Second Floor | 42299 | 42301 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3566 | steel reinforcement for column CC9 axis A11/B6 (Re-work) | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42299 | 42301 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3567 | form work for column CC9 axis A11/B6 (Re-work) | Form Work | Column | 10.30 to 15.20 | Second Floor | 42299 | 42303 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3568 | steel reinforcement for column CC7 axis B4/A10 (Re-work) | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42299 | 42299 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3569 | steel reinforcement for 1 column CC1 axis B13/A11 west | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42299 | 42301 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3570 | form work for 1 column CC1 axis B13/A11 west | Form Work | Column | 5.40 to 10.30 | First Floor | 42299 | 42303 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3571 | steel reinforcement for stair 7 axis A10/B10 to B11 | Steel Reinforcement | Stair | 1.10 to 5.40 | First Floor | 42301 | 42305 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3572 | bottom layer steel reinforcement for slab 5C-3 axis B14 to B19/A15 to A13 | Steel Reinforcement | Slab | 1.10 | BOH | 42301 | 42303 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3573 | form work for core 8 axis B1/A2 to A3 | Form Work | Core | 26.70 to 30 | Typical Floor | 42301 | 42305 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3574 | steel reinforcement for column C5 axis B18/A2 | Steel Reinforcement | Column | 15.20 to 18.50 | 3rd | 42302 | 42305 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3575 | form work for column C5 axis B18/A2 | Form Work | Column | 15.20 to 18.50 | 3rd | 42302 | 42306 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3576 | fixation of shear connectors for column CC1 axis A10/B9 east | Shear Connectors | Column | 10.30 to 15.20 | 3rd | 42302 | 42309 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3577 | installation of composite column (Torque) CC1 axis A10/B9 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42302 | 42309 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3578 | fixation of shear connector for column CC1 axis A8/B9 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42302 | 42305 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3579 | installation of 2 composite column (Torque) CC7 axis A6/B12-B10 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42302 | 42306 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3580 | fixation of shear connector for 2 composite columns CC7 axis A6/B12-B10 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42302 | 42306 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3581 | installation of 2 composite columns (Torque) CC9 axis A11/B10-B12 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42302 | 42305 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3582 | fixation of shear connector for 2 composite columns CC9 axis A11/B10-B12 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42302 | 42305 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3583 | fixation of shear connectors for composite column CC1 axis A10/B9 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42302 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3584 | installation of composite column (Torque) CC1 axis A10/B9 west | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42302 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3585 | installation of composite column (Torque) CC7 axis A6/B9 west | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42302 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3586 | fixation of shear connector CC7 axis A6/B9 west | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42302 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3587 | installation of composite column (Torque) CC7 axis A6/B9 east | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42302 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3588 | fixation of shear connector for column CC7 axis A6/B9 east | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42302 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3589 | top layer steel reinforcement work, dowels and final inspection for slab 5C-3 and 5C-4 axis A13 to A15/B14 to B19 | Steel Reinforcement | Slab | 1.10 | BOH | 42302 | 42306 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3590 | duct grouting for post tension slab third stage axisB13 to B18/A6 to A12 at R.D tower | Grout | Slab | 5.40 | First Floor | 42302 | 42303 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3591 | form work for core 1 axis A8/B16-B17 | Form Work | Core | 5.40 to 10.30 | First Floor | 42303 | 42304 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3592 | form work removal for third pour strip axis B13 to B18/A6 to A12 | Removing Form Work | Slab | 5.40 | First Floor | 42303 | 42304 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3593 | stressing for strands for second stage pour strip at R.D tower axis B9 to B13/A6 to A12 | Stressing | Slab | 10.30 | Second Floor | 42303 | 42305 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3594 | form work for core 3 axis B10 to B12/A8 to A10 | Form Work | Core | 16.20 to 19.50 | 3rd | 42303 | 42305 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3595 | steel reinforcement for core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | Core | 20.10 to 23.40 | Typical Floor | 42303 | 42306 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3596 | bottom layer steel reinforcement for slab 5D-6 axis A4 to A7/B19 to B21 | Steel Reinforcement | Slab | 1.10 | BOH | 42303 | 42306 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3597 | steel reinforcement for 4 columns C8 driver stair case axis between axis B19 to B20/between A14 to A15 | Steel Reinforcement | Column | -3.80 to 1.10 | BOH | 42304 | 42306 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3598 | form work for 4 columns C8 driver stair case axis between axis B19 to B20/between A14 to A15 | Form Work | Column | -3.80 to 1.10 | BOH | 42304 | 42309 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3599 | form work for beam B5 axis B14 to B19/between A12 to A13 | Form Work | Beam | 1.10 | BOH | 42304 | 42306 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3600 | form work for column CC6 axis B18/A2 | Form Work | Column | 15.20 to 18.50 | 3rd | 42305 | 42306 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3601 | steel reinforcement for pouring strip between second and third stage axis A6 to A5/B10 | Steel Reinforcement | Slab | 5.40 | First Floor | 42305 | 42306 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3602 | top layer steel reinforcement work, dowels and final inspection for slab 5D-6 axis B19 to B21/A4 to A7 | Steel Reinforcement | Slab | 1.10 | BOH | 42306 | 42309 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3603 | fixation of shear connector for column CC3 axis A11/B9 east | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42305 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3604 | steel reinforcement for core 4 and column CC1 axis B9/A8 | Steel Reinforcement | Core Column | 10.30 to 15.20 | Second Floor | 42305 | 42306 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3605 | form work for column CC7 axis B13/A6 east side | Form Work | Column | 5.40 to 10.30 | First Floor | 42305 | 42306 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3606 | steel reinforcement for column CC7 axis B13/A6 east side | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42305 | 42306 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3607 | form work for column CC1 axis B13/A11 east side | Form Work | Column | 5.40 to 10.30 | First Floor | 42305 | 42306 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3608 | steel reinforcement for column CC1 east side axis B13/A11 east side | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42305 | 42306 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3609 | top layer steel reinforcement work, dowels and final inspection for slab of core 2 axis B14 to B16/A8 to A10 | Steel Reinforcement | Slab | 5.40 | First Floor | 42305 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3610 | installation of column CC3 (torque) axis A11/B9 east side | Composite Columns | Column | 10.30 to 15.20 | First Floor | 42305 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3611 | form work removal for slab 5D-7 axis A5 to A6/B9 to B10 | Removing Form Work | Slab | 1.10 | BOH | 42306 | 42311 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3612 | steel reinforcement for column CC7 axis A6/B12 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42306 | 42309 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3613 | form work for column CC7 axis A6/B12 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42306 | 42309 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3614 | form work for column CC1* axis A8/B13 east side | Form Work | Column | 5.40 to 10.30 | First Floor | 42306 | 42309 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3615 | steel reinforcement work for column CC1* axis A8/B13 east side | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42306 | 42309 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3616 | steel reinforcement for 2 panoramic columns A5 to A6/B9 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42306 | 42311 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3617 | inspection for holes and dowels fixation in core 6 axis B16 to B17/A1 to A2 | Dowels | Core | 15.20 | 3rd | 42306 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3618 | steel reinforcement for shear wall 6 axis C4/A2 to A3 | Steel Reinforcement | SHW | 28.20 to 31.50 | Typical Floor | 42308 | 42318 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3619 | steel reinforcement for shear wall 7 axis C3/A2 to A3 | Steel Reinforcement | SHW | 28.30 to 31.60 | Typical Floor | 42308 | 42319 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3620 | steel reinforcement for core 7 axis C7/A2-A3 | Steel Reinforcement | Core | 27.20 to 30.50 | Typical Floor | 42308 | 42320 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3621 | form work for double column CC7 axis A6/B9 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42311 | 42313 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3622 | installation of 2 columns (Torque) CC9 axis A11/B10-B12 | Composite Columns | Column | 15.20 to 20.10 | Typical Floor | 42308 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3623 | stressing cable No. 27 in X direction second pour strip axis B9 to B13/A6 to A12 | Stressing | Slab | 10.30 | Second Floor | 42309 | 42309 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3624 | raising stress up to 80% for P.T cables according to transmittal 1091 for slab stage 2 axis C3-C4 to B21/A1 to A3 | Stressing | Slab | 15.20 | 3rd | 42308 | 42311 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3625 | form work for column CC1 axis A10/B13 east side | Form Work | Column | 5.40 to 10.30 | First Floor | 42309 | 42309 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3626 | steel reinforcement for column CC1 axis A10/B13 east side | Steel Reinforcement | Column | 5.40 to 10.30 | First Floor | 42309 | 42309 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3627 | form work for core 4 axis B9 to B8/A7 to A10 | Form Work | Core | 10.30 to 15.20 | First Floor | 42309 | 42311 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3628 | steel reinforcement for 2 panoramic elevator columns axis B10/A6-A5 | Steel Reinforcement | Column | 10.30 to 15.20 | First Floor | 42309 | 42311 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3629 | form work for 2 panoramic elevator columns axis B9/A5-A6 | Form Work | Column | 10.30 to 15.20 | First Floor | 42309 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3630 | grouting for second pour strip axis B9 to B13/A6 to A12 | Grout | Slab | 10.30 | First Floor | 42309 | 42311 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3631 | steel reinforcement for pour strip between first and second pour strip axis B9 to B8/A6 to A12 | Steel Reinforcement | Slab | 10.30 | First Floor | 42309 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3632 | steel reinforcement for 2 columns CC9 axis A11/B10-B12 | Steel Reinforcement | Column | 10.30 to 15.20 | First Floor | 42309 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3633 | form work for 2 columns CC9 axis A11/B10-B12 | Form Work | Column | 10.30 to 15.20 | First Floor | 42309 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3634 | form work for third pour strip axis A6 to A12/B13 to B19 | Form Work | Slab | 10.30 | Second Floor | 42310 | 42313 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3635 | steel reinforcement for double column CC1 axis A10/B9 and CC3 axis A11/B9 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42310 | 42311 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3636 | form work for 2 panoramic columns and 1 column CC7 axis B10/A5 to A6 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42310 | 42313 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3637 | form work for double column CC1 axis A10/B9 and CC3 axis A11/B9 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42310 | 42311 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3638 | installation for composite column (torque) CC3 axis B9/A11 west side | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42310 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3639 | fixation of shear connectors for column CC3 axis B9/A11 west side | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42310 | 42311 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3640 | form work removal for second stage pour strip axis A12 to A6/B9 to B12 | Removing Form Work | Slab | 10.30 | Second Floor | 42311 | 42316 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3641 | steel reinforcement for beam B7 axis A6 to A10/B13 | Steel Reinforcement | Beam | 10.30 | Second Floor | 42311 | 42312 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3642 | inspection for holes and dowels fixation for core 5 slab axis A8 to A10/B6 to B8 | Dowels | Slab | 15.20 | 3rd | 42311 | 42313 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3643 | form work for stair 5 axis A8 to A9/B8 to B9 | Form Work | Stair | 10.30 to 15.20 | Second Floor | 42311 | 42313 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3644 | form work for stair 3 axis A8/B6 to B7 | Form Work | Stair | 10.30 to 15.20 | Second Floor | 42311 | 42320 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3645 | form work for R.D tower pour strip first stage axis B4 to B9/A6 to A12 | Form Work | Slab | 15.20 | 3rd | 42311 | 42313 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3646 | form work for column CC1 axis B9/A10 west side | Form Work | Column | 10.30 to 15.20 | Second Floor | 42311 | 42312 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3647 | bottom layer steel reinforcement for first pour strip at hotel tower axis C1 to C5/A1 to A7 | Steel Reinforcement | Slab | 21.80 | Typical Floor | 42312 | 42316 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3648 | top layer steel reinforcement for first pour strip at hotel tower axis C1 to C5/A1 to A7 | Steel Reinforcement | Slab | 21.80 | Typical Floor | 42312 | 42316 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3649 | final inspection for post tension slab (Tendons- strands- anchors- profiles) for first strip at hotel tower axis C1 to C5/A1 to A7 | Cables | Slab | 21.80 | Typical Floor | 42312 | 42313 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3650 | bottom layer steel reinforcement work, for third pour strip at R.D tower axis B13 to B18/A6 to A12 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42312 | 42317 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3651 | steel reinforcement for 1 double column CC7 axis A6/B9 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42311 | 42312 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3652 | ducts grouting for second pour strip axis C5 to B19/A1 to A3 | Grout | Slab | 15.20 | 3rd | 42313 | 42318 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3653 | form work for core 2 slab axis A9/B15 to B16 | Form Work | Slab | 10.30 | Second Floor | 42313 | 42320 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3654 | form work for stair 11 axis A9/B17 | Form Work | Stair | 5.40 to 10.30 | First Floor | 42313 | 42318 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3655 | final inspection for post tension slab (Tendons- strands- anchors- profiles) for first strip at R.D tower axis A6 to A12/B4 to B9 | Cables | Slab | 15.20 | 3rd | 42313 | 42316 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3656 | top layer steel reinforcement for first strip at R.D tower axis A6 to A12/B4 to B9 | Steel Reinforcement | Slab | 15.20 | 3rd | 42313 | 42316 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3657 | bottom layer steel reinforcement for first pour strip at R.D tower axis A6 to A12/B4 to B9 | Steel Reinforcement | Slab | 15.20 | 3rd | 42313 | 42316 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3658 | drilling and fixation for dowels at hotel tower second pour strip axis A2/B19 to B17 | Dowels | Slab | 18.50 | Typical Floor | 42313 | 42318 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3659 | drilling and fixation for dowels at stair case 5 axis A8 to A9/B8 to B9 | Dowels | Stair | 10.30 to 15.20 | Second Floor | 42315 | 42318 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3660 | steel reinforcement for shear wall 8 axis C2/A1 to A3 | Steel Reinforcement | SHW | 21.80 to 25.10 | Typical Floor | 42316 | 42318 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3661 | form work for shear wall 8 axis C2/A1 to A3 | Form Work | SHW | 21.80 to 25.10 | Typical Floor | 42316 | 42319 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3662 | form work for stair case 12 axis A2/B1 | Form Work | Stair | 18.50 to 21.80 | Typical Floor | 42316 | 42318 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3663 | steel reinforcement for shear wall 1 axis C1 to C5/A1 | Steel Reinforcement | SHW | 28.10 to 31.40 | Typical Floor | 42316 | 42317 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3664 | form work for shear wall 1 axis C1 to C5/A1 | Form Work | SHW | 28.10 to 31.40 | Typical Floor | 42316 | 42318 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3665 | stressing for first pour strip at hotel tower for Y&X directions axis b1 to C5/A1 to A3 | Stressing | Slab | 21.80 | Typical Floor | 42316 | 42320 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3666 | form work removal for slab 5D-6 axis B19 to B21/A4 to A7 | Removing Form Work | Slab | 1.10 | BOH | 42316 | 42317 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3667 | form work removal for slab 5C-3 axis B14 to B19/A15 to A13 | Removing Form Work | Slab | 1.10 | BOH | 42316 | 42317 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3668 | form work for slab 5C-6 axis B19 to B21/A14 to A15 | Form Work | Slab | 1.10 | BOH | 42317 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3669 | form work for core 5 axis B6 to B8/A8 to A10 | Form Work | Core | 20.10 to 23.40 | Typical Floor | 42317 | 42319 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3670 | steel reinforcement for stair case 5 axis B8 to B9/A8 to A9 | Steel Reinforcement | Stair | 10.30 to 15.20 | Second Floor | 42317 | 42320 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3671 | shear connector for 1 column CC7 axis A11/B4 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42317 | 42320 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3672 | installation of column CC7 (Torque) axis A11/B4 | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42317 | 42320 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3673 | steel reinforcement for stair case 11 axis B17/A9 | Steel Reinforcement | Stair | 5.40 to 10.30 | First Floor | 42317 | 42320 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3674 | bottom steel reinforcement for core 2 slab axis A8 to A10/B14 to B16 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42317 | 42324 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3675 | form work for second pouring strip at R.D tower axis B9 to B13/A6 to A12 | Form Work | Slab | 15.20 | 3rd | 42317 | 42320 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3676 | steel reinforcement for core 2 axis A8 to A10/B14 to B16 | Steel Reinforcement | Core | 16.20 to 20.10 | Second Floor | 42317 | 42325 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3677 | fixation of shear connector for 3 columns CC7 axis B4/A10-A9-A8 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42317 | 42320 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3678 | installation for 3 columns CC7 (torque) axis B4/A10-A9-A8 | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42317 | 42320 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3679 | form work for shear wall 6 axis C4/A2 to A3 | Form Work | SHW | 28.20 to 31.50 | Typical Floor | 42317 | 42319 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3680 | steel reinforcement for pour strip between first and second pour strip between axis C4 and C5/A1 to A3 | Steel Reinforcement | Slab | 15.20 | 3rd | 42318 | 42319 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3681 | form work for shear wall 7 axis C3/A2 to A3 | Form Work | SHW | 28.40 to 31.70 | Typical Floor | 42318 | 42323 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3682 | final inspection for third pour strip (Tendons- strands- anchors- profiles) at R.D tower axis A6 to A12/B13 to B18 | Cables | Slab | 10.30 | Second Floor | 42318 | 42323 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3683 | top layer steel reinforcement for third pour strip axis A6 to A12/B13 to B18 at R.D tower | Steel Reinforcement | Slab | 10.30 | Second Floor | 42318 | 42320 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3684 | fixation of shear connector for 3 columns CC7 axis A6/B5-B6-B8 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42318 | 42320 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3685 | installation (Torque) for 3 columns CC7 axis A6/B5-B6-B8 | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42318 | 42320 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3686 | bottom layer steel reinforcement for core 5 slab axis A8 to A10/B6 to B8 | Steel Reinforcement | Slab | 15.20 | 3rd | 42318 | 42320 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3687 | top layer steel reinforcement for core 5 slab axis A8 to A10/B6 to B8 | Steel Reinforcement | Slab | 15.20 | 3rd | 42318 | 42320 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3688 | repair for column CC7 axis A11/B8 | Repair | Column | 10.30 to 15.20 | Second Floor | 42319 | 42320 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3689 | steel reinforcement for stair case 3 axis A8 to A9/B6 to B8 | Steel Reinforcement | Stair | 10.30 to 15.20 | Second Floor | 42318 | 42325 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3690 | stressing for first pour strip at R.D tower axis B4 to B9/A6 to A12 | Stressing | Slab | 15.20 | 3rd | 42318 | 42326 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3691 | drilling and fixation of dowels for stair case 12 axis B1/A1 to A2 | Dowels | Stair | 18.50 to 21.80 | Typical Floor | 42319 | 42320 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3692 | steel reinforcement for stair case 12 axis A2/B1 | Steel Reinforcement | Stair | 18.50 to 21.80 | Typical Floor | 42320 | 42336 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3693 | form work for core 7 axis A2 to A3/C7 | Form Work | Core | 28.40 to 31.70 | Typical Floor | 42319 | 42324 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3694 | fixation for shear connector for column CC7 axis A10/B4 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42322 | 42331 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3695 | installation (torque) for column CC7 axis A10/B4 | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42322 | 42331 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3696 | installation (torque) for 1 column CC7 axis B13/A6 east side | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42322 | 42323 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3697 | installation (torque) for 2 column CC1 axis B13/A11-A10 east side | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42322 | 42323 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3698 | installation (torque) for 1 column CC1* axis B13/A8 east side | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42322 | 42323 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3699 | installation (torque) for 4 columns CC4 axis B19/A9, D1, D2, D3 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42322 | 42330 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3700 | fixation for shear connector for 1 column CC7 axis B13/A6 east side | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42322 | 42323 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3701 | fixation for shear connector for 1 column CC1* axis B13/A8 east side | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42322 | 42323 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3702 | fixation for shear connector for 2 columns CC1 axis B13/A11-A10 east side | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42322 | 42323 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3703 | fixation for shear connector for 4 columns CC4 axis B19/A9, D1, D2, D3 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42322 | 42330 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3704 | stressing for third pour strip slab axis B13 to B18/A6 to A12 | Stressing | Slab | 10.30 | Second Floor | 42323 | 42331 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3705 | steel reinforcement for stair case 6 axis B10 to B11/A8 to A9 | Steel Reinforcement | Stair | 10.30 to 15.20 | Second Floor | 42323 | 42336 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3706 | installation (Torque) for 2 columns CC1 axis B13/A10-A11 west side | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42323 | 42327 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3707 | installation (Torque) for 1 column CC1* axis B13/A8 west side | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42323 | 42327 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3708 | fixation of shear connectors for 2 columns CC1 axis B13/A10-A11 west side | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42323 | 42327 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3709 | fixation of shear connectors for 1 column CC1* axis B13/A8 west side | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42323 | 42327 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3710 | steel reinforcement for core 1 axis A8/B16-B17 | Steel Reinforcement | Core | 10.30 to 15.20 | Second Floor | 42323 | 42325 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3711 | form work for core 3 axis B10 to B12/A8 to A10 | Form Work | Core | 19.50 to 20.10 | Typical Floor | 42323 | 42325 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3712 | steel reinforcement for beams at second pour strip slab at hotel axis C5 to B19/A1 to A3 | Steel Reinforcement | Beam | 18.50 | Typical Floor | 42323 | 42331 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3713 | steel reinforcement for 4 columns CC7 axis B4/A9-A8& A6/B5-B6 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42323 | 42324 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3714 | form work for 4 columns CC7 axis B4/A9-A8& A6/B5-B6 | Form Work | Column | 15.20 to 20.10 | 3rd | 42323 | 42325 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3715 | steel reinforcement for 2 columns CC7 axis B4/A11 and A6/B8 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42323 | 42324 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3716 | form work for 3 columns CC7 axis B4/A10-A11& A6/B8 | Form Work | Column | 15.20 to 20.10 | 3rd | 42324 | 42325 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3717 | steel reinforcement for 1 column CC7 axis B4/A10 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42324 | 42325 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3718 | bottom layer steel reinforcement for second stage of R.D tower slab axis B9 to B13/A6 to A12 | Steel Reinforcement | Slab | 15.20 | 3rd | 42324 | 42327 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3719 | steel reinforcement for 1 column CC4 axis D4 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42324 | 42326 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3720 | form work for 1 column CC4 axis D4 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42324 | 42327 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3721 | steel reinforcement for core 2 slab axis A8 to A10/B14 to B16 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42324 | 42325 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3722 | form work for ramp 4 axis B17 to C9/A3 to A4 | Form Work | Ramp | -7.20 to 1.10 | B2, B1, BOH | 42324 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3723 | drilling and fixation for dowels for part of slab 4A axis B17 to B19/A1 to A3 | Dowels | Slab | 1.10 | BOH | 42324 | 42325 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3724 | surface preparation and repair for 1 column CC9 axis A11/B8 | Repair | Column | 10.30 to 15.20 | Second Floor | 42325 | 42325 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3725 | fixation for shear connectors for 2 columns CC9 axis A11/B6-B8 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42325 | 42327 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3726 | installation (torque) for 2 columns CC9 axis A11/B6-B8 | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42325 | 42327 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3727 | form work for core 1 axis A9/B17 | Form Work | Core | 10.30 to 15.20 | Second Floor | 42325 | 42327 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3728 | form work for stair case 7 axis A10/B10-B11 | Form Work | Stair | 5.40 to 10.30 | First Floor | 42325 | 42329 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3729 | steel reinforcement for 1 column CC4 axis D2 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42325 | 42326 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3730 | form work for 1 column CC4 axis D2 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42325 | 42327 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3731 | installation (torque) for 1 column CC4 axis D4 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42325 | 42326 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3732 | fixation of shear connector for 1 column CC4 axis D4 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42325 | 42326 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3733 | steel reinforcement for shear wall 1 axis B19 to B11/A1 | Steel Reinforcement | SHW | 25.50 to 28.80 | Typical Floor | 42326 | 42329 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3734 | steel reiforcement for shear wall 1 axis B11 to B6/A1 | Steel Reinforcement | SHW | 27.30 to 30.60 | Typical Floor | 42326 | 42329 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3735 | installation (torque) for 1 column CC7 axis B16/A12 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42325 | 42326 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3736 | shear connector for 1 column CC7 axis B16/A12 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42325 | 42326 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3737 | steel reinforcement for 1 column CC7 axis B16/A12 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42325 | 42327 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3738 | form work for 1 column CC7 axis B16/A12 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42325 | 42329 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3739 | steel reinforcement for core 8 axis B1/A1 to A3 | Steel Reinforcement | Core | 30 to 33.30 | Typical Floor | 42325 | 42329 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3740 | steel reinforcement for 2 columns CC9 axis A11/B6-B8 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42326 | 42331 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3741 | installation (torque) for 2 columns CC7 axis A6/B14& A6/B13 west side | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42326 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3742 | fixation of shear connectors for 2 columns CC7 axis A6/B14& A6/B13 west side | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42326 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3743 | steel reinforcement for panoramic beams axis B9 to B10/A5 to A6 | Steel Reinforcement | Beam | 15.20 | 3rd | 42327 | 42331 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3744 | installation (torque) for 1 column CC9 axis B14/A11 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42327 | 42331 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3745 | fixation of shear connectors for 1 column CC9 axis A11/B14 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42327 | 42331 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3746 | form work for core 2 axis B14 to B15/A8 to A10 | Form Work | core | 16.20 to 19.50 | 3rd | 42329 | 42331 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3747 | steel reinforcement for 1 column CC4 axis B19/A9 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42326 | 42327 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3748 | form work for 1 column CC4 axis B19/A9 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42326 | 42329 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3749 | ducts grouting for first post tension slab axis A6 to A12/B4 to B9 | Grout | Slab | 15.20 | 3rd | 42326 | 42327 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3750 | top layer steel reinforcement for slab 5C-6 axis A13 to A15/B21 to B19 | Steel Reinforcement | Slab | 1.10 | BOH | 42326 | 42329 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3751 | steel reinforcement for 1 double column CC1 axis B13/A11 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42329 | 42333 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3752 | steel reinforcement for 1 column CC1 axis B13/A10 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42327 | 42333 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3753 | form work for 1 column CC1 axis B13/A10 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42327 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3754 | steel reinforcement for 1 column CC1* axis B13/A8 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42327 | 42331 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3755 | form work for 1 column CC1* axis B13/A8 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42327 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3756 | form work for 2 columns CC9 axis A11/B6-B8 | Form Work | Column | 15.20 to 20.10 | 3rd | 42327 | 42331 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3757 | increasing torque up to 80% of breaking load for cable 1& 2 at Y direction | Stressing | Slab | 21.80 | Typical Floor | 42327 | 42331 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3758 | form work for 1 double column CC1 axis B13/A11 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42329 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3759 | installation (torque) for 1 column CC4 axis B16/A10 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42329 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3760 | installation (torque) for 1 column CC7 axis B16/A6 | Composite Columns | Column | 10.30 to 15.20 | Second Floor | 42329 | 42331 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3761 | fixation of shear connectors for 1 column CC4 axis B16/A10 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42329 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3762 | fixation of shear connectors for 1 column CC7 axis B16/A6 | Shear Connectors | Column | 10.30 to 15.20 | Second Floor | 42329 | 42331 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3763 | bottom layer steel reinforcement for second stage of post tension slab axis C5 to B19/A1 to A3 | Steel Reinforcement | Slab | 18.50 | Typical Floor | 42329 | 42331 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3764 | top layer steel reinforcement for second stage of post tension slab axis C5 to B19/A1 to A3 | Steel Reinforcement | Slab | 18.50 | Typical Floor | 42329 | 42331 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3765 | final inspection for second stage post tension slab (Tendons- strands- anchors- profiles) at hotel tower axis C5 to B19/A1 to A3 | Cables | Slab | 18.50 | Typical Floor | 42329 | 42333 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3766 | form work for core 8 axis A2 to A3/B1 | Form Work | core | 30.00 to 33.30 | Typical Floor | 42330 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3767 | form work removing for first stage of post tension axis B1 to C5 | Removing Form Work | Slab | 21.80 | Typical Floor | 42332 | 42336 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3768 | steel reinforcement for column CC7 axis B16/A6 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42330 | 42331 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3769 | form work for column CC7 axis B16/A6 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42330 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3770 | form work for column CC9 axis A11/B14 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42330 | 42337 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3771 | steel reinforcement for column CC9 axis A11/B14 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42330 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3772 | form work for 1 double column CC7 axis B13/A6 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42330 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3773 | steel reinforcement for 1 double column CC7 axis B13/A6 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42330 | 42337 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3774 | steel reinforcement for panoramic beam B9 axis B9 to B10/A5 to A6 | Steel Reinforcement | Beam | 15.20 | 3rd | 42331 | 42337 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3775 | form work for 1 column CC7 axis B14/A16 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42331 | 42336 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3776 | steel reinforcement for 1 column CC4 axis D1 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42331 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3777 | steel reinforcement for 1 column CC7 axis B14/A16 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42331 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3778 | form work for 1 column CC4 axis D1 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42331 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3779 | steel reinforcement for 1 column CC4 axis D3 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42331 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3780 | form work for 1 column CC4 axis D3 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42331 | 42336 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3781 | bottom layer steel reifnorcement for slab 5D-4& 5D-8 axis A1 to A4/B17 to B21 | Steel Reinforcement | Slab | 1.10 | BOH | 42331 | 42333 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3782 | steel reinforcement for 1 column CC4 axis B16/A11 | Steel Reinforcement | Column | 10.30 to 15.20 | Second Floor | 42332 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3783 | form work for 1 column CC4 axis B16/A11 | Form Work | Column | 10.30 to 15.20 | Second Floor | 42332 | 42336 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3784 | surface preparation prior to repair work for bottom of slab as shown in attached sketch | Repair | Slab | -3.80 to 1.10 | BOH | 42330 | 42331 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3785 | grouting for cables for first stage of post tension at hotel tower axis B1 to B5/A1 to A3 | Grout | Slab | 21.80 | Typical Floor | 42332 | 42333 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3786 | form work for stair case 3 axis B6 to B7/A8 to A9 | Form Work | Stair | 15.20 to 20.10 | 3rd | 42333 | 42343 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3787 | form work for shear wall 1 axis B11 to B19/A1 | Form Work | SHW | 25.50 to 28.80 | Typical Floor | 42333 | 42336 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3788 | steel reinforcement for shear wall 6 axis C4/A2 to A3 | Steel Reinforcement | SHW | 31.50 to 34.80 | Typical Floor | 42333 | 42336 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3789 | tendons, strands, anchors and profiles final inspection for post tension slab second stage at R.D tower axis A6 to A12/B9 to B12 | Cables | Slab | 15.20 | 3rd | 42333 | 42336 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3790 | bottom layer steel reinforcement for panoramic slab axis B9 to B10/A5 to A6 | Steel Reinforcement | Slab | 15.20 | 3rd | 42333 | 42336 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3791 | top layer steel reinforcement work, dowels and final inspection for panoramic slab axis B9 to B10/A5 to A6 | Steel Reinforcement | Slab | 15.20 | 3rd | 42333 | 42336 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3792 | inspection for holes and dowels fixation at stair case 10 axis B14 to B15/A8 to A9 | Dowels | Stair | -11.00 to -7.20 | B2, B1 | 42333 | 42336 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3793 | top steel reinforcement for second stage post tension slab axis A6 to A12/B9 to B12 | Steel Reinforcement | Slab | 1.10 | BOH | 42333 | 42337 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3794 | top layer steel reinforcement work, dowels and final inspection request for slab 5D-4 and 5D-8 axis B17 to B21/A1 to A4 | Steel Reinforcement | Slab | 1.10 | BOH | 42333 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3795 | bottom layer steel reinforcement for ramp 4 axis A6 to A12/B9 to B12 | Steel Reinforcement | Ramp | -3.80 to 1.10 | BOH | 42333 | 42339 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3796 | form work for shear wall 1 axis B6 to B10/A1 | Form Work | SHW | 27.00 to 30.30 | Typical Floor | 42357 | 42358 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3797 | steel reinforcement for stair case 4 axis A10/B7 to B8 | Steel Reinforcement | Stair | -11.00 to -7.20 | B2 | 42334 | 42345 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3798 | steel reinforcement for shear wall 7 axis C3/A2 to A3 | Steel Reinforcement | SHW | 31.50 to 34.80 | Typical Floor | 42334 | 42336 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3799 | drilling and fixation for dowels for column C5 axis B18/A1 to A2 | Dowels | Column | 18.50 to 21.80 | Typical Floor | 42334 | 42337 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3800 | steel reinforcement for shear wall 5/5* axis C5/A2 to A3 | Steel Reinforcement | SHW | 18.50 to 21.80 | Typical Floor | 42334 | 42339 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3801 | steel reinforcement for shear wall 3 axis C6/A2 to A3 | Steel Reinforcement | SHW | 18.50 to 21.80 | Typical Floor | 42334 | 42339 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3802 | steel reinforcement for core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | core | 23.40 to 26.70 | Typical Floor | 42336 | 42339 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3803 | form work for stair case 10 axis A8 to A9/B14 to B15 | Form Work | Stair | -11.00 to -7.20 | B2 | 42336 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3804 | form work for shear wall 6 axis C4/A2 to A3 | Form Work | SHW | 31.50 to 34.80 | Typical Floor | 42336 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3805 | form work for shear wall 7 axis C3/A2 to A3 | Form Work | SHW | 31.50 to 34.80 | Typical Floor | 42336 | 42340 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3806 | form work for shear wall 5/5* axis C5/A2 to A3 | Form Work | SHW | 18.50 to 21.80 | Typical Floor | 42336 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3807 | form work for shear wall 3 axis A1 to A3/C6 | Form Work | SHW | 18.50 to 21.80 | Typical Floor | 42336 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3808 | form work for shear wall 2*/3* axis C8/A2 to A3 | Form Work | SHW | 18.50 to 21.80 | Typical Floor | 42336 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3809 | steel reinforcement for shear wall 2*/3* axis C8/A2 to A3 | Steel Reinforcement | SHW | 18.50 to 21.80 | Typical Floor | 42336 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3810 | installation (torque) for 1 column CC6 axis C9/A2 | Composite Columns | Column | 18.50 to 21.80 | Typical Floor | 42336 | 42337 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3811 | installation (torque) for 1 column CC5 axis C11/A2 | Composite Columns | Column | 18.50 to 21.80 | Typical Floor | 42336 | 42337 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3812 | fixation for shear connectors for 1 column CC5 axis C11/A2 | Shear Connectors | Column | 18.50 to 21.80 | Typical Floor | 42336 | 42337 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3813 | fixation for shear connectors for 1 column CC6 axis C9/A2 | Shear Connectors | Column | 18.50 to 21.80 | Typical Floor | 42336 | 42337 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3814 | top layer steel reinforcement for ramp 4 axis A6 to A12/B9 to B12 | Steel Reinforcement | Ramp | -3.80 to 1.10 | BOH | 42336 | 42339 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3815 | fixation for shear connectors for 1 double column CC1 axis B9/A11 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42337 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3816 | fixation for shear connectors for 1 double column CC3 axis B9/A10 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42337 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3817 | steel reinforcement for 1 double column CC1 axis B9/A11 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42337 | 42340 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3818 | steel reinforcement for 1 double column CC3 axis B9/A10 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42337 | 42339 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3819 | form work for 1 double column CC1 axis B9/A11 | Form Work | Column | 15.20 to 20.10 | 3rd | 42337 | 42340 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3820 | form work for 1 double column CC3 axis B9/A10 | Form Work | Column | 15.20 to 20.10 | 3rd | 42337 | 42340 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3821 | steel reinforcement for 2 panoramic columns axis B9/between A5-A6 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42337 | 42340 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3822 | installation (torque) for 3 columns CC7 axis A6/B12-B10-B9 east side | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42337 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3823 | fixation for shear connectors for 3 columns CC7 axis A6/B12-B10-B9 east side | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42337 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3824 | steel reinforcement for pouring strip between second and third stage axis A6 to A5/B10 | Steel Reinforcement | Slab | 10.30 | Second Floor | 42337 | 42340 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3825 | drilling and fixation for dowels for stair 14 axis A1/B15 to B16 | Dowels | Stair | 15.20 to 20.10 | 3rd | 42337 | 42339 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3826 | steel reinforcement for 1 column CC6 axis C11/A2 to A3 | Steel Reinforcement | Column | 18.50 to 21.80 | Typical Floor | 42337 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3827 | steel reinforcement for 1 column CC5 axis C9/A2 to A3 | Steel Reinforcement | Column | 18.50 to 21.80 | Typical Floor | 42337 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3828 | drilling and fixation for dowels for beam axis B1/A1 | Dowels | Beam | 25.10 | Typical Floor | 42337 | 42341 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3829 | drilling and fixation for dowels of shear wall 6 axis C4/A2 to A3 | Dowels | SHW | 25.10 | Typical Floor | 42337 | 42339 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3830 | form work for 1 column CC6 axis C11/A2 to A3 | Form Work | Column | 18.50 to 21.80 | Typical Floor | 42337 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3831 | form work for 1 column CC5 axis C9/A2 to A3 | Form Work | Column | 18.50 to 21.80 | Typical Floor | 42337 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3832 | form work removing for slab 5D-6 axis A12 to A15/B19 to B21 | Removing Form Work | Slab | 1.10 | BOH | 42337 | 42339 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3833 | steel reinforcement for shear wall 2 axis C10/A3 R.D tower side | Steel Reinforcement | SHW | 18.50 to 21.80 | Typical Floor | 42337 | 42339 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3834 | form work for ramp 4 beams axis A3 to A4/B9 to B17 | Form Work | Beam | -7.20 to 1.10 | BOH | 42338 | 42340 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3835 | drilling and fixation for holes and dowels at shear wall 7& 6 axis C4/A2 to A1& C3/A2 to A1 | Dowels | SHW | 25.10 | Typical Floor | 42338 | 42341 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3836 | steel reinforcement for shear wall 1 and 1 column C1 axis B19 to B20/A1 | Steel Reinforcement | SHW | 18.50 | Typical Floor | 42338 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3837 | steel reinforcement for 1 column C5 axis B18/A2 | Steel Reinforcement | Column | 18.50 to 21.80 | Typical Floor | 42338 | 42339 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3838 | form work for shear wall 2 axis C10/A1 to A3 | Form Work | SHW | 18.50 to 21.80 | Typical Floor | 42338 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3839 | stressing of strands for second pour strip post tension slab at hotel tower axis C5 to B19/A1 to A3 | Stressing | Slab | 18.50 | Typical Floor | 42338 | 42340 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3840 | steel reinforcement for panoramic column axis A5 to A6/B10 to B11 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42338 | 42339 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3841 | steel reinforcement for panoramic column axis B10/A6 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42338 | 42341 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3842 | installation (torque) for 1 column CC9 axis B10/A11 | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42338 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3843 | fixation of shear connectors for 1 column CC9 axis A11/B10 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42338 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3844 | fixation of shear connectors for 1 column CC1 axis B9/A8 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42338 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3845 | fixation of shear connectors for 1 column CC1 axis B12/A11 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42338 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3846 | installation (torque) for 1 column CC9 axis B12/A11 | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42338 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3847 | fixation of shear connectors for 1 column CC7 axis B9/A6 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42338 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3848 | installation (torque) for 1 column CC7 axis B9/A6 west side | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42338 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3849 | stressing for strands for second post tension slab axis A6 to A12/B8 to B12 | Stressing | Slab | 15.20 | 3rd | 42338 | 42345 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3850 | ducts grouting for the third post tension slab axis A6 to A12/B4 to B9 | Grout | Slab | 10.30 | Second Floor | 42338 | 42339 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3851 | drilling and fixation for dowels at beam of hotel slab axis B1 to B2/B2/A3 | Dowels | Beam | 25.10 | Typical Floor | 42339 | 42341 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3852 | drilling and fixation for holes and dowels at core 6 axis B16 to B17/A2 | Dowels | core | 18.50 to 21.80 | Typical Floor | 42339 | 42341 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3853 | form work for shear wall 1 and 1 column C1 axis B19 to B20/A1 | Form Work | SHW | 18.50 to 21.80 | Typical Floor | 42339 | 42340 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3854 | form work for 1 column C5 axis B18/A2 | Form Work | Column | 18.50 to 21.80 | Typical Floor | 42339 | 42340 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3855 | form work for shear wall 2 axis C10/A2 Hotel Side | Form Work | SHW | 18.50 to 21.80 | Typical Floor | 42339 | 42341 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3856 | steel reinforcement for shear wall 2 axis C10/A2 Hotel Side | Steel Reinforcement | SHW | 18.50 to 21.80 | Typical Floor | 42339 | 42340 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3857 | form work for 1 panoramic column axis A6 to A5/B10 to B11 | Form Work | Column | 15.20 to 20.10 | 3rd | 42339 | 42343 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3858 | form work for 2 panoramic columns axis A6 to A5/B9 to B10 | Form Work | Column | 15.20 to 20.10 | 3rd | 42339 | 42346 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3859 | steel reinforcement for core 4 axis B8 to B9/A7 to A10 | Steel Reinforcement | Core | 15.20 to 20.10 | 3rd | 42339 | 42341 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3860 | form work for core 4 axis A8/B9 | Form Work | core | 15.20 to 20.10 | 3rd | 42339 | 42344 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3861 | form work for 1 column CC9 axis A11/B12 | Form Work | Column | 15.20 to 20.10 | 3rd | 42339 | 42345 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3862 | steel reinforcement for 1 column CC9 axis A11/B12 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42339 | 42343 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3863 | steel reinforcement for 1 column CC9 axis A11/B10 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42339 | 42343 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3864 | form work for 1 column CC9 axis A11/B10 | Form Work | Column | 15.20 to 20.10 | 3rd | 42339 | 42345 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3865 | form work for 1 column CC7 axis A6/B9 | Form Work | Column | 15.20 to 20.10 | 3rd | 42339 | 42348 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3866 | steel reinforcement for 1 double column CC7 axis A6/B9 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42348 | 42348 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3867 | surface preparation and repair for slab axis B13 to B14/A5 to A6 | Repair | Slab | 1.10 | BOH | 42339 | 42340 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3868 | form work for 1 column CC7 axis A6/B12 | Form Work | Column | 15.20 to 20.10 | 3rd | 42340 | 42340 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3869 | steel reinforcement for 1 column CC7 axis A6/B12 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42340 | 42340 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3870 | surface preparation and repair for core 1 axis A9/B17 | Repair | Core | -3.80 to 1.10 | BOH | 42340 | 42360 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3871 | surface preparation and repair for core 2 axis A7 to A10/B14 to B16 | Repair | Core | -3.80 to 1.10 | BOH | 42340 | 42360 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3872 | steel reinforcement for beam at pour strip between stage 2 and 3 axis A6/B10 to B13 | Steel Reinforcement | Beam | 15.20 to 20.10 | 3rd | 42340 | 42345 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3873 | steel reinforcement for core 6 axis B15 to B17/A1 to A2 | Steel Reinforcement | core | 18.50 to 21.80 | Typical Floor | 42340 | 42341 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3874 | form work for core 5 axis A8 to A10/B6 to B8 | Form Work | core | 23.40 to 26.70 | Typical Floor | 42340 | 42369 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3875 | steel reinforcement for stair case 7 axis B12 to B13/A7 to A9 | Steel Reinforcement | Stair | 5.40 to 10.30 | First Floor | 42341 | 42344 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3876 | form work for stair case 11 axis B16 to B17/A9 | Form Work | Stair | 10.30 to 15.20 | Second Floor | 42341 | 42343 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3877 | steel reinforcement for beam at third post tension slab axis A6/B12 to B14 | Steel Reinforcement | Beam | 15.20 to 20.10 | 3rd | 42341 | 42348 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3878 | form work for third post tension slab axis A6 to A12/B12 to B19 | Form Work | Slab | 15.20 | 3rd | 42341 | 42343 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3879 | form work for core 6 axis A1 to A2/B15 to B17 | Form Work | core | 18.50 to 21.80 | Typical Floor | 42341 | 42343 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3880 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3881 | bottom layer steel reinforcement for third stage post tension slab axis B13 to B18/A6 to A12 | Steel Reinforcement | Slab | 15.20 | 3rd | 42343 | 42346 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3882 | bottom layer steel reinforcement for core 3 slab axis B10 to B12/A8 to A10 | Steel Reinforcement | Slab | 15.20 | 3rd | 42343 | 42348 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3883 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3884 | form work for panoramic column axis B10/A6 | Form Work | Column | 15.20 to 20.10 | 3rd | 42344 | 42346 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3885 | steel reinforcement for stair case 3 axis A8 to A9/B6 to B8 | Steel Reinforcement | Stair | 15.20 to 20.10 | 3rd | 42344 | 42353 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3886 | drilling and dowels fixation for Hotel slab axis B17 to B19/A1 | Dowels | Slab | 21.80 | Typical Floor | 42345 | 42346 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3887 | steel reinforcement for core 3 axis A8 to A10/B10 to B12 | Steel Reinforcement | core | 20.10 to 23.40 | Typical Floor | 42344 | 42345 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3888 | top layer steel reinforcement for core 3 slab axis A10 to A8/B10 to B12 | Steel Reinforcement | Slab | 15.20 | 3rd | 42344 | 42348 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3889 | steel reinforcement for stair case 11 axis A9/B16 to B17 | Steel Reinforcement | Stair | 10.30 to 15.20 | Second Floor | 42344 | 42347 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3890 | form work for slab at axis B12 to B13/A3 to A4 | Form Work | Slab | 1.10 | BOH | 42345 | 42361 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3891 | form work removal for ramp 4 axis A4 to A3/B17 to B13 | Removing Form Work | Ramp | -3.80 to 1.10 | BOH | 42345 | 42346 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3892 | form work removal for slab 5D-4 and 5D-8 axis A1 to A4/B21 to B17 | Removing Form Work | Slab | 1.10 | BOH | 42345 | 42346 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3893 | surface preparation and repair for beam axis B18 to B19/A15 | Repair | Beam | -3.80 to 1.10 | BOH | 42345 | 42368 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3894 | top layer steel reinforcement for third stage of post tension slab axis B13 to B18/A6 to A12 | Steel Reinforcement | Slab | 15.20 | 3rd | 42346 | 42349 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3895 | steel reinforcement for core 2 slab axis A8 to A10/B14 to B16 | Steel Reinforcement | Slab | 15.20 | 3rd | 42346 | 42349 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3896 | ducts grouting for the second post tension slab axisB9 to B13/A6 to A12 | Grout | Slab | 15.20 | 3rd | 42346 | 42352 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3897 | form work for stair case 12 axis A2/B1 | Form Work | Stair | 21.80 to 25.10 | Typical Floor | 42346 | 42349 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3898 | (Tendons- strands- anchors- profiles) for third stage post tension slab at R.D tower | Cables | Slab | 15.20 | 3rd | 42346 | 42348 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3899 | steel reinforcement for pour strip between first and second post tension axis B9/A6 to A12 | Steel Reinforcement | Slab | 15.20 | 3rd | 42346 | 42347 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3900 | drilling and fixation for dowels at core 7 slab axis C7/A2 to A3 | Dowels | Slab | 21.80 | Typical Floor | 42346 | 42352 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3901 | form work for driver stair case axis B19 to B20/A15 to A14 | Form Work | Column | -11.00 to -7.20 | B2 | 42346 | 42348 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3902 | bottom layer steel reinforcement for slab at axis B12 to B13/A3 to A4 | Form Work | Slab | 1.10 | BOH | 42346 | 42348 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3903 | top layer steel reinforcement for slab at axis B12 to B13/A3 to A4 | Form Work | Slab | 1.10 | BOH | 42346 | 42348 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3904 | check reinforcement details and cleaning for pits prior to pouring concrete for the pits of wells No. 7, 8, 11, 13, 14 | Dewatering | Reinforcement | -11.00 | B2 | 42347 | 42357 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3905 | check reinforcement details and cleaning for pits prior to pouring concrete for the pits of wells No. 1, 5, 6, 9, 10 | Dewatering | Reinforcement | -11.00 | B2 | 42345 | 42357 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3906 | steel reinforcement for core 2 axis A8 to A10/B14 to B16 | Steel Reinforcement | Core | 20.10 to 23.40 | Typical Floor | 42348 | 42352 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3907 | bottom layer steel reinforcement for first stage of post tension slab axis B1 to C5/A1 to A3 | Steel Reinforcement | Slab | 25.10 | Typical Floor | 42348 | 42349 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3908 | top layer steel reinforcement for first stage of post tension slab axis B1 to C5/A1 to A3 | Steel Reinforcement | Slab | 25.10 | Typical Floor | 42348 | 42349 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3909 | (Tendons- strands- anchors- profiles) for first stage post tension slab at Hotel axis B1 to C5/A1 to A3 | Cables | Slab | 25.10 | Typical Floor | 42348 | 42350 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3910 | check reinforcement details and cleaning for pits prior to pouring concrete for the pits of wells No. WB, WC, WD, WE, WF, WG | Dewatering | Reinforcement | -11.00 | B2 | 42348 | 42367 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3911 | fixation of shear connectors for 2 double columns CC1 axis B13/A11-A10 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42350 | 42353 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3912 | fixation of shear connectors for 1 double column CC1* axis A8/B13 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42350 | 42353 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3913 | fixation of shear connectors for 6 columns CC4 axis D1, D2, D3, D4, A9/B19& B16/A10 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42350 | 42354 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3914 | steel reinforcement for shear wall 1 axis B1 to B5/A1 | Steel Reinforcement | SHW | 30.70 to 34 | Typical Floor | 42350 | 42352 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3915 | form work for shear wall 1 axis B1 to B5/A1 | Form Work | SHW | 30.70 to 34 | Typical Floor | 42350 | 42352 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3916 | tendons- strands- anchors- profiles for first stage of post tension slab at R.D tower axis B4 to B9/A6 to A12 | Cables | Slab | 20.10 | Typical Floor | 42351 | 42357 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3917 | steel reinforcement for first stage of post tension slab axis A6 to A12/B4 to B9 | Steel Reinforcement | Slab | 20.10 | Typical Floor | 42351 | 42357 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3918 | fixation for shear connectors for 1 column CC7 axis B13/A6 east side | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42351 | 42354 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3919 | installation (torque) for 1 column CC7 axis B13/A6 east side | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42351 | 42353 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3920 | form work for core 3 axis B10 to B12/A8 to A10 | Form Work | Core | 20.10 to 23.40 | Typical Floor | 42351 | 42366 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3921 | steel reinforcement for shear wall 8 axis C2/A1 to A3 | Steel Reinforcement | SHW | 25.10 to 28.40 | Typical Floor | 42351 | 42352 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3922 | installation (torque) for 1 column CC7 axis A12/B16 | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42352 | 42354 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3923 | installation (torque) for 1 column CC7 axis A6/B13 east side | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42352 | 42354 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3924 | installation (torque) for 1 column CC7 axis A6/B16 | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42352 | 42353 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3925 | installation (torque) for 1 column CC7 axis B14/A6 | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42352 | 42353 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3926 | form work for 1 column CC4 axis A10/B16 | Form Work | Column | 15.20 to 20.10 | 3rd | 42352 | 42358 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3927 | steel reinforcement for 1 column CC4 axis A10/B16 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42352 | 42357 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3928 | steel reinforcement for 1 column CC4 axis D1 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42352 | 42357 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3929 | form work for 1 column CC4 axis D1 | Form Work | Column | 15.20 to 20.10 | 3rd | 42352 | 42357 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3930 | steel reinforcement for 1 column CC4 axis D4 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42352 | 42354 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3931 | form work for 1 column CC4 axis D4 | Form Work | Column | 15.20 to 20.10 | 3rd | 42352 | 42357 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3932 | steel reinforcement for core 1 axis A8/B16-B17 | Steel Reinforcement | core | 15.20 to 20.10 | 3rd | 42352 | 42357 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3933 | form work for core 1 axis A8 to A10/B16 to B18 | Form Work | core | 15.20 to 20.10 | 3rd | 42352 | 42373 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3934 | steel reinforcement for 1 column CC4 axis D2 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42352 | 42354 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3935 | form work for 1 column CC4 axis D2 | Form Work | Column | 15.20 to 20.10 | 3rd | 42352 | 42354 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3936 | steel reinforcement for 1 column CC4 axis A9/B19 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42352 | 42357 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3937 | form work for 1 column CC4 axis A9/B19 | Form Work | Column | 15.20 to 20.10 | 3rd | 42352 | 42358 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3938 | steel reinforcement for 1 column CC4 axis D3 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42352 | 42354 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3939 | form work for 1 colum CC4 axis D3 | Form Work | Column | 15.20 to 20.10 | 3rd | 42352 | 42354 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3940 | steel reinforcement for 2 columns CC1 axis B13/A10-A11 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42352 | 42357 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3941 | form work for 2 columns CC1 axis B13/A10-A11 | Form Work | Column | 15.20 to 20.10 | 3rd | 42352 | 42357 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3942 | steel reinforcement for 1 double column CC1* axis A8/B13 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42352 | 42357 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3943 | form work for 1 double column CC1* axis A8/B13 | Form Work | Column | 15.20 to 20.10 | 3rd | 42352 | 42359 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3944 | form work for stair case 7 axis A10/B10-B11 | Form Work | Stair | 10.30 to 15.20 | Second Floor | 42352 | 42357 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3945 | steel reinforcement for core 5 slab axis A8 to A10/B6 to B8 | Steel Reinforcement | Slab | 20.10 | Typical Floor | 42352 | 42357 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3946 | form work for shear wall 8 axis C2/A2 to A3 | Form Work | SHW | 25.10 to 28.40 | Typical Floor | 42352 | 42357 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3947 | grouting of ducts at second pour strip at Hotel tower axis B19 to B15/A1 to A3 | Grout | Slab | 18.50 | Typical Floor | 42353 | 42357 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3948 | stressing of slab at first pour strip at Hotel tower axis B1 to B5/A1 to A3 | Stressing | Slab | 25.10 | Typical Floor | 42353 | 42358 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3949 | form wrok for 3 columns CC7 axis A6/B14-B16& A12/B16 | Form Work | Column | 15.20 to 20.10 | 3rd | 42353 | 42358 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3950 | steel reinforcement for 3 columns CC7 axis A6/B14-B16& A12/B16 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42353 | 42357 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3951 | form work removal at second pour strip at Hotel tower axis B19 to C5/A1 to A3 | Removing Form Work | Slab | 18.50 | Typical Floor | 42353 | 42357 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3952 | stressing of strands for third stage post tension slab at R.D tower axis B13 to B18/A6 to A12 | Stressing | Slab | 15.20 | 3rd | 42353 | 42359 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3953 | steel reinforcement for driver stair case axis B19 to B20/A15 to A14 | Steel Reinforcement | Column | -11.00 to -7.20 | B2 | 42353 | 42361 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3954 | tendons- strands- anchors- profiles for second stage of post tension slab at Hotel tower axis B5 to B19/A1 to A3 | Cables | Slab | 21.80 | Typical Floor | 42354 | 42357 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3955 | bottom layer steel reinforcement for second stage slab axis B19 to B5/A1 to A3 at Hotel tower | Steel Reinforcement | Slab | 21.80 | Typical Floor | 42354 | 42357 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3956 | top layer steel reinforcement for second stage slab axis B19 to B5/A1 to A3 at Hotel tower | Steel Reinforcement | Slab | 21.80 | Typical Floor | 42354 | 42357 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3957 | form work for 1 column CC9 axis A11/B14 | Form Work | Column | 15.20 to 20.10 | 3rd | 42354 | 42359 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3958 | fixation of shear connectors for 1 column CC9 axis A11/B14 | Shear Connectors | Column | 15.20 to 20.10 | 3rd | 42354 | 42357 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3959 | installation (torque) for 1 column CC9 axis A11/B14 | Composite Columns | Column | 15.20 to 20.10 | 3rd | 42354 | 42357 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3960 | steel reinforcement for 1 column CC9 axis A11/B14 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42354 | 42357 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3961 | form work for 1 double column CC7 axis B13/A6 | Form Work | Column | 15.20 to 20.10 | 3rd | 42354 | 42361 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3962 | steel reinforcement for 1 double column CC7 axis B13/A6 | Steel Reinforcement | Column | 15.20 to 20.10 | 3rd | 42354 | 42357 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3963 | fixation for shear connectors for 2 columns CC9 axis A11/B6-B8 | Shear Connectors | Column | 20.10 to 23.40 | 3rd | 42354 | 42359 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3964 | installation (torque) for 2 columns CC9 axis A11/B6-B8 | Composite Columns | Column | 20.10 to 23.40 | 3rd | 42354 | 42359 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3965 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3966 | form work for stair case 4 axis B7 to B8/A10 | Form Work | Stair | -7.20 to -3.80 | B2 | 42354 | 42358 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3967 | check reinforcement details and cleaning for pits prior to pouring concrete for the pits of wells No. 12 | Dewatering | Reinforcement | -11.00 | B2 | 42357 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3968 | form work for core 2 axis A8 to A10/B14 to B16 | Form Work | Core | 19 to 22.30 | Typical Floor | 42357 | 42369 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3969 | steel reinforcement for shear wall 1 axis B11 to B19/A1 | Steel Reinforcement | SHW | 27.80 to 31.10 | Typical Floor | 42357 | 42359 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3970 | steel reinforcement for shear wall 3 axis C6/A2 to A3 | Steel Reinforcement | SHW | 21.80 to 25.10 | Typical Floor | 42359 | 42359 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3971 | steel reinforcement for shear wall 5 axis C5/A1 to A3 | Steel Reinforcement | SHW | 21.80 to 25.10 | Typical Floor | 42359 | 42359 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3972 | steel reinforcement for shear wall 6 axis C4/A2 to A3 | Steel Reinforcement | SHW | 34.90 to 38.20 | Typical Floor | 42359 | 42361 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3973 | steel reinforcement for shear wall 7 axis C3/A2 to A3 | Steel Reinforcement | SHW | 34.90 to 38.20 | Typical Floor | 42359 | 42361 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3974 | stressing for firsat satge cables axis B4 to B9/A6 to A12 | Stressing | Slab | 20.10 | Typical Floor | 42359 | 42366 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3975 | steel reinforcement for stair case 7 axis B12 to B13/A7 to A9 | Steel Reinforcement | Stair | 10.30 to 15.20 | Second Floor | 42359 | 42365 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3976 | steel reinforcement for 3 columns CC7 axis A6/B5-B6-B8 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42364 | 42365 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3977 | steel reinforcement for panoramic beam s axis B9 to B10/A5 to A6 | Steel Reinforcement | Beam | 20.10 | Typical Floor | 42359 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3978 | installation (torque) for 1 column CC1 axis B9/A10 west side | Composite Columns | Column | 20.10 to 23.40 | Typical Floor | 42359 | 42359 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3979 | installation (torque) for 2 columns CC9 axis A11/B10-B12 | Composite Columns | Column | 20.10 to 23.40 | Typical Floor | 42359 | 42360 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3980 | fixation of shear connectors for 2 columns CC9 axis A11/B10-B12 | Composite Columns | Column | 20.10 to 23.40 | Typical Floor | 42357 | 42360 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3981 | steel reinforcement for stair case 10 axis B14 to B15/A8 to A9 | Steel Reinforcement | Stair | -11.00 to -7.20 | B2 | 42359 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3982 | installation (Torque) for 1 column CC1 axis B9/A10 east side | Composite Columns | Column | 20.10 to 23.40 | Typical Floor | 42359 | 42359 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3983 | fixation of shear connectors for 1 double column CC1 axis B9/A10 | Shear Connectors | Column | 20.10 to 23.40 | Typical Floor | 42359 | 42359 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3984 | dowels drilling and fixation for shear wall 7 axis C3/A2 to A3 | Dowels | SHW | 34.90 | Typical Floor | 42359 | 42361 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3985 | dowels drilling and fixation for shear wall 6 axis C4/A2 to A3 | Dowels | SHW | 34.90 | Typical Floor | 42359 | 42361 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3986 | steel reinforcement for shear wall 2 axis C10/A2 to A3 residential side | Steel Reinforcement | SHW | 21.80 to 25.10 | Typical Floor | 42360 | 42361 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3987 | form work for shear wall 1 axis B11 to B19/A1 | Form Work | SHW | 28.00 to 31.30 | Typical Floor | 42360 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3988 | fixation of shear connector for CC5 axis C9/A3 | Shear Connectors | Column | 21.80 to 25.10 | Typical Floor | 42360 | 42361 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3989 | fixation of shear connectors for 1 column CC6 axis C11/A3 | Shear Connectors | Column | 21.80 to 25.10 | Typical Floor | 42360 | 42361 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3990 | installation (torque) for 1 column CC1* axis A8/B13 east side | Composite Columns | Column | 20.10 to 23.40 | Typical Floor | 42368 | 42369 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3991 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3992 | check reinforcement details and cleaning for pits prior to pouring concrete for the pits of wells No. WA, W15, W4 | Dewatering | Reinforcement | -11.00 | B2 | 42360 | 42383 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3993 | form work for shear wall 5/5* axis C5/A2 to A3 | Form Work | SHW | 21.80 to 25.10 | Typical Floor | 42360 | 42361 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3994 | form work for shear wall 3 axis C6/A2 to A3 | Form Work | SHW | 21.80 to 25.10 | Typical Floor | 42360 | 42361 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3995 | form work for shear wall 6 axis C4/A2 to A3 | Form Work | SHW | 35 to 38.30 | Typical Floor | 42360 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3996 | steel reinforcement for shear wall 3*/2* axis C8/A2 to A3 | Steel Reinforcement | SHW | 21.80 to 25.10 | Typical Floor | 42360 | 42361 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3997 | form work for shear wall 7 axis C3/A2 to A3 | Form Work | SHW | 35 to 38.30 | Typical Floor | 42360 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3998 | steel reinforcement for pour strip between second and third stage at R.D tower axis B13/A6 to A12 | Steel Reinforcement | Slab | 15.20 | 3rd | 42360 | 42360 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-3999 | ducts grouting for third post tension slab at R.D tower axis B13 to B18/A6 to A12 | Grout | Slab | 15.20 | 3rd | 42360 | 42360 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4000 | form work for shear wall 2*/3* axis C8/A2 to A3 | Form Work | SHW | 21.80 to 25.10 | Typical Floor | 42360 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4001 | form work for shear wall 2 axis C10/A2 to A3 residential side | Form Work | SHW | 21.80 to 25.10 | Typical Floor | 42360 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4002 | installation (torque) for 1 column CC1 axis B9/A8 | Composite Columns | Column | 20.10 to 23.40 | Typical Floor | 42361 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4003 | fixation of shear connector for 1 column CC1 axis B9/A8 | Shear Connectors | Column | 20.10 to 23.40 | Typical Floor | 42361 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4004 | installation (torque) for 1 double column CC3 axis B9/A11 | Composite Columns | Column | 20.10 to 23.40 | Typical Floor | 42361 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4005 | fixation for shear connectors for 1 double column CC3 axis B9/A11 | Shear Connectors | Column | 20.10 to 23.40 | Typical Floor | 42361 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4006 | steel reinforcement for 1 column CC5 axis C9/A2 to A3 | Steel Reinforcement | Column | 21.80 to 25.10 | Typical Floor | 42361 | 42366 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4007 | steel reinforcement for 1 column CC6 axis C11/A2 to A3 | Steel Reinforcement | Column | 21.80 to 25.10 | Typical Floor | 42361 | 42366 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4008 | steel reinforcement for shear wall 1 and column C1 axis B19 to B20/A1 | Steel Reinforcement | SHW | 21.80 to 25.10 | Typical Floor | 42361 | 42364 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4009 | form work for 1 column CC5 axis C9/A2 to A3 | Form Work | Column | 21.80 to 25.10 | Typical Floor | 42361 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4010 | form work for 1 column CC6 axis C11/A2 to A3 | Form Work | Column | 21.80 to 25.10 | Typical Floor | 42361 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4011 | form work for shear wall 1 and 1 column C1 axis B19 to B20/A1 | Form Work | SHW | 21.80 to 25.10 | Typical Floor | 42361 | 42366 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4012 | stressing for cables for second stage post tension slab axis B6 to B19/A1 to A3 | Stressing | Slab | 21.80 | Typical Floor | 42361 | 42366 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4013 | steel reinforcement for stair case 4 axis A10/B7 to B8 | Steel Reinforcement | Stair | -7.20 to -3.80 | B2 | 42361 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4014 | steel reinforcement for 2 columns CC9 axis A11/B6-B8 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42361 | 42364 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4015 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4016 | surface preparation for area at axis B14/A15 to A13 | Repair |  | -3.80 to 1.10 | BOH | 42361 | 42364 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4017 | repair for area at axis B14/A15 to A13 | Repair |  | -3.80 to 1.10 | BOH | 42361 | 42368 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4018 | steel reinforcement for pouring strip between first and second stage at hotel tower axis C4 to C5/A1 to A3 | Steel Reinforcement | Slab | 18.50 | Typical Floor | 42364 | 42366 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4019 | steel reinforcement for modification of core 2 according to transmittal 1159 axis B14 to B16/A7 to A10 | Steel Reinforcement | Core | 20.10 to 23.40 | Typical Floor | 42365 | 42379 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4020 | steel reinforcement for modification of core 5 according to transmittal 1159 axis B6 to B8/A8 to A10 | Steel Reinforcement | Core | 23.40 to 26.70 | Typical Floor | 42365 | 42366 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4021 | steel reinforcement for 4 columns axis B4/A8-A9-A10-A11 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42364 | 42366 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4022 | steel reinforcement for modification of core 3 according to transmittal 1159 axis B10 to B12/A8 to A10 | Steel Reinforcement | Core | 20.10 to 23.40 | Typical Floor | 42365 | 42366 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4023 | form work for 2 columns CC9 axis A11/B6-B8 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42365 | 42367 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4024 | form work for 3 columns CC7 axis B4/A9-A10-A11 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42365 | 42367 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4025 | surface preparation and repair for first post tension slab axis B4 to B9/A6 to A12 at R.D tower | Repair | Slab | 20.10 | Typical Floor | 42365 | 42366 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4026 | steel reinforcement for core 7 axis C7/A2-A3 | Steel Reinforcement | Core | 30.90 to 34.20 | Typical Floor | 42365 | 42366 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4027 | raising stress up to 5% for P.T cables for slab first stage CABLES NO. 21-21A-33-24-25-26-27-28 axis B1 to B6/A1 to A3 | Stressing | Slab | 25.10 | Typical Floor | 42366 | 42366 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4028 | duct grouting for first post tension slab at R.D tower axis A6 to A12/B4 to B8 | Grout | Slab | 20.10 | Typical Floor | 42366 | 42367 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4029 | fixation of shear connectors for 5 column CC4 axis D4-D3- D2- D1- A9/B19 | Shear Connectors | Column | 20.10 to 23.40 | Typical Floor | 42366 | 42367 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4030 | installation (torque) for 5 column CC4 axis D4-D3- D2- D1- A9/B19 | Shear Connectors | Column | 20.10 to 23.40 | Typical Floor | 42366 | 42367 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4031 | form work for stair case 14 axis A2/B15 to B17 | Form Work | Stair | 15.20 to 18.50 | 3rd | 42366 | 42367 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4032 | steel reinforcement for stair case 14 axis A2/B15 to B17 | Form Work | Stair | 15.20 to 18.50 | 3rd | 42366 | 42371 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4033 | steel reinforcement for core 6 axis B15 to B17/A1 to A2 | Steel Reinforcement | Core | 21.80 to 25.10 | Typical Floor | 42366 | 42371 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4034 | steel reinforcement for shear wall 2 axis C10/A2 to A3 residential side | Steel Reinforcement | SHW | 21.80 to 25.10 | Typical Floor | 42366 | 42367 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4035 | steel reinforcement for column C5 axis B18/A2 to A3 | Steel Reinforcement | Column | 21.80 to 25.10 | Typical Floor | 42366 | 42367 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4036 | form work for core 7 axis A2 to A3/C7 | Form Work | Core | 30.90 to 34.20 | Typical Floor | 42366 | 42367 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4037 | form work for core 6 axis A1 to A2/B15 to B17 | Form Work | Core | 21.80 to 25.10 | Typical Floor | 42366 | 42369 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4038 | form work for column C5 axis B18/A2 to A3 | Form Work | Column | 21.80 to 25.10 | Typical Floor | 42366 | 42367 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4039 | form work for shear wall 2 axis C10/A2 to A3 residential side | Form Work | SHW | 21.80 to 25.10 | Typical Floor | 42366 | 42367 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4040 | installation (torque) for 2 columns CC1 axis B13/A10-A11 east side | Composite Columns | Column | 20.10 to 23.40 | Typical Floor | 42368 | 42369 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4041 | fixation for shear connectors for 2 columns CC1 axis B13/A10-A11 east | Shear Connectors | Column | 20.10 to 23.40 | Typical Floor | 42367 | 42374 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4042 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4043 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4044 | form work removing for first stage slab at hotel axis B1 to B5/A1 to A3 | Removing Form Work | Slab | 25.10 | Typical Floor | 42367 | 42372 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4045 | duct grouting for first post tension slab at Hotel tower axis A6 to A12/B4 to B8 | Grout | Slab | 25.10 | Typical Floor | 42367 | 42371 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4046 | form work for stair case 6 axis B10 to B11/A8 to A9 | Form Work | Stair | 15.20 to 20.10 | 3rd | 42369 | 42372 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4047 | steel reinforcement for beam 7 at third post tension slab axis A6 to A10/B13 | Steel Reinforcement | Beam | 20.10 | Typical Floor | 42369 | 42373 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4048 | installation (torque) for 1 column CC1* axis A8/B13 west side | Composite Columns | Column | 20.10 to 23.40 | Typical Floor | 42369 | 42374 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4049 | installation (torque) for 2 columns CC1 axis A10-A11/B13 west side | Composite Columns | Column | 20.10 to 23.40 | Typical Floor | 42369 | 42374 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4050 | bottom layer steel reinforcement for hotel slab first stage axis B1 to B5/A1 to A3 | Steel Reinforcement | Slab | 28.40 | Typical Floor | 42369 | 42371 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4051 | steel reinforcement for stair case 12 axis B1/A2 | Steel Reinforcement | Stair | 21.80 to 25.10 | Typical Floor | 42369 | 42373 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4052 | tendons- strands- anchors- profiles for first stage of post tension slab at Hotel tower axis B5 to B1/A1 to A3 | Cables | Slab | 28.40 | Typical Floor | 42369 | 42371 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4053 | top layer steel reinforcement for post tension slab first stage at hotel axis B1 to C5/A1 to A3 | Steel Reinforcement | Slab | 28.40 | Typical Floor | 42369 | 42371 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4054 | steel reinforcement for placing boom opening axis C9 to C10/A2 to A3 | Steel Reinforcement |  | 5.40 | First Floor | 42369 | 42374 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4055 | restressing by 5% for 15 cables No. 1- 2- 4- 5- 7- 8- 9- 11- 13-15- 16- 2c- 2d- 16a at second stage Hotel slab | Cables | Slab | 21.80 | Typical Floor | 42374 | 42378 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4056 | bottom layer steel reinforcement for second stage of post tension slab at R.D tower axis B9 to B13/A6 to A12 | Steel Reinforcement | Slab | 20.10 | Typical Floor | 42371 | 42375 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4057 | steel reinforcement for stair case 6 axis B10 to B11/A8 to A9 | Steel Reinforcement | Stair | 15.20 to 20.10 | 3rd | 42371 | 42378 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4058 | steel reinforcement for core 3 axis A8 to A10/B10 to B12 | Steel Reinforcement | Core | 23.40 to 26.70 | Typical Floor | 42372 | 42379 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4059 | steel reinforcement for beam of driver stair case | Steel Reinforcement | Beam | -7.20 to -3.80 | B1 | 42371 | 42373 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4060 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4061 | drilling and fixation of dowels for core 7 axis C7/A2 to A3 | Dowels | Core | 21.80 | Typical Floor | 42372 | 42374 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4062 | steel reinforcement for shear wall 8 axis C2/A2 to A3 | Steel Reinforcement | SHW | 28.40 to 31.70 | Typical Floor | 42372 | 42374 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4063 | form work for beam of driver stair case | Form Work | Beam | -7.20 to -3.80 | B1 | 42372 | 42374 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4064 | form work for core 2 axis B14 to B15/A8 to A10 | Form Work | Core | 22.30 to 23.40 | Typical Floor | 42373 | 42383 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4065 | steel reinforcement for columns gas room axis B20 to B21/A1 to A3 | Steel Reinforcement | Column | 1.10 | BOH | 42373 | 42375 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4066 | form work removal for first stage slab at R.D tower axis B4 to B9/A6 to A12 | Removing Form Work | Slab | 20.10 | Typical Floor | 42373 | 42379 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4067 | form work for stair case 3 axis B6 to B7/A8 to A9 | Form Work | Stair | 20.10 to 23.40 | Typical Floor | 42373 | 42375 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4068 | stressing of strands for first stage post tension slab at Hotel axis B1 to C5/A1 to A3 | Stressing | Slab | 28.40 | Typical Floor | 42373 | 42378 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4069 | steel reinforcement for core 3 slab axis A10 to A8/B10 to B12 | Steel Reinforcement | Slab | 20.10 | Typical Floor | 42374 | 42375 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4070 | top layer steel reinforement for second stage of post tension slab of R.D tower axis B9 to B13/A6 to A12 | Steel Reinforcement | Slab | 20.10 | Typical Floor | 42374 | 42375 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4071 | tendons- strands- anchors- profiles for second stage of post tension slab at R.D tower axis B9 to B13/A6 to A12 | Cables | Slab | 20.10 | Typical Floor | 42374 | 42379 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4072 | form work for shear wall 8 axis C2/A2 to A3 | Form Work | SHW | 28.40 to 31.70 | Typical Floor | 42374 | 42375 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4073 | form work for columns gas room axis B20 to B21/A1 to A3 | Form Work | Column | 1.10 | BOH | 42375 | 42378 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4074 | steel reinforcement for 1 double column CC3 axis B9/A11 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42378 | 42379 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4075 | steel reinforcement for 1 double column CC1 axis B9/A10 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42378 | 42379 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4076 | steel reinforcement for shear wall 9 and 1 column CC1 axis A8 to A9/B9 | Steel Reinforcement | SHW | 20.10 to 23.40 | Typical Floor | 42378 | 42379 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4077 | steel reinforcement for 1 double column CC7 axis B9/A6 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42378 | 42379 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4078 | steel reinforcement for 2 columns CC7 axis A6/B10-B12 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42378 | 42381 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4079 | steel reinforcement for 2 double columns CC9 axis A11/B10-B12 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42378 | 42379 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4080 | top layer steel reinforcement for second stage post tension slab axis C5 to B19/A1 to A3 | Steel Reinforcement | Slab | 25.10 | Typical Floor | 42378 | 42381 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4081 | bottom layer steel reinforcement for second stage post tension slab axis C5 to B19/A1 to A3 | Steel Reinforcement | Slab | 25.10 | Typical Floor | 42378 | 42381 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4082 | tendons- strands- anchors- profiles for second stage of post tension slab at hotel tower axis C5 to B19/A1 to A3 | Cables | Slab | 25.10 | Typical Floor | 42378 | 42381 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4083 | steel reinforcement for core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | Core | 26.70 to 30 | Typical Floor | 42378 | 42381 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4084 | steel reinforcement for stair case 3 axis B6 to B7/A8 | Steel Reinforcement | Stair | 20.10 to 23.40 | Typical Floor | 42379 | 42383 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4085 | stressing of strands for second stage post tension slab axis B9 to B13/A6 to A12 | Stressing | Slab | 20.10 | Typical Floor | 42379 | 42383 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4086 | form work for driver stair case axis B19 to B20/A15 to A14 | Form Work | Stair | -7.20 to -3.80 | Typical Floor | 42379 | 42390 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4087 | form work for first stage of slab of R.D tower axis A6 to A12/B4 to B8 | Form Work | Slab | 23.40 | Typical Floor | 42379 | 42381 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4088 | form work for shear wall 9 and 1 column CC1 axis A8 to A9/B9 | Form Work | SHW | 20.10 to 23.40 | Typical Floor | 42379 | 42381 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4089 | form work for double column CC7 axis A6/B9 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42379 | 42381 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4090 | form work for double column CC1 axis A10/B9 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42379 | 42381 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4091 | form work for double column CC3 axis A11/B9 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42379 | 42381 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4092 | form work for 2 columns CC9 axis A11/B10-B12 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42379 | 42381 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4093 | form work for 2 columns CC7 axis A6/B10-B12 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42379 | 42383 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4094 | form work for stair case 11 axis B16 to B17/A9 | Form Work | Stair | 15.20 to 20.10 | 3rd | 42380 | 42383 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4095 | form work for stair case 7 axis A10/B10-B11 | Form Work | Stair | 15.20 to 20.10 | 3rd | 42380 | 42383 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4096 | form work for core 3 axis B10 to B12/A8 to A10 | Form Work | Core | 23.40 to 26.70 | Typical Floor | 42380 | 42383 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4097 | steel reinforcement for shear wall 1 axis B6 to B19/A1 | Steel Reinforcement | SHW | 31.70 to 34 | Typical Floor | 42380 | 42381 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4098 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4099 | top and bottom layers steel reinforcement for first stage post tension slab at R.D tower axis B4 to B9/A6 to A12 | Steel Reinforcement | Slab | 23.40 | Typical Floor | 42381 | 42383 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4100 | form work for third stage of slab of R.D tower axis A6 to A12/B4 to B8 | Form Work | Slab | 20.10 | Typical Floor | 42381 | 42383 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4101 | grouting for second stage slab at Hotel axis C5 to B19/A1 to A3 | Grout | Slab | 21.80 | Typical Floor | 42381 | 42383 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4102 | form work for stair case 12 axis A2/B1 | Form Work | Stair | 21.80 to 25.10 | Typical Floor | 42381 | 42386 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4103 | form work for slab of gas room axis A3 to A2/B20 to B21 | Form Work | Slab | 3.45 | First Floor | 42381 | 42383 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4104 | steel reinforcement for slab of gas room axis A3 to A2/B20 to B21 | Steel Reinforcement | Slab | 3.45 | First Floor | 42381 | 42383 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4105 | form work for shear wall 1 axis B6 to B10/A1 | Form Work | SHW | 31.70 to 34 | Typical Floor | 42382 | 42383 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4106 | steel reinforcement for pour strip axis B6 to B7/A1 to A3 | Steel Reinforcement | Slab | 21.80 | Typical Floor | 42382 | 42385 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4107 | top and bottom layer steel reinforcement for slab of core 5 axis A10/B10-B11 | Steel Reinforcement | Slab | 20.10 | 3rd | 42382 | 42383 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4108 | tendons- strands- anchors and profiles for first stage of post tension slab at R.D tower axis A6 to A12/B4 to B8 | Cables | Slab | 23.40 | Typical Floor | 42382 | 42386 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4109 | steel reinforcement for stair case 7 axis B12 to B13/A7 to A9 | Steel Reinforcement | Stair | 15.20 to 20.10 | 3rd | 42382 | 42392 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4110 | steel reinforcement for stair case 11 axis B17/A9 | Steel Reinforcement | Stair | 15.20 to 20.10 | 3rd | 42382 | 42387 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4111 | steel reinforcement for shear wall 5/5* axis C5/A2 to A3 | Steel Reinforcement | SHW | 25.10 to 28.40 | Typical Floor | 42383 | 42383 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4112 | steel reinforcement for shear wall 3 axis C6/A2 to A3 | Steel Reinforcement | SHW | 25.10 to 28.40 | Typical Floor | 42383 | 42383 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4113 | steel reinforcement for shear wall 2 axis C10/A2 to A3 residential side | Steel Reinforcement | SHW | 25.10 to 28.40 | Typical Floor | 42383 | 42383 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4114 | steel reinforcement for core 8 axis B1/A2 to A3 | Steel Reinforcement | Core | 33.30 to 36.60 | Typical Floor | 42383 | 42386 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4115 | form work for shear wall 5/5* axis C5/A2 to A3 | Form Work | SHW | 25.10 to 28.40 | Typical Floor | 42383 | 42386 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4116 | form work for shear wall 3 axis C6/A2 to A3 | Form Work | SHW | 25.10 to 28.40 | Typical Floor | 42383 | 42386 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4117 | form work for shear wall 2 axis C10/A2 to A3 residential side | Form Work | SHW | 25.10 to 28.40 | Typical Floor | 42383 | 42387 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4118 | steel reinforcement for shear wall 3*/2* axis C8/A2 to A3 | Steel Reinforcement | SHW | 25.10 to 28.40 | Typical Floor | 42383 | 42385 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4119 | form work for shear wall 3*/2* axis C8/A2 to A3 | Form Work | SHW | 25.10 to 28.40 | Typical Floor | 42383 | 42386 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4120 | installation (Torque) for columns CC5& CC6 axis A3/C11-C9 | Composite Columns | Column | 25.10 to 28.40 | Typical Floor | 42385 | 42386 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4121 | fixation for shear connectors for columns CC5& CC6 axis A3/C11-C9 | Shear Connectors | Column | 25.10 to 28.40 | Typical Floor | 42385 | 42387 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4122 | stressing for cables of post tension for second stage slab axis B6 to B19/A1 to A3 | Stressing | Slab | 25.10 | Typical Floor | 42385 | 42387 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4123 | steel reinforcement for shear wall 2 axis C10/A2 to A3 outer side | Steel Reinforcement | SHW | 25.10 to 28.40 | Typical Floor | 42385 | 42387 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4124 | form work for shear wall 2 axis C10/A2 to A3 outer side | Form Work | SHW | 25.10 to 28.40 | Typical Floor | 42385 | 42387 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4125 | form work for core 5 axis A8 to A10/B6 to B8 | Form Work | Core | 26.70 to 30 | Typical Floor | 42385 | 42387 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4126 | tendons- strands- anchors and profiles for third stage of post tension slab at R.D tower axis A6 to A12/B13 to B18 | Cables | Slab | 20.10 | Typical Floor | 42385 | 42388 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4127 | top and bottom layers steel reinforcement for third stage of post tension slab at R.D tower axis A6 to A12/B13 to B18 | Steel Reinforcement | Slab | 20.10 | Typical Floor | 42385 | 42388 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4128 | steel reinforcement for shear wall 1 and column C1 axis B19 to B20/A1 | Steel Reinforcement | SHW | 25.10 to 28.40 | Typical Floor | 42386 | 42387 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4129 | form work for shear wall 1 and column C1 axis B19 to B20/A1 | Form Work | SHW | 25.10 to 28.40 | Typical Floor | 42386 | 42390 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4130 | drilling and fixation for dowels of core 6 axis B15 to B17/A1 | Dowels | Core | 25.10 to 28.40 | Typical Floor | 42386 | 42387 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4131 | steel reinforcement for column C5 axis B18/A1 | Steel Reinforcement | Column | 25.10 to 28.40 | Typical Floor | 42386 | 42387 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4132 | form work for column C5 axis B18/A1 | Form Work | Column | 25.10 to 28.40 | Typical Floor | 42386 | 42388 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4133 | groutig for cables at second stage of post tension slab at R.D tower axis A6 to A12/B9 to B12 | Grout | Slab | 20.10 | Typical Floor | 42386 | 42392 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4134 | form work for gas room beams axis A1 to A3/B20 to B21 | Form Work | Beam | 4.45 | BOH | 42386 | 42392 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4135 | steel reinforcement for columns of RMU room axis A14 to A15/B20 to B21 | Steel Reinforcement | Column | 1.10 to 4.45 | BOH | 42386 | 42387 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4136 | form work for columns of RMU room axis A14 to A15/B20 to B21 | Form Work | Column | 1.10 to 4.45 | BOH | 42386 | 42387 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4137 | steel reinforcement for column CC5 axis C9/A3 | Steel Reinforcement | Column | 25.10 to 28.40 | Typical Floor | 42386 | 42387 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4138 | steel reinforcement for column CC6 axis C11/A3 | Steel Reinforcement | Column | 25.10 to 28.40 | Typical Floor | 42386 | 42387 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4139 | form work for column CC5 axis C9/A3 | Form Work | Column | 25.10 to 28.40 | Typical Floor | 42386 | 42387 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4140 | form work for column CC6 axis C11/A3 | Form Work | Column | 25.10 to 28.40 | Typical Floor | 42386 | 42387 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4141 | form work removal for second stage pour strip axis A12 to A6/B9 to B12 | Removing Form Work | Slab | 20.10 | Typical Floor | 42386 | 42387 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4142 | steel reinforcement for pour strip between first and second strip at R.D tower axis A6 to A12.B9 | Steel Reinforcement | Slab | 20.10 | Typical Floor | 42387 | 42392 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4143 | steel reinforcement for core 6 axis B15 to B17/A1 to A2 | Steel Reinforcement | Core | 25.10 to 28.40 | Typical Floor | 42387 | 42387 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4144 | form work for core 8 axis A2 to A3/B1 | Form Work | Core | 33.40 to 36.70 | Typical Floor | 42387 | 42387 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4145 | grouting for first stage of post tension slab at Hotel axis B1 to B6/A1 to A3 | Grout | Slab | 28.40 | Typical Floor | 42388 | 42390 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4146 | Form work for core 6 axis B15 to B17/A1 to A2 | Form Work | Core | 25.10 to 28.40 | Typical Floor | 42388 | 42392 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4147 | steel reinforcement for 2 columns CC9A axis A11/B6-B8 | Steel Reinforcement | Column | 23.40 to 26.70 | Typical Floor | 42388 | 42389 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4148 | form work for 2 columns CC9A axis A11/B6-B8 | Form Work | Column | 23.40 to 26.70 | Typical Floor | 42388 | 42392 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4149 | form work for 4 columns CC7 axis A7-A11/B4 | Form Work | Column | 23.40 to 26.70 | Typical Floor | 42388 | 42395 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4150 | form work for 3 columns CC7 axis A6/B5-B6-B8 | Form Work | Column | 23.40 to 26.70 | Typical Floor | 42388 | 42392 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4151 | steel reinforcement for 4 columns CC7 axis B4/A7-A9-A10-A11 | Steel Reinforcement | Column | 23.40 to 26.70 | Typical Floor | 42388 | 42392 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4152 | steel reinforcement for 3 columns CC7 axis A6/B5-B6-B8 | Steel Reinforcement | Column | 23.40 to 26.70 | Typical Floor | 42388 | 42392 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4153 | steel reinforcement for core 2 axis A8 to A10/B14 to B16 | Steel Reinforcement | Core | 23.40 to 26.70 | Typical Floor | 42389 | 42392 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4154 | stressing of strands for first stage post tension slab at R.D tower axis A6 to A12/B4 to B8 | Stressing | Slab | 23.40 | Typical Floor | 42389 | 42395 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4155 | steel reinforcement for 2 columns CC7 axis A6/B14-B16 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42389 | 42396 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4156 | form work for 2 columns CC7 axis A6/B14-B16 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42389 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4157 | form work for 5 columns CC4 axis D1, D2, D3, D4, A9/B19 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42389 | 42395 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4158 | steel reinforcement for 5 columns CC4 axis D1, D2, D3, D4, A9/B19 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42389 | 42392 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4159 | drilling and fixation for dowels of core 7 axis C7/A2 to A3 | Dowels | Core | 28.40 | Typical Floor | 42389 | 42392 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4160 | steel reinforcement for shear wall 1 axis B1 to B6/A1 | Steel Reinforcement | SHW | 34 to 37.30 | Typical Floor | 42390 | 42392 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4161 | form work for second stage of post tension slab at R.D tower axis A6 to A12/B9 to B13 | Form Work | Slab | 23.40 | Typical Floor | 42390 | 42392 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4162 | form work for stair case 6 axis B10 to B11/A8 to A9 | Form Work | Stair | 20.10 to 23.40 | Typical Floor | 42390 | 42392 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4163 | steel reinforcement for driver stair case axis B19 to B20/A15 to A14 | Steel Reinforcement | Stair | -7.20 to -3.80 | B1 | 42390 | 42399 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4164 | steel reinforcement for 2 columns C8 axis B19/A14-A16 | Steel Reinforcement | Column | 1.10 to 3.45 | First Floor | 42390 | 42392 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4165 | form work for 2 columns C8 axis B19/A14-A16 | Steel Reinforcement | Column | 1.10 to 3.45 | First Floor | 42390 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4166 | steel reinforcement for 6 columns distributor room axis from B17 to B19/A14 to A15 | Steel Reinforcement | Column | zero to 4.10 | First Floor | 42390 | 42392 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4167 | form work for 6 columns distributor room axis from B17 to B19/A14 to A15 | Steel Reinforcement | Column | zero to 4.10 | First Floor | 42390 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4168 | form work for slab of core 3 axis B10 to B12/A8 to A10 | Form Work | Slab | 23.40 | Typical Floor | 42390 | 42392 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4169 | form work for 1 column CC7 axis A12/B16 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42392 | 42395 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4170 | fixation of shear connectors for column CC9 axis A11/B14 | Shear Connectors | Column | 20.10 to 23.40 | Typical Floor | 42392 | 42395 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4171 | steel reinforcement for 1 column CC7 axis A12/B16 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42392 | 42395 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4172 | installation (torque) for 1 column CC4 axis A10/B16 | Composite Columns | Column | 20.10 to 23.40 | Typical Floor | 42392 | 42396 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4173 | fixation for shear connectors for 1 column CC4 axis A10/B16 | Shear Connectors | Column | 20.10 to 23.40 | Typical Floor | 42392 | 42396 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4174 | installation (torque) for 1 column CC9 axis A11/B14 | Composite Columns | Column | 20.10 to 23.40 | Typical Floor | 42392 | 42395 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4175 | steel reinforcement for core 1 axis A8/B16-B17 | Steel Reinforcement | Core | 20.10 to 23.40 | Typical Floor | 42393 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4176 | steel reinforcement for 2 double columns CC1 axis B13/A10-A11 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42393 | 42396 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4177 | steel reinforcement for 1 double column CC7 axis A6/B13 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42393 | 42396 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4178 | form work for core 2 axis A8 to A10/B14 to B16 | Form Work | Core | 23.40 to 26.70 | Typical Floor | 42393 | 42399 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4179 | form work for 1 double column CC7 axis B13/A6 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42393 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4180 | form work for 2 double columns CC1 axis B13/A10-A11 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42393 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4181 | steel reinforcement for core 3 axis A8 to A10/B10 to B12 | Steel Reinforcement | Core | 26.70 to 30.00 | Typical Floor | 42393 | 42397 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4182 | stressing of strands for third stage post tension slab at R.D tower axis B13 to B18/A6 to A12 | Stressing | Slab | 21.10 | Typical Floor | 42393 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4183 | form work for shear wall 1 axis B1 to B6/A1 | Form Work | SHW | 34.90 to 38.20 | Typical Floor | 42393 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4184 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4185 | form work for second stage of post tension slab axis B6 to B19/A1 | Form Work | Slab | 28.40 | Typical Floor | 42393 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4186 | steel erinforcement for 1 double column CC1* axis A8/B13 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42395 | 42396 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4187 | form work for 1 double column CC1* axis A8/B13 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42395 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4188 | steel reinforcement for stair case 6 axis B10 to B11/A8 to A9 | Steel Reinforcement | Stair | 20.10 to 23.40 | Typical Floor | 42395 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4189 | top and bottom layer steel reinforcement for second stage of post tension slab axis B9 to B13/A6 to A12 | Steel Reinforcement | Slab | 23.40 | Typical Floor | 42395 | 42399 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4190 | tendons- strands- anchors and profiles for second stage of post tension slab ais B9 to B13/A6 to A12 | Cables | Slab | 23.40 | Typical Floor | 42395 | 42399 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4191 | steel reinforcement for 1 column CC4 axis B16/A10 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42396 | 42397 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4192 | form work for 1 column CC4 axis B16/A10 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42396 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4193 | form work for 1 column CC9 axis A11/B14 | Form Work | Column | 20.10 to 23.40 | Typical Floor | 42396 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4194 | steel reinforcement for 1 column CC9 axis A11/B14 | Steel Reinforcement | Column | 20.10 to 23.40 | Typical Floor | 42396 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4195 | tendons, strands, anchors and profiles final inspection for post tension slab second stage at Hotel axis B6 to B19/A1 to A3 | Cables | Slab | 28.40 | Typical Floor | 42396 | 42399 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4196 | bottom layer steel reinforcement for post tension slab second stage at hotel axis B6 to B19/A1 to A3 | Steel Reinforcement | Slab | 28.40 | Typical Floor | 42396 | 42399 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4197 | steel reinforcement for shear wall 1 axis B6 to B10/A1 | Steel Reinforcement | SHW | 35.00 to 38.30 | Typical Floor | 42396 | 42399 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4198 | top layer steel reinforcement for post tension slab second stage at hotel tower axis B6 to B19/A1 to A3 | Steel Reinforcement | Slab | 28.40 | Typical Floor | 42396 | 42399 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4199 | steel reinforcement for shear wall 6 axis C4/A2 to A3 | Steel Reinforcement | SHW | 38.30 to 41.30 | Typical Floor | 42396 | 42399 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4200 | steel reinforcement for shear wall 7 axis C3/A2 to A3 | Steel Reinforcement | SHW | 38.30 to 41.30 | Typical Floor | 42396 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4201 | steel reinforcement for 2 columns axis between A14 to A15/ between B20 to B21 | Steel Reinforcement | Column | -3.80 to zero | BOH | 42397 | 42400 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4202 | form work for 2 columns axis between A14 to A15/ between B20 to B21 | Steel Reinforcement | Column | -3.80 to zero | BOH | 42397 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4203 | form work for shear wall 1 axis B6 to B10/A1 | Form Work | SHW | 35.00 to 38.30 | Typical Floor | 42397 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4204 | form work removal for first stage of post tension slab at R.D tower axis B4 to B9/A6 to A12 | Removing Form Work | Slab | 23.40 | Typical Floor | 42397 | 42399 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4205 | form work for first stage of post tension slab at R.D tower axis B4 to B9/A6 to A12 | Form Work | Slab | 26.70 | Typical Floor | 42397 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4206 | form work for core 5 slab axis A8 to A10/B6 to B8 | Form Work | Slab | 26.70 | Typical Floor | 42397 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4207 | form work for stair case 7 axis A10/B10-B11 | Form Work | Stair | 20.10 to 23.40 | Typical Floor | 42397 | 42400 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4208 | form work for first stage of post tension slab at Hotel axis B1 to B6/A2 to A3 | Form Work | Slab | 31.70 | Typical Floor | 42393 | 42399 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4209 | steel reinforcement for core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | Core | 30 to 33.30 | Typical Floor | 42400 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4210 | form work for core 3 axis B10 to B12/A8 to A10 | Form Work | Core | 26.70 to 30 | Typical Floor | 42400 | 42400 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4211 | installation (torque) for 2 columns CC1 axis B9/A8-A11 west side | Composite Columns | Column | 23.40 to 26.70 | Typical Floor | 42400 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4212 | installation (torque) for 1 column CC3 axis B9/A10 west side | Composite Columns | Column | 23.40 to 26.70 | Typical Floor | 42400 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4213 | form work for core 1 axis A8/B16-B17 | Form Work | Core | 20.10 to 23.40 | Typical Floor | 42400 | 42401 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4214 | grouting for cables for first stage of post tension at R.D tower axis A6 to A12/B4 to B9 | Grout | Slab | 23.40 | Typical Floor | 42400 | 42404 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4215 | form work removal for third stage of post tension slab at R.D tower axis B13 to B18/A6 to A12 | Removing Form Work | Slab | 20.10 | Typical Floor | 42400 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4216 | repair for area at axis A12 to A14/B14 to B18 | Repair |  | -7.20 to -3.80 | B1 | 42400 | 42411 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4217 | top layer steel reinforcement for first stage of post tension slab at Hotel axis B1 to B6/A2 to A3 | Steel Reinforcement | Slab | 31.70 | 8th | 42400 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4218 | bottom layer steel reinforcement for first stage of post tension slab at Hotel axis B1 to B6/A2 to A3 | Steel Reinforcement | Slab | 31.70 | 8th | 42400 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4219 | tendons, strands, anchors and profiles final inspection for post tension slab first stage at Hotel axis B6 to B1/A2 to A3 | Cables | Slab | 31.70 | 8th | 42400 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4220 | drilling and fixation for dowels of shear wall 7 axis C3/A2 to A3 | Dowels | SHW | 38.30 to 41.30 | 11th Floor | 42400 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4221 | steel reinforcement for core 7 axis C7/A2-A3 | Steel Reinforcement | Core | 35 to 38.30 | 10th Floor | 42400 | 42401 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4222 | steel reinforcement for shear wall 1 axis B6 to B19/A1 | Steel Reinforcement | SHW | 35 to 38.30 | 10th Floor | 42400 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4223 | form work for shear wall 6 axis A1 to A3/C4 | Form Work | SHW | 38.30 to 41.30 | 11th Floor | 42400 | 42401 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4224 | steel reinforcement for pour strip between second and third stage axis B13/A6 to A12 | Steel Reinforcement | Slab | 20.10 | 4th | 42400 | 42404 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4225 | steel reinforcement for 3 columns CC7 axis A6/B10-B12-B9 | Steel Reinforcement | Column | 23.40 to 26.70 | 6th | 42400 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4226 | form work for 3 columns CC7 axis A6/B10-B12-B9 | Form Work | Column | 23.40 to 26.70 | 6th | 42400 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4227 | fixation of shear connectors for 2 columns CC9 axis A11/B10-B12 | Shear Connectors | Column | 23.40 to 26.70 | 6th | 42400 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4228 | installation (torque) for 2 columns CC1 axis B9/A8-A11 east side | Composite Columns | Column | 23.40 to 26.70 | 6th | 42400 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4229 | fixation of shear connectors for 2 columns CC1 axis B9/A8-A11 east side | Shear Connectors | Column | 23.40 to 26.70 | 6th | 42400 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4230 | installation (torque) for 1 column CC3 axis B9/A10 east side | Composite Columns | Column | 23.40 to 26.70 | 6th | 42400 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4231 | fixation of shear connectors for 1 column CC3 axis B9/A10 east side | Shear Connectors | Column | 23.40 to 26.70 | 6th | 42400 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4232 | steel reinforcement for 1 column CC9 axis B10/A11 | Steel Reinforcement | Column | 23.40 to 26.70 | 6th | 42400 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4233 | form work for 1 column CC9 axis B10/A11 | Form Work | Column | 23.40 to 26.70 | 5th | 42400 | 42404 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4234 | stressing for strands for second stage post tension slab axis B9 to B13/A6 to A12 | Stressing | Slab | 23.40 | 6th | 42400 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4235 | steel reinforcement for stair case 7 axis B12 to B13/A7 to A9 | Steel Reinforcement | Stair | 20.10 to 23.40 | 5th | 42401 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4236 | steel reinforcement for 1 double column CC1 axis A10/B9 | Steel Reinforcement | Column | 23.40 to 26.70 | 5th | 42401 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4237 | form work for 1 double column CC1 axis A10/B9 | Form Work | Column | 23.40 to 26.70 | 5th | 42401 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4238 | form work for 1 double column CC3 axis B9/A11 | Form Work | Column | 23.40 to 26.70 | 5th | 42401 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4239 | steel reinforcement for 1 double column CC3 axis A11/B9 | Steel Reinforcement | Column | 23.40 to 26.70 | 5th | 42401 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4240 | steel reinforcement for shear wall 9 and 1 column CC1 axis A8 to A9/B9 | Steel Reinforcement | SHW | 23.40 to 26.70 | 5th | 42401 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4241 | form work for shear wall 9 and 1 column CC1 axis A8 to A9/B9 | Form Work | SHW | 23.40 to 26.70 | 5th | 42401 | 42404 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4242 | form work for 1 column CC9 axis A11/B12 | Form Work | Column | 23.40 to 26.70 | 5th | 42401 | 42404 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4243 | steel reinforcement for 1 column CC9 axis A11/B12 | Steel Reinforcement | Column | 23.40 to 26.70 | 5th | 42401 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4244 | form work for stair case 3 axis B6 to B7/A8 to A9 | Form Work | Stair | 23.40 to 26.70 | 5th | 42401 | 42401 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4245 | steel reinforcement for shear wall 2 axis C10/A2 to A3 | Steel Reinforcement | SHW | 28.40 to 31.70 | 8th | 42401 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4246 | steel reinforcement for shear wall 3 axis C6/A2 to A3 | Steel Reinforcement | SHW | 28.40 to 31.70 | 8th | 42401 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4247 | form work for core 7 axis A2 to A3/C7 | Form Work | Core | 35 to 38.30 | 10th Floor | 42401 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4248 | form work for shear wall 1 axis B10 to B19/A1 | Form Work | SHW | 35 to 38.30 | 10th Floor | 42401 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4249 | fixation of shear connectors for CC5& CC6 axis C9-C11/A3 | Shear Connectors | Column | 28.40 to 31.70 | 8th | 42401 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4250 | grouting for cables for third stage of post tension slab at R.D tower axis B13 to B18/A6 to A12 | Grout | Slab | 20.10 | 4th | 42402 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4251 | steel reinforcement for stair case 3 axis A8 to A9/B6 to B8 | Steel Reinforcement | Stair | 23.40 to 26.70 | 6th | 42402 | 42404 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4252 | form work for shear wall 2 axis A2 to A3/C10 | Form Work | SHW | 28.40 to 31.70 | 8th | 42401 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4253 | form work for shear wall 3 axis A1 to A3/C6 | Form Work | SHW | 28.40 to 31.70 | 8th | 42402 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4254 | grouting for cables post tension slab second stage at Hotel tower axis C5 to B19/A1 to A3 | Grout | Slab | 25.10 | 6th | 42402 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4255 | stressing for cables post tension slab second stage at Hotel tower axis C5 to B19/A1 to A3 | Stressing | Slab | 28.90 | 7th | 42402 | 42409 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4256 | steel reinforcement for 2 columns CC5& CC6 axis C9-C11/A3 | Steel Reinforcement | Column | 28.40 to 31.70 | 8th | 42402 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4257 | form work for 2 columns CC5& CC6 axis C9-C11/A3 | Form Work | Column | 28.40 to 31.70 | 8th | 42402 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4258 | form work for shear wall 5/ 5* axis C5/A2 to A3 | Form Work | SHW | 28.40 to 31.70 | 8th | 42402 | 42407 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4259 | steel reinforcement for shear wall 5/5* axis C5/A2 to A3 | Steel Reinforcement | SHW | 28.40 to 31.70 | 8th | 42402 | 42406 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4260 | steel reinforcement for shear wall 3/3* axis C8/A2 to A3 | Steel Reinforcement | SHW | 28.40 to 31.70 | 8th | 42402 | 42406 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4261 | form work for shear wall 3/3* axis C8/A2 to A3 | Form Work | SHW | 28.40 to 31.70 | 8th | 42402 | 42407 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4262 | form work for shear wall 1 and 1 column C1 axis B19 to B20/A1 | Form Work | SHW | 28.40 to 31.70 | 8th | 42402 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4263 | steel reinforcement for shear wall 1 and 1 column C1 axis B19 to B20/A1 | Steel Reinforcement | SHW | 28.40 to 31.70 | 8th | 42402 | 42403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4264 | steel reinforcement for core 6 axis B15 to B17/A1 to A2 | Steel Reinforcement | Core | 28.40 to 31.70 | 8th | 42403 | 42404 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4265 | Form work for core 6 axis B15 to B17/A1 to A2 | Form Work | Core | 28.40 to 31.70 | 8th | 42403 | 42407 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4266 | form work for column C5 axis B18/A1 to A3 | Form Work | Column | 28.40 to 31.70 | 8th | 42403 | 42407 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4267 | steel reinforcement for column C5 axis B18/A1 to A2 | Steel Reinforcement | Column | 28.40 to 31.70 | 8th | 42403 | 42406 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4268 | holes and dowels fixation for column C5 axis B18/A1 to A2 | Dowels | Column | 28.40 to 31.70 | 8th | 42403 | 42403 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4269 | steel reinforcement for 1 column distribution room axis B20 to B19/A15 | Steel Reinforcement | Column | zero to 4.10 | LGF | 42404 | 42404 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4270 | form work for 1 column distribution room axis B20 to B19/A15 | Form Work | Column | zero to 4.10 | LGF | 42404 | 42404 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4271 | form work for distribution room slab axis B17 to B19/A14 to A15 | Form Work | Slab | 3.80 | LGF | 42403 | 42407 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4272 | top and bottom layers and beam steel reinforcement for first stage of post tension slab at R.D tower axis B4 to B9/A6 to A12 | Steel Reinforcement | Slab | 26.70 | 6th | 42403 | 42404 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4273 | steel reinforcement for core 2 axis A8 to A10/B14 to B16 | Steel Reinforcement | Core | 26.70 to 30 | 7th | 42403 | 42407 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4274 | tendons- strands- anchors and profiles for first stage of post tension slab at R.D tower axis A6 to A12/B4 to B8 | Cables | Slab | 26.70 | 6th | 42403 | 42404 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4275 | form work for third stage of slab of R.D tower axis A6 to A12/B13 to B18 | Form Work | Slab | 23.40 | 5th | 42404 | 42407 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4276 | form work for shear wall 7 axis C3/A2 to A3 | Form Work | SHW | 38.30 to 41.30 | 11th Floor | 42404 | 42407 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4277 | steel reinforcement for beams at third stage of R.D tower axis B13 to B18/A6 to A12 | Steel Reinforcement | Slab | 26.70 | 6th | 42404 | 42407 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4278 | form work for core 5 axis B6 to B8/A8 to A10 | Form Work | Core | 30 to 33.30 | 8th | 42404 | 42407 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4279 | form work for core 8 axis B1/A2 to A3 | Form Work | Core | 38.30 to 41.60 | 10th Floor | 42404 | 42409 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4280 | steel reinforcement for core 8 axis B1/A1 to A3 | Steel Reinforcement | Core | 38.30 to 41.60 | 10th Floor | 42404 | 42407 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4281 | form work for shear wall 8 axis C2/A2 to A3 | Form Work | SHW | 31.70 to 35 | 9th | 42404 | 42407 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4282 | steel reinforcement for shear wall 8 axis C2/A2 to A3 | Steel Reinforcement | SHW | 31.70 to 35 | 9th | 42404 | 42407 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4283 | form work for RMU room slab axis B20 to B21/A14 to A15 | Form Work | Slab | 3.80 | First Floor | 42406 | 42407 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4284 | form work for stair case 11 axis B16 to B17/A9 | Form Work | Stair | 20.10 to 23.40 | 5th | 42406 | 42407 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4285 | installation (torque) for 2 colums CC9 axis A11/B8-B6 | Composite Columns | Column | 26.70 to 30 | 7th | 42407 | 42411 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4286 | fixation for shear connectors for 2 columns CC9 axis A11/B6-B8 | Shear Connectors | Column | 26.70 to 30 | 7th | 42407 | 42409 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4287 | form work for 3 columns CC7 axis A6/B5-B6-B8 | Form Work | Column | 26.70 to 30 | 7th | 42407 | 42408 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4288 | steel reinforcement for 3 columns CC7 axis A6/B5-B6-B8 | Steel Reinforcement | Column | 26.70 to 30 | 7th | 42407 | 42408 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4289 | steel reinforcement for 4 columns CC7 axis B4/(A7-A8)-A9-A10-A11 | Steel Reinforcement | Column | 26.70 to 30 | 7th | 42407 | 42409 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4290 | form work for 4 columns CC7 axis B4/(A7-A8)-A9-A10-A11 | Form Work | Column | 26.70 to 30 | 7th | 42407 | 42410 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4291 | form work removal for second stage of slab of R.D tower axis A6 to A12/B9 to B13 | Removing Form Work | Slab | 23.40 | 5th | 42408 | 42410 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4292 | steel reinforcement for stair case 11 axis A8 to A10/B16 to B18 | Steel Reinforcement | Stair | 20.10 to 23.40 | 5th | 42408 | 42411 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4293 | grouting for cables for second stage slab axis A6 to A12/B8 to B12 | Grout | Slab | 23.40 | 5th | 42408 | 42409 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4294 | form work for stair case 6 axis B10 to B11/A8 to A9 | Form Work | Stair | 23.40 to 26.70 | 6th | 42408 | 42410 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4295 | steel reinforcement for pour strip between A6 to A12/B8 to B9 | Steel Reinforcement | Slab | 23.40 | 5th | 42408 | 42410 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4296 | stressing of strands for first stage slab axis A6 to A12/B4 to B9 | Stressing | Slab | 26.70 | 6th | 42408 | 42409 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4297 | bottom and top steel reinforcement for RMU, Distributor room slab axis B17 to B20/A14 to A15 | Steel Reinforcement | Slab | 4.10 | LGF | 42408 | 42420 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4298 | form work for stair case 14 axis A2/B15 to B17 | Form Work | Stair | 18.50 to 21.80 | 5th | 42408 | 42409 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4299 | steel reinforcement for pouring strip between C4 to C5/A1 to A3 | Steel Reinforcement | Slab | 25.10 | 6th | 42408 | 42408 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4300 | stressing for cables first stage axis C4 to B1/A1 to A3 | Stressing | Slab | 31.70 | 8th | 42409 | 42410 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4301 | steel reinforcement for column CC9 axis A11/B6 | Steel Reinforcement | Column | 26.70 to 30.00 | 7th | 42409 | 42411 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4302 | form work for column CC9 axis A11/B6 | Form Work | Column | 26.70 to 30.00 | 7th | 42409 | 42411 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4303 | steel reinforcement for slab inside core 2 axis A8 to A10/B14 to B15 | Steel Reinforcement | Slab | 20.10 | 4th | 42409 | 42411 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4304 | form work removal for first stage slab axis A6 to A12/B4 to B9 | Removing Form Work | Slab | 26.70 | 6th | 42409 | 42410 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4305 | steel reinforcement for shear wall 1 axis B1 to C7/A1 | Steel Reinforcement | SHW | 38.30 to 41.60 | 10th Floor | 42409 | 42410 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4306 | form work for shear wall 1 axis B1 to C7/A1 | Form Work | SHW | 38.30 to 41.60 | 10th Floor | 42409 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4307 | steel reinforcement for stair case 12 axis B1/A2 | Steel Reinforcement | Stair | 38.30 to 41.60 | 10th Floor | 42409 | 42420 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4308 | form work for second stage slab axis B6 to B19/A1 to A3 | Form Work | Slab | 31.70 | 8th | 42409 | 42413 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4309 | form work for first stage slab axis B6 to B1/A1 to A3 | Form Work | Slab | 35.00 | 9th | 42409 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4310 | form work for second stage slab axis B9 to B12/A6 to A12 | Form Work | Slab | 26.70 | 6th | 42409 | 42410 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4311 | steel reinforcement for core 3 axis A8 to A10/B10 to B12 | Steel Reinforcement | Core | 30 to 33.30 | 8th | 42410 | 42411 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4312 | top and bottom layers steel reinforcement for third stage of post tension slab at R.D tower axis A6 to A12/B13 to B18 | Steel Reinforcement | Slab | 23.40 | 5th | 42410 | 42411 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4313 | tendons- strands- anchors and profiles for third stage of post tension slab at R.D tower axis A6 to A12/B13 to B18 | Cables | Slab | 23.40 | 5th | 42410 | 42411 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4314 | form work for core 2 axis A7 to A10/B14 to B16 | Form Work | Core | 26.70 to 30 | 7th | 42410 | 42410 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4315 | steel reinforcement for shear wall 6 axis C4/A2 to A3 | Steel Reinforcement | SHW | 41.60 to 44.90 | 12th Floor | 42410 | 42411 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4316 | form work for shear wall 6 axis C4/A2 to A3 | Form Work | SHW | 41.60 to 44.90 | 12th Floor | 42410 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4317 | form work for core 3 slab axis B10 to B12/A8 to A10 | Form Work | Slab | 26.70 | 5th | 42410 | 42410 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4318 | steel reinfororcement for 3 columns CC7 axis A6/B16-B14-B13 | Steel Reinforcement | Column | 23.40 to 26.70 | 6th | 42414 | 42417 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4319 | form work for 3 columns CC7 axis A6/B16-B14-B13 | Form Work | Column | 23.40 to 26.70 | 6th | 42414 | 42417 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4320 | steel reinforcement for 2 columns CC4 axis D1& D2 | Steel Reinforcement | Column | 23.40 to 26.70 | 6th | 42414 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4321 | form work for 2 columns CC4 axis D1& D2 | Form Work | Column | 23.40 to 26.70 | 6th | 42414 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4322 | installation (torque) for 5 columns CC4 axis D1, D2, D3, D4& A9/B19 | Composite Columns | Column | 23.40 to 26.70 | 6th | 42414 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4323 | fixation of shear connectors for 5 columns CC5 axis D1, D2, D3, D4& A9/B19 | Shear Connectors | Column | 23.40 to 26.70 | 6th | 42414 | 42415 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4324 | grouting for R.D tower slab first stage axis B4 to B9/A6 to A12 | Grout | Slab | 26.70 | 6th | 42414 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4325 | form work for first stage of R.D tower slab axis B4 to B9/A6 to A12 | Form Work | Slab | 30.00 | 7th | 42414 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4326 | form work for stair case 3 axis B6 to B7/A8 to A9 | Form Work | Stair | 26.70 to 30.00 | 7th | 42414 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4327 | form work for stair case 6 axis B10 to B11/A8 to A9 | Form Work | Stair | 23.40 to 26.70 | 6th | 42414 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4328 | form work for stair case 7 axis A10/B10-B11 | Form Work | Stair | 23.40 to 26.70 | 6th | 42414 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4329 | form work for stair case 4 axis B7 to B8/A10 | Form Work | Stair | -3.80 to -0.45 | LGF | 42414 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4330 | steel reinforcement for 2 columns CC4 axis D3& A9/B19 | Steel Reinforcement | Column | 23.40 to 26.70 | 6th | 42414 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4331 | form work for 2 columns CC4 axis D3& A9/B19 | Form Work | Column | 23.40 to 26.70 | 6th | 42414 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4332 | steel reinforcement for core 1 axis A8/B16-B17 | Steel Reinforcement | Core | 23.40 to 26.70 | 6th | 42414 | 42416 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4333 | form work for core 1 axis A8/B16-B17 | Form Work | Core | 23.40 to 26.70 | 6th | 42414 | 42420 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4334 | steel reinforcement for 1 column CC9 axis A11/B14 | Steel Reinforcement | Column | 23.40 to 26.70 | 6th | 42414 | 42416 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4335 | form work for 1 column CC9 axis A11/B14 | Form Work | Column | 23.40 to 26.70 | 6th | 42414 | 42417 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4336 | steel reinforcement for 1 column CC7 axis A12/B16 | Steel Reinforcement | Column | 23.40 to 26.70 | 6th | 42414 | 42417 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4337 | form work for 1 column CC7 axis A12/B16 | Form Work | Column | 23.40 to 26.70 | 6th | 42414 | 42417 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4338 | fixation of shear connectors for 1 column CC4 axis B16/A10 | Shear Connectors | Column | 23.40 to 26.70 | 6th | 42414 | 42415 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4339 | installation (torque) for 1 column CC4 axis B16/A10 | Composite Columns | Column | 23.40 to 26.70 | 6th | 42414 | 42415 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4340 | top layer steel reinforcement for first stage at hotel tower axis B1 to C5/A1 to A3 | Steel Reinforcement | Slab | 35.00 | 8th | 42414 | 42415 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4341 | bottom layer steel reinforcement for first stage hotel slab axis B1 to C5/A1 to A3 | Steel Reinforcement | Slab | 35.00 | 8th | 42414 | 42415 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4342 | tendons, strands, anchors and profiles for first stage hotel slab axis B1 to C5/A1 to A3 | Cables | Slab | 35.00 | 8th | 42414 | 42415 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4343 | fixation of shear connectors for 1 column CC9 axis A11/B14 | Shear Connectors | Column | 23.40 to 26.70 | 6th | 42414 | 42415 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4344 | 5% increasing for cables No. 8-14& 17 at first stage of hotel slab axis B1 to C5/A1 to A3 | Cables | Slab | 31.70 | 8th | 42415 | 42417 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4345 | check of force and 5% increasing for cables No. 8-29-30-31-32-33-35-39-40-41-42-44& 17 at second stage hotel slab axis C5 to B19/A1 to A3 | Cables | Slab | 28.40 | 7th | 42415 | 42416 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4346 | installation (torque) for 2 columns CC1 axis B13/A10-A11 east side | Composite Columns | Column | 23.40 to 26.70 | 6th | 42415 | 42416 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4347 | installation (torque) for 1 column CC1* axis B13/A8 east side | Composite Columns | Column | 23.40 to 26.70 | 6th | 42415 | 42417 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4348 | steel reinforcement for 1 column CC4 axis D4 | Steel Reinforcement | Column | 23.40 to 26.70 | 6th | 42415 | 42416 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4349 | form work for 1 column CC4 axis D4 | Form Work | Column | 23.40 to 26.70 | 6th | 42415 | 42417 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4350 | stressing for strands for third stage post tension slab axis B13 to B18/A6 to A12 | Stressing | Slab | 23.40 | 5th | 42415 | 42417 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4351 | form work for core 3 axis B10 to B12/A8 to A10 | Form Work | Core | 30.00 to 33.30 | 8th | 42415 | 42416 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4352 | steel reinforcement for core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | Core | 33.30 to 36.60 | 9th | 42415 | 42416 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4353 | top and bottom layer steel reinforcement for second stage of post tension slab axis B9 to B13/A6 to A12 | Steel Reinforcement | Slab | 26.70 | 6th | 42415 | 42416 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4354 | tendons- strands- anchors and profiles for second stage of post tension slab ais B9 to B13/A6 to A12 | Steel Reinforcement | Slab | 26.70 | 6th | 42415 | 42416 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4355 | top and bottom layers steel reinforcement for core 3 slab axis B10 to B12/A7 to A10 | Steel Reinforcement | Slab | 26.70 | 6th | 42415 | 42416 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4356 | top and bottom layer steel reinforcement for stair case 7 axis B10 to B11/A10 | Steel Reinforcement | Stair | 23.40 to 26.70 | 6th | 42415 | 42416 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4357 | steel reinforcement for shear wall 1 axis B1 to C2/A1 | Steel Reinforcement | SHW | 38.30 to 41.60 | 10th Floor | 42415 | 42416 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4358 | form work for 1 column CC9 axis B8/A11 | Form Work | Column | 26.70 to 30 | 7th | 42411 | 42413 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4359 | steel reinforcement for 1 column CC9 axis B8/A11 | Steel Reinforcement | Column | 26.70 to 30 | 7th | 42411 | 42411 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4360 | form work for shear wall 1 axis B1 to C2/A1 | Form Work | SHW | 38.30 to 41.60 | 10th Floor | 42415 | 42417 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4361 | form work for core 8 axis A2 to A3/B1 | Form Work | Core | 41.60 to 44.90 | 11th Floor | 42416 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4362 | steel reinforcement for core 8 axis A2 to A3/B1 | Steel Reinforcement | Core | 41.60 to 44.90 | 11th Floor | 42416 | 42420 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4363 | form work for shear wall 1 axis C7 to B19/A1 | Form Work | SHW | 38.30 to 41.60 | 7th | 42416 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4364 | steel reinforcement for shear wall 1 axis C7 to B19/A1 | Steel Reinforcement | SHW | 38.30 to 41.60 | 7th | 42416 | 42420 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4365 | form work removing for second stage hotel slab axis C5 to B19/A1 to A3 | Removing Form Work | Slab | 28.40 | 7th | 42416 | 42427 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4366 | steel reinforcement for core 2 slab axis A8 to A10/B14 to B16 | Steel Reinforcement | Slab | 23.40 | 5th | 42416 | 42422 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4367 | installation (torque) for 2 columns CC1 axis B13/A10-A11 west side | Composite Columns | Column | 23.40 to 26.70 | 6th | 42416 | 42420 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4368 | installation (torque) for 1 column CC1* west side axis A8/B13 | Composite Columns | Column | 23.40 to 26.70 | 6th | 42416 | 42434 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4369 | installation (torque) for 2 double columns CC1 axis A10-A11 | Composite Columns | Column | 23.40 to 26.70 | 6th | 42416 | 42416 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4370 | fixation of shear connectors for 1 column CC1* axis A8/B13 | Shear Connectors | Column | 23.40 to 26.70 | 6th | 42416 | 42416 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4371 | form work for 1 column CC1* axis B13/A8 | Form Work | Column | 23.40 to 26.70 | 6th | 42417 | 42420 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4372 | steel reinforcement for 1 column CC1* axis B13/A8 | Steel Reinforcement | Column | 23.40 to 26.70 | 6th | 42417 | 42418 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4373 | top layer steel reinforcement for second stage of hotel tower slab axis C5 to B19/A1 to A3 | Steel Reinforcement | Slab | 31.70 | 8th | 42417 | 42420 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4374 | tendons, strands, anchors and profiles second stage hotel axis C5 to B19/A1 to A3 | Cables | Slab | 31.70 | 8th | 42417 | 42420 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4375 | bottom layer steel reinforcement for second stage hotel tower slab axis C5 to B19/A1 to A3 | Steel Reinforcement | Slab | 31.70 | 8th | 42417 | 42420 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4376 | fixation of shear connectors for 1 double column CC3 axis B9/A11 | Shear Connectors | Column | 26.70 to 30 | 7th | 42374 | 42420 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4377 | fixation of shear connectors for 2 columns CC1 axis B9/A10-A8 | Shear Connectors | Column | 26.70 to 30 | 7th | 42418 | 42420 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4378 | steel reinforcement for 2 double columns CC1 axis B13/A10-A11 | Steel Reinforcement | Column | 26.70 to 30 | 7th | 42418 | 42418 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4379 | form work for 2 double columns CC1 axis B13/A10-A11 | Form Work | Column | 23.40 to 26.70 | 6th | 42418 | 42420 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4380 | form work for stair case 10 axis A8 to A9/B14 to B15 | Form Work | Stair | -7.20 to -3.80 | B1 | 42418 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4381 | steel reinforcement for stair case 3 axis A8 to A9/B6 to B8 | Steel Reinforcement | Stair | 26.70 to 30 | 7th | 42418 | 42418 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4382 | form work for column CC4 axis B16/A10 | Form Work | Column | 23.40 to 26.70 | 6th | 42416 | 42417 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4383 | steel reinforcement for column CC4 axis B16/A10 | Steel Reinforcement | Column | 23.40 to 26.70 | 6th | 42416 | 42417 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4384 | steel reinforcement for first stage slab at R.D tower axis B4 to B9/A6 to A12 | Steel Reinforcement | Slab | 30.00 | 7th | 42418 | 42420 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4385 | tendons, strands, anchors and profiles first stage slab axis B4 to B9/A6 to A12 | Cables | Slab | 30.00 | 7th | 42418 | 42420 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4386 | form work for core 5 axis B6 to B8/A8 to A10 | Form Work | Core | 33.30 to 36.60 | 9th | 42418 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4387 | steel reinforcement for 3 columns CC7 axis A6/B9- B10- B12 | Steel Reinforcement | Column | 26.70 to 30.00 | 7th | 42418 | 42420 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4388 | form work for 3 columns CC7 axis A6/B9- B10- B12 | Form Work | Column | 26.70 to 30.00 | 7th | 42418 | 42423 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4389 | steel reinforcement for 1 double column CC3 axis B9/A11 | Steel Reinforcement | Column | 26.70 to 30.00 | 7th | 42418 | 42420 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4390 | form work for 1 double column CC3 axis B9/A11 | Form Work | Column | 26.70 to 30.00 | 7th | 42418 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4391 | steel reinforcement for 1 double column CC1 axis B9/A10 | Steel Reinforcement | Column | 26.70 to 30.00 | 7th | 42418 | 42420 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4392 | form work for 1 double column CC1 axis B9/A10 | Form Work | Column | 26.70 to 30.00 | 7th | 42418 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4393 | steel reinforcement for shear wall 9 axis A8 to A9/B9 | Steel Reinforcement | SHW | 26.70 to 30.00 | 7th | 42418 | 42422 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4394 | form work for shear wall 9 axis A8 to A9/B9 | Form Work | SHW | 26.70 to 30.00 | 7th | 42418 | 42423 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4395 | installation (torque) for 2 columns CC9 axis A11/B10-B12 | Composite Columns | Column | 26.70 to 30.00 | 7th | 42418 | 42420 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4396 | form work for core 7 axis A2 to A3/C7 | Form Work | Core | 38.30 to 41.60 | 11th Floor | 42420 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4397 | steel reinforcement for core 7 axis C7/A2-A3 | Steel Reinforcement | Core | 38.30 to 41.60 | 11th Floor | 42420 | 42422 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4398 | form work for shear wall 7 axis C3/A2 to A3 | Form Work | SHW | 41.60 to 44.90 | 12th Floor | 42420 | 42428 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4399 | steel reinforcement for shear wall 7 axis C3/A2 to A3 | Steel Reinforcement | SHW | 41.60 to 44.90 | 12th Floor | 42420 | 42427 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4400 | steel reinforcement for stair case 4 axis A10/B7 to B8 | Steel Reinforcement | Stair | -3.80 to -0.45 | BOH | 42421 | 42427 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4401 | steel reinforcement for 7 columns CC4-A axis A6/B5-B6-B8, B4/A8-A9-A10-A11 | Steel Reinforcement | Column | 30.00 to 33.30 | 8th | 42421 | 42422 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4402 | form work for 7 columns CC4-A axis A6/B5-B6-B8, B4/A8-A9-A10-A11 | Form Work | Column | 30.00 to 33.30 | 8th | 42421 | 42424 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4403 | stressing for second stage of post tension axis B9 to B13/A6 to A12 | Stressing | Slab | 26.70 | 6th | 42421 | 42422 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4404 | grouting for third stage slab axis B13 to B18/A6 to A12 | Grout | Slab | 23.40 | 5th | 42421 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4405 | steel reinforcement for pour strip between second and third stage axis B13/A6 to A12 | Steel Reinforcement | Slab | 23.40 | 5th | 42421 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4406 | steel reinforcement for stair case 10 axis B14 to B15/A8 to A9 | Steel Reinforcement | Stair | -7.20 to -3.80 | B1 | 42421 | 42429 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4407 | steel reinforcement for 2 columns CC9 axis A11/B10-B12 | Steel Reinforcement | Column | 26.70 to 30.00 | 7th | 42421 | 42422 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4408 | form work for 2 columns CC9 axis A11/B10-B12 | Form Work | Column | 26.70 to 30.00 | 7th | 42421 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4409 | fixation of shear connectors for 2 columns CC9 axis A11/B10-B12 | Shear Connectors | Column | 26.70 to 30.00 | 7th | 42421 | 42422 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4410 | steel reinforcement for slab of core 5 axis B6 to B8/A7 to A11 | Steel Reinforcement | Slab | 30.00 | 7th | 42421 | 42421 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4411 | fixation of shear connectors for 2 columns CC9 axis A11/B8-B6 | Shear Connectors | Column | 30.00 to 33.30 | 8th | 42421 | 42422 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4412 | form work for double shear wall 5* axis C5/A2 to A3 | Form Work | SHW | 31.70 to 35.00 | 9th | 42421 | 42427 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4413 | steel reinforcement for shear wall 5* axis C5/A2-A3 | Steel Reinforcement | SHW | 31.70 to 35.00 | 9th | 42421 | 42424 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4414 | steel reinforcement for double shear wall 3* axis C8/A2 to A3 | Steel Reinforcement | SHW | 31.70 to 35.00 | 9th | 42421 | 42423 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4415 | form work for double shear wall 3* axis C8/A2 to A3 | Form Work | SHW | 31.70 to 35.00 | 9th | 42421 | 42423 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4416 | form work for shear wall 8 axis C2/A2 to A3 | Form Work | SHW | 35.00 to 38.30 | 10th Floor | 42421 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4417 | steel reinforcement for shear wall 8 axis C2/A2 to A3 | Steel Reinforcement | SHW | 35.00 to 38.30 | 10th Floor | 42421 | 42422 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4418 | form work for shear wall 3 axis C6/A2 to A3 | Form Work | SHW | 31.70 to 35.00 | 9th | 42421 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4419 | steel reinforcement for shear wall 3 axis C6/A2 to A3 | Steel Reinforcement | SHW | 31.70 to 35.00 | 9th | 42421 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4420 | fixation of shear connectors for columns CC5& CC6 axis A3/B15-B13 | Shear Connectors | Column | 31.70 to 35.00 | 9th | 42421 | 42423 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4421 | installation (torque) for 1 column CC6 axis C11/A2 | Composite Columns | Column | 31.70 to 35.00 | 9th | 42421 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4422 | form work for 2 columns CC9 axis A11/B6-B8 | Form Work | Column | 30.00 to 33.30 | 8th | 42422 | 42423 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4423 | steel reinforcement for 2 columns CC9 axis A11/B6-B8 | Steel Reinforcement | Column | 30.00 to 33.30 | 8th | 42422 | 42423 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4424 | grouting for cables of first stage of post tension slab at hotel axis C5 to C1/A1 to A3 | Grout | Slab | 31.70 | 9th | 42422 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4425 | stressing for cables of post tension for second stage slab axis B6 to B19/A1 to A3 | Stressing | Slab | 31.70 | 9th | 42422 | 42429 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4426 | steel reinforcement for 1 column CC6 axis C11/A2 to A3 | Steel Reinforcement | Column | 31.70 to 35.00 | 9th | 42422 | 42424 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4427 | form work for 1 column CC6 axis C11/A2 to A3 | Form Work | Column | 31.70 to 35.00 | 9th | 42422 | 42427 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4428 | form work for column CC5 axis C9/A3 | Form Work | Column | 31.70 to 35.00 | 9th | 42422 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4429 | steel reinforcement for column CC5 axis C9/A3 | Steel Reinforcement | Column | 31.70 to 35.00 | 9th | 42422 | 42423 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4430 | form work for column C5 axis B18/A1 to A3 | Form Work | Column | 31.70 to 35.00 | 9th | 42422 | 42427 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4431 | steel reinforcement for column C5 axis B18/A1 to A2 | Steel Reinforcement | Column | 31.70 to 35.00 | 9th | 42422 | 42424 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4432 | form work for shear wall 2 axis C10/A2 to A3 | Form Work | SHW | 31.70 to 35.00 | 9th | 42422 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4433 | steel reinforcement for shear wall 2 axis C10/A2 to A3 | Steel Reinforcement | SHW | 31.70 to 35.00 | 9th | 42422 | 42423 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4434 | stressing for cables of post tension for first stage slab axis B1 to C5/A1 to A3 | Stressing | Slab | 35.00 | 9th | 42422 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4435 | grouting for cables of second satage slab at hotel axis C5 to B19/A1 to A3 | Grout | Slab | 28.40 | 8th | 42422 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4436 | form work for stair case 11 axis B16 to B17/A9 | Form Work | Stair | 23.40 to 26.70 | 6th | 42422 | 42423 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4437 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4438 | form work removal for third stage of post tension slab at R.D tower axis B13 to B18/A6 to A12 | Form Work | Slab | 23.40 | 5th | 42422 | 42427 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4439 | steel reinforcement for stair case 11 axis B17/A9 | Steel Reinforcement | Stair | 23.40 to 26.70 | 6th | 42423 | 42429 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4440 | form work for second stage slab at R.D tower axis B9 to B13/A6 to A12 | Form Work | Slab | 30.00 | 7th | 42423 | 42427 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4441 | steel reinforcement for pour strip between first and second stage axis B9/A6 to A12 | Steel Reinforcement | Slab | 26.70 | 6th | 42423 | 42427 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4442 | stressing for first stage post tension slab axis B4 to B9/A6 to A12 | Stressing | Slab | 30.00 | 7th | 42423 | 42427 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4443 | steel reinforcement for core 6 axis B15 to B17/A1 to A2 | Steel Reinforcement | Core | 31.70 to 35.00 | 9th | 42423 | 42424 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4444 | form work for core 6 axis B15 to B17/A1 to A2 | Form Work | Core | 31.70 to 35.00 | 9th | 42423 | 42427 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4445 | steel reinforcement for shear wall 1 and 1 column C1 axis B19 to B20/A1 | Steel Reinforcement | SHW | 31.70 to 35.00 | 9th | 42423 | 42427 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4446 | form work for shear wall 1 and 1 column C1 axis B19 to B20/A1 | Form Work | SHW | 31.70 to 35.00 | 9th | 42423 | 42427 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4447 | steel reinforcement for core 3 axis A8 to A10/B10 to B12 | Steel Reinforcement | Core | 33.30 to 36.60 | 8th | 42424 | 42427 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4448 | grouting for cables for second stage of post tension slab axis B9 to B13/A6 to A12 | Grout | Slab | 26.70 | 6th | 42424 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4449 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4450 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4451 | form work for stair case 6 axis B10 to B11/A8 to A9 | Form Work | Stair | 26.70 to 30.00 | 6th | 42424 | 42427 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4452 | Canceled
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4453 | steel reinforcement for beams at third stage of R.D tower axis B13 to B18/A6 to A12 | Steel Reinforcement | Slab | 26.70 | 6th | 42425 | 42428 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4454 | form work for stair case 7 axis A10/B10-B11 | Form Work | Stair | 26.70 to 30.00 | 7th | 42425 | 42429 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4455 | form work for core 5 slab axis A8 to A10/B6 to B8 | Form Work | Slab | 33.30 | 8th | 42428 | 42429 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4456 | form work for second stage of slab axis C5 to B19/A1 to A3 | Form Work | Slab | 35.00 | 9th | 42428 | 42429 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4457 | form work for first stage slab axis B4 to B9/A1 to A3 | Form Work | Slab | 33.30 | 8th | 42428 | 42429 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4458 | steel reinforcement for stair case 6 axis B10 to B11/A8 to A9 | Steel Reinforcement | Stair | 26.70 to 30.00 | 7th | 42428 | 42431 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4459 | steel reinforcement for stair case 7 axis B12 to B13/A7 to A9 | Steel Reinforcement | Stair | 26.70 to 30.00 | 7th | 42428 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4460 | steel reinforcement for third stage slab axis B13 to B18/A6 to A12 | Steel Reinforcement | Slab | 26.70 | 6th | 42428 | 42428 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4461 | tendons, strands, anchors and profiles for third stage slab axis B13 to B18/A6 to A12 | Cables | Slab | 26.70 | 6th | 42428 | 42429 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4462 | steel reinforcement for core 2 axis A8 to A10/B14 to B16 | Steel Reinforcement | Core | 30.00 to 33.30 | 8th | 42428 | 42430 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4463 | raising stress up to 5% for 2 cables (1-12) at first stage slab at hotel axis B1 to B5/A1 to A3 | Stressing | Slab | 35.00 | 9th | 42428 | 42429 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4464 | form work for third stage of R.D tower sslab axis B13 to B18/A6 to A12 | Form Work | Slab | 26.70 | 6th | 42428 | 42429 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4465 | fixation for shear connectors for 2 double columns CC1 axis B13/A10-A11 | Shear Connectors | Column | 26.70 to 30 | 7th | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4466 | fixation of shear connectors for 5 columns CC4 axis D4/A12, D3/A10, D2/A8, D1/A7, A9/B19 | Shear Connectors | Column | 26.70 to 30 | 7th | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4467 | form work for core 3 axis B10 to B12/A8 to A10 | Form Work | Core | 33.30 to 36.60 | 8th | 42429 | 42429 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4468 | form work for stair case 3 axis B6 to B7/A8 to A9 | Form Work | Stair | 30 to 33.30 | 7th | 42429 | 42429 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4469 | grouting for first stage slab of R.D tower axis B4 to B9/A6 to A12 | Grout | Slab | 30.00 | 7th | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4470 | steel reinforcement for shear wall 1 axis B1 to B5/A1 | Steel Reinforcement | SHW | 41.60 to 44.90 | 12th Floor | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4471 | top and bottom layer steel reinforcement for first stage slab axis B1 to B5/A1 to A3 | Steel Reinforcement | Slab | 38.40 | 10th Floor | 42429 | 42431 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4472 | tendons, strands, anchors and profiles for first stage of hotel slab axis B1 to B5/A1 to A3 | Cables | Slab | 38.40 | 10th Floor | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4473 | steel reinforcement for beams at first stage slab axis C2 to B1/A1 to A3 | Steel Reinforcement | Beams | 38.40 | 10th Floor | 42429 | 42429 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4474 | form work for first stage slab at Hotel axis B1 to B5/A1 to A3 | Form Work | Slab | 38.40 | 10th Floor | 42429 | 42429 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4475 | fixation of shear connectors for 1 column CC4 axis A10/B16 | Shear Connectors | Column | 26.70 to 30.00 | 6th | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4476 | tendons-strands- anchors and profiles for second stage of post tension slab axis B9 to B13/A6 to A12 | Cables | Slab | 30.00 | 7th | 42429 | 42432 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4477 | steel reinforcement for 2 columns CC7 axis A6/B14-B16 | Steel Reinforcement | Column | 26.70 to 30.00 | 6th | 42429 | 42430 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4478 | form work for 1 double column CC7 axis A6/B13 | Form Work | Column | 26.70 to 30.00 | 6th | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4479 | steel reinfrorcement for 5 columns CC4 axis D1, D2, D3, D4, A9/B19 | Steel Reinforcement | Column | 26.70 to 30.00 | 6th | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4480 | steel reinforcement for 1 column CC7 axis A12/B16 | Steel Reinforcement | Column | 26.70 to 30.00 | 6th | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4481 | form work for 5 columns CC4 axis D1, D2, D3, D4, A9/B19 | Form Work | Column | 26.70 to 30.00 | 6th | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4482 | form work for 2 columns CC7 axis A6/B14-B16 | Form Work | Column | 26.70 to 30.00 | 6th | 42429 | 42431 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4483 | steel reinforcement for second stage slab axis B9 to B13/A6 to A12 | Steel Reinforcement | Slab | 30.00 | 7th | 42429 | 42431 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4484 | steel reinforcement for 1 double column CC7 axis A6/B13 | Steel Reinforcement | Column | 26.70 to 30.00 | 6th | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4485 | steel reinforcement for slab of core 3 axis B10 to B12/A8 to A10 | Steel Reinforcement | Slab | 30.00 | 7th | 42429 | 42431 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4486 | form work for 1 column CC7 axis A12/B16 | Form Work | Column | 26.70 to 30.00 | 6th | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4487 | installation (torque) for 1 column CC9 axis A11/B14 | Composite Columns | Column | 26.70 to 30.00 | 6th | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4488 | steel reinforcement for core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | Core | 36.90 to 39.90 | 9th | 42429 | 42432 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4489 | form work for 1 column CC4 axis A10/B16 | Form Work | Column | 26.70 to 30.00 | 6th | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4490 | steel reinforcement for 1 column CC4 axis A10/B16 | Steel Reinforcement | Column | 26.70 to 30.00 | 6th | 42429 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4491 | steel reinforcement for 2 double columns CC1 axis B13/A10-A11 | Steel Reinforcement | Column | 26.70 to 30.00 | 6th | 42430 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4492 | form work for 2 double columns CC1 axis B13/A10-A11 | Form Work | Column | 26.70 to 30.00 | 6th | 42430 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4493 | steel reinforcement for 1 double column CC1* axis B13/A8 | Steel Reinforcement | Column | 26.70 to 30.00 | 6th | 42430 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4494 | form work for 1 double column CC1* axis B13/A8 | Form Work | Column | 26.70 to 30.00 | 6th | 42430 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4495 | steel reinforcement for stair case 3 axis A8 to A9/B6 to B8 | Steel Reinforcement | Stair | 30.00 to 33.30 | 7th | 42430 | 42434 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4496 | fixation of shear connector for 1 double column CC1* axis B13/A8 | Shear Connectors | Column | 26.70 to 30.00 | 6th | 42430 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4497 | form work removal for first stage of post tension slab at R.D tower axis B4 to B9/A6 to A12 | Removing Form Work | Slab | 30.00 | 7th | 42430 | 42431 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4498 | form work for shear wall 1 axis B1 to B5/A1 | Form Work | SHW | 41.60 to 44.90 | 11th Floor | 42430 | 42432 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4499 | steel reinforcement for B1 at driver stair case axis B19/A14 | Steel Reinforcement | Beams | -1.698 | BOH | 42430 | 42437 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4500 | form work for B1 at driver stair case axis B19/A14 | Form Work | Beams | -1.698 | BOH | 42430 | 42443 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4501 | steel reinforcement for stair case 4 axis A10/B7 to B8 | Steel Reinforcement | Stair | -0.45 to 1.10 | BOH | 42431 | 42439 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4502 | form work for stair case 4 axis B7 to B8/A10 | Form Work | Stair | -0.45 to 1.10 | BOH | 42431 | 42434 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4503 | form work for core 2 axis B14 to B15/A8 to A10 | Form Work | Core | 30.00 to 33.30 | 7th | 42431 | 42434 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4504 | form work for 1 column CC9 axis A11/B14 | Form Work | Column | 26.70 to 30.00 | 6th | 42431 | 42436 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4505 | steel reinforcement for 1 column CC9 axis A11/B14 | Steel Reinforcement | Column | 26.70 to 30.00 | 6th | 42431 | 42434 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4506 | stressing of strands for third stage post tension slab axis B13 to B17/A6 to A12 | Stressing | Slab | 26.70 | 6th | 42431 | 42436 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4507 | steel reinforcement for core 5 slab axis A8 to A10/B6 to B8 | Steel Reinforcement | Core | 33.30 | 8th | 42431 | 42445 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4508 | steel reinforcement for first stage slab at R.D tower axis B4 to B9/A6 to A12 | Steel Reinforcement | Slab | 33.30 | 8th | 42431 | 42445 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4509 | tendons, strands, anchors and profiles for first stage of R.D slab axis B4 to B9/A6 to A12 | Cables | Slab | 33.30 | 8th | 42431 | 42434 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4510 | form work for stair case 12 axis A2/B1 | Form Work | Stair | 28.40 to 31.70 | 7th | 42431 | 42434 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4511 | steel reinforcement for stair case 14 axis B16/A1 to A2 | Steel Reinforcement | Stair | 18.50 to 21.80 | 4th | 42431 | 42439 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4512 | fixation of shear connector for CC9 axis A11/B14 | Shear Connectors | Column | 26.70 to 30.00 | 6th | 42432 | 42434 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4513 | steel reinforcement for shear wall 9 axis A8 to A9/B9 | Steel Reinforcement | SHW | 30.00 to 33.30 | 7th | 42432 | 42435 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4514 | form work for shear wall 9 axis A8 to A9/B9 | Steel Reinforcement | SHW | 30.00 to 33.30 | 7th | 42432 | 42437 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4515 | form work for 2 columns CC9-A axis A11/B10-B12 | Form Work | Column | 30.00 to 33.30 | 7th | 42432 | 42436 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4516 | steel reinforcement for 2 columns CC9-A axis A11/B10-B12 | Steel Reinforcement | Column | 30.00 to 33.30 | 7th | 42432 | 42434 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4517 | steel reinforcement for 1 double column CC3-A axis A11/B9 | Steel Reinforcement | Column | 30.00 to 33.30 | 7th | 42432 | 42434 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4518 | form work for 1 double column CC3-A axis A11/B9 | Form Work | Column | 30.00 to 33.30 | 7th | 42432 | 42434 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4519 | form work for 2 columns CC7-A axis A6/B10-B12 | Form Work | Column | 30.00 to 33.30 | 7th | 42432 | 42434 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4520 | steel reinforcement for 2 columns CC7-A axis A6/B10-B12 | Steel Reinforcement | Column | 30.00 to 33.30 | 7th | 42432 | 42434 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4521 | form work for 1 double column CC7-B axis A6/B9 | Form Work | Column | 30.00 to 33.30 | 7th | 42432 | 42436 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4522 | steel reinforcement for 1 double column CC7-B axis A6/B9 | Steel Reinforcement | Column | 30.00 to 33.30 | 7th | 42432 | 42434 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4523 | form work for 1 double column CC1-A axis A10/B9 | Form Work | Column | 30.00 to 33.30 | 7th | 42432 | 42434 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4524 | steel reinforcement for 1 double column CC1-A axis A10/B9 | Steel Reinforcement | Column | 30.00 to 33.30 | 7th | 42432 | 42434 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4525 | grouting for cables ducts for first stage hotel slab axis C5 to B1/A1 to A3 | Grout | Slab | 35.00 | 9th | 42432 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4526 | tendons, strands, anchors and profiles second stage hotel slab axis C5 to B19/A1 to A3 | Cables | Slab | 35.00 | 9th | 42432 | 42436 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4527 | bottom layer steel reinforcement for second stage hotel tower slab axis C5 to B19/A1 to A3 | Steel Reinforcement | Slab | 35.00 | 9th | 42432 | 42435 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4528 | top layer steel reinforcement for second stage hotel slab axis C5 to B19/A1 to A3 | Steel Reinforcement | Slab | 35.00 | 9th | 42432 | 42435 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4529 | Steel Reinforcement for core 1 axis B16-B18-A9 | Steel Reinforcement | core | 26.70 to 30 | 6th | 42434 | 42436 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4530 | Form work for core 1 axis B6-A9 | Form Work | core | 26.70 to 30 | 6th | 42434 | 42437 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4531 | Form work for core 5 axis B8.B5-A11-A8 | Form Work | core | 36.60 To 39.90 | 9th | 42435 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4532 | Form work for stair case 7 B11.B10/A10 | Form Work | core | 30.00TO33.30 | 7th | 42435 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4533 | Form work for 3 columns CC7-A(A6/B5.6.8) | Form Work | Column | 33.30 to 36.60 | 8th | 42435 | 42437 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4534 | Steel Reinforcement for 3columns CC7-A Axis (A6/B5.6.8) | Steel Reinforcement | Column | 33.30 to 36.60 | 8th | 42435 | 42437 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4535 | form work for 4 columns CC7-A Axis (A7.11.B4) | Form Work | Column | 33.30 to 36.60 | 8th | 42435 | 42437 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4536 | Steel Reinforcement for 2 columns CC9-A axis A11/B6.8 | Steel Reinforcement | Column | 33.30 to 36.60 | 8th | 42435 | 42437 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4537 | Fixation of shear connector for 2 columns CC9-A Axis (A11.B6.8) | Shear Connectors | Column | 33.30 to 36.60 | 8th | 42435 | 42437 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4538 | form work for 2 columns CC9-A axis A11/B6-B8 | Form Work | Column | 33.30 to 36.60 | 8th | 42435 | 42439 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4539 | Steel reinforcement for 4 columns CC7-A Axis (A7.11.B4) | Steel Reinforcement | Column | 33.30 to 36.60 | 8th | 42435 | 42437 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4540 | stressing of strands for second stage post tension slab axis B9 to B13/A6 to A12 | Stressing | slab | 30.00 | 7th | 42435 | 42437 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4541 | Steel reinforcement for shear waal 8 C2/A2 To A3 | Steel Reinforcement | wall | 38.30 TO 41.60 | 11th Floor | 42435 | 42436 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4542 | form work for shear wall 8 C2/A2 TO A3 | Form Work | wall | 38.30 TO 41.60 | 11th Floor | 42435 | 42437 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4543 | form work removal for third post tension slab Axis A6 to A12 /B13.D3 | Form Work | slab | 26.70 | 6th | 42436 | 42438 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4544 | grouting for cables for third stage of post tension slab Axis A6 to A12 /B13.D3 | Cables | slab | 26.70 | 6th | 42436 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4545 | Form work for stair case 6 axis B10 to B11/A8 | Form Work | Stair | 30.00TO33.30 | 7th | 42436 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4546 | Steel reinforcement for core 3 | Steel Reinforcement | Core | 36.60 To 39.90 | 9th | 42436 | 42437 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4547 | form work for shear wall 1 | Form Work | wall | 41.60 to 44.90 | 10th Floor | 42436 | 42439 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4548 | Steel reinforcement for shear wall 1 B6 TO B19/A 1 | Steel Reinforcement | wall | 41.60 to 44.90 | 10th Floor | 42436 | 42439 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4549 | Steel reinforcement fo core wall 8 Axis B1 TO B2/A1 TO A3 | Steel Reinforcement | wall | 44.90 TO 48.20 | 13th floor | 42436 | 42439 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4550 | stressing for cables of first stag hotel tower slab Axis B1 TO C5/ A1 TO A3 | Stressing | slab | 38.30 | 10th Floor | 42436 | 42438 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4551 | Steel reinforcement for pour strip between second and third post tension slab | Steel Reinforcement | Slab | 26.70 | 6th | 42436 | 42437 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4552 | Form work removal for second post tension slab Axis A6.12/B9.13 | Form Work | Slab | 30.00 | 7th | 42437 | 42438 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4553 | Stressing of strands for first stage post tension slab Axis A6.12/B4.9 | Stressing | Slab | 33.30 | 8th | 42437 | 42438 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4554 | Steel rinforcement for Sh.W1+C1 | Steel Reinforcement | SHW | 35.00 to 38.30 | 10th Floor | 42441 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4555 | Steel reinforcement for pour strip between first and second stage axis B8 TO B9/A6 to A12 | Steel Reinforcement | Slab | 30.00 | 7th | 42437 | 42439 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4556 | Steel reinforcement for core 2Axis A8 TO A10 / B14 TO B16 | Steel Reinforcement | Core | 33.30 To 36.60 | 8th | 42438 | 42439 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4557 | grouting for cables for second stage of post tension slab axis B8 to B12/A6 to A12 | Grout | slab | 30.00 | 7th | 42438 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4558 | form work for stair case 11 axis B16 to B17/A9 | Form Work | stair | 26.70 TO 30.00 | 6th | 42438 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4559 | form work for core wall 8 Axis B1/A2 TO A3 | Form Work | wall | 44.90 TO 48.20 | 13th floor | 42438 | 42439 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4560 | Steel reinforcement for shear wall 6 Axis C4/A2 TO A3 | Steel Reinforcement | wall | 44.90 TO 48.20 | 13th floor | 42438 | 42439 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4561 | Form work for shear wall 6 Axis C4/A2 TO A3 | Form Work | Wall | 44.90 TO 48.20 | 13th floor | 42438 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4562 | form work for shear wall 7 axis C3/A2 to A3 | Form Work | Wall | 44.90 TO 48.20 | 13th floor | 42438 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4563 | steel reinforcement for shear wall 7 axis C3/A2 to A3 | Steel Reinforcement | Wall | 44.90 TO 48.20 | 13th floor | 42438 | 42443 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4564 | Steel rinforcement for temporary Opening at core 5 Axis A10/B6 TO B7 | Steel Reinforcement | core | 1.10 TO 5.40 | ground Floor | 42439 | 42443 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4565 | form work for columns Double shear wall 3* Axis C8/A2 TO A3 | Form Work | wall | 35.0 TO 38.3 | 10th Floor | 42439 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4566 | Steel Reinforcement For columns Double shear wall 3* Axis C8/A2 TO 3 | Steel Reinforcement | wall | 35.0 TO 38.3 | 10th Floor | 42439 | 42445 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4567 | Form Work For Columns and Walls Axis C10/A2TOA3 | Form Work | wall | 35.0TO38.3 | 10th Floor | 42439 | 42445 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4568 | Steel Reinforcement For Columns and shear walls Axis C10/A2 TO 3 | Steel Reinforcement | wall | 35.0TO38.3 | 10th Floor | 42439 | 42445 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4569 | Form work For Columns and Double shear wall 5* Axis C5/A2 TO A3 | Form Work | wall | 35.0 TO 38.3 | 10th Floor | 42439 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4570 | Steel Reinforcement for columns and Double shear wall 5* Axis C5/A2 TO A3 | Steel Reinforcement | wall | 35.0 TO 38.3 | 10th Floor | 42439 | 42443 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4571 | Form Work for Columns and Shear Walls Axis C6/A2 TO A3 | Form Work | wall | 35.0 TO 38.3 | 10th Floor | 42439 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4572 | Steel Reinforcement for columns and shear walls Axis C6/A2 TO A3 | Steel Reinforcement | wall | 35.0 TO 38.3 | 10th Floor | 42439 | 42445 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4573 | Form Work for Columns and Shear Walls CC5 & CC6 Axis A3/C9 &A3/C11 | Form Work | wall | 35.0 TO 38.3 | 10th Floor | 42439 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4574 | Steel Reinforcement For columns and sher walls CC5 & CC6 Axis A3/C9&A3 TO C11 | Steel Reinforcement | wall | 35.0 TO 38.3 | 10th Floor | 42439 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4575 | Steel Reinforcement For stair case 11 Axis A9/B16 to B17 | Steel Reinforcement | wall | 26.70 TO 30.00 | 6th | 42439 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4576 | Tendons-Sreands-Anchors and Profiles for third stage of post tension slab Axis A6 TO A12/B13 TO B19 | Post Tension | Slab | 30.00 | 3rd | 42441 | 42445 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4577 | Form work removal for first stage of slab Axis A6 TO A10/B4 TO B9 | Form Work | Slab | 33.30 | 7th | 42441 | 42443 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4578 | Top & bottom layers and beams Steel reinforcement for third post tension slab | Steel Reinforcement | Slab | 30.00 | 7th | 42441 | 42445 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4579 | form work for Sh.W1+C1 | Form Work | SHW | 35.00 to 38.30 | 10th Floor | 42441 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4580 | Steel reinforcement for column C5 Axis B18/A1 TO A3 | Steel Reinforcement | Column | 35.00 to 38.30 | 10th Floor | 42441 | 42445 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4581 | form work for column C5 axis B18/A1 to A3 | Form Work | Column | 35.00 to 38.30 | 10th Floor | 42441 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4582 | Steel reinforcement for core 6 axis B16 /A1 to A3 | Steel Reinforcement | Core | 35.00 to 38.30 | 10th Floor | 42441 | 42445 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4583 | Form work for core 6 Axis B16 / A1 TO A3 | Form Work | Core | 35.00 to 38.30 | 10th Floor | 42441 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4584 | Stressing for cables of second stage hotel tower slab Axis C5 To B19/A1 TO A3 | Stressing | Slab | 35.00 | 10th Floor | 42441 | 42445 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4585 | Form Work for core3 Axis A8 TO A10/B10 TO B12 | Form Work | Core | 36.60 To 39.90 | 9th | 42442 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4586 | Top & bottom Steel reinforcement for Surge tank ground slab Axis B2 TO B4/A4 TO A5 | Steel Reinforcement | Slab | -3.30 | BOH | 42442 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4587 | Steel reinforcement for stair case 7axis A10/B10 TO B11 | Steel Reinforcement | Stair | 30.00 TO 33.30 | 7th | 42442 | 42445 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4588 | Form Work Second stage | Form Work | Slab | 38.30 | 9th | 42442 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4589 | Form Work First stage Axis A6 TO A12 / B4 TO B9 | Form Work | Slab | 36.60 | 8th | 42442 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4590 | Form Work for stair case3 Axis A8/B6 TO B7 | Form Work | Stair | +33.30 TO 36.60 | 8th | 42443 | 42445 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4591 | Steel Reinforcement for stair case 6 axis A8/B11 TO B13 | Steel Reinforcement | Stair | +30.00 TO 33.30 | 7th | 42443 | 42445 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4592 | Form Work For Core 2 Level A8 TO A10/B14 TO B16 | Form Work | Core | +33.30 TO 36.60 | 8th | 42444 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4593 | Tendons-Strands- anchors and profiles for second stage of post tension slab axis A6 TO A1/B9TOB13 | Post Tension | Slab | +33.30 | 8th | 42444 | 42448 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4594 | Top&Bottom Layers and beams Steel Reinforcement for second post trnsion slab Axis A6 TO A1/B9 TO B13 | Steel Reinforcement | Slab | +33.30 | 8th | 42444 | 42448 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4595 | Steel Reinforcement for stair 12Axis A1 TO A2 /B1TO B2 | Steel Reinforcement | Stair | 28.40 to 31.70 | 8th | 42444 | 42452 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4596 | form work for core 7 axis A2 to A3/C7 | Form Work | Core | 41.60 to 44.90 | 13th floor | 42444 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4597 | steel reinforcement for core 7 axis C7/A2-A3 | Steel Reinforcement | Core | 41.60 to 44.90 | 13th floor | 42444 | 42448 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4598 | Steel reinforcement for driver stair Axis A14 TO A15/B18 TO B19 | Steel Reinforcement | Stair | -3.80 TO 1.10 | BOH | 42444 | 42452 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4599 | Form Work For driver Stair Axis A14 TO A15/B18 TO B19 | Form Work | Stair | -3.80 TO 1.10 | Podium | 42444 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4600 | Grouting for cable of second stage hotel tower slab | Cables | Grout | 31.70 | 8th | 42444 | 42449 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4601 | Steel reinforcement for pour strip Axis C5/A1 TO A3 | Steel Reinforcement | Pour strip | 31.70 | 8th | 42444 | 42448 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4602 | Bottom Steel Reinforcement for first stage hotel tower slab Axis C5 TO B1/A1TOA3 | Post Tension | Slab | 41.60 | 11th Floor | 42445 | 42448 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4603 | Top steel Reinforcement for first stage hotel tower slab Axis C5 TO B1/A1 TO A3 | Steel Reinforcement | Slab | 41.60 | 11th Floor | 42445 | 42448 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4604 | Tendons,strands,anchors and profiles first stage hotel tower slab Axis C5 TO B1/A1 TO A3 | Post Tension | Slab | 41.60 | 11th Floor | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4605 | Form work for First stage hotel tower slab Axis C5TOB1/A1toA3 | Form Work | Slab | 41.60 | 11th Floor | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4606 | Form work removal for first stage hotel tower slab Axis C5toB1/A1toA3 | Form Work | Slab | 38.30 | 10th Floor | 42445 | 42448 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4607 | Steel Reinforcement for CC7 Axis A6 TO B14 | Steel Reinforcement | Column | 30to+33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4608 | Form work for CC7 Axis A6 TO B14 | Form Work | Column | +30 to +33.30 | 7th | 42445 | 42449 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4609 | Steel Reinforcement For 2 CC7 Axis A6 TO B16/A12 to B16 | Steel Reinforcement | Column | +30 TO +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4610 | Form work for 2 CC7 Axis B16 TO A6/B16 TO A12 | Form Work | Column | +30 to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4611 | Shear Connector for 6 CC4 Axis D1,D2,D3,D4,(B16,A10),(B16,A10) ,(A9,B19) | Shear Connectors | Column | +30 to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4612 | Shear Connector for CC9 Axis +30 TO +33.30 | Shear Connectors | Column | +30 to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4613 | Form work for CC9 Axis B14,A11 | Form Work | Column | +30 to +33.30 | 7th | 42445 | 42449 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4614 | Steel reinforcement for CC9 Axis B14 TO A11 | Steel Reinforcement | Column | +30 to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4615 | Steel Reinforcement for 2 CC4 Axis D1TO D2 | Steel Reinforcement | Column | +30to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4616 | Form work for 2CC4 Axis D1,D2 | Form Work | Column | +30to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4617 | Form work for 2 CC4 Axis A9 TO B19/D3 | Form Work | Column | +30to +33.30 | 7th | 42445 | 42449 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4618 | Steel Reinforcement for 2 CC4Axis A9TO B19/D3 | Steel Reinforcement | Column | +30to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4619 | Shear Connector for 2DCC1 Axis B13/A11 to A10 | Shear Connectors | Column | +30to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4620 | Steel reinforcement for 2DCC1 Axis B13 to A11/B13toA10 | Steel Reinforcement | Column | +30to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4621 | Form work for 2DCC1 Axis B13toA11/B13toA10 | Form Work | Column | +30to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4622 | Form work for 2 CC4 Axis A10toB16/D4 | Form Work | Column | +30to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4623 | Steel Reinforcement for 2 CC4 Axis A10to B16/D4 | Steel Reinforcement | Column | +30to +33.30 | 7th | 42445 | 42448 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4624 | Shear Connector For DCC1* Axis B13toA8 | Shear Connectors | Column | +30to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4625 | Form work for CC1* Axis B13toA8 | Form Work | Column | +30to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4626 | Steel Reinforcement For DCC1* Axis B13 TO A8 | Steel Reinforcement | Column | +30to +33.30 | 7th | 42445 | 42448 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4627 | Form work for DCC7 Axis B13toA6 | Form Work | Column | +30to +33.30 | 7th | 42445 | 42449 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4628 | Steel Reinforcement for DCC7 Axis B13 to A6 | Steel Reinforcement | Column | +30to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4629 | Torque for CC1*East Axis B13toA8 | Composite Columns | Column | +30to +33.30 | 7th | 42445 | 42448 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4630 | Installation (Torque)For Column CC1* West Axis A8/B13 | Composite Columns | Column | +30.00 TO 33.30 | 7th | 42446 | 42449 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4631 | Fixation of shear connector for (DCC1)(DCC3)(CC1/Core4) Axis A8toA10&11/B9 | Shear Connectors | Column | +33.30to36.60 | 8th | 42446 | 42449 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4632 | Form work for 2 CC7A Axis A6/B10toB12 | Form Work | Column | +33.30to36.60 | 8th | 42446 | 42450 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4633 | Steel reinforcement for 2 CC7A Axis A6/B10toB12 | Steel Reinforcement | Column | +33.30to36.60 | 8th | 42446 | 42449 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4634 | Form work for 2 CC9A Axis A11/B10to B12 | Form Work | Column | +33.30to36.60 | 8th | 42446 | 42452 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4635 | Steel reinforcement for 2 CC9A | Steel Reinforcement | Column | +33.30to36.60 | 8th | 42446 | 42449 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4636 | Form work for (DCC7-B),(DCC1A)and (DCC3A) Axis A6toA10&A12/B9 | Form Work | Column | +33.30to36.60 | 8th | 42446 | 42452 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4637 | Steel Reinforcement for (DCC7-B),(DCC1A)and (DCC3A) Axis A6toA10&12/B9 | Steel Reinforcement | Column | +33.30to36.60 | 8th | 42446 | 42450 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4638 | Top&Bottom layers and beams Steel Reinforcement for(First Post tension slab+Core 5 Slab)Axis A6toA10/B4TOB9 | Post Tension | core | +36.60 | 9th | 42446 | 42449 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4639 | Tendons-Strands-Anchors and Profiles for first stage of post tension slab Axis A6toA10/B4toB9 | Post Tension | slab | +36.60 | 9th | 42446 | 42448 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4640 | Form work removval for second stage hotel tower slab Axis C5TO B19/A1TO A3 | Form Work | slab | 31.70 | 8th | 42446 | 42449 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4641 | Grouting for cables of first stage hotel tower slab Axis C5toB1/A1toA3 | Grout | Grout | 38.30 | 10th Floor | 42446 | 42449 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4642 | Sher conector for 2 CC9 Axis A11/B10.12 | Shear Connectors | Column | +33.30 TO 36.60 | 8th | 42448 | 42449 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4643 | Stressing of strands for third stage post tension slab Axis A6.12/B13.19 | Post Tension | slab | +30.00 | 7th | 42448 | 42453 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4644 | Grouting for cables for first stage of post tension slab Axis A6 to 12/B4to B9 | Post Tension | slab | +33.30 | 8th | 42448 | 42449 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4645 | Form work for core 1 Axis A8toA10/B17 | Form Work | Core | +30.00to33.30 | 7th | 42448 | 42449 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4646 | Steel Reinforcement for Core 1 Axis A8 TO A10/B17 | Steel Reinforcement | Core | +30.00 to 33.30 | 7th | 42448 | 42449 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4647 | Form work for SHW9 Axis A8 to A10/B9 | Form Work | SHW | +33.30 TO 36.60 | 8th | 42448 | 42452 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4648 | Steel reinforcement for SHW9 Axis A8 to A10/B9 | Steel Reinforcement | SHW | +33.30 TO 36.60 | 8th | 42448 | 42450 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4649 | Stressing of strands for second stage post tension slab axis A6 TO A12 /B8TO B13 | Post Tension | slab | +33.30 | 8th | 42450 | 42456 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4650 | Bottom Steel Reinforcement for Second Stage Hotel Tower slab Axis C5 TO B19 / A1TOA3 | Steel Reinforcement | slab | 38.30 | 10th Floor | 42450 | 42452 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4651 | Tendons,Strands,Anchors and profiles for second stage hotel tower slab Axis C5 TO B19 /A1 TO A3 | Post Tension | slab | 38.30 | 10th Floor | 42450 | 42456 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4652 | Top steel reinforcement for second stage hotel tower slab Axis C5 TO B19/A1 TO A3 | Steel Reinforcement | slab | 38.30 | 10th Floor | 42450 | 42452 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4653 | Steel reinforcement for columns and shear walls 8 Axis C2/A1 TO A3 | Steel Reinforcement | SHW | 41.60 to 44.90 | 12nd Floor | 42450 | 42452 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4654 | Form Work For Columns and shear walls 8 Axis C2/A2 TO A3 | Form Work | SHW | 41.60 to 44.90 | 12nd Floor | 42450 | 42452 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4655 | steel reinforcement for core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | core | +39.90 TO 43.20 | 9th | 42450 | 42452 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4656 | Form Work For Stair Case 6 Axis A8/B10 TO B12 | Form Work | case | +33.30 TO 36.60 | 8th | 42450 | 42452 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4657 | form work for stair case 7 axis A10/B10-B11 | Form Work | case | +33.30 TO 36.60 | 8th | 42450 | 42452 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4658 | Steel reinforcement for Core3 Axis A8 TO A10/B10 TO B12 | Steel Reinforcement | Core | +39.90 TO 43.20 | 9th | 42451 | 42452 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4659 | Form Work For 3 CC7-A Axis A6/B5TOB6&B8 | Form Work | Column | +36.60 TO 39.90 | 9th | 42451 | 42453 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4660 | steel reinforcement For 3 CC7-A Axis A6/B5TOB6&B8 | Steel Reinforcement | Column | +36.60 TO 39.90 | 9th | 42451 | 42453 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4661 | Steel Reinforcement For 4 CC7-A Axis A8 TO A9,A10&A11/B4 | Steel Reinforcement | Column | +36.60 TO 39.90 | 9th | 42451 | 42453 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4662 | Form work For 4 CC7-A Axis Axis A8 TO A9,A10&A11/B4 | Form Work | Column | +36.60 TO 39.90 | 9th | 42451 | 42453 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4663 | Steel reinforcement for 2 CC9-A Axis A11/B6 TO B8 | Steel Reinforcement | Column | +36.60 TO 39.90 | 9th | 42451 | 42453 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4664 | Form work For 2CC9-A Axis A11/B6 TO B8 | Form Work | Column | +36.60 TO 39.90 | 9th | 42451 | 42453 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4665 | Stressing For Cables Of First stag hotel tower slab Axis C5 TO B1/A1 TO A3 | Stressing | Slab | 41.60 | 11th Floor | 42451 | 42452 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4666 | Form work For Stair 14 Axis B15 TO B16 / A1 TO A2 | Form Work | stair | 21.80 to 25.10 | 6th | 42451 | 42456 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4667 | Form Work Removal For Second stage hotel tower slab Axis C5 TO B19/A1 TO A2 | Form Work | Slab | 35.00 | 9th | 42451 | 42455 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4668 | Check form work for Slab 33.30 third stage Level 33.30 | Form Work | Slab | 33.30 | 8th | 42451 | 42452 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4669 | Grouting For Cables Of second hotel tower slab Axis C5 TO B19 / A1 TO A3 | Grout | Slab | 35.00 | 9th | 42452 | 42455 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4670 | Form Work for stair case 11 Axis A7 TO A8 / B16 TO B17 | Form Work | Case | 30.00 TO 33.30 | 7th | 42452 | 42452 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4671 | Steel Reinforcement for stair case 10 Axis A6 TO A7/B14 TO B15 | Steel Reinforcement | Case | -3.80 TO -0.45 | BOH | 42452 | 42458 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4672 | Steel reinforcement for core 2 Axis A8 TO A10 / B14 TO B16 | Steel Reinforcement | Core | 36.60 TO 39.90 | 9th | 42452 | 42456 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4673 | Steel reinforcement for beams at third post tension slab Axis A6 TO A10 /B13 | Steel Reinforcement | Slab | +33.30 | 8th | 42452 | 42458 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4674 | Form work for shear Wall 1 Axis C7 TO B19/A1 | Form Work | SHW | 44.90 TO 48.20 | 13th floor | 42452 | 42456 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4675 | Steel reinforcement for shear wall 1 Axis C7 TO B19 / A1 | Steel Reinforcement | SHW | 44.90 TO 48.20 | 13th floor | 42452 | 42455 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4676 | Form Work For Core 5 Axis A8 TO A10/B6 TO B8 | Form Work | Core | +39.90 TO 43.20 | 9th | 42453 | 42455 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4677 | Steel reinforcement for stair 14 Axis B15 to B16/A1 TO A2 | Steel Reinforcement | Stair | 21.80 to 25.10 | 8th | 42453 | 42457 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4678 | Form Work For Sher Wall 3 Axis C6 /A2 TO A3 | Form Work | SHW | 38.30 TO 41.60 | 10th Floor | 42453 | 42456 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4679 | Steel reinforcement for Shear Wall 3 Axis C6 /A2 TO A3 | Steel Reinforcement | SHW | 38.30 TO 41.60 | 10th Floor | 42453 | 42455 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4680 | Form Work Removal For third Stage Of post tension slab Axis A7 TO A8/B16 TO B17 | Form Work | Slab | +30.00 | 7th | 42453 | 42455 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4681 | Form Work Removal For First stage Hotel Tower Slab Axis C5 TO B1/A1 TO A2 | Form Work | Slab | 41.60 | 9th | 42456 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4682 | Steel Reinforcement for stair 11 Axis B17/A9 | Steel Reinforcement | stair | 30.00 TO 33.30 | 8th | 42455 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4683 | Grouting for cables of third stage RD tower slab Axis B13 TO B19 / A6 TO A12 | Grout | Slab | 30.00 | 7th | 42455 | 42467 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4684 | Steel reinforcement for pour strip between second and third stage RD tower Slab Axis B12 TO B13 / A6 TO A12 | Steel Reinforcement | Slab | 30.00 | 7th | 42455 | 42456 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4685 | form work for columns CC5/CC6 AXIS C1/A2.A3 | form work | Column | 38.30TO41.60 | 10th Floor | 42455 | 42456 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4686 | steel reinforcement for columns cc5/cc6 axis C1/A2.A3 | Steel Reinforcement | Column | 38.30TO41.60 | 10th Floor | 42455 | 42457 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4687 | steel reinforcement for shear wall2 AXIS C10/A2.A3 | Steel Reinforcement | SWH | 38.30TO41.60 | 10th Floor | 42455 | 42457 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4688 | form work for shear wall2 AXIS C10/A2.A3 | form work | SWH | 38.30TO41.60 | 10th Floor | 42455 | 42456 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4689 | steel reinforcement for shear wall2/3* AXIS C8/A2.A3 | Steel Reinforcement | SWH | 38.30TO41.60 | 10th Floor | 42455 | 42457 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4690 | form work for shear wall D2/3* Axis c8/A2.A3 | Form work | SWH | 38.30TO41.61 | 10th Floor | 42455 | 42456 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4691 | form work for shear wall D 5/5* Axis C5/A2.A3 | Form work | SWH | 38.30TO41.61 | 10th Floor | 42455 | 42456 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4692 | steel reinforcement for shear wall D 5/5* Axis C5/A2.A3 | Steel Reinforcement | SWH | 38.30TO41.61 | 10th Floor | 42455 | 42457 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4693 | Steel Reinforcement for Column C5 Axis B18/A1 | Steel Reinforcement | Column | 38.30TO41.61 | 10th Floor | 42455 | 42457 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4694 | Form work for Column C5 Axis B18/A1 | Form work | Column | 38.30TO41.61 | 10th Floor | 42455 | 42457 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4695 | Steel Reinforcement For Sher Wall 1+C1 Axis B19 / A1 | Steel Reinforcement | SHW | 38.30TO41.61 | 10th Floor | 42455 | 42457 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4696 | Form Work For Sher Wall 1+ C1 Axis B19/A1 | Form work | SHW | 38.30TO41.61 | 10th Floor | 42455 | 42457 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4697 | Top Steel Reinforcement For third stage RD tower Slab Axis A6 TO A12 /B13 TO B19 | Steel Reinforcement | third stage | 33.30 | 7th | 42456 | 42458 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4698 | Tendons,Strands,Anchors and profiles third stage RD Tower Slab Axis A6 TO A12 / B13 TO B19 | Post Tension | third stage | 33.30 | 7th | 42456 | 42458 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4699 | Bottom Steel reinforcement For third stage RD Tower Slab Axis A6 TO A12/ B13 TO B19 | Steel Reinforcement | third stage | 33.30 | 7th | 42456 | 42458 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4700 | Steel Reinforcement For Core 6 Axis B15 TO B16/A1 TO A2 | Steel Reinforcement | Core | 38.30 TO 41.60 | 10th Floor | 42456 | 42457 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4701 | Form Work For Core 6 Axis B15 TO B16 / A1 TO A2 | Form Work | Core | 38.30 TO 41.60 | 10th Floor | 42456 | 42458 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4702 | Form Work For Stair 12 Axis B1 TO B2/ A1 TO A2 | Form Work | Stair | 31.70 TO 35.00 | 11th Floor | 42456 | 42456 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4703 | Stressing for cables of second stage hotel tower slab Axis C5 To B19/A1 TO A3 | Stressing | Slab | 38.30 | 9th | 42456 | 42458 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4704 | Grouting for cables of first stage hotel tower slab Axis C5 TO B1 /8A1 TO A3 | Grout | Slab | 41.60 | 9th | 42456 | 42459 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4705 | steel reinforcement for stair 6 Axis A10/B10 TO B11 | Steel Reinforcement | stair | 33.30 TO 36.60 | 8th | 42456 | 42460 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4706 | steel reinforcement for stair 7 Axis A10/B10 TO B11 | Steel Reinforcement | stair | 33.30 TO 36.60 | 8th | 42456 | 42460 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4707 | Form Work For Core 3 Axis A8 TO A10 /B10 TO B12 | Form work | Core | 39.90 TO 43.20 | 9th | 42457 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4708 | form work for slab second stage | Form work | Slab | 36.60 | 9th | 42458 | 42458 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4709 | Steel Reinforcement For Core 8 Axis A1 TO A3 /B1 TO B2 | Steel Reinforcement | Core | 48.20 TO 50.00 | 7th | 42458 | 42459 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4710 | Steel Reinforcement For Pour strip between first and second stage Axis A6 TO B8 TO B9 | Steel Reinforcement | slab | +33.30 | 8th | 42458 | 42458 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4711 | Form work Removal for Second stage of Post tension Slab Axis A6 TO A12 B9 TO B13 | Form work | slab | +33.30 | 8th | 42458 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4712 | form work for core 7 axis A2 to A3/C7 | Form work | Core | 44.90 TO 48.20 | 13th floor | 42458 | 42464 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4713 | form work for shear wall 1 Axis B1 to C7/A1 | Wall | SHW | 44.90 TO 48.20 | 13th floor | 42458 | 42462 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4714 | steel reinforcement for shear wall 1 axis B1 to C7/A1 | Wall | SHW | 44.90 TO 48.20 | 13th floor | 42458 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4715 | steel reinforcement for core 7 axis C7/A2-A3 | Core | Core | 44.90 TO 48.20 | 13th floor | 42458 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4716 | Form Work For Core 8 Axis B1 TO B2/A1 TO A3 | Core | Core | 48.20 TO 50.00 | 13th floor | 42458 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4717 | Form Work For Slab First Stage | form work | Slab | 39.90 | 9th | 42459 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4718 | Steel Reinforcement For Stair 12 Axis B1 TO B2 /A1 TO A2 | Steel Reinforcement | Stair | 31.70 TO 35.00 | 9th | 42459 | 42463 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4719 | Form Work Removal For First Stage Of Post tension slab Axis A6 TO A12 /B4 TO B9 | Form Work | Slab | +36.60 | 9th | 42459 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4720 | Shear Connector For CC9 Axis B14 TO A11 | Shear Connectors | Column | 33.30 TO 36.60 | 8th | 42459 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4721 | Steel Reinforcement For CC1* Axis B13 TO A8 | Steel Reinforcement | Column | 33.30 TO 36.60 | 8th | 42459 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4722 | Form Work For CC1*Axis B13 TO A8 | Form Work | Column | 33.30 TO 36.60 | 8th | 42459 | 42462 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4723 | Shear Connector For CC1* Axis B13 TO A8 | Shear Connectors | Column | 33.60 TO 36.60 | 8th | 42459 | 42465 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4724 | Steel Reinforcement for DCC7 Axis B13 to A6 | Steel Reinforcement | Column | 33.30 TO 36.60 | 8th | 42459 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4725 | Form work for DCC7 Axis B13toA6 | Form work | Column | 33.30 TO 36.60 | 8th | 42459 | 42462 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4726 | Steel Reinforcement For 3 CC7 Axis B16 TO B14 /A6 )-(B16 /A12) | Steel Reinforcement | Column | 33.30 TO 36.60 | 8th | 42459 | 42460 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4727 | Form work For CC7 Axis B16 TO B14/A6)-(B16 TO A12 ) | Form work | Column | 33.30 TO 36.60 | 8th | 42459 | 42462 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4728 | Steel Reinforcement For 5CC4 Axis D1 TO D2 TO D3 &D4 A9 / B19 | Steel Reinforcement | Column | 33.30 TO 36.60 | 8th | 42459 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4729 | Form work For 5 CC4 Axis D1,D2,D3,D4,A9/B19 | Form work | Column | 33.30 TO 36.60 | 8th | 42459 | 42465 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4730 | Shear Connector For 6 CC4 Axis D1,D2,D3,D4,(B16,A10),(A9,B19) | Shear Connectors | Column | 33.30 TO 36.60 | 8th | 42459 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4731 | Stell Reinforcement For CC9 Axis B14 / A11 | Steel Reinforcement | Column | 33.30 TO 36.60 | 8th | 42459 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4732 | Form work for CC9 Axis B14,A11 | Form work | Column | 33.30 TO 36.60 | 8th | 42459 | 42465 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4733 | Top & Bottom Layers and Beams Steel Reinforcement For Second Post Tension Slab Axis A6 TO A10 / B9 B13 | Steel Reinforcement | Slab | +36.60 | 9th | 42459 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4734 | Tendos-Strands-Anchors And Profiles For Second Stage Of Post Tension Slab Axis A6 TO A10 / B9 TO B13 | Post Tension | Slab | +36.60 | 9th | 42459 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4735 | Shear Connector For 2 DCC1 Axis B13/A11 TO A10 | Shear Connectors | Column | 33.30 TO 36.60 | 8th | 42459 | 42465 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4736 | Form work For 2 DCC1 Axis B13 TO A11 /B13 TO A10 | Form work | Column | 33.30 TO 36.60 | 8th | 42459 | 42465 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4737 | Steel reinforcement for 2DCC1 Axis B13 to A11/B13toA10 | Steel Reinforcement | Column | 33.30 TO 36.60 | 8th | 42459 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4738 | Form Work For Slab First Stage Hotel | Form Work | Slab | 44.90 | 11th Floor | 42459 | 42466 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4739 | Form Work For Slab Second Stage Hotel | Form Work | Slab | 41.60 | 10th Floor | 42459 | 42462 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4740 | Form Work For Column CC4 Axis A10/B16 | Form Work | Column | 33.30 TO 36.60 | 8th | 42460 | 42465 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4741 | Steel Reinforcement For Column CC4 Axis A10/B16 | Steel Reinforcement | Column | 33.30 TO 36.60 | 8th | 42460 | 42460 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4742 | form work Removable for Driver Stair Case | Form Work | Stair | -3.80to+1.10 | BOH | 42460 | 42462 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4743 | Stressing Of strands for third stage post tension slab Axis A6 TO A12 / B13 TO B19 | Post Tension | Slab | +33.30 | 8th | 42462 | 42474 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4744 | Form work for core2 Axis A8 TO A10/B14 TO B16 | form work | Core | 36.60 TO 39.90 | 9th | 42462 | 42464 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4745 | Steel Reinforcement For core1 Axis A8 TO A10/B17 | Steel Reinforcement | Core | 36.60 TO 39.90 | 9th | 42462 | 42467 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4746 | Form work for core1 Axis A8 TO A10 / B17 Axis A8 TO A10/B17 | form work | Core | 33.30 TO 36.60 | 8th | 42462 | 42467 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4747 | Steel reinforcement for 2CC7-A Axis A6/B10 TO 12 | Steel Reinforcement | Column | 36.60 TO 39.90 | 9th | 42462 | 42465 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4748 | Form work For 2 CC7-A Axis A6/B10 TO12 | form work | Column | 36.60 TO39.90 | 9th | 42462 | 42465 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4749 | Form WOrk For (DCC7-B),(DCC1-A)And (DCC3A) Axis A6 TOA10 &A12/B9 | Form work | Column | 36.60 TO39.90 | 9th | 42462 | 42467 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4750 | Steel reinforcement For (DCC7-B),(DCC1-A)And (DCC3A) Axis A6 TOA10 &A12/B9 | Steel Reinforcement | Column | 36.60 TO39.90 | 9th | 42462 | 42467 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4751 | Form work for 2 CC9-A Axis A11/B10 TO B12 | Form work | Column | 36.60 TO39.90 | 9th | 42462 | 42465 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4752 | Steel Reinforcement for 2 CC9-A Axis A11/B10 TO B12 | Steel Reinforcement | Column | 36.60 TO39.90 | 9th | 42462 | 42465 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4753 | Steel Reinforcement For SH.W9 Axis A8 TO A10/B9 | Steel Reinforcement | Column | 36.60 TO39.90 | 9th | 42462 | 42467 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4754 | Form work for SH.W 9 Axis A8 TO A10/B9 | Form work | SHW | 36.60 TO39.90 | 9th | 42462 | 42467 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4755 | Steel Rinforcement For Core 5 Axis A8 TO A10 /B6 TO B8 | Steel Reinforcement | Core | 43.20 TO 46.50 | 11th Floor | 42463 | 42465 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4756 | Steel Reinforcement For Stair Case 3 axis A8/B6 to B7 | Steel Reinforcement | Case | 36.60 TO 39.90 | 9th | 42463 | 42467 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4757 | Top&Bottom layers and beams Steel Reinforcement for First post tension slab Axis A6 TO A10 / B4 TO B9 | Steel Reinforcement | Slab | +39.90 | 10th Floor | 42464 | 42466 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4758 | Duct grouting for cable at first stage post tension slab Axis A6 TO A12 / B4 TO B9 | Grout | Slab | +36.60 | 9th | 42464 | 42467 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4759 | Tendos-Strands-Anchors And Profiles For First stage of post tension slab Axis A6 TO A10 / B4 TO B9 | Post Tension | Slab | +39.90 | 10th Floor | 42464 | 42466 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4760 | Duct grouting for cable at Second stage post tension slab Axis A6 TO A12 / B9 TO B13 | Post Tension | Slab | +33.30 | 8th | 42464 | 42465 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4761 | Stressing of strands for second stage post tension slab Axis A6 TO A12/B4 TO B9 | Post Tension | Slab | +36.60 | 9th | 42464 | 42466 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4762 | Bottom , top layer and beam steel reinforcement work for part 2 of P.T slab Axis B6 TO B20/A1 TO A4 | Post Tension | Slab | 41.60 | 11th Floor | 42465 | 42467 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4763 | Tendons,Strands,Anchors And Profiles For Slab Axis B6 TO B20/A1 TO A4 | Post Tension | Slab | 41.60 | 11th Floor | 42465 | 42467 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4764 | Drilling, Fixing for shear wall (6&7) | Fixing | SH.W | 44.90 | 12th Floor | 42465 | 42470 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4765 | form work for stair case 7 axis A10/B10-B11 | Form work | stair | + 36.60 TO 39.90 | 9th | 42465 | 42470 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4766 | steel reinforcement for columns as shown in attached sketch at level 1.10 | Steel Reinforcement | Column | 1.10 | ground Floor | 42466 | 42473 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4767 | Steel Reinforcement For core 3 Axis A8 TO A10/B10 to B12 | Steel Reinforcement | Core | + 43.20 TO 46.50 | 11th Floor | 42466 | 42470 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4768 | Steel reinforcement For 3CC7-A Axis A6 / B5 TO B6 & B8 | Steel Reinforcement | Core | + 39.90 to 43.20 | 9th | 42466 | 42467 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4769 | Form Work For 3CC7-A Axis A6 / B5 TO B6 & B8 | Form Work | Column | + 39.90 to 43.20 | 9th | 42466 | 42469 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4770 | Steel reinforcement For 4CC7-A Axis A8 TO A9 & A10 /B4 | Steel Reinforcement | Column | + 39.90 to 43.20 | 9th | 42466 | 42472 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4771 | Form Work For 4 CC7-A Axis A8 TO A9 & A10 /B4 | Form Work | Column | + 39.90 to 43.20 | 9th | 42466 | 42472 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4772 | Steel Reinforcement for 2 CC9-A Axis A11/B6 TO B8 | Steel Reinforcement | Column | + 39.90 to 43.20 | 9th | 42466 | 42467 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4773 | Form Work for 2 CC9-A Axis A11/B6 TO B8 | Form Work | Column | + 39.90 to 43.20 | 9th | 42466 | 42469 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4774 | Form Work For Core 5 Axis A7to A11/ B5 TO B9 | Form Work | core | 43.20 TO 46.50 | 11th Floor | 42467 | 42469 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4775 | Steel Reinforcement For SH.W 7 | Steel Reinforcement | SH.W | 48.20 TO 51.5 | 13th floor | 42467 | 42470 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4776 | Steel Reinforcement For SH.W 6 | Steel Reinforcement | SH.W | 48.20 TO 51.5 | 13th floor | 42467 | 42470 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4777 | Steel Reinforcement For SH.W1 Axis B11 TO B19 | Steel Reinforcement | SH.W | 48.20 TO 51.50 | 14th floor | 42469 | 42474 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4778 | Form Work For SH.W1 Axis B11 TO B19 | Form work | SH.W | 48.20 TO 51.50 | 12th Floor | 42469 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4779 | Form work for SH.W1 Axis B1TO B5 | Form work | SH.W | 48.20 TO 51.50 | 12th Floor | 42470 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4780 | Steel Reinforcement For SH.W1 Axis B1 TO B5 | Steel Reinforcement | SH.W | 48.20 TO 51.50 | 12th Floor | 42470 | 42478 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4781 | Steel Reinforcement For SH.W 5/5* Axis B6 / A2 | Steel Reinforcement | SH.W | 41.60 to 44.90 | 12th Floor | 42470 | 42473 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4782 | Form work for SH.W5/5* Axis B1TO B5 | Form work | SH.W | 41.60 to 44.90 | 12th Floor | 42470 | 42473 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4783 | Form work for SH.W3 Axis C6/A2 TO A3 | Form work | SH.W | 41.60 to 44.90 | 12th Floor | 42470 | 42472 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4784 | Steel Reinforcement for SH.W3 Axis C6/A2 TO A3 | Steel Reinforcement | SH.W | 41.60 to 44.90 | 12th Floor | 42470 | 42472 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4785 | Form Work For SH.W 2*/3* Axis B12/A2 TO A3 | Form Work | SH.W | 41.60 to 44.90 | 12th Floor | 42470 | 42473 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4786 | Steel reinforcement For SH.W 2*/3* Axis B12/A2 TO A3 | Steel Reinforcement | SH.W | 41.60 to 44.90 | 12th Floor | 42470 | 42473 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4787 | Form Work For SH.W6 Axis C4/A2 TO A3 | Form Work | SH.W | 48.20 to 51.50 | 12th Floor | 42470 | 42473 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4788 | Steel reinforcement For Temporary Opening at Core 5 Axis A10/B6 TO B7 | Steel Reinforcement | Core | + 1.10 TO 5.40 | ground Floor | 42471 | 42479 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4789 | Form Work For SH.W7 Axis C3/A2 TO A3 | Form Work | SH.W | 48.20 to 51.50 | 12th Floor | 42470 | 42473 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4790 | TOP LAYER STEEL REINFORCEMENT FOR SLAB | Steel Reinforcement | slab | 44.9 | 12th Floor | 42470 | 42472 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4791 | Tendons,Strands,Anchors And Profiles For Slab (Part1)Axis C3/A2 TO A3 | Steel Reinforcement | Slab | 44.90 | 12th Floor | 42470 | 42472 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4792 | Form Work For Stair Case11 Axis A7 TO A8/B16 TO B17 | Form work | Case | 33.30 TO 36.60 | 8th | 42470 | 42473 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4793 | Form Work For Stair Case 6 Axis A8/B10 TO B12 | Form work | Case | + 36.60 TO 39.90 | 9th | 42470 | 42473 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4794 | Steel Reinforcement For Pour Strip between First and second stage Axis A6 TO A12/ B8 TO B9 | Steel Reinforcement | Stage | 36.60 | 9th | 42470 | 42472 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4795 | Stressing Of Strands For Furst Stage Post tension Slab Axis A6 TO A12/ B4 TO B9 | Post Tension | Stage | + 39.90 | 10th Floor | 42470 | 42473 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4796 | Steel Reinforcement For Stair Case 11 Axis A7 TO A8 / B16 TO B17 | Steel Reinforcement | stair | 33.30 TO 36.60 | 8th | 42471 | 42474 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4797 | Form Work for columns as shown in attached sketch at level 1.10 | Form work | Column | 1.10 | ground Floor | 42472 | 42473 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4798 | Steel Reinforcement for stair case 6 Axis A8/B10 TO B12 | Steel Reinforcement | stair | + 36.60 TO 39.90 | 9th | 42472 | 42477 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4799 | Top & Bottom Layers and beamss steel rinforcement For Third post tension Slab Axis A6 TO A10/ B13TO B19 | Steel Reinforcement | Slab | + 36.60 | 9th | 42473 | 42474 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4800 | Tendons-Strands-Anchors and Profiles for Second Stage Of Post tension Slab Axis A6 TO A12/B13 TO B19 | Form Work | Slab | + 36.60 | 9th | 42473 | 42474 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4801 | Steel reinforcement For Stair Case 7 Axis A10/B10 TO B11 | Steel Reinforcement | Case | + 36.60 TO 39.90 | 9th | 42473 | 42477 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4802 | Form work For Slab First Stage Residential Tower | Form Work | First Stage | 43.20 | 10th Floor | 42474 | 42477 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4803 | Steel Reinforcement For Column C5 Axis B18/A1 | Steel Reinforcement | C5 | 41.60 TO 44.90 | 12nd Floor | 42472 | 42473 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4804 | Form Work For Column C5 Axis B18/A1 | Form Work | C5 | 41.60 TO 44.90 | 12nd Floor | 42472 | 42473 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4805 | Steel Reinforcement For Columns CC5&CC6 | Steel Reinforcement | CC5&CC6 | 41.60 TO 44.90 | 12nd Floor | 42472 | 42473 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4806 | Form woork for columns CC5&CC6 Axis C9 TO C11/ A3 | Form work | CC5&CC6 | 41.60 TO 44.90 | 12nd Floor | 42472 | 42473 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4807 | Steel Reinforcement For Core 6 Axis B15 TO B16/A1 | Steel Reinforcement | Core | 41.60 TO 44.90 | 12nd Floor | 42472 | 42474 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4808 | Form Work For Core 6 Axis B15 TO 16/ A1 | Form Work | Core | 41.60 TO 44.90 | 12nd Floor | 42472 | 42474 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4809 | Steel Reinforcement For Shear Wall1+C1 Axis B19/A1 | Steel Reinforcement | SH.W 1+C1 | 41.60 TO 44.90 | 12nd Floor | 42472 | 42474 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4810 | Form work For Shear Wall 1+C1 Axis B19/ A | Form work | SH.W 1+C1 | 41.60 TO 44.90 | 12nd Floor | 42472 | 42474 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4811 | form work for shear wall2 AXIS C10/A2.A3 | Form work | SH.W 2 | 41.60 TO 44.90 | 12nd Floor | 42473 | 42473 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4812 | Steel reinforcement for shear wall2 AXIS C10/A2.A3 | Steel Reinforcement | SH.W 2 | 41.60 TO 44.90 | 12nd Floor | 42473 | 42473 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4813 | Form work For Slab Third stage Axis A6 TO A12/B13TOB19 | Form work | third stage | 36.60 | 9th | 42473 | 42477 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4814 | Form work For Slab second stage Axis B8 TO B13/A6 TO A12 | Form work | second stage | 39.90 | 9th | 42473 | 42477 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4815 | Top&Bottom Layers And Beams Steel Reinforcement For Second Post Tension Slab Axis A6 TO A10/B9 TO B13 | Steel Reinforcement | second stage | + 39.90 | 9th | 42474 | 42477 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4816 | Tendos-Strands-Anchors And Profiles For Second Stage Of Post Tension Slab Axis A6 TO A10 / B9 TO B13 | Form work | second stage | + 39.90 | 9th | 42474 | 42477 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4817 | form work for shear wall 8 axis C2/A2 to A3 | Form work | SH.W | 44.90 TO 48.20 | 13th floor | 42474 | 42477 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4818 | steel reinforcement for shear wall 8 axis C2/A2 to A3 | Steel Reinforcement | SH.W | 44.90 TO 48.20 | 13th floor | 42474 | 42477 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4819 | Form Work Removal For First Stage Of Post tension slab Axis A6 TO A12 /B4 TO B9 | form work | First Stage | + 39.90 | 9th | 42476 | 42479 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4820 | Steel Reinforcement For Core8 Axis B1/A2 TO A3 | Steel Reinforcement | Core | 50.00 TO 53.30 | 15th Floor | 42474 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4821 | Form work For Core 3 Axis A8 TO A11/B10 TOB12 | Form work | Core | 43.20 TO 46.50 | 11th Floor | 42474 | 42477 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4822 | Steel Reinforcement For Pour Strip Between Second And third Stage Axis A6 TO A12 / B12 TO B13 | Steel Reinforcement | second stage & third stage | + 33.30 | 8th | 42474 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4823 | Form Work For Stair Case 3 axis B6 to B7/A8 | Form Work | First Stage | 39.90 TO 43.20 | 10th Floor | 42476 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4824 | Steel Reinforcement For Stair Case 3 Axis A8/B6 TO B7 | Steel Reinforcement | First Stage | 39.90 TO 43.20 | 10th Floor | 42476 | 42486 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4825 | Form work Removal for second stage of post tension Slab Axis A6 TO A12 B8 TO B13 | Form work | second stage | + 36.60 | 9th | 42476 | 42479 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4826 | Installation (Torque)For Column CC1* West Axis A8/B13 | Torque | third stage | + 36.60 TO 39.90 | 9th | 42476 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4827 | Form Work For CC4 Axis A11/B16 | Form Work | third stage | + 36.60 TO 39.90 | 9th | 42476 | 42481 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4828 | Steel Reinforcement For CC4 Axis A11/B16 | Steel Reinforcement | third stage | + 36.60 TO 39.90 | 9th | 42476 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4829 | Steel Reinforcement For Core 2 Axis A8 TO A10/B14 TO B16 | Steel Reinforcement | Core | + 39.90 TO 43.20 | 9th | 42476 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4830 | Steel reinforcement For 5 CC4 Axis D1,D2,D3,D4,A9/B19 | Steel Reinforcement | third stage | +36.60 TO 39.90 | 9th | 42476 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4831 | Form work For 5 CC4 Axis D1,D2,D3,D4,A9/B19 | Form work | third stage | +36.60 TO 39.90 | 9th | 42476 | 42479 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4832 | Form Work For CC9 Axis B14/A11 | Form work | third stage | +36.60 TO 39.90 | 9th | 42476 | 42481 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4833 | Steel reinforcement for CC9 Axis B14 /A11 | Steel Reinforcement | third stage | +36.60 TO 39.90 | 9th | 42476 | 42479 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4834 | Steel Reinforcement For DCC7 Axis B13 /A6 | Steel Reinforcement | third stage | +36.60 TO 39.90 | 9th | 42476 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4835 | Form work for DCC7 Axis B13toA6 | Form work | third stage | +36.60 TO 39.90 | 9th | 42476 | 42479 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4836 | Shear Connector For CC1* Axis B13 TO A8 | Shear Connectors | third stage | 36.60 TO 39.90 | 9th | 42476 | 42479 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4837 | Steel reinforcement for 2DCC1 Axis B13 to A11/B13toA10 | Steel Reinforcement | third stage | +36.60 TO 39.90 | 9th | 42476 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4838 | Form Work For 2 DCC1 Axis B13/A11/B13/A10 | Form work | third stage | +36.60 TO 39.90 | 9th | 42476 | 42483 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4839 | Form Work For 3CC7 Axis B16 TO B14/A6-B16/A12 | Form work | third stage | +36.60 TO 39.90 | 9th | 42476 | 42479 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4840 | Steel Reinforcement For 3 CC7 Axis B16 TO B14 /A6 )-(B16 /A12) | Steel Reinforcement | third stage | +36.60 TO 39.90 | 9th | 42476 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4841 | Grouting For Cables Of Second Stage Post tension Slab Hotel Tower Axis C7/A2 TO A3 | Grout | Grout | 38.30 | 10th Floor | 42476 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4842 | Stressing For Cables Of First Stage Post Tension Slab hotel tower Axis B1 TO C5/A1 TO A3 | Stressing | Stressing | 44.90 | 12th Floor | 42476 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4843 | Form work For Core 8 Axis B1/A2,A3 | Form Work | Core | 50.00 TO 53.30 | 15th Floor | 42476 | 42480 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4844 | form work for shear wall 1 axis B6 to B10/A1 | Form work | SH.W | 48.20 TO 51.50 | 14th floor | 42476 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4845 | steel reinforcement for core 7 axis C7/A2-A3 | Steel Reinforcement | Core | 48.20 TO 51.50 | 14th floor | 42476 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4846 | Form Work For Core7 Axis C7/A2 TO A3 | Form Work | Core | 48.20 TO 51.50 | 14th floor | 42476 | 42480 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4847 | Steel Reinforcement For SH.W9 Axis A8 TO A10/B9 | Steel Reinforcement | SH.W | + 39.90 to 43.20 | 9th | 42477 | 42481 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4848 | Form Work For SH.W 9 Axis A8 TO A10/B9 | Form Work | SH.W | + 39.90 to 43.20 | 9th | 42477 | 42486 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4849 | Steel Reinforcement For 2 CC7 Axis A6/B10 TO B12 | Steel Reinforcement | Column | + 39.90 to 43.20 | 9th | 42477 | 42481 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4850 | Form work For 2 CC7-A Axis A6/B10 TO12 | Form Work | Column | + 39.90 to 43.20 | 9th | 42477 | 42483 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4851 | Steel Reinforcement For 2 CC9 A Axis A11 TO B10 TO B12 | Steel Reinforcement | Column | + 39.90 to 43.20 | 9th | 42477 | 42483 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4852 | Form work for 2 CC9-A Axis A11/B10 TO B12 | Form Work | Column | + 39.90 to 43.20 | 9th | 42477 | 42486 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4853 | Steel Reinforcement For(DCC7-B),(DCC1A)And(DCC3A)Axis A6 TO A10&A12/B9 | Steel Reinforcement | Column | + 39.90 to 43.20 | 9th | 42477 | 42486 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4854 | Form Work (DCC7-B),(DCC1A)And (DCC3A)Axis A6 TO A10&A12/B9 | Form Work | Column | + 39.90 to 43.20 | 9th | 42477 | 42486 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4855 | Installation (Torque)For Column CC1* east Axis A8/B13 | Torque | Column | + 36.60 TO 39.90 | 9th | 42477 | 42479 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4856 | Form Work For Fence Columns(4Columns)As Attached Axis B1 TO B19/A15 | Form Work | Column | UP TO 4.30 | ground Floor | 42477 | 42478 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4857 | Steel Reinforcement For Fence Columns(12 Columns)as Attached Axis B1 TO B19/A15 | Steel Reinforcement | Column | UP TO 4.30 | ground Floor | 42477 | 42479 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4858 | Steel Reinforcement For Shear Wall 1 Axis B6 TO B10/A1 | Steel Reinforcement | SH.W | 48.20 TO 51.50 | 14th floor | 42474 | 42478 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4859 | Steel Reinforcement For DCC1* Axis B13 /A8 | Steel Reinforcement | Column | + 36.60 TO 39.90 | 9th | 42478 | 42479 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4860 | Form work For DCC1* Axis B13/A8 | Form Work | Column | + 36.60 TO 39.90 | 9th | 42478 | 42481 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4861 | Stressing Of strands for third stage post tension slab Axis A6 TO A12 / B13 TO B19 | Stressing | third stage | +36.60 | 9th | 42478 | 42481 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4862 | steel reinforcement for core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | Core | 46.50 TO 49.80 | 12th Floor | 42478 | 42479 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4863 | Form Work For Stair 12 Axis B1/A2 | Form work | Stair | 35.00 TO 38.30 | 10th Floor | 42478 | 42480 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4864 | steel reinforcement for stair 12 axis B1/A2 | Steel Reinforcement | Stair | 35.00 TO 38.30 | 10th Floor | 42478 | 42479 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4865 | Form Work For Stair 14 Axis B16/A2 | Form Work | Stair | 25.10 TO 28.40 | 7th | 42478 | 42480 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4866 | Steel Reinforcement For Stair 14 Axis B16/A2 | Steel Reinforcement | Stair | 25.10 TO 28.40 | 7th | 42478 | 42488 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4867 | Form Work For Shear Wall 7 Axis C3/A2 TO A3 | Form Work | SH.W | 51.50 TO 54.80 | 15th Floor | 42478 | 42483 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4868 | Steel Reinforcement For Shear Wall 7 Axis C3/ A2 TO A3 | Steel Reinforcement | SH.W | 51.50 TO 54.80 | 15th Floor | 42478 | 42481 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4869 | Steel Reinforcement For Shear Wall 6 Axis C4/A2 TO A3 | Steel Reinforcement | SH.W | 51.50 TO 54.80 | 15th Floor | 42478 | 42479 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4870 | Form Work For Shear Wall 6 Axis C4/ A2 TO A3 | Form Work | SH.W | 51.50 TO 54.80 | 15th Floor | 42478 | 42483 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4871 | check form work for Slab 44.90 second stage | Form Work | Slab | 44.90 | 11th Floor | 42478 | 42480 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4872 | Steel Reinforcement for Core 1 Axis A8 TO A10/B17 | Steel Reinforcement | Core | 36.60 TO 39.90 | 9th | 42479 | 42481 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4873 | Form Work For Core 2 Axis A8 TO A10 / B14 TO B16 | Form Work | Core | 39.90 TO 43.20 | 10th Floor | 42479 | 42483 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4874 | Stressing Of Strands For Second Stage Post Tension Slab Axis A6 TO A12/B4 TO B9 | Stressing | Slab | +39.90 | 10th Floor | 42479 | 42483 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4875 | Tendos-Strands-Anchors And Profiles For First stage of post tension slab Axis A6 TO A10 / B4 TO B9 | Anchor | First Stage | + 43.20 | 11th Floor | 42479 | 42481 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4876 | Top& bottom Layers And Beams Steel Reinforcement For FirstPost Tension Slab Axis A6 TO A10/ B4 TO B9 | Steel Reinforcement | First Stage | +43.20 | 11th Floor | 42479 | 42481 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4877 | form work for stair case 7 axis A10/B10-B11 | Form work | Second Stage | + 39.90 TO 43.20 | 10th Floor | 42479 | 42483 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4878 | Grouting For Cables For Third Stage Of Post tension Slab Axis A6 TO A12/B13 TO B19 | Grout | third stage | +33.30 | 8th | 42479 | 42481 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4879 | Grouting For Cables For Second Stage Of Post Tension Slab Axis A6 To A12/B8 TO B12 | Grout | Second Stage | +36.60 | 9th | 42479 | 42481 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4880 | Surface Preparation And Repair Work For 2 Columns CC7 And Slab Axis A10 TO A11/B4 | Repair | Column | 36.60 | 9th | 42480 | 42490 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4881 | Form Work Inspection For (Two)Fence Columns As attached | Form work | Column | 1.10 TO 430 | ground Floor | 42480 | 42486 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4882 | Steel Reinforcement For Shear wall 1 Axis B19/A1 | Steel Reinforcement | SH.W | 51.50 TO 54.80 | 15th Floor | 42481 | 42483 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4883 | Form Work For Shear Wall 1 Axis B10 TO B19/A1 | Form Work | SH.W | 51.50 TO 54.80 | 15th Floor | 42481 | 42487 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4884 | Bottom Steel Reinforcement for Second Stage Hotel Tower slab Axis C5 TO B19 / A1TOA3 | Steel Reinforcement | Second Stage | 44.90 | 12nd Floor | 42481 | 42484 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4885 | Top Steel Reinforcement For Second Stage Hotel Tower Axis C5 TO B19 / A1 TO A3 | Steel Reinforcement | Second Stage | 44.90 | 12nd Floor | 42481 | 42484 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4886 | Tendons,Strands,Anchors And Profiles For Second Stage Slab Hotel Tower Axis C5 TO B19/A1 TO A3 | Form Work | Second Stage | 44.90 | 12nd Floor | 42481 | 42486 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4887 | Form Work For Core 1 Axis A8 TO A10/B17 | Form Work | third stage | 36.60 TO 39.90 | 9th | 42481 | 42483 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4888 | Duct grouting For Cable at first stage post tension Slab Axis A6 TO A12/B4 TO B9 | Grout | Slab | + 36.90 | 10th Floor | 42481 | 42483 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4889 | Check Form work At 39.90 Third Stage Axis B6 TO B19/A1 To A3 | Form work | third stage | 39.90 | 9th | 42483 | 42487 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4890 | Check Form work at 48.20 third stage | Form work | second stage | 48.20 | 12th Floor | 42483 | 42487 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4891 | Form Work For CC7-A Axis A6/B5 TO B6 &B8 | Form work | First Stage | + 43.20 TO 46.50 | 11th Floor | 42483 | 42488 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4892 | steel reinforcement For 3 CC7-A Axis A6/B5TOB6&B8 | Steel Reinforcement | First Stage | + 43.20 TO 46.50 | 11th Floor | 42483 | 42488 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4893 | Steel Reinforcement For 4 ColumnsCC7-A Axis A8 TO A9,10,11/B4 | Steel Reinforcement | First Stage | + 43.20 TO 46.50 | 11th Floor | 42483 | 42488 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4894 | Form work For 4 ColumnsCC7-A Axis A8 TO A9,10,11/B4 | Form work | First Stage | + 43.20 TO 46.50 | 11th Floor | 42483 | 42488 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4895 | Steel Reinforcement For core 3 Axis A8 TO A10/B10 to B12 | Steel Reinforcement | Core | 46.50 TO 49.80 | 12th Floor | 42483 | 42486 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4896 | Steel Reinforcement For 3 CC9-A Axis A11/B6 To B8 | Steel Reinforcement | First Stage | + 43.20 TO 46.50 | 11th Floor | 42483 | 42486 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4897 | Form work For 2 Column CC9-A Axis A11/B6 TO B8 | Form work | First Stage | + 43.20 TO 46.50 | 11th Floor | 42483 | 42486 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4898 | Form Work Removal For Third Stage Of Post Tension Slab Axis A6 TO A12/B8 TO B13 | Form work | third stage | +36.60 | 9th | 42484 | 42486 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4899 | Form Work Removal For Second Stage Of Post tension Slab Axis A6 TO A12/B8 TO B13 | Form work | Second Stage | +39.90 | 10th Floor | 42484 | 42486 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4900 | Form Work for stair case 11 Axis A7 TO A8 / B16 TO B17 | Form work | third stage | 36.60 TO 39.90 | 10th Floor | 42484 | 42487 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4901 | Groting For Cables Of First Stage Hotel Tower Axis C5 TO B1/A1 TO A3 | Grout | First Stage | 44.90 | 12nd Floor | 42484 | 42506 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4902 | Form Work Removal For first Stage Slab Hotel Tower Axis C5 TO B1/A1 TO A3 | Form work | First Stage | 44.90 | 12nd Floor | 42484 | 42486 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4903 | Form Work For Stair Case 10 Axis A6 TO A7/B14 TO B15 | Form work | third stage | 0.45 TO +1.10 | ground Floor | 42484 | 42487 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4904 | Steel Reinforcement For Pour Strip Between Second And third stage Axis A6 TO A12/B12 TO B13 | Steel Reinforcement | Pour strip | +36.60 | 9th | 42484 | 42486 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4905 | Grouuting For Cables Of Second Stage Slab Hotel Tower Axis C5 TO B19/A1 TO A3 | Grout | Second Stage | 41.60 | 11th Floor | 42484 | 42501 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4906 | Form Work Removal For Second Stage Slab Hotel Tower Axis C5 TO B19/A1 TO A3 | Form Work | Second Stage | 41.60 | 11th Floor | 42484 | 42488 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4907 | Form Work For core 5 Axis A8 TO A10/B6 TO B8 | Form Work | Core | +46.50 TO 49.80 | 12th Floor | 42486 | 42490 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4908 | steel reinforcement for core 8 axis B1/A2 to A3 | Steel Reinforcement | Core | 53.30 TO 56.60 | 16th Floor | 42486 | 42488 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4909 | Form Work For Core 8 Axis B1/A2 | Form Work | Core | 53.30 TO 56.60 | 16th Floor | 42486 | 42490 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4910 | Form Work For Shear Wall 1 Axis B1 TO B10/A1 | Form Work | SH.W | 51.50 TO 54.80 | 15th Floor | 42486 | 42490 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4911 | Steel Reinforcement For Shear Wall 1 Axis B1 TO B10/A1 | Steel Reinforcement | SH.W | 51.50 TO 54.80 | 15th Floor | 42486 | 42487 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4912 | Steel Reinforcement For Stair Case 11 Axis A7 TO A8/B16 TO B17 | Steel Reinforcement | Case | 36.60 TO 39.90 | 9th | 42486 | 42488 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4913 | Steel reinforcement For Pour Strip Between First And Second Stage Axis A6 TO A12/B8 TO B9 | Steel Reinforcement | Second Stage | +39.90 | 10th Floor | 42486 | 42487 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4914 | Bottom Steel Reinforcment For First Stage Hotel Tower Slab Axis A1 TO A3/B1 TO C5 | Steel Reinforcement | Post tension | 48.20 | 13th floor | 42487 | 42488 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4915 | Tendons,strands,anchors and profiles first stage hotel tower slab Axis C5 TO B1/A1 TO A3 | Anchor | Post tension | 48.20 | 13th floor | 42487 | 42488 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4916 | Top steel Reinforcement for first stage hotel tower slab Axis C5 TO B1/A1 TO A3 | Steel Reinforcement | Post tension | 48.20 | 13th floor | 42487 | 42488 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4917 | Form Work for stair case6 Axis A8/ B10/B12 | Form Work | Case | 39.90to43.20 | 10th Floor | 42487 | 42490 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4918 | Top& bottom Layers And Beams Steel Reinforcement For third post tension slab .AXIS A6 to A10/B13 to B19 | Steel Reinforcement | third Stage | +39.90 | 10th Floor | 42487 | 42488 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4919 | Tendos-Strands-Anchors And Profiles For Second Stage Of Post Tension Slab Axis A6 TO A12 / B13 TO B19 | Anchor | third Stage | +39.90 | 10th Floor | 42487 | 42490 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4920 | Check Form work At Level 43.20 Second Stage | Form Work | slab | 43.20 | 10th Floor | 42488 | 42490 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4921 | form work for Fence columns 1A,6A,7,14A Axis B1 TO B19/A15 | Form Work | Column | UP TO 4.30 | X | 42488 | 42495 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4922 | Steel Reinforcement For Shear Wall 2 axis C10/A2 to A3 | Steel Reinforcement | SH.W | 44.90 TO 48.20 | 13th floor | 42488 | 42493 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4923 | Form Work For Shear Wall 2 axis C10/A2 to A3 | Form Work | SH.W | 44.90 TO 48.20 | 13th floor | 42488 | 42493 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4924 | Steel Reinforcement For Shear Wall3 axis C6/A2 to A3 | Steel Reinforcement | SH.W | 44.90 TO 48.20 | 13th floor | 42488 | 42488 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4925 | Form Work For Shear Wall 3 axis C6/A2 to A3 | Form Work | SH.W | 44.90 TO 48.20 | 13th floor | 42488 | 42493 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4926 | Form Work For Shear Wall 6 Axis C4/A2 TO A3 | Form Work | SH.W | 54.80 TO 58.10 | 16th Floor | 42490 | 42497 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4927 | Steel Reinforcement For Shear Wall 6 Axis C4/A2 TO A3 | Steel Reinforcement | SH.W | 54.80 TO 58.10 | 16th Floor | 42490 | 42495 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4928 | Stressing For Cables Of Second Stage Hotel Tower Axis C5 TO B19/A1 TO A3 | Stressing | Slab | 44.90 | 12nd Floor | 42490 | 42493 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4929 | Stressing For Cables Of First Stage Slab Hotel Tower Axis C5 TO B1/A1 TO A3 | Stressing | Slab | 48.20 | 13th floor | 42490 | 42497 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4930 | Steel Reinforcemnt For Core 2 Axis B15/A9 | Core | Core | 43.20 TO 46.50 | 12nd Floor | 42490 | 42490 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4931 | Form Work For Shear Wall 3* Axis C8/A2 TO A3 | Form Work | SH.W | 44.90 TO 48.20 | 13th floor | 42490 | 42493 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4932 | Steel Reinforcement For Shear Wall 3* Axis C8/A2 TO A3 | Steel Reinforcement | SH.W | 44.90 TO 48.20 | 13th floor | 42490 | 42493 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4933 | Form Work For Shear Wall 5* Axis C5/A2 TO A3 | Form Work | SH.W | 44.90 TO 48.20 | 13th floor | 42490 | 42493 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4934 | Steel Reinforcement For Shear Wall 5* Axis C5/A2 TO A3 | Steel Reinforcement | SH.W | 44.90 TO 48.20 | 13th floor | 42490 | 42493 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4935 | Steel Reinforcement For Column CC5 & CC6 Axis C9/A3 & C11/A3 | Steel Reinforcement | Column | 44.90 TO 48.20 | 13th floor | 42490 | 42493 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4936 | Form Work For Columns CC5 & CC6 Axis C9/A3 &C11/3 | Form Work | Column | 44.90 TO 48.20 | 13th floor | 42490 | 42493 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4937 | Steel reinforcement For column Axis D1 TO D2&D3&D4/A9 | Steel Reinforcement | Column | 39.90 TO 43.20 | 10th Floor | 42490 | 42493 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4938 | Form Work For Core Walls Axis B12 To B10/A1 To A3 | Form Work | Core | 46.50 TO 49.80 | 12th Floor | 42490 | 42493 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4939 | Form Work For Column Axis D1 To D2 &D3 TO D4/A9 | Form Work | Column | 39.90 TO 43.20 | 10th Floor | 42490 | 42493 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4940 | Form Work For Column Axis B16 /A10 TO A11,A6 TO A11 &A12/B14&B16 | Form Work | Column | 39.90 TO 43.20 | 10th Floor | 42490 | 42497 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4941 | Steel reinforcement For Columns And Shear Walls Axis B16/A10 TO A11,A6 &A11 TO A12/B14 TO B16 | Steel Reinforcement | Column | 39.90 TO 43.20 | 10th Floor | 42490 | 42493 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4942 | Form Work For Column Axis B13 / A6 TO A8 & A10 TO A11 | Form Work | Column | 39.90 TO 43.20 | 10th Floor | 42490 | 42497 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4943 | Steel Reinforcement For Column And Shear Walls Axis B13/A6 TO A8/A10 TO a11 | Steel Reinforcement | Column | 39.90 TO 43.20 | 10th Floor | 42490 | 42495 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4944 | Check Form Work At Level 46.50 First Stage | Form Work | First Stage | 46.50 | 12th Floor | 42493 | 42497 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4945 | Steel Reinforcement For Shear Wall 8 Axis C2/A2 TO A3 | Steel Reinforcement | SH.W | 48.20 TO 51.50 | 11th Floor | 42493 | 42494 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4946 | Form Work For Shear Wall 8 Axis C2/A2 TO A3 | Form Work | SH.W | 48.20 TO 51.50 | 11th Floor | 42493 | 42493 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4947 | Form Work For Shear Wall 1 + C1 Axis A1/B19 | Form Work | SH.W | 44.90 TO 48.20 | 13th floor | 42493 | 42497 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4948 | Steel Reinforcement For Shear Wall 1+C1 Axis A1/B19 | Steel Reinforcement | SH.W | 44.90 TO 48.20 | 13th floor | 42493 | 42495 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4949 | steel reinforcement for shear wall 7 axis C3/A2 to A3 | Steel Reinforcement | SH.W | 54.80 TO 58.10 | 16th Floor | 42493 | 42495 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4950 | Form Work For Shear Wall 7 Axis C3/A2 TO A3 | Form Work | SH.W | 54.80 TO 58.10 | 16th Floor | 42493 | 42497 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4951 | Form Work For Column C5 Axis A1 TO B18 | Form Work | Column | 44.90 TO 48.20 | 13th floor | 42493 | 42495 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4952 | Steel Reinforcement For Column Axis A1 TO B18 | Steel Reinforcement | Column | 44.90 TO 48.20 | 13th floor | 42493 | 42495 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4953 | Form Work For Core 6 Axis A1 TO B15 | Form Work | Core | 44.90 TO 48.20 | 13th floor | 42493 | 42495 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4954 | Steel Reinforcement For Core 6 Axis A1 TO B15 | Steel Reinforcement | Core | 44.90 TO 48.20 | 13th floor | 42493 | 42495 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4955 | Form Work For Core 1 Axis A9/B17 | Form Work | Core | 39.90 TO 43.20 | 12th Floor | 42493 | 42500 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4956 | Stressing For Cables third stage slab RD ToWER Axis A6 TO A12 / B13 TO B19 | Stressing | third stage | 39.90 | 12th Floor | 42493 | 42500 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4957 | Tendons,Strands,Anchors and Profiles For second Stage Slab RD tower Axis A6 TO A12/B9 TO B13 |  | Slab | 43.20 | 12th Floor | 42493 | 42495 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4958 | Bottom Steel Reinforcement For Second Stage RDTower slab Axis A6 TO A12/B9 TO B13 | Steel Reinforcement | Slab | 43.20 | 12th Floor | 42493 | 42495 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4959 | Top Steel Reinforcement For Second Stage Slab RD Tower Axis A6 TO A12/B9 TO B13 | Steel Reinforcement | Slab | 43.20 | 12th Floor | 42493 | 42495 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4960 | Steel Reinforcement For Core 1 Axis A9/B17 | Steel Reinforcement | Core | 39.90 TO 43.20 | 11th Floor | 42493 | 42500 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4961 | Steel Reinforcement For Stair 7 Axis A10/ B11 | Steel Reinforcement | Stair | 39.90 TO 43.20 | 11th Floor | 42493 | 42495 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4962 | Steel Reinforcement For Stair 6 Axis A8/B11 | Steel Reinforcement | Stair | 39.90 TO 43.20 | 11th Floor | 42493 | 42495 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4963 | Steel Reinforcement For CC7 Axis A12/B16 | Steel Reinforcement | Column | 39.90 TO 43.20 | 12th Floor | 42493 | 42495 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4964 | Form Work For Core 2 Axis A9/B15 | Form Work | Core | 43.20 TO 46.50 | 12th Floor | 42494 | 42497 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4965 | Check Form Work At Level 48.20 Second Stage | Form Work | Slab | 48.20 | 12th Floor | 42494 | 42497 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4966 | Check Form Work At Level 51.50 First Stage | Form Work | Slab | 51.50 | 13th floor | 42494 | 42497 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4967 | Steel Reinforcement For 2CC9 Axis A11/B10 TO B12 | Steel Reinforcement | Column | 43.20 TO 46.50 | 12th Floor | 42497 | 42500 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4968 | Form Work For 2Columun CC9 Axis A11/B10 TO B12 | Form Work | Column | 43.20 TO 46.50 | 12th Floor | 42497 | 42500 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4969 | Steel Reinforcement For SH.W9 Axis A8 TO A10/B9 | Steel Reinforcement | SH.W | 43.20 TO 46.50 | 12th Floor | 42497 | 42500 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4970 | Form Work For SH.W 9 Axis A8 TO A10/B9 | Form Work | SH.W | 43.20 TO 46.50 | 12th Floor | 42497 | 42502 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4971 | Top & Bottom Layers And Beams Steel Reinforcement For First Post Tension Slab Axis A6 TO A10/B4TO B9 | Steel Reinforcement | Slab | +46.50 | 12th Floor | 42497 | 42502 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4972 | Tendons -Strands-Anchors And Profiles For First Stage OF Post Tension Slab Axis A6 TO A10/B4 TO B9 | Form Work | Slab | +46.50 | 12th Floor | 42497 | 42500 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4973 | Form Work For Double CC1 And DCC3 Axis A10 TO A11/B9 | Form Work | Column | 43.20 TO 46.50 | 12th Floor | 42497 | 42502 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4974 | Steel Reinforcement For DCC1 And DCC3 Axis A10 TO A11/B9 | Steel Reinforcement | Column | 43.20 TO 46.50 | 12th Floor | 42497 | 42500 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4975 | Steel Reinforcement For 2 CC7 Axis A6/B10 TO B12 | Steel Reinforcement | Column | 43.20 TO 46.50 | 12th Floor | 42497 | 42501 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4976 | Form Work For 2Column CC7 Axis A6/B10 TO B12 | Form Work | Column | 43.20 TO 46.50 | 12th Floor | 42497 | 42501 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4977 | Steel Reinforcement For Stair Case 3 Axis A8/B6 TO B7 | Steel Reinforcement | stair | 43.20 TO 46.50 | 12th Floor | 42497 | 42500 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4978 | Steel Reinforcement For Double Column CC7 Axis A6/B9 | Steel Reinforcement | Column | 43.20 TO 46.50 | 12th Floor | 42497 | 42502 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4979 | Form Work For DCC7 Axis A6/B9 | Form Work | Column | 43.20 TO 46.50 | 12th Floor | 42497 | 42502 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4980 | Stressing by 5% For Cable No.(23)For Slab Stage 1 | Stressing | Slab | 48.20 | 13th floor | 42499
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4981 | Grouting For Cables For Third Stage Of Post tension slab Axis A6 to A12 /B13 | Grout | Slab | +36.60 | 9th | 42499 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4982 | Grouting For Cables For Second Stage of post tension slab Axis A6 TO A12/B8 TO B12 | grout | Slab | +39.90 | 10th Floor | 42499 | 42501 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4983 | Duct grouting For Cable at first stage post tension Slab Axis A6 TO A12/B4 TO B9 | grout | Slab | +43.20 | 11th Floor | 42499 | 42508 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4984 | Stressing of strands for second stage post tension slab Axis A6 TO A12/B4 TO B9 | Stressing | Slab | +43.20 | 11th Floor | 42499 | 42501 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4985 | Steel reinforcement For Stair Case 10 Axis A6 TO A7/B14 TO B15 | Steel Reinforcement | Stair | -0.45 to +1.10 | ground Floor | 42499 | 42502 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4986 | Form work inspection For 4 Columns As attached(15.17.18.19) | Form Work | columun | 1.10 to 4.40 | ground Floor | 42499 | 42502 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4987 | Stell Reinforcement For 4 Columns As attached (1B,6B,11B,16A21A,22A,23A) | Steel Reinforcement | columun | 1.10 to 4.40 | ground Floor | 42499 | 42507 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4988 | Check Form work level 43.20 Third stage | Form Work | Slab | 43.20 | 10th Floor | 42499 | 42501 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4989 | Form Work for stair case 11 Axis A7 TO A8 / B16 TO B17 | Form Work | Stair | 39.90 TO 43.20 | 10th Floor | 42500 | 42504 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4990 | Form work removal for third stage of post tension Slab Axis A6 TO A12/B8 TO B13 | Form Work | Slab | +39.90 | 10th Floor | 42500 | 42501 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4991 | bottom layer steel reinforcement for slab Axis B1 TO B6/A3 | Steel Reinforcement | Slab | 51.50 | 14th floor | 42500 | 42501 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4992 | steel reinforcement for Shear wall 1 Axis B12 TO B14/A1 | Steel Reinforcement | SH.W | 54.80 TO 58.10 | 15th Floor | 42500 | 42502 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4993 | tendons, strands, anchors and profiles for slab Axis B1 TO B6/A1 TO A3 | Cables | slab | 51.50 | 14th floor | 42500 | 42501 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4994 | Steel Reinforcement For Pour Strip Between Second And third Stage Axis A6 TO A12 / B12 TO B13 | Steel Reinforcement | slab | +39.90 | 10th Floor | 42501 | 42502 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4995 | Steel Reinforcement For Stair11 Axis A7,A8 to B16,B17 | Steel Reinforcement | third Stage | 39.90 TO 43.20 | 11th Floor | 42501 | 42506 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4996 | Steel Reinforcement For Core 5 Axis A8,A10 to B6,B8 | Steel Reinforcement | core | 49.80 to 53.10 | 13th floor | 42501 | 42502 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4997 | Top layer steel reinforcement for slab Axis B1 TO B6/A3 | Steel Reinforcement | slab | 51.50 | 14th floor | 42501 | 42502 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4998 | Steel Reinforcement For Core 7 Axis B11/A2 to A3 | Steel Reinforcement | core | 51.50 TO 54.80 | 14th floor | 42502 | 42506 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-4999 | Form Work For SH.W 1 Axis.B10 TO B19 /A1 | Form Work | sh.w | 54.80 TO 58.10 | 15th floor | 42502 | 42502 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5000 | Steel Reinforcement For p.t slab commen pour strib between (1&2) AXIS B6/A1 toA3 | Steel Reinforcement | slab | 44.90 | 12th Floor | 42502 | 42507 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5001 | Bottom Steel Reinforcement For Second Stage slab hotel Axis B5 to B19 /A1 toA3 | Steel Reinforcement | Slab | 48.20 | 13th floor | 42504 | 42506 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5002 | TOP Steel Reinforcement For Second Stage slab hotel Axis B5 to B19 /A1 toA3 | Steel Reinforcement | Slab | 48.20 | 13th floor | 42504 | 42506 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5003 | Tendons,Strands,Anchors and Profiles For second Stage Slab hotel tower Axis B5 to B19 /A1 toA3 | Anchor | Slab | 48.20 | 13th floor | 42504 | 42506 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5004 | Form Work For Core 7AxisB11/A2 TO A3 | Form Work | core | 51.50 TO 54.80 | 14th floor | 42504 | 42507 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5005 | Form Work For 4 CC7 Axis A8 To A9 TO A10&A11/B4 | Form work | Columun | +46.50 TO 49.80 | 12th Floor | 42505 | 42508 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5006 | Steel Reinfrorcement for 5 columns CC7 Axis A8 TO A9 TO A10&A11/B4 | Steel Reinforcement | Columun | +46.50 TO 49.80 | 12th Floor | 42505 | 42507 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5007 | Form Work For 2 Columun CC9 Axis A11/B6 TO B8 | Form work | Columun | +46.50 TO 49.80 | 12th Floor | 42505 | 42508 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5008 | steel reinforcement For 2Columun CC9 Axis A11/B6 TO B8 | Steel Reinforcement | Columun | +46.50 TO 49.80 | 12th Floor | 42505 | 42507 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5009 | Steel Reinforcement For 3 CC7 Axis A6/B5 TO B6 TO B8 | Steel Reinforcement | Columun | +46.50 TO 49.80 | 12th Floor | 42505 | 42506 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5010 | Form work For 3 CC7 Axis A6/B5 TO B6 TO B8 | Form Work | Columun | +46.50 TO 49.80 | 12th Floor | 42505 | 42508 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5011 | Stressing Of Strands For First stage Post tension Slab Axis A6 TO A12/B4 TO B9 | Stressing | slab | +46.50 | 12th Floor | 42505 | 42508 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5012 | Form Work Removal For Second Stage Of Post tension Slab Axis A6 TO A12/B8 TO B13 | Form Work | slab | +43.20 | 11th Floor | 42505 | 42511 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5013 | Top&Bottom Layers and Beams Steel Reinforcement For Third Post tension Slab Axis A6TO A10/B13 TO B19 | Steel Reinforcement | slab | -43.20 | 11th Floor | 42505 | 42506 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5014 | Tendos -Strands-Anchors and profiles for third stage of post tension slab Axis A6 TO A12/B13 TO B9 | Anchor | Slab | +43.20 | 11th Floor | 42505 | 42506 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5015 | Form Work For Stair 12 Axis B1/A2 TO A3 | form work | stair | 38.30 TO 41.60 | 11th Floor | 42505 | 42506 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5016 | Steel Reinforcement For Stair 12 Axis B1/A2 TOA3 | Steel Reinforcement | stair | 38.30 TO 41.60 | 11th Floor | 42505 | 42507 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5017 | Steel Reinforcement For Shear wall 8 Axis C2/A2 TO A3 | Steel Reinforcement | SH.W | 51.50 TO 54.80 | 15th floor | 42505 | 42506 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5018 | Form Work For Shear Wall 8 Axis C2/A2 TO A3 | form Work | SH.W | 51.50 TO 54.80 | 15th floor | 42505 | 42509 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5019 | Check Form work At Level 46.50 Second stage | form Work | slab | 46.50 | 11th Floor | 42505 | 42506 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5020 | Steel Reinforcement For core 3 Axis A8 TO A10/B10 to B12 | Steel Reinforcement | core | 49.80 TO 53.10 | 13th floor | 42506 | 42507 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5021 | Steel reinforcement for shear wall 2 Axis C10/A2 To A3 | Steel Reinforcement | SH.W | 48.20 TO 51.50 | 14th floor | 42507 | 42509 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5022 | Form Work For Shear wall 2 Axis C10/A2TOA3 | Form Work | SH.W | 48.20 TO 51.50 | 14th floor | 42507 | 42509 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5023 | Steel Reinforcement For Shear wall 3 Axis C8/A2 TO A3 | Steel Reinforcement | SH.W | 48.20 TO 51.50 | 14th floor | 42507 | 42507 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5024 | Form Work For Shear Wall 3 axis C6/A2 to A3 | form work | SH.W | 48.20 TO 51.50 | 14th floor | 42507 | 42508 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5025 | Steel Reinforcement For Shear Wall 5* Axis C5/A2 TO A3 | Steel Reinforcement | SH.W | 48.20 TO 51.50 | 14th floor | 42507 | 42507 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5026 | Form Work For Shear Wall 5 * Axis C5/A2 TO A3 | form work | SH.W | 48.20 TO 51.50 | 14th floor | 42507 | 42508 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5027 | Steel Reinforcement For Shear Wall 3* Axis C8/A2 TO A3 | Steel Reinforcement | SH.W | 48.20 TO 51.50 | 14th floor | 42507 | 42507 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5028 | Form Work For Shear Wall3* Axis C8/A2 TO A3 | Form Work | SH.W | 48.20 TO 51.50 | 14th floor | 42507 | 42508 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5029 | Grouting For Cables of second stage hotel Tower slab Axis C5 TO B19/A1 TO A3 | Grout | Grout | 44.99 | 12th Floor | 42507 | 42508 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5030 | Stressing for Cables Of First Stage Hotel Tower Slab Axis C5 TO B1/A1 TO A3 | Stressing | Slab | 51.50 | 14th floor | 42507 | 42508 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5031 | Steel Reinforcement For stair 7 Axis A8/B11 | Steel Reinforcement | stair | 43.20 TO 46.50 | 11th Floor | 42507 | 42509 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5032 | Form Work For stair 7 Axis A8/B11 | form Work | stair | 43.20 TO 46.50 | 11th Floor | 42507 | 42507 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5033 | Steel Reinforcement For stair 6 Axis A8/B11 | Steel Reinforcement | stair | 43.20 TO 46.50 | 11th Floor | 42507 | 42518 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5034 | Form Work For stair 6 Axis A8/B11 | Form work | stair | 43.20 TO 46.50 | 11th Floor | 42507 | 42507 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5035 | Steel reinforcement For Pour Strip Between First And Second Stage Axis A6 TO A12/B8 TO B9 | Steel Reinforcement | Pour strip | +43.20 | 11th Floor | 42507 | 42508 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5036 | Form work For Stair 14 Axis B15 TO B16 / A1 TO A2 | form work | stair | 28.40 TO 31.70 | 8th | 42508 | 42509 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5037 | Form Work For core 5 Axis A8 TO A10/B6 TO B8 | form work | core | 49.80 TO 53.10 | 13th floor | 42507 | 42509 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5038 | Core 7 Axis B10/A2 TO A3 | Steel Reinforcement | core | 54.80 TO 58.10 | 15th floor | 42515 | 42519 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5039 | Form Work For Fence 4 Columns No.21B,24 | form work | fence | 1.10 TO 4.40 |  | 42508 | 42522 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5040 | Steel Reinforcement For Fence Columns No. 21B,24 | Steel Reinforcement | fence | 1.10 TO 4.40 |  | 42508 | 42522 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5041 | Steel Reinforcement For Shear Wall1+C1 Axis B19/A1 | Steel Reinforcement | SH.W+C1 | 48.20 TO 51.50 | 14th floor | 42508 | 42509 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5042 | Form Work For Shear Wall 1 +C1 Axis B19/A1 | Form Work | SH.W+C1 | 48.20 TO 51.50 | 14th floor | 42508 | 42509 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5043 | Steel Reinforcement For CC4 Axis A11/B16 | Steel Reinforcement | Columun | +43.20 To 46.50 | 11th Floor | 42508 | 42515 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5044 | Form Work For CC4 Axis A11/B16 | form Work | Columun | +43.20 To 46.50 | 11th Floor | 42508 | 42518 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5045 | Shear Connector For CC1* Axis B13 TO A8 | Shear Connectors | Columun | 43.20 TO 46.50/46.50 TO49.80 | 13th floor | 42508 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5046 | Steel Reinforcement For Core 2 Axis A8 TO A10/B14TO B16 | Steel Reinforcement | Core | +46.50 TO 49.80 | 13th floor | 42508 | 42509 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5047 | Steel Reinforcement For 2DCC1 Axis B13 TO A11/B13 TO A10 | Steel Reinforcement | Columun | +43.20 TO 46.50 | 13th floor | 42508 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5048 | Form work for 2DCC1 Axis B13toA11/B13toA10 | form Work | Columun | +43.20 TO 46.50 | 13th floor | 42508 | 42518 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5049 | Steel Reinforcement For 5CC4 Axis D1 TO D2 TO D3 &D4 A9 / B19 | Steel Reinforcement | Columun | +43.20 TO 46.50 | 13th floor | 42508 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5050 | Form work For 5 CC4 Axis D1,D2,D3,D4,A9/B19 | form work | Columun | +43.20 TO 46.50 | 13th floor | 42508 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5051 | Grouting For Cables For Third Stage Of Post Tension Slab | Grout | third stage | +39.90 | 10th Floor | 42508 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5052 | Steel Reinforcement For 3CC7 Axis B16 TO B14/A6-B16/A12 | Steel Reinforcement | Columun | +43.20 TO 46.50 | 13th floor | 42508 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5053 | Form Work For 3CC7 Axis B16 TO B14/A6-B16/A12 | form Work | Columun | +43.20 TO 46.50 | 13th floor | 42508 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5054 | Steel Reinforcement For CC9 Axis +43.20 TO 46.50 | Steel Reinforcement | Columun | +43.20 TO 46.50 | 13th floor | 42508 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5055 | Form Work For CC9 Axis B14/A11 | Form Work | Columun | +43.20 TO 46.50 | 13th floor | 42508 | 42518 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5056 | Steel Reinforcement For DCC7 Axis B13/A6 | Steel Reinforcement | Columun | +43.20 TO 46.50 | 13th floor | 42508 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5057 | Form Work For DCC7 Axis B13/A6 | form Work | Columun | +43.20 TO 46.50 | 13th floor | 42508 | 42518 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5058 | Tendos -Strands-Anchors and profiles for Second stage of post tension slab Axis A6 TO A10/B13 TO B9 | Anchor | Slab | +46.50 | 12th Floor | 42508 | 42511 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5059 | Top&Bottom Layers And Beams steel Reinforcemenet For Second Stage Of Slab Axis A6 TO A10/B9 TO B13 | Steel Reinforcement | Slab | +46.50 | 12th Floor | 42508 | 42509 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5060 | Grouting For Cables for Second Stage Of Post Tension Slab | Grout | Slab | +43.20 | 11th Floor | 42508 | 42509 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5061 | Form Work Removal For First Stage Post tension Slab Axis A6 TO A12/B4 TO B9 | Form Work | Slab | +46.50 | 12th Floor | 42508 | 42511 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5062 | Steel Reinforcement For Column C5 Axis B18/A1 | Steel Reinforcement | Columun | 48.20 TO 51.50 | 14th floor | 42508 | 42509 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5063 | Form Work For Column C5 Axis B18/A1 | form Work | Columun | 48.20 TO 51.50 | 14th floor | 42508 | 42509 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5064 | Steel Reinforcement For Coiumns CC6 &CC5 | Steel Reinforcement | Columun | 48.20 TO 51.50 | 14th floor | 42508 | 42509 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5065 | Form Work For Columns CC6 &CC5 Axis C9/A3TO C11/A3 | Form Work | Columun | 48.20 TO 51.50 | 14th floor | 42508 | 42509 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5066 | Form Work For Core 6 Axis B15 TO B16/A1 TO A2 | Form Work | Core | 48.20 TO 51.50 | 14th floor | 42508 | 42509 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5067 | Steel Reinforcement For Core 6 Axis B15 TO B16/A1 TO A2 | Steel Reinforcement | Core | 48.20 TO 51.50 | 14th floor | 42508 | 42509 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5068 | Steel reinforcement For stair 14 Axis B16/A1 | Steel Reinforcement | stair | 28.40 TO 31.70 | 8th | 42509 | 42518 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5069 | Steel reinforcement For 2 CC9 Axis A11/B10 TO B12 | Steel Reinforcement | second stage | 46.50 TO 49.80 | 12th Floor | 42511 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5070 | Form Work For 2 CC9 Axis A11/B10 TO 12 | Form Work | second stage | 46.50 TO 49.80 | 12th Floor | 42511 | 42515 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5071 | Steel Reinforcement for Core 1 Axis A8 TO A10/B17 | Steel Reinforcement | third stage | 43.20 TO 46.50 | 11th Floor | 42511 | 42519 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5072 | form Work For 2CC7 Axis A6/B10 TO B12 | form Work | second stage | + 46.50 TO 49.80 | 12th Floor | 42511 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5073 | Steel Reinforcemet For 2 CC7 Axis A6/B10 TO B12 | Steel Reinforcement | second stage | + 46.50 TO 49.80 | 12th Floor | 42511 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5074 | Form work For DCC7 Axis A6/B9 | form Work | second stage | + 46.50 TO 49.80 | 12th Floor | 42511 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5075 | Steel Reinforcement For DCC7 Axis A6/B9 | Steel Reinforcement | second stage | + 46.50 TO 49.80 | 12th Floor | 42511 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5076 | Form work For DCC1 And DCC3 Axis A10 TO A11/B9 | form Work | second stage | + 46.50 TO 49.80 | 12th Floor | 42511 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5077 | Steel Reinforcement For DCC1 And DCC3 Axis A10 TO A11/B9 | Steel Reinforcement | second stage | + 46.50 TO 49.80 | 12th Floor | 42511 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5078 | Stressing Of strands for third stage post tension slab Axis A6 TO A12 / B13 TO B19 | Stressing | third stage | +43.20 | 11th Floor | 42511 | 42513 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5079 | Steel Reinforcement For DCC1* Axis B13 TO A8 | Steel Reinforcement | third stage | 43.20 TO 46.50 | 12th Floor | 42511 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5080 | Form work For DCC1* Axis B13/A8 | Form work | third stage | 43.20 TO 46.50 | 12th Floor | 42511 | 42515 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5081 | Steel Reinforcement For SH.W9 Axis A8 TO A10/B9 | Steel Reinforcement | second stage | 46.50 TO 49.80 | 12th Floor | 42511 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5082 | Form Work For SH.W9 Axis A8 TO A10/B9 | Form work | second stage | 46.50 TO 49.80 | 12th Floor | 42511 | 42515 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5083 | Check Form Work At 49.80 First stage Axis First stage | form work | slab | 49.80 | 12th Floor | 42511 | 42515 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5084 | Stressing For Cables Of Second Stage slab Hotel Tower Axis C5 TO B19/A1 TO A3 | Stressing | slab | 48.20 | 13th floor | 42512 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5085 | Form Work For Stair Case 3 Axis A8/B6 TO B7 | form work | First Stage | 46.50 To 49.80 | 13th floor | 42512 | 42515 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5086 | Form work For Core 3 Axis A8 TO A11/B10 TOB12 | Form Work | core | 49.80 TO 53.10 | 13th floor | 42512 | 42513 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5087 | Form Work For Fence 1B,6B,11B,20 | Form Work | fence | 1.10 TO 4.40 |  | 42513 | 42515 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5088 | Grouting For Cables Of First Stage Slab Hotel Tower Axis C5 TO B1/A1 TO A3 | Grout | slab | 48.20 | 13th floor | 42513 | 42518 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5089 | Stressing of strands for second stage post tension slab Axis A6 TO A12/B4 TO B9 | Stressing | slab | +46.50 | 12th Floor | 42514 | 42519 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5090 | Duct grouting For Cable at first stage post tension Slab Axis A6 TO A12/B4 TO B9 | Grout | slab | +46.50 | 12th Floor | 42514 | 42526 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5091 | Steel Reinforcement For Stair Case 3 Axis A8/B6 TO B7 | Steel Reinforcement | First Stage | 46.50 TO 49.80 | 12th Floor | 42514 | 42518 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5092 | Form Work Rmoval For Second Stage Hotel tower Slab Axis C5 TO B19/A1 TO A3 | form Work | second stage | 48.20 | 13th floor | 42514 | 42518 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5093 | FormWork Removal For First stage Hotel Tower Slab Axis C5 TO B1/A1 TO A3 | form Work | First Stage | 51.50 | 14th floor | 42514 | 42518 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5094 | Steel Reinforcement For Shear Wall 1 Axis B10 TO B1/A1 | Steel Reinforcement | SH.W | 54.80 To 58.10 | 15th floor | 42514 | 42518 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5095 | Form WOrk For Shear Wall 1 Axis B10 TO B1/A1 | form work | SH.W | 54.80 To 58.10 | 15th floor | 42514 | 42519 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5096 | Check Form Work At Level 51.50 Second Stage | form work | second stage | 51.50 | 13th floor | 42514 | 42519 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5097 | Form Work For Core 7 Axis B10/A2 TO A3 | form work | Core | 54.80 TO 58.10 | 15th Floor | 42515 | 42519 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5098 | Form Work For Stair 12 Axis B1/A2 | form work | Stair | 41.60 TO 44.90 | 12th Floor | 42515 | 42521 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5099 | Top& Bottom Layers and Beams Steel Reinforcement For First post tension slab Axis A6 To A10/B4 To B9 | Steel Reinforcement | First Stage | +49.80 | 13th floor | 42515 | 42518 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5100 | steel reinforcement for core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | Core | 53.10 TO 56.40 | 14th floor | 42515 | 42518 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5101 | Form Work For Core 2 Axis 46.50 TO 49.80 | form Work | Core | 53.10 TO 56.40 | 14th floor | 42515 | 42519 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5102 | Tendons -Strands-Anchors And Profiles For First Stage OF Post Tension Slab Axis A6 TO A10/B4 TO B9 | Anchor | First Stage | +49.80 | 13th floor | 42515 | 42519 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5103 | Steel Reinforcement For Pour Strip between Second and thurd stage Axis A6 TO A12/B12 TO B13 | Steel Reinforcement | Pour strip | 43.20 | 11th Floor | 42515 | 42518 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5104 | Steel Reinforcement For Pour Strip Hotel Tower Axis C5/A1 To A3 | Steel Reinforcement | Pour strip | 48.20 | 13th floor | 42516 | 42519 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5105 | Grouting For Cables of second stage hotel Tower slab Axis C5 TO B19/A1 TO A3 | Grout | second stage | 48.20 | 13th floor | 42516 | 42521 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5106 | Check Form Work At 49.80 Second Stage | form Work | second stage | 49.80 | 12th Floor | 42516 | 42519 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5107 | Form Work For Columns 16A,21A,22,23 | form Work | fence | 1.10 To 4.40 |  | 42516 | 42520 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5108 | Steel Reinforcement For Core 8 Axis B1/A1 TO A2 | Steel Reinforcement | Core | 56.60 TO 60 | 17th Floor | 42518 | 42520 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5109 | Tendos ,Strands,Anchors and profiles for second stage Hotel tower Slab Axis c5 TO B19/A1 TO A3 | Anchor | second stage | 51.50 | 14th floor | 42518 | 42519 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5110 | Bottom Steel reinforcement For Second Stage slab hotel tower Axis C5 TO B19/A1 TO A3 | Steel Reinforcement | second stage | 51.50 | 14th floor | 42518 | 42520 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5111 | Top Steel Reinforcement For Second Stage Slab Hotel Tower Axis C5 To B19/A1 TO A3 | Steel Reinforcement | second stage | 51.50 | 14th floor | 42518 | 42520 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5112 | Steel Reinforcement For Shear wall 1 Axis B10 TO B19/A1 | Steel Reinforcement | SH.W | 58.10 TO 61.40 | 17th Floor | 42519 | 42521 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5113 | Form Work For Shear Wall 1 Axis B10 TO B19/A1 | form work | SH.W | 58.10 TO 61.40 | 17th Floor | 42519 | 42523 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5114 | Form Work For Core 8 Axis B1/A1 TO A3 | form work | Core | 56.60 TO 60 | 17th Floor | 42519 | 42521 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5115 | Steel Reinforcement For SH.W 7 Axis A2 TO A3/B6 | Steel Reinforcement | SH.W | +58.10 TO 61.40 | 17th Floor | 42520 | 42523 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5116 | Steel Reinforcem,ent For SH.W 6 Axis A2 TO A3/C4 | Steel Reinforcement | SH.W | +58.10 TO 61.40 | 17th Floor | 42520 | 42523 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5117 | Grouting For Cables for Third Stage Of Post tension Slab | Grout | third stage | +43.20 | 11th Floor | 42520 | 42521 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5118 | Form Work Removal For Second Stage Of Post tension Slab Axis A6 TO A12/B8 TO B13 | Form work | second stage | +46.50 | 12th Floor | 42520 | 42522 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5119 | Stressing of strands for first stage post tension slab Axis A6.12/B4.9 | Stressing | First Stage | +49.80 | 13th floor | 42520 | 42529 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5120 | Steel Reinforcement For Stair Case 7 Axis A10 /b10 TO B11 | Steel Reinforcement | second stage | +46.50 TO 49.80 | 13th floor | 42520 | 42521 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5121 | Steel Reinforcement For Stair Case 6 Axis A8/B11 TO B13 | Steel Reinforcement | second stage | +46.50 TO 49.80 | 13th floor | 42520 | 42521 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5122 | Tendos-Strands-anchors And Profiles for Second Stage Of Post Tension Slab Axis A6 TO A12/B9 TO B13 | Anchor | second stage | +49.80 | 13th floor | 42520 | 42521 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5123 | Top&Bottom Layers and Beams Steel reinforcement For Second stage Of Slab Axis A6 TO A12/ B9 TO B13 | Steel Reinforcement | second stage | +49.80 | 13th floor | 42520 | 42521 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5124 | Steel Reinforcement For 3 CC7 Axis A6/B5 TO B6 &B8 | Steel Reinforcement | First Stage | 49.80 TO 53.10 | 14th floor | 42520 | 42521 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5125 | Form work For 3 CC7 Axis A6/B5 TO B6 TO B8 | Form Work | First Stage | 49.80 TO 53.10 | 14th floor | 42520 | 42523 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5126 | Steel Reinfrocement For 4 CC7 Axis A8 TO A9 &A10 TO A11/B4 | Steel Reinforcement | First Stage | 49.80 TO 53.10 | 14th floor | 42520 | 42521 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5127 | Form Work For 4 CC7 Axis A8 TO A9 &A10 TO A11/B4 | Form Work | First Stage | 49.80 TO 53.10 | 14th floor | 42520 | 42523 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5128 | Form work For 2 CC9 Axis A11/B6 TO B8 | Form Work | First Stage | 49.80 TO 53.10 | 14th floor | 42520 | 42523 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5129 | Steel reinforcement For 2 CC9 Axis A11/B6 TO B8 | Steel Reinforcement | First Stage | 49.80 TO 53.10 | 14th floor | 42520 | 42522 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5130 | Form work For Core 5 Axis A8 TO A10/B6 TO B8 | form Work | core | +53.10 TO 56.40 | 12th Floor | 42521 | 42523 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5131 | Steel Reinforcement For core 3 Axis A8 TO A10/B10 to B12 | Steel Reinforcement | core | +53.10 TO 56.40 | 12th Floor | 42521 | 42521 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5132 | Form Work For Stair 11 Axis B17/A8 | form work | stair | 43.20 TO 46.50 | 12th Floor | 42522 | 42525 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5133 | Check Form work At 54.80 First stage | form work | First Stage | 54.80 | 14th floor | 42521 | 42525 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5134 | Form Work For Shear wall 5* Axis C5/A2 TO A3 | Form work | SH.W | 51.50 TO 54.80 | 15th Floor | 42521 | 42523 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5135 | Form Work For Shear Wall 3 axis C6/A2 to A3 | Form work | SH.W | 51.50 TO 54.80 | 15th Floor | 42521 | 42523 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5136 | Steel reinforcement For Shear wall 5* Axis C5/a2 TO A3 | Steel Reinforcement | SH.W | 51.50 TO 54.80 | 15th Floor | 42521 | 42523 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5137 | Steel reinforcement for Shear wall 3 Axis C6/A2 TO A3 | Steel Reinforcement | SH.W | 51.50 TO 54.80 | 15th Floor | 42521 | 42523 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5138 | Steel reinforcement For Shear wall 3* Axis C8/A2 TO A3 | Steel Reinforcement | SH.W | 51.50 TO 54.80 | 15th Floor | 42522 | 42526 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5139 | Form Work For Shear Wall 3* Axis C8/A2 TO A3 | form work | SH.W | 51.50 TO 54.80 | 15th Floor | 42522 | 42526 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5140 | Form work For Shear wall 2 Axis C10/A2 TO A3 | form work | SH.W | 51.50 TO 54.80 | 15th Floor | 42522 | 42523 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5141 | Steel reinforceement For Shear wall 2 Axis C10/A2 TO A3 | Steel Reinforcement | SH.W | 51.50 TO 54.80 | 15th Floor | 42522 | 42523 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5142 | Steel reinforcement for Pour Strip 1/2 Axis B9/A6TO A12 | Steel Reinforcement | Pour strip | 46.50 | 12th Floor | 42523 | 42523 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5143 | Form Work for Columun CC6 Axis c11 /A3 | form work | Columun | 51.50 TO 54.80 | 15th floor | 42523 | 42526 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5144 | Steel Reinforcement For Columun CC6 Axis C11/ A3 | Steel Reinforcement | Columun | 51.50 TO 54.80 | 15th floor | 42523 | 42526 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5145 | Steel Reinforcement For Stair Case 11 Axis A7 TO A8/B16 TO B17 | Steel Reinforcement | Stair | 43.20 TO 46.50 | 12th Floor | 42523 | 42527 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5146 | Form work For DCC1 And DCC3 Axis A10 TO A11/B9 | form work | second Stage | 49.80 TO 53.10 | 14th floor | 42523 | 42527 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5147 | Steel Reinforcement For DCC1 And DCC3 Axis A10 TO A11/B9 | Steel Reinforcement | second Stage | 49.80 TO 53.10 | 14th floor | 42523 | 42526 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5148 | Form work For DCC7 Axis A6/B9 | Form Work | second Stage | 49.80 TO 53.10 | 14th floor | 42523 | 42526 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5149 | Steel Reinforcement For DCC7 Axis A6/B9 | Steel Reinforcement | second Stage | 49.80 TO 53.10 | 14th floor | 42523 | 42526 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5150 | Form Work For SH.W 9 Axis A8 TO A10/B9 | Form Work | second Stage | 49.80 TO 53.10 | 14th floor | 42523 | 42527 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5151 | Steel Reinforcement For SH.W 9 Axis A8 TO A10/B9 | Steel Reinforcement | second Stage | 49.80 TO 53.10 | 14th floor | 42523 | 42526 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5152 | Steel Reinforcement For 2 CC9 Axis A11/B10 TO B12 | Steel Reinforcement | second Stage | 49.80 TO 53.10 | 14th floor | 42523 | 42526 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5153 | Form Work For 2 CC9 Axis A11/B10 TO B12 | form Work | second Stage | 49.80 TO 53.10 | 14th floor | 42523 | 42526 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5154 | Steel Reinforcement For 2CC7 Axis A6/B10 TO B12 | Steel Reinforcement | second Stage | 49.80 TO 53.10 | 14th floor | 42523 | 42526 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5155 | form Work For 2CC7 Axis A6/B10 TO B12 | form Work | second Stage | 49.80 TO 53.10 | 14th floor | 42523 | 42526 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5156 | Steel Reinforcement For Shear Wall 1 + C1 Axis B19/A1 | Steel Reinforcement | SH.W | 51.50 TO 54.80 | 15th Floor | 42525 | 42527 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5157 | Form Work for Shear wall1+C1 Axis B19/A1 | form work | SH.W+C1 | 51.50 TO 54.80 | 15th Floor | 42525 | 42527 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5158 | Steel Reinforcement For Core 6 Axis B15 TO B16/A1 TO A2 | Steel Reinforcement | core | 51.50 TO 54.80 | 15th Floor | 42525 | 42527 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5159 | Form Work For Core 6 Axis B15 TO B16/A1 TO A2 | form Work | core | 51.50 TO 54.80 | 15th Floor | 42525 | 42528 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5160 | Steel Reinfrocement For Columun CC5 Axis C9/A3 | Steel Reinforcement | columun | 51.50 TO 54.80 | 15th Floor | 42525 | 42526 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5161 | Form Work For Columun CC5 Axis C9/A3 | form Work | columun | 51.50 TO 54.80 | 15th Floor | 42525 | 42527 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5162 | Steel reinforcement For ColumunC5 Axis B18/A1 | Steel Reinforcement | columun | 51.50 TO 54.80 | 15th Floor | 42525 | 42526 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5163 | Form work for Columun C5 Axis B18/A1 | form work | columun | 51.50 TO 54.80 | 15th Floor | 42525 | 42527 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5164 | Top steel Reinforcement For First Stage Slab Hotel Tower Axis B1 TO C5/A1 TO A3 | Steel Reinforcement | slab | 54.80 | 15th Floor | 42525 | 42526 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5165 | Bottom Steel Reinfrocement For first stage Slab Hotel Tower Axis B1 TO C5/A1 TO A3 | Steel Reinforcement | slab | 54.80 | 15th Floor | 42525 | 42526 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5166 | Tendons -Strands-Anchors And Profiles First stage Hotel Tower Slab Axis B1 TO C5/A1 TO A3 | Anchor | First Stage | 54.80 | 15th Floor | 42525 | 42526 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5167 | Stressing For Cables of Second Stage Post tension Slab Hoteel Tower Axis B19 To C5/A1 TO A3 | Stressing | second Stage | 51.50 | 15th Floor | 42525 | 42532 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5168 | Groutig For Cables Of First stage Post tension Slab Hotel Tower Axis B1 TO C5/A1 To A3 | Grout | First Stage | 51.50 | 15th Floor | 42525 | 42537 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5169 | Check Form work At 53.10 First stage | form work | second stage | 53.10 | 13th floor | 42526 | 42534 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5170 | form Work For Core 3 Axis A8 TO A11/B10 TO B12 | form work | core | 53.10 TO 56.40 | 14th floor | 42526 | 42529 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5171 | Tendos-Strands-Anchors and profiles for third stage of post tension slab Axis a6 TO A12/B13 TO B19 | Post Tension | slab | +46.50 | 12th Floor | 42526 | 42528 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5172 | Stressing of strands for second Stage Post tension Slab Axis A6 TO A12/B4 TO B9 | Post Tension | slab | +49.80 | 13th floor | 42526 | 42532 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5173 | Grouting For Cables For Second stage Of Post tension Slab | Grout | slab | +46.50 | 12th Floor | 42526 | 42527 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5174 | Top & bottom layers and beams steel reinforcement for third post tension slab Axis A6 TO A12/B13 TO B19 | Steel Reinforcement | slab | +46.50 | 12th Floor | 42526 | 42527 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5175 | steel reinforcement for Columns 16B | Steel Reinforcement | fence | 1.10 |  | 42528 | 42528 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5176 | Form work For Stair Case 3 Axis A8/B6 TO B7 | form Work | stair | 49.80 TO 53.10 | 14th floor | 42528 | 42534 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5177 | Form Work For Fence Column 16B Axis A15 | form Work | fence | 1.10 |  | 42528 | 42534 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5178 | Steel Reinforcement for shear wall 8 Axis C2/A2 TO A3 | Steel Reinforcement | SH.W | 54.80 To 58.10 | 16th Floor | 42529 | 42532 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5179 | Form Work For Shear Wall 8 Axis C2/A2 TO A3 | form Work | SH.W | 54.80 To 58.10 | 16th Floor | 42529 | 42534 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5180 | Form Work for Core 8 Axis B1/A2 TO A3 | form Work | core | 60.00 TO 63.30 | 17th Floor | 42529 | 42534 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5181 | Steel Reinforcement For Core 8 Axis B1/A2 TO A3 | Steel Reinforcement | core | 60.00 TO 63.30 | 17th Floor | 42529 | 42532 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5182 | Form Work For Shear Walls 6&7 Axis C3 TO C4/A2 TO A3 | form Work | SH.W | 58.10 TO 61.40 | 17th Floor | 42529 | 42534 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5183 | Form Work for Core 5 Axis B6 TO B8/A8 To A10 | form Work | Core | 55.50 TO 56.40 | 16th Floor | 42530 | 42534 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5184 | Steel Reinforcement For Core 2 Axis B14 TO B15/A8 TO A10 | Steel Reinforcement | Core | 49.80 TO 53.10 | 15th Floor | 42530 | 42532 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5185 | Steel reinforcement For 5 Columuns CC4 Axis D1 TO D2 &D3 TO D4/A9 | Steel Reinforcement | Columun | 46.50 TO 49.80 | 14th floor | 42530 | 42533 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5186 | Form work For 5 Columuns CC4 Axis D1 TO D2 &D3 TO D4/A9 | form work | Columun | 46.50 TO 49.80 | 14th floor | 42530 | 42535 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5187 | Form work For 2 Columun CC7 & CC4 Axis B16/A6 TO A12 &A10 TO A11 | form work | Columun | 46.50 TO 49.80 | 14th floor | 42530 | 42535 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5188 | Steel Reinforcement For 2 Columuns CC7 &CC4 Aixis B16/A6 TO A12&A10 TO A11 | Steel Reinforcement | Columun | 46.50 TO 49.80 | 14th floor | 42530 | 42533 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5189 | Steel reinfocement For 2 Columuns CC7 & CC9 Axis B14/A6 TO A11 | Steel Reinforcement | Columun | 46.50 TO 49.80 | 14th floor | 42530 | 42533 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5190 | Form Work For 2 Columuns CC7 & CC9 Axis B14/A6 TO A11 | form work | Columun | 46.50 TO 49.80 | 14th floor | 42530 | 42535 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5191 | Steel Reinforcement For 4 Double Columns Axis B13/a6 TO A8,A10&A11 | Steel Reinforcement | Columun | 46.50 TO 49.80 | 14th floor | 42530 | 42533 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5192 | Form work For 4 Double Columns Axis B13/A6 TO A8 &A10TO A11 | form Work | Columun | 46.50 TO 49.80 | 14th floor | 42530 | 42540 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5193 | Steel Reinforcement For Stair 3 Axis B6 TO B8/A8 TO A10 | Steel Reinforcement | Stair | 49.80 TO 53.10 | 16th Floor | 42530 | 42534 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5194 | Stressing For Cables Of First Stage Post Tension Slab hotel tower Axis B1 TO C5/A1 TO A3 | Stressing | post tension | 54.80 | 16th Floor | 42530 | 42534 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5195 | Check Form work At 54.80 Second stage | form Work | second stage | 54.80 | 14th floor | 42530 | 42534 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5196 | Steel Reinforcement For Shear Wall 1 Axis C7 TO B1/A1 | Steel Reinforcement | shear Wall | 58.10 TO 61.40 | 16th Floor | 42532 | 42533 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5197 | Form Work For Shear Wall 1 Axis C7 TO B1/A1 | form work | shear Wall | 58.10 TO 61.40 | 16th Floor | 42532 | 42534 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5198 | Steel Reinforcement For Core 7 Axis C7/A2 TO A3 | Steel Reinforcement | core | 58.10 TO 61.40 | 16th Floor | 42532 | 42533 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5199 | Form Work For Core 7 Axis C7/A2 TO A3 | Form work | core | 58.10 TO 61.40 | 16th Floor | 42532 | 42537 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5200 | Tendons-Strands-anchors and profiles for first stage of post tension slab axis A6 TO A12/B4 TO B9 | Anchor | First Stage | +53.10 | 14th floor | 42532 | 42534 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5201 | Top& Bottom layers beams steel reinforcement For First post tension slab Axis A6 TO A12/B4 TO B9 | Steel Reinforcement | First Stage | +53.10 | 14th floor | 42532 | 42533 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5202 | Stressing of strands for third stage post tension slab Axis A6 TO A12/B13 TO B19 | Post Tension | third stage | +46.50 | 12th Floor | 42533 | 42537 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5203 | Steel Reinforcement For Pour Strip Of Slab Hotel Tower Axis C5/A1 TO A3 | Steel Reinforcement | Pour strip | 51.50 | 14th floor | 42533 | 42535 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5204 | Form Work For Stair Case 6 Axis A8/B10 TO B12 | form work | stair | 49.80 TO 53.10 | 14th floor | 42534 | 42537 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5205 | form work for stair case 7 axis A10/B10-B11 | form work | stair | 49.80 TO 53.10 | 14th floor | 42534 | 42537 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5206 | Top Steel Reinforcement For Second Stage Slab Hotel Tower Axis C5 To B19/A1 TO A3 | Steel Reinforcement | second Stage | 54.80 | 14th floor | 42534 | 42535 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5207 | Tendos ,Strands,Anchors and profiles for second stage Slab hotel tower Axis C5 TO B19/A1 To A3 | Stressing | second Stage | 54.80 | 14th floor | 42534 | 42535 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5208 | Bottom Steel Reinforcement For Second Stage Slab Hotel Tower Axis C5 TO B19/A1 TOA3 | Steel Reinforcement | second Stage | 54.80 | 14th floor | 42534 | 42535 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5209 | Form Work For Shear Wall 6 Axis C4/A2 TO A3 | form work | SH.W | 61.40 TO 64.70 | 17th Floor | 42535 | 42539 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5210 | Form Work for Shear wall 7 Axis C3/A2 tO A3 | form work | SH.W | 61.40 TO 64.70 | 17th Floor | 42535 | 42541 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5211 | Steel reinforcement For Shear Wall 6 Axis C4/A2 TO A3 | Steel Reinforcement | SH.W | 61.40 TO 64.70 | 17th Floor | 42535 | 42537 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5212 | Steel reinforcement for Shear wall 7 Axis C3/A2 tO A3 | Steel Reinforcement | SH.W | 61.40 TO 64.70 | 17th Floor | 42535 | 42540 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5213 | Form Work For Shear wall 1 Axis B10 TO B19/A1 | form work | SH.W | 61.40 TO 64.70 | 17th Floor | 42535 | 42544 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5214 | Steel Reinforcement for Shear wall 1 Axis B10 TO B19/A1 | Steel Reinforcement | SH.W | 61.40 TO 64.70 | 17th Floor | 42535 | 42540 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5215 | Steel Reinforcement For Stair Case 6 Axis A8/B11 TO B13 | Steel Reinforcement | stair | +49.80 TO 53.10 | 14th floor | 42536 | 42537 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5216 | Form Work For Core 2 Axis A8 TO A10/B14 TO B16 | form Work | core | 49.80 TO 53.10 | 14th floor | 42536 | 42537 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5217 | Steel Reinforcement For Pour Strip Between first and second stage Axis A6 TO A12/B8 TO B9 | Steel Reinforcement | Pour strip | +49.80 | 13th floor | 42536 | 42540 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5218 | Steel Reinforcement For Core 3 Axis A8 TO A10/B10 TO B12 | Steel Reinforcement | Core | 56.40 TO 59.70 | 16th Floor | 42536 | 42537 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5219 | Steel Reinforcement For Core 1 Axis A8 TO A10/B17 | Steel Reinforcement | Core | 46.50 TO 49.80 | 13th floor | 42536 | 42537 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5220 | Check Form work At 58.10 first stage | form work | second stage | 58.10 | 15th Floor | 42537 | 42539 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5221 | Steel Reinforcement For Stair Case 7 Axis A10/B10 TO B11 | Steel Reinforcement | second stage | 49.80 TO 53.10 | 14th floor | 42537 | 42541 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5222 | Top & Bottom Layers and beams steel reinforcement For second Post Tension slab Axis A6 To A12/B9 TO B13 | Steel Reinforcement | second stage | +53.10 | 14th floor | 42537 | 42537 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5223 | Tendons Strands Anchors and profiles for Second Stage Of Post tension Slab Axis A6 TO A12/B9 TO B13 | Anchor | second stage | +53.10 | 14th floor | 42537 | 42540 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5224 | Steel reinforcement for Shear wall 3 Axis C6/A2 TO A3 | Steel Reinforcement | SH.W | 54.80 To 58.10 | 16th Floor | 42537 | 42537 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5225 | Steel Reinforcement For Shear wall 5* Axis C5/A2 TO A3 | Steel Reinforcement | SH.W | 54.80 To 58.10 | 16th Floor | 42537 | 42540 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5226 | Form work For Shear wall 5* Axis C5/A2 TO A3 | form work | SH.W | 54.80 To 58.10 | 16th Floor | 42537 | 42541 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5227 | Form work For Shear wall3 Axis C6/A2 TO A3 | form work | SH.W | 54.80 To 58.10 | 16th Floor | 42537 | 42540 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5228 | form work For Shear wall 3* Axis C8/A2 TO A3 | form work | SH.W | 54.80 To 58.10 | 16th Floor | 42537 | 42540 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5229 | Steel reinforcement For Shear wall 3* Aixs C8/A2 TO A3 | Steel Reinforcement | SH.W | 54.80 To 58.10 | 16th Floor | 42537 | 42537 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5230 | Form work For Core 1 Shear wall 1 Axis B16 TO B18/A8 TO A10 | form work | core+SH.W | +46.50 TO 49.80 | 12th Floor | 42539 | 42541 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5231 | Steel Reinforcement For Stair 12 Axis C6/A2 TO A3 | Steel Reinforcement | Stair | 41.60 TO 44.90 | 12th Floor | 42540 | 42563 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5232 | Steel reinforcement For Stair 14 Axis B16/A1 | Steel Reinforcement | Stair | 31.70 TO 35.00 | 9th | 42540 | 42563 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5233 | Form work For Stair 14 Axis B16/A1 | form work | Stair | 31.70 TO 35.00 | 9th | 42540 | 42541 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5234 | Form Work For Columns and Shear Walls Axis C9/A3)(C11/A3)(C10/A2 TO A3&B18/A1 | form work | columun | 54.50 TO 58.10 |  | 42540 | 42543 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5235 | Steel Reinforcement For Columuns and Shear walls Axis C9/A3 &C11/A3 &C10/A2 TO A3&B18/A1 | Steel Reinforcement | columun & SH.W | 54.50 TO 58.10 |  | 42540 | 42541 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5236 | Form work For Columuns and shear walls | form work | columun | 54.80 TO 58.10 |  | 42540 | 42544 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5237 | Steel Reinforcement For Columns and shear walls | Steel Reinforcement | SH.W | 54.50 TO 58.10 |  | 42540 | 42543 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5238 | Form work for Core 6 Walls axis B15 TO B17/A1 | form work | Core | 54.50 TO 58.10 |  | 42540 | 42544 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5239 | Steel Reinforcement For Core 6 Walls | Steel Reinforcement | Core | 54.50 TO 58.10 |  | 42540 | 42543 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5240 | Steel reinforcement For 7 Columun CC7Axis A6/B5)(A6/B6)(A6/B8)(8/B4)(A9/B4)(A10/B4)(A11/B4) | Steel Reinforcement | columun | 53.10 TO 56.40 |  | 42540 | 42540 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5241 | Form work For 7 Columun CC7 Axis A6/B5)(A6/B6)(A6/B8)(A8/B4)(A9/B4)(A10/B4)(A11/B4) | form work | columun | 53.10 TO 56.40 | 13th floor | 42540 | 42548 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5242 | Steel reinforcemnet For 2 Columun CC9 Axis A11/B6 TO B8 | Steel Reinforcement | columun | 53.10 TO 56.40 | 13th floor | 42540 | 42541 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5243 | Form work For 2 Coulmns CC9 Axis A11/B6)(A1/B8 | form work | columun | 53.10 TO 56.40 | 13th floor | 42540 | 42548 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5244 | Stressing for cables of second stage post tension slab hotel tower Axis C5 TO B19/A1 TO A3 | Post Tension | Stressing | 54.80 | 15th Floor | 42541 | 42550 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5245 | Grouting For Ducts of second stage post tension slab hotel tower Axis C5 TO B19/A1 TO A3 | Post Tension | Grout | 51.50 | 14th floor | 42541 | 42548 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5246 | Grouting For ducts Of First stage post tension slab hotel tower Axis C5 TO B1/A1 TO A3 | Post Tension | Grout | 54.80 | 15th floor | 42541 | 42555 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5247 | Tendons,Strands,anchors and profiles for first stage slab hotel tower Axis B1 TO C5/A1 TO A3 | form work | First Stage | 58.10 | 16th Floor | 42542 | 42543 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5248 | Bottom and top steel reinforcement for First stage Hotel Tower Axis B1 TO C5/A1 TO A3 | Steel Reinforcement | First Stage | 58.10 | 16th Floor | 42542 | 42547 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5249 | Steel reinforcement For SH.W 1 Axis B1 TO B11/A1 | Steel Reinforcement | SH.W | 61.40 TO 64.70 | 17th Floor | 42542 | 42548 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5250 | Stressing for Cables Of First stage Post tension Slab R.D Tower Axis A6 TO A12/B4 TO B9 | Post Tension | Slab | 53.10 | 13th floor | 42542 | 42548 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5251 | Check Form work At 49.80 third stage | form work | third stage | 49.80 | 12th Floor | 42542 | 42544 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5252 | Form work For Stair 11Axis B16 TO B18/a8 TO A10 | form work | Stair | 46.50 TO 49.80 | 11-12th Floor | 42543 | 42544 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5253 | Form work For 2Coulmuns CC9 Axis B10 TO B12/A11 | form work | columun | 53.10 TO 56.40 | 14th floor | 42544 | 42553 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5254 | Steel reinforcement For 2 Coulmns CC9 Axis B10 TO B12/A11 | Steel Reinforcement | columun | 53.10 TO 56.40 | 14th floor | 42544 | 42547 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5255 | Form work for Shear wall9 Axis A8 TO A9/B9 | form work | SH.W | 53.10 TO 56.40 | 14th floor | 42544 | 42548 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5256 | steel reinforcement for shear wall 9 axis A8 to A9/B9 | Steel Reinforcement | SH.W | 53.10 TO 56.40 | 14th floor | 42544 | 42547 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5257 | Form work For DCC7&DCC1&DCC3 Axis A6 TO A11/B9 | form work | columun | 53.10 TO 56.40 | 14th floor | 42544 | 42548 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5258 | Steel Reinforcement For DCC7&DCC1&DCC3 Axis A6 TO A11/B9 | Steel Reinforcement | columun | 53.10 TO 56.40 | 14th floor | 42544 | 42547 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5259 | Steel Reinforcement For 2 Columuns CC7 Axis B10 TO B12/A6 | Steel Reinforcement | columun | 53.10 TO 56.40 | 14th floor | 42544 | 42547 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5260 | Form work For 2 Coulmns CC7 Axis B10 TO B12/A6 | form work | columun | 53.10 TO 56.40 | 14th floor | 42544 | 42548 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5261 | Form work For Core 3 Axis A7 TO A10/B10 TO B12 | form work | Core | 56.40 TO 59.70 | 15th Floor | 42543 | 42544 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5262 | Steel Reinforcement For Pour strip between second and third stage Axis A6 TO A12/B12 TO B13 | Steel Reinforcement | Pour strip | 46.50 | 12th Floor | 42544 | 42548 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5263 | steel reinforcement for core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | Core | 56.40 TO 59.70 | 16th Floor | 42546 | 42548 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5264 | Steel Reinforcement for stair 11 Axis B17/A9 | Steel Reinforcement | Stair | 46.50 TO 49.80 | 13th floor | 42547 | 42550 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5265 | Steel Reinforcement For Columuns and Shear walls Axis C9/A3 &C11/A3 &C10/A2 TO A3&B18/A1)&C2/A2 TO A5 | Steel Reinforcement | SH.W | 58.10 TO 61.40 | 17th Floor | 42547 | 42548 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5266 | Form work For Columuns and shear walls 8 Axis C2/A2 TO A5 | Form work | SH.W | 58.10 TO 61.40 | 17th Floor | 42547 | 42550 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5267 | Form work For Core Walls 7 Axis B15 TO B17/A1 | Form work | Core | 61.40 TO 64.70 | 17th Floor | 42547 | 42553 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5268 | Steel reinforcement For Core Walls 7 Axis B15 TO B17/A1 | Steel Reinforcement | Core | 61.40 TO 64.70 | 17th Floor | 42547 | 42548 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5269 | Stressing OF Strand For Second Stage Post tension Slab Axis A6 TO A12/B9 TO B13 | Stressing | Slab | 53.10 | 14th floor | 42547 | 42550 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5270 | Form work For SH.W 1Axis B1 TO B11/A1 | form Work | SH.W | 61.40 TO 64.70 | 18th Floor | 42548 | 42550 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5271 | TOP & Bottom Layers and Beams Steel Reinforcement For Thired stage Post tension Slab Axis B13 TO B19/A6 To A12 | Steel Reinforcement | Slab | 49.80 | 13th floor | 42549 | 42550 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5272 | Tendons -Strands-Anchors and Profiles For Third stage of post tension slab Axis B13 TO B19/A6 TO A12 | Anchor | Slab | 49.80 | 13th floor | 42549 | 42550 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5273 | Steel reinforcement For Core2 Axis B14 TO B15/A8 TO A10 | Steel Reinforcement | Core | 53.10 TO 56.40 | 15th Floor | 42549 | 42550 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5274 | Form work For Core 2 Axis B14 TO B15/A8 TO A10 | form work | Core | 53.10 TO 56.40 | 15th Floor | 42550 | 42555 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5275 | Grouting For Cables for third stage Of Post tension slab Axis B13 TO B19/A6 TO A12 | Grout | Slab | 46.50 | 12th Floor | 42549 | 42553 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5276 | Stressing for Cables First Stage Slab Axis C5TOB1/A1 TO A3 | Stressing | Slab | 58.10 | 16th Floor | 42549 | 42555 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5277 | Check form work at 58.10 Second stage | form work | second stage | 58.10 | 15th Floor | 42549 | 42553 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5278 | Form work For Core 5 Axis B5 TO B8/A7 TO A11 | form work | Core | 56.40 TO 59.70 | 16th Floor | 42550 | 42553 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5279 | Form Work For Core 8 Axis B1 TO C2/A1 TO A3 | form work | Core | 64.70 TO 68 | 19th Floor | 42550 | 42555 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5280 | Steel Reinforcement For Core 8 Axis B1 TO C2/A1 TO A3 | Steel Reinforcement | Core | 64.70 TO 68 | 19th Floor | 42550 | 42555 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5281 | Steel reinforcement Top & Bottom For Second Stage Slab Hotel Tower Axis B5 TO B19/A1 TO A3 | Steel Reinforcement | Slab | 58.10 | 15th Floor | 42550 | 42555 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5282 | Tendons,Strands,Anchors and profiles for second stage slab hotel tower Axis B5 TO B19/A1 TO A3 | Anchor | Slab | 58.10 | 15th Floor | 42550 | 42553 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5283 | Duct Grouting For Cable at first stage post tension slab Axis a6 TO A12/b4 TO B9 | Grout | Slab | +49.80 | 13th floor | 42553 | 42575 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5284 | grout for cable for second stage of post tension slab axis A6 TO A12/B9 TO B13 | Grout | Slab | +49.80 | 13th floor | 42553 | 42553 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5285 | Steel reinforcement For Core 3 Axis A8 TO A12/B10 TO B12 | Steel Reinforcement | core | 59.70 TO 63 | 17th Floor | 42553 | 42553 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5286 | Form work for CC1* Axis B13toA8 | form work | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5287 | Steel Reinforcement For CC1* Axis B13 TO A8 | Steel Reinforcement | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42555 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5288 | Form Work For DCC7 Axis B13/A6 | form work | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5289 | Steel Reinforcement For DCC7 Axis B13/A6 | Steel Reinforcement | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42564 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5290 | Form work For 5 CC4 Axis D1,D2,D3,D4,A9/B19 | form work | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42563 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5291 | Steel reinforcement For 5 CC4 Axis D1,D2,D3,D4,A9/B19 | Steel Reinforcement | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42555 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5292 | Form Work For CC9 Axis B14/A11 | form work | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5293 | Steel reinforcement For CC9 Axis B14/A11 | Steel Reinforcement | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42555 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5294 | Form work for 2DCC1 Axis B13toA11/B13toA10 | Form work | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5295 | Steel Reinforcement For 2DCC1 Axis B13 TO A11/B13 TO A10 | Steel Reinforcement | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42555 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5296 | Form Work For CC4 Axis A11/B16 | Form work | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42567 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5297 | Steel Reinforcement For CC4 Axis A11/B16 | Steel Reinforcement | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42555 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5298 | Form work For CC7 Axis B16/A12 | form work | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42567 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5299 | Steel reinforcement For CC7 Axis B16/A12 | Steel Reinforcement | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42555 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5300 | Form work For 2CC7 Axis A6/B14TO B16 | Form work | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5301 | Steel rinforcement For 2CC7 Axis B16TO B14/A6 | Steel Reinforcement | Columun | 49.80 TO 53.10 | 14th floor | 42554 | 42564 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5302 | Form work For Shear wall 3* Axis C8/A2 TO A3 | form work | SH.W | 58.10 TO 61.40 | 17th Floor | 42555 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5303 | Steel reinforcement For Shear wall 5* Axis C5/A2 TO A3 | Steel Reinforcement | SH.W | 58.10 TO 61.40 | 17th Floor | 42555 | 42555 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5304 | Form work For Shear wall 5* Axis C5/A2 TO A3 | form work | SH.W | 58.10 TO 61.40 | 17th Floor | 42555 | 42563 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5305 | Steel reinforcement For Shear wall 3* Axis C8/A2 TO A3 | Steel Reinforcement | SH.W | 58.10 TO 61.40 | 17th Floor | 42555 | 42567 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5306 | Form Work For Shear Wall 3 axis C6/A2 to A3 | form work | SH.W | 58.10 TO 61.40 | 17th Floor | 42555 | 42563 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5307 | Steel reinforcement for Shear wall 3 Axis C6/A2 TO A3 | Steel Reinforcement | SH.W | 58.10 TO 61.40 | 17th Floor | 42555 | 42555 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5308 | Tendons,Strands,Anchors and Profiles for Slab Axis | Stressing | Slab | 49.80 | 13th floor | 42562 | 42564 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5309 | Stressing for cables of second stage post tension slab hotel tower Axis C5 TO B19/A1 TO A3 | Post Tension | Slab | 58.10 | 16th Floor | 42562 | 42564 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5310 | Form work For First Stage Hotel Tower Axis B1 TO C5/A1 TO A3 | Form work | First Stage | 61.40 | 15th Floor | 42563 | 42564 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5311 | Form Work For First Stage Slab RD Tower | Form work | Slab | 56.40 | 15th Floor | 42563 | 42564 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5312 | Tendos Strands-Anchors and Profiles for first stage of Post tension slab Axis A6 TO A10/B4 TO B9 | Stressing | Slab | 56.40 | 15th Floor | 42563 | 42567 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5313 | Steel Reinforcement For Stair Case 3 Axis A8/B6 TO B7 | Steel Reinforcement | Stair | 53.10 TO 56.40 | 15th Floor | 42563 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5314 | Form work For Stair Case 7Axis A10/B10 TO B11 | Form work | Stair | 53.10 TO 56.40 | 15th Floor | 42563 | 42567 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5315 | Form Work For Stair Case 6 Axis A8/B10 TO B12 | Form work | Stair | 53.10 TO 56.40 | 15th Floor | 42563 | 42567 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5316 | Top & Bottom Layers and beams Steel reinforcement for First Post Tension Slab Axis A6 TO A12/B4TO B9 | Steel Reinforcement | First Stage | 56.40 | 15th Floor | 42563 | 42567 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5317 | Form work For Shear wall 2 Axis C10/A2 TO A3 | form work | SH.W | 58.10 TO 61.40 | 17th Floor | 42564 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5318 | Steel Reinforcement For Shear Wall 2 Axis C10/A2 TO A3 | Steel Reinforcement | SH.W | 58.10 TO 61.40 | 17th Floor | 42564 | 42567 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5319 | Steel Reinforcement For Shear Wall 1+C1 Axis A1/B19 | Steel Reinforcement | SH.W | 58.10 TO 61.40 | 17th Floor | 42564 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5320 | Form Work for Shear wall1+C1 Axis B19/A1 | Form Work | SH.W | 58.10 TO 61.40 | 17th Floor | 42564 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5321 | Steel Reinforcement For Columun CC5 & CC6 Axis C9 TO C11/A3 | Steel Reinforcement | columun | 58.10 TO 61.40 | 17th Floor | 42564 | 42567 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5322 | Form Work For Columuns CC5 & CC6 Axis C9 TO C11/A3 | Form Work | columun | 58.10 TO 61.40 | 17th Floor | 42564 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5323 | Form Work For Core 6 Axis B15 TO B16/A1 TO A2 | Form Work | Core | 58.10 TO 61.40 | 17th Floor | 42564 | 42572 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5324 | Steel Reinforcement For Core 6 Axis B15 TO B16/A1 TO A2 | Steel Reinforcement | Core | 58.10 TO 61.40 | 17th Floor | 42564 | 42570 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5325 | Form Work For Columun C5 Axis B18/A1 | Form work | columun | 58.10 TO 61.40 | 17th Floor | 42564 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5326 | Steel Reinforcement For Columun C5 Axis B18/A1 | Steel Reinforcement | columun | 58.10 TO 61.40 | 17th Floor | 42564 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5327 | Form Work For Core 1 Axis A8 TO A10/B17 | Form work | Core | 49.80 TO 53.10 | 14th floor | 42565 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5328 | Steel Reinforcement For Core 1 Axis A8 TO A10/B17 | Steel Reinforcement | Core | 49.80 TO 53.10 | 14th floor | 42565 | 42567 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5329 | Form Work For Slab Stage RD Tower Axis B9 TO B13/A6 TO A12 | Form work | Slab | 54.40 | 11th Floor | 42567 | 42569 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5330 | Tendos,Strands,Anchors and Profiles For First Stage Hotel Tower Axis B1 TO C5/A1 TO A3 | Stressing | Slab | 61.40 | 17th Floor | 42567 | 42569 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5331 | Bottom And Top Steel Reinforcement For First Stage Slab Hotel Tower Axis B1 TO C5/A1 TO A3 | Steel Reinforcement | Slab | 61.40 | 17th Floor | 42567 | 42569 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5332 | Top,Bottom Layers And beams Steel reinforcement For Slab Inside Core 5 Axis A6 TO A12/B9 TO B13 | Steel Reinforcement | Core | 56.40 | 15th Floor | 42568 | 42572 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5333 | Steel Reinforcement for Stair Case 7 Axis A10/B10 TO B11 | Steel Reinforcement | Stair | +53.10 TO 56.40 | 15th Floor | 42568 | 42572 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5334 | Steel reinforcement For Stair Case 6 Axis A8/B11 TO B13 | Steel Reinforcement | Stair | +53.10 TO 56.40 | 15th Floor | 42568 | 42572 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5335 | Form Work Removal For Second Stage Of Post tension Slab Axis A6 TO A12/B8 TO B13 | Form Work | Slab | +53.10 | 14th floor | 42568 | 42569 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5336 | Form Work Removal For Third Stage Of Post tension Slab Axis A6 TO A12/B13 TO B19 | Form Work | Slab | 49.80 | 13th floor | 42568 | 42569 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5337 | Tendons-Strands-Anchors and Profiles For Second Stage OF Post tension Slab Axis A6 TO A12/B13 TO B9 | Anchor | Slab | 56.40 | 15th Floor | 42568 | 42572 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5338 | Top & Bottom Layers and beams Steel Reinforcement For Second Stage Of Slab Axi s A6 TO A12/B9 TO B13 | Steel Reinforcement | slab | 56.40 | 15th Floor | 42568 | 42572 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5339 | Steel Reinforcement For 2 CC9 Axis A11/B6 TO B8 | Steel Reinforcement | Columun | +56.40 TO 59.70 | 16th Floor | 42568 | 42572 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5340 | Form Work For 2 CC9 Axi A11/B6 TO B8 | Form Work | Columun | +56.40 TO 59.70 | 16th Floor | 42568 | 42572 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5341 | Steel Reinforcement Work For 4 CC7 Axis A8 TO A9&A10,11/B4 | Steel Reinforcement | Columun | +56.40 TO 59.70 | 16th Floor | 42568 | 42569 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5342 | Form Work For 4 CC7 Axis A8 TO A9 &A10 TO A11/B4 | Form Work | Columun | +56.40 TO 59.70 | 16th Floor | 42568 | 42572 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5343 | Form Work For 3CC7 Axis A6/B5 TO B6&B8 | Form Work | Columun | +56.40 TO 59.70 | 16th Floor | 42568 | 42572 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5344 | Steel Reinforcement For 3 CC7 Axis A6/B5 TO B6&B8 | Steel Reinforcement | Columun | +56.40 TO 59.70 | 16th Floor | 42568 | 42570 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5345 | Steel Reinforcement For Pour Strip Between Second and third Stage Axis A6 TO A12/B2 TO B13 | Steel Reinforcement | Pour strip | 49.80 | 13th floor | 42568 | 42572 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5346 | Steel reinforcement For Pour Strip Between First and Second Stage Axis A6 TO A12/B8 TO B9 | Steel Reinforcement | Pour strip | 53.10 | 14th floor | 42568 | 42569 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5347 | form Work For Core 3 Axis A8 TO A11/B10 TO B12 | Form Work | Core | 59.70 TO 63 | 17th Floor | 42569 | 42572 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5348 | steel reinforcement for core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | Core | 59.70 TO 63 | 17th Floor | 42569 | 42570 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5349 | steel reinforcement for Fence Beams Axis B13 TO B17/A1 | Steel Reinforcement | fence | 3.90 TO 4.30 |  | 42570 | 42572 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5350 | Form Work For Fence Beams | Form Work | fence | 3.90 TO 4.30 |  | 42570 | 42575 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5351 | Stressing for Cables Of First stage Post tension Slab R.D Tower | Stressing | Slab | 56.40 | 15th Floor | 42570 | 42575 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5352 | Check Form Work At 53.10third stage | form work | Slab | 53.10 | 13th floor | 42571 | 42578 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5353 | Form Work For Core 7 Axis C7/A2 TO A3 | form work | Core | 64.70 TO 68.00 | 18th Floor | 42572 | 42576 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5354 | Steel Reinforcement For Core 7 Axis C7/A2 TO A3 | Steel Reinforcement | Core | 64.70 TO 68.00 | 18th Floor | 42572 | 42572 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5355 | Form Work For Shear Wall 1 Axis B10 TO B19/A1 | Form Work | SH.W | 64.70 TO 68.00 | 18th Floor | 42572 | 42576 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5356 | Steel Reinforcement For Shear Wall 1 Axis B10 TO B19/A1 | Steel Reinforcement | SH.W | 64.70 TO 68.00 | 18th Floor | 42571 | 42572 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5357 | Steel Reinforcement For Shear Wall 7 Axis C3/A2 TO A3 | Steel Reinforcement | SH.W | 64.70 TO 68.00 | 18th Floor | 42572 | 42572 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5358 | Form Work For Shear Wall 7 Axis C3/A2 TO A3 | Form Work | SH.W | 64.70 TO 68.00 | 18th Floor | 42572 | 42576 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5359 | Form Work For Shear Wall 6 Axis C4/A2 TO A3 | Form Work | SH.W | 64.70 TO 68.00 | 18th Floor | 42572 | 42576 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5360 | Steel Reinforcement For Shear Wall 6 Axis C4/A2 TO A3 | Steel Reinforcement | SH.W | 64.70 TO 68.00 | 18th Floor | 42572 | 42572 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5361 | Check Location Of Form Work For SH.W 1 From Level 64.70 TO 68.00 at Axis B6 TO B10/A1 | Form Work | SH.W | 64.70 TO 68.00 | 18th Floor | 42577 | 42577 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5362 | Form Work For Shear Wall 8 Axis C2/A2 TO A3 | Form Work | SH.W | 61.40 TO 64.70 | 17th Floor | 42572 | 42576 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5363 | Grouting For Ducts of second stage post tension slab hotel tower Axis C5 TO B19/A1 TO A3 | Grout | Slab | 58.10 | 16th Floor | 42574 | 42575 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5364 | Grouting For ducts Of First stage post tension slab hotel tower Axis C5 TO B1/A1 TO A3 | Grout | Slab | 58.10 | 16th Floor | 42571 | 42572 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5365 | Steel Reinforcement For Shear Wall 8 Axis C2/A2 TO A3 | Steel Reinforcement | SH.W | 61.40 TO 64.70 | 17th Floor | 42571 | 42572 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5366 | Check Form Work At 61.40 Second Stage Level 61.40 | form work | Slab | 61.40 | 16th Floor | 42572 | 42578 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5367 | Form Work For Columun DCC7 Axis B9/A6 | form work | Columun | 56.40 TO 59.70 | 16th Floor | 42572 | 42577 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5368 | Steel Reinforcement For DCC 7 Axis B9/A6 | Steel Reinforcement | Columun | 56.40 TO 59.70 | 16th Floor | 42572 | 42576 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5369 | Form Work For SH.W 9+CC1 Axis B9/A8 To A9 | Form Work | SH.W | 56.40 TO 59.70 | 16th Floor | 42572 | 42577 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5370 | Steel Reinforcement For SH.W 9+CC1 Axis B9/A8 TO A9 | Steel Reinforcement | SH.W | 56.40 TO 59.70 | 16th Floor | 42572 | 42577 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5371 | Form Work For 2Columns CC9 Axis B10 TO B12/A11 | Form Work | Columun | 56.40 TO 59.70 | 16th Floor | 42572 | 42577 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5372 | Steel Reinforcement For 2Columun CC9 Axis A11/B10 TO B12 | Steel Reinforcement | Columun | 56.40 TO 59.70 | 16th Floor | 42572 | 42576 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5373 | Form Work For 2 Columuns D CC1&D CC3 Axis B9/A10 TO A11 | form Work | Columun | 56.40 TO 59.70 | 16th Floor | 42572 | 42577 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5374 | Steel Reinforcement For 2 Columuns D CC1&D CC3 Axis B9/A10 TO A11 | Steel Reinforcement | Columun | 56.40 TO 59.70 | 16th Floor | 42572 | 42575 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5375 | Form Work For Columuns CC7 Axis B10 TO B12/A6 | form Work | Columun | 56.40 TO 59.70 | 16th Floor | 42572 | 42577 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5376 | Steel Reinforcement For 2 Columuns CC7 Axis B10 TO B12/A6 | Steel Reinforcement | Columun | 56.40 TO 59.70 | 16th Floor | 42572 | 42572 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5377 | Steel Reinforcement For Core 2 Axis B16 TO B15/A8 TO A10 | Steel Reinforcement | Core | 56.40 TO 59.70 | 16th Floor | 42572 | 42572 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5378 | Steel Reinforcement For Shear Wall 1 Axis B5 TO B10/A1 | Steel Reinforcement | SHW | 64.70 To 68.00 | 19th Floor | 42575 | 42576 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5379 | Form Work For Core 5 Axis B5 TO B8/A7 TO A11 | Form Work | Core | 59.70 TO 63 | 19th Floor | 42575 | 42575 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5380 | Form Work For Stair 12 Axis B1 /A2 | Form Work | Stair | 44.90 TO 48.20 | 13th floor | 42575 | 42582 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5381 | Form Work For Stair 14 Axis B15/B16/A1 | Form Work | Stair | 35.00 TO 38.30 | 10th Floor | 42575 | 42582 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5382 | Form Work For Stair Case 11 Axis A7 TO A8/B16 TO B17 | Form Work | Stair | 49.80 TO 53.10 | 14th floor | 42576 | 42579 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5383 | Top and Bottom Layers Of Steel Reinforcement Work ,Dowels and final Inspection For Pour Strip Stage | Steel Reinforcement | Pour strip | 61.40 | 17th Floor | 42577 | 42577 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5384 | Post Tension Works For Slab (Tendons-Strands-Anchors and Profiles Axis B6 TO B19/A1 TO A3 | Post Tension | Slab | 61.40 | 17th Floor | 42577 | 42579 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5385 | steel Reinforcement For Stair Case 11 Axis A7 TO A8/B16 TO B17 | Steel Reinforcement | Stair | 49.80 TO 53.10 | 14th floor | 42577 | 42579 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5386 | Form Work For Columns And Shear Walls Axis B6 TO B10/A1 | Form Work | SH.W | 64.70 TO 68.00 | 19th Floor | 42577 | 42579 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5387 | Steel Reinforcement Work And Final Inspection For Pour Strip Between 1st and 2nd Pour Strip Axis B5 /A1 TO A3 | Steel Reinforcement |  | +54.80 | 15th Floor | 42577 | 42577 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5388 | Top & bottom layers and beams steel reinforcement for third post tension slab Axis A6 TO A12/B13 TO B19 | Steel Reinforcement | Slab | 53.10 | 15th Floor | 42578 | 42579 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5389 | Tendons-Strands-Anchors and Profiles for third stage of post tension slab Axis A6 TO A12/B13 TO B19 | Anchor | Slab | 53.10 | 15th Floor | 42578 | 42579 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5390 | Steel rinforcemnt For Core 3 Axis A8 TO A10/B10 To A12 | Steel Reinforcement | Core | +59.70 TO 63.00 | 18th Floor | 42578 | 42578 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5391 | Steel Reinforcement For Pour Strip Of Slab Axis B5/A1 TO A3 | Steel Reinforcement | Slab | 58.10 | 16th Floor | 42578 | 42579 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5392 | steel reinforcement for shear wall 1 axis B1 to B5/A1 | Steel Reinforcement | SH.W | 64.70 TO 68.00 | 19th Floor | 42578 | 42579 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5393 | Form Work For Shear Wall 1 Axis B1 TO B5/A1 | Form Work | SH.W | 64.70 TO 68.00 | 19th Floor | 42579 | 42582 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5394 | Steel Reinforcement For Stair 12 Axis A1 TO A2/B1 | Steel Reinforcement | Stair | 44.90 TO 46.20 | 13th floor | 42579 | 42585 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5395 | Check Form Work at 59.70 First Stage | Form Work | First Stage | 59.70 | 15th Floor | 42579 | 42581 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5396 | Form Work For Core 2 Axis A8 TO A12/B14 TO B16 | Form Work | Core | 56.40 TO 59.70 | 16th Floor | 42581 | 42582 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5397 | Form work For Stair Case 3 Axis A8/B6 TO B7 | Form Work | Stair | 56.40 TO 59.70 | 16th Floor | 42581 | 42582 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5398 | Form Work For Stair Case 7 Axis A10/B10 TO B11 | Form Work | Stair | 56.40 TO 59.70 | 16th Floor | 42581 | 42583 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5399 | Steel Reinforcement For Beams Of Fence From Column Axis B6/A11 | Steel Reinforcement | fence | 4.30 | ground Floor | 42582 | 42583 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5400 | steel reinforcement for core 5 axis A8 to A10/B6 to B8 | Steel Reinforcement | Core | 63.00 TO 66.30 | 18th Floor | 42582 | 42583 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5401 | Steel reinforcement For Stair Case 3 Axis A8/B6 TO B7 | Steel Reinforcement | Stair | 56.40 TO 59.70 | 16th Floor | 42582 | 42585 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5402 | Duct Grouting For Cable at first stage post tension slab Axis A6 TO A12/B4 TO B9 | Post Tension | Slab | +49.80 | 13th floor | 42582 | 42583 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5403 | Duct grouting For Cable at third stage post tension Slab Axis A6 TO A12/B4 TO B9 | Post Tension | Slab | +49.80 | 13th floor | 42582 | 42584 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5404 | Form Work For 2 CC7 Axis B16 TO B14/A6 | Form Work | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42585 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5405 | Steel Reinforcement For 2 CC7 Axis B16 TO B14/A6 | Steel Reinforcement | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42584 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5406 | Form Work For DCC7 Axis B13/A6 | Form Work | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42589 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5407 | Steel Reinforcement For DCC7 Axis B13/A6 | Steel Reinforcement | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42585 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5408 | Steel Reinforcement For Cc7 Axis B16/A12 | Steel Reinforcement | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42584 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5409 | Form Work For CC7 Axis B16/A12 | Form Work | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42585 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5410 | Form Work For CC9 Axis B14 TO A11 | Form Work | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42589 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5411 | Steel Reinforcement For CC9 Axis B14/A11 | Steel Reinforcement | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42585 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5412 | Form Work For 2DCC1 Axis B13/A11 &B13/A10 | Form Work | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42589 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5413 | Steel Reinforcement For 2DCC1 Axis B13 /A11 &B13/A10 | Steel Reinforcement | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42585 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5414 | Form Work For DCC1* Axis B13/A8 | Form Work | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42589 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5415 | Steel Reinforcement For DCC1* Axis B13/A8 | Steel Reinforcement | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42585 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5416 | Steel reinforcement For 5 CC4 Axis D1,D2,D3,D4,A9/B19 | Steel Reinforcement | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42584 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5417 | Form work For 5 CC4 Axis D1,D2,D3,D4,A9/B19 | Form Work | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42585 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5418 | Steel Reinforcement For CC4 Axis A11/B16 | Steel Reinforcement | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42585 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5419 | Form Work For CC4 Axis A11/B16 | Form Work | Columun | +53.10 TO 56.40 | 15th Floor | 42582 | 42589 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5420 | Form Work For Stair Case 6 Axis A8/B10 TO B12 | Form Work | Stair | 56.40 TO 59.70 | 16th Floor | 42582 | 42585 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5421 | Form Work For Shear Wall 5/5*Axis B6/A2 TO A3 | Form Work | SH.W | 61.40 TO 64.70 | 18th Floor | 42583 | 42584 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5422 | steel reinforcement for shear wall 5/5* Axis B6/A2 TO A3 | Steel Reinforcement | SH.W | 61.40 TO 64.70 | 18th Floor | 42582 | 42583 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5423 | Form Work For Columns And Shear Walls Axis C10/A2 TO A3 | Form Work | COLUMUNS +SH.W | 61.40 TO 64.70 | 18th Floor | 42583 | 42584 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5424 | Form Work For Shear Wall 2*/3*Axis C8/A2 TO A3 | Form Work | SH.W | 61.40 TO 64.70 | 18th Floor | 42583 | 42584 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5425 | Form Work For Shear Wall 3 Part (1 &2) Axis C6/A2 TO A3 | Form Work | SH.W | 61.40 TO 64.70 | 18th Floor | 42583 | 42584 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5426 | Form Work For Columuns CC5 Axis B13/A3 | Form Work | SH.W | 61.40 TO 64.70 | 18th Floor | 42583 | 42584 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5427 | Steel Reinforcement For Columuns And Shear Walls 3*/2* Axis C8/A2 TO A3 | Steel Reinforcement | SH.W | 61.40 TO 64.70 | 18th Floor | 42582 | 42583 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5428 | Steel Reinforcement For Columuns And Shear Wall 3 Axis C6/A2 TO A3 | Steel Reinforcement | SH.W | 61.40 TO 64.70 | 18th Floor | 42582 | 42583 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5429 | Steel Reinforcement For Columuns Shear Walls Axis C10/A2 TO A3 | Steel Reinforcement | SH.W | 61.40 TO 64.70 | 18th Floor | 42582 | 42583 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5430 | Steel Reinforcement For Columuns And Shear Wall Axis B13/A3 | Steel Reinforcement | SH.W | 61.40 TO 64.70 | 18th Floor | 42582 | 42583 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5431 | Grouting For Cables Of First Stage Post tension Slab Hotel Tower Axis B1 TO C5/A1 TO A3 | Post Tension | Slab | 61.40 | 17th Floor | 42583 | 42588 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5432 | Steel Reinforcement For Core Walls 6 Axis B15 TO B17/A1 | Steel Reinforcement | Core | 61.40 TO 64.70 | 18th Floor | 42583 | 42585 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5433 | Stressing for cables of second stage post tension slab hotel tower Axis C5 TO B19/A1 TO A3 | Stressing | Slab | 61.40 | 17th Floor | 42583 | 42585 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5434 | Steel Reinforcement For Columun and Shear Walls Axis C11/A3 | Steel Reinforcement | Columun | 61.40 TO 64.70 | 18th Floor | 42583 | 42584 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5435 | Steel Reinforcement For ColumunC5 and Shear Walls Axis B18/A1 | Steel Reinforcement | Columun | 61.40 TO 64.70 | 18th Floor | 42583 | 42584 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5436 | Steel Reinforcement For Columun C1 And Shear Walls 1 Axis B19/A1 | Steel Reinforcement | SH.W+C1 | 61.40 TO 64.70 | 18th Floor | 42583 | 42585 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5437 | Steel Reinforcement For Temporary at Opening at Core 2 (TO CLOSE NCR No-094)Axis A9 TO A11/B14 TO B16 | Steel Reinforcement | Core | +1.10 TO 5.40 |  | 42583 | 42589 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5438 | Form Work For Temporary Opening at core 2 -(TO Close NCR No-094) Axis A9 TO A11/B14 TO B16 | Form Work | Core | +1.10 TO 5.40 |  | 42583 | 42610 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5439 | Tendons-Strands-Anchors and Profiles for First stage of post tension slab Axis A6 TO A12/B4 TO B9 | Anchor | Slab | 59.70 | 16th Floor | 42583 | 42585 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5440 | Top & Bottom Layers and beams Steel Reinforcement For First post tension Slab Axis A6 TO A12/B4 TO B9 | Steel Reinforcement | Slab | 59.70 | 16th Floor | 42583 | 42585 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5441 | Form Work For Columns C5 And Shear Walls Axis B18/A1 | Form Work | Columun | 61.40 TO 64.70 | 18th Floor | 42584 | 42584 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5442 | Form Work For ColumunsCC6 and Shear Walls Axis C11/A3 | Form Work | Columun | 61.40 TO 64.70 | 18th Floor | 42584 | 42584 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5443 | Form Work For Core Walls 6 Axis B15 TO B17/A1 | Form Work | Core | 61.40 TO 64.70 | 18th Floor | 42583 | 42588 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5444 | Form Work For Columuns and Shear Walls Axis B19/A1 | Steel Reinforcement | SH.W | 61.40 TO 64.70 | 18th Floor | 42584 | 42588 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5445 | Form Work For Stair Case 4 Axis A11/B7 TO B8 | Form Work | Stair | 1.10 TO 5.40 | ground Floor | 42583 | 42585 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5446 | Stressing Of Strands for Second Stage Post tension Slab Axis A6 TO A12/B9 TO B13 | Stressing | Slab | 56.40 | 15th Floor | 42583 | 42585 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5447 | FORM WORK FOR BEAMS OF FENCE FROM COLUMN NO B6 TO COLUMN A11 | Form Work | fence | 4.30 | ground Floor | 42584 | 42585 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5448 | Duct Grouting For Cable at first stage Post tension slab Axis A6 TO A12/B4 TO B9 | Grout | Post tension | 53.10 | 14th floor | 42584 | 42585 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5449 | Demolition of the Upper Concrete ,cleaning and re-adjustment the steel reinforcement For Core 2 Axis A9 TO A11/B14 TO B16 | Steel Reinforcement | third stage | 56.40 TO 59.70 | 16th Floor | 42584 | 42589 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5450 | Grouting For Cable For Second Stage Of Post tension slab Axis A6 TO A12/B9 TO B13 | Grout | Second Stage | 53.10 | 14th floor | 42584 | 42585 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5451 | Steel Reinforcement For Core 1 Axis A8 TO A10/B17 | Steel Reinforcement | Core | 53.10 TO 56.40 | 15th floor | 42584 | 42585 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5452 | Form Work For Core 1 Axis A8 TO A10/B17 | form Work | Core | 53.10 TO 56.40 | 15th floor | 42584 | 42588 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5453 | Check Form Work At level 64.70 First stage | form Work | slab | 64.70 | 16th Floor | 42584 | 42591 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5454 | Form Work For Core 3 Axis B10 TO B12/A6 TO A10 | form Work | Core | 63.00 TO 66.30 | 18th Floor | 42585 | 42585 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5455 | Check Level Of Form Work At 59.70 Second Stage | form Work | slab | 59.70 | 15th Floor | 42586 | 42588 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5456 | Form Work For Columun and Shear Walls1 Axis B11 TO B19/A1 | form Work | SH.W | 68.00 TO 71.30 |  | 42585 | 42590 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5457 | Steel Reinforcement For Columun and Shear Walls Axis B11 TO B19/A1 | Steel Reinforcement | SH.W | 68.00 TO 71.30 |  | 42585 | 42589 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5458 | Stressing For Part (1) Slab Axis B4 TO B8/A6 TO A12 | Stressing | Slab | 56.40 | 15th Floor | 42585 | 42588 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5459 | Stressing For Part (3) Slab Axis B13 TO D3/A6 TO A12 | Stressing | Slab | 53.10 | 14th floor | 42585 | 42589 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5460 | Form Work For Core Walls 8 Axis B1/A1 TO A3 | Form Work | Core | 67.00 TO 70.30 | 20th Floor | 42588 | 42590 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5461 | Steel reinforcement For Core Walls 8 Axis B1 TO A1/A3 | Steel Reinforcement | Core | 67.00 TO 70.30 | 20th Floor | 42586 | 42588 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5462 | Steel Reinforcement For Beams Of From Columuns B11 To Columun A16 | Steel Reinforcement | Fence | 4.30 | Podium | 42588 | 42589 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5463 | Check Form Work At 64.70 Second Stage | Form Work | second Stage | 64.70 | 17th Floor | 42589 | 42590 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5464 | Form Work For Fence Beams as attached Axis A15 From Columun 11A TO 16A | Form Work | fence | 4.30 | ground Floor | 42589 | 42590 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5465 | Form Work Removal For First Stage Of Post tension slab Axis A6 TO A12 /B4 TO B9 | Form Work | Post tension | 56.40 | 15th Floor | 42590 | 42591 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5466 | Form Work For Stair Case 11 Axis A7 To A8/B16 TO B17 | Form Work | Stair | 53.10 TO 56.40 | 15th Floor | 42590 | 42593 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5467 | Form Work Removal For Second Stage Of Post tension Slab Axis A6 TO A12/B8 TO B13 | Form Work | Slab | 56.40 | 15th Floor | 42590 | 42591 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5468 | Steel Reinforcement For Stair Case 6 Axis 56.40 TO 59.70 | Steel Reinforcement | Stair | 56.40 TO 59.70 | 16th Floor | 42590 | 42591 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5469 | Steel Reinforcement Work For 4 CC7 Axis A8 TO A9,10,11/B4 | Steel Reinforcement | Columun | 59.70 TO 63.00 | 17th Floor | 42590 | 42591 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5470 | Steel reinforcement For 3 CC7 Axis A6/B5,6,8 | Steel Reinforcement | Columun | 59.70 TO 63.00 | 17th Floor | 42590 | 42591 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5471 | Steel Reinforcement For 2 CC9 Axis 59.70 TO 63.00 | Steel Reinforcement | Columun | 59.70 TO 63.00 | 17th Floor | 42590 | 42591 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5472 | Form Work Removal For Third Stage Of Post tension Slab Axis A6 TO A12/B13 TO B19 | Form Work | Slab | 53.10 | 14th floor | 42590 | 42593 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5473 | Form Work For 4CC7 Axis A8,9,10,11/B4 | Form Work | Columun | 59.70 TO 63.00 | 17th Floor | 42590 | 42595 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5474 | Form work For 3 CC7 Axis A6/B5 TO B6 TO B8 | Form Work | Columun | 59.70 TO 63.00 | 17th Floor | 42590 | 42595 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5475 | Form Work For 2CC9 Axis A11/B6 TO B8 | Form Work | Columun | 59.70 TO 63.00 | 17th Floor | 42590 | 42595 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5476 | Stressing OF Strands Post tension Slab Axis A6 TO A12/b4 TO B9 | Stressing | Slab | 59.70 | 16th Floor | 42590 | 42591 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5477 | Form Work For Shear Wall 6 Axis 68.10 TO 71.40 | form work | SH.W | 68.10 TO 71.40 | 19th Floor | 42590 | 42596 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5478 | Steel reinforcemnt For Shear wall 6 Axis C4/A2 TO A3 | Steel Reinforcement | SH.W | 68.10 TO 71.40 | 19th Floor | 42590 | 42591 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5479 | Form work For Core 5 Axis A8 TO A10/B6 TO B8 | Form Work | core | 63.00 TO 66.30 | 18th Floor | 42590 | 42591 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5480 | Tendons-Strands-anchors and profiles for second stage Of Post tension slab Axis A6 TO A12/B9 TO B13 | Post Tension | Slab | 59.70 | 16th Floor | 42591 | 42593 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5481 | Top& Bottom Layers and beams Steel reinforcemnt For Second Post tension Slab Axis A6 TO A12/B9 TO B13 | Steel Reinforcement | Slab | 59.70 | 16th Floor | 42591 | 42593 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5482 | Steel Reinforcement For Stair Case 7 Axis A10 /b10 TO B11 | Steel Reinforcement | Stair | 6.40 TO 59.70 | 16th Floor | 42591 | 42593 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5483 | Steel reinforcement For Pour Strip between second and third stage Axis A6 TO A12/B12 TO B13 | Steel Reinforcement | Pour strip | 53.10 | 14th floor | 42591 | 42591 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5484 | Steel reinforcemnt For Pour Strip between first and second stage Axis A6 TO A12/B6 TO B9 | Steel Reinforcement | Pour strip | 56.40 | 15th Floor | 42591 | 42591 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5485 | Form Work For Shear Wall 7 Axis C3/A2 TO A3 | Form work | SH.W | 68.10 TO 71.40 | 19th Floor | 42591 | 42596 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5486 | Steel reinforcement For Shear Wall 7 Axis C3/A2 TO A3 | Steel Reinforcement | SH.W | 68.10 TO 71.40 | 19th Floor | 42591 | 42593 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5487 | Steel reinforcement For Fence From Columuns No B16 To No A12 Axis A15/B3 TO B8 | Steel Reinforcement | fence | +1.10 | BOH | 42592 | 42593 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5488 | Steel reinforcement For Stair Case 4 Axis A11/B7 TO B8 | Steel Reinforcement | Stair | 1.10 TO 5.40 | BOH | 42592 | 42595 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5489 | Form Work For Stair 12 Axis B1/A2 TO A3 | Form Work | Stair | 48.20 TO 51.50 | 14th floor | 42593 | 42597 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5490 | Steel reinforcement For Shear Wall 1 Axis B1 TO B11/A1 | Steel Reinforcement | SH.W | 68.00 TO 71.30 | 20th Floor | 42593 | 42595 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5491 | Form Work For Shear Wall 1 Axis B1 TO B11/A1 | Form Work | SH.W | 68.00 TO 71.30 | 20th Floor | 42593 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5492 | Duct grouting For Cable at third stage post tension Slab Axis A6 TO A12/B4 TO B9 | Grout | Slab | +53.10 | 14th floor | 42593 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5493 | Check Form Work At 56.40 third Stage | form Work | third stage | 56.40 | 15th Floor | 42595 | 42595 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5494 | Top And Bottom Steel reinforcement For First stage Hotel Slab Axis C5 TO B1/A1 TO A3 | Steel Reinforcement | Slab | 64.70 | 18th Floor | 42595 | 42596 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5495 | Tendons,Strands.anchors and profiles first stge Hotel Tower Slab Axis C5 TO B1/A1 TO A3 | Anchor | Slab | 64.70 | 18th Floor | 42595 | 42596 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5496 | Steel reinforcement For Stair Case 11 Axis A7 TO A8/B16 TO B17 | Steel Reinforcement | Stair | 53.10 TO 56.40 | 15th Floor | 42595 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5497 | Steel reinforcement For Core 2 Axis A8 TO A10/B14 TO B16 | Steel Reinforcement | Core | +59.70 TO 63.00 | 17th Floor | 42595 | 42596 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5498 | Form Work For Beam Of Fence From Columns No B16 TO No A12 | form Work | Fence | +4.30 | BOH | 42595 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5499 | Steel reinforcement For Stair 14 Axis B16/A2 | Steel Reinforcement | Stair | 35.00 TO 38.30 | 10th Floor | 42596 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5500 | Steel Reinforcement For DCC1 And DCC3 Axis A10 TO A11/B9 | Steel Reinforcement | Columun | +59.70 TO 63.00 | 17th Floor | 42596 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5501 | Form work For DCC1 And DCC3 Axis A10 TO A11/B9 | Form Work | Columun | +59.70 TO 63.00 | 17th Floor | 42596 | 42600 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5502 | Form Work For 2 CC9 Axis A11/B10 TO B12 | Form Work | Columun | +59.70 TO 63.00 | 17th Floor | 42596 | 42600 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5503 | Steel reinforceemnt For 2 CC9 Axis A11/B10 TO B12 | Steel Reinforcement | Columun | +59.70 TO 63.00 | 17th Floor | 42596 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5504 | Steel reinforcement For 2 CC7 Axis A6/B10 TO B12 | Steel Reinforcement | Columun | +59.70 TO 63.00 | 17th Floor | 42596 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5505 | Form Work For 2CC7 Axis A6/B10 TO B122 | Form Work | Columun | +59.70 TO 63.00 | 17th Floor | 42596 | 42600 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5506 | Form Work For SH.W 9 Axis A8 TO A10/B9 | Form Work | SH.W | +59.70 TO 63.00 | 17th Floor | 42596 | 42600 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5507 | Steel Reinforcement For SH.W 9 Axis A8 TO A10/B9 | Steel Reinforcement | SH.W | +59.70 TO 63.00 | 17th Floor | 42596 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5508 | Form Work For DCC7 Axis A6/B9 | Form Work | Columun | +59.70 TO 63.00 | 17th Floor | 42596 | 42600 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5509 | Steel reinforcement For DCC7 Axis A6/B9 | Steel Reinforcement | Columun | +59.70 TO 63.00 | 17th Floor | 42596 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5510 | Top and Bottom Steel Reinforcement For Second Stage Hotel Tower Slab Axis B19 TO C5/A1 TO A3 | Steel Reinforcement | Slab | 64.70 | 18th Floor | 42597 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5511 | Tendons ,Strands,Anchors and Profiles second stage hotel slab Axis B19 TO C5/A1 TO A3 | Anchor | Slab | 64.70 | 18th Floor | 42597 | 42598 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5512 | Form work removal for first stage of post tension slab A6 TO A12/B4 TO B9 | Form Work | Slab | 56.40 | 15th Floor | 42597 | 42600 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5513 | Steel reinforcement For Core 3 Axis A8 TO A10/B10 TO B12 | Steel Reinforcement | Core | 66.30 TO 69.60 | 19th Floor | 42598 | 42599 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5514 | Form Work For Core 2 Axis A8 TO A10/B14 TO B16 | Form Work | Core | 59.70 TO 63.00 | 17th Floor | 42598 | 42602 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5515 | Form Work For Stair Case 3 Axis | Form Work | Stair | 59.70 TO 63.00 | 17th Floor | 42598 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5516 | Form Work For Shear Wall 8 Axis C2/ A2 TO A3 | Form Work | SH.W | 64.70 TO 68.00 | 19th Floor | 42598 | 42600 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5517 | Steel reinforcement For Shear wall 8 Axis C2/A2 TO A3 | Steel Reinforcement | SH.W | 64.70 TO 68.00 | 19th Floor | 42598 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5518 | Steel reinforcement For Core 7 Axis C7/A2 TO A3 | Steel Reinforcement | Core | 68.00 TO 71.30 | 20th Floor | 42598 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5519 | Form Work For Core 7 Axis C7/A2 TO A3 | Form Work | Core | 68.00 TO 71.30 | 20th Floor | 42599 | 42600 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5520 | Grouting For Ducts Of First stage post tension slab hotel tower Axis C5 TO B19/A1 TO A3 | Grout | slab | 61.40 | 17th Floor | 42598 | 42600 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5521 | Check Form Work at 63.00 First stage | Form work | slab | 63.00 | 15th Floor | 42598 | 42598 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5522 | Tendons-Strands-Anchors and Profiles for third stage of post tension slab Axis A6 TO A12/B13 TO B19 | Anchor | slab | 56.40 | 15th Floor | 42599 | 42600 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5523 | Top&Bottom Layers and beams Steel reinforcement For third post tension Slab Axis A6TO A12/B13 TO B19 | Steel Reinforcement | slab | 56.40 | 15th Floor | 42599 | 42600 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5524 | Grouting For Cables for second stage of Post tension slab Axis A6 TO A12/B9 TO B13 | Grout | slab | 56.40 | 15th Floor | 42599 | 42600 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5525 | Stressing Of Strands For second stage Post tension Slab Axis A6 TO A12/B9 TO B13 | Stressing | slab | 59.70 | 16th Floor | 42599 | 42605 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5526 | Form Work For Core 8 Axis B1/A1 TO A3 | Form work | Core | 68.00 TO 71.30 | 20th Floor | 42600 | 42605 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5527 | Steel reinforcement For Core 8 Axis B1/A1 TO A3 | Steel Reinforcement | Core | 68.00 TO 71.30 | 20th Floor | 42599 | 42600 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5528 | Stressing For Cables Of First Stage Post Tension Slab hotel tower Axis B1 TO C5/A1 TO A3 | Stressing | Slab | 64.70 | 18th Floor | 42600 | 42605 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5529 | Steel reinforcement For Pouring Strip Hotel Tower Axis C5/A1 TO A3 | Steel Reinforcement | Pour strip | 61.40 | 18th Floor | 42600 | 42605 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5530 | Steel reinforcement For Columun C5 Axis B18/ A1 | Steel Reinforcement | columun | 64.70 TO 68.00 | 19th Floor | 42602 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5531 | Form Work For Columuns Axis B18/A1 | Form Work | columun | 64.70 TO 68.00 | 19th Floor | 42602 | 42606 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5532 | Steel reinfocement For Columuns CC5&CC6 Axis C11&C9/A3 | Steel Reinforcement | columun | 64.70 TO 68.00 | 19th Floor | 42602 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5533 | Form Work For Columuns CC5 &CC6 Axis C11&C9/A3 | Form Work | columun | 64.70 TO 68.00 | 19th Floor | 42602 | 42606 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5534 | Form Work For Shear Wall 3 Axis C6/A2 TO A3 | Form Work | SH.W | 64.70 TO 68.00 | 19th Floor | 42602 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5535 | Steel reinforcement For Shear Wall 3 Axis C6/A2 TO A3 | Steel Reinforcement | SH.W | 64.70 TO 68.00 | 19th Floor | 42602 | 42603 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5536 | Form Work For Shear wall 3* Axis C8/A2 TO A3 | Form Work | SH.W | 64.70 TO 68.00 | 19th Floor | 42602 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5537 | Steel Reinforcemnent For Shear Wall 3* Axis C8/A2 TO A3 | Steel Reinforcement | SH.W | 64.70 TO 68.00 | 19th Floor | 42602 | 42605 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5538 | Form Work For Shear Wall 5* Axis C5/A2 TO A3 | Form Work | SH.W | 64.70 TO 68.00 | 19th Floor | 42602 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5539 | Steel reinforcement For Shear Wall5* Axis C5/A2 TO A3 | Steel Reinforcement | SH.W | 64.70 TO 68.00 | 19th Floor | 42602 | 42605 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5540 | Form Work For Shear wall 2 Axis C10/A2 TO A3 | Form Work | SH.W | 64.70 TO 68.00 | 19th Floor | 42602 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5541 | Steel reinforcement For Shear Wall 2 Axis C10/A2 TO A3 | Steel Reinforcement | SH.W | 64.70 TO 68.00 | 19th Floor | 42602 | 42605 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5542 | Form Work For Shear Wall1+C1 Axis B19/A1 | Form Work | SH.W+C1 | 64.70 TO 68.00 | 19th Floor | 42602 | 42606 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5543 | Steel Reinforcement For Shear Wall1+C1 Axis B19/A1 | Steel Reinforcement | SH.W+C1 | 64.70 TO 68.00 | 19th Floor | 42602 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5544 | Steel Reinforcement For Core 6 Axis B15 TO b16/A1 TO A2 | Steel Reinforcement | Core | 64.70 TO 68.00 | 19th Floor | 42602 | 42606 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5545 | Form Work For Core 6 Axis B15 TO B16/A1 TO A2 | Form Work | Core | 64.70 TO 68.00 | 19th Floor | 42602 | 42607 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5546 | Form Work For Shear Wall 6 Axis C4/A2 TO A3 | Form Work | SH.W | 71.30 TO 74.60 | 21th Floor | 42602 | 42607 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5547 | Steel reinforcement For Shear Wall Axis C4/A2 TO A3 | Steel Reinforcement | SH.W | 71.30 TO 74.60 | 21th Floor | 42602 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5548 | Steel reinforcement For Shear Wall 7 Axis C3/A2 TO A3 | Steel Reinforcement | SH.W | 71.30 TO 74.60 | 21th Floor | 42602 | 42603 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5549 | Form Work For Shear Wall 7 Axis C3/A2 TO A3 | Form Work | SH.W | 71.30 TO 74.60 | 21th Floor | 42602 | 42607 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5550 | Steel reinforcement For Stair 3 Axis A8/B7 | Steel Reinforcement | Stair | 59.70 TO 63.00 | 17th Floor | 42602 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5551 | Check form work at 63.00 second stage | form Work | Slab | 63.0 | 16th Floor | 42603 | 42605 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5552 | Check Form Work At 68 First stage Axis First stag | form Work | slab | 68.00 | 18th Floor | 42603 | 42605 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5553 | Steel reinforcement For Core 5 Axis ¦A8/B6 | Steel Reinforcement | Core | 66.30 TO 69.60 | 19th Floor | 42603 | 42605 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5554 | Form Work For Shear Wall 1 Axis B19 TO B10/A1 | Form Work | SH.W | 71.30 TO 74.60 | 19th Floor | 42603 | 42606 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5555 | Steel reinforcement For Shear Wall 1 Axis B19 TO B10/A1 | Steel Reinforcement | SH.W | 71.30 TO 74.60 | 20th Floor | 42603 | 42605 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5556 | Form Work For Stair 6 Axis A8/B7 | Form Work | Stair | 59.70 TO 63.00 | 17th Floor | 42603 | 42606 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5557 | Form Work For 3 Columns CC7 Axis B16/A12 & A6/B14 & B16/A6 | Form Work | Columun | 56.40 TO 59.70 | 16th Floor | 42604 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5558 | Steel reinforcement For 3 Columuns CC7 Axis B16/A12 & A6/B14 & B16/A6 | Steel Reinforcement | Columun | 56.40 TO 59.70 | 16th Floor | 42604 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5559 | Form Work For 6 CC4 Axis D1,D2,D3,D4+(B18 TO B19/A9)&(A16/B10 TO B11) | Form Work | Columun | 56.40 TO 59.70 | 16th Floor | 42604 | 42606 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5560 | Steel Reinforcement For 6 CC4 Axis D1,D2,D3,D4+(B18 TO B19/A9)&(A16/B10 TO B11) | Steel Reinforcement | Columun | 56.40 TO 59.70 | 16th Floor | 42604 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5561 | Top and Bottom Steel Reinforcement For First Stage Slab RD Tower Axis B4 TO B9/A6 TO A12 | Steel Reinforcement | Slab | 63.00 | 17th Floor | 42604 | 42605 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5562 | Tendons,Strands,anchors and Profiles First Stage RD Tower Slab Axis B4 TO B9/A6 TO A12 | Anchor | Slab | 63.00 | 17th Floor | 42604 | 42605 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5563 | Form work for 2 Columns D cc7 + Dcc1* Axis B13 TO A6 TO A8 | Form Work | Column | 56.40 TO 59.70 | 16th Floor | 42604 | 42607 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5564 | Stressing for cables of third stage RD tower slab Axis B13 TO B19 TO A6 TO A12 | Stressing | Stressing | 56.40 | 15th Floor | 42604 | 42607 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5565 | Steel reinforcement for 2 columns DCC7 +DCC1* Axis B13 / A6 TO A8 | Steel Reinforcement | Column | 56.40 TO 59.70 | 16th Floor | 42604 | 42606 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5566 | Form work For 2 Columns DCC1 Axis B13/A10 TO A11 | Form work | Column | 56.40 TO 59.70 | 16th Floor | 42604 | 42607 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5567 | Steel reinforcement For 2 Columns DCC1 Axis B13/A10 TO A11 | Steel Reinforcement | Column | 56.40 TO 59.70 | 16th Floor | 42604 | 42606 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5568 | Steel reinforcement For Columns CC9 Axis B14 / A11 | Steel Reinforcement | Column | 56.40 TO 59.70 | 16th Floor | 42604 | 42605 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5569 | Form work For Columns CC9 Axis B14/A11 | Form Work | Column | 56.40 TO 59.70 | 16th Floor | 42604 | 42607 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5570 | Stressing For Cables of Second Stage Post tension Slab Hotel Tower Axis B19 TO C5/A1 TO A3 | Stressing | Slab | 64.70 | 18th Floor | 42604 | 42609 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5571 | Form Work For Stair 7 Axis B10/A10 | Form Work | Stair | 59.70 TO 63.00 | 16th Floor | 42604 | 42606 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5572 | Form Work for core 1 Axis A8 TO A10 / B17 | Form Work | Core | 56.40 TO 59.70 | 16th Floor | 42605 | 42607 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5573 | Steel reinforcement For Core1 Axis A8 TO A10 / B17 | Steel Reinforcement | Core | 56.40 TO 59.70 | 16th Floor | 42605 | 42606 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5574 | Form Work For Shear Wall 1 Axis B10 TO B1/A1 | Form work | SH.W | 71.30 TO 74.60 | 21th Floor | 42606 | 42611 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5575 | Steel Reinforcement For Shear wall 1 Axis B10 TO B1/A1 | Steel Reinforcement | SH.W | 71.30 TO 74.60 | 21th Floor | 42606 | 42607 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5576 | Steel Reinforcement For Stair Case 6 Axis A8/B11 TO B13 | Steel Reinforcement | Stair | 59.70 TO 63.00 | 17th Floor | 42606 | 42610 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5577 | Steel Reinforcement Work For 4 CC7 Axis A8 TO A9&A10,11/B4 | Steel Reinforcement | Columun | 63.00 TO 66.30 | 18th Floor | 42606 | 42609 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5578 | Form Work For 4 CC7 Axis A8 TO A9 &A10 TO A11/B4 | Form Work | Columun | 63.00 TO 66.30 | 18th Floor | 42606 | 42611 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5579 | Steel Reinforcement For 3 CC7 Axis A6/B5 TO B6&B8 | Steel Reinforcement | Columun | 63.00 TO 66.30 | 18th Floor | 42606 | 42609 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5580 | Form work For 3 CC7 Axis A6/B5 TO B6 TO B8 | Form Work | Columun | 63.00 TO 66.30 | 18th Floor | 42606 | 42611 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5581 | Steel Reinforcement For 2 CC9 Axis A11/B6 TO B8 | Steel Reinforcement | Columun | 63.00 TO 66.30 | 18th Floor | 42606 | 42609 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5582 | Form work For 2 CC9 Axis A11/B6 TO B8 | Form Work | Columun | 63.00 TO 66.30 | 18th Floor | 42606 | 42611 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5583 | Form Work Removal For Third Stage Of Post Tension Slab Axis A6 TO A12/B13 TO B19 | Form Work | Slab | 56.40 | 15th Floor | 42606 | 42610 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5584 | Form Work Removal For Second Stage Of Post tension Slab Axis A6 TO A12 /B8 TO B13 | Form Work | Slab | 59.70 | 17th Floor | 42607 | 42610 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5585 | Form Work Removal For First stage Of Post tension Slab Axis A6 To A12/B4 TO B9 | Form Work | Slab | 59.70 | 17th Floor | 42607 | 42610 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5586 | Form work For Core 5 Axis A8 TO A10/B6 TO B8 | Form Work | Core | 66.30 TO 69.60 | 19th Floor | 42606 | 42609 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5587 | Steel reinforcement For Pour Strip Between First And Second Stage Axis A6 TO A12/B68 TO B9 | Steel Reinforcement | Pour strip | 59.70 | 16th Floor | 42606 | 42607 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5588 | Check Form Work at 68 Second Stage | Form work | Second stage | 68.00 | 19th Floor | 42607 | 42610 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5589 | Top And Bottom Steel Reinforcement For First Stage Hotel Tower Slab Axis B1 TO C5/A1 TO A3 | Steel Reinforcement | Slab | 68.00 | 19th Floor | 42607 | 42607 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5590 | Tendons,Strands,ancjors and Profiles for first stage Hotel Tower Slab Axis B1 TO C5/A1 TO A3 | Anchor | Slab | 68.00 | 19th Floor | 42607 | 42609 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5591 | Steel Reinforcement For Stair Case7 Axis A10/B10 TO B11 | Steel Reinforcement | Stair | 59.70 TO 63.00 | 17th Floor | 42609 | 42610 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5592 | Check Form Work At 59.70 third stage | Form Work | third stage | 59.70 | 16th Floor | 42610 | 42616 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5593 | Stressing Of Strands for first stage Post tension Slab Axis A6 TO A12/B4 TO B9 | Stressing | Slab | 63.00 | 17th Floor | 42609 | 42612 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5594 | Steel reinforcement For Pour Strip 2 & 3 Axis A6 TO A12/B12 TO B13 | Steel Reinforcement | Pour strip | 56.40 | 15th Floor | 42610 | 42612 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5595 | Grouting For Part 3 Axis A6 TO A12 / B13 TO B19 | Grout | Part 3 | 56.40 | 15th Floor | 42610 | 42612 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5596 | Grouting For Part 1 Axis A6 TO A12/B4 TO B8 | Grout | Part 1 | 59.70 | 16th Floor | 42610 | 42620 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5597 | Grouting For Ducts of second stage post tension slab hotel tower Axis C5 TO B19/A1 TO A3 | Grout | Slab | 64.70 | 18th Floor | 42610 | 42635 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5598 | Grouting For Ducts Of First stage Post Tension Slab Hotel Tower Axis B1 TO C5/A1 T A3 | Grout | Slab | 64.70 | 18th Floor | 42610 | 42614 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5599 | Form Work Removal For First stage Hotel Tower Slab Axis B1 TO C5/A1 To A3 | Form Work | Slab | 64.70 | 18th Floor | 42610 | 42612 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5600 | Form Work Removal For Second Stage Hotel Tower Slab Axis B19 TO C5/A1 TO A3 | Form Work | Slab | 64.70 | 18th Floor | 42610 | 42612 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5601 | Tendons,Strands anchors and Profiles for second stage RD tower Slab Axis B9 TO B12/A6 TO A12 | Anchor | Slab | 63.00 | 17th Floor | 42610 | 42610 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5602 | Top And Bottom Steel reinforcement for Second stage RD Tower Slab Axis B9 TO B12/A6 TO A12 | Steel Reinforcement | Slab | 63.00 | 17th Floor | 42610 | 42610 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5603 | Duct Grouting For Cable at first stage Post tension slab Axis A6 TO A12/B4 TO B9 | Grout | Slab | 56.40 | 15th Floor | 42610 | 42612 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5604 | Steel reinforcment For Shear Wall 8 Axis C2/A2 TO A3 | Steel Reinforcement | SH.W | 68.00 TO 71.30 | 19th Floor | 42611 | 42611 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5605 | Form Work For Shear wall 8 Axis C2/A2 TO A3 | Form Work | SH.W | 68.00 TO 71.30 | 19th Floor | 42611 | 42614 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5606 | Form Work For Core 8 Axis B1/A2 TO A3 | Form Work | Core | 74.60 TO 77.90 | 21th Floor | 42611 | 42614 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5607 | Steel Reinforcemnt For Core 8 Axis B1/A2 TO A3 | Steel Reinforcement | Core | 74.60 TO 77.90 | 21th Floor | 42611 | 42618 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5608 | Steel Reinforcemnt For Core 2 Axis B15/A8 | Steel Reinforcement | Core | 63.00 TO 66.30 | 17th Floor | 42611 | 42614 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5609 | Form work for Core 3 Axis A8 TO A11/B10 TO B12 | Form work | Core | 66.30 TO 69.60 | 19th Floor | 42612 | 42613 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5610 | Steel reinforcement For DCC7 Axis A6/B9 | Steel Reinforcement | Columun | 63.00 TO 66.30 | 18th Floor | 42612 | 42614 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5611 | Form work For DCC7 Axis A6/B9 | Form work | Columun | 63.00 TO 66.30 | 18th Floor | 42612 | 42616 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5612 | Form work For Stair Case 11 Axis A7 TO A8/B16 TO B17 | Form work | Stair | 56.40 TO 59.70 | 16th Floor | 42612 | 42616 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5613 | Steel Reinforcement For 2CC7 Axis A6/B10 TO B12 | Steel Reinforcement | Columun | 63.00 TO 66.30 | 18th Floor | 42612 | 42614 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5614 | Form work for 2CC7 Axis A6/B10 TO B12 | Form work | Columun | 63.00 TO 66.30 | 18th Floor | 42612 | 42616 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5615 | Steel reinforcemnt for SH.W9 Axis A8 TO A10/B9 | Steel Reinforcement | SH.W | 63.00 TO 66.30 | 18th Floor | 42612 | 42614 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5616 | Form Work For SH.W 9 Axis A8 TO A10/B9 | Form Work | SH.W | 63.00 TO 66.30 | 18th Floor | 42612 | 42616 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5617 | Steel Reinforcement For DCC1 And DCC3 Axis A10 TO A11/B9 | Steel Reinforcement | Columun | 63.00 TO 66.30 | 18th Floor | 42612 | 42614 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5618 | Form work For DCC1 And DCC3 Axis A10 TO A11/B9 | Form work | Columun | 63.00 TO 66.30 | 18th Floor | 42612 | 42616 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5619 | Form work For 2CC9 Axis A11/B10 TO B12 | Form work | Columun | 63.00 TO 66.30 | 18th Floor | 42612 | 42616 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5620 | Steel reinforcemnt For 2 CC9 Axis A11/B10 TO B12 | Steel Reinforcement | Columun | 63.00 TO 66.30 | 18th Floor | 42612 | 42614 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5621 | Stressing For Cables Of First Stage Post tension Slab Hotel Tower Axis B1 TO C5/A1 TO A3 | Stressing | Slab | 68.00 | 19th Floor | 42612 | 42614 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5622 | Form Work For Stair 14 Axis A8/B7 | form work | Stair | 38.30 TO 41.60 |  | 42612 | 42616 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5623 | Tendons,Strands,anchors and profiles second stage hotel tower slab Axis B19 TO C5/A1 TO A3 | Anchor | Slab | 68.00 | 19th Floor | 42613 | 42614 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5624 | Top and Bottom Steel reinforcement For Second Stage Hotel Tower Slab Axis A1 TO A3/B19 TO C5 | Steel Reinforcement | Slab | 68.00 | 19th Floor | 42613 | 42614 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5625 | Steel reinforcemnt For Stair Case 11 Axis A7 TO A8/B16 TO B17 | Steel Reinforcement | Stair | 56.40 TO 59.70 | 16th Floor | 42613 | 42618 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5626 | Form work For Stair Case 3 Axis A8/B6 TO B7 | Form Work | Stair | 63.00 TO 66.30 | 18th Floor | 42613 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5627 | Check Form Work At 66.30 First Stage | Form Work | Slab | 66.30 | 17th Floor | 42614 | 42616 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5628 | Form Work For Stair 12 Axis B1/A2 | Form Work | Stair | 48.20 TO 51.50 | 13th floor | 42614 | 42632 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5629 | Steel reinforcemnt For Stair 14 Axis B6/A2 | Steel Reinforcement | Stair | 38.30 TO 41.60 | 11th Floor | 42614 | 42614 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5630 | Check Form work at 71.30 First stage | Form work | Slab | 70.30 | 19th Floor | 42617 | 42618 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5631 | Form Work For Shear Wall 7 Axis C3/A2 TO A3 | Form work | SH.W | 74.60 TO 77.90 | 22th Floor | 42617 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5632 | Steel Reinforcement For Shear Wall 7 Axis C3/ A2 TO A3 | Steel Reinforcement | SH.W | 74.60 TO 77.90 | 22th Floor | 42617 | 42618 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5633 | Steel Reinforcement For Shear Wall 6 Axis C4/ A2 TO A3 | Steel Reinforcement | SH.W | 74.60 TO 77.90 | 22th Floor | 42617 | 42618 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5634 | Form Work For Shear Wall 6 Axis C4/ A2 TO A3 | Form work | SH.W | 74.60 TO 77.90 | 22th Floor | 42617 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5635 | Stressing for Cables second stage | Stressing | Slab | 63.00 | 17th Floor | 42617 | 42619 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5636 | Steel Reinforcement for Stair 3 Axis B6 TO B7 / A8 | Steel Reinforcement | Stair | 63.00 TO 66.30 | 18th Floor | 42617 | 42619 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5637 | Form Work For Shear Wall 2 Axis C10/A2 TO A3 | Form work | SH.W | 68.00 TO 71.30 | 20th Floor | 42618 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5638 | Top and Bottom reinforcement Axis B13 TO B19 /A6 TO A12 | Steel Reinforcement | Slab | 59.70 | 16th Floor | 42617 | 42618 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5639 | Tendons.Strands.Anchors.and profiles for Cabels Axis B13 TO B19 / A6 TO A12 | Anchor | Slab | 59.70 | 16th Floor | 42617 | 42619 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5640 | Steel reinforcement For Shear Wall 2 Axis C10/A2 TO A3 | Steel Reinforcement | SH.W | 68.00 TO 71.30 | 20th Floor | 42618 | 42619 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5641 | Form Work For Shear Wall3* Axis C8/A2 TO A3 | Form Work | SH.W | 68.00 TO 71.30 | 20th Floor | 42618 | 42619 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5642 | Steel Reinforcemnt For Shear Wall 3* Axis C8/A2 TO A3 | Steel Reinforcement | SH.W | 68.00 TO 71.30 | 20th Floor | 42618 | 42620 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5643 | Form Work For Shear Wall 3 | Form Work | SH.W | 68.00 TO 71.30 | 20th Floor | 42618 | 42619 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5644 | Steel Reinforcement For Shear wall3Axis C6/A2 TO A3 | Steel Reinforcement | SH.W | 68.00 TO 71.30 | 20th Floor | 42618 | 42618 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5645 | Form Work For Shear wall 5* Axos C5/A2 TO A3 | Form Work | SH.W | 68.00 TO 71.30 | 20th Floor | 42618 | 42619 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5646 | Steel Reinforcement For Shear wall 5* Axis C5/A2 TO A3 | Steel Reinforcement | SH.W | 68.00 TO 71.30 | 20th Floor | 42618 | 42618 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5647 | Steel reinforcement for CC5 & CC6 AxisC5 TO C11/ A3 | Steel Reinforcement | Columun | 68.00 TO 71.30 | 20th Floor | 42619 | 42619 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5648 | Form Work for CC5 & CC6 Axis C5 TO C11/ A3 | Form Work | Columun | 68.00 TO 71.30 | 20th Floor | 42619 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5649 | Steel reinforcment for 1 Columuns DCC7 Axis B13/A6 | Steel Reinforcement | Columun | 59.70 TO 63.00 | 16-17Floor | 42619 | 42620 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5650 | Form work For 1Columuns DCC7 Axis B13/A6 | Form work | Columun | 59.70 TO 63.00 | 16-17Floor | 42619 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5651 | Steel reinforcement For 2Columuns DCC1+DCC1* third stage Axis B13/A8 TO A12 | Steel Reinforcement | Columun | 59.70 TO 63.00 | 16-17Floor | 42619 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5652 | Form work For 2 Columuns DCC1+ DCC1* third stage Axis B13/A8 TO A12 | Form work | Columun | 59.70 TO 63.00 | 16-17Floor | 42619 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5653 | Steel reinforcement For Columuns CC9 Axis B14/A11 | Steel Reinforcement | Columun | 59.70 TO 63.00 | 16-17Floor | 42619 | 42620 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5654 | Form Work For Columun CC9 Axis B14/A11 | Form work | Columun | 59.70 TO 63.00 | 16-17Floor | 42619 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5655 | Steel reinforcement For 3 Columuns CC7 Axis B14 TO B17/A6 TO A12 | Steel Reinforcement | Columun | 59.70 TO 63.00 | 16-17Floor | 42619 | 42620 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5656 | Form Work For 3 Columuns CC7 Axis B14 TO B17/A6 TO A12 | Form work | Columun | 59.70 TO 63.00 | 16-17Floor | 42619 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5657 | Steel reinforcement For Columuns CC4 Axis B16 TO B19/A6 TO A12 | Steel Reinforcement | Columun | 59.70 TO 63.00 | 16-17Floor | 42619 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5658 | Form work For 6 Columuns CC4 Axis B16 TO B19/A6 TO A12 | Form work | Columun | 59.70 TO 63.00 | 16-17Floor | 42619 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5659 | steel reinforcement for first stage slab at R.D tower axis B4 to B9/A6 to A12 | Steel Reinforcement | Slab | 66.30 | 18th Floor | 42619 | 42620 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5660 | Tendons,Strands,Anchors and Profiles for Cabls Axis B4 TO B9/A6 TO A12 | Anchor | Slab | 66.30 | 18th Floor | 42619 | 42620 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5661 | Form work For Core 2 Axis B14 TO B16/A8 TO A10 | Form work | Core | 63.00 TO 66.30 | 17-18th Floor | 42619 | 42620 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5662 | Grouting For Second Stage Slab Axis B9 TO B13/A6 TO A12 | Grout | Slab | 59.70 | 16th Floor | 42619 | 42635 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5663 | Tendons,Strands,Anchors and Profiles First Stage Hotel Tower Slab Axis B1 TO C5/A1 TO A3 | Anchor | Slab | 71.30 | 20th Floor | 42620 | 42620 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5664 | Top and Bottom Steel Reinforcement For First Stage Hotel Tower Slab Axis B1 TO C5 /A1 TO A3 | Steel Reinforcement | Slab | 71.30 | 20th Floor | 42620 | 42620 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5665 | Stressing For Cable Of Second Stage Post tension slab hotel tower Axis B19 TO C5/A1 TO A3 | Stressing | Slab | 68.00 | 19th Floor | 42620 | 42620 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5666 | Steel Reinforcemnt For Shear Wall1+C1 Axis B19/A1 | Steel Reinforcement | SH.W+C1 | 68.00 TO 71.30 | 20th Floor | 42621 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5667 | Check Form Work At 66.30 Second Stage | form work | Slab | 66.30 | 17th Floor | 42620 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5668 | Form work For Shear Wall 1+C1 Axis B19/ A1 | form work | SH.W+C1 | 68.00 TO 71.30 | 20th Floor | 42621 | 42632 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5669 | Steel reinforcemet For C5 Axis B18/A1 | Steel Reinforcement | Columun | 68.00 TO 71.30 | 20th Floor | 42621 | 42632 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5670 | Form Work For Columun C5 Axis B18/A1 | form work | Columun | 68.00 TO 71.30 | 20th Floor | 42621 | 42632 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5671 | Steel reinforcement For Core 6 Axis B16/A2 | Steel Reinforcement | Core | 68.00 TO 71.30 | 20th Floor | 42621 | 42630 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5672 | Form work For Core 6 Axis B16/A2 | form work | Core | 68.00 TO 71.30 | 20th Floor | 42621 | 42632 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5673 | Steel reinforcement For Core 5 Axis B6 TO B8/A7 TO A10 | Steel Reinforcement | Core | 69.60 TO 72.90 | 20th Floor | 42621 | 42621 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5674 | Stressing For Cables of third Post tension slab RD Tower Axis B13 TO B19/A6 TO A12 | Stressing | Slab | 59.70 | 15th Floor | 42630 | 42635 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5675 | Stressing For Cable Of First Post tension Slab RD Tower Axis B4 TO B9/A6 TO A12 | Stressing | Slab | 66.30 | 17th Floor | 42630 | 42634 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5676 | Stressing For Cables Of First Stage Post tension Slab Hotel Tower Axis B1 TO C5/A1 TO A3 | Stressing | Slab | 71.30 | 20th Floor | 42630 | 42634 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5677 | steel reinforcement for shear wall 8 axis C2/A1 to A3 | Steel Reinforcement | SH.W | 71.30 TO 74.60 | 21th Floor | 42631 | 42632 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5678 | Form Work For Shear Wall 8 Axis C2/A1 TO A3 | Form work | SH.W | 71.30 TO 74.60 | 21th Floor | 42632 | 42632 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5679 | Form Work For Core 1 Axis B17/A9 | Form work | Core | 59.70 TO 63.00 | 16th Floor | 42632 | 42633 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5680 | Form work For Stair 6,7 Axis B10 TO B11/A8 TO A10 | Form work | Stair | 63.00 TO 66.30 | 17th Floor | 42631 | 42632 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5681 | Form work For 3 Columns CC7 Axis B5 TO B6&B8/A6 | Form work | Columun | 66.30 TO 69.60 | 17th Floor | 42632 | 42635 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5682 | Steel reinforcement For 3 Columuns CC7 Axis B5 TO B6&B8/A6 | Steel Reinforcement | Columun | 66.30 TO 69.60 | 17th Floor | 42631 | 42632 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5683 | Steel reinforcement For Core 1 Axis B17/A9 | Steel Reinforcement | Core | 59.70 TO 63.00 | 16th Floor | 42631 | 42632 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5684 | Form work For Axis C7/ A2 TO A3 | form work | Core | 71.30 TO 74.60 | 20th Floor | 42632 | 42633 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5685 | Steel reinforcement For Core 7 Axis C7/ A2 TO A3 | Steel Reinforcement | Core | 71.30 TO 74.60 | 20th Floor | 42632 | 42632 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5686 | Steel reinforcement For 4 Columns CC7 Axis B4 / A7 TO A8, A9,A10,A11 | Steel Reinforcement | Columns | 66.30 TO 69.60 | 17th Floor | 42632 | 42633 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5687 | Form Work for 4 Columns CC7 Axis B4 / A7 TO A8, A9,A10,A11 | Form Work | Columns | 66.30 TO 69.60 | 17th Floor | 42632 | 42635 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5688 | Steel reinforcement For 2 Columns CC9 Axis B6 TO B8/A11 | Steel Reinforcement | Columns | 66.30 TO 69.60 | 17th Floor | 42632 | 42633 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5689 | Form Work for 2 Columns CC9 Axis B6 TO B8/A11 | Form Work | Columns | 66.30 TO 69.60 | 17th Floor | 42632 | 42635 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5690 | Steel reinforcement for Stair 6 , 7 Axis B10 TO B11 / A8 TO A10 | Steel Reinforcement | Stair | 66.30 TO 69.60 | 17th Floor | 42632 | 42635 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5691 | Steel reinforcement for pour strip 1/2 Axis B8 TO B B9 /A6 TO A12 | Steel Reinforcement | Pour strip | 63.00 | 15th Floor | 42632 | 42635 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5692 | Form Work For Shear Wall 1 Axis B19 TO B10/A1 | Form Work | SH.W | 74.60 TO 77.90 | 22th Floor | 42633 | 42635 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5693 | Steel Reinforcement For Shear Wall 1 Axis B19 TO B10/A1 | Steel Reinforcement | SH.W | 74.60 TO 77.90 | 22th Floor | 42633 | 42634 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5694 | Form Work for Core 5 Axis B6 TO B8/A8 To A10 | Form Work | core | 69.60 TO 72.90 | 19th Floor | 42634 | 42634 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5695 | steel reinforcement for core 3 axis B10 to B12/A8 to A10 | Steel Reinforcement | core | 69.60 TO 72.90 | 19th Floor | 42634 | 42635 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5696 | Tendons.Strands.Anchors.and profiles for Cabels Axis B9 TO B13 / A6 TO A12 | Anchor | Slab | 66.30 | 18th Floor | 42634 | 42634 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5697 | Top and bottom Steel reinforcement For Second Stage RD Tower Slab Axis B9 TO B13/A6 TO A12 | Steel Reinforcement | Slab | 66.30 | 18th Floor | 42634 | 42635 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5698 | Check Form Work At 63.00 third Stage | Form Work | Slab | 63.00 | 16th Floor | 42635 | 42642 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5699 | Check Form Work At 71.30 Second Stage | Form Work | Slab | 71.30 | 19th Floor | 42634 | 42639 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5700 | Steel Reinforcemenet For Pour Strip 1/2 At Hotel Tower Axis C5/A1 TO A3 | Steel Reinforcement | Pour strip | 64.70 | 18th Floor | 42635 | 42635 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5701 | Steel Reinforcement For Stair 12 Axis B1/A2 | Steel Reinforcement | Stair | 48.20 TO 51.50 | 14th floor | 42635 | 42635 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5702 | Form Work For Stair 11 Axis B16 TO B17/A9 | Form Work | Stair | 59.70 TO 63.00 | 17th Floor | 42638 | 42639 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5703 | Form Work For Columun CC7 At Second Stage Axis B10 TO B12/A6 | Form Work | Columun | 66.30 TO 69.60 | 19th Floor | 42639 | 42642 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5704 | Steel reinforcement For 2 Columuns CC7 at second stage Axis B10 TO B12/A6 | Steel Reinforcement | Columun | 66.30 TO 69.60 | 19th Floor | 42639 | 42641 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5705 | Form work For 2 Columun CC9 At Second stage Axis B10 TO B12/A11 | Form work | Columun | 66.30 TO 69.60 | 19th Floor | 42639 | 42642 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5706 | Steel Reinforcement For 2 Columuns CC At second stage Axis B10 TO B12/A11 | Steel Reinforcement | Columun | 66.30 TO 69.60 | 19th Floor | 42639 | 42641 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5707 | Form work For 1 Columun DCC7 At Second stage Axis B9/A6 | Form work | Columun | 66.30 TO 69.60 | 19th Floor | 42639 | 42642 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5708 | Steel reinforcement For 1 Columun DCC7 At Second stage Axis B9/A6 | Steel Reinforcement | Columun | 66.30 TO 69.60 | 19th Floor | 42639 | 42641 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5709 | Form Work Shaer Wall 9 Axis B9/A8 TO A9 | Form work | SH.W | 66.30 TO 69.60 | 19th Floor | 42639 | 42642 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5710 | Steel reinforcement For Shaear Wall Axis B9/A8 TO A9 | Steel Reinforcement | SH.W | 66.30 TO 69.60 | 19th Floor | 42639 | 42641 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5711 | Form Work 1 Columun DCC3 at Second Stage Axis B9/A11 | Form work | Columun | 66.30 TO 69.60 | 19th Floor | 42639 | 42642 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5712 | Steel reinforcement For 1 Columun DCC3 At Second stage Axis B9/A11 | Steel Reinforcement | Columun | 66.30 TO 69.60 | 19th Floor | 42639 | 42641 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5713 | Form work For 1 Columun DCC1 At Second stage Axis B9/A10 | Form work | Columun | 66.30 TO 69.60 | 19th Floor | 42639 | 42642 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5714 | Steel reinforcement For 1 Columun DCC1 At second stage Axis B9/A10 | Steel Reinforcement | Columun | 66.30 TO 69.60 | 19th Floor | 42639 | 42641 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5715 | Stressing For Cables Second Stage Axis B9 TO B13/A6 TO A12 | Stressing | Slab | 66.30 | 18th Floor | 42639 | 42642 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5716 | Steel reinforcement for commen pour strip 2/3 Axis B12 TO B13 / A6 TO A12 | Steel Reinforcement | Pour strip | 59.70 | 16th Floor | 42640 | 42642 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5717 | Form Work For Stair 14 Axis B16/A1 | Form Work | Stair | 41.60 TO 449.0 | 12th Floor | 42640 | 42641 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5718 | Tendons,Strands,Anchors and Profiles For Second Stage Hotel Tower Slab Axis B19 TO C5/A1 TO A3 | Anchor | Slab | 71.30 | 20th Floor | 42641 | 42642 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5719 | Top and Bottom steel Reinforcement For Second stage Hotel Tower Slab Axis B19 TO C5/A1 TOB A3 | Steel Reinforcement | Slab | 71.30 | 20th Floor | 42641 | 42642 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5720 | Form Work For Core3 Axis B10 TO B12/A8 TO A10 | Form work | Core | 69.60 TO 72.90 | 20th Floor | 42641 | 42642 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5721 | Steel Reinforcement For Core 2 | Steel Reinforcement | Core | 66.30 TO 69.60 | 19th Floor | 42641 | 42642 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5722 | Check Form Work At 63.00 at Core 2 | form Work | Core | 63.00 | 16th Floor | 42641 | 42642 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5723 | Check Form Work At 69.60 First stage | form Work | Slab | 69.60 | 18th Floor | 42642 | 42644 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5724 | Steel Reinforcement for stair 11 Axis B17/A9 | Steel Reinforcement | Stair | 59.70 TO 63.00 | 17th Floor | 42642 | 42647 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5725 | Form Work For Shear Wall 1 Axis B1 TO B10/A1 | Form Work | SH.W | 74.60 TO 77.90 | 22th Floor | 42644 | 42646 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5726 | Steel reinforcement For Shear Wall 1 Axis B1 TO B10/A1 | Steel Reinforcement | SH.W | 74.60 TO 77.90 | 22th Floor | 42644 | 42647 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5727 | Form Work For Stair Axis B1/A2 | Form Work | Stair | 51.50 TO 54.80 | 15th Floor | 42644 | 42653 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5728 | Steel Reinforcement For Shear Wall3 axis C6/A2 to A3 | Steel Reinforcement | SH.W | 71.30 TO 74.60 | 21th Floor | 42646 | 42647 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5729 | Check Form work at 76.60 first stage | Form work | Slab | 74.60 | 20th Floor | 42646 | 42652 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5730 | Check FormWork at 69.60 at secand stage | Form work | Slab | 69.60 | 18th Floor | 42646 | 42652 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5731 | Check level of Form Work At 69.60 Second Stage | Form work | Slab | 69.60 | 18th Floor | 42646 | 42652 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5732 | Top& Bottom Steel Reinforcement For third stage slab Axis B13 TO B19/A6TO A12 | Steel Reinforcement | Slab | 63.00 | 17th Floor | 42646 | 42647 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5733 | Tendons,Strands,Anchors and Profiles for Sabels Axis B13 TO B19/A6 TO A12 | Anchor | Slab | 63.00 | 17th Floor | 42646 | 42647 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5734 | Steel reinforcement For Commen Pour Strip (1&2) Axis B9/A6 TO A12 | Steel Reinforcement | Pour strip | 66.30 | 18th Floor | 42646 | 42647 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5735 | Steel reinforcement For Core 8 Axis B1/A2 TO A3 | Steel Reinforcement | Core | UP TO 79.20 | 23th Floor | 42646 | 42647 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5736 | Form Work For Core 8 Axis B1/A2 TO A3 | Form Work | Core | UP TO 79.20 | 23th Floor | 42646 | 42651 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5737 | Form Work For Shear Wall 2 Axis C10/A2 TO A3 | Form Work | SH.W | 71.30 TO 74.60 | 21th Floor | 42646 | 42651 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5738 | Form Work For Shear Wall 3* Axis C8/A2 TO A3 | Form Work | SH.W | 71.30 TO 74.60 | 21th Floor | 42646 | 42651 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5739 | Steel Reinforcement For Shear Wall 2 Axis C10/A2 TO A3 | Steel Reinforcement | SH.W | 71.30 TO 74.60 | 21th Floor | 42646 | 42647 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5740 | Steel reinforcement For Shear Wall 3 * Axis C8/A2 TO A3 | Steel Reinforcement | SH.W | 71.30 TO 74.60 | 21th Floor | 42646 | 42651 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5741 | Form Work For Shear Wall 3 Axis C6/A2 TO A3 | Form Work | SH.W | 71.30 TO 74.60 | 21th Floor | 42646 | 42651 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5742 | Steel reinforcement For Shear Wall 5* Axis C5/A2 TO A3 | Steel Reinforcement | SH.W | 71.30 TO 74.60 | 21th Floor | 42646 | 42647 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5743 | Form Work For Shear wall 5* Axis C5/A2 TO A3 | Form Work | SH.W | 71.30 TO 74.60 | 21th Floor | 42646 | 42651 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5744 | Steel reinforcement For Core 5 Axis A6 To A12/B6 TO B8 | Steel Reinforcement | core | 72.90 TO 76.20 | 20th Floor | 42646 | 42651 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5745 | Steel reinforcement For Shaear wall 1+C1 Axis B19/A1 | Steel Reinforcement | SH.W | 71.30 TO 74.60 | 21th Floor | 42647 | 42651 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5746 | Steel reinforcement For Columun C5 Axis B18/A1 | Steel Reinforcement | Columun | 71.30 TO 74.60 | 21th Floor | 42647 | 42652 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5747 | Steel reinforcement For Columun CC5 &CC6 Axis C9 TO C11/A3 | Steel Reinforcement | Columun | 71.30 TO 74.60 | 21th Floor | 42647 | 42651 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5748 | Steel reinforcement For Core 6 Axis B16/A2 | Steel Reinforcement | Core | 71.30 TO 74.60 | 21th Floor | 42647 | 42651 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5749 | Form Work For Core 6 Axis B16/A2 | Form Work | Core | 71.30 TO 74.60 | 21th Floor | 42647 | 42651 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5750 | Form Work For Columun CC5 & CC6 Axis C9 TO C11/A3 | Form Work | Columun | 71.30 TO 74.60 | 21th Floor | 42647 | 42651 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5751 | Form Work For Columun C5 Axis B18/A1 | Form Work | Columun | 71.30 TO 74.60 | 21th Floor | 42647 | 42651 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5752 | Form Work For Shear wall 1+C1 Axis B19/A1 | Form Work | SH.W | 71.30 TO 74.60 | 21th Floor | 42647 | 42651 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5753 | Steel reinforcement For Stair 3 Axis B7/A8 | Steel Reinforcement | Stair | 66.30 TO 69.60 | 17th Floor | 42647 | 42652 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5754 | Top & Bottom Steel reinforcement for Surge Tank ground Slab Axis B2 TO B4/A4 TO A5 | Steel Reinforcement | Slab | -3.80 | BOH | 42647 | 42651 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5755 | Inspection For holes and dowels Fixation Of Edge Cantilever Slab Hotel Tower Axis B13 TO B10/A1 TO A3 | Holes And Dowels Fixation | Slab | 54.80 | 15th FLoor | 42760 | 42761 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5756 | Tendons.Strands,Anchors and Profiles for Cabels Axis B9/A6 TO A12 | Anchor | Slab | 69.60 | 19th Floor | 42648 | 42651 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5757 | Steel Reinforcement For First Stage Slab Axis B9/A6 TO A12 | Steel Reinforcement | Slab | 69.60 | 19th Floor | 42648 | 42651 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5758 | Form Work For Surge Tank Axis B2/A6 | Form Work | Surge Tank | 3.80 | BOH | 42648 | 42652 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5759 | Form Work For Core 7 Axis C7/A2 | Form Work | Core | 74.60 TO 77.90 | 22th Floor | 42648 | 42652 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5760 | Steel reinforcement For Core 7 Axis C7/A2 | Steel Reinforcement | Core | 74.60 TO 77.90 | 22th Floor | 42648 | 42651 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5761 | Steel reinforcement For Stair 14 Axis B16/A2 | Steel Reinforcement | Stair | 41.60 TO 44.90 | 15th Floor | 42648 | 42654 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5762 | Form Work for core 2 Axis A9 / B7 | Form Work | Core | 66.30 TO 69.60 | 19th Floor | 42648 | 42651 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5763 | Form Work For 1 Columuns DCC7 Axis B13/A6 | Form Work | Columun | 63.00 TO 66.30 | 18th Floor | 42651 | 42653 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5764 | Steel reinforcement For 1 Columuns DCC7 Axis B13/A6 | Steel Reinforcement | Columun | 63.00 TO 66.30 | 18th Floor | 42651 | 42653 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5765 | Form Work For 2 Columuns DCC1 & Columun DCC1* Axis B13/A8 TO A12 | Form Work | Columun | 63.00 TO 66.30 | 18th Floor | 42651 | 42653 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5766 | Steel reinforcement For 2 Columuns DCC1 & Clumun DCC1 Axis B13/A8 TO A12 | Steel Reinforcement | Columun | 63.00 TO 66.30 | 18th Floor | 42651 | 42653 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5767 | Form Work For 6 Columun CC4 Axis B16 TO B19/A6 TO A12 | Form work | Columun | 63.00 TO 66.30 | 18th Floor | 42651 | 42653 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5768 | Steel reinforcement For 6 Columuns CC4 At third Stage Axis B16 TO B19/A6 TO A12 | Steel Reinforcement | Columun | 63.00 TO 66.30 | 18th Floor | 42651 | 42653 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5769 | Form Work For 3 Columuns CC7 Axis B14 TO B17/A6 TO A12 | Form work | Columun | 63.00 TO 66.30 | 18th Floor | 42651 | 42653 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5770 | Steel reinforcement For 3 Columuns CC7 Axis B14 TO B17/A6 TO A12 | Steel Reinforcement | Columun | 63.00 TO 66.30 | 18th Floor | 42651 | 42653 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5771 | Form work For Columuns CC9 At third stage Axis B14/A11 | Form work | Columun | 63.00 TO 66.30 | 18th Floor | 42651 | 42653 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5772 | Steel reinforcement For Columun CC9 At third stage Axis B14/A11 | Steel Reinforcement | Columun | 63.00 TO 66.30 | 18th Floor | 42651 | 42653 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5773 | Grouting For First & Second Stage Hotel Tower Slab Axis B19 TO B1/A1 TO A3 | Grout | Slab | 68.00 | 19th Floor | 42652 | 42652 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5774 | Grouting For First & Second Stage Hotel Tower Slab Axis B19 TO B1/A1 TO A3 | Grout | Slab | 71.30 | 20th Floor | 42652 | 42665 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5775 | Form Work Removal For First & Second Stage Hotel Slab Axis B19 TO B1/A1 TO A3 | Form work | Slab | 71.30 | 20th Floor | 42652 | 42659 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5776 | Form Work Removal For First & Second Stage Hotel Slab Axis B19 TO B1/A1 TO A3 | Form work | Slab | 68.00 | 19th Floor | 42652 | 42653 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5777 | Form Work For Stair 7 Axis B11/A10 | Form work | Stair | 66.30 TO 69.60 | 15th Floor | 42652 | 42652 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5778 | Steel reinforcement For Core 1 Axis B17/A9 | Steel Reinforcement | Core | 63.00 TO 66.30 | 15th Floor | 42652 | 42653 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5779 | Form Work For Stair 6 Axis B11/A8 | Form work | Stair | 66.30 TO 69.60 | 18-19th Floor | 42652 | 42652 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5780 | Form Work For Core 1 Axis B17/A9 | Form work | Core | 63.00 TO 66.30 | 15th Floor | 42652 | 42653 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5781 | Form Work For 4 Columuns CC7 Axis B4/A8 TO A9&A10 TO A11 | Form work | Columuns | 69.60 TO 72.90 | 20th Floor | 42653 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5782 | Form Work For 3Columuns CC7 Axis A6/B5 TO B6&B9 | Form work | Columuns | 69.60 TO 72.90 | 20th Floor | 42653 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5783 | Steel reinforcement For 3 Columuns CC7 Axis A6/B5 TO B6 & B9 | Steel Reinforcement | Columuns | 69.60 TO 72.90 | 20th Floor | 42653 | 42656 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5784 | Form Work For 2 Columuns CC9 Axis A11/B6 TO B8 | Form work | Columuns | 69.60 TO 72.90 | 20th Floor | 42653 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5785 | Steel reinforcement For 2 Colunmns CC9 Axis A11/B6 TO B8 | Steel Reinforcement | Columuns | 69.60 TO 72.90 | 20th Floor | 42653 | 42656 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5786 | Steel reinforcemnt For 4 Columuns CC7 Axis B4/A8 TO A9&A10 TO A11 | Steel Reinforcement | Columuns | 69.60 TO 72.90 | 20th Floor | 42653 | 42656 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5787 | Form Work For Shear Wall 1 Axis B17 TO B10/A1 | Form Work | SH.W | 77.90 TO 81.27 | 23th Floor | 42653 | 42656 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5788 | Steel reinforcement For Shear wall 1 Axis B17 TO B10/A1 | Steel Reinforcement | SH.W | 77.90 TO 81.27 | 23th Floor | 42653 | 42653 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5789 | Form Work For Core 3 Axis A11/B6 TO B8 | Form work | Core | 72.90 TO 76.20 | 21th Floor | 42653 | 42663 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5790 | Steel reinforcement For Core 3 Axis A11/B6 TO B8 | Steel Reinforcement | Core | 72.90 TO 76.20 | 21th Floor | 42653 | 42654 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5791 | Stressing For Cables Of First Stage Post Tension Slab Residential Tower | Stressing | Post tension | 69.60 | 19th Floor | 42653 | 42656 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5792 | Check Form Work At 74.60 Second Stage | Form work | Second stage | 74.60 | 20th Floor | 42653 | 42654 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5793 | Top&Bottom Steel reinforcement For First stage Hotel Tower Slab Axis B1 TO C5/A1 TO A3 | Steel Reinforcement | Slab | 74.60 | 21th Floor | 42654 | 42654 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5794 | Tendons,Strands,Anchors and Profiles first stage Hotel Tower Slab | Anchor | Slab | 74.60 | 21th Floor | 42654 | 42654 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5795 | Form Work For Core 5 Axis A11/B6 TO B8 | Form work | Core | 72.90 TO 76.20 | 21th Floor | 42654 | 42656 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5796 | Steel reinforcement For Stair 6 Axis A11/B6 TO B8 | Steel Reinforcement | Stair | 66.30 TO 69.60 | 19th FLoor | 42654 | 42656 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5797 | Steel reinforcement For Stair7Axis A11/B6 TO B8 | Steel Reinforcement | Stair | 66.30 TO 69.60 | 19th FLoor | 42654 | 42656 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5798 | Stressing For Cable Of Third Stage Post Tension Slab Residential Tower Axis B13 TO B19/A6 TO A12 | Stressing | Slab | 63.00 | 17th Floor | 42654 | 42654 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5799 | Grouting For Ducts Of Third Stage Post Tension Slab Residential Tower Axis B13 TO B19/A6 TO A12 | Grout | Slab | 59.70 | 16th Floor | 42654 | 42656 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5800 | Top& Bottom steel Reinforcement for secand stage slab Residential tower Axis B13 TO B9 /A6 TO A12 | Steel Reinforcement | Slab | 69.60 | 19th Floor | 42655 | 42656 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5801 | Tendons, Strands, Anchors and Profiles secand stage slab Axis B13 TO B9 / A6 TO A12 | Anchor | Slab | 69.60 | 19th Floor | 42655 | 42654 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5802 | Grouting For Ducts Of First And second Stage post Tension Slab Residentail Tower Axis A6 TO A12/ B4 TO B13 | Grout | Slab | 63.00 | 17th Floor | 42656 | 42658 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5803 | Steel reinforcement For Surge Tank Walls Axis B5/A4 | Steel Reinforcement | Surge Tank | 3.80 TO .47 | BOH | 42658 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5804 | Check Form Work At 66.30 At Core 2 Slab | Form Work | Slab | 66.30 | 17th Floor | 42659 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5805 | Check Form Work At 66.30 At third stage | Form Work | Slab | 66.30 | 17th Floor | 42659 | 42661 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5806 | Form Work For Shear wall+CC1 Axis B4/A8 TO A9 | Form Work | SH.W+CC1 | 69.60 TO 72.90 | 19th FLoor | 42660 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5807 | Steel Reinforcement For Shear Wall9+CC1 Axis B4/A8 TO A9 | Steel Reinforcement | SH.W+CC1 | 69.60 TO 72.90 | 19th FLoor | 42660 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5808 | Steel reinforcement For 3 Columuns DCC3,DCC1&DCC7 Axis B4/A11 TO A10&A6 | Steel Reinforcement | Columuns | 69.60 TO 72.90 | 19th FLoor | 42660 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5809 | Form Work For 3 Columuns DCC3,DCC1&DCC7 Axis B4/A11 TO A10&A6 | Form Work | Columuns | 69.60 TO 72.90 | 19th FLoor | 42660 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5810 | Form Work For 2 Columuns CC9 Axis A11/B10 TO B12 | Form Work | Columuns | 69.60 TO 72.90 | 19th FLoor | 42660 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5811 | Steel Reinforcement For 2Columuns CC9 Axis A11/B10 TO B12 | Steel Reinforcement | Columuns | 69.60 TO 72.90 | 19th FLoor | 42660 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5812 | Steel reinforcement For 2 Columuns CC7 Axis A6/B10 TO B12 | Steel Reinforcement | Columuns | 69.60 TO 72.90 | 19th FLoor | 42660 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5813 | Form Work For 2 Columuns CC7 Axis A6/B10 TO B12 | Form Work | Columuns | 69.60 TO 72.90 | 19th FLoor | 42660 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5814 | Form Work For Stair 11 Axis | Form Work | Stair | 63.00 TO 66.30 | 17th Floor | 42659 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5815 | Form Work For Shear Wall 8 Axis | Form Work | SH.W | 74.60 TO 77.90 | 22th Floor | 42659 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5816 | Steel reinforcement For Shear Wall 8 Axis | Steel Reinforcement | SH.W | 74.60 TO 77.90 | 22th Floor | 42659 | 42661 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5817 | Form Work For Shear Wall 1 Axis B1 TO C5/A1 | Form Work | SH.W | 77.90 TO 81.27 | 23th Floor | 42659 | 42661 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5818 | Steel Reinforcement For Shear Wall 1 Axis B1 TO C5/A1 | Steel Reinforcement | SH.W | 77.90 TO 81.27 | 23th Floor | 42659 | 42661 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5819 | Top&Bottom Steel reinforcement For 2nd stage Hotel Tower Slab Axis B19 TO C5/A1 TO A3 | Steel Reinforcement | Slab | 74.60 | 21th Floor | 42660 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5820 | Tendons,Strands anchors and Profiles for second stage RD tower Slab Axis B19TO C5/A1 TO A3 | Anchor | Slab | 74.60 | 21th Floor | 42660 | 42661 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5821 | Steel reinforcemnt For Pour Strip 2/3 Residential Tower Slab Axis B13/A6 TO A12 | Steel Reinforcement | Slab | 63.00 | 17th Floor | 42660 | 42661 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5822 | Stressing For Cables Of First Stage Post tension Hotel Tower Slab Axis B1 TO C5/A2 TO A3 | Stressing | Slab | 74.60 | 21th Floor | 42660 | 42665 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5823 | Steel Reinforcement for stair 11 Axis B17/A9 | Steel Reinforcement | Stair | 63.00 TO 66.30 | 17th Floor | 42660 | 42667 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5824 | Steel reinforcement For Shear wall 1 Axis B10 TO C5/A1 | Steel Reinforcement | SH.W | 77.90 TO 81.27 | 23th Floor | 42661 | 42662 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5825 | Form Work For Shear Wall 1 Axis B10 TO C5/A1 | Form Work | SH.W | 77.90 TO 81.27 | 23th Floor | 42661 | 42663 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5826 | Form Work For Core 7 Axis C7/A2 TO A3 | Form Work | Core | 77.90 TO 81.27 | 23th Floor | 42661 | 42663 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5827 | Steel reinforcement For Core 7 Axis C7/ A2 TO A3 | Steel Reinforcement | Core | 77.90 TO 81.27 | 23th Floor | 42661 | 42662 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5828 | Tendons,Strands,Anchors and Profiles for Third Stage Slab Residential Tower Axis B13 TO B19/A6 TO A12 | Anchor | Slab | 66.30 | 18th Floor | 42662 | 42665 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5829 | Top&Bottom Steel reinforcement For Third Stage Slab Residential Tower Axis B13 TO B19/A6 TO A12 | Steel Reinforcement | Slab | 66.30 | 18th Floor | 42662 | 42667 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5830 | Form Work For Stair 14 | Form Work | Stair | 44.90 TO 48.20 | 13th floor | 42662 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5831 | Steel reinforcement For Stair 12 | Steel Reinforcement | Stair | 51.50 TO 54.80 | 15th FLoor | 42662 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5832 | Check Form Work At 74.60 Second Stage | Form Work | Slab | 77.90 | 21th Floor | 42663 | 42665 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5833 | Stressing For Cable Of Second Stage Post tension slab Residential Tower Axis B9 TO B13/A6 TO A12 | Stressing | slab | 69.60 | 19th FLoor | 42662 | 42667 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5834 | Check Form Work at 72.90 at Core 5 Stage Axis First | Form Work | Slab | 72.90 | 19th Floor | 42662 | 42665 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5835 | Check Form Work at 72.90 first stage Axis First | Form Work | Slab | 72.90 | 19th Floor | 42662 | 42663 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5836 | Form Work For Shear Wall 1 Axis B10 TO B17/A1 | Form Work | SH.W | 81.27 TO 84.50 | 24th Floor | 42663 | 42667 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5837 | Steel reinforcement For Shear Wall 1 Axis B10 TO B17/A1 | Steel Reinforcement | SH.W | 81.27 TO 84.50 | 24th Floor | 42663 | 42667 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5838 | Form Work For Surge Tank Axis B5/A4 | Form Work | Surge Tank | -.380 TO +.47 | BOH | 42663 | 42667 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5839 | Steel reinforcement for core 2 | Steel Reinforcement | Core | 69.90 TO 72.20 | 19th Floor | 42665 | 42667 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5840 | Steel reinforcement For Shear Wall 2 Axis C10/A2 TO A3 | Steel Reinforcement | SH.W | 74.60 TO 77.90 | 22th Floor | 42666 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5841 | Steel reinforcement For Shear Wall 3* Axis C8/A2 TO A3 | Steel Reinforcement | SH.W | 74.60 TO 77.90 | 22th Floor | 42666 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5842 | Steel reinforcement For Shear Wall 3 Axis C6/A2 TO A3 | Steel Reinforcement | SH.W | 74.60 TO 77.90 | 22th Floor | 42666 | 42667 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5843 | Steel reinforcement For Shear Wall 5* Axis C5/A2 TO A3 | Steel Reinforcement | SH.W | 74.60 TO 77.90 | 22th Floor | 42666 | 42667 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5844 | Steel reinforcement For 3 Columuns CC7 Axis A6/B14 TO B16&B16/A12 | Steel Reinforcement | Columuns | 66.30 TO 69.60 | 18th Floor | 42666 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5845 | Steel reinforcement For 5 Columuns CC4 Axis D1 TO D2 &D3 TO D4/A9 | Steel Reinforcement | Columuns | 66.30 TO 69.60 | 18th Floor | 42666 | 42669 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5846 | Steel reinforcement For 2 Columuns DCC1* & DCC7 Axis B13/A6 TO A8 | Steel Reinforcement | Columuns | 66.30 TO 69.60 | 18th Floor | 42666 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5847 | Steel reinforcement For 2 Columuns DCC1 Axis B13/A11 TO A10 | Steel Reinforcement | Columuns | 66.30 TO 69.60 | 18th Floor | 42666 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5848 | Form Work For 3 Columuns CC7 Axis A6/B14 TO B16&B16/A12 | Form Work | Columuns | 66.30 TO 69.60 | 18th Floor | 42666 | 42670 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5849 | Form work For 5 Columuns CC4 Axis D1 TO D2 &D3 TO D4/A9 | Form Work | Columuns | 66.30 TO 69.60 | 18th Floor | 42666 | 42670 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5850 | Form Work For 2 Columuns DCC1*&DCC7 Axis B13/A6 TO A8 | Form Work | Columuns | 66.30 TO 69.60 | 18th Floor | 42666 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5851 | Form Work For 2 Columuns DCC1 Axis B13/A11 TO A10 | Form Work | Columuns | 66.30 TO 69.60 | 18th Floor | 42666 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5852 | Form Work For Core 1 Axis B17/A9 | Form Work | Core | 66.30 TO 69.60 | 18th Floor | 42666 | 42675 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5853 | Steel reinforcement For Core 1 Axis B17/A9 | Steel Reinforcement | Core | 66.30 TO 69.60 | 18th Floor | 42666 | 42675 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5854 | Steel reinforcement For 2 Columuns CC9&CC4 Axis B14/A11 TO B16/A10 | Steel Reinforcement | Columuns | 66.30 TO 69.60 | 18th Floor | 42666 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5855 | Form Work For 2 Columuns CC9&CC4 Axis B14/A11&B16/A10 | Form Work | Columuns | 66.30 TO 69.60 | 18th Floor | 42666 | 42670 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5856 | Form Work For Shear Wall 2 Axis C10/A2 TO A3 | Form Work | SH.W | 74.60 TO 77.90 | 22th Floor | 42666 | 42667 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5857 | Form Work For Shear Wall 3* Axis C8/A2 TO A3 | Form Work | SH.W | 74.60 TO 77.90 | 22th Floor | 42666 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5858 | Form Work For Shear Wall 5* Axis C5/A2 TO A3 | Form Work | SH.W | 74.60 TO 77.90 | 22th Floor | 42666 | 42667 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5859 | Form Work For Shear Wall 3 Axis C6/A2 TO A3 | Form Work | SH.W | 74.60 TO 77.90 | 22th Floor | 42666 | 42667 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5860 | Form Work For Stair 3 | Form Work | Stair | 69.60 TO 72.90 | 20th Floor | 42666 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5861 | Steel reinforcement For Pour Strip 1/2 Axis B9/A6 TO A12 | Steel Reinforcement | Pour strip | 69.60 | 15th FLoor | 42666 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5862 | Steel Reinforcement For Tower crane opening Axis C3 TO C4/A2 TO A3 | Steel Reinforcement | crane | 54.80 | 15th FLoor | 42666 | 42667 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5863 | Form Work For Columuns CC5 & CC 6 Axis C9 TO C11/A3 | Form Work | Columuns | 74.60 TO 77.90 | 22th Floor | 42657 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5864 | Steel reinforcement For Columuns CC5 & CC6 Axis C9 TO C11/A3 | Steel Reinforcement | Columuns | 74.60 TO 77.90 | 22th Floor | 42657 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5865 | Steel Reinforcemnet For Stair 14 | Steel Reinforcement | Stair | 44.90 TO 48.20 | 13th floor | 42657 | 42670 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5866 | Steel reinforcement For Stair 3 | Steel Reinforcement | Stair | 69.60 TO 72.90 | 21th FLoor | 42657 | 42668 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5867 | Steel reinforcement For Core 5 | Steel Reinforcement | Core | 76.20 TO 79.50 | 22th Floor | 42657 | 42669 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5868 | Check Level Of Form Work At Level 72.90 Second Stage | form work | Slab | 72.90 | 19th FLoor | 42657 | 42670 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5869 | Steel reinforcemnt For Columuns C5 Axis B18/A1 | Steel Reinforcement | Columuns | 74.60 TO 77.90 | 21th Floor | 42668 | 42670 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5870 | Form Work For Columuns C5 Axis B18/A1 | Form Work | Columuns | 74.60 TO 77.90 | 21th Floor | 42668 | 42670 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5871 | Form Work For Shear Wall1+C1 Axis B19/A1 | Form Work | SH.W+C1 | 74.60 TO 77.90 | 21th Floor | 42668 | 42670 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5872 | Steel reinforcemnt For Shear Wall 1+ C1 Axis B19/A1 | Steel Reinforcement | SH.W+C1 | 74.60 TO 77.90 | 21th Floor | 42668 | 42668 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5873 | Steel reinforcemnt For Core 6 Axis B16/A2 | Steel Reinforcement | Core | 74.60 TO 77.90 | 21th Floor | 42668 | 42668 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5874 | Form Work For Core 6 Axis B16/A2 | Form Work | Core | 74.60 TO 77.90 | 21th Floor | 42668 | 42670 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5875 | Steel Reinforcement For Pour Strip Hotel Tower Axis C5/A1 To A3 | Steel Reinforcement | Pour strip | 71.30 | 20th Floor | 42668 | 42669 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5876 | Grouting For Ducts Of Third Stage Post Tension Residential Tower | Grout | Post tension | 63.00 | 17th Floor | 42669 | 42670 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5877 | Stressing For Cables Of third Stage Post tension Residential Tower | Stressing | Post tension | 63.00 | 18th Floor | 42669 | 42675 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5878 | Stressing For Cables Of Second Stage Post Tension Hotel Tower Slab Axis B19 TO C5/A2 TO A3 | Stressing | Post tension | 74.60 | 21th Floor | 42669 | 42673 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5879 | Form Work For Core 2 | Form Work | Core | 69.60 TO 72.90 | 19th FLoor | 42669 | 42670 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5880 | Top & Bottom Steel reinforcement For First Stage Residential Tower Slab Axis B4 TO B9/A6 TO A12 | Steel Reinforcement | Slab | 72.90 | 20th Floor | 42669 | 42670 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5881 | Tendons,Strands,Anchors and Profiles First stage Residential Tower Slab Axis B4 TO B9/A6 TO A12 | Anchor | Slab | 72.90 | 20th Floor | 42669 | 42670 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5882 | Form Woek For Stair 12 | Form Work | Stair | 54.80 TO 58.10 | 16th Floor | 42670 | 42673 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5883 | Form Work For Stair 6 | Form Work | Stair | 69.60 TO 72.90 | 20th Floor | 42670 | 42670 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5884 | check form work at 77.90 secand stage | Form Work | Slab | 77.90 | 21th FLoor | 42670 | 42676 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5885 | Top & Bottom Steel reinforcement For First Stage Hotel Tower Slab Axis B1 TO C5/A1 TO A3 | Steel Reinforcement | Slab | 77.90 | 22th Floor | 42672 | 42673 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5886 | Tendons,Strands,Anchors and Profiles First Stage Hotel Tower Slab Axis B1 TO C5/A1 TO A3 | Anchor | Slab | 77.90 | 22th Floor | 42672 | 42672 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5887 | Steel reinforcement For Columuns And Shear Walls Axis A11/B6 TO B8 | Steel Reinforcement | SH.W+CC9 | 72.90 TO 76.20 | 19th FLoor | 42673 | 42677 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5888 | Steel reinforcemnt For Columns and Shear walls Axis B4/A8 TO A9&A10/A11 | Steel Reinforcement | SH.W+CC7 | 72.90 TO 76.20 | 19th FLoor | 42673 | 42675 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5889 | Steel reinforcement For Columuns and Shear Walls Axis A6/B5 TO B6&B8 | Steel Reinforcement | SH.W+CC7 | 72.90 TO 76.20 | 19th FLoor | 42673 | 42675 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5890 | Form Work For 2 Columuns CC9 Axis B8 TO B6&B5/A6 | Form Work | SH.W+CC9 | 72.90 TO 76.20 | 19th FLoor | 42674 | 42677 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5891 | Form Work For 3 Columuns CC7 Axis B8 TO B6&B5/A6 | Form Work | SH.W+CC7 | 72.90 TO 76.20 | 19th FLoor | 42674 | 42677 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5892 | Form Work For 4 Columuns CC7 Axis B4/A8 TO A9&A10 TO A11 | Form Work | SH.W+CC7 | 72.90 TO 76.20 | 19th FLoor | 42674 | 42675 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5893 | Form Work For Stair Case | Form Work | Stair | 69.60 TO 72.90 | BOH | 42674 | 42674 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5894 | Steel reinforcement For Stair 12 | Steel Reinforcement | Stair | 54.80 TO 58.10 | 16th Floor | 42674 | 42677 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5895 | Steel reinforcement For Stair 7 | Steel Reinforcement | Stair | 69.60 TO 72.90 | 20th Floor | 42674 | 42677 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5896 | Steel reinforcement For Stair 6 | Steel Reinforcement | Stair | 69.60 TO 72.90 | 20th Floor | 42674 | 42677 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5897 | Steel reinforcement For Core 3 | Steel Reinforcement | Core | 76.20 TO 79.50 | 21th FLoor | 42674 | 42676 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5898 | Grouting For Ducts Of First Stage Post Tension Slab Residential Tower Axis B4 TO B9/A6 TO A12 | Grout | Slab | 66.30 | 18th FLoor | 42674 | 42675 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5899 | Form Work For Surge Tank Roof Slab | Form Work | Slab | +47 | BOH | 42675 | 42676 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5900 | Top and Bottom Steel reinforcement For Surge tank roof slab | Steel Reinforcement | Slab | +47 | BOH | 42675 | 42676 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5901 | Steel Reinforcement For Shear Wall 1 Axis B1 TO B10/A1 | Steel Reinforcement | SH.W | 81.27 TO 84.50 | Upper Roof | 42676 | 42677 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5902 | Form Work For Shear Wall 1 Axis B1 TO B10/A1 | Form Work | SH.W | 81.27 TO 84.50 | Upper Roof | 42676 | 42677 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5903 | Top & Bottom Steel reinforcement For Second Stage Tower Axis B13 TO B9/A6 TO A12 | Steel Reinforcement | Slab | 72.90 | 20th Floor | 42676 | 42677 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5904 | Tendons,Strands,Anchors and Profiles Second Stage Residential Tower Slab Axis B13 TO B9/A6 TO A12 | Anchor | Slab | 72.90 | 20th Floor | 42676 | 42677 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5905 | Form Work For Core 5 | Form Work | Core | 76.20 TO 79.50 | 22th Floor | 42676 | 42677 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5906 | Steel reinforcement For Stair 14 | Steel Reinforcement | Stair | 48.20 TO 51.50 | 14th floor | 42676 | 42687 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5907 | Check Form Work At 69.60 at Core 2 Slab | Form work | Slab | 69.60 | 18th Floor | 42676 | 42679 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5908 | Check Form Work At 69.60 at third stage Slab | Form work | Slab | 69.60 | 18th Floor | 42676 | 42677 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5909 | Form Work For Stair 14 | Form work | Stair | 48.20 TO 51.50 | 14th floor | 42677 | 42677 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5910 | Bottom,Top Layer and Beam Steel reinforcemnt Work For Part 2 Of P.T Slab Axis B19 TO C5/A1 TO A3 | Steel Reinforcement | Slab | 77.90 | 20th Floor | 42677 | 42677 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5911 | Tendons,Strands,Anchors and Profiles second stage Hotel tower slab Axis B19 TO C5/A1 TO A3 | Anchor | Slab | 77.90 | 20th Floor | 42677 | 42677 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5912 | Steel reinforcement For Pour Strip 2/3 | Steel Reinforcement | Pour strip | 66.30 | 18th Floor | 42677 | 42679 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5913 | Grouting For Ducts Of First Stage Post tension Slab Hotel Tower Axis C5 TO B1/A1 TO A3 | Grout | Post tension | 74.60 | 21th FLoor | 42679 | 42682 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5914 | Stressing For Cables Of First Stage Post Tension Slab Hotel Tower Axis C5 TO B1/A1 TO A3 | Stressing | Post tension | 77.90 | 21th FLoor | 42679 | 42682 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5915 | Form Work for stair 11 Axis B16 TO B18 / A9 TO A7 | Form Work | Stair | 66.30 TO 69.60 | 19th FLoor | 42679 | 42679 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5916 | Form Wor For Shear Wall 9+CC1 Axis A8 TO A9/B13 | Form Work | SH.W 9+ CC1 | 72.90 TO 76.20 | 20th Floor | 42680 | 42683 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5917 | Steel Reinforcement For Shear Wall9+CC1 Axis B4/A8 TO A9 | Steel Reinforcement | SH.W 9+ CC1 | 72.90 TO 76.20 | 20th Floor | 42680 | 42684 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5918 | Steel Reinforcement For 2Columuns CC9 Axis A11/B10 TO B12 | Steel Reinforcement | Columuns | 72.90 TO 76.20 | 20th Floor | 42680 | 42684 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5919 | Form Work For 2 Columuns CC9 Axis A11/B10 TO B12 | Form Work | Columuns | 72.90 TO 76.20 | 20th Floor | 42680 | 42683 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5920 | Form Work For 2 Columuns CC7 Axis A6/B10 TO B12 | Form Work | Columuns | 72.90 TO 76.20 | 20th Floor | 42680 | 42683 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5921 | Steel reinforcement For 2 Columuns CC7 Axis A6/B10 TO B12 | Steel Reinforcement | Columuns | 72.90 TO 76.20 | 20th Floor | 42680 | 42684 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5922 | Steel reinforcement For Columuns DCC7,DCC1,DCC3 Axis A6/B13 &A10/B13&A11/B13 | Steel Reinforcement | Columuns | 72.90 TO 76.20 | 20th Floor | 42680 | 42684 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5923 | Form Work For Columuns DCC7,DCC1,DCC3 Axis A6/B13,A10/B13,A11/B13 | Form Work | Columuns | 72.90 TO 76.20 | 20th Floor | 42680 | 42683 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5924 | Steel reinforcement For Stair 11 | Steel Reinforcement | Stair | 66.30 TO 69.60 | 18th Floor | 42680 | 42684 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5925 | Steel Reinforcement For Core 2 Axis | Steel Reinforcement | Core | 72.90 TO 76.20 | 20th Floor | 42681 | 42684 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5926 | Stressing For Cables Of Second Stage Post tension Hotel Tower Slab Axis B19 TO C5/A1 TO A3 | Stressing | Post tension | 77.90 | 22th Floor | 42682 | 42687 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5927 | Stressing For Cables Of Second Stage Post tension Slab Residential Tower Axis B9 TO B13/A6 TO A12 | Stressing | Post tension | 72.90 | 20th Floor | 42682 | 42687 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5928 | Steel reinforcement For Pour Strip Hotel Tower Axis C5/A1 TO A3 | Steel Reinforcement | Pour strip | 74.60 | 21th FLoor | 42682 | 42683 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5929 | Grouting For Ducts Of Second Stage Post tension Slab Hotel Tower Axis C5 TO B19/A1 TO A3 | Grout | Post tension | 74.60 | 21th FLoor | 42682 | 42687 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5930 | Check Form Work At 76.20 At First Stage | form Work | Slab | 76.20 | 20th Floor | 42682 | 42684 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5931 | Check Form Work At 76.20 At Core 5 Stage | form Work | Core | 76.20 | 20th Floor | 42683 | 42687 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5932 | Grouting For Ducts Of Second Stage Post tension Slab Residential Tower Axis B13 TO B9/A1 TO A3 | Grout | slab | 66.30 | 18th FLoor | 42683 | 42687 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5933 | Form Work For Core 3 Axis B11/A9 | Form Work | Core | 76.20 TO 79.50 | 22th Floor | 42683 | 42684 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5934 | Top & Bottom Steel reinforcement For Third Stage Residential Tower Slab Axis B13 TO B19/A6TO A12 | Steel Reinforcement | slab | 69.60 | 19th FLoor | 42683 | 42684 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5935 | Tendons,Strands,Anchors and profiles third stage RD Tower Slab Axis A6 TO A12 / B13 TO B19 | Anchor | slab | 69.60 | 19th FLoor | 42683 | 42684 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5936 | Form Work For Stair 12 | Form Work | Stair | 58.10 TO 61.40 | 16th FLoor | 42684 | 42687 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5937 | Grouting For Ducts Of third Stage Post Tension Residential Tower Axis B13 TO B19/A6 TO A12 | Grout | post tension | 66.30 | 18th FLoor | 42684 | 42687 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5938 | Form Work For Stair 3 Axis B7/ A8 | Form Work | Stair | 72.90 TO 76.20 | 22th Floor | 42686 | 42689 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5939 | Check Form Work at Ground Floor at Swimming Pool area at Axis A9 TO A3/C1 TO B4 | Form Work | slab | 1.10 | ground Floor | 42686 | 42688 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5940 | Steel reinforcement For 3 Coumuns CC7 Axis A6/B14 TO B16&B16/A12 | Steel Reinforcement | Columuns | 69.60 TO 72.90 | 19th FLoor | 42687 | 42690 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5941 | Steel reinforcement For 2 Columuns DCC1* & DCC7 Axis B13/A6 TO A8 | Steel Reinforcement | Columuns | 69.60 TO 72.90 | 19th FLoor | 42687 | 42691 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5942 | Steel reinforcement For 5 Columuns CC4 Axis D1 TO D2 &D3 TO D4/A9 | Steel Reinforcement | Columuns | 69.60 TO 72.90 | 19th FLoor | 42687 | 42695 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5943 | Steel reinforcement For 2 Columuns DCC1 Axis B13/A11 TO A10 | Steel Reinforcement | Columuns | 69.60 TO 72.90 | 19th FLoor | 42687 | 42691 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5944 | Form Work For Columuns CC9,CC4 Axis B14/A11 TO B16/A10 | Form Work | Columuns | 69.60 TO 72.90 | 19th FLoor | 42687 | 42695 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5945 | Steel reinforcement For 2 Columuns CC9&CC4 Axis B14/A11 TO B16/A10 | Steel Reinforcement | Columuns | 69.60 TO 72.90 | 19th FLoor | 42687 | 42691 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5946 | Bottom And Top Layer Steel reinforcement Work For P.T Slab (Commen Pour Strip Between Stage (1&2) | Steel Reinforcement | Slab | 77.90 | 20th Floor | 42688 | 42690 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5947 | Form Work For Core 2 Walls | Form Work | Core | 72.90 TO 76.20 | 12th Floor | 42688 | 42689 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5948 | Form Work For 3 Columuns Axis A6/B14 TO B16 & B16/A12 | Form Work | Columuns | 69.60 TO 72.90 | 19th FLoor | 42688 | 42690 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5949 | Form Work For 5Columuns CC4 Axis D1,D2,D3,D4/A9 | Form Work | Columuns | 69.60 TO 72.90 | 19th FLoor | 42688 | 42701 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5950 | Form Work For 2 Columuns DCC1 Axis B13/A11 TO A10 | Form Work | Columuns | 69.60 TO 72.90 | 19th FLoor | 42688 | 42691 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5951 | Form Work For 2 Columuns DCC1*&DCC7 Axis B13/A6 TO A8 | Form Work | Columuns | 69.60 TO 72.90 | 19th FLoor | 42688 | 42691 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5952 | Steel reinforcement For Stair 12 | Steel Reinforcement | Stair | 58.10 TO 61.40 | 16th FLoor | 42689 | 42695 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5953 | Stressing For Cables Of Third Stage Post Tension Slab Residential Tower Axis B19 TO B13/A6 TO A12 | Stressing | Slab | 66.90 | 19th FLoor | 42689 | 42693 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5954 | Grouting For Ducts Of Second Stage Post Tension Slab Residential Tower Axis B9 TO B13/A6 TO A12 | Grout | Slab | 69.60 | 19th FLoor | 42689 | 42690 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5955 | Grouting For Ducts Of First Stage Post Tension Slab Residential Tower Axis B4 TO B9/A6 TO A12 | Grout | Slab | 69.60 | 19th FLoor | 42689 | 42690 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5956 | Grouting For Ducts Of First Stage Post Tension Slab Hotel Tower Axis B1 TO C5/A1 TO A3 | Grout | Slab | 77.90 | 22th Floor | 42689 | 42690 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5957 | Top&Bottom Steel reinforcemnet For First Stage Residential Tower Slab | Steel Reinforcement | Slab | 76.20 | 20th Floor | 42689 | 42690 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5958 | Tendons,Strands,Anchors and Profiles First stage Residential Tower Slab Axis B4 TO B9/A6 TO A12 | Anchor | Slab | 76.20 | 20th Floor | 42689 | 42691 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5959 | Steel reinforcement For Stair 3 Axis B7/A8 | Steel Reinforcement | Stair | 72.90 TO 76.20 | 22th Floor | 42689 | 42691 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5960 | Check Level Of Form Work At 76.20 At Second Stage At Core 3 | Form Work | Core | 76.20 | 20th Floor | 42689 | 42695 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5961 | Check Form Work At 76.20 At Core 3 | Form Work | Core | 76.20 | 20th Floor | 42689 | 42695 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5962 | Check Form Work At 76.20 At Second Stage | Form Work | Core | 76.20 | 20th Floor | 42689 | 42691 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5963 | Form Work For Core 1 Axis | Form Work | Core | 69.60 TO 72.90 | 19th FLoor | 42690 | 42695 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5964 | Steel Reinforcement For Core 1 Axis | Steel Reinforcement | Core | 69.60 TO 72.90 | 19th FLoor | 42690 | 42691 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5965 | Form Work For Core 6 Axis B16/ A2 | Form Work | Core | 77.90 TO 81.27 | 23th Floor | 42690 | 42693 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5966 | Steel Reinforcement For Core 6 Axis B16/A2 | Steel Reinforcement | Core | 77.90 TO 81.27 | 23th Floor | 42690 | 42691 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5967 | Form Work For Stair 6 Axis B11/A8 | Form Work | Stair | 72.90 TO76.20 | 22th Floor | 42691 | 42693 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5968 | Steel reinforcemnt For Columuns and shear Walls Axis B5 TO B8/A6 | Steel Reinforcement | Columun+SH.W | 76.20 TO 79.50 | 21th Floor | 42694 | 42695 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5969 | Steel reinforcement For Columus And Shear Walls Axis B4/A7 TO A11 | Steel Reinforcement | Columun+SH.W | 76.20 TO 79.50 | 21th Floor | 42694 | 42695 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5970 | Steel Reinforcement For Columuns And Shear Walls Axis B6/A8 TO A11 | Steel Reinforcement | Columun+SH.W | 76.20 TO 79.50 | 21th Floor | 42694 | 42695 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5971 | Form Work For Columuns And Shear Wall Axis A11/B6 TO B8 | Form Work | Columun+SH.W | 76.20 TO 79.50 | 21th Floor | 42694 | 42695 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5972 | Form Work For Columuns And Shear Walls Axis A6/B5 TO B8 | Form Work | Columun+SH.W | 76.20 TO 79.50 | 21th Floor | 42694 | 42695 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5973 | Form Work For Columuns And Shear Walls Axis A7 TO A11/B4 | Form Work | Columun+SH.W | 76.20 TO 79.50 | 21th Floor | 42694 | 42695 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5974 | Steel Reinforcement For Pour Strip Between Stage (2&3) | Steel Reinforcement | Stair | 72.90 TO 76.20 | 21th Floor | 42695 | 42701 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5975 | Form Work for Stair Case 7 | Form Work | Stair | 72.90 TO 76.20 | 21th Floor | 42695 | 42695 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5976 | Steel reinforcement For Shea Wall 7 Axis C3/A2 TO A3 | Steel Reinforcement | SH.W | 77.90 TO 81.27 | 23th Floor | 42696 | 42701 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5977 | Form Work For Shear Wall Axis C5/A2TO A3 | Form Work | SH.W | 77.90 TO 81.27 | 23th Floor | 42696 | 42701 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5978 | Steel reinforcement For Shear Wall 6 Axis C4/A2 TO A3 | Steel Reinforcement | SH.W | 77.90 TO 81.27 | 23th Floor | 42696 | 42701 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5979 | Form Work For Shear Wall 6 Axis C4/A2TO A3 | Form Work | SH.W | 77.90 TO 81.27 | 23th Floor | 42696 | 42701 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5980 | Form Work for Shear Wall 8 Axis C2/ A1 TO A3 | Form Work | SH.W | 77.90 TO 81.27 | 23th Floor | 42695 | 42701 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5981 | Steel reinforcement for Shear Wall 8 Axis C2/ A1 TO A3 | Steel Reinforcement | SH.W | 77.90 TO 81.27 | 23th Floor | 42695 | 42701 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5982 | Surface Preparation Prior to repair for Stair 12 to closed NCR 151 Axis | Surface Preparation | Stair | 44.90 TO 48.20 | 12th & 13th | 42695 | 42710 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5983 | Surface Preparation Prior to Apply Repair Work To Close NCR#152 Axis B6/A6 | Surface Preparation | Columun | -11.00 TO -7.20 | B2 Floor | 42696 | 42705 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5984 | Grouting For Ducts Of 3rd Stage Post Tension Slab | Grout | Slab | 69.60 | 19th FLoor | 42696 | 42701 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5985 | Steel reinforcement Work For Core 2 Walls | Steel Reinforcement | core | 76.20 TO 79.50 | 21rth Floor | 42696 | 42703 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5986 | Inspection For Holes and Dowels Fixation For Base Centrifugal Chiller Axis B3,4,5/A12 TO A13 | Chiller | Base Centrifugal Chiller | -3.80 | BOH | 42696 | 42703 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5987 | Steel reinforcement For Base Centrifugal Chiller Axis B3,4,5/A12 TO A13 | Steel Reinforcement | Base Centrifugal Chiller | -3.80 | BOH | 42696 | 42702 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5988 | Bottom Steel Reinforcemnt For Swimming Pool and Slab Around Swimming Pool Axis B1 TO B3/A3 TO A7 | Steel Reinforcement | Swimming Pool | 1.10 | ground Floor | 42696 | 42703 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5989 | Steel reinforcement For Columuns and Shear Walls Axis B19/A1 | Steel Reinforcement | Columuns | 77.90 TO 81.27 | 22th Floor | 42697 | 42701 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5990 | Steel reinforcement for Stair case 7 | Steel Reinforcement | Stair | 72..90 To 76.20 | 21th Floor | 42697 | 42703 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5991 | Bottom,Top Layer and Beam Steel reinforcemnt Work For Part 2 Of P.T Slab | Steel Reinforcement | Slab | 76.20 | 20th Floor | 42697 | 42703 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5992 | Form Work For Columuns and Shear Wlls Axis B19/A1 | Form Work | SH.W | 77.90 TO 81.27 | 22th Floor | 42698 | 42702 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5993 | Post Tension For Part 2 Of P.T Slab | Post Tension | Slab | 76.20 | 20th Floor | 42697 | 42701 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5994 | Check Form Work At 79.50 at Core 5 | Form Work | Core | 79.50 | 21th Floor | 42698 | 42701 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5995 | Check Form Work At 79.50 at First Stage | Form Work | Slab | 79.50 | 21th Floor | 42698 | 42701 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5996 | Form Work For Core 7 Axis C7/A2 TO A3 | Form Work | Core | 81.27 TO 84.50 | Upper Roof | 42698 | 42705 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5997 | Steel reinforcement For Core 7 Axis C7/A2 TO A3 | Steel Reinforcement | Core | 81.27 TO 84.50 | Upper Roof | 42698 | 42704 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5998 | Steel reinforcement For Columun C5 Axis B18/A1 | Steel Reinforcement | Columun | 77.90 TO 81.27 | 23th Floor | 42698 | 42701 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-5999 | Form Work For Columuns C5 Axis B18/A1 | Form Work | Columun | 77.90 TO 81.27 | 23th Floor | 42698 | 42702 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6000 | Check form work at 72.90 at Third stage slab Axis | Form Work | Slab | 72.90 | 19th FLoor | 42700 | 42704 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6001 | Check form work at 72.90 at Core 2 Axis core2 slab | Form Work | Core | 72.90 | 19th FLoor | 42700 | 42704 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6002 | Form Work for stair 12 Axis | Form Work | Stair | 61.40 TO 64.70 | 17th Floor | 42700 | 42704 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6003 | Form Work for Stair 14 Axis | Form Work | Stair | 51.50 TO 54.80 | 14th floor | 42700 | 42701 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6004 | Grouting for ducts of secand stage post tension slab hotel tower Axis C5 To B19 / A1 TO A3 | Grout | Slab | 77.90 | 22th Floor | 42700 | 42701 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6005 | Form Work for stair Case 3 Axis | Form Work | Stair | 76.20 To79.50 | 22th Floor | 42701 | 42704 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6006 | Form Work for stair Case 6 Axis | Form Work | Stair | 72.90 TO 76.20 | 21th Floor | 42697 | 42701 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6007 | Form Work for stair11 Axis B17 /A9 | Form Work | Stair | 69.60 TO 72.90 | 20th Floor | 42701 | 42704 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6008 | Grouting for ducts of first & second post tension slab residential tower Axis B4 TO B13 /A1 TO A13 | Grout | Slab | 72.90 | 20th Floor | 42701 | 42704 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6009 | Steel Reinforcement for stair 6 Axis B11/ A8 | Steel Reinforcement | Stair | 72.90 TO 76.20 | 22th Floor | 42698 | 42703 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6010 | Steel reinforcement For Columun DCC7,DCC1,DCC3 Axis A6/B13,A10/B13,A11/B13 | Steel Reinforcement | Columun | 76.20 TO 79.50 | 22th Floor | 42702 | 42703 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6011 | Form Work For Columuns Axis DCC7,DCC1,DCC3 Axis A6/B13,A10/B13,A11/B13 | Form Work | Columun | 76.20 TO 79.50 | 22th Floor | 42702 | 42705 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6012 | Form Work For Shear Wall9+CC1 Axis A8TO A9/B9 | Form Work | SH.W+CC1 | 76.20 TO 79.50 | 22th Floor | 42702 | 42705 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6013 | Steel reinforcement For Shear Wall9+CC1 Axis A8TO A9/B9 | Steel Reinforcement | SH.W+CC1 | 76.20 TO 79.50 | 22th Floor | 42702 | 42704 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6014 | Form Work For 2 Columuns CC7 Axis A6/B10 TO B12 | Form Work | Columuns | 76.20 TO 79.50 | 22th Floor | 42702 | 42705 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6015 | Steel reinforcement For 2 Columuns CC7 Axis A6/B10 TO B12 | Steel Reinforcement | Columuns | 76.20 TO 79.50 | 22th Floor | 42702 | 42703 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6016 | Form Work For 2 Columuns CC9 Axis A11/B10 TO B12 | Form Work | Columuns | 76.20 TO 79.50 | 22th Floor | 42702 | 42705 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6017 | Steel reinforcement For 2 Columuns CC9 Axis A11/B10 TO B12 | Steel Reinforcement | Columuns | 76.20 TO 79.50 | 22th Floor | 42702 | 42703 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6018 | Form Work For Columuns Axis CC5&CC6 Axis C9 TO C11/A3 | Form Work | Columuns | 76.20 TO 79.50 | 22th Floor | 42702 | 42704 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6019 | Steel reinforcement For Columuns Axis CC5&CC6 Axis C9 TO C11/A3 | Steel Reinforcement | Columuns | 76.20 TO 79.50 | 22th Floor | 42702 | 42703 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6020 | Form Work For Shear Wall 2 Axis C10/A2 TO A3 | Form Work | SH.W | 77.90 TO 81.27 | 23th Floor | 42702 | 42704 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6021 | Steel reinforment For Shear Wall 2 Axis C10/A2 TO A3 | Steel Reinforcement | SH.W | 77.90 TO 81.27 | 23th Floor | 42702 | 42705 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6022 | Top Steel reinforcement For Swimming Pool And Slab Around Swimming Pool Axis B1 TO B4/A3 TO A9 | Steel Reinforcement | Swimming Pool | 1.10 | ground Floor | 42702 | 42705 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6023 | Inspection For Holes and Dowels Fixation For Of Part Of Slab Drop At The 10 th Floor Of Hotel At the Area Between Axes (814 TO 819 ) TO Closed NCR 147 Axis B3,4,5/A12 TO A13 | Holes And Dowels Fixation | NCR | 38.30 | 10th Floor | 42702 | 42704 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6024 | Form Work For Core 2 Axis B14 TO B15/A8 TO A9 | Form Work | Core | 76.20 TO 79.50 | 22th Floor | 42702 | 42704 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6025 | Steel reinforcement for shear Wall 3* Axis C8/ A2 TO A3 | Steel Reinforcement | SH.W | 77.90 TO 81.27 | 23th Floor | 42703 | 42705 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6026 | Form Work for Shear Wall 3* Axis C8 /A2 TO A3 | Form Work | SH.W | 77.90 TO 81.27 | 23th Floor | 42703 | 42708 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6027 | Form Work For Shear Wall 3 Axis C6 /A2 TO A3 | Form Work | SH.W | 77.90 TO 81.27 | 23th Floor | 42703 | 42710 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6028 | Steel rinfocement For Shear Wall 3 Axis C6/A2 TO A3 | Steel Reinforcement | SH.W | 77.90 TO 81.27 | 23th Floor | 42703 | 42704 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6029 | Form Work For Shear Wall 5* Axis C5/A2 TO A3 | Form Work | SH.W | 77.90 TO 81.27 | 23th Floor | 42703 | 42708 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6030 | Steel reinforcement For Shear Wll 5* Axis C5/A2 TO A3 | Steel Reinforcement | SH.W | 77.90 TO 81.27 | 23th Floor | 42703 | 42705 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6031 | Inspection For Installation and Testing Water Bar Of Swimming Pool | Swimming Pool | Swimming Pool | 1.10 | Basement | 42704 | 42705 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6032 | Steel reinforcement fOr Stair 14 | Steel Reinforcement | Stair | 51.50 TO 54.80 | 15th Floor | 42704 | 42705 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6033 | Steel reinforcement For Stair 12 | Steel Reinforcement | Stair | 61.40 TO 64.70 | 17th Floor | 42704 | 42705 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6034 | Stressing Post Tension For Part 2 Of P.T Slab | Stressing | Slab | 76.20 | 20th Floor | 42704 | 42712 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6035 | Steel reinforcemnt Work For Stair Case No.3 | Steel Reinforcement | Stair | 76.20 TO 79.50 | 22th Floor | 42704 | 42709 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6036 | Steel reinforcement For Work Stair Case No.11 | Steel Reinforcement | Stair | 69.60 TO 72.90 | 19th Floor | 42704 | 42714 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6037 | Check Form Work At 81.27 First Stage | Form Work | First Stage | 81.27 | 22th Floor | 42705 | 42708 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6038 | Surface Preparation Prior TO Repair Honeycombs in Core 8 at The 14 th Floor TO Closed NCR 149 | Surface Preparation | Repair | 48.20 TO 51.50 | 14th floor | 42705 | 42712 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6039 | Repair Work For Columun CC7 TO Cloce NCR#152 Axis A8/B3 | Column | NCR | -11.00 TO 7.20 | B2 Floor | 42707 | 42717 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6040 | Tendons Strands Anchors and profiles first stage residential tower slab | Anchor | Slab | 79.50 | 22th Floor | 42707 | 42710 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6041 | Top & Bottom Steel reinforcement For First Stage Residential Tower Slab Axis B4 TO B9/A6 TO A12 | Steel Reinforcement | Slab | 81.27 | 23th Floor | 42707 | 42709 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6042 | Inspection for repair for stair 12 closed NCR 151 Axis | Repair | Stair | 44.90 TO 48.20 | 13th floor | 42708 | 42712 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6043 | Ispection for repair for Core 8 to closed NCR 149 Axis | Repair | Core | 48.20 TO 51.50 | 14th floor | 42708 | 42712 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6044 | Surface Preparation and Repair Work with Steel Fixation According TO (RFI )No.1027 TO Close NCR NO 146 Axis B14 TO B19 | Slab | NCR |  | 11th Floor | 42709 | 42712 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6045 | Steel reinforcement For Core 8 Axis B1/A1 TO A3 | Steel Reinforcement | Core | UP TO 81.27 | 23th Floor | 42709 | 42712 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6046 | Check Form work At 79.50 at core 3 | Form Work | Core | 79.50 | 21th Floor | 42709 | 42712 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6047 | Check Form Work At 79.50 at second Stage | Form Work | Slab | 79.50 | 21th Floor | 42709 | 42712 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6048 | Form Work For Stair 7 | Form Work | Stair | 76.20 TO 79.50 | 22th Floor | 42710 | 42712 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6049 | Form Work For Stair 6 | Form Work | Stair | 76.20 TO 79.50 | 22th Floor | 42710 | 42712 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6050 | Steel reinforcement For Pour Strip 1/2 | Steel Reinforcement | Slab | 76.20 | 20th Floor | 42710 | 42712 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6051 | Steel reinforcement For 2 Columuns CC9 Axis A11/B6 TO B8 | Steel Reinforcement | Columuns | 79.50 TO 82.90 | 23th Floor | 42710 | 42712 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6052 | Form Work For 2 Columuns CC9 Axis A11/B6 TO B8 | Form Work | Columuns | 79.50 TO 82.90 | 23th Floor | 42710 | 42712 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6053 | Steel reinforcement For 3 Columuns CC7 Axis A6/B5 TO B6 & B8 | Steel Reinforcement | Columuns | 79.50 TO 82.90 | 23th Floor | 42710 | 42712 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6054 | Form Work For 3 Columuns CC7 Axis A6/B5 TO B6 & B8 | Form Work | Columuns | 79.50 TO 82.90 | 23th Floor | 42710 | 42712 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6055 | Steel reinforcement For 4 Columuns CC7 Axis B4/A7 TO A8&A9,A10,A11 | Steel Reinforcement | Columuns | 79.50 TO 82.90 | 23th Floor | 42710 | 42712 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6056 | Form Work For 4 Columuns CC7 Axis B4/A8 TO A9&A10 TO A11 | Form Work | Columuns | 79.50 TO 82.90 | 23th Floor | 42710 | 42712 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6057 | Bottom,Top Layer and Beam Steel reinforcement Work For Part 3 Of P.T Slab | Steel Reinforcement | Slab | 72.90 | 19th FLoor | 42711 | 42712 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6058 | Tendons ,Strands,Anchors and Profiles 3rd stage R.D tower slab Axis | Anchor | Slab | 72.90 | 19th FLoor | 42711 | 42714 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6059 | Inspectino for repair at hotel tower for 5th floor Axis | Repair | Slab | 25.10 | 5th | 42711 | 42724 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6060 | Inspectino for repair at hotel tower for 4th floor Axis | Repair | Slab | 21.80 | 4th | 42711 | 42719 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6061 | Inspection for repair for connection between slab and shear wall 1 to closed NCR 150 | Repair | Slab | 48.20 | 13th floor | 42711 | 42724 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6062 | Surface prepartion for the connection between slab and shear wall 1 to closed NCR 150 Axis | Repair | Slab | 48.20 | 13th floor | 42711 | 42724 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6063 | Inspection For Repair At Hotel For 6th Floor | Repair | Slab | 28.40 | 6th | 42712 | 42724 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6064 | Tendons,Strands,Anchors and Profiles First Stage Hotel Tower Slab Axis B1 TO C5/A1 TO A3 | Anchor | Slab | 81.27 | 23th Floor | 42714 | 42717 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6065 | Top&Bottom Steel reinforcement For First Stage Hotel Tower Slab Axis B1 TO C5/A1 TO A3 | Steel Reinforcement | Slab | 81.27 | 23th Floor | 42714 | 42717 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6066 | Form Work FOR Core 8 Axis B1/A1 TO A3 | Form Work | Core | 81.27 | 23th Floor | 42714 | 42719 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6067 | Steel reinforcement For Work For Stair Case No (6&7) | Steel Reinforcement | Stair | 76.20 TO 79.50 | 19th FLoor | 42715 | 42724 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6068 | Steel reinforcemnet For Columuns 4 CC7,6CC4,CC9,DCC1&DCC1* | Steel Reinforcement | Columns | 72.90 TO 76.20 | 20th Floor | 42715 | 42717 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6069 | Form Work For Columuns 4CC7,6CC4,DCC1&DCC1* Axis B13 TO B19/A6 TO A12 | Form Work | Columns | 72.90 TO 76.20 | 20th Floor | 42715 | 42717 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6070 | Form Work For Core Walls | Form Work | Core | 72.90 TO 76.20 | 20th Floor | 42715 | 42722 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6071 | Steel reinforcement Work For Core Walls | Steel Reinforcement | Core | 72.90 TO 76.20 | 20th Floor | 42715 | 42719 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6072 | Form Work For 3 Columuns CC7 and 1 Columun CC9 Axis A12,A6&B16/A6&B14 TO B4/A11 | Form Work | Columuns | 72.90 TO 76.20 | 20th Floor | 42717 | 42719 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6073 | Form Work For 6 Columuns CC4 Axis D1,D2,D3,D4/A9&B16 | Form Work | Columuns | 72.90 TO 76.20 | 20th Floor | 42717 | 42719 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6074 | Stressing For Cables Of Third Stage Post Tension Slab Residential Tower Axis B19 TO B13/A6 TO A12 | Stressing | Slab | 72.90 | 20th Floor | 42717 | 42719 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6075 | Stressing for cables of first stage post tension slab residential tower Axis B9 TO B4 / A6 TO A12 | Stressing | Slab | 79.50 | 22th Floor | 42717 | 42719 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6076 | Form work for stair 4 Axis A10 /B7 | Form Work | Stair | 5.40 TO 10.30 | 2nd | 42717 | 42719 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6077 | TOP & Bottom Steel Reinforcement For Second Stage Tower Slab Axis B13 TO B9/A6 TO A12 | Steel Reinforcement | Slab | 79.50 | 22 th Floor | 42718 | 42719 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6078 | Tendons,Strands,Anchors and Profiles Second Stage Residential Tower Slab Axis B13 TO B9/A6 TO A12 | Anchor | Second Stage | 79.50 | 22th Floor | 42718 | 42719 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6079 | Inspection For Repair At 14th Floor Hotel Tower | Repair |  | 51.50 | 14th floor | 42719 | 42726 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6080 | Steel reinforcement For Fence Wall Along Axis C1/A3 TO A6 | Steel Reinforcement | Fence Wall | 1.10 TO 4.30 | ground Floor | 42719 | 42726 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6081 | Steel reinforcement For Stair Case 4 | Steel Reinforcement | Stair | 5.40 TO 10.30 | 1st | 42719 | 42722 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6082 | Form Work for Fence Wall along Axis C1 | Form Work | Fence Wall | 1.10 TO 4.30 | GF | 42721 | 42724 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6083 | Steel reinforcement for pour strip 2/3 residential tower slab Axis B13 /A6 TO A12 | Steel Reinforcement | Pour strip | 72.90 | 20th Floor | 42721 | 42722 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6084 | Form Work for Columns 2CC9,2CC7,DCC3,DCC1,DCC7 &SH.W9 Axis B13 TOB9 / A6 TO A11 | Form Work | Columns | 79.50 TO 82.90 | 22th Floor | 42722 | 42726 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6085 | Steel reinforcement For Columuns(2 CC9,2CC7,DCC3,DCC1,DCC7&SH.W9 | Steel Reinforcement | Columns | 79.50 TO 82.90 | 22th Floor | 42722 | 42724 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6086 | Grouting For Ducts Of Third Stage Post Tension Slab Residential Tower Axis B13 TO B19/A1 TO A3 | Grout | Slab | 72.90 | 20th Floor | 42723 | 42724 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6087 | Steel reinforcement For Stair 1 Columuns Axis A10 TO A9/B3 TO B4 | Steel Reinforcement | Stair | 1.10 TO 4.10 | ground Floor | 42724 | 42726 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6088 | Stressing Post Tension For Part 2 Of P.T Slab | Stressing | Slab | 79.50 | 21th FLoor | 42724 | 42726 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6089 | Form Work For Core 5 | Form Work | Core | 79.50 TO 82.90 | 22th Floor | 42725 | 42733 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6090 | Steel reinforcement For Core 5 | Steel reinforcement | Core | 79.50 TO 82.90 | 22th Floor | 42725 | 42732 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6091 | Form Work For Core 5 | Form Work | Core | 23.40 | 5th | 42725 | 42726 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6092 | Steel reinforcement For Core 5 | Steel reinforcement | Core | 23.40 | 5th | 42725 | 42726 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6093 | Coring For MEP Opeining Of Coupling Beams At Core 5 (Trn-1159&1210) | Opening | Core | 23.40 | 5th | 42725 | 42744 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6094 | Steel Reinforcement For Columun and Shear Walls | Steel Reinforcemnt | Columun | 1.10 TO 4.30 | BoH | 42725 | 42732 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6095 | Check Form Work at 76.20 at Core2 | Form Work | Core | 76.20 | 20th Floor | 42725 | 42726 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6096 | Check Form Work At 76.20 At third Part | Form Work | Slab | 76.20 | 20th Floor | 42725 | 42726 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6097 | Steel reinforcement For Fence Columuns and Shear Walls Axis A8 TO A12/C1 | Steel reinforcement | Fence Wall | 1.10 TO 4.30 | BOH | 42726 | 42728 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6098 | Surface Preparation and Repair Work Axis B1 TO B19/A1 to A3 | Surface Preparation | Repair | 28.40 | 7th | 42726 | 42732 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6099 | Surface Preparation and Repair Work Axis B1 TO B19/A1 to A3 | Surface Preparation | Repair | 37.30 | 8th | 42726 | 42732 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6100 | Surface Preparation and Repair Work Axis B2 TO B18 | Surface Preparation | Repair | 54.80 | 15th Floor | 42726 | 42756 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6101 | Form Work For Stair Case No 12 | Form work | Stair | 64.70 TO 68.00 | 18th FLoor | 42726 | 42732 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6102 | Form Work Stair Case No 14 | Form work | Stair | 54.80 TO 58.10 | 15th Floor | 42726 | 42732 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6103 | Form Work Fence Wall along Axis C1 /A6 TO A8 | Form Work | Fence Wall | 1.10 TO 4.30 | GF | 42726 | 42732 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6104 | Form Work Fence Wall along Axis B1 : C1 /A1 TO A3 | Form Work | Fence Wall | 1.10 TO 4.30 | GF | 42726 | 42732 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6105 | Inspection For Repair at Hotel For 9th Floor | Repair |  | 35.00 | 9th | 42729 | 42740 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6106 | Top & Bottom Steel reinforcement For Stair 1 Roof | Steel reinforcement | Stair | 4.10 | GF | 42729 | 42732 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6107 | Form Work For Stair 1 Roof &Columuns Axis B3 TO B4/A9 TO A10 | Form Work | Stair | 4.10 | GF | 42729 | 42732 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6108 | Steel reinforcement For Fence Wall Along Axis C1/A8 TO A15 | Steel reinforcement | Fence Wall | 1.10 TO 4.30 | GF | 42730 | 42732 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6109 | Form Work For Fence Wall Along Axis C1/A8 TO A15 | Form Work | Fence Wall | 1.10 TO 4.30 | GF | 42730 | 42738 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6110 | Steel reinforcement For Stair 14 Axis B17/A2 | Steel reinforcement | Stair | 54.80 TO 58.10 | 15th FLoor | 42730 | 42735 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6111 | Steel reinforcement Work For Core Walls #3 | Steel reinforcement | Core | 79.50 TO 82.90 | 22th Floor | 42731 | 42732 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6112 | Steel reinforcement Work For Stair Case NO 11 | Steel reinforcement | Stair | 72.90 TO 76.20 | 18th FLoor | 42731 | 42732 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6113 | Steel reinforcement For Commun Pour Strip 1/2 Axis A10/B7 | Steel reinforcement | Pour strip | 79.50 | 22th Floor | 42731 | 42732 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6114 | Steel reinforcement For Fence Wall Along Axis C1/A3 TO A15 | Steel reinforcement | Fence Wall | 1.10 TO 4.30 | ground Floor | 42731 | 42732 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6115 | Form Work For Stair 11 Axis B16 TO B18/A9 TO A7 | Form Work | Stair | 72.90 TO 76.20 | 18th FLoor | 42731 | 42732 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6116 | Steel reinforcement For Stair 12 Axis B1/A2 | Steel reinforcement | Stair | 64.70 TO 68.00 | 19th Floor | 42732 | 42735 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6117 | Inspection For Repair At Hotel Tower For 10 th Floor | Repair | Repair | 38.30 | 10th Floor | 42732 | 42740 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6118 | Tendons Strands,Anchors And Profiles 3rd Stage R.D Tower Slab Axis B13 TO B20/Between A5&A6 TO Between A12 TO A13 | Anchor | Slab | 76.20 | 20th Floor | 42736 | 42742 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6119 | Bottom,Top Layer and Beam Steel reinforcement Work For Part 3 Of P.T Slab | Steel Reinforcement | Slab | 76.20 | 21th Floor | 42736 | 42738 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6120 | Surface Preparation and Repair Work | Surface Preparation | Repair | 41.60 | 11th Floor | 42736 | 42749 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6121 | Steel reinforcemnt For Plasing Boom Opeining At Hotel Axis B13/A3 | Steel reinforcement | Slab Openinig | 41.60 | 11th Floor | 42736 | 42754 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6122 | Check Form Work For Slab At Level 82.90 Core 5 | Form Work | Core | 82.90 | 23th Floor | 42737 | 42752 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6123 | Check Form Work For Slab At Level 82.90 First Stage | Form Work | Slab | 82.90 | 23th Floor | 42737 | 42738 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6124 | Tower Crane Opining From Work For Core Walls | Opening | Core | 20.10 TO23.40 | 4th | 42738 | 42756 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6125 | Tower Crane Opining Steel reinforcemnt For Core Walls | Opening | Core | 20.10 TO23.40 | 4th | 42738 | 42740 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6126 | Inspection For Repair At Hotel For 12th Floor | Repair | At Hotel | 44.90 | 12th Floor | 42738 | 42750 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6127 | Inspection For Repair at Hotel For 13th Floor | Repair | At Hotel | 48.20 | 13th floor | 42738 | 42750 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6128 | Form Work For Core Walls | Form work | Core | 79.50 TO 82.90 | 22th Floor | 42739 | 42742 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6129 | Grouting For Ducts Of First Stage Post Tension Slab Residential Tower | Grout | Slab | 79.50 | 22th Floor | 42739 | 42743 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6130 | Surface Preparation Prior To Repair At Hotel For 12th Floor | Repair | Syrface Preparation | 44.90 | 12th Floor | 42739 | 42745 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6131 | Surface Preparation Prior To Repair At Hotel For 13th Floor | Repair | Syrface Preparation | 48.20 | 13th floor | 42739 | 42745 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6132 | Form Work For Stair 14 Axis B17/A2 | Form Work | Stair | 58.10 TO 61.40 | 16th Floor | 42740 | 42743 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6133 | Form Work For Stair 12 Axis B1/A2 | Form Work | Stair | 68.00 TO 71.30 | 19th Floor | 42740 | 42743 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6134 | Surface Preparation Prior TO Repair At Hotel Tower | Repair | Surface Preparation | 58.10 | 16th Floor | 42744 | 42754 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6135 | Surface Preparation Prior TO Repair At Hotel Tower | Repair | Surface Preparation | 54.80 | 15th Floor | 42744 | 42754 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6136 | Steel reinforcement For 3 Columuns CC7 Axis A6/B14 To B16&B16/A12 | Steel Reinforcemnt | Columun | 76.20 To 79.50 | 21th Floor | 42745 | 42745 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6137 | Form Work For 3Columuns CC7 Axis A6/B14 TO B16&B16/A12 | Form Work | Columun | 76.20 To 79.50 | 21th Floor | 42745 | 42758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6138 | Steel reinforcement For 5 Columuns CC4 Axis D1 TO D2 &D3 TO D4/A9 | Steel Reinforcemnt | Columun | 76.20 To 79.50 | 21th Floor | 42745 | 42749 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6139 | Form work For 5 Columuns CC4 Axis D1 TO D2 &D3 TO D4/A9 | Form Work | Columun | 76.20 To 79.50 | 21th Floor | 42745 | 42758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6140 | Steel reinforcement For 2 Columuns DCC1* & DCC7 Axis B13/A6 TO A8 | Steel Reinforcemnt | Columun | 76.20 To 79.50 | 21th Floor | 42745 | 42745 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6141 | Form Work For 2 Columuns DCC1*&DCC7 Axis B13/A6 TO A8 | Form Work | Columun | 76.20 To 79.50 | 21th Floor | 42745 | 42758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6142 | Steel reinfrocement For 2 Columuns CC9&CC4 Axis B14/A11&B16/A10 | Steel Reinforcemnt | Columun | 76.20 To 79.50 | 21th Floor | 42745 | 42745 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6143 | Form Work For 2 Columuns CC9 TO CC4 Axis B14/A11 & B16/A10 | Form Work | Columun | 76.20 To 79.50 | 21th Floor | 42745 | 42758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6144 | Steel reinforcement For 2 Columuns DCC1 Axis B13/A11 TO A10 | Steel Reinforcemnt | Columun | 76.20 To 79.50 | 21th Floor | 42745 | 42745 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6145 | Form Work For 2Columun DCC1 Axis B13/A11 TO A10 | Form Work | Columun | 76.20 To 79.50 | 21th Floor | 42745 | 42758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6146 | Form Work For Core 1 Axis B17/A9 | Form Work | Core | 76.20 TO 79.50 | 21th Floor | 42746 | 42758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6147 | Steel reinforcement For Core 1 Axis B17/A9 | Steel reinforcement | Core | 76.20 TO 79.50 | 21th Floor | 42746 | 42749 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6148 | Steel reinforcemnt For Stair 12 Axis B17/A2 | Steel reinforcement | Stair | 68.00 TO 71.30 | 19th Floor | 42746 | 42752 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6149 | Check Form Work For Slab At Level 82.90 Second Stage | Form Work | Slab | 82.90 | 22th Floor | 42746 | 42752 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6150 | Check Form Work For Slab At Level 82.90 Core Second Stage | Form Work | Slab | 82.90 | 22th Floor | 42746 | 42758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6151 | Surface Preparation Prior TO Repair at Soffit Slab Around Swimming Pool To Closed NCR#174 | Repair | Slab | 1.10 | BOH | 42749 | 42756 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6152 | Steel reinforcement For Stair 14 Axis B17/A2 | Steel reinforcement | Stair | 58.10 TO 61.40 | 16th Floor | 42746 | 42752 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6153 | Steel reinforcement For Fence Columuns Along axis C1/A1 TO A15 | Steel reinforcement | Columuns | 4.30 UP TO 9.20 | ground Floor | 42749 | 42752 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6154 | Stressing For Cable Of Third Stage Post Tension Slab Residential Tower Axis B13 TO B19/A6 TO A12 | Stressing | Slab | 76.20 | 21th Floor | 42751 | 42754 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6155 | Grouting For Ducts Of First Stage Post Tension Slab Residential Tower Axis B4 TO B9/A6 TO A12 | Grout | Slab | 79.50 | 22 th Floor | 42751 | 42752 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6156 | Grouting For Ducts Of Secnd Stage Post Tension Slab Residential Tower Axis B1 TO B9/A6 TO A12 | Grout | Slab | 79.50 | 22 th Floor | 42751 | 42752 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6157 | Inspection For Repair at Hotel Tower For 18th Floor Axis B1 TO B19/A1 TO A3 | Repair |  | 64.70 | 18th Floor | 42751 | 42761 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6158 | Inspection For Repair At Hotel Tower For 17th Floor Axis B1 TO B19/A1 TO A3 | Repair |  | 61.40 | 17th Floor | 42751 | 42761 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6159 | Inspection For Repair AT Hotel Tower For 16 th Floor Axis B1 TO B19/A1 TO A3 | Repair |  | 58.10 | 16th floor | 42751 | 42756 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6160 | Surface Preparation Prior To Repair At Hotel Tower For 17th Floor | Repair | Surface Preparation | 61.40 | 17th Floor | 42751 | 42761 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6161 | Inspection For Repair at Soffit Slab Around Swimming Pool To Closed NCR#174 | Repair | Swimming Pool | 1.10 | BOH | 42751 | 42756 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6162 | Surface Preparation Prior To Rapair At Hotel Tower For 18th Floor | Repair | Surface Preparation | 64.70 | 18th Floor | 42751 | 42761 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6163 | Surface prepartion prior to repair at residential tower for 4th floor apartments 7,8,9,10 | Repair | Surface Preparation | 20.10 To 23.40 | 4th | 42752 | 42808 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6164 | inspection for repair at residential tower for 4th floor apartments 7,8,9,10 | Repair | Surface Preparation | 20.10 To 23.40 | 4th | 42752 | 42808 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6165 | inspection for repair at residential tower for 4th floor apartments 43,4,5,6 | Repair | Surface Preparation | 21.10 TO 23.40 | 4th | 42752 | 42808 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6166 | Surface prepartion prior to repair at residential tower for 4th floor apartments 43,4,5,6 | Repair | Surface Preparation | 20.10 | 4th | 42752 | 42780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6167 | Steel Reinforcement For Stair 4 Axis B6 TO B8/A8 TO A10 | Steel reinforcement | Stair | 10.30 TO 15.20 | 2nd | 42753 | 42758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6168 | Form Work For Stair 4 Axis B1 TO B4/A3 To A9 | Form Work | Stair | 10.30 TO 15.20 | 2nd | 42753 | 42756 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6169 | Steel reinforcement For Core 5 Opining Axis B6 TO B8/A8 TO A10 | Steel reinforcement | Core | 20.10 TO 23.40 | 3rd | 42753 | 42761 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6170 | Steel reinforcement For Cantilevers Of Roof Slab Residential Tower Axis B4 To B9/A6 TO A12 | Steel reinforcement | Slab | 82.90 | 23th Floor | 42753 | 42758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6171 | Bottom Steel Reinforcemnt For First Stage Residential Tower Slab Axis B4 To B9/A6 To A12 | Steel reinforcement | Slab | 82.90 | 23th Floor | 42753 | 42758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6172 | Check Form Work at 79.50 at Core 2 | Form Work | Core | 79.50 | 21th Floor | 42756 | 42758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6173 | Check Form Work at 79.50 at third stage | Form Work | Slab | 79.50 | 21th Floor | 42756 | 42756 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6174 | Form Work For Stair 14 Axis B17/A2 | Form Work | Stair | 61.40 TO 64.70 | 17th Floor | 42756 | 42761 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6175 | Steel reinforcement For Fence Beams (B30X60)along Axis B1 TO C0/A1 TO A10 | Steel reinforcement | Fence | 6.85 | Ground Floor | 42756 | 42761 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6176 | Form Work For Fence Beam(B 30X60)along Axis B1 TO C1/A10 TO A10 | Form Work | Fence | 6.85 | Ground Floor | 42756 | 42758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6177 | Form Work For Flence Columuns Along Axis B1 To C1/A1 TO A10 | Form Work | Fence | 4.30 TO 6.85 | ground Floor | 42756 | 42758 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6178 | Form Work For Stair 12 Axis B1/A1 TO A3 | Form Work | Stair | 71.30 TO 74.60 | 21th Floor | 42757 | 42759 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6179 | Steel reinforcement For Pour Strip 2/3 Residentaial Tower Slab Axis B13/A6 TO A12 | Steel reinforcemnt | Slab | 76.20 | 22 th Floor | 42759 | 42766 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6180 | Steel Reinforcement for stair 11 Axis B17/A9 | Steel reinforcemnt | Stair | 76.20 TO 79.50 | 23th Floor | 42759 | 42766 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6181 | Form Work For Stair 11 Axis B17/A9 | Form Work | Stair | 76.20 TO 79.50 | 22th Floor | 42759 | 42761 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6182 | Inspection For Repair at Hotel Tower For 20th Floor | Repair | Repair | 71.30 | 20th Floor | 42759 | 42775 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6183 | Surface Prepration Prior To Repair at Hotel Tower For 20th Floor | Repair | Surface Preparation | 71.30 | 20th Floor | 42759 | 42766 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6184 | Inspection For Repair at Hotel Tower For 19th Floor | Repair | Repair | 68.00 | 19th Floor | 42759 | 42766 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6185 | Surface Preparation Prior To Repair at Hotel Tower For 19th Floor | Repair | Surface Preparation | 68.00 | 19th Floor | 42759 | 42761 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6186 | Inspection For Repair at Residential Tower For 16th Floor | Repair | Repair | 59.70 | 16th Floor | 42759 | 42780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6187 | Surface Preparation Prior At repair at Residential Tower For 16 th Floor | Repair | Surface Preparation | 59.70 | 16th Floor | 42759 | 42774 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6188 | Inspection For Repair At Residential Tower For 15th Floor | Repair | Repair | 56.40 | 15th Floor | 42759 | 42780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6189 | Surface Preparation Prior At Repair at Residential Tower For 15 th Floor | Repair | Repair | 56.40 | 15th Floor | 42759 | 42774 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6190 | Inspection For Repair At Residential tower For 14th Floor | Repair | Repair | 53.10 | 14th floor | 42759 | 42780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6191 | Surface Preparation Prior To Repair At Residential Tower For 14th Floor | Repair | Surface Preparation | 53.10 | 14th floor | 42759 | 42780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6192 | Inspection For Repair At Residential Tower For 13th Floor | Repair | Repair | 49.80 | 13th floor | 42759 | 42780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6193 | Surface Preparation To Repair at Residentail Tower For 13th Floor | Repair | Repair | 49.80 | 13th floor | 42759 | 42780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6194 | Tendons, strands, anchors ,and profiles for third stage residential tower slab Axis B13 TO B 19 /A6 TO A12 | Anchor |  | 79.50 | 22th Floor | 42760 | 42761 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6195 | Inspection For Repair at Residential Tower For 4th Floor Apartments 1/2 | Repair | Repair | 20.10 | 4th | 42759 | 42808 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6196 | Surface Preparation Prior to Repair at Residential Tower For 4th Floor Apartments 1/2 | Repair | Repair | 20.10 | 4th | 42759 | 42780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6197 | Form Work for fence beam (B 30X60 ) along Axis C1 / A10 TO A15 | Form Work | Fence | 6.85 | GF | 42760 | 42764 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6198 | Form Work for fence columns along Axis C1 /A10 TO A15 | Form work | Fence | 4.30 TO 6.85 | GF | 42760 | 42764 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6199 | Bottom Steel Reinforcemnt For third Stage Residential Tower Slab Axis B13 To B19/A6 To A12 | Steel Reinforcement | Slab | 79.50 | 22th Floor | 42760 | 42764 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6200 | Top Steel Reinforcement For third stage RD tower Slab Axis A6 TO A12 /B13 TO B19 | Steel Reinforcement | Slab | 79.50 | 22th Floor | 42760 | 42764 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6201 | Steel reinforcement for stair 12 Axis B1 /A2 | Steel Reinforcement | Stair | 71.30 TO 74.60 | 21th Floor | 42761 | 42766 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6202 | Surface prepartaion priopr to repair of concrete at R.W for Apartments 7.8.9.10 | Repair |  |  | 6th | 42763 | 42848 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6203 | Inspection for repair of concrete at R.W for Apartments 7.8.9.10 | Repair | Concrete |  | 5th | 42763 | 42848 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6204 | Surface prepartaion priopr to repair of concrete at R.W for Apartments 7.8.9.10 | Repair | Concrete |  | 5th | 42763 | 42848 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6205 | Inspection for repair of concrete at R.W for Apartments 7.8.9.10 | Repair | Concrete |  | 6th | 42763 | 42848 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6206 | Top Steel reinforcement For First Stage Residentail Tower Roof Slab Axis B4 TO B9/A6 TO A12 | Steel reinforcement | Slab | 82.90 | 23th Floor | 42764 | 42766 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6207 | Tendons,Strands,Anchors and Profiles For First Stage Residential Tower Roof Slab Axis B4 TO B9/A6 TO A12 | Anchor | Slab | 82.90 | 23th Floor | 42764 | 42766 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6208 | Form Work For Stair 7 Axis B10 TO B11/A10 | Form Work | Stair | 79.50 TO 82.90 | 23th Floor | 42765 | 42766 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6209 | Steel reinforcement For Stair 7 Axis B10 TO B11/A10 | Steel reinforcement | Stair | 79.50 TO 82.90 | 23th Floor | 42765 | 42771 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6210 | Surface Preparation Prior TO Repair at Hotel For 21th Floor | Repair | Surface Preparation | 74.60 | 21th Floor | 42766 | 42778 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6211 | Inspection For Repair at Hotel Tower For 21th Floor Axis B1 TO B19/A1 TO A3 | Repair | Repair | 74.60 | 21th Floor | 42766 | 42779 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6212 | Steel reinforcemnt For Stair 14 Axis B17/A2 | Steel reinforcement | Stair | 61.40 TO 64.70 | 17th Floor | 42766 | 42771 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6213 | Top and Bottom Steel reinforcement For Second Stage Residentail Tower Roof Slab Axis B9 To B13/A6 To A12 | Steel reinforcement | Slab | 82.90 | 23th Floor | 42767 | 42771 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6214 | Tendons,Strands,Anchors and Profiles For Second Stage Residential Tower Roof Slab Axis B9 TO B13/A6 TO A12 | Anchor | Slab | 82.90 | 23th Floor | 42767 | 42771 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6215 | Steel reinforcement Work for core Walls #2 | Steel reinforcement | Core | 79.50 TO 82.90 | 22th | 42771 | 42774 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6216 | Steel reinforcement For Work Core Walls#1 | Steel reinforcement | Core | 79.50 TO 82.90 | 22th | 42771 | 42775 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6217 | Form Work For Core Walls 1 | Form Work | Core | 79.50 TO 82.90 | 22th | 42771 | 42777 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6218 | Steel Reinforcement For Columuns and Shear Walls (6CC4),(4CC7),(CC9),(2DCC1)&(DCC1*) | Steel reinforcemnt | Columuns | 77.90 TO 81.27 | 22th Floor | 42771 | 42775 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6219 | Form Work For Columuns and Shear Wall (6CC4),(4CC7),(CC9),(2DCC1)&(DCC1*) | Form Work | Columuns | 79.50 TO 82.70 | 22th Floor | 42771 | 42779 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6220 | Surface Preparation Prior To Repair Work | Repair | Surface Preparation | .50 TO 7.20 | B2 Floor | 42771 | 42791 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6221 | Form Work For Stair 14 | Form Work | Stair | 64.70 To 68.00 | 18th Floor | 42772 | 42774 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6222 | Form Work For Stair 12 Axis B1/A2 | Form Work | Stair | 74.60 TO 77.90 | 22th Floor | 42772 | 42774 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6223 | Surface Preparation Prior To damp Proofing under slab on grade Axis B18 To B21/A1 To A15 | Surface Preparation | Slab | -11.00 | B2 Floor | 42772 | 42775 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6224 | Steel reinforcement For Core 5 Beams After MEP Opening at 4th Floor | Steel reinforcement | Core | 201.10 TO 23.40 | 4th | 42773 | 42775 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6225 | Form Work For Fence Columun and Beams Axis B1 TO C1/A1 TO A10 | Form Work | Fence | 6.85 TO 9.20 | Ground Floor | 42773 | 42774 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6226 | Steel reinforcement For Fence Columuns and Beams Axis B1 TO C1/A1 TO A10 | Steel reinforcement | Fence | 6.85 TO 9.20 | Ground Floor | 42773 | 42773 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6227 | Steel reinforcement for equipment bases on the residential roof part 1 Axis A6 TO A12 / B4 TO B9 | Steel reinforcement | Bases | 82.90 | 23th Floor | 42774 | 42775 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6228 | Form work for equipment bases on the residential roof part 1 | Form Work | Bases | 82.90 | 23th Floor | 42774 | 42775 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6229 | Form Work For Core 2 | Form Work | Core | 79.50 TO 82.90 | 23th Floor | 42774 | 42775 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6230 | Steel reinforcemnt For Stair 14 Axis B17/A2 | Steel reinforcemnt | Stair | 64.70 To 68.00 | 18th Floor | 42778 | 42786 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6231 | Steel Reinforcemnt For 12 Axis B1/A2 | Steel reinforcemnt | Stair | 74.60 TO 77.90 | 22 th Floor | 42778 | 42787 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6232 | Stressing For Cable Of Third Stage Post Tension Slab Residential Tower Axis B1 to C5/A1 to A3 | Stressing | Slab | 81.27 | 23 th Floor | 42778 | 42794 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6233 | Tendons,Strands,Anchors and Profiles second stage hotel tower slab Axis A1 to A3/C5 To B19 | Anchor | Slab | 81.27 | 23 th Floor | 42778 | 42780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6234 | Top and bottom Steel reinforcemnt For second Stage Hotel tower Axis A1 to A3/C5 to B19 | Steel reinforcemnt | Slab | 81.27 | 23 th Floor | 42778 | 42780 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6235 | Apply Primer Coat of damp Proofing under slab on grade Axis B19 to B21/A1 to A15 | Damp proofing | Slab | -11.00 | B2 Floor | 42778 | 42779 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6236 | Surface Prepration Prior To damp proofing under Slab on grade Axis B16 To B18/A1 To A7 | Damp proofing | Slab | -11.00 | B2 Floor | 42778 | 42779 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6237 | Stressing for Cable Of First Stage Post tension Slab Residential Tower Axis B4 to B9/A6 to A12 | Stressing | post tension | 82.90 | 23 th Floor | 42778 | 42785 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6238 | Stressing For Cable Of second stage Post Tension Residential Tower Axis B13 To B9/A6 To A12 | Stressing | post tension | 82.90 | 23 th Floor | 42778 | 42786 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6239 | Stressing for cable of third stage Post Tension Slab Residentail Tower Axis B13 to B19/A6 to A12 | Stressing | post tension | 79.50 | 22th Floor | 42778 | 42778 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6240 | Steel reinforcemnt for Pour Strip (2/3) Residentail Tower Slab Axis B13/A6 to A12 | Steel reinforcemnt | Slab | 79.50 | 22th Floor | 42778 | 42779 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6241 | Apply First Coat of damp proofing under slab on grade | Damp proofing | Slab | -11.00 | B2 Floor | 42779 | 42780 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6242 | Apply Primer Coat of damp Proofing under slab on grade Axis B16 TO B18/A1 TO A7 | Damp proofing | Slab On Grade | -11.00 | B2 Floor | 42779 | 42780 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6243 | Surface Preparation Prior To Damp Proofing under slab on grade Axis B16 To B18/A7 To A15 | Damp proofing | Slab On Grade | -11.00 | B2 Floor | 42779 | 42791 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6244 | Form Work For Fence Columuns and Beams Axis C1/A10 TO A15 | Form Work | Columuns and Beams | 6.85 TO 9.20 | Ground Floor | 42779 | 42782 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6245 | Steel reinforcement For Fence Columuns and Beams Axis C1/A10 TO A15 | Steel reinforcement | Fence | 6.85 TO 9.20 | Ground Floor | 42779 | 42780 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6246 | Inspection For repair of concrete at Residentail Tower at 20th Floor | Repair | Concrete | X | 20th Floor | 42780 | 42808 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6247 | Surface Preparation Prior TO Repair of Concrete at Residential at 20th Floor | Repair | Surface Preparation | X | 20th Floor | 42780 | 42792 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6248 | Inspection For Repair Of Concrete at Residentail Tower at 19th Floor | Repair | Concrete | X | 19th Floor | 42780 | 42808 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6249 | Surface Preparation Prior to Repair of Concrete at Residential at 19th Floor | Repair | Surface Preparation | X | 19th Floor | 42780 | 42792 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6250 | Inspection For Repair Of Concrete at Residentail Tower at 18th Floor | Repair | Concrete | X | 18th Floor | 42780 | 42808 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6251 | Surface Preparation Prior to Repair of Concrete at Residential At 18th Floor | Repair | Surface Preparation | X | 18th Floor | 42780 | 42792 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6252 | Inspection For Repair of Concrete at Residential Tower at 17th Floor | Repair | Concrete | X | 17th Floor | 42780 | 42808 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6253 | Surface Preparation Prior To Repair Of Concrete At Residential at 17th Floor | Repair | Concrete | X | 17th Floor | 42780 | 42792 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6254 | Surface Preparation Prior To Repair of Concrete at Residential at 16th Floor | Repair | Surface Preparation | X | 16th Floor | 42780 | 42780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6255 | Surface Peparation Prior to Repair Of Concrete at Residential at 15th Floor | Repair | Surface Preparation | X | 15th Floor | 42780 | 42780 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6256 | Steel Reinforcement For Beams B1 at 5th Floor In Core 5 Near Axis A10 | Steel reinforcemnt | Core | X | 5th | 42780 | 42786 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6257 | Inspection For Holes and Dowels Fixation For Beam B1 At 5th Floors in Core 5 Near Axis A10 | Holes | Core | X | 5th | 42780 | 42785 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6258 | Apply First Coat of damp proofing under slab on grade | Damp proofing | Slab | -11.00 | B2 Floor | 42782 | 42785 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6259 | Apply Second Coat Of Damp Proofing Under Slab On Grade Axis B21 To B19/A1 TO A15 | Damp proofing | Second | -11.00 | B2 Floor | 42782 | 42785 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6260 | Apply Primer Coat of Damp Proofing under slab on grade Axis B19 To B16/A7 To A15 | Damp proofing | Slab | -11.00 | B2 Floor | 42782 | 42785 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6261 | Steel reinforcement For Pour Strip Hotel Tower Slab Axis C5/A1 TO A3 | Steel reinforcement | Slab | 77.90 | 22th Floor | 42782 | 42786 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6262 | Form Work for Stair 4 Axis A10 /B7 to B8 | form work | Stair | 15.20 TO 20.10 | 3th Floor | 42782 | 42785 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6263 | steel reinforcement for shear wall 8 axis C2/A1 to A3 | Steel reinforcemnt | shear Wall | 81.27 To 85.27 | Upper Roof | 42782 | 42786 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6264 | Form Work For Shear Wall 8 Axis C2/A1 TO A3 | Form Work | shear Wall | 81.27 To 85.27 | Upper Roof | 42782 | 42786 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6265 | Check Form Work For Slab At Level 82.90 Third Stage | Form Work | Slab | 82.90 | 22th Floor | 42782 | 42785 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6266 | Check Form Work For Slab Level 82.90 Core 2 | Form Work | Core | 82.90 | 22th Floor | 42782 | 42787 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6267 | Steel reinforcement For Equipment bases on the residential roof part 2 Axis A6 TO A12 / B9 TO B12 | Seel reinforcement | Roof | 82.90 | 23th Floor | 42784 | 42786 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6268 | Form Work For Equipment bases on the residential roof part 2 | Form Work | Roof | 82.90 | 23th Floor | 42784 | 42791 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6269 | Steel reinforcement for 2 Columns CC9 Axis A11 / B6 TO B8 | Steel Reinforcement | Columns | 82.90 TO 85.90 | Upper roof | 42786 | 42798 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6270 | Form Work For 2 Columns CC9 AxisA11 /B6 TO B8 | Form Work | Columns | 82.90 TO 85.90 | Upper roof | 42786 | 42798 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6271 | Steel Reinforcement for 3 Columns CC7 Axis A6 / B5 , B6 , B8 | Steel reinforcemnt | Columns | 82.90 TO 85.90 | Upper roof | 42786 | 42786 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6272 | Form Work for 3 columns CC7 Axis A6 /B5 , B6 , B8 | Form Work | Columns | 82.90 TO 85.90 | Upper roof | 42786 | 42798 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6273 | Steel Reinforcement for 4 Columns CC7 Axis B4 /A7 TO A11 | Steel reinforcemnt | Columns | 82.90 TO 85.90 | Upper roof | 42786 | 42786 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6274 | Form Work For 4Columns CC7 Axis B4 /A7 TO A11 | Form Work | Columns | 82.90 TO 85.90 | Upper roof | 42786 | 42798 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6275 | Steel reinforcemt for parpet and planted columns on the residiential roof part 1Axis B4 TO B9 / A6 TO A12 | Steel reinforcement | Columns | 82.90 TO 85.90 | Upper roof | 42786 | 42791 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6276 | Form Work For Parapet and planted columns on the residential roof part 1Axis B4 TO B9 /A6 TO A12 | Form Work | Columns | 82.90 TO 85.90 | Upper roof | 42786 | 42795 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6277 | Steel Reinforcement for pour Strip 1/2 residential tower Axis A10 /B7 TO B8 | Steel reinforcement | Columns | 82.90 | Upper roof | 42785 | 42786 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6278 | Steel reinforcemnt For Shear Wall3* Axis C8/A2 TO A3 | Steel reinforcement | shear Wall | 81.27 TO 85.27 | Upper roof | 42787 | 42787 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6279 | Steel reinforcemenmt For Shear Wall 2 Axis C10/A2 TO A3 | Steel reinforcement | shear Wall | 81.27 TO 85.27 | Upper roof | 42787 | 42792 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6280 | Steel reinforcement For Shear Wall 3 Axis C6/A2 TO A3 | Steel reinforcement | shear Wall | 81.27 TO 85.27 | Upper roof | 42787 | 42787 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6281 | Steel reinforcement For Shear Wall 5* Axis C5/A2 TO A3 | Steel reinforcement | shear Wall | 81.27 TO 85.27 | Upper roof | 42787 | 42787 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6282 | Form Work For Shear Wall 5* Axis C5/A2 TO A3 | Form Work | shear Wall | 81.27 TO 85.27 | Upper roof | 42787 | 42791 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6283 | Form Work For Shear Wall 3 Axis C6/A2 TO A3 | Form Work | shear Wall | 81.27 TO 85.27 | Upper roof | 42787 | 42791 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6284 | Form Work For Shear Wall 2 Axis C10/A2 TO A3 | Form Work | shear Wall | 81.27 TO 85.27 | Upper roof | 42787
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6285 | Form Work For Shear Wall 3* Axis C8/A2 TO A3 | Form Work | shear Wall | 81.27 TO 85.27 | Upper roof | 42787 | 42791 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6286 | Steel reinforcement For Stair 14 Axis B17/A2 | Steel reinforcement | Stair | 68.00 TO 71.30 | 19th Floor | 42796 | 42800 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6287 | Steel reinforcement For hotel Tower Parapet & Posts Axis B1 To B10/A3 to A4 | Steel reinforcemnt | Parapet & Posts | 81.27 TO 85.27 | Upper roof | 42787 | 42788 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6288 | Form Work For Hotel Tower Parapet & Posts Axis B1 To B10/A3 To A4 | Form Work | Parapet & Posts | 81.27 TO 85.27 | Upper roof | 42787 | 42791 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6289 | Apply First Coat of damp proofing under slab on grade Axis B15 to B19/A5 to A15 | Damp proofing | Slab | -11.00 | B2 Floor | 42787 | 42791 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6290 | Apply Second Coat Of Damp Proofing Under Slab On Grade Axis B14 to B19/A1 To A5 | Damp proofing | Slab | -11.00 | B2 Floor | 42787 | 42791 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6291 | Steel Reinforcemnt For Columuns CC5 & CC6 Axis C9 To C11/A3 | Steel reinforcemnt | Columuns | 81.27 To 85.27 | Upper Roof | 42788 | 42792 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6292 | Form Work For Columuns CC5&CC6 Axis C9 To C11/A3 | Form Work | Columuns | 81.27 To 85.27 | Upper Roof | 42788
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6293 | Stressing For Cables of Second Stage Post tension Hotel Axis B1to C5/A1 to A3 | Stressing | Slab | 81.27 | Upper Roof | 42788 | 42802 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6294 | Form Work for Equipment bases on the Hotel Roof Part 1 Axis A1 to A3/B1 to C5 | Form Work | Columuns | 81.27 | Upper Roof | 42788
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6295 | Steel Reinforcemnt For Equipment bases on the Hotel Roof Part 1 Axis A1 To A3/B1 TO C5 | Steel reinforcemnt | Columuns | 81.27 | Upper Roof | 42788 | 42796 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6296 | Check Form Work For Slab At Level 84.50 TO 85.10 Machine Slab At Core 3 | Form Work | SLab | 82.90 | 22th Floor | 42791 | 42802 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6297 | Check Form Work For Slab At Level 84.50 TO 85.10 Machine Slab At Core 5 | Form Work | SLab | 82.90 | 22th Floor | 42791 | 42802 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6298 | Form Work For Core 6 Axis B19 TO B16/A1 TO A3 | Form Work | Core | 81.27 TO 85.27 | Upper Roof | 42791 | 42802 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6299 | Steel reinforcement For Core 6 Axis B19 TO B16/A1 TO A3 | Steel reinforcment | Core | 81.27 TO 85.27 | Upper Roof | 42791 | 42800 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6300 | Grouting For ducts Of First Stage Post Tension Slab Residentail Tower Axis B4 TO B9/A6 TO A12 | Grouting | Slab | 82.90 | 23th Floor | 42791 | 42796 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6301 | Form Work For Shallow Parapet Hotel Tower Parapet Axis B19 TO B10/A1 TO A3 | Shallow Parapet | Parapet | 81.27 TO 82.77 | Upper Roof | 42791 | 42800 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6302 | Steel reinforcement For Shallow Parapet Hotel Tower Parapet Axis B19 TO B10/A1 To A3 | Shallow Parapet | Parapet | 81.27 TO 82.77 | Upper Roof | 42791 | 42796 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6303 | Inspection For Holes and Dowels Fixation of Beam Core 5 to Closed NCR#181 Axis A9 TO A10/B8 | Holes | Core | 23.40 | 4th | 42792 | 42798 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6304 | Inspection For holes and dowels Fixation Of Edge Cantilever Slab Hotel Tower Axis B13 TO B10/A1 TO A3 | Holes | Slab | 61.40 | 17th Floor | 42792 | 42796 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6305 | Inspection For holes and dowels Fixation Of Edge Cantilever Slab Hotel Tower Axis B13 TO B10/A1 TO A3 | Holes | Slab | 64.70 | 18th Floor | 42792 | 42796 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6306 | Form Work For Stair 14 Axis B17/A2 | Form Work | Stair | 68.00 TO 71.30 | 17th Floor | 42792 | 42793 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6307 | Top and bottom Steel Reinforcement For third Stage Residentail Roof Axis | Steel reinforcemnt | Roof | 82.90 | 23th Floor | 42793 | 42798 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6308 | Tendons,Strand,Anchors And Profiles For third Stage Residential tower Roof Slab Axis B19 to B13/A6 to A12 | Anchor | Roof | 82.90 | 23th Floor | 42793 | 42798 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6309 | Steel reinforcemnt For Beams Core to Closed NCR#181 Axis A9 TO A10/B8 | Steel reinforcement | Core | 23.40 | 4th | 42793 | 42794 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6310 | Steel reinforcement For Stair 4 Axis A10/B8 | Steel reinforcement | Stair | 15.20 TO 20.10 | 3th Floor | 42794 | 42798 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6311 | Apply primer coat of damp proofing under slab on grade Axis B13 TO B18 / A13 To A15 | Slab on grade | Slab | -11.00 | B2 Floor | 42795 | 42798 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6312 | Surface prepartion prior to damp proofing under slab on grade B13 TO B18 /A13 TO A15 | Slab on grade | Slab | -11.00 | B2 Floor | 42795 | 42798 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6313 | Steel reinforcement for hotel parpet and cantilever part 1Axis C5 TO B1 / A3 | Steel reinforcement | Hotel parapet | UP 86.70 | Upper Roof | 42795 | 42798 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6314 | Form Work for hotel parpet and cantilever part 1 Axis C5 TO B1 /A3 | Form Work | Hotel parapet | UP 86.70 | Upper Roof | 42795 | 42798 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6315 | Steel reinforcement for elevator machine slabs at core 3 Axis A9 /B10 TO B12 | Steel reinforcement | Slab | 84.50 TO 85.10 | Upper roof | 42799 | 42807 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6316 | Steel reinforcement for elevator machine slabs at core5 Axis A9 /B6 TO B8 | Steel reinforcement | Slab | 84.50 TO 85.10 | Upper roof | 42799 | 42802 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6317 | Surface Preparation Prior TO Repair at hotel tower for shear wall 1 4th floor Axis B1 TO B15 / A1 | Repair | Shear wall |  | 4th | 42800 | 42803 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6318 | Steel Reinforcement For Concrete Base Axis B11 TO B14/A15 TO A14 | Steel Reinforcemnt | Concrete | -3.80 | BOH | 42838 | 42840 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6319 | Primer Liquid Bituminous Axis A4 TO A5/A6 TO B15 | Primer | Bituminous | -11.00 | B2 Floor | 42838 | 42840 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6320 | Surface Preparation Prior TO Repair at hotel tower for shear wall 1( 5th floor) Axis B1 TO B15 / A1 | Repair | Shear wall |  | 5th | 42800 | 42803 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6321 | Surface prepartion prior to repair for stair 10 Axis | Repair | Stair | -11.00 TO 1.10 | B2 & B1 & BOH | 42800 | 42802 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6322 | Inspection for repair of stair 10 Axis | Repair | Stair | -11.00 TO 1.10 | B2 & B1 & BOH | 42800 | 42803 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6323 | Inspection for repair of stair 4 Axis | Repair | Stair | -11.00 TO 1.10 | B2 & B1 & BOH | 42800 | 42803 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6324 | Surface prepartion prior to repair for stair 4 Axis B17/ A2 | Repair | Stair | -11.00 TO 1.10 | B2 & B1 & BOH | 42800 | 42802 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6325 | Surface prepartion prior to repair for driver stair Axis | Repair | Stair | -11.00 TO 1.10 | B2 & B1 & BOH | 42800 | 42802 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6326 | Inspection for repair of driver stair Axis | Repair | Stair | -11.00 TO 1.10 | B2 & B1 & BOH | 42800 | 42803 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6327 | Form Work For Equipment bases on the Residential Roof Part 3 Axis ?B19 to B13/A6 to A12 | Form work | Equipment bases | 82.90 | Upper roof | 42801 | 42803 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6328 | Steel Reinforcement For Equipment bases on the Residential Roof Part 3 Axis B19 TO B13/A6 TO A12 | Steel reinforcemnt | Equipment bases | 82.90 | Upper roof | 42801 | 42803 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6329 | Steel reinforcement For Parapet On the Residential Roof Part 2 Axis B9 TO B13/A6 TO A12 | Steel reinforcemnt | Parapet | 82.90 TO 85.90 | Upper roof | 42801 | 42803 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6330 | Steel reinforcemt for Shear Wall 1 Axis A1/B1 TO B15 | Steel reinforcemnt | shear Wall | 84.50 TO 85.27 | Upper roof | 42801 | 42807 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6331 | Steel reinforcement For Core 2 Opening Axis B14 TO B15/A8 TO A10 | Steel reinforcemnt | Core | 30.00 TO 33.30 | 7th | 42801 | 42803 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6332 | Form Work For Core 2 Opening Axis B14 TO B15/A8 TO A10 | Form Work | Core | 30.00 TO 33.30 | 7th | 42801 | 42803 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6333 | Form Work For Core 5 Opening Axis B6 TO B8/A8 TO A10 | Form Work | Core | 30.00 TO 33.30 | 7th | 42801 | 42803 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6334 | Steel reinforcement For Core 5 Opining Axis B6 TO B8/A8 TO A10 | Steel reinforcement | Core | 30.00 TO 33.30 | 7th | 42801 | 42803 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6335 | Fabrication Inspection For Visual Inspection & Dimension & Penetration Test | Farbrication For Steel Bridge | Steel Bridge | 10.30 | 2th Floor | 42802 | 42803 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6336 | Form Work For Equipment Bases on Hotel Roof Part 1 Axis B1 TO C5/A3 TO A1 | Form Work | Equipment bases | 81.27 | Upper roof | 42803 | 42807 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6337 | Steel Reinforcemnt For Equipment bases on Hotel Roof Part 1 Axis B1 TO C5/A3 TO A1 | Steel Reinforcement | Equipment bases | 81.27 | Upper roof | 42803 | 42807 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6338 | Form Work For Stair 14 Axis B17/A2 | Form Work | Staie | 71.30 TO 74.60 | 20th Floor | 42803 | 42807 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6339 | Steel reinforcement For Pour Strip Hotel Tower Axis C5/A1 TO A3 | Steel reinforcemnt | Pour strip | 81.27 | 23th FLoor | 42803 | 42812 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6340 | Grouting For ducts Of third Stage Post Tension Slab Residentail Tower Axis B13 to B19/A6 to A12 | Grouting | Slab | 82.90 | 23th Floor | 42807 | 42812 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6341 | Stressing For Coables Of Third Stage Post Tension Slab Residentail Tower Axis B19 TO B13/A6 TO A12 | Stressing | Slab | 82.90 | 23th Floor | 42807 | 42812 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6342 | Grouting For Ducts Of Third Stage Post Tension Slab Residential Tower Axis B13 TO B19/A1 TO A3 | Grouting | Slab | 79.50 | 22 th Floor | 42807 | 42812 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6343 | Steel Reinforcement for hotel parapet and Cantilever part 2 Axis B7 to B11/A3 | Steel reinforcemnt | Hotel parapet | 81.27 to 86.70 | Upper Roof | 42808 | 42809 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6344 | Inspection For Holes And Dowels Fixation For Base Centrifugal Chiller Axis B3 to B4&B5/A5TO B13 | Base Centrifugal Chiller | Chiller | -3.80 | BOH | 42809 | 42817 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6345 | Apply Second Coat Of Damp Proofing Under Slab on Grade Axis B9 to B14/A11 to A15 | Slab on grade | slab | -11.00 | B2 | 42809 | 42812 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6346 | Apply first Coat of damp proofing under slab on grade Axis B6 to B9/A11 to A15 | Slab on grade | slab | -11.00 | B2 | 42809 | 42817 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6347 | Apply Primer Coat of Damp Proofing Under Slab On Grade Axis B4 to B6/A11 To A15 | Slab on grade | slab | -11.00 | B2 | 42809 | 42817 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6348 | Check Form Work At 85.27 | Form Work | First Stage | 85.27 | 23th Floor | 42809 | 42809 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6349 | Form Work For Stair 4 Axis A10/B8 | Form Work | Stair 4 | 20.10 To 23.40 | 4th | 42810 | 42812 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6350 | Form Work For Parapet Part 2 Axis A6 To B8/B12 | Form Work | Parapet Part 2 | 82.90 To 85.40 | 4th | 42810 | 42812 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6351 | Form Work for hotel parapet and cantilever part 2 Axis C5 To C7/A3 | Form Work | Hotel parapet | 81.27 To 84.60 | Upper Roof | 42810 | 42812 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6352 | Form Work for stair 12 Axis B1/A2 | Form Work | stair 12 | 77.90 TO 81.27 | 23th Floor | 42810 | 42812 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6353 | Steel reinforcement for stair 12 Axis B1/A2 | Steel reinforcement | stair 12 | 77.90 TO 81.27 | 23th Floor | 42810 | 42817 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6354 | steel renforcement for pour strip2/3 residential tower Axis A6 To A12/B13 | steel reinforcement | Pour strip | 82.90 | 23th Floor | 42810 | 42812 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6355 | steel reinforcement for Stair 14 Axis B17/A2 | steel reinforcement | Stair 14 | 71.30 TO 74.60 | 23th Floor | 42812 | 42815 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6356 | Increasing by 5% for cable number Y 215 of part 1 hotel tower slab Axis B1 To C5/A2 To A3 | Cable number Y 215 | slab | 81.27 | 23th Floor | 42812 | 42820 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6357 | Form Work for residential tower parapet part 1 Axis A12/B4 To B9 | Form Work | parapet part 1 | 82.90 To 85.90 | Upper Roof | 42812 | 42812 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6358 | Grouting for ducts of first stage post tension slab Hotel tower Axis B1 To C5/A1 To A3 | Grouting | Post tension | 81.27 | 23th Floor | 42813 | 42817 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6359 | Grouting For Ducts Of Second Stage Post Tension Slab Hotel Tower Axis B19 TO C5/A1 TO A3 | Grouting | Post tension | 81.27 | 23th Floor | 42813 | 42817 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6360 | Form Work For Residential tower parapet part 2 Axis A12/B9 TO B13 | Form Work | Parapet | 82.90 to 85.90 | Upper Roof | 42814 | 42816 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6361 | Surface Preparation Prior TO Repair For Stair 4 TO Closed NCR#194 | Stair 4 Repair | Surface Preparation | 5.40 TO 20.10 | 1st to 2nd &3rd Floor | 42814 | 42817 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6362 | Surface Preparation Prior TO Damp Proofing Under Slab On Grade Axis B16 TO B4/A1 TO A3 | Slab on grade | Surface Preparation | -11.00 | B2 | 42814 | 42817 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6363 | Apply Primer Coat Of Damp Proofing Under Slab On Grade Axis B16 TO B4/A1 TO A3 | Slab on grade | Damp proofing | -11.00 | B2th Floor | 42814 | 42817 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6364 | Form Work For Hotel Parapet and Cantilever Part 2 Axis C5 TO C7/A3 | Form Work | Parapet | 84.70 TO 86.70 | Upper Roof | 42815 | 42817 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6365 | Steel Reinforcemnt For Stair4 Axis B8/A10 | Steel reinforcement | Stair | 20.10 TO 23.40 | 4th | 42815 | 42819 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6366 | Form Work For Stair 10 Axis B15/A8 | Form WOrk | Stair | 1.10 TO 5..40 | Ground Floor | 42815 | 42820 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6367 | Apply Second Coat Of Damp Proofing Under Slab On Grade Axis B6 TO B9/A11 TO A15 | Slab on grade | Slab | -11.00 | B2 | 42815 | 42817 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6368 | Apply First Coat of damp Proofing Under Slab On Grade Axis B4 to B6/A11 TO A15 | Slab on grade | Damp proofing | -11.00 | B2 | 42815 | 42817 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6369 | Steel Reinforcement For Residential Tower Cradle Beams And Cantilevers Part 1 Axis A6 to A12/B4 TO B9 | Steel Reinforcemnt | Beams | 85.90 | Upper Roof | 42815 | 42829 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6370 | Steel reinforcemnt For base Centrifugal Chiller Axis B3 to B4 &B5/A5/A13 | Steel Reinforcemnt | Bases Centrifugal Chiller | -3.80 | BOH | 42815 | 42821 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6371 | Inspection repair for stair 4 to closed NCR #194 Axis B8/A10 | Inspection repair | Stair 4 Repair | 5.40 To 20.10 | 1st to 2nd &3rd Floor | 42816 | 42819 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6372 | Steel Reinforcemnt For Core 8 Hotel Tower Axis A1 TO A3/B1 | Steel reinforcement | Core | 81.27 TO 85.27 | Upper roof | 42817 | 42819 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6373 | Form Work For Core 8 Hotel Tower Axis A1 TO A3/B1 | Form Work | Core | 81.27 TO 85.27 | Upper roof | 42817 | 42821 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6374 | Steel reinforcement For Parapet Part 3R.D Tower Axis B13 TO B19/A6 TO A12 | Steel Reinforcemnt | Parapet Part 3 | 82.90 TO 85.90 | Upper roof | 42817 | 42821 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6375 | Form Work For Parapet On The Residential Roof Part 3 Axis B13 TO B19/A6 TO A12 | Form WOrk | Parapet Part 3 | 82.90 TO 85.90 | Upper roof | 42817 | 42822 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6376 | Surface Preparation Prior to Repair For Stair 3 | Stair 4 Repair | Surface Preparation | 5.40 to 20.10 | 1st to 2nd &3rd Floor | 42817 | 42821 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6377 | Surface Preparation Prior TO Repair For Stair 6 | Stair 6 Repair | Surface Preparation | 5.40 to 20.10 | 1st to 2nd &3rd Floor | 42817 | 42821 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6378 | Surface Preparation Prior TO Repair to repair for stair 7 | Stair 7 Repair | Stair | 5.40 to 20.10 | 1st to 2nd &3rd Floor | 42817 | 42821 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6379 | Surface Preparation To Repair For Stair 11 | Stair | Surface Preparation | 5.40 to 20.10 | 1st to 2nd &3rd Floor | 42817 | 42821 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6380 | Inspection Repair For Stair 11 | Stair | Stair | 5.40 to 20.10 | 1st to 2nd &3rd Floor | 42817 | 42829 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6381 | Inspection Repair For Stair 7 | Stair | Stair | 5.40 to 20.10 | 1st to 2nd &3rd Floor | 42817 | 42821 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6382 | Inspection Repair For Stair 6 | Stair | Stair | 5.40 to 20.10 | 1st to 2nd &3rd Floor | 42817 | 42829 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6383 | Inspection Repair For Stair 3 | Stair | Stair | 5.40 to 20.10 | 1st to 2nd &3rd Floor | 42817 | 42829 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6384 | Form Work For Stair 14 Axis B17/A2 | Form Work | Stair | 74.60 TO 77.90 | 22th Floor | 42817 | 42823 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6385 | Steel reinforcemnt For Stair 14 | Steel reinforcemnt | Stair | 74.60 TO 77.90 | 22th Floor | 42817 | 42826 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6386 | Surface Preparation Perior to repair of Stair 5 Axis A8 To A9/B8 | Surface Preparation | Repair | 5.20 To 20.10 | 1st & 2nd &3rd Floor | 42820 | 42820 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6387 | Inspection for repair of Concrete at Stair 5 Axis A8 To A9/B8 | Stair | Repair | 5.40 TO 20.10 | 1st & 2nd &3rd Floor | 42820 | 42821 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6388 | Surface Preparation and repair of concrete at walls between apartments ( 1&2) at 4th Floor of residential tower Axis A8 To A9/B17 | Surface Preparation | Repair | 20.10 To 23.40 | 4th | 42820 | 42820 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6389 | Inspection for Holes and dowels fixation for stair 10 Axis B14 To B15/A8 To A9 | Stair | Holes | 1.10 To 5.40 | Ground Floor | 42820 | 42821 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6390 | Bottom And Top Steel reinforcement for upper roof hotel tower slab Axis A1 To A3/C5 To B19 | Steel reinforcement | Upper roof slab | 85.27 | Upper Roof | 42820 | 42826 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6391 | Tendons, Strands ,anchors and profiles for upper roof hotel tower slab Axis A1 To A3/C5 To B19 | Slab | Upper roof slab | 85.27 | Upper Roof | 42820 | 42826 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6392 | Apply first coat of damp proofing under slab on grade Axis B4 To B16/A1 To A3 | Damp proofing | Slab On Grade | -11.00 | B2 | 42821 | 42821 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6393 | Apply second coat of damp proofing under slab on grade Axis B6 To B9/A11 To A15 | Damp proofing | Slab On Grade | -11.00 | B2 | 42821 | 42821 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6394 | Apply second coat of damp proofing under slab on grade Axis B4 To B16/A1 To A3 | Damp proofing | Slab On Grade | -11.00 | B2 | 42821 | 42826 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6395 | Steel Reinforcemnt For Stair 10 Axis B13 to B19/A12 | Steel Reinforcemnt | Stair | 1.10 to 5.40 | Ground Floor | 42821 | 42826 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6396 | Steel Reinforcemnt For Elevator Machine Slab Core 2 Axis B15 TO B16 | Steel Reinforcemnt | Slab | 84.50 TO 85.10 | Upper Roof | 42822 | 42826 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6397 | Form Work For Stair 4 Axis B7 TO B8/A9 TO A11 | Form Work | Stair | 23.40 TO 26.70 | 5th | 42822 | 42823 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6398 | Form Work For Crade Beam and Cantilever Part 1 Axis B4 TO B6 | Form Work | Cradle Beam | 85.90 | Upper Roof | 42822 | 42823 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6399 | Inspection For Holes and dowels Fixation For Core 4 Slab(Pit Elevaroorrs 4,4) Axis B9/A8 to A9 | Holes | Core | -7.20 to -6.20 | B2 | 42823 | 42826 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6400 | Steel Reinforcement For Stair 4 Axis B7 to B8/A9 to A11 | Steel reinforcement | Stair | 23.40 TO 26.70 | B2 | 42823 | 42829 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6401 | Form Work For Parapet Residenital Tower Part 3 Axis B12 TO B16/A12 | Form Work | Parapet Part | 82.90 to 85.90 | Upper Roof | 42823 | 42826 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6402 | Bottom and top Steel Reinforcement For Upper Roof Hotel Tower Slab Axis A1 to A3/C5 to B1 | Steel Reinforcement | Slab | 85.27 | Upper Roof | 42824 | 42826 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6403 | Form Work For Parapet Residenital Tower Part 3 Axis B16 TO B19/A3 | Form Work | Parapet | 82.90 To 85.90 | Upper Roof | 42826 | 42829 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6404 | Steel Reinforcement for Shear Wall 1 Axis B1 To B17/A1 | Steel Reinforcement | shear Wall | 85.27 To 86.70 | Upper Roof | 42827 | 42829 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6405 | Form work for Shear Wall 1 Axis B1 To B17/A1 | Form Work | shear Wall | 85.27 To 86.70 | Upper Roof | 42827 | 42840 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6406 | Steel Reinforcement for Cradle Beam part 2 Axis B6 To B13/A6 | Steel Reinforcemet | Cradle Beam Part 2 | 85.90 | Upper Roof | 42827 | 42829 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6407 | Form Work for Cradle Beam part 2 Axis B6 To B13/A6 | Form Work | Cradle Beam Part 2 | 85.90 | Upper Roof | 42827 | 42829 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6408 | Apply primer Coat of damp proofing under slab on grade Axis B13 To B14/A3 To A5 & A8 To A14/B1 To B4 & A1 To A3/B2 To B6 | Damp proofing | Slab | -11.00 | B2 | 42827 | 42829 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6409 | Apply first Coat of damp proofing under slab on grade Axis B13 To B14/A3 To A5 & A8 To A14/B1 To B4 & A1 To A3/B2 To B6 | Damp proofing | Slab | -11.00 | B2 | 42827 | 42829 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6410 | Apply second Coat of damp proofing under slab on grade Axis B13 To B14/A3 To A5 & A8 To A14/B1 To B4 & A1 To A3/B2 To B6 | Damp proofing | Slab | -11.00 | B2 | 42827 | 42836 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6411 | Surface Preparation Prior to damp proofing under slab on grade Axis B13 To B14/A3 To A5 & A8 To A14/B1 To B4 & A1 To A3/B2 To B6 | Surface Preparation | Slab | -11.00 | B2 | 42827 | 42829 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6412 | Form Work For Core 3 Axis A9/B10 TO B12 | Form Work | Core | 84.50 TO 85.10/88.15 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6413 | Steel Reinforcemnt For Core 3 Axis A9 TO A10/B12 | Steel Reinforcement | Core | 84.50 TO 85.10/88.15 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6414 | Form Work For RD Tower Cradle Beams Axis B5 TO B12/A12 TO A11 | Form Work | Cradle Beams | 85.90 | Upper Roof | 42830 | 42834 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6415 | Steel reinforcement For RD Tower Cradle Beams Axis B5 TO B12/A12 TO A11 | Steel Reinforcement | Cradle Beams | 85.90 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6416 | Steel reinforcement For Columuns CR 30 X30,CR5&CR1 | Steel Reinforcement | Columun | 82.90 TO 85.90 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6417 | Form Work For Columuns CR 30X30 CR5&CR1 Axis A9 TO A11/B10 TO B12 | Form Work | Columun | 82.90 TO 85.90 | Upper Roof | 42830 | 42838 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6418 | Steel Reinforcemnt For 2 Columuns CC9 Axis A11/B10 TO B12 | Steel Reinforcement | Columun | 82.90 TO 85.90 | Upper Roof | 42830 | 42834 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6419 | Form Work For 2 Columuns CC9 Axis A11/B10 TO B12 | Form Work | Columun | 82.90 TO 85.90 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6420 | Steel Reinforcemnt For 2 Columuns CC7Axis A6/B10 TO B12 | Steel Reinforcemnet | Columun | 82.90 TO 85.90 | Upper Roof | 42830 | 42834 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6421 | Form Work For 2 Columuns CC7 Axis A6/B10 TO B12 | Form Work | Columun | 82.90 TO 85.90 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6422 | Form Work For Columun DCC7,DCC1,DCC3 Axis A6/B9/A10/B9/A11/B9 | Form Work | Columun | 82.90 TO 85.90 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6423 | Steel Reinforcemnt For Columuns DCC7&DCC1&DCC3 Axis A6/B9 & A10/B9&A11/B9 | Steel Reinforcemnet | Columun | 82.90 TO 85.90 | Upper Roof | 42830 | 42834 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6424 | Form Work For RD Tower Cradle Beams Axis B6 TO B12/A6 | Form Work | Cradle Beams | 85.90 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6425 | Form Work For RD Tower Parapet Axis B14/A12 TO D1/A6 | Form Work | Parapet | 82.90 TO 85.90 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6426 | Steel reinforcement For RD Tower Parapet Axis B14/A12 TO D1/A6 | Steel reinforcemnt | Parapet | 82.90 TO 85.90 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6427 | Steel Reinforcemnt For Shallow Parapet Hotel Tower Axis A1 TO A3/B10 TO B17 | Steel reinforcemnt | Parapet | 85.27 To 86.70 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6428 | Form Work For Shallow Parapet Hotel Tower Axis A1 to A3/B10 to B17 | Form Work | Parapet | 85.27 To 86.70 | Upper Roof | 42830 | 42834 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6429 | Steel Reinforcemnt For Core 7 Hotel Tower Axis A1 to A3/C7 | Steel Reinforcemnt | Core | 85.27 to 90.2 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6430 | Form Work For Core 7 Hotel Axis A1 to A3/C7 | Form Work | Core | 85.27 to 90.2 | Upper Roof | 42830 | 42837 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6431 | Inspection Of Holes and Dowels Fixation For (CB1) Beam of Core(3) to Closed NCR#188 Axis A8 to A9/B11 to B12 | CBI-Beam of Core 3 | NCR#188 | 23.40 | 4th | 42830 | 42834 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6432 | Steel reinforcement for ( CB1) beam of core (3) to closed NCR#188 between Axis A8 To A9/B11 To B12 | CBI-Beam of Core 3 | NCR#188 | 23.40 | 4th | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6433 | Steel reinforcement for shear wall 3+Planted columns Axis C8/A2,3 | Steel reinforcement | shear 3* | 85.27 To 90.02 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6434 | Form work for shear wall 3 + planted co;umns Axis C8/A2.3 | Form Work | shear 3* | 85.27 To 90.02 | Upper Roof | 42830 | 42834 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6435 | Form work for equipment bases on the hotel upper roof Axis A1 To A3/B1 To B16 | Form Work | Equipment bases | 85.27 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6436 | Steel reinforcement for equipment bases on the hotel upper roof Axis A1 To A3/B1 To B16 | Steel reinforcement | Equipment bases | 85.27 | Upper Roof | 42830 | 42834 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6437 | Surface Preparation And Repair At Elevator Shaft | Repair Elev | Surface Preparation | 20.20 to 30.10 | 4th to 7th Floor | 42834 | 42836 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6438 | Check Form Work For Machine Slab At 86.67 | Form WOrk | Machine Slab | 86.67 | 23th Floor | 42835 | 42840 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6439 | Steel Reinforcement For Cradle Beam Axis B12 TO B16/A6 TO A7 As Per Attached | Steel Reinforcement | Cradel Beaam | 85.90 |  | 42836 | 42838 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6440 | Form Work For Cradel Beam Axis B12 TO B16/A6 TO A7 As Per Attached | Form WOrk | Cradel Beaam | 85.90 |  | 42836 | 42838 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6441 | Steel reinforcement For Wall Core 5 Axis B5 TO B9/A8 TO A10 As Per Attached | Steel reinforcement | Core | 85.10 To 88.15 &84.50 To 88.15 |  | 42836 | 42838 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6442 | Inspection For Holes And Dowels Fixation For Inverted Beam (Shed 1:Between Axis B12 TO B14)&(Shed 2: Between Axis B8 & B10 | Holes And Dowels Fixation | Holes | 5.40 TO 10.30 | 1st TO 2nd Floor | 42836 | 42838 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6443 | Form Work For Concrete Bases Axis C2 to C4 As Per Attached | Form WOrk | Concrete | BOH | Podium | 42836 | 42838 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6444 | Steel Reinforcement For Concrete beam axis C2 TO C4 As Per Attached | Steel reinforcement | Concrete | BOH | Podium | 42836 | 42838 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6445 | Steel Reinforcement For Wall Core 8 Axis B1/A1 TO A3) As Per Attached | Steel reinforcement | Core | 85.27 TO 90.27 |  | 42836 | 42838 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6446 | Form Work For Wall Core Axis B6 to B8/A8 to A10 As Per Attached | Form Work | Core | 84.50 to 88.15 &85.10 to 88.15 |  | 42837 | 42840 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6447 | Form work for Concrete Bases Axis B11 to B14/A15 to A14 | Form Work | Concrete | -3.80 | BoH | 42838 | 42840 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6448 | Form Work For Shallow Parapet Axis B15 TO B17/A1 | Form Work | Shallow Parapet | 85.27 to 86.70 |  | 42837 | 42840 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6449 | Form Work For Stair 10 Axis B14 tO B15/A8 TO A9)as Per Attached | Form Work | Stair | 5.40 TO 10.30 |  | 42837 | 42840 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6450 | Sandblasting For Steel Bridge | Sandblasting | Steel Bridge | 10.30 | 2nd | 42837 | 42838 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6451 | Primer For Steel Bridge | Steel Bridge | Steel Bridge | 10.30 | 2nd | 42837 | 42838 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6452 | Check Form Work at Level 85.90 at Cradle Beam Axis B16 TO B12/A06 TO A12 | Form WOrk | Cradle | 85.90 | 23th Floor | 42838 | 42840 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6453 | Apply First Coat Of Bituminous Damp Proofing For Raft Axis A3 TO A5/B6 TO B14 | Bituminous Damp Proofing | Damp proofing | X | BOH | 42840 | 42840 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6454 | Form Work For Wall Slab Axis B8 TO B9/A9 TO A10 As Per Attached | Form WOrk | Slab | -7.20 | B1 | 42840 | 42849 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6455 | Steel Reinforcement For Slab Axis B8 To B9/A9 To A10 | Steel Reinforcement | Slab | -7.20 | B1 | 42840 | 42843 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6456 | Form Work For Stair 14 Axis B15 To B17/A1 | Form Work | Slab | 77.90 To 81.27 | X | 42840 | 42849 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6457 | Apply Second coat Of Bltuminous Dampproofing For Raft Axes A3 To A5/B6 To B14 | Bituminous Damp Proofing | Damp proofing | X | BOH | 42841 | 42843 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6458 | Form Work For Cradle beam Axis B12 TO B16/A10 TO A12 As Per Attached | Form Work | Cradle Beam | 85.90 | X | 42843 | 42845 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6459 | Steel reinforcement For Cradle Beam Axis B12 TO B16/A10 TO A12 | Steel reinforcement | Cradle Beam | 85.90 | X | 42843 | 42845 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6460 | Form Work For Beams Axis B7 TO B14/A12 | Form Work | Beams | 5.40 TO 10.30 | X | 42843 | 42845 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6461 | Steel Reinforcement For Beams Axis B7 TO B14/A12 | Steel Reinforcement | Beams | 5.40 TO 10.30 | X | 42843 | 42845 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6462 | Steel Reinforcement For Opening in the Core Wall (Core 2 & Core 5) | Steel Reinforcement | Core | 39.90 | X | 42843 | 42845 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6463 | Form Work For Opening In the Core Wall (Core 2& Core 5) Axis B7 TO B15/A8 TO A10 | Form Work | Core | 39.90 | X | 42843 | 42845 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6464 | Repair For Walls Axis B6/A9&B12/A9 | Repair | Walls | X | B2 | 42843 | 42845 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6465 | Surface Preparation For Walls Axis B6/A9&B12/A9 as Per Attached | Repair | Surface Preparation | X | B2 | 42843 | 42845 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6466 | Apply Primer Coat Of Bitumlnous Damp Axis B6 to B10/A4 to A6 | Damp proofing | Bituminous | X | B2 | 42843 | 42845 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6467 | Surface Preparation Prior To Apply Bituminous Damp Proofing Axis B6 to B10/A4 to A6 | Damp proofing | Surface Preparation | X | B2 | 42843 | 42845 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6468 | Check Form Work Of Machine Slab At Level 87.12 Core 8 | Form Work | Core | 87.12 | 23th Floor | 42844 | 42849 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6469 | Installation For Steel Bridge Axis A3 to A6 | Steel Bridge | Steel Bridge | 10.30 | 2nd | 42844 | 42848 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6470 | Steel Reinforcement For Cradle Beams Axis B16 TO B19/A6 TO A12 | Steel Reinforcement | Cradel Beaam | 85.90 | 23rd Floor | 42845 | 42852 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6471 | Form Work For Cradle Beam Axis B16 TO B19/A6 TO A12 | Form Work | Cradel Beaam | 85.90 | 23rd Floor | 42845 | 42849 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6472 | Steel Reinforcement For Stair 10 Axis B14 TO B15/A7 TO A8 | Steel Reinforcement | Stair 10 | 5.40 To 10.30 | X | 42847 | 42852 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6473 | Surface Preparation and Repair For all Items Axis A6 to A12 to B4 to B19 | Repair | Surface Preparation Repair | X | 22nd Floor | 42847 | 42852 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6474 | Surface Preparation And Repair For Elev. 01 A9 / B6 to B7 | Repair Elev | Surface Preparation Repair | X | 7th.15th Floor | 42847 | 42858 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6475 | Form Work For Stair 4 Axis B7 TO B8/A10 As Per Attached | Form WOrk | Stair | 23.40 TO 26.70 | X | 42848 | 42852 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6476 | Steel Reinforcemnt For Core 2 Axis B15 TO B16/A8 TO A9 | Steel reinforcemnt | Core | 85.10 TO 88.15 | X | 42848 | 42852 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6477 | Steel Reinforcement For Machine Room Slab Axis B10 to B11/A2 to A3 | Steel reinforcemnt | Machine Slab | 86.87 | X | 42848 | 42852 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6478 | Surface Preparation and repair at Hotel Tower For Shear Wall 1(7th Floor) Axis B3 TO B8/A1 | Surface Preparation | Repair | 28.50 | 7th | 42849 | 42852 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6479 | Form Work For Core 2 Axis | Form WOrk | Core | 85.10 TO 88.15 |  | 42849 | 42852 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6480 | Steel Reinforcemnt For Fence Beams Axis C1/A13 TO A15 | Steel Reinforcement | Fence Bems | 9.20 |  | 42849 | 42852 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6481 | Check Location Of Form Work For Steel Bridge At Level 10.30 Axis B12 To B14/A05 to A03 | Form Work | Steel Bridge | 10.30 | 2nd | 42849 | 42852 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6482 | Form Work For Columuns Core 5 Axis B6 TO B8/A9 TO A11 | Form Work | Core | 82.90 TO 88.15 |  | 42851 | 42855 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6483 | Steel Reinforcement For Parapet Axis B15 TO B19/A6 TO A12 | Steel reinforcemnt | Parapet | 85.90 TO 88.90 | Top | 42851 | 42858 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6484 | Form Work For Core 8 And Slab Of Machene Room Axis B1 TO B2/A2 TO A3 | Form Work | Core & Slab | 85.27 TO 87.12 | 25th Floor | 42852 | 42855 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6485 | Compaction Test For Backfilling Under Slab On Grade Axis A1 TO A5/B18 TO B21 as Per attached | Back Filling | Compaction |  | B2 Floor | 42857 | 42859 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6486 | Compaction Test For Backfilling Under Slab On Grade Axis A1 TO A5/B13 TO B18 as Per attached | Back Filling | Compaction |  | BoH | 42857 | 42859 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6487 | Surface Preparation and Repair For BOH Axis A1 TO A15/B1 TO B21 | Surface Preparation | Repair |  | BoH | 42857 | 42862 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6488 | Comoaction Test For Backfilling Under Slab On Grade Axis A1 To A5/B13 To B15 | Back Filling | Compaction | X | B2 Floor | 42857 | 42859 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6489 | Form Work Posts Axis (B1 To B2/A2 To A3) As Per Attached | Form WOrk | Posts | 85.27 To 90.27 | X | 42857 | 42887 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6490 | Steel Reinforcement For Posts Axis (B1 To B2/A2 To A3) As Per Attached | Steel Reinforcement | Posts | 85.27 To 90.27 | X | 42857 | 42887 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6491 | Form Work For Core 7 Machine Room Slab Axis (B10 To B12/A2 To A3) As Per Attached | Form WOrk | Core 7 (Machine Room Slab) | 86.87 To 90.02 | X | 42857 | 42858 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6492 | Steel Reinforcement For Machine Room Slab Axis (B1 To B2/A2 To A3) As Per Attached | Steel Reinforcement | machine Room Slab (Core 8) | 87.12 | X | 42857 | 42859 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6493 | Inspection For Holes And Dowels Fixation For Stair 4 axis B6 to B8/A10 To A11 As Per Attached | Fixation Stair 4 | Holes | (26.70 To 30.00) | 6th To 7th Floor | 42857 | 42859 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6494 | Surface Preparation And Repair For Ac- Shaft Axis A10/B6 To B7 | Surface Preparation | Repair | X | 4th to 7th Floor | 42857 | 42859 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6495 | Steel Reinforcement For Steel Bridge Axis (A3 To A6) As Per Attached | Surface Preparation | Steel Bridge | 10.35 | X | 42857 | 42859 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6496 | Inspection For Holes And Dowels Fixation For Pads Axis B3 To B15/A2To A6 As Per Attached | Inspection Holes | Holes | (-3.80) | BoH | 42858 | 42865 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6497 | Surface Prepartion Prior To Repair For Core 5 To Close NCR# 195 Axis A9 To A11/B5 To B9 | Surface Preparation | Repair For Core 5 | X | 2nd&7th Floor | 42858 | 42862 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6498 | Form Work For Parapet Axis B15 TO B19/A6 TO A12 | Form Work | Parapet | 85.90 TO 88.90 |  | 42859 | 42861 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6499 | Form Work For Upstand Axis B1 TO B2/A1 TO A3 | Form Work | Upstand | -11.00 | BOH | 42861 | 42872 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6500 | Steel Reinforcement for Upstand Axis A1 to A3/B1 TO B2 | Steel Reinforcement | Upstand | -11.00 | BOH | 42861 | 42872 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6501 | Steel Reinforcement for Sumpit Axis A4 / B19 | Steel Reinforcement | Sumpit | -11.00 | BOH | 42861 | 42862 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6502 | Form Work For Sumpit Axis B19/A4 | Form WOrk | Sumpit | -11.00 | BOH | 42861 | 42862 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6503 | Form Work For Slab On Grade Axis B18 TO B21/A1 TO A4 | Form WOrk | Slab On Grade | -10.50 | BOH | 42861 | 42862 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6504 | Steel Reinforcement For Slab On Grade Axis A1 TO A4/B18 TO B21 | Steel Reinforcement | Slab On Grade | -10.50 | BOH | 42861 | 42862 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6505 | Steel Reinforcement For Pads Axis A2 To A6/B3 To B15 | Steel Reinforcement | PADS | -3.80 | BOH | 42861 | 42862 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6506 | Surface Preparation Prior to Apply Bituminous Damp Proofing Axis B1 To B14/A4 to A11 | Surface Preparation | Damp proofing |  | B2 Floor | 42861 | 42862 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6507 | Surface Preparation and Repair For Apartements No.(1,2,3,4,5,6) | Surface Preparation | Repair |  | 5th TO 6th Floor | 42862 | 42865 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6508 | Steel Reinforcement For Core 2 Opening Axis A8 to A9/B14 to B15 | Steel Reinforcement | Core | 10.30 | 2nd | 42863 | 42865 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6509 | Form Work For Core 2 Opening Axis A8 TO A9/B14 TO B15 | Form Work | Core | 10.30 | 2nd | 42863 | 42868 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6510 | Steel Reinforcement For Stair 4 Axis A10/B7 TO B8 | Steel Reinforcement | Stair | 26.70 TO 30.00 |  | 42863 | 42865 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6511 | Steel Reinforcement For Parapet Axis A6/B7 TO B16 | Steel Reinforcement | Parapet | 85.90 TO 88.90 |  | 42863 | 42865 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6512 | Steel Reinforcement For Core 2 Axis A10/B15 to B16 | Steel Reinforcement | Core | 84.50 to 88.15 |  | 42863 | 42865 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6513 | Form Work For Core 2 Axis A9 TO A10/B15 TO B16 | Form Work | Core | 84.50 to 88.15 |  | 42863 | 42865 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6514 | Form Work For Stair 10 Axis A8 TO A9/B14 TO B15 | Form Work | Stair | 10.30 TO 15.20 |  | 42863 | 42865 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6515 | Surface Preparation Prior TO Apply Bituminous Damp Proofing Axis B3 TO B13/A4 TO A11 | Surface Preparation | Insulation | -10.50 | B2 | 42864 | 42868 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6516 | Primer Coat Of Bituminous Damp Proofing For Raft Axis B2 TO B3/A3 TO A9 | Primer | Damp proofing | -10.50 | B2 | 42864 | 42865 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6517 | First Coats Of Bituminous Damp Proofing For Raft Axis B2 TO B3/A3 TO A9 |  | Damp proofing | -10.50 | B2 | 42864 | 42868 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6518 | Form Work For Slab On Grade Axis A1 TO A4/B1 TO B18 | Form Work | Slab On Grade | -10.50 | B2 | 42864 | 42870 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6519 | Steel Reinforcement For Slab On Grade Axis A TO A4/B13 TO B18 | Steel Reinforcement | Slab On Grade | -10.50 | B2 | 42864 | 42870 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6520 | Compaction Test For BackFilling Under Slab On Grade Axis A1 TO A4/B9 TO B13 | Back Filling | Compaction | -10.50 | B2 | 42864 | 42875 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6521 | Surface Praeparation and Repair For Floors (7th ,8th,9th Floor) Except Bedrooms | Surface Preparation | Repair |  | 7th TO 9th Floor | 42864 | 42872 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6522 | Holes and Dowels Fixation For Air Handling Unit | Holes And Dowels Fixation | Air handling Unit | 5.40 TO 10.30 &15.20 | 1st to 2nd &3rd Floor | 42865 | 42870 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6523 | Steel Reinforcement For Stair 10 on Axis B14 to B15/A7 | Steel Reinforcement | Stair | 10.30 TO 15.20 | 1st TO 2nd Floor | 42865 | 42870 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6524 | Second Coat Of Bituminous Damp Proofing For Raft Axis B2 TO B3/A3 TO A9 | Slab on grade | Damp proofing | -10.50 | B2 | 42864 | 42870 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6525 | Steel Reinforcemnt For PADS | Steel Reinforcement | PADS | 5.40 To 10.30&15.20 | 1st&2ndTO3rd Floor | 42866 | 42870 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6526 | Form Work FOR PADS | Form Work | PADS | 5.40 To 10.30&15.20 | 1st&2ndTO3rd Floor | 42866 | 42870 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6527 | Form Work For Parapet Axis A6/B12 to B16 | Form Work | Parapet | 85.90 TO 88.15 | 23rd Floor | 42866 | 42868 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6528 | Steel Reinforcemnet For Parapet Axis A6/B7 TO B12 | Steel Reinforcement | Parapet | 85.90 TO 88.15 | 23rd Floor | 42866 | 42870 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6529 | Primer Coat Of Bituminous Damp Proofing For Raft Axis B4 TO B16/A6 TO A12 | Raft | Damp proofing | -10.50 | B2 | 42866 | 42870 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6530 | Suface Preparation and Repair for AC-shaft Axis A9 TO A11/B6 TO B7 | Repair | Surface Preparation |  | 15th TO 22nd Floor | 42868 | 42870 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6531 | First Coats Of Bituminous Damp Proofing For Raft Axis B4 TO B16/A6 TO A12 | Damp Proofing | Raft | -10.50 | B2 | 42868 | 42870 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6532 | Surface Preparation Prior To Water Proofing Axis B1 to B4/A4 to A8 | Water Proofing | Surface Preparation |  | Land Scape | 42868 | 42875 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6533 | Second Coat Of Bituminous Damp Proofing For Raft Axis B4 To B16/A6 to A12 | Damp Proofing | Raft | -10.50 | B2 | 42869 | 42882 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6534 | Form Work For Stair 4 Axis B7 TO B8/A10 As Per Attached | Form Work | Stair | 30.00 TO 33.30 | 7th | 42870 | 42875 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6535 | Form Work For Stair 10 Axis B14 tO B15/A8 TO A9)as Per Attached | Form Work | Stair | 15.20 TO 20.10 | 3rd TO 4th Floor | 42871 | 42875 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6536 | Form Work For Parapet Axis B7 TO B12/A6 As Per Attached | Form Work | Parapet | 85.90 to 88.15 | 23rd Floor | 42871 | 42875 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6537 | Surface Preparation and Repair For AC- Shaft Axis A9 to A11/B6 to B7 As Per Attached | Repair | Surface Preparation |  | 8th TO 14th Floor | 42872 | 42875 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6538 | Steel Reinforcement For Stair No.4 Axis B5 TO B7/A9 TO A11 | Steel Reinforcement | Stair |  | 7th TO 8th Floor | 42872 | 42875 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6539 | Steel Reinforcement For Slab On Grade Axis B2 TO B13/A2 TO A5 | Steel Reinforcement | Slab On Grade | -10.50 | B2 Floor | 42872 | 42879 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6540 | Form Work For Slab On Grade Axis B2 TO B13 /A2 TO A5 | Form Work | Slab On Grade | -10.50 | B2 Floor | 42872 | 42879 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6541 | Surface Preparation And Repair For Elev.Shaft Of Core (3) Axis B10 TO B12/A8 TO A10 | Repair Elev | Surface Preparation | 15.30 TO 79.60 | 3rd TO 22nd Floor | 42872 | 42879 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6542 | Repair For Core 5 TO Close NCR#195 Axis A9 TO A11/B5 TO B9 | Repair | NCR#195 |  | 2nd TO 7th Floor | 42872 | 42882 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6543 | Compaction Test For Backfilling Under Slab On Grade Axis A5 TO A14/B1 TO B21 | Back Filling | Compaction | -10.50 | B2 Floor | 42873 | 42882 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6544 | Surface Preparation And Repair For Corridor Axis A1 to A2/B2 to B15 | Repair | Surface Preparation |  | 18th Floor | 42873 | 42879 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6545 | Primer Coat Of Bituminous Damp Proofing For Raft Axis B3 TO B11/A8 TO A11 | Damp Proofing | Bituminous | -10.50 | B2 Floor | 42873 | 42879 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6546 | Surface Preparation Prior TO Bituminous Damp Proofing For Raft Axis B6 TO B9/A8 TO A11 | Damp Proofing | Bituminous | -10.50 | B2 Floor | 42876 | 42879 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6547 | Second Coat Of Bituminous Damp Proofing For Raft Axis B3 TO B11/A8 TO A11 | Damp Proofing | Bituminous | -10.50 | B2 Floor | 42876 | 42879 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6548 | First Coat Of Bituminous Damp Proofing For Raft Axis B3 TO B11/A8 TO A11 | Damp Proofing | Bituminous | -10.50 | B2 Floor | 42876 | 42879 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6549 | Steel Reinforcement For Stair 10 Axis A8 TO A9/B14 TO B15 | Steel Reinforcemnt | Stair | 15.20 TO 20.10 | 3rd TO 4th Floor | 42877 | 42882 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6550 | Steel Reinforcement For Parapet Axis A12 TO B7/B18 | Steel Reinforcemnt | Parapet | 85.90 TO 88.90 | 23rd Floor | 42877 | 42882 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6551 | Apply Primary Coat Damp Proofing Axis C1 TO B2/A1 TO A6 | Damp Proofing | Slab On Grade | -10.50 | B2 Floor | 42879 | 42882 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6552 | Steel Reinforcement For Slab On Grade Axis B8 TO B12/A10 To A15 | Steel Reinforcement | Slab On Grade | -10.50 | B2 Floor | 42878 | 42887 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6553 | Repair For Core 3 Axis B11 TO B12/A9 TO A11 | Repair | COre | 30.10 TO 79.60 | 7rd TO 22nd Floor | 42878 | 42882 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6554 | Form Work For Parapet Axis B6 TO B18/A11 | Form Work | Parapet | 85.90 TO 88.15 | 23rd Floor | 42879 | 42882 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6555 | Surface Preparation Prior TO Apply Damp Proofing Axis C1 TO B2/A1 TO A6 | Damp Proofing | Surface Preparation | -10.50 | B2 Floor | 42879 | 42882 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6556 | Apply Primer Coat Damp Proofing Axis B6 TO B8/A8 TO A10 | Damp Proofing | Slab On Grade | -10.50 | B2 Floor | 42879 | 42887 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6557 | Primer Coat Damp Proofing Axis A8 TO A10/B6 TO B8 | Damp Proofing | Slab On Grade | -10.50 | B2 Floor | 42882
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6558 | First Coat Damp Proofing Axis A9 TO A11/B3 TO B6 | Damp Proofing | Slab On Grade | -10.50 | B2 Floor | 42882 | 42887 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6559 | Form Work For Stair 10 | Form Work | Stair | 20.10 TO23.40 | 4th TO5th Floor | 42883 | 42887 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6560 | Form Work For Stair 4 | Form Work | Stair | 33.30 TO 36.60 | 8th TO 9th Floor | 42883 | 42887 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6561 | Steel Reinforcement For Slab On Grade Axis A11 TO A14/B12 TO B13 | Steel Reinforcement | Slab On Grade | -10.50 | B2 FLoor | 42884 | 42887 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6562 | Apply Primer Coat Damp Proofing Axis A3 TO A6/B5 ToB6 As Per Attached | Damp Proofing | Slab On Grade | -10.5 | B2 FLoor | 42885 | 42891 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6563 | Surface Preparation Prior TO Apply Damp Proofing Axis A3 To A6/B5 To B6 As Per Attached | Damp Proofing | Surface Preparation | -10.50 | B2 Floor | 42885 | 42891 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6564 | Steel Reinforcement For Slab On Grade Axis A10 TO A15/B3 TO B8 | Steel Reinforcement | Slab On Grade | -10.50 | B2 Floor | 42886 | 42891 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6565 | Apply Second Coat Damp Proofing Axis A8 TO A11/B3 TO B6 | Damp Proofing | Slab On Grade | -10.50 | B2 Floor | 42886 | 42891 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6566 | Inspection For Holes and Dowels Fixation For Pads Axis B1 TO B4/A4 TO A6 | Holes And Dowels Fixation | Pads | -3.8 | BOH | 42886 | 42893 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6567 | Apply First Coat Damp Proofing Axis A8 TO A10/B6 TO B8 | Damp Proofing | Slab On Grade | -10.50 | B2 Floor | 42887 | 42893 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6568 | Apply First Coat Damp Proofing Axis A3 TO A6/B5 TO B6 | Damp Proofing | Slab On Grade | -10.50 | B2 Floor | 42887 | 42893 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6569 | Surface Preparation And Repair For ELEV-02 & ELEV-03 | Repair Elev | Surface Preparation | - | 4th TO 22nd | 42889 | 42893 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6570 | Apply First Coat Isolation (Internal) For The Main Swimming Pool | Swimming Pool | Swimming Pool | 1.10 | Basement | 42890 | 42894 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6571 | Apply Second Coat Damp Proofing Axis A3 TO A6/B5 TO B6 | Slab on grade | Damp proofing | -10.5 | B2 Floor | 42891 | 42893 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6572 | Compaction Test For Backfilling Under Slab On Grade Axis A2 TO A9/B2 TO B4 | Back Filling | Compaction | -10.50 | B2 Floor | 42891 | 42899 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6573 | Form Work For Concrete Bases Axis Boiler Room As Per Attached | Concrete Bases | Bases | -3.8 | BOH | 42891 | 42894 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6574 | Steel Reinforcement For Concrete Bases Axis Boiler Room As Per Attached | Concrete Bases | Concrete | -3.80 | BOH | 42891 | 42894 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6575 | Steel Reinforcement For Stair10 Axis A8 To A9/B14 TO B15 | Steel Reinforcement | Stair 10 | 20.10 To 23.40 | 4th To 5th Floor | 42892 | 42897 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6576 | Steel Reinforcement For Stair 4 Axis A10/B7 TO B8 | Steel Reinforcement | Stair 4 | 33.30 TO 36.60 | 8th TO 9th Floor | 42892 | 42897 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6577 | Apply Final Coat Isolation (Internal) For The main Swimming Pool | Swimming Pool | Swimming Pool | 1.10 | Basement | 42893 | 42897 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6578 | Steel Reinforcement For Slab On Grade Axis A1 To A3/B3 To B9 | Steel Reinforcement | Slab On Grade | -10.50 | B2 Floor | 42894 | 42899 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6579 | Compaction Test For Backfilling Under Slab On Grade Axis A8 TO A14/B19 TO B21 | Back Filling | Slab On Grade | -10.50 | B2 Floor | 42894 | 42903 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6580 | Steel Reinforcement For Slab On Grade Axis A4 To A5/B13 To B18 | Steel Reinforcement | Slab On Grade | -10.50 | B2 Floor | 42894 | 42897 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6581 | Apply First Coat Isolation (Internal) For The child Swimming Pool | Swimming Pool | Swimming Pool | 1.1 | Basement | 42903 | 42906 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6582 | Repair Work For Elevator (7) Core(3) | Repair Elev | Core | 1.10 TO 46.60 | GR TO 12th Floor | 42896 | 42899 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6583 | Steel Reinforcement For Upper Roof Slab Axis B10 To B11/A2 To A3 | Upper Roof Slab | Steel Reinforcement | 90.02 | Upper Roof | 42898 | 42903 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6584 | Repair Work For Elevator (7) Core(3) | Repair Elev | Core | 1.10 | 13th To 22th Floor | 42898 | 42903 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6585 | Steel Reinforcement For Pump Room Pads Axis As Pe Attached | Pump Room Pads | Steel Reinforcement | -10.5 | B2 Floor | 42898 | 42903 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6586 | Apply Final (Third) Coat Isolation (Internal) For The main Swimming Pool | Swimming Pool | Swimming Pool | 1.10 | Basement | 42898 | 42903 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6587 | Steel Reinforcement For Parapet For Core 8 Axis B1 TO B2/A3 | Steel Reinforcement | Core | 86.70 TO 90.27 | X | 42899 | 42903 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6588 | Steel Reinforcement For Slab On Grade Axis A6 To A15/B1 TO B3 | Steel Reinforcement | Slab On Grade | -10.50 | B2 Floor | 42899 | 42903 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6589 | Steel Reinforcement For Slab On Grade Axis A3 TO A6/B1 TO B4 | Steel Reinforcement | Slab On Grade | -10.50 | B2 Floor | 42899 | 42905 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6590 | Steel Reinforcemnt For RMU Slab Axis B16 TO B19/A14 | Steel Reinforcement | Slab | -10.50 | RMU | 42900 | 42905 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6591 | Compaction Test For Backfilling Under Slab On Grade Axis B3 TO B13/A6 TO A11 | Back Filling | Slab On Grade | -10.5 | B2 Floor | 42901 | 42913 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6592 | Steel Reinforcement For Slab On Grade Axis B19 TO B21/A7 TO A15 | Steel Reinforcement | Slab On Grade | -10.5 | B2 Floor | 42901 | 42905 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6593 | Compaction Test For Backfilling Under Slab On Grade Axis B16 TO B19/A6 TO A12 | Back Filling | Slab On Grade | -10.5 | B2 Floor | 42904 | 42913 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6594 | Form Work For Rmu Columns | Form Work | Rmu Columns | 4.85 | X | 42904 | 42906 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6595 | Form Work For Rmu Slab | Form Work | Rmu Slab | 4.85 | X | 42904 | 42905 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6596 | Steel Reinforcemet For Rmu Columns | Steel Reinforcement | Rmu Columns | 4.85 | X | 42904 | 42905 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6597 | Check Form Work For RMU Room Roof and Columun as Shown In Attached Sketch | Form Work | Rmu Columns | 4.85 | X | 42905 | 42907 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6598 | Steel Reinforcemet For Concrete Posts Axis B14 To B15 To A7 To A10 | Steel Reinforcement | Posts | 82.90 To 88.15 | Upper Roof | 42906 | 42913 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6599 | Form Work For Concrete Posts Axis B14 To B15/A7 To A10 | Form Work | Posts | 82.90 To 88.15 | Upper Roof | 42906 | 42913 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6600 | Apply Second Coat Isolation (Internal) For The Child Swimming Pool | Isolation Internal | Swimming Pool | 1.10 | Basement | 42906 | 42913 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6601 | Compaction Test For Backfilling Under Slab On Grade Axis B3 TO B9/A5 TO A11 | Back Filling | Slab On Grade | -10.5 | B2 Floor | 42907 | 42920 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6602 | Apply Third (Final) Coat Isolation (Internal)for the Child Swimming Pool | Swimming Pool | Isolation | 1.1 | Basement | 42907 | 42913 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6603 | Water Test For Swimming Pools | Swimming Pool | Isolation | 1.1 | Basement | 42917 | 42920 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6604 | Steel Reinforcement For Slab On Grade Axis B16 To B19/A6 To A12 | Steel Reinforcement | Slab On Grade (Rc) | -10.50 | B2 Floor | 42918 | 42926 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6605 | Steel Reinforcement For Slab On Grade Axis B3 To B8/A5 To A11 | Steel Reinforcement | Slab On Grade (Rc) | -10.50 | B2 Floor | 42918 | 42938 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6606 | Steel Reinforcement For Slab On Grade Axis B13 To B19/A11 To A15 | Steel Reinforcement | Slab On Grade (Rc) | -10.50 | B2 Floor | 42919 | 42920 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6607 | Repaire For Core 6 To Close NCR 176 | Core 6 | NCR#176 | -7.2 | B1 Floor | 42921 | 42926 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6608 | Formwork For Stair 10 Axis A8 To A9/B14 To B15 | Stair 10 | Form Work | 23.40 TO 26.70 | 5th TO 6th Floor | 42921 | 42925 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6609 | Form Work For Rmu Inverted Beams Axis A14/B16 To B19 | Rmu Inverted Beams | Rmu Beams | 4.85 To 5.25 |  | 42921 | 42925 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6610 | Steel Reinforcement For Stair 10 Axis A8 To A9/B14 TO B15 | Stair 10 | Steel Reinforcement | 23.40 to 26.70 | 5th TO 6th Floor | 42925 | 42929 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6611 | Form Work For Screed Axis (B2 To B6/A11 To A15) & ( A4 To A6/B1 To B3) | Screed | Form Work | -3.8 | BOH | 42926 | 42929 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6612 | Form Work For Stair 4 Axis A10/B7 To B8 | Stair 4 | Form Work | 36.60 to 39.90 | 9th to 10th Floor | 42927 | 42931 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6613 | Compaction Test for Backfilling under Slab on grade Axis B5 To B13/A4 To A5 | Slab on grade | Compaction | -10.5 | B2 | 42928 | 42936 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6614 | Surface Preparation Prior To Repair For Stair 10 Axis As Per Attached | Stair 10 | Surface Preparation | X | 3rd TO 4th Floor | 42933 | 42938 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6615 | Steel Reinforcement For Stair 4 Axis A10/B7 To B8 | Stair 4 | Steel Reinforcement | 36.0 to 39.90 | 9th to 10th Floor | 42934 | 42936 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6616 | Compaction Test For BACKFILLING Under Slab on grade Axis A6 To A10/B8 To B12 | Slab on grade | Compaction | -10.5 | B2 | 42934 | 42938 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6617 | Steel Reinforcement For Slab on grade Axis B5 To B8/A4 To A6 | Slab on grade | Steel Reinforcement | -10.5 | B2 | 42935 | 42938 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6618 | Compaction Test For BackFilling Under slab on grade Axis A5 To A11/B12 To B15 | Slab on grade | Compaction | -10.5 | B2 | 42936 | 42945 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6619 | Steel Reinforcement For Slab on grade Axis B6 To B12/A4 To A7 | Slab on grade | Steel Reinforcement | -10.5 | B2 | 42940 | 42945 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6620 | Form Work For Parapet For RMU Axis As per attached | RMU | Form Work | 1.1 |  | 42940 | 42943 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6621 | Steel Reinforcement For Parapet For RMU Axis As per attached | RMU | Steel Reinforcement | 1.1 |  | 42940 | 42943 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6622 | Form Work For UPSTAND Axis B10 To B14/A6 | UPSTAND | Form Work | 15.3 | 3rd | 42941 | 42945 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6623 | Steel Reinforcement For UPSTANd Axis B10 To B14/A6 | UPSTAND | Steel Reinforcement | 15.3 | 3rd | 42941 | 42945 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6624 | Check Formwork at upper roof slab for core 3 as shown in attached sketch Axis Core 3 | slab third stage | Form Work | 88.15 | Upper Roof slab core 3 | 42941 | 42949 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6625 | Check Formwork at upper roof slab for core 5 as shown in attached sketch Axis Core 5 | slab third stage | Form Work | 88.15 | Upper Roof slab core 5 | 42941 | 42949 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6626 | Repair For Stair 10 Axis As per Attached | Stair 10 | Repair |  | 3rd TO 4th Floor | 42942 | 42945 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6627 | Reinforced Steel prior to apply shot crete (internal) for the swimming pool Axis As per attached | Swimming Pool | Steel Reinforcement | 1.1 |  | 42942 | 42945 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6628 | Steel Reinforcement For UPSTAND Axis As per attached | UPSTAND | Steel Reinforcement | 15.3 | 3rd | 42942 | 42945 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6629 | FormWork For UPSTAND As per attached | UPSTAND | Form Work | 15.3 | 3rd | 42942 | 42945 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6630 | Compaction Test For BackFiling Under Slab on grade Axis A5 To A8/B13 To B21 | Slab on grade | Compaction | -10.5 | B2 Floor | 42943 | 42949 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6631 | Steel Reinforcement For Slab on grade Axis A6 To A11/B6 To B13 | Slab on grade | Steel Reinforcement | -10.5 | B2 Floor | 42943 | 42953 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6632 | FormWork For Stair 10 Axis A8 To A9/B14 To B15 | Stair 10 | Form Work | 26.70 to 30.00 | 6th To 7th Floor | 42946 | 42955 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6633 | Steel Reinforcement for Stair 10 Axis A8 to A9/B14 TO B15 | Stair 10 | Steel Reinforcement | 26.70 to 30.00 | 6th To 7th Floor | 42946 | 42949 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6634 | Formwork For Stair 4 Axis A10/B7 To B8 | Stair 4 | Form Work | 39.90 to 43.20 | 10th to 11th Floor | 42946 | 42955 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6635 | Steel Reinforcement For Stair 4 Axis A10/B7 To B8 | Stair 4 | Steel Reinforcement | 39.90 to 43.20 | 10th to 11th Floor | 42946 | 42953 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6636 | Check Formwork at Upper roof slab for core 2 as shown in attached sketch | upper Roof Slab core 2 | Form Work | 88.15 | core 2 | 42946 | 42949 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6637 | Steel Reinforcement For upper Roof Slab of Core 3 Axis A9 To A10/B10 To B12 | Upper Roof Slab | Steel Reinforcement | 88.15 | Roof | 42954 | 42964 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6638 | SURFACE PREPARATION AND REPAIR FOR ELEV. 8,9 Axis A7 To A9/B15 To B16 | Repair Elev | Surface preparation |  | 4th to 10th Floor | 42947 | 42953 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6639 | Steel Reinforcement For Parapet For core (7) Axis A2 To A3/B11 To B12 | Parapet for Core (7) | Steel Reinforcement | 91.57 | Roof | 42948 | 42953 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6640 | Steel Reinforcement for Upper Roof slab Core (8) Axis A1 To A3/B1 | Upper Roof Core (8) | Steel Reinforcement | 90.27 to 91.57 | Roof | 42948 | 42953 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6641 | Steel Reinforcement For Slab on Grade Axis A3 To A5/B3 To B7 | Slab on grade | Steel Reinforcement | -10.5 | B2 | 42950 | 42953 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6642 | Steel Reinforcement For Slab on grade Axis A5 To A12/B11 To B13 | Slab on grade (RC) | Steel Reinforcement | -10.5 | B2 | 42952 | 42955 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6643 | Steel Reinforcement For Slab on grade Axis A6 To A12/B13 To B17 | Slab on grade (RC) | Steel Reinforcement | -10.5 | B2 | 42952 | 42961 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6644 | Steel Reinforcement For Stair 10 Axis A8 To A9/B14 TO B15 | Stair 10 | Steel Reinforcement | 30.00 TO 33.30 | 7th TO 8th Floor | 42953 | 42964 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6645 | Formwork For Stair 10 Axis A8 To A9/B14 To B15 | Stair 10 | Form Work | 30.00 TO 33.30 | 7th TO 8th Floor | 42953 | 42956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6646 | Steel Reinforcement For Stair 4 Axis A10/B7 To B8 | Stair 4 | Steel Reinforcement | 43.20 to 46.50 | 11th To 12th Floor | 42953 | 42964 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6647 | Formwork For Stair 4 Axis A10/B7 To B8 | Stair 4 | Form Work | 43.20 to 46.50 | 11th To 12th Floor | 42953 | 42956 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6648 | Steel Reinforcement For Slab on grade Axis A5 To A6/B13 To B21 | Slab on grade ( RC ) | Steel Reinforcement | -10.5 | B2 Floor | 42955 | 42957 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6649 | Formwork For Screed Axis C1 To B6/A1 To A8 | Screed | Form Work | -3.8 | BOH | 42957 | 42961 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6650 | Surface Preparation and Repair for Elev. 8.9 | Repair Elev | Surface preparation |  | B2 To 4th Floor | 42960 | 42964 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6651 | Repair For Slab On grade to close NCR # 217 Axis (B5 To B6/A2 To A3) & (B8 To C6/A2 To A3) | Slab on grade | REpair | -10.5 | B2 Floor | 42963 | 42967 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6652 | Steel Reinforcement for upper roof slab of core 5 | Upper Roof Slab core 5 | Steel Reinforcement | 88.15 | Upper Roof | 42964 | 42967 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6653 | Factory Inspection For Fabrication for SPA Stair | SPA Stair | Factory Inspection | 10.30 TO 15.20 |  | 42967 | 42969 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6654 | Pouring Sika Dure 42 Under Base Plates For Space Truss | Space Truss | Sika Dure | 14.20 To 15.20 | 3rd | 42967 | 42969 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6655 | Installation For Space Truss | Space Truss | Installation | 14.20 To 15.20 | 3rd | 42967 | 42974 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6656 | Surface Preparation And Repair For ELEV .8.9 | Repair Elev | Surface preparation |  | 10th To 22th Floor | 42969 | 42977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6657 | Steel Reinforcement For RMU ROOM | Slab on Grade | Steel Reinforcement | 1.25 | Ground Floor | 42969 | 42974 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6658 | Steel Reinforcement For Upper Roof Slab CORE (2) | Upper Roof Slab Core (2) | Steel Reinforcement | 88.15 | Upper Roof | 42973 | 42977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6659 | Grouting for ducts of post tension slab Hotel tower Axis B6 To B16/A1 To A3 Upper Roof Slab | Grouting | post tension | 85.27 | 23th floor | 42974 | 42977 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6660 | Grouting for ducts of second stage post tension slab Hotel tower Axis B6 To B19/A1 To A3 | Grouting | post tension | 81.27 | 23th floor | 42974 | 42977 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6661 | Form Work for upper Roof Parapet Axis C7/ C8 To A2 Core (7) | Upper Roof Parapet | Form Work | 90.02 To 91.57 |  | 42974 | 42977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6662 | Steel Reinforcement For Stair 4 Axis A10/B7 To b8 | Stair4 | Steel Reinforcement | 46.50 TO 49.80 | 12th to 13th Floor | 42975 | 42977 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6663 | Formwork For Stair 4 Axis A10/B7 To b8 | Stair4 | Form Work | 46.50 TO 49.80 | 12th to 13th Floor | 42975 | 42977 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6664 | Formwork For Screed Axis A8 To A11/B12 To B19 | Screed BOH | Form Work | -3.8 | BOH | 42988 | 42990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6665 | Formwork For Screed Axis A13 To A15/B13 To B19 | Screed BOH | Form Work | -3.8 | BOH | 42988 | 42990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6666 | Formwork For Upper Roof Parapet Axis A2 To A3/B1 | Parapet | Form Work | 92.07 | Upper Roof | 42989 | 42990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6667 | Steel Reinforcement For Upper Roof Parapet Axis A2 To A3/B1 | Parapet | Steel Reinforcement | 92.07 | Upper Roof | 42989 | 42990 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6668 | Steel Reinforcement For Stair 14 Axis A1/B15 To B17 | Stair 14 | Steel Reinforcement | 77.9 To 81.27 |  | 42989
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6669 | Fromwork For Stair 10 | Stair 10 | Form Work | 36.60 to 39.90 | 9th to 10th Floor | 42996 | 43005 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6670 | Steel Reinforcement For Stair 10 | Stair 10 | Steel Reinforcement | 36.60 to 39.90 | 9th to 10th Floor | 42996 | 43005 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6671 | Formwork For Stair 4 | Stair 4 | Form Work | 49.80 To 53.10 | 13th To 14th Floor | 42998 | 43005 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6672 | Steel Reinforcement For Stair 4 | Stair 4 | Steel Reinforcement | 49.80 To 53.10 | 13th To 14th Floor | 42998 | 43005 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6673 | Steel Reinforcement For Slab on Grade Axis A1 To A3 /B1 To B2 & A6 To A8/B1 To b2 | Slab on grade | Steel Reinforcement | -3.8 | B2 | 43010 | 43011 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6674 | Formwork For Stair 10 | Stair 10 | Form Work |  | 10th to 11th Floor | 43010 | 43015 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6675 | Steel Reinforcement For Stair 10 | Stair 10 | Steel Reinforcement |  | 10th to 11th Floor | 43010 | 43018 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6676 | Steel Reinforcement For Stair 4 | Stair 4 | Steel Reinforcement |  | 14th To 15th Floor | 43010 | 43018 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6677 | Formwork For Stair 4 | Stair 4 | Form Work |  | 14th To 15th Floor | 43010 | 43015 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6678 | Formwork For SHALLOW POOL (2) Axis A5 TO A6/B12 To B13 | Shallow Pool | Form Work | 1.1 |  | 43010 | 43018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6679 | Reinforced Steel For Shallow Pool (2) Axis A5 To A6/B12 To B13 | Shallow Pool | Steel Reinforcement | 1.1 |  | 43010 | 43018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6680 | Reinforced Steel For Fountain (1) Axis A4 To A5/B19 To B20 | Fountain (1) | Steel Reinforcement | 1.1 |  | 43010 | 43018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6681 | Formwork For Fountain (1) Axis A4 To A5/B19 To B20 | Fountain (1) | Form Work | 1.1 |  | 43010 | 43018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6682 | Formwork For Screed Axis A7 To A11/B9 To B14 | Screed | Form Work | 15.3 | 3rd | 43011 | 43015 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6683 | Formwork For Concrete Roof Posts Axis A6 To A8/B6 To B9 | Residential Roof Posts | Form Work |  | Roof | 43015 | 43015 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6684 | Shot Crete For Swimming Pool Main & Shallow | Swimming Pool | Shot Crete | 1.1 |  | 43015 | 43018 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6685 | Form Work For Screed Axis A9 To A11/B7 To B11 | Screed | Form Work | 5.5 | 1st | 43017 | 43020 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6686 | Form Work For Screed Axis A9 To A11/B9 To B10 | Screed | Form Work | 10.4 | 2nd | 43017 | 43020 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6687 | Installation For SPA Stair | SPA_Stair | Installation | 10.30 TO 15.20 | 2nd To 3rd Floor | 43024 | 43047 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6688 | Formwork For Stair 4 | Stair 4 | Form Work |  | 15th To 16th Floor | 43025 | 43030 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6689 | Steel Reinforced For Stair 4 | Stair 4 | Steel Reinforcement |  | 15th To 16th Floor | 43025 | 43030 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6690 | Formwork For Stair 10 | Stair 10 | Form Work |  | 11th To 12th Floor | 43025 | 43030 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6691 | Steel Reinforced For Stair 10 | Stair 10 | Steel Reinforcement |  | 11th To 12th Floor | 43025 | 43030 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6692 | Steel Reinforcement For Roof Concrete Posts Axis A4 To A12/B4 To B9 | Concrete Posts | Steel Reinforcement | 88.25 | Roof | 43030 | 43036 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6693 | Formwork For Roof Concrete Posts Axis A4 To A12/B4 To B9 | Concrete Posts | Form Work | 88.25 | Roof | 43030 | 43036 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6694 | Check Level of S.O.G after pour at 1.10 as shown in attached sketch |  |  | 1.1 | Ground Floor | 43030 | 43038 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6695 | Formwork For HELICAL STAIR BEAM | HELICAL STAIR BEAM | Form Work | 5.4 |  | 43031 | 43039 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6696 | Reinforced Steel For HELICAL STAIR BEAM | HELICAL STAIR BEAM | Steel Reinforcement | 5.4 |  | 43031 | 43039 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6697 | Formwork for Stair 4 | Stair 4 | Form Work |  | 16-17Floor | 43034 | 43039 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6698 | Reinforced Steel For Stair 4 | Stair 4 | Steel Reinforcement |  | 16-17Floor | 43034 | 43039 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6699 | Reinforced Steel For Stair 10 | Stair 10 | Steel Reinforcement |  | 12th to 13th Floor | 43034 | 43039 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6700 | Formwork for Stair 10 | Stair 10 | Form Work |  | 12th to 13th Floor | 43034 | 43039 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6701 | Rectifying comments For CIR#6667 For Soace Truss Insrallation | Space Truss |  | 14.20 To 15.20 | 3rd | 43040 | 43045 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6702 | Formwork For Stair 10 | Stair 10 | Form Work |  | 13th To 14th Floor | 43045 | 43047 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6703 | Reinforced Steel For Stair 10 | Stair 10 | Steel Reinforcement |  | 13th To 14th Floor | 43045 | 43047 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6704 | Reinforced Steel For Panoramic elevator columns | Panoramic elevator |  | -10.5 | B2 | 43045 | 43051 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6705 | Formwork For Panoramic elevator columns | Panoramic elevator |  | -10.5 | B2 | 43045 | 43055 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6706 | Formwork For Panoramic elevator columns | Panoramic elevator |  | -7.2 | B1 Floor | 43045 | 43055 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6707 | Reinforced Steel For Panoramic elevator columns | Panoramic elevator |  | -7.2 | B1 Floor | 43045 | 43055 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6708 | Formwork For Concrete Roof Posts Axis A4 To A12/B9 To B18 | Concrete Posts | Form Work | 88.25 | Roof | 43051 | 43055 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6709 | Reinforced Steel For Concrete Roof Posts Axis A4 To A12/B9 To B18 | Concrete Posts | Steel Reinforcement | 88.25 | Roof | 43051 | 43055 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6710 | Surface Preparation prior to water Proofing for 2 fountains | Fountain | Surface preparation | 1.1 | Ground Floor | 43057 | 43059 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6711 | Steel Reinforcement for Ground Columns Axis B19 To B21/A1 | Ground Columns | Steel Reinforcement | 1.1 | Ground Floor | 43057 | 43059 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6712 | Formwork for Ground Columns Axis B19 To B21/A1 | Ground Columns | Form Work | 1.1 | Ground Floor | 43057 | 43060 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6713 | Formwork For Stair 10 | Stair 10 | Form Work |  | 14th To 15th Floor | 43058 | 43059 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6714 | Steel Reinforcement For Stair 10 | Stair 10 | Steel Reinforcement |  | 14th To 15th Floor | 43058 | 43059 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6715 | Steel Reinforcement For Ground Columns Axis A1 To A2/B3 To B4 | Ground Shaft | Steel Reinforcement | 1.1 | Ground Floor | 43062 | 43068 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6716 | Formwork For Ground Columns Axis A1 To A2/B3 To B4 | Ground Shaft | Form Work | 1.1 | Ground Floor | 43062 | 43068 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6717 | Steel Reinforcement For Ground SHAFT Axis A1 To A2/B6 To B7 | Ground Shaft | Steel Reinforcement | 1.1 | Ground Floor | 43065 | 43068 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6718 | Formwork For Ground SHAFT Axis A1 To A2/B6 To B7 | Ground Shaft | Form Work | 1.1 | Ground Floor | 43065 | 43068 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6719 | 1st coat waterproofing for fountain no.(1) | Fountain (1) | Waterproofing | 1.1 | Ground Floor | 43074 | 43078 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6720 | Surface preparation prior to waterproofing for fountain no(2) | Fountain (2) | Waterproofing | 1.1 | Ground Floor | 43074 | 43078 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6721 | Formwork For Stair 10 | Stair 10 | Form Work |  | 15th To 16th Floor | 43074 | 43078 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6722 | Steel Reinforcement For Stair 10 | Stair 10 | Steel Reinforcement |  | 15th To 16th Floor | 43074 | 43078 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6723 | Formwork For Shafts opennings Axis A1 To A2/B2 To B9 | Shaft opennings | Form Work | 1.1 | Ground Floor | 43075 | 43078 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6724 | Steel Reinforcement For Shafts opennings Axis A1 To A2/B2 To B9 | Shaft opennings | Steel Reinforcement | 1.1 | Ground Floor | 43075 | 43078 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6725 | Third Coat Waterproofing For fountain (1) | Fountain (1) | Waterproofing | 1.1 | Ground Floor | 43078 | 43083 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6726 | Second Coat Waterproofing For fountain (1) | Fountain (1) | Waterproofing | 1.1 | Ground Floor | 43078 | 43083 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6727 | Steel Reinforcement For Panoramic elevator columns | Panoramic elevator columns | Steel Reinforcement | -3.8 | BOH | 43078 | 43083 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6728 | Formwork For Panoramic elevator columns | Panoramic elevator columns | Form Work | -3.8 | BOH | 43078 | 43083 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6729 | Steel Reinforcement For Panoramic elevator columns | Panoramic elevator columns | Steel Reinforcement | -3.8 | BOH | 43082 | 43083 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6730 | 1st coat waterproofing for fountain no.(2) | Fountain (2) | Waterproofing | 1.1 | Ground Floor | 43087 | 43088 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6731 | 1st coat waterproofing for fountain no.(3) | Fountain (3) | Waterproofing | 1.1 | Ground Floor | 43087 | 43088 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6732 | 2nd coat waterproofing for fountain no.(3) | Fountain (3) | Waterproofing | 1.1 | Ground Floor | 43088 | 43092 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6733 | 3rd coat waterproofing for fountain no.(3) | Fountain (3) | Waterproofing | 1.1 | Ground Floor | 43088 | 43092 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6734 | 2nd coat waterproofing for fountain no.(2) | Fountain (2) | Waterproofing | 1.1 | Ground Floor | 43088 | 43092 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6735 | 3rd coat waterproofing for fountain no.(2) | Fountain (2) | Waterproofing | 1.1 | Ground Floor | 43088 | 43092 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6736 | Formwork For Stair 10 | Stair 10 | Form Work |  | 16-17Floor | 43090 | 43095 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6737 | Steel Reinforcement For Stair 10 | Stair 10 | Steel Reinforcement |  | 16-17Floor | 43090 | 43094 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6738 | Water Test For Fountain No (1) | Fountain (1) | Water Test | 1.1 | Ground Floor | 43089 | 43093 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6739 | Factory Inspection For Helical Stair | HELICAL STAIR | Factory Inspection |  |  | 43090 | 43093 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6740 | Water Test For Fountain No (3) | Fountain (3) | Water Test | 1.1 | Ground Floor | 43090 | 43093 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6741 | Water Test For Fountain No (2) | Fountain (2) | Water Test | 1.1 | Ground Floor | 43090 | 43093 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6742 | Steel Reinforcement For Panoramic elevator columns | Panoramic Elevator columns | Steel Reinforcement | 1.10 To 5.40 | Ground Floor | 43095 | 43097 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6743 | Steel Reinforcement For Ground Shaft | Shaft opennings | Steel Reinforcement | 1.1 | Ground Floor | 43097 | 43101 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6744 | Formwork For Ground Shaft | Shaft opennings | Form Work | 1.1 | Ground Floor | 43097 | 43101 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6745 | Formwork For Panoramic elevator columns | Panoramic Elevator columns | Form Work | 1.10 To 5.40 | Ground Floor | 43097 | 43106 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6746 | Steel Reinforcement For Mashrabia Columns | Mashrabia Columns | Steel Reinforcement | 1.10 To 5.40 | Ground Floor | 43099 | 43101 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6747 | Formwork For Mashrabia Columns | Mashrabia Columns | Form Work | 1.10 To 5.40 | Ground Floor | 43099 | 43101 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6748 | Compaction Test For BackFiling Under Slab on grade Axis A5 To A6/B9 To B12 | Slab on grade | Compaction | -10.5 | B2 | 43101 | 43106 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6749 | Steel Reinforcement for Slab on grade Axis A5 To A6/B9 To B12 | Slab on grade | Steel Reinforcement | -10.5 | B2 | 43101 | 43109 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6750 | Formwork For Mashrabia Beam only Axis B9/C6 | Mashrabia Slab | Form Work | 5.4 |  | 43102 | 43111 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6751 | Steel Reinforcement For Mashrabia Beam only Axis B9/C6 | Mashrabia Slab | Steel Reinforcement | 5.4 |  | 43102 | 43111 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6752 | Factory Inspection For Helical Stair Primer Coat | HELICAL STAIR | Factory Inspection |  |  | 43103 | 43106 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6753 | Steel Reinforcement For Mashrabia Beam Axis B9/C6 | Mashrabia Beam | Steel Reinforcement | 10.3 |  | 43108 | 43111 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6754 | Formwork For Mashrabia Beam Axis B9/C6 | Mashrabia Beam | Form Work | 10.3 |  | 43108 | 43111 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6755 | Steel Reinforcement For Panoramic elevator columns | Panoramic Elevator columns | Steel Reinforcement | 1.10 To 5.40 | 1st To 2nd | 43109 | 43111 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6756 | Formwork For Panoramic elevator columns | Panoramic Elevator columns | Form Work | 1.10 To 5.40 | 1st To 2nd | 43109 | 43115 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6757 | Steel Reinforcement For Mashrabia Columns Axis B9 | Mashrabia Columns | Steel Reinforcement | 5.40 To 10.30 |  | 43117 | 43118 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6758 | Steel Reinforcement For Mashrabia Columns Axis B11 | Mashrabia Columns | Steel Reinforcement | 10.30 To 13.95 |  | 43117 | 43118 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6759 | Formwork For Mashrabia Columns Axis B9 | Mashrabia Columns | Form Work | 5.40 To 10.30 |  | 43117 | 43118 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6760 | Formwork For Mashrabia Columns Axis B11 | Mashrabia Columns | Form Work | 10.30 To 13.95 |  | 43117 | 43118 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6761 | Start Demolish For Parapet of Shallow Pool No .1 | Panoramic Elevator columns | Shallow Parapet | 1.1 | Ground Floor | 43118 | 43118 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6762 | Steel Reinforcement For Panoramic elevator columns | Panoramic Elevator columns | Steel Reinforcement | 10.30 To 15.20 |  | 43121 | 43122 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6763 | Formwork For Panoramic elevator columns | Panoramic Elevator columns | Form Work | 10.30 To 15.20 |  | 43121 | 43128 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6764 | Steel Reinforcement For Mashrabia Columns | Mashrabia Columns | Steel Reinforcement | 10.30 To 13.95 |  | 43121 | 43128 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6765 | Formwork For Mashrabia Columns | Mashrabia Columns | Form Work | 10.30 To 13.95 |  | 43121 | 43128 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6766 | Steel Reinforcement For Shallow Pool Floor | Fountain | Steel Reinforcement | 1.1 | Ground Floor | 43121 | 43128 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6767 | Reinforcement For Lintel Carried out By Planted Walls For Terrace Guest Room Axis A2 To A3/C3 To C5 | Lintel And Posts | Steel Reinforcement | 5.4 | 1st | 43128 | 43128 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6768 | Formwork For Lintel Carried Out By Planted Walls For Terrace Guest Room Axis A2 To A3/C3 To C5 | Lintel And Posts | Form Work | 5.4 | 1st | 43128 | 43128 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6769 | Installation For Helical Stair | HELICAL STAIR |  | 1.10 To 5.40 | Ground Floor | 43128 | 43128 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6770 | Reinforcement FOR FOUNTAIN PARAPET & slab Axis A4/B5 To B6 | Fountain parapet | Steel Reinforcement | 1.1 | Ground Floor | 43129 | 43135 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6771 | Formwork FOR FOUNTAIN PARAPET Axis A4/B5 To B6 | Fountain parapet | Form Work | 1.1 | Ground Floor | 43129 | 43136 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6772 | Steel Reinforcement For Panoramic elevator columns | Panoramic Elevator columns | Steel Reinforcement | 15.20 TO 20.10 |  | 43132 | 43136 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6773 | Formwork For Panoramic elevator columns | Panoramic Elevator columns | Form Work | 15.20 TO 20.10 |  | 43132 | 43136 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6774 | Steel Reinforcement For Shallow Pool Upstand | Shallow Pool Upstand | Steel Reinforcement | 1.1 | Ground Floor | 43137 | 43141 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6775 | Formwork For Shallow Pool Upstand | Shallow Pool Upstand | Form Work | 1.1 | Ground Floor | 43137 | 43141 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6776 | Steel Reinforcement For Panoramic elevator Beams | Panoramic Elevator Beams | Steel Reinforcement | 18.87 | Ground Floor | 43146 | 43146 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6777 | Formwork For Panoramic elevator Beams | Panoramic Elevator Beams | Form Work | 18.87 | Ground Floor | 43146 | 43152 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6778 | Steel Reinforcement For Lintel Carried out planted walls for terrace guest room Axis A2 To A3/C3 To C1 | Lintel And Posts | Steel Reinforcement | 5.4 | 1st | 43153 | 43155 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6779 | Formwork For Lintel Carried out planted walls for terrace guest room Axis A2 To A3/C3 To C1 | Lintel And Posts | Form Work | 5.4 | 1st | 43153 | 43155 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6780 | Surface Preparation and Repair for outer side for shear wall | outer shear wall | surface preparation | 1.10 To 5.40 | Ground Floor | 43174 | 43177 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6781 | Steel Reinforcement For Reer from 1.10 to 4.70 | Rear Entrance | Steel Reinforcement | 1.10 to 4.70 | Ground Floor | 43197 | 43202 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6782 | check level and Formwork For Reer Entrance slap at 4.70 | Rear Entrance | Form Work | 4.7 | Ground Floor | 43197 | 43202 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6783 | check level and Formwork of Reception Desk slap at 5.54 | Reception desk | Form Work | 5.54 | 1st | 43197 | 43213 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6784 | Surface Preparation and Repair for outer side for shear wall (2nd Strip) | outer shear wall | surface preparation |  | Ground Floor | 43198 | 43200 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6785 | Steel Reinforcement of column and beam from 1.10 to 3.45 | Main Entrance | Steel Reinforcement | 1.10 to 3.45 | Ground Floor | 43200 | 43213 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6786 | Driling for Holes for Implanting Dowels | Placing Boom Opening | Driling |  | 18th To 22nd | 43201 | 43202 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6787 | check level and Formwork of main entrance columns and beams from level 1.10 to 3.45 | Main Entrance | Form Work | 1.10 to 3.45 | Ground Floor | 43202 | 43208 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6788 | Steel Reinforcement For Placing Boom Openning | Placing Boom Opening | Steel Reinforcement |  | 18th To 22nd | 43206 | 43209 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6789 | check level and Steel Rainforcement of main entrance columns from level 4.05 To 8.35 | Main Entrance | Steel Reinforcement |  | Ground Floor | 43213 | 43214 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6790 | check level and Formwork of main entrance columns from level 4.05 to 8.35 | Main Entrance | Form Work |  | Ground Floor | 43213 | 43216 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6791 | check level and Steel Rainforcement for reception desk | Reception desk | Steel Reinforcement | 1.1 | Ground Floor | 43216 | 43230 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6792 | REPAIR WORK FOR BOILER ROOM SLAB Axis A4 to A5/B1 To B2 | Boiler Room Slab |  |  | B1 Floor | 43222 | 43226 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6793 | check level and Formwork of main entrance For Slab | Main Entrance | Form Work | 8.35 | Ground Floor | 43236 | 43237 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6794 | Repair For Core (7) | Repair |  |  | 4th to 8th Floor | 43237 | 43240 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6795 | check Reinforcement of main entrance For Slap | Main Entrance | Form Work | 8.35 | Ground Floor | 43246 | 43250 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6796 | check Steel Reinforcement for Green wall 2 from level 1.10 to 4.04 | Green Wall 2 | Steel Reinforcement | 1.1 | Ground Floor | 43256 | 43258 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6797 | check Formwork for Green wall 2 from level 1.10 to 4.04 | Green Wall 2 | Form Work | 1.1 | Ground Floor | 43256 | 43258 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6798 | check Steel Reinforcement for Green wall 2 from level 4.04 to 7.33 | Green Wall 2 | Steel Reinforcement |  | Ground Floor | 43261 | 43262 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6799 | check Formwork for Green wall 2 from level 4.04 to 7.33 | Green Wall 2 | Form Work |  | Ground Floor | 43261 | 43264 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6800 | Steel Reinforcement For Up stand Axis A5 To A6/B10 To B12 | Parapet | Steel Reinforcement |  | 2nd | 43276 | 43276 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6801 | Repair work for Elevator (2) & Elevator (3) | Repair Elev | Elevator 2&3 |  | B2 To 3rd | 43279 | 43288 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6802 | Repair work for Elevator (7) | Repair Elev | Elevator 7 | 1.10 To 46.60 | B2 To GR | 43279 | 43283 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6803 | Steel Reinforcement For Lintel Carried out planted walls for terrace guest room | Lintel And Posts | Steel Reinforcement | 10.3 | 2nd | 43286 | 43288 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6804 | Formwork For Lintel Carried out planted walls for terrace guest room | Lintel And Posts | Form Work | 10.3 | 2nd | 43286 | 43288 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6805 | Repair work for Elevator (10) | Repair Elev | Elevator 10 |  | B2 To 22nd | 43290 | 43296 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6806 | Repair work for Elevator (1) | Repair Elev | Elevator 1 |  | 15th To 22nd | 43305 | 43306 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6807 | Repair work for Elevator (5 & 6) | Repair Elev | Elevator 5 & 6 |  | B2 To 3rd | 43305 | 43306 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6808 | Repair work for Elevator Shaft (4 & 4`) | Repair Elev | Elevator 4 & 4` |  | BOH : Gr | 43314 | 43317 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6809 | Steel Renforcement for R7 SLAB | R7 Slab | Steel Reinforcement | 20.1 | 4th | 43338 | 43340 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6810 | Formwork for R7 SLAB | R7 Slab | Form Work | 20.1 | 4th | 43338 | 43340 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6811 | Check Reinforcement of columns and beams for green wall 1 | green Wall 1 | Steel Reinforcement | 1.1 | Ground Floor | 43346 | 43349 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6812 | Check Formwork of columns and beams for green wall 1 | green Wall 1 | Form Work | 1.1 | Ground Floor | 43346 | 43349 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6813 | Check Reinforcement of columns and beams for green wall 1 | green Wall 1 | Steel Reinforcement | 4.04 To 7.33 | Ground Floor | 43353 | 43356 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6814 | Check Formwork of columns and beams for green wall 1 | green Wall 1 | Form Work | 4.04 To 7.33 | Ground Floor | 43353 | 43356 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6815 | Shaping and implaanting steel reinforcement work for core walls Axis B6 To B8 | Core 5 | Steel Reinforcement |  | BOH | 43367 | 43369 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6816 | Shaping and implaanting steel reinforcement work for core walls | Core 5 | Steel Reinforcement |  | BOH | 43372 | 43374 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6817 | Surface Preparation and repair above steel frame door | Repair |  |  | B2 | 43382 | 43384 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6818 | Steel Renforcement for core walls (R18 ) | Core 5 | Steel Reinforcement |  | BOH | 43382 | 43384 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6819 | surface preparation and repair at elevator Shaft core 8 | Repair Elev | Elevator shaft 8 |  | 20th To 23rd | 43383 | 43384 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6820 | Steel Bars Repair AT (GF-51) | Repair | Steel Reinforcement |  |  | 43388 | 43389 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6821 | Form work For core wall R18 Axis (B6 To B8)/ ( A11 To A10) | Core 5 | Form Work |  | BOH | 43388 | 43389 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6822 | surface preparation and repair at elevator Shaft core 8 | Repair Elev | Elevator shaft 8 |  | 15th To 19th | 43390 | 43394 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6823 | shaping and lmplanting steel reinforcement work for slab (-7.20) | slab | Steel Reinforcement | -7.2 | B1 Floor | 43390 | 43394 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6824 | shaping and lmplanting steel reinforcement work for slab (-3.80) | slab | Steel Reinforcement | -3.8 | BOH | 43390 | 43394 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6825 | shaping and lmplanting steel reinforcement work for slab pump Room | slab | Steel Reinforcement | 1.1 | Ground Floor | 43391 | 43394 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6826 | Formwork for Slab Pump Room Opening | slab | Form Work | -7.2 | B1 Floor | 43391 | 43394 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6827 | Formwork for Slab Pump Room Opening | slab | Form Work | -3.8 | BOH | 43391 | 43394 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6828 | Formwork for Slab Pump Room Opening | slab | Form Work | 1.1 | Ground Floor | 43391 | 43394 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6829 | Steel Reinforcement for Slab Pump Room Opening | slab | Steel Reinforcement | 1.1 | Ground Floor | 43391 | 43394 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6830 | Steel Reinforcement for Slab Pump Room Opening | slab | Steel Reinforcement | -3.8 | BOH | 43391 | 43394 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6831 | Steel Reinforcement for Slab Pump Room Opening | slab | Steel Reinforcement | -7.2 | B1 Floor | 43391 | 43394 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6832 | surface preparation and repair at elevator Shaft core 8 | Repair Elev | Elevator shaft 8 |  | 10th To 14th | 43400 | 43402 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6833 | Steel Reinforcement work for core wall (R18) | Core 5 | R18 | -3.8 | BOH | 43401 | 43402 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6834 | Form work for core wall (R18) | Core 5 | R18 | -3.8 | BOH | 43402 | 43403 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6835 | Surface preparation and repair at pump room shaft | Repair | Surface preparation | -7.2 | B1 Floor | 43405 | 43408 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6836 | Surface preparation and repair at pump room shaft | Repair | Surface preparation | -3.8 | BOH | 43405 | 43408 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6837 | Surface preparation and repair at pump room shaft | Repair | Surface preparation | 1.1 | Ground Floor | 43405 | 43408 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6838 | surface preparation and repair at elevator Shaft core 8 | Repair Elev | Elevator shaft 8 |  | 5th To 9th | 43407 | 43408 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6839 | surface preparation and repair at elevator Shaft core 8 | Repair Elev | Elevator shaft 8 |  | 1st To 4th | 43418 | 43423 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6840 | Steel Reinforcement work for Lintels | Lintel | Steel Reinforcement |  | Ground Floor | 43421 | 43423 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6841 | Form work for Lintels | Lintel | Form Work |  | Ground Floor | 43421 | 43423 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6842 | surface preparation and repair at elevator Shaft core 8 | Repair Elev | Elevator shaft 8 |  | B2 To 1st | 43432 | 43435 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6843 | Injection and repair work to prevent water leakage at Elevator Shaft (8.9) Core 2 | Repair Elev | Elevator shaft 8.9 |  | B2 | 43438 | 43440 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6844 | shaping and implanted work for core wall (R18) Axis A9 To A11 /B6 | Core 5 | R18 | -3.8 | BoH | 43444 | 43446 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6845 | Steel Reinforcement work for core wall (R18) Axis (A9 To A11)/(B6) | Core 5 | R18 | -3.8 | BOH | 43450 | 43451 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6846 | Repair Work And surface preparaton Core (7)AS per Attached. | Repair | Core7 |  | 23:20th | 43454 | 43464 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6847 | Formwork for core wall (R18) Axis (A9 To A11)/(B6) | Core 5 | R18 | -3.8 | BOH | 43457 | 43464 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6848 | Repair Work And surface preparaton Core (7)AS per Attached. | Repair | Core7 |  | 10th To 19th | 43463 | 43464 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6849 | Repair Work And surface preparaton Core (7)AS per Attached. | Repair | Core7 |  | Grd To 9th | 43464 | 43467 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6850 | Repair Work And surface preparaton For Surge Tank Wall)AS per Attached. | Repair | Surge Tank |  | BOH | 43498 | 43500 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6851 | Installation of Swellable bar around penetrations of pipes for surge tank wall | Repair | Surge Tank |  | BOH | 43501 | 43506 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6852 | Shapping & Implanted For Reinforcement Work For core Walls | Core 2 | Entrance 2 GR-045 | +1.10 | #REF! | 43509 | 43510 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6853 | Shapping & Implanted Work In Core Wall AS Per Attached | Repair | Core2 |  | Ground Floor | 43510 | 43513 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6854 | Steel Reinforcement work for core wall (core 2) | Core 2 | Steel Reinforcement | +1.10 | Ground Floor | 43512 | 43513 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6855 | Form work for core wall (core 2) | Core 2 | Form Work | +1.10 | Ground Floor | 43515 | 43519 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6856 | site trail mix for jacketing works for concrete (class 400 kg/Cm2 | Jacketing works | trail mix |  | Ground : Third | 43515 | 43519 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6857 | Steel Reinforcement work for core wall (core 2) | Core 2 | Steel Reinforcement | +1.10 | Ground Floor | 43521 | 43524 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6858 | Form work for core wall (core 2) | Core 2 | Form Work |  | Ground Floor | 43523 | 43527 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6859 | Steel Reinforcement work for core wall (core 2) | Core 2 | Steel Reinforcement |  | 1st | 43523 | 43527 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6860 | Form work for core wall (core 2) | Core 2 | Form Work |  | 1st | 43523 | 43527 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6861 | Shaping and implanted Reinforcement in core wall | Repair | Core 3 |  | Ground Floor | 43524 | 43527 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6862 | shaping and surface preparation flooring to pour screed | Repair | Surface preparation |  | B1 Floor | 43529 | 43530 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6863 | Steel Reinforcement work for core walls (core 3) | Core 3 | Steel Reinforcement |  | Ground Floor | 43530 | 43531 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6864 | Repair and surface preparation for roof post (Core 5) | Repair | Surface preparation |  | Roof | 43531 | 43538 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6865 | Witnessing or site retrial mix of concrete class( 400kg/Cm2) for Jacketing and Staircases | Jacketing works | Concrete |  | Ground To 3rd | 43533 | 43535 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6866 | Shaping and implanted Reinforcement in core wall (3) | Core wall | Steel Reinforcement |  | Ground | 43535 | 43538 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6867 | Steel Reinforcement work in core wall (3) | Core wall | Steel Reinforcement |  | Ground | 43537 | 43538 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6868 | Shaping and implanted Reinforcement in core wall (5) | Core wall | Steel Reinforcement |  | Ground | 43543 | 43545 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6869 | Shaping and implanted Reinforcement in core slab (6) | core slab | Steel Reinforcement | -7.2 | B1 Floor | 43544 | 43548 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6870 | Form work for core slab (6) | core slab | Form Work | -7.2 | B1 Floor | 43544 | 43548 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6871 | Form work in core wall (3) | Core wall | Form Work |  | Ground | 43545 | 43548 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6872 | Steel Reinforcement work in core wall (5) | Core wall | Steel Reinforcement |  | Ground | 43549 | 43552 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6873 | Shaping and implanted Reinforcement in core wall (5) | Core wall | Steel Reinforcement |  | Ground | 43551 | 43555 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6874 | Bottom and top layer Steel reinforcement Work For Core slab (6) | core slab | Steel Reinforcement | -7.2 | B1 Floor | 43551 | 43555 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6875 | Repair and surface preparation for roof post (Core 2) | Repair | Surface preparation |  | Roof | 43554 | 43556 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6876 | Steel Reinforcement work in core wall (5) | Core wall | Steel Reinforcement |  | Ground | 43556 | 43559 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6877 | Form work in core wall (5) | Core wall | Form Work |  | Ground | 43559 | 43561 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6878 | Steel Reinforcement for Revolving Door Pit | Revolving Door | Steel Reinforcement | 1.1 | Ground | 43564 | 43568 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6879 | Form Work for Revolving Door Pit | Revolving Door | Form Work | 1.1 | Ground | 43564 | 43568 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6880 | Surface preparation works, prior to repair material mortar filling for slab soffit to close NCR- 0353 |  | Surface preparation |  | 8th | 43568 | 43569 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6881 | Shaping and implanted Reinforcement in core wall (5) | Core wall | Steel Reinforcement |  | 1st | 43576 | 43577 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6882 | Chipping & implanted work for shaft 14 | Core wall |  |  | 2nd | 43579 | 43583 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6883 | Chipping & implanted work for core 2 walls | Core wall |  |  | 2nd | 43579 | 43583 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6884 | Steel Reinforcement work in core wall (5) | Core wall | Steel Reinforcement |  | 1st | 43582 | 43583 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6885 | Steel Reinforcement work for Beam (9) | Beam (9) | Steel Reinforcement |  | 2nd | 43585 | 43587 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6886 | Formwork for wall core (5) | Core wall | Form Work |  | 1st | 43587 | 43587 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6887 | Steel Reinforcement work for Core Wall Shaft 14 As Per Attached. | Core 2 | Steel Reinforcement |  | 2nd | 43589 | 43590 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6888 | Formwork for Beam (9)As Per Attached. | Beam (9) | Form Work |  | 2nd | 43589 | 43590 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6889 | Shaping and implanted Steel Work For Shaft 14 As Per Attached. | Shaft 14 | Steel Shaft |  | 3rd | 43589 | 43590 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6890 | Installation Of Atrium Fan Support No# 1,2,3 AS Per Attached. | Fan Support. | Grid Lines .Atrium Fan Support (1,2,3) |  | 3rd | 43590 | 43594 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6891 | Shaping and implanted Steel Work For slab core (6) | Repair | Steel Reinforcement |  | BOH | 43594 | 43596 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6892 | Formwork For opening | Slab opening | Form Work |  | BOH | 43594 | 43596 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6893 | Installation Of Atrium Fan Support No# 4 AS Per Attached. | Fan Support. | Grid Lines .Atrium Fan Support (4) |  | 3rd | 43597 | 43598 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6894 | Form work for core wall shaft (14) | Shaft 14 | Form Work |  | 2nd | 43598 | 43599 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6895 | Steel Reinforcement for core wall shaft (14) | Shaft 14 | Steel Reinforcement |  | 3rd | 43598 | 43599 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6896 | shaping work for floor at lobby B1-001 | Repair | Shaping work |  | B1 Floor | 43598 | 43599 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6897 | Shaping and implanted For shafts 1 & 2 |  | Shaping work |  | Ground | 43598 | 43599 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6898 | Shaping and implanted For shafts 3 & 4 |  | Shaping work |  | Ground | 43599 | 43600 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6899 | Shaping and implanted For core wall (5) |  | Shaping work |  | 2nd | 43600 | 43601 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6900 | Shaping and implanted For core wall (5) |  | Shaping work |  | 3rd | 43600 | 43601 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6901 | Form work for core wall shaft (14) | Shaft 14 | Form Work |  | 3rd | 43600 | 43601 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6902 | Steel Reinforcement for shafts (1-2-3-4) |  | Steel Reinforcement |  | Ground | 43606 | 43608 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6903 | Formwork for shafts (1-2-3-4) |  | Form Work |  | Ground | 43606 | 43608 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6904 | Steel Reinforcement for core wall (5) | Core (5) | Steel Reinforcement |  | 2nd | 43612 | 43613 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6905 | Steel Reinforcement for core wall (5) | Core (5) | Steel Reinforcement |  | 3rd | 43627 | 43628 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6906 | Repair work for Concrete walls due to Electrical work damage | Repair |  |  | 1st | 43628 | 43634 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6907 | Form work for core wall (5) | Core (5) | Form Work |  | 2nd | 43632 | 43634 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6908 | Shaping and implanted Steel Work For Shaft 9 As Per Attached. | Shaft 9 | Steel Shaft |  | 1st | 43632 | 43634 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6909 | Form work for core wall (5) | Core (5) | Form Work |  | 3rd | 43635 | 43638 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6910 | Steel Reinforcement for Shaft (9) | Shaft 9 | Steel Reinforcement |  | 1st | 43640 | 43641 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6911 | Inspection Reinforced concrete slab repair to close NCR#358 | Repair |  |  | 3rd | 43641 | 43642 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6912 | Form work for Shaft (9) | Shaft 9 | Form Work |  | 1st | 43648 | 43649 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6913 | Shaping and implanted Steel Work For Shaft 9 As Per Attached. | Shaft 9 | Steel Shaft |  | 3rd | 43652 | 43654 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6914 | Repair work for Concrete walls due to Electrical work damage | Repair |  |  | 2nd | 43653 | 43654 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6915 | Steel Reinforcement for Shaft (9) | Shaft 9 | Steel Reinforcement |  | 3rd | 43656 | 43659 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6916 | Form work for shaft 9 | Core (5) | Form Work |  | 3rd | 43660 | 43661 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6917 | Installation of sub frame for Top Fan Type (1) (EF-08-09-10-11-12) | sub frame | Installation |  | Roof | 43670 | 43673 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6918 | Installation of sub frame for Top Fan Type (2) (EF-07) | sub frame | Installation |  | Roof | 43670 | 43673 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6919 | Installation of sub frame for Top Fan Type (3) (EF-1-02-03-04-05-06) | sub frame | Installation |  | Roof | 43670 | 43673 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6920 | Installation of sub frame for Top Fan Type (4) (EF-07) | sub frame | Installation |  | Roof | 43670 | 43673 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6921 | Shaping,Formwork and Pouring For Concrete Pavement curbstone for Ramp (B14-B18)/(A13-A12) | Concrete Pavement | Form Work |  | BOH | 43726 | 43727 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6922 | Form Work for Slab Opening | Core (5) | Form Work |  | B1 Floor | 43746 | 43752 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6923 | Shaping and Implanted Steel Reinforcement | RMU Slab | Steel Reinforcement |  | Ground | 43746 | 43752 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6924 | Steel Reinforcement work for new proposed roof slab for atrium | Atrium | Steel Reinforcement |  | 1st | 43753 | 43764 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6925 | Form work and steel Reinforcement for Guest Room Terrace Lintel | Guest Room Terrace Lintel | Form work & Reinforcement |  | Ground | 43755 | 43764 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6926 | Steel Reinforcement for Shaft Slab Opening core 5 | Shaft Slab Opening | Steel Reinforcement |  | B1 Floor | 43757 | 43764 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6927 | Form work for Shaft Slab Opening core 3 | Shaft Slab Opening | Form Work |  | B1 Floor | 43757 | 43764 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6928 | Installation of Sub Frame For Roof Top Fan Type (3) | sub frame |  | EF-1-4-5-6 | Roof | 43765 | 43769 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6929 | Installation of Sub Frame For Roof Top Fan Type (4) | sub frame |  | EF-2 | Roof | 43765 | 43769 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6930 | Steel Reinforcement for RMU Slab | RMU Slab | Steel Reinforcement |  | Ground | 43782 | 43790 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6931 | Bottom and top layer Steel reinforcement Work For Core slab (3) | Shaft 14 | Steel Reinforcement |  | B1 Floor | 43788 | 43790 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6932 | Gypsum Dots For observing the Cracks at App 7 According to our specialist report (SUB 1098-CN-AS-TRN-1895) | Craks | Gypsum Dots |  | 13th To 22nd | 43789 | 43793 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6933 | Form work For RMU Slab | RMU Slab | Form Work |  | BoH | 43823 | 43825 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6934 | Steel Reinforcement For Placing Tower Crane Openning | Placing Tower Crane | Steel Reinforcement |  | 18th To 20th Floor | 43831 | 43838 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6935 | Steel Renforcement Work for closine Tower Crane Opening | Steel | Steel Reinforcement |  | 21th To 22th Floor | 43834 | 43838 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6936 | Inspection For loading cantilever slab Close to close NCR#431 | NCR | NCR | Core 5 | 7th | 43849 | 43852 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6937 | Shaping And implanted Steel Work For Column EX.RMU Room AS Per Attached | RMU |  | RMU Room | Ground | 43899 | 43912 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6938 | Steel Reinforcement For external battery Column's as per attached | 2 Columins DCC 9 | Steel Reinforcement | 10.1 | Ground | 43913 | 43919 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6939 | Inspection Request For Surface Preparation , Shaping and drilling For lmplanting Steel rebars For Stair 4 | Surface Preparation | Inspection Request | Stair 4 | 17th TO 18th Floor | 43916 | 43919 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6940 | Inspection For Form Work For Stair Case. AS Per Attached | Stair Case |  | Staircase 4 | 17th TO 18th Floor | 43918 | 43919 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6941 | Form Work For Slab | External Battery |  | 10.1 | Ground | 43920 | 43923 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6942 | Inspection Request For Surface Preparation , Shaping and drilling For lmplanting Steel rebars For Shafts | Surface | Shafts | Shafts | 3rd | 43921 | 43923 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6943 | Bottom top layer And Beam Steel reinforcement Work For Core slab | External Battery | Slab | 10.1 | Ground | 43922 | 43925 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6944 | Inspection For Steel For Closing Shaft To Start Pouring as Per Attached . | Closing Shaft | Slab |  | 3rd | 43932 | 43934 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6945 | Form Work For Shaft To Start Casting Shaft As Per Attached | Shafts | Shafts |  | 3rd | 43933 | 43936 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6946 | Inspection For Steel Reinforcement Work To Closing Shaft as Per Attached . | Shaft | Shaft |  | 3rd | 43934 | 43936 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6947 | Inspection For Form Work To Closing shaft . AS Per Attached | Shaft | Shaft (13&6) |  | 3rd | 43934 | 43936 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6948 | Form Work For Stair 4 . AS Per Attached | Stair 4 | Stair 4 |  | 18th To 19th Floor | 43934 | 43936 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6949 | Steel Reinforcement For Stair 4 . AS Per Attached | Stair 4 | Stair 4 |  | 18th To 19th Floor | 43934 | 43936 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6950 | Steel Reinforcement For Stair 4 . AS Per Attached | Stair 4 | Stair 4 |  | 19th To 20th Floor | 43944 | 43949 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6951 | Form Work For Stair 4 . AS Per Attached | Stair 4 | Stair 4 |  | 19th To 20th Floor | 43944 | 43949 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6952 | Steel Reinforcement For Shaft(R12 & R8 &R7) . AS Per Attached | Shaft(R12 & R8 &R7) | Shaft |  | 3rd | 43954 | 43956 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6953 | Form Work For Shaft(R12 & R8 &R7) . AS Per Attached | Shaft(R12 & R8 &R7) | Shaft |  | 3rd | 43954 | 43956 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6954 | Steel Reinforcement For Stair 4 . AS Per Attached | Stair 4 | Stair 4 |  | 20th To 21st Floor | 43955 | 43958 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6955 | Form Work For Stair 4 . AS Per Attached | Stair 4 | Stair 4 |  | 20th To 21st Floor | 43955 | 43958 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6956 | Form Work For Slabat BOH . AS Per Attached | Slab |  |  | BOH | 43955 | 43958 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6957 | Steel Reinforcement For Stair 4 . AS Per Attached | Stair 4 | Stair 4 |  | 21st&22nd Floor | 43962 | 43965 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6958 | Form Work For Stair 4 . AS Per Attached | Stair 4 | Stair 4 |  | 21st&22nd Floor | 43962 | 43965 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6959 | Steel Reinforcement For Stair 4 . AS Per Attached | Stair 4 | Stair 4 |  | 22nd&23rd Floor | 43967 | 43986 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6960 | Form Work For Stair 4 . AS Per Attached | Stair 4 | Stair 4 |  | 22nd&23rd Floor | 43967 | 43986 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6961 | Steel Reinforcement For Laundry AS Per Attached | Laundry | Laundry |  | BOH | 43969 | 43986 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6962 | Form Work For Slab Above Stair 4 . AS Per Attached | Stair 4 | Stair 4 |  | Roof | 43989 | 43991 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6963 | Steel Reinforcement For Slab Above Stair 4 . AS Per Attached | Stair 4 | Stair 4 |  | Roof | 43989 | 43991 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6964 | Inspection Request For Surface Preparation , Shaping and lmplanting Steel rebars For Front Fence Columns As Per Attached | Surface Preparation | Inspection Request | Front Fence Columns | Ground | 43991 | 43993 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6965 | Steel Reinforcement For Columns And Beams AS Per Attached | Columns And Beams |  | Public Area | Ground | 43996 | 43999 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6966 | Inspection Request To close NCR # 296 |  |  | Public Area | 1st & 2nd & 3rd | 43998 | 44000 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6967 | Inspection For Check Alignment , Welding , Dimension Of Six Number Of Structural Glasses Supporting Column Of Atrium |  |  |  |  | 44004 | 44005 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6968 | Inspection For Check Alignment, Welding , Dimension Of Seven Number Of Structural, Glasses Supporting Column Of Atrium | Supporting Column |  |  |  | 44007 | 44011 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6969 | Form Work For Upper Roof Slab R14 . AS Per Attached | R 14 | R 14 |  | Upper Roof | 44009 | 44011 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6970 | Steel Reinforcement For Upper Roof Slab R14 . AS Per Attached | R 14 | R 14 |  | Upper Roof | 44009 | 44011 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6971 | Inspection For Check Alignment , Welding , Dimension Of Nine Number Of Structural Glasses Supporting Column Of Atrium | Atrium | Steel Reinforcement |  |  | 44020 | 44024 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6972 | Inspection Request For Surface Preparation, Shaping and Implanting Steel Rebars For Anchor Bolts For Steel Column in Atrium As Per Attached | Atrium |  |  | Ground | 44033 | 44037 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6973 | Inspection For Check Alignment , Welding , Dimension Of Three Number Of Structural Glasses Supporting Column Of Atrium | Atrium |  |  |  | 44034 | 44037 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6974 | Surface Preparation Fpor Carbon Fiber AS Per Attached | Zone 2 & 3 (Main Kitchen) | Zone 2 & 3 (Main Kitchen) |  | BOH | 44039 | 44046 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6975 | Steel Reinforcement For Shaft 3 . AS Per Attached |  | R 3 |  | 3rd | 44039 | 44046 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6976 | Formwork For Shaft 3 . AS Per Attached |  | R 3 |  | 3rd | 44039 | 44046 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6977 | Formwork For Sidewalk . AS Per Attached | Sidewalk | BOH |  | BOH | 44040 | 44046 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6978 | Steel Reinforcement For Shaft R 3 & R1 . AS Per Attached | Shaft R 3 & R1 |  |  | 3rd | 44053 | 44055 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6979 | Formwork For Shaft R 3 & R1 . AS Per Attached | Shaft R 3 & R1 |  |  | 3rd | 44053 | 44055 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6980 | PRE-Function Metal Screen Steel Fixation Frame . AS Per Attached | PRE-Function |  | PRE-Function Ball Room | 1st | 44060 | 44062 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6981 | Inspection For Chiseling Of Concrete Top Surface Around Swimming Pool Drainage System Pipes As Per Attached Location |  |  |  | BOH | 44061 | 44062 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6982 | Installation of Carbon Fiber As Per Attached | Zone 2 |  |  | BOH | 44062 | 44068 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6983 | Inspection request for the executed protection layer for the installed carbon fiber strips | Zone 2 |  |  | BOH | 44072 | 44074 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6984 | Installation of Carbon Fiber As Per Attached | Zone 3 |  |  | BOH | 44072 | 44074 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6985 | Test Preparation For Carbon Fiber At Zone 2 & 3 As Per Attached | Zone 2 & 3 |  |  | BOH | 44073 | 44076 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6986 | Surface Preparation For Carbon Fiber At Zone 2 As Per Attached | Zone 3 |  |  | BOH | 44076 | 44082 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6987 | Formwrk For Shaft R 2 & R2' . AS Per Attached | Shaft R 2 & R2' | R 2 & R2' |  | 3rd | 44081 | 44083 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6988 | Steel Reinforcement For Shaft R 2 & R2' . AS Per Attached | Shaft R 2 & R2' | R 2 & R2' |  | 3rd | 44081 | 44083 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6989 | Installation of Carbon Fiber At Zone 3 As Per Attached | Zone 3 |  |  | BOH | 44096 | 44097 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6990 | Installation the Bulk Head of atrium as per attached | Atrium |  |  |  | 44089 | 44100 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6991 | Formwrk For Shisha Pantry . AS Per Attached | Shisha Pantry |  |  | Ground | 44103 | 44104 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6992 | Steel Reinforcement For Shisha Pantry . AS Per Attached | Shisha Pantry |  |  | Ground | 44103 | 44104 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6993 | Formwrk For Stair 10 . AS Per Attached | Stair 10 |  |  | 16th To 19th Foor | 44108 | 44109 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6994 | Steel Reinforcement For Stair 10 . AS Per Attached | Stair 10 |  |  | 16th To 19th Foor | 44108 | 44109 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6995 | Formwork For Stair 10 . AS Per Attached | Stair 10 |  |  | 19th Floor | 44126 | 44129 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6996 | Surfacepreparation Implanting Steel Rebar For Shaft 0.0 Slab . AS Per Attached | Shaft 0.0 |  |  | Ground | 44131 | 44137 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6997 | Formwork For Shaft 0.0 Slab . AS Per Attached | Shaft 0.0 |  |  | Ground | 44131 | 44137 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6998 | Steel Reinforcement For Stair 10 . AS Per Attached | Stair 10 |  |  | 19th To 21st Foor | 44137 | 44140 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-6999 | Formwrk For Stair 10 . AS Per Attached | Stair 10 |  |  | 20th To 21st Foor | 44137 | 44138 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7000 | Formwork For jaccuzi . AS Per Attached | jaccuzi |  |  | 2nd | 44143 | 44145 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7001 | Steel Reinforcement For jaccuzi . AS Per Attached | jaccuzi |  |  | 2nd | 44145 | 44147 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7002 | Formwork For jaccuzi . AS Per Attached | jaccuzi |  |  | 3rd | 44147 | 44147 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7003 | Steel Reinforcement For jaccuzi . AS Per Attached | jaccuzi |  |  | 3rd | 44151 | 44154 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7004 | Formwrk For Stair 10 . AS Per Attached | Stair 10 |  |  | 21st&23rd Floor | 44156 | 44159 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7005 | Steel Reinforcement For Stair 10 . AS Per Attached | Stair 10 |  |  | 21st&23rd Floor | 44161 | 44165 | C
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7006 | Steel Reinforcement For Stair 10 . (TOP) AS Per Attached | Stair 10 . (TOP) |  |  | 21st&23rd Floor | 44174 | 44178 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7007 | Formwrk For Retaining Wall Of Gass . AS Per Attached | Retaining Wall |  |  | Ground | 44187 | 44189 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7008 | Steel Reinforcement For Retaining Wall Of Gass . AS Per Attached | Retaining Wall |  |  | Ground | 44187 | 44189 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7009 | RE-Installation Of Space Truss . AS Per Attached | Space Truss |  |  | Atrium | 44187 | 44192 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7010 | Steel Reinforcement For Front Fence AS Per Attached | Front Fence |  |  | Ground | 44192 | 44195 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7011 | Formwork For Front Fence AS Per Attached | Front Fence |  |  | Ground | 44192 | 44195 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7012 | Steel Reinforcement For Cab Slab At Stair 10 . AS Per Attached | Stair 10 .Core 2 |  |  | upper Roof | 44194 | 44199 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7013 | Formwork For Cab Slab At Stair 10 . AS Per Attached | Stair 10 .Core 2 |  |  | upper Roof | 44194 | 44199 | A
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7014 | Formwork For Shisha Pantry . AS Per Attached | Shisha Pantry |  |  | Ground | 44214 | 44220 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7015 | Steel Reinforcement For Shisha Pantry . AS Per Attached | Shisha Pantry |  |  | Ground | 44214 | 44221 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7016 | Mockup Installation Of Steel Structure Suppart For Absorption Chiller Chimney (Plat no 1-2) | Shaft R-18 |  | ECS | BOH | 44222 | 44226 | B
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7017 | Steel Reinforcement For Green Walls Cloumns . AS Per Attached | Green Walls Cloumns | Green Walls 5 |  | Ground | 44223 |  | W
SECON Nile Towers | 1098-CN-AS-CIR-S-CO-7018 | Formwork For Green Walls Cloumns . AS Per Attached | Green Walls Cloumns | Green Walls 5 |  | Ground | 44223 |  | W